UK Development Engagement Programme Business Case – 16th May 2024
Summary Sheet

Please Note: This Business Case was developed and approved under a previous government.

Portfolio/ Business/Country Plan Summary: Delivering White Paper We Will 9.20 (new business area)

Title: UK Development Engagement Programme
Programme summary. / The programme will provide up to £3 million over 3-years to raise UK public awareness and support for international development. Pillar 1 will collaborate with key stakeholders on targeted communications. Pillar 2 will fund small scale research, the piloting of development awareness activity, and M&E to assess the effectiveness of such activities. Programme beneficiaries will be people living in developing countries who will benefit from a stronger whole-of-UK contribution to development and the goals of the 2023 International Development White Paper, particularly those living in extreme poverty and/or impacted by climate change, biodiversity loss, fragility, and conflict. The UK public are also expected to benefit should stronger and sustainable UK public support for developing countries help create a more stable and prosperous world.
What is the rationale for UK Aid spending? / Increasing development engagement is a strategic priority for the FCDO. As highlighted in the Integrated Review Refresh 2023, the UK’s contribution to international development is essential for the UK’s security and prosperity in a world with escalating crises including accelerating humanitarian need, illegal migration, climate change, fragility, and conflict. But this is not well enough understood within the UK. / The FCDO’s UK Development Engagement Programme aims to support: / The Foreign Secretary’s priority to “Promote International Development and address critical global challenges”, amplifying and connecting international development campaigns, focussing on the UK-facing aspects of strategy, policy, partnerships, and communications. / The Deputy Foreign Secretary’s commitment to reinvigorate UK leadership on international development through a diverse range of partnerships, made in his Chatham House speech (April 2023) / The commitment in the November 2023 White Paper “International development in a contested world: ending extreme poverty and tackling climate change” (Chapter 9) to work directly with the UK development sector and engage directly with the UK public to explain the importance of development work and deliver the Sustainable Development Goals (SDGs). / The programme is 100% ODA eligible, falling under the OECD DAC rule allowing for the funding of activities designed to increase public support for development cooperation.
Programme Value: Up to £3 million over 3 years.		Country/ Region or Sector: Non-specific country.
Department/Country Office confirmation of review processes		Director, Development Engagement
Contact name		Director, Development Engagement / UK Development Strategy and Engagement Adviser, SRO / PRO
Threshold for final approval of Business Case: / Director, Development Engagement
Date of Approval of Concept Note:	14th February 2024	Name and role of Approver: Director for Development Engagement following steers by the Deputy Foreign Secretary.
Date of Approval of Business Case:	16th May 2024	Name and role of Approver: Director for Development Engagement
Programme Code: 400208	AMP Start Date: 30/10/2024	AMP End Date: 15/08/2027
Overall programme risk rating:	Major

## Strategic Case

The Challenge
The UK remains highly valued internationally for its role in international development, while its contribution to development is critical for the UK’s security and prosperity in a world with escalating crises, including from instability and conflict, climate change and illegal migration. However, the UK’s role in international development is not well understood, while there has been a decline in British public support for aid spending over the past decade. Currently, 48% of Britons think that what happens in developing countries affects them too, while 53% of Britons are concerned about poverty in those countries. 52% of Britons think that the UK should keep or increase its current aid budget. This statistic is up from 43% in November 2013, but down from 56% in June 2022 and is lower than polled in the early 2000s. It is also lower than similarly polled in some peer countries, for example, the US and France at 57% and 58% respectively. In its 2023 Annual Survey of UK Public Opinion on Foreign Policy and Global Britain, the British Foreign Policy Group also found that international development spending remains a source of contention. 61% of Britons believe that international aid and development spending takes away money that should be spent on domestic needs, and just 14% of Britons believe that the UK should restore its 0.7% GNI spending commitment now. Polling also sheds light on ‘pro-social’ behaviours with surveys indicating that the percentage of Britons that have donated to a global poverty charity in the past 12 months has decreased from 36% in November 2013 to 20% in January 2024.
[note] Oh, S. 2024. DEL Dashboard – Great Britain January 2024. London: Development Engagement Lab
[note] 2023 Annual Survey of UK Public Opinion on Foreign Policy and Global Britain - British Foreign Policy Group (bfpg.co.uk)
[note] Oh, S. 2024. DEL Dashboard – Great Britain January 2024. London: Development Engagement Lab

The Intervention
The intervention aims to address the challenge of low engagement by the UK public on international development by spending up to £3 million over 3 years to increase public awareness of, and support for development. The context in which the intervention will take place is challenging. Amid difficult domestic conditions, surveys conducted by DEL (Development Engagement Lab) find that public concern for issues related to economic crises, job security and wages remains the top issues people care about in the UK. However, the intervention’s ambition is grounded in the belief that greater public awareness of, and support for international development will translate into stronger action by the public and UK institutions, which will help progress towards achieving the SDGs. Such action will also improve the UK’s prosperity and security if it positively shapes the international environment and helps address risks to the UK, for example, from health, climate change and conflict issues. Starting with positive attitudinal shifts as a precursor, the intervention will seek to positively impact behavioural change over time through a range of routes, for example:

- Through individuals and businesses contributing more to development goals by
  - using their voices more for advocacy,
  - choices such as donating more to charity, adopting ethical criteria in choosing products and services and.
  - actions such as, donating time to volunteering, or starting an initiative.

Through a greater public understanding of, and commitment to international development in support of HMG’s White Paper commitments. This could be an important enabler for the UK’s development efforts, both bilaterally and through enhancing the UK’s impact on the multilateral and global development system.

The intervention will contain two pillars:

Pillar 1 – The UK Development (UK Dev) Engagement Campaign
To build awareness of, and support for international development, FCDO will collaborate on a targeted engagement campaign. The campaign will collaborate with key stakeholders in the UK development sector. Building from previous audience insight, the campaign will target segments of the UK public most likely to increase their support for international development. The campaign will start with a 12-month pilot phase focused on a segment of the public defined through previous research”. It will expose the target audience to content showing the positive impact of international development work. At the conclusion of the pilot phase, FCDO will work with the other campaign collaborators to assess how the remaining programme budget should be spent under an implementation phase that involves a scaled-up campaign deployed over the remaining programme duration.

The collaboration will be structured as follows:
- The primary programme partner will help to anchor an HMG and non-HMG collaboration and, with FCDO, will be jointly responsible for campaign delivery. The programme partner will also buy social media space to place content into the public domain (see below). We will explore the use of different social media platforms to engage different audiences during the pilot phase, including for example Facebook, TikTok and Instagram.
- FCDO will work with the primary programme partner to ensure the provision of content informed by audience insight (avoiding humanitarian content given the public’s existing good levels of exposure to it). Instead, content will be aligned with White Paper themes, will demonstrate the core importance of partnerships, and will be spent within the scope of the International Development Act 2002 and DAC rules on ODA eligibility.
- Philanthropic foundations working in the UK are expected to provide funding, through their own grant mechanisms, to support the primary programme partner’s work within this collaboration. This will include funding to enable the partner to buy social media space.
- The programme will continue to use long-standing nationally representative tri-annual surveys to track British public engagement with global poverty and sustainable development issues.

Pillar 2 – the UK Development (UKDev) Engagement Partnership
This pillar will focus on activities designed to increase UK public support for development. This will involve working with UK-based civil society organisations, representatives of academia, the private sector, youth, and diaspora groups throughout the UK to promote understanding of, and engagement in, international development work. Activities will include supporting various events throughout the year, which aim to build a broad coalition in support of international development. FCDO resources under this pillar will also be spent on research activities to provide an evidence base for most effective engagement approaches – for example, on how best to engage with diaspora communities, or identifying the most effective means to increase public support through educational or other outreach approaches. Resources are also expected to be spent on hosting and contributing to strategically selected development awareness and learning opportunities.

Proposed Impact and Outcomes
The intended impact of the intervention is more supportive attitudes and behaviours towards international development by UK individuals. The intended outcome is disaggregated by pillars:
- For Pillar 1: By 2027, to measurably improve the attitude and behaviours of the target audience(s) exposed to the campaign with respect to the need for and effectiveness of ODA.
- For Pillar 2: More, and more effective approaches to UK development engagement as evidenced i) quantitatively by the number of new FCDO programmes including a focus on development engagement and ii) qualitatively by an expert evaluation to assess the effectiveness of approaches.

For the impact and outcomes to be achieved, the following assumptions must hold:
- Domestic economic and/or political conditions do not significantly deteriorate in such a way as to reduce support for international development cooperation. Should they do so, it would reinforce the ‘charity starts at home’ perception, which could detract focus and support from international development efforts.
- There is sustained cross-party political support for international development.
- Development engagement activities tangibly impact awareness of, and support for international development in a timely manner.

FCDO’s Comparative Advantage
Consultations with key international development sector stakeholders have concluded that there is clear demand from the sector for FCDO to increase its development engagement efforts. FCDO’s (and historically DFID’s) reputation on international development can attract attention and crowd in both effort and financing from others – for example, under pillar 1, the programme involving philanthropic foundations, enabling previous targeted communications campaigns to be scaled up and impact maximised. For pillar 2, FCDO, with its broad view of the international development landscape and funding support for a wide range of development organisations, is well placed to conduct holistic research, deepen its engagement with those who might get more involved, and host events to improve understanding of effective development engagement approaches.

Collaboration with other HMG Departments
With the ambition of influencing development engagement approaches across HMG, the intervention endeavours to work with selected other HMG departments on thematic agendas. This may include the Department of Health (including NHS diaspora health professionals) to highlight UK international development support in overseas health sectors; the Department of Education for building awareness of, and support for development through educational (including school) activities; the Department for Science, Innovation and Technology to showcase the UK’s international support through these agendas; and the Department for Levelling Up, Housing and Communities, for researching and deploying development engagement approaches at the local level.

Beneficiaries
Programme beneficiaries will be people living in developing countries who will benefit from a stronger whole-of-UK contribution to development and the goals of the 2023 International Development White Paper, particularly those living in extreme poverty, and/or impacted by challenges such as climate change, biodiversity loss, fragility, and conflict. Given the inter-connectedness of nations, the UK public are also expected to mutually benefit should stronger public support for developing countries help create a world that is more stable and prosperous. There is also an intrinsic benefit in building citizen education with respect to the opportunities and challenges that lay ahead in the future. Careful attention will be given to how development issues are labelled, explained, and made relevant to UK lives.

The Evidence Base
Pillar 1
The engagement campaign will target segments of the UK public judged most likely to increase their support for international development. Evidence on the types of messengers and messages that work in increasing support from these groups is good due to audience insight derived from previous campaigns. From longitudinal analysis, DEL suggests that development related content that is most influential, and may prove to have the most lasting impact, is content that appeals to peoples’ values and sense of fairness, has an element of surprise, and creates a feeling of personal resonance. DEL also suggests that factors that affect support are efficacy – the feeling that an individual, NGO, government etc – can make a difference – the levels of need, and a focus on the basics such as food security, health and water and sanitation. The pilot phase will test content and approaches, including through using content more aligned with White Paper themes. Content for the full implementation phase will be informed by insights gained from the pilot phase.
[note] Public engagement with aid: What do we know from 10 years of research? | Development Compass

There is a lack of evidence on how attitudinal changes translate into behavioural changes. The 2011 Review of Using Aid Funds in the UK to Promote Awareness of Global Poverty, concluded that the evidence on how increased verbalised support catalyses positive behavioural changes at the individual level is weak. The evaluation also found that raising awareness of development issues in the UK is “likely” to contribute to reducing global poverty. However, it was not possible to establish a direct link or quantify the contribution due to past DFID interventions being un-strategic and/ or not properly evaluated. The same evaluation also found little evidence to support the assertion that public opinion is critical for there to be political commitment to aid, with it appearing instead that political commitment to aid is more a question of leadership. However, it hypothesised that there is a level of public support below which it would be politically impossible to increase or even maintain levels of aid. Given the weaknesses in the evidence base, the campaign recognises the importance of collecting evidence on what works. It will therefore include a robust monitoring, evaluation and learning component, starting with the testing of content in the pilot phase, that will seek to address evidence gaps. However, due to complexities in causalities and correlations associated with targeting attitudinal and behavioural changes through communications campaigns, there is a significant risk that evidence gaps will persist throughout and beyond the programme’s lifetime.
[note] Review of using aid funds in the UK to promote awareness of global poverty (publishing.service.gov.uk)

Pillar 2
There is not much recent evidence on how the UK Government can conduct or support development engagement approaches in a manner that motivates and inspires individuals and institutions to start to or increase their support for international development. However, the 2011 Review did conclude that development education plays an important role in creating an environment that supports efforts to tackle global poverty. It therefore recommended that DFID, the organisation in place at the time, focus its investment within the school system as this is where the next generation, which is key to eradicating global poverty, is being educated. It further noted that school linking – linking UK schools with schools in developing countries – yielded a significant positive impact on pupil awareness of development issues, as well as recording ‘life-changing’ experiences and attitudinal change by both pupils and teachers. The Review also concluded that DFID had a legitimate role to play in continuing to support the work that the UK’s development focused NGOs are already doing – and will continue to do – in raising awareness. Like pillar 1, gathering evidence to inform future engagement approaches will be a core focus under pillar 2 to gain more granularity to improve understanding.

Strategic Fit
Increasing development engagement is a strategic priority for the UK development sector and for the FCDO. Increased engagement underpins the aims of the March 2023 Integrated Review Refresh including shaping the international environment and tackling root causes of risks to the UK such as health, climate change or conflict, through investing in action overseas. These risks are of growing importance to domestic policy and to our national wellbeing.

The intervention also aims to deliver the International Development White Paper commitments on working directly with the UK development sector (sections 9.2 to 9.11) and engaging directly with the UK public to explain the importance of development work (sections 9.19 to 9.22), thereby supporting the effective implementation of HMG’s White Paper goals.
[note] International development in a contested world: ending extreme poverty and tackling climate change, a white paper on international development - GOV.UK (www.gov.uk)

The intervention will also deliver against:
The Foreign Secretary’s priority to “Promote International Development and address critical global challenges”, amplifying and connecting international development campaigns, focussing on the UK-facing aspects of strategy, policy, partnerships, and communications.

The Deputy Foreign Secretary’s commitment, to reinvigorate UK leadership on international development through a diverse range of partnerships, made in his April 2023 Chatham House speech on The Future of International Development.
[note] Future of international development: Minister Andrew Mitchell's speech - GOV.UK (www.gov.uk)

Furthermore, the intervention will support the objectives in the International Development Communication Strategy to demonstrate to the UK public the value of international development, as part of foreign policy, to increase awareness and help increase the number of supporters of aid. FCDO also has a duty to communicate to the public on its use of taxpayers’ money. Outcome level targets for increasing public support for international development will also be anchored into the FCDO Outcomes Framework, as part of the refresh of the Outcome Delivery Plan.

Key Markers and Programme Controls
The intervention meets ODA eligibility requirements under the DAC rule allowing for the funding of activities designed to increase public support.

Public Sector Equality Duty: We will ensure that any delivery partners embed robust policies to prevent discrimination, harassment, or victimisation of any people and/or communities engaged in the intervention, including those that feature in content under pillar 1. However, it will be difficult to ascertain otherwise the extent to which people with protected characteristics will be impacted because the intervention will – under pillar 1, focus on a targeted segment of the population in which specific evidence on protected characteristics is not available and – under pillar 2, focus on awareness raising activities and strengthening the evidence base on development engagement across a broad UK audience.

Gender Equality and Inclusion, Disability, Climate and Environment: Under pillar 1, during the pilot phase, we will explore opportunities to promote gender equality, disability inclusion and climate and environmental when devising content. Under pillar 2, we will also explore how development engagement approaches can amplify messages on these subject areas when commissioning research and hosting events. However, with DEL’s longitudinal study suggesting that content talking about gender equality and the environment reduces support for international development from the average person, our initial assessment is that pillar 1 will be gender and climate/environment neutral. From a gender perspective, we will use opportunities to ensure gender diversity will be considered when commissioning research through external consultants, and when engaging public speakers in development engagement events.

Safeguarding: For both pillars 1 and 2, all programme partners will be made aware of FCDO’s zero tolerance policy on sexual exploitation, abuse and harassment and inaction, and the requirements on reporting. In addition, for pillar 1, careful attention will be given to the content used, specifically that it does not include footage of vulnerable people and groups. Under pillar 2, safeguarding practices will be deployed for any events working with children and/or vulnerable groups.

Counter-Terrorist Financing and Anti-Money Laundering: The programme will comply with the FCDO’s counter-terrorist financing and anti-laundering policy, applying Programme Operating Framework (PrOF) rules and principles to avoid UK taxpayer money being diverted. We will ensure a) a robust due diligence process of any partners receiving FCDO financing that includes assessing the risks of aid diversion, and b) robust programme management, by producing and regularly updating risks and delivery plans, and closely coordinating with partners.

Risk
The programme is assessed to be a major risk intervention. For pillar 1, major risks are associated with FCDO’s constrained delivery capacity. If the programme proceeds beyond the pilot phase into the full implementation phase, there are also major risks of the campaign being insufficiently compelling and/or lacking in scale to move the needle on raising awareness and increasing support for development. For both pillars, a further major risk is to reputational damage from spending ODA in the UK, and if an enhanced development engagement is portrayed as politically motivated given the timing of the political cycle. A detailed risk register is included in the Management Case. All risks will be mitigated, and a risk register will be maintained.

## Appraisal Case

Theory of Change
The Theory of Change for the intervention is summarised in the diagram below.

As per the Strategic Case, the intervention’s intended impact is more supportive attitudes and behaviours towards international development by the UK public and institutions. Previous audience testing concludes that the pathway to achieving this from the outcome level is to i) raise the awareness of the importance of international development with the target audience and ii) increase the number of and have more effective engagement approaches. The outcome level therefore relies on outreach, research, and engagement efforts, as expressed at the output level, through i) engaging, through communicating with the public, particularly the target audience, on the importance of international development and ii) gathering research and evidence to inform effective engagement approaches, and harnessing opportunities to collaborate with a broad range of sector stakeholders on development engagement activities. At the input level, FCDO’s political capital and continued organisational commitment to strengthening UK development engagement is key. In addition, financing for internal and external technical expertise would be important, as would financing to commission research and evaluation products on effective development engagement approaches.

There will be a significant challenge to ensure that inputs and outputs achieve the intended outcomes. Several assumptions, as documented in the diagram, would need to be met. There is also the issue of how to ensure that engagement approaches result in sustainably more supportive attitudes and behaviours. Addressing this question would be a focus for the research activity.

Regarding evidence, as detailed in the Strategic Case, for pillar 1 there is existing audience insight to build on. However, the evidence for pillar 2 is more mixed, and in some places weak, hence the focus for this pillar is to develop a strong monitoring and evaluation framework to inform on the best development engagement approaches.

Theory of Change for raising UK public awareness of, and support for, international development

ASSUMPTIONS

Domestic economic and social conditions do not significantly deteriorate to detract attention from international development.

There is sustained political support for development engagement activities.

Social media is the best platform to target the audience.

Content is appropriate for shifting the opinion of the target audience.

The development engagement activity, which is short term and low scale under the programme, can tangibly and sustainably make a difference.

Research activity is well targeted and designed to credibly inform development engagement approaches.

A wider group of UK based stakeholders on development can mobilise their constituencies’ support effectively

Monitoring data continues to be available.
IMPACT
More supportive attitudes and behaviours towards international development by the UK public and UK institutions

Pillar 2: Increased number of, and more effective development engagement approaches.
Pillar 1: Improvement in attitudes and behaviours towards international development among the target audience(s).
OUTCOMES

OUTPUTS

Pillar 2: Evidence generated, synthesised, and used to improve understanding of effective development engagement approaches. Harnessing development engagement opportunities.
Pillar 1: Public engagement with content

FCDO political capital and organisational commitment, including Ministerial, to development engagement.
Programme funding for research products, hosting and participating in events, external contractors for technical expertise.
FCDO staff time and technical skills including the G7 project funded communications expert.
INPUTS

CHALLENGE: The UK’s role in international development is not well understood by the UK public, while there has been a decline in public support for aid spending over the past decade. Currently, 48% of Britons think that what happens in developing countries affects them; 53% of Britons are concerned about poverty in those countries; 52% of Britons think that the UK should keep or increase its aid budget. The proportion of people that have donated to a global poverty charity in the past months stands at just 20%.
The appraisal case below outlines levels of ambition to deliver the intended impact and outcomes based on a total budget envelope of up to £3 million over 3 years – FYs 24/25, 25/26 and 26/27.

Option 1 (Counter-factual). No new standalone UK development engagement programme: Work to achieve the intended impact and outcomes through existing and new centrally managed civil society programmes, for example UK Aid Match II and the currently-under-design International Volunteering Scheme – and through existing theme-by-theme engagement with UK civil society and the Deputy Foreign Secretary’s existing regular meetings with BOND.

Option 2: Increase FCDO’s UK development engagement through a targeted communications campaign aiming to raise awareness of development and influence the target audience(s) to increase their support for it. A campaign would be comprised of a 12-month pilot phase to test content and approaches. Should the pilot phase prove successful in engaging, raising awareness and support from the targeted audience, the campaign would be scaled up for the remainder of the programme period. Should the pilot prove unsuccessful, the campaign would be terminated, or the approach would be re-set.

Delivery option: A possible collaboration between HMG and development organisations working in the UK. The non-HMG partners would be experienced in targeted communication campaigns. Based on their expertise and experience in delivering similar initiatives, and to deliver the new programme at pace, this option is considered as the only viable delivery option.

Option 3: Increase FCDO’s UK development engagement through working with a broad range of UK partners and commissioning research to inform what works best in terms of engagement approaches. This would include working with UK based CSOs, academia, the private sector, youth, and diaspora groups to promote understanding of, engagement in, and support for international development. It would involve supporting various events throughout the year, which aim to build a broad coalition in support of international development, with resources expected to be spent on hosting. FCDO resources under this pillar would also be spent on research activities to build an evidence base on how best to conduct development engagement activities.

Delivery option: Programme objectives can only be delivered in-house, led by FCDO’s UK Development Engagement team, in collaboration with other FCDO and Whitehall Departments

Option 4: Combined approach of options 2 and 3.

Cost-Benefit Analysis

Below details the costs and benefits of each option. At this stage, it is not possible to predict costs split over the FYs. Given the nature of the benefits, it is not possible to quantify and therefore monetise them. A qualitative appraisal of benefits has therefore been conducted. Across the options, the benefits are similar in nature. The options instead represent different levels of ambition and therefore differing potentials to impact public awareness and support for international development.

Option 1: Counterfactual – No new standalone programme. Deliver UK development engagement through existing and planned new civil society programmes.
Cost: £0.

Benefits: Limited as FCDO would still lack a strategic approach or understanding on this agenda.

Option 2: Targeted communications campaign.
Cost: Up to £2,428,824 (rounded up to £2.43m) split as follows between the pilot and main implementation phases:

Pilot phase: Up to £511,032 overall cost o/w FCDO’s estimated cost is up to £255,516 (includes 0.7 FTE of the G7 specialist) for the pilot phase. FCDO costs would include a G7 project funded communications expert to assist with campaign planning and delivery and a budget to transfer to country posts to create new local content. They will also include a budget to ensure a robust evaluation of the impact of the content on the target audience is done and made available in full to all the partners. While not costed under the programme, broader UK Development Engagement Team staff time will also be used to deliver the pilot phase. Philanthropic foundations working in the UK would contribute funds for social media space as well as support the creation of insight-informed content at an estimated cost of £255,516.

Assuming the pilot phase is scaled up into a full campaign: Up to £4,364,560 overall cost o/w FCDO’s estimated cost is £2,173,308 for the implementation phase. Regardless of whether the pilot phase is successful or not, FCDO would continue to project fund the G7 communications expert as the staff member is being project funded to also support pillar 2 activities. If critical capacity constraints are highlighted during the pilot phase, FCDO would also explore the possibility of contracting an external strategic communications agency – cost included in estimates to support a larger scale campaign over FYs 25/26 and 26/27. A budget would also be available to transfer funding to country posts to support new content creation. The programme partner will seek funding, including to buy media space, to match the level invested by the FCDO.

Benefits
Through more supportive attitudes and behaviours towards international development, resulting in increased acts to reduce poverty:

VOICES By UK individuals starting to exercise or exercising more voice through actively joining in debate or campaigns on an international development social, economic, or environmental issue: Opens political and other civic spaces for the change necessary to tackle poverty.

CHOICES By UK consumers starting to adopt or increasingly adopting ethical criteria in choosing products and services: Increase in the ethical market in the UK through greater sales of Fairtrade products and services, resulting in a transfer of wealth back to farmers and workers in developing countries through decent incomes and decent work opportunities. By UK individuals starting to donate to or increasing levels of charitable giving: More funding to organisations addressing international development and/or disaster relief.

ACTIONS By UK individuals starting or increasing volunteering time: More un-paid time given to organisations addressing overseas aid and/or disaster relief. Or by individuals starting their own campaigns or initiatives on international development themes.

Through increased individual support for HMG’s international development ambitions:

By UK individuals providing new or increased apolitical support for international development: More effective implementation of the International Development White Paper, and thus the benefits doing so aims to deliver, both for people in developing countries and the UK public.

Delivery mechanism: Possible programme partners have previously collaborated on a similar targeted engagement campaign, and therefore have several years of collective experience, in addition to their individual experiences on UK development engagement, including communications, activities. This new initiative leverages this previous experience, and in doing so, offers the most efficient and cost-effective delivery approach for FCDO as it will build on previous audience insight.

Option 3:
Cost: Up to £570,000 (rounded up) – fully attributed to FCDO as expenses from other partners are unpredictable at this stage.
Benefits: Same as for option 2 but at a higher unquantifiable level given the option’s engagement with a wide range of stakeholders to reach a broader audience for raising awareness to, and support from. This option also has the additional benefit of helping to build a global public good through the research and evidence collection on approaches to improve domestic awareness of, and support for international development.

Option 4
Cost: Up to £3 million – combined cost of options 2 and 3.
Benefits: Same as for options 2 and 3 but at a higher unquantifiable level given the multi-pronged approach

Preferred Option: Option 4. Due to organisational re-prioritisation, FCDO’s UK development engagement efforts have decreased substantially over the past five years. In parallel, moving the needle on UK public awareness of, and support for international development will be challenging, particularly amid continued difficult economic and social domestic conditions. Option 4 is therefore preferred as it includes option 2, which is a short-term and targeted intervention, and option 3, which is a longer-term, broad-based, and strategic intervention. For a relatively low cost, the combination of both options – as option 4 – has the highest ambition, innovation, and flexibility, and therefore the greatest potential to tangibly impact attitudes and behaviours.

VfM
Using a combination of quantitative and qualitative indicators that reflect the Theory of Change, costs and benefits, the Management Case provides an indicative VfM framework for pillar 1, which will be firmed up in consultation with partners, and a confirmed framework for pillar 2.

## Commercial Case

Pillar 1
The appraisal case has identified a potential programme partner to be the main partner anchoring the multi-partner collaboration under Pillar 1. This follows an unsolicited proposal to FCDO, in which the organisation detailed its previous experience on similar engagement initiatives, in collaboration with key UK stakeholders As such, the potential programme partner has been assessed as uniquely positioned to anchor the collaboration and is the best option for FCDO from a value-for-money perspective. The commercial approach for pillar 1 is as follows:

For the 12-month pilot phase:
FCDO will not transfer any financing to the potential programme partner. The collaboration will therefore be formalised through an MoU between the two organisations. The MoU will detail the purpose of the programme, and the FCDO’s and the partner’s responsibilities including on reporting and risk management arrangements amongst other standard clauses such as safeguarding. Amongst other things, the potential programme partner will be responsible for
  - Helping to lay the foundation of the programme by providing research material including on existing audience insight, tracking data, new experimental analysis, and message testing.
  - Leading the multi-partner collaboration during the pilot phase to test content aimed at the target audience. The potential programme partner will have a similar lead effort if the pilot phase is evolved into a full implementation phase.
  - Providing quarterly assessment reports on performance against results and VfM indicators, and on risk management and mitigation. Providing assessments to help inform the programme’s Annual Review and eventually the Programme Completion Review.
  - Advising on learning and future approaches to increase impact.

If the potential programme partner sub-contracts to other implementing organisations, the partner will reflect the provisions of the MoU with that organisation. The MoU will also include a break clause to enable the collaboration to be terminated with the agreement of all funding partners should the campaign during the pilot phase prove unsuccessful.

FCDO will mostly rely on internal, and if necessary, other Whitehall expertise to deliver the programme during the pilot phase. Internally, our funding will be spent on a project funded G7 communications specialist in compliance with FCDO requirements as defined in ProF guidance for such roles. This specialist will either be recruited from within FCDO or elsewhere in HMG. There are various reasons why home-based civil servants, rather than external experts, will make the best delivery route. HMG representatives will be better placed to build trusted relationships within FCDO and with the other Whitehall Departments detailed in the Strategic Case. In-house delivery will also help build FCDO confidence and capability for UK facing development engagement activities, while avoiding the inevitable mark-up that occurs with external contractors. In addition to the above, a budget will be made available to ensure a robust evaluation of the impact of the content on the target audience is done and made available in full to all the partners, and some funding may be internally transferred to country posts to finance content creation, following FCDO low value procurement best practice. Any external support will be procured with the support of a Departmental Procurement Officer.

For the implementation phase, should the pilot phase prove successful:
Should the campaign under the pilot phase be scaled up into a full campaign for the remainder of the programme period, FCDO will re-assess options at that stage to ensure the relevant expertise for programme success. The G7 project funded communications expert will remain in place for the whole 3 years to support delivery of both programme pillars, and the delivery route will continue to rely as much as possible on internal expertise. The programme will also continue to fund any necessary content creation in country posts. However, if internal capacity constraints become apparent during the pilot phase, the following options will be explored:

- Securing capacity support through Cabinet Office’s Global Communication Services International team. This would involve an intra-HMG internal transfer of resources.
- Securing external strategic communications and/or monitoring, evaluation and learning expertise. There are a considerable number of strategic communications agencies in the market that can provide campaign strategy planning and campaign M&E services. If appropriate, procurement would be through a FCDO Framework Agreement, which would allow the FCDO programme team to procure expert advice through a select number of pre-approved suppliers. Using frameworks reduces procurement timescales while still offering a competitive process to ensure we continue to drive VfM. If an external supplier is contracted, the arrangements to manage the supplier will be compliant with FCDO requirements. Ahead of procuring an agency, the Development Engagement Team will work with Communications Directorate to secure Professional Communications Assurance from the Cabinet Office.

Other non-funded programme partners under pillar 1
Philanthropic foundations working in the UK and audience insight specialists are also main programme collaborators with the following agreed division-of-labour:

Funds contributed by philanthropic foundations are expected to be used by the potential primary programme partner to buy social media space to place content into the public domain, as well as to support the creation of insight-informed content. We will explore the use of different social media platforms to engage different audiences during the pilot phase, including for example Facebook, TikTok and Instagram. Part of the package when buying social media space will include digital results metrics gathered by the social media channel, and these statistics will play an input in assessing programme performance – see the Management Case.

The audience insight specialist will use its long-standing nationally representative tri-annual surveys to track British public engagement with global poverty and sustainable development issues.

As detailed in the Management Case, an over-arching results and governance framework will be agreed between FCDO and all programme partners to formally connect the collaborators. Partners will also form a programme Advisory Committee that will meet quarterly – see Management Case.

Pillar 2
Under this pillar, FCDO will collaborate with a wide range of partners drawn from UK-based civil society organisations, representatives of academia, the private sector, youth, and diaspora groups to promote understanding of, and engagement in, international development work. The G7 project funded post, referred to above, will also support the implementation of this pillar. Expenditure for any research under this pillar is likely to be low value contracts (below the Delegated Threshold currently at £138,760 including VAT) or contributions to existing call-down contracts managed by other parts of FCDO that may be fit for purpose. For low value contracts, the programme management team will seek support from the Departmental Procurement Officer to engage in mini-competitive processes. This will be the preferred approach as the better route to drive VfM. However, if a research product is particularly low value and/or time sensitive, a single source procurement will be used if it justifies and meets the relevant criteria. Contract management arrangements will be devised once a supplier is selected but will comply with FCDO requirements.

Any expenditure associated with supporting development engagement events, for example, hosting roundtables, will comply with requirements for managing external meeting costs, travel etc.

Both pillars 1 and 2
For additional monitoring, evaluation, and learning activities, we will seek a M&E advisor using the 10% provision. However, if this search isn’t successful in securing the right expertise, we will contract externally for an M&E specialist. If appropriate, this specialist would be procured through a FCDO Framework Agreement and would be a low-value procurement – below the delegated threshold, currently at £138,760 including VAT. All procurement will be complaint with the Public Contracts Regulations 2015.

## Financial Case

Expected costs and key drivers of the programme.

The programme budget, as approved in the Concept Note, is up to £3 million over three years. Programme spend is ODA eligible as it falls under the DAC rule allowing for the funding of activities designed to increase public support for development cooperation – for example, activities that improve awareness in the donor country of development efforts, needs and issues. Supplementary powers in section 4 of the International Development Act 2002 also allows for the promotion of ‘awareness of global poverty and of the means of reducing such poverty’.

Funding for the programme will come from DG Humanitarian & Development’s programme ODA RDEL budget allocation. An indicative cost split over the three FYs is detailed in the table below, with rounding up to £3,000,000 for both pillars over the three-year period. These are estimates based on experience of similar activities. However, it must be noted that they are estimated with a high degree of uncertainty as i) under pillar 1, it is unclear whether the pilot phase will proceed to full implementation phase, and if it does, it is unclear whether external expertise will need to be funded and ii) under pillar 2, the opportunities to commission specific pieces of research and to host and participate in development engagement events are yet to be defined. Estimates will be refined during the pilot phase.

	FY 24/25 – Pilot Phase (Pillar 1 only)	FY 25/26	FY 27/28	Total
Pillar 1	Internal transfers to country costs for local content creation: Up to £100,000	Internal transfers to country costs for local content creation: Up to £200,000	Internal transfers to country costs for local content creation: Up to £200,000	Up to £500,000
	Externally contracted evaluation expertise: Up to £100,000	Externally contracted strategic communications expertise: Up to £800,000	Externally contracted strategic communications expertise: Up to £800,000	Up to £1.7 million
		Externally contracted M&E expertise: Up to £50,000	Externally contracted M&E expertise: Up to £50,000	Up to £100,000
	0.7 FTE G7 project funded staff: £55,516	0.5 FTE G7 project funded staff: £36,654	0.5 FTE G7 project funded staff: £36,654	£128,824

Pillar 2	Externally commissioned research into effective development engagement approaches: Up to £70,000	Externally commissioned research into effective development engagement approaches: Up to £70,000	Externally commissioned research into effective development engagement approaches: Up to £70,000	Up to £210,000
	FCDO hosting and participating in development engagement events/activity: Up to £60,000	FCDO hosting and participating in development engagement events/activity: Up to £100,000	FCDO hosting and participating in development engagement events/activity: Up to £100,000	Up to £260,000
	0.3 FTE G7 project funded staff: £23,793	0.5 FTE G7 project funded staff: £36,654	0.5 FTE G7 project funded staff: £36,654	£103,101

Total / For pillar 1: / For pillar 2:	FY 24/25 / Up to £255,516 / Up to £153,793	FY 25/26 / Up to £1,086,654 / Up to £206,654	FY 26/27 / Up to £1,086,654 / Up to £206,654	Totals / Rounded up to £2,430,000 / Rounded up to £570,000
[note] Average cost of a UK based FTE Grade 7 is £79,308. All calculations above for this position assumes this.

Key cost drivers
The key cost drivers for both pillars will be technical expert and consultancy costs – for example, for the in-house G7 communications expert, the cost of contracting a strategic communications agency, and the cost of research and evaluation products. To ensure VfM, FCDO commercial benchmarking information will be reviewed ahead of contracting, in line with FCDO procurement best practices. In due course, we will also work with commercial colleagues to agree the payment mechanism, which we anticipate being a payment-by-results strategy supported by key performance indicators to incentivise performance.

Due Diligence Assessment
We will ensure that any direct recipients of FCDO funding have a completed due diligence assessment in accordance with FCDO requirements.

Monitoring, Reporting and Accounting for Funds
Overall reporting and governance arrangements are set out in the Management Case. The SRO will ensure that all financial reporting meets FCDO standards and are submitted on time prior to disbursing payments. All payments will be approved by the SRO. For pillar 1, the SRO and PRO, in collaboration with the potential programme partner, will also oversee the budgets and forecasting. For pillar 2, the SRO and PRO will oversee budgets and forecasting.

Other accounting considerations
There will be no forms of funding under this programme which would involve the return of capital to FCDO, or which would create liabilities for the UK Government.

## Management Case

Within FCDO, the programme will be managed by the UK Development Engagement Team. The SRO and PRO for the programme will be G6 and HEO positions respectively from within this team, while a programme funded G7 communications expert, based within the Communications Directorate, will also drive delivery. In addition, other roles within the Development Engagement team, including the SCS2 Director, will support the delivery of both pillars. The team will also collaborate strongly with other directorates, particularly Communications Directorate and the Development and Open Societies Directorate to deliver efficiently and maximise impact against programme objectives. As outlined in the Strategic Case, we will also engage other Whitehall departments to support delivery.

Governance And Decision-Making Arrangements

Pillar 1
Using FCDO’s best practice template and advice from Commercial Directorate, FCDO will sign an MoU with the potential programme partner as the anchor of the multi-partner collaboration, as noted in the Commercial Case. The MoU will detail the purpose of the programme, and the responsibilities of the FCDO and programme partners, including on reporting and risk management arrangements amongst other standard clauses such as safeguarding. Given the 12-month pilot phase, the MoU will include a break-clause to enable the collaboration to be terminated, or the approach re-set, should the pilot campaign prove unsuccessful. Ahead of the pilot campaign being deployed, FCDO will agree the success criteria for judging the performance of the campaign with partners.

In addition to an MoU between the FCDO and the partners, an over-arching results and governance framework will be agreed between the main collaborators with the flexibility for other partners to be added during implementation if necessary. This framework will outline the programme’s vision, log frame and VfM indicators, the division-of-labour amongst partners, and programme monitoring and accountability arrangements. While the governance framework will be devised to cover the whole 3-year programme period, it will be reviewed after the pilot phase to ensure that it is fit-for-purpose should the programme continue for the full 3-years.

Programme partners will also form an Advisory Committee that will meet quarterly to discuss performance, risks, and solutions for course corrections, if necessary. This committee will focus on strategic decision making, with the potential programme partner providing documentation to support this quarterly assessment.

Pillar 2
The decision on which research issues and activities to support under pillar 2, and how they will be conducted, will be taken by the UK Development Engagement Team under the guidance of its SCS2 Director. Decisions will be made in consultation with internal and, where necessary external organisations that have existing opportunities for development engagements. Given that activities have yet to be defined and will be dispersed, at this stage, it is not possible to specify a governance arrangement but as activities are confirmed, arrangements will be agreed in compliance with FCDO requirements.

Monitoring Plan
In addition to the above governance arrangements, the UK Development Engagement Team will monitor programme performance. A delivery plan monitoring key decisions, financial and risk management, and recommendations/lessons learned, will be kept up to date as part of regular programme management activity. In addition, under pillar 1, FCDO will meet with the potential programme partner each month to discuss programme performance and risk management, amongst other issues.

After the 12-month pilot phase, and every following year, FCDO will conduct an Annual Review of the programme assessing results against performance milestones and value-for-money indicators. When the programme concludes, FCDO will conduct a Programme Completion Review, assessing the programme’s overall performance and whether it achieved the intended results and VfM ambitions.

Beneficiary feedback
Feedback from direct beneficiaries, such as the public (under pillar 1), CSOs, local communities and other recipients of the development engagement approaches will be sought to ensure that lessons learned are integrated into programme design while also building the evidence base. An option to be explored during the pilot phase is whether to attain feedback on development engagement approaches through carefully selected focus groups.

The Log-frame
Programme performance will be measured against the impact, outcome and output statements noted in the Theory of Change. Below details an indicative log frame. If both pillars are implemented over the full 3-year duration, suggested wording, measurement and data sources for the indicators may change as the evidence base builds.

Intended Impact
Improved attitudes and behaviours towards international development by the UK public and institutions.

Outcome Statement
Pillar 1: Improvement in attitudes and behaviours towards international development by the target audience(s).

Indicators:

Measurable positive attitudinal shifts amongst the target audience exposed to the campaign with regards to the following statements:
- ‘ODA makes a great deal of a difference to improving the lives of poor people in poor countries.’
- ‘ODA improves lives by providing access to education, healthcare, clean water + sanitation.’
- ‘ODA gives people key skills + tools so they can lift themselves out of poverty.’
- ‘Helping people in need is the right thing to do.’
- ‘I want to help make a difference to the lives of people in poor countries, in whatever ways I can.’

Measurable positive movement of the percentage of the audience from being behaviourally “marginally engaged” to “transactionally engaged” on the issue of international development, as tracked by audience insight specialists (NB – achieving this will be subject to sufficient investment in both understanding movement along the marketing funnel from awareness to action and serving appropriate content at a sufficient scale and frequency).

Pillar 2: Increased number of, and more effective, development engagement approaches.

Indicators:
- Number of new FCDO programmes including improving UK development engagement as an objective. (Source: Internal monitoring by the UK Development Engagement Team. Baseline: 0).
- Qualitative results from an independent evaluation to assess the effectiveness of FCDO’s development engagement approach at the end of the programme period. This could include impact assessments using quantitative measures to see if interventions changed peoples planned and taken voices, choices and actions.

Outputs
Pillar 1: Public response to different types of content.

Indicators: A measurement matrix will be developed in consultation with the media buying agency contracted by the potential programme partner that will provide relevant metrics on the type and value of digital engagement by the audience with social media content (for example, length of video view, positive share with comment etc.).

Pillar 2: Evidence generated, synthesised, and used to improve understanding of effective development engagement approaches, and events participated in that aim to raise awareness of, and support for international development.

Indicators:
Number of research products produced. (Source: UK Development Engagement Team. Baseline: 0)
Number of engagement outreach events participated in. (Source: UK Development Engagement Team. Baseline: 0)

Inputs
For both pillars: G7 project funded communications expert and other (non-project funded) FCDO staff time; FCDO political capital and organisational commitment to strengthening development engagement; funding – for external contractors, research products, and engaging in awareness raising and support building events.

  Key assumptions underpinning the log-frame.
- Domestic economic and social conditions do not significantly deteriorate to detract attention from international development.
- There is sustained apolitical support for UK development engagement activities.
- Social media is the best platform to target the audience.
- Content is appropriate for shifting the opinion of the target audience.
- The development engagement programme, which is short term and low scale, tangibly makes a difference in raising awareness and shifting opinion.
- Monitoring data continues to be available.
- Research activity is well targeted and designed to credibly inform development engagement approaches.

Value-for-money
The following indicative indicators, both quantitative and qualitative, will be used to assess the VfM of the programme, though may be adjusted during its course depending on data availability and as new evidence emerges on effective development engagement approaches.

Economy indicators
Pillars 1 & 2: / G7 project funded admin FTE cost. / If external expertise is contracted during the implementation phase: consultancy/agency fee day rate.
Pillar 2: / Cost per research product. / Cost per event, directly organised or contributed to.

Efficiency indicators
Pillar 1: / Cost per individual reached through the campaign, disaggregated where possible between those who are part of the target audience(s) and those who are not. / Visibility: Whether the campaign reached the target audience(s). Whether the messaging was effective in aiding understanding of development and aid. / Interest: Was the content appropriate to engage the target audience(s).
Pillar 2: / Research that provides evidence of effective approaches which FCDO can either implement or support others to implement – for example, a menu of more efficient interventions.

The programme will build a culture of learning and adaptive management so that data on effectiveness can influence the programme’s approach and delivery throughout its lifetime. Effectiveness indicators will be qualitative and will include:

Effectiveness indicators
Pillars 1 & 2: / Perceptions of effectiveness: Whether there has been an increase in the perceived positive impact of international development and aid. / Personal motivation: Whether individuals are now more minded to contribute, or contribute more, to international development. / Associated factors: Whether knowledge of international development and aid has increased, whether there is increased optimism that progress in international development can be made, and whether there is improved trust in international development actors (including Government, International Organisations, aid workers, businesses, and NGOs).

Assessing cost effectiveness through a narrative requires an understanding of the amount spent to create the outcomes observed. Data will be taken from all the sources used to measure outcomes under the programme, including surveys so that rounded and holistic conclusions can be drawn.

We anticipate the programme will also build capability within FCDO to target sharper and better development engagement communications to the UK public.

Cost Effectiveness indicators
Pillar 1: / Cost per percentage point of positive attitudinal shift amongst target audience(s) reached, including their stated intention related to positive behaviours towards international development as measured by audience insight specialists.
Pillar 2: Actual costs will be calibrated to ensure cost-effective (actual cost versus what can be bought while ensuring quality).

Equity

Equity indicators
Pillar 1 & 2: Data, to be determined, that analyses different audiences and partners reached – beyond the usual ‘in’ audiences and partners in the UK. / Data, to be determined, that analyses how individual’s use of ‘voice’, ‘choices’ and the ‘actions’ they undertake support equitable international development.

Risk appetite statement
The programme is assessed as a major risk. With robust controls and mitigations from FCDO, in collaboration with partners, risks will be managed and carefully monitored. Under pillar 1 – the riskier of the two pillars - throughout the pilot phase, and if it proves successful, the full campaign phase, data will be used to inform risk management and ensure that it is monitored effectively. This will include through the Advisory Committee, which will discuss risk issues quarterly in addition to monthly monitoring by FCDO and the potential programme partner. Across both pillars, the SRO will ensure the effective management of risk and retain overall accountability, as per Rule 18 of the ProF. The PRO will support the SRO by leading the active risk management process, in collaboration with partners as necessary.

Risk categories and mitigation/controls

	Risk Appetite by risk category
Risk Category	Definition of Risk	Risk	Current appetite level	Mitigation and control
Strategy and Context	Risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact.	Challenging economic and social domestic conditions make it difficult to engage audiences on international development issues.	Receptive	Careful attention will be given to how development issues are labelled, explained, and made relevant to UK lives.
Policy and Programme Delivery	Risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing and/or operational support. These risks undermine our impact and influence.	Ineffective engagement activity, e.g., the campaign is insufficiently compelling, does not have enough time to change opinion, or yields unintended consequences – for example, brain drain perceptions when using diaspora NHS staff stories, spending taxpayer money overseas amid a cost-of-living crisis at home. / Funding for existing ability to longitudinally measure whole population attitudes and behaviours is cut.	Receptive	Pillar 1 will build on existing audience insight into the type of content that best engages the target audience, while the early pilot test will also generate performance data on which to build from. The Development Engagement team will also collaborate with internal colleagues and external development experts to ensure that engagement and content is designed and targeted appropriately and includes effective examples of mutually beneficial development work. The partners in the advisory group overseeing the pillar 1 programme will work to ensure funding for audience insight specialists. / Pillar 2 is focused on building the evidence base for what works best to improve development engagement.
Public Service Delivery and Operations	Risk arising from weaknesses in the delivery of consular services or the delivery of internal operations which support our core business and wider HMG, including security, legal, technology and information and property risks, impacting delivery, our people, and British citizens.	Future decision to cut roles negatively impact ability to implement work on development engagement under this programme	Cautious	Ensure work is well-nested within wider organisational structures both policy and communications and adapts through the programme cycle.
People	Risk arising from weaknesses in leadership and engagement, culture, and behaviours and/or workforce capacity and capability, impacting on performance.	Limited staff capacity, particularly regarding communications and M&E expertise and the small size of the UK Development Engagement Team, undermines the quality and pace of delivery.	Receptive	Under pillar 1, if proven necessary during the pilot phase, additional external – either HMG or non-HMG expertise – will be contracted to address capacity gaps. / Under pillar 2, UK Development Engagement Team activities will include a focus on delivering engagement objectives through existing and new FCDO CSO programme. Opportunities to rely more heavily on this approach will be considered if the team’s own capacity is overly duly constrained.
Financial and Fiduciary	Risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak VfM, compliance and delivery failures and reputational damage.	Funds are not used for their intended purposes or not managed in accordance with requirements.	Minimal	Under pillar 1 during the pilot phase, financial spend will largely be internal – either within FCDO or transfers to other HMG departments. If the pilot phase is successful and scaled up into the implementation phase, any external contractors will be carefully managed to mitigate financial and fiduciary risks, in accordance with FCDO requirements. / Under pillar 2, contracts for research and events are expected to be of low-value and will be carefully managed in accordance with FCDO requirements to minimise risks.
Safeguarding	Risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage.	Under pillar 1: Content exposes vulnerable people and/or groups. / Under pillar 2: Engagement events exposes children and/or vulnerable groups.	Cautious	All programme partners will be made aware of FCDO’s zero tolerance policy on sexual exploitation, abuse and harassment and inaction, and the requirements on reporting. In addition, for pillar 1, careful attention will be given to the content used, specifically that it does not include footage of vulnerable people and groups. Good practice will also be followed on securing filming permissions from content subjects. / Under pillar 2, safeguarding practices will be deployed for any events working with children and/or vulnerable groups.
Reputational	Risk arising from political or adverse events, including delivery failures and ethical violations, damaging FCDO’s and/or UK’s reputation	For pillars 1 and 2 / Given timing of the political cycle, risk that enhancing engagement with UK audiences will be perceived as a political motive to build pre-election domestic support. / Amid difficult domestic conditions, communication on UK support for international development triggers a backlash with the view that “charity starts at home”.	Receptive	Content used under pillar 1 will be carefully selected and will not use HMG branding but instead focus on communicating the importance of international development. / Engagement, including the content under pillar 1, will focus on communicating the mutual benefits that international development delivers – for developing countries, and in making the world safer and more prosperous for the UK. / The broadly supported White Paper on International Development provides the mandate for public engagement in support of development, and the programme will liaise with Communications Directorate and the Press Office during the design stage to mitigate any perception risks. Wider Partnership work (pillar 2) will lay the foundations for longer term collaboration (to 2030) between FCDO and other UK development actors.
[note] Minimal appetite – Willing to accept the majority of activities carrying a minor degree of residual risk. Cautious appetite – Willing to accept the majority of activities carrying a moderate degree of residual risk. Receptive appetite – Willing to accept the majority of activities carrying a major degree of residual risk. Eager appetite – Willing to accept the majority of activities carrying a severe degree of residual risk.

Learning
The programme recognises from the outset that the evidence based on development engagement is weak in some areas, and hence monitoring, evaluation and learning, will be a core focus of the programme. Where possible, in-house, or elsewhere in HMG M&E expertise will be used, in addition to data gathered by audience insight specialists and any other social media digital monitoring. However, the option to contract externally, when specific expertise is required and where it proves to be better value-for-money, will be used, as detailed in the Commercial Case.

Pillar 1 will build on the existing evidence base on the type of content that works best in influencing the target audience(s) to increase their awareness of, and support for international development. It will also seek to address evidence gaps on how verbalised support for international development catalyses positive behavioural changes.

Pillar 2 is focused on building evidence on what works to improve the sector’s (HMG and the UK development community’s) engagement with people in the UK. Likely questions will be around who we should be engaging better with and how (e.g. UK diaspora, young people) and through what means (e.g. education, outreach to communities/regions, working with specialist NGO’s). Faith based civil society groups who are currently very active in this space will have lessons we can draw on for evidence of engagement styles worth trying. We will test ideas for areas of focus with UK Development engagement partners. We will also design a light touch strategy that learns lessons from the 2011 review of earlier FCDO (DFID) work in this area. This will frame commissioning new research and learning from FCDO’s own future increased engagement with people and communities in the UK. The strategy will be clear on the assumptions we are testing, the change we want to see, the evidence we will gather - all brought together in a clear evaluation framework. Finally, we will conduct in-house research, and if necessary, commission external products to learn from the domestic engagement approaches of other G7+ countries.