## Annual Review Template

Title: Global Compacts on Refugees and Migration Programme (GCP)
Programme Value £ (full life): £24,240,000		Review date: 23/06/2025
Programme Code: 400209	AMP start date: 01/04/2024	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2024/25
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Business Case / BC Addendum 1
DevTracker Link to results framework:	Logframe

A. SUMMARY AND OVERVIEW

Description of programme
The FCDO’s Global Compacts on Refugees and Migration Programme (GCP) was established to support the implementation of the 2018 Global Compacts on Migration and Refugees, addressing the growing scale of global human mobility and associated protection and social cohesion challenges. Through a combination of multilateral and bilateral delivery, the GCP is supporting initiatives focusing on i) promoting safer, more orderly, and regular migration, ii) increasing inclusion of refugee children in national education systems, iii) combatting gender discrimination in nationality laws, iv) improving host and transit countries’ ability to support migrants and forcibly displaced people, and v) supporting refugee and stateless people’s inclusion in the decision- and policy-making that pertains to them. The programme reflects UK strategic priorities and contributes to strengthening the international architecture for managing displacement and migration.

The programme operated using both bilateral and bilateral through multilateral methods. Bilateral projects include partnerships with the Asia Pacific Network of Refugees (APNOR), and the Women’s Refugee Commission (WRC). Bilateral through multilateral projects include contributions to the Migration Multi-Partner Trust Fund (MMPTF), Internal Displacement Solutions Fund (IDSF), UN Office of the Special Advisor on Internal Displacement (UNOSA), Global Concessional Financing Facility (GCFF), and Inclusion Support Program for Refugee Education (INSPIRE). A final project, a contribution to the Rome Process Financing Facility (RPFF), was postponed to the second year of the programme due to administrative delays outside of FCDO’s control.

Summary supporting narrative for the overall score in this review
GCP has made a strong start in its first year of implementation, with all five outputs meeting or exceeding their milestones. Three outputs (1, 2, and 3) were rated A+ due to significant overachievement, particularly in the number of engagement events held, countries supported, and capacity-building activities delivered. Outputs 4 and 5 were rated A, reflecting solid delivery but with some limitations—namely, delays in GCFF project approval and limited reporting detail from INSPIRE due to timing misalignments. These variations were not due to partner underperformance but rather to external factors and communication challenges, which are being addressed in Year 2 planning.
The programme’s overall output score of A reflects this strong performance across a diverse and complex portfolio. Despite the challenges of launching a multi-component programme with varied delivery models, GCP has demonstrated clear progress toward its intended outcomes. The majority of partners delivered on time and within budget, and several exceeded expectations in terms of reach and influence. The programme is well-positioned to achieve its intended impact within the current timeframe and budget, particularly with planned improvements to indicator clarity, partner engagement, and delivery planning in the year ahead.

Major lessons and recommendations for the year ahead
Key lessons and recommendations from this year include:
- Programme team to consider adjusting the logframe to more accurately reflect meaningful progress, rather than using simple indicators such as “projects funded”, as well as use disaggregated data where possible. This review of the logframe might necessitate a review and revision of the theory of change (ToC), since it is the basis of the logframe and so should remain in sync with it. [see section G: p. 15].
- Programme team to clarify indicator definitions and expected reporting from partners before setting new targets for the coming year, to ensure reporting more accurately reflects actual, substantive outcomes [see section B: pp. 3-4, section G: p. 14].
- Meaningful refugee participation (MRP) training planning should commence as soon as possible, with dates booked at least a month in advance. Training materials should be reviewed in depth and by a wide range of stakeholders, not just the programme team [Output 1 analysis: pp. 5-6].
- Programme team to remain in close contact with GCFF managing unit to ensure project is approved promptly [see Output 4 analysis: p. 9].
- The programme team should consider conducting more in-person monitoring visits, to ensure a more in-depth understanding of programme impact, operating context, and partner performance. In these visits, programme teams should seek to include beneficiary engagement, and to do so by other means where in-person visits are not possible [see section G: p. 14].
- The programme team should work with policy colleagues and MMPTF through the Steering Committee on ways to broaden the donor base (e.g. increased engagement with the private sector), due to foreseen fundraising shortfalls [see section F: p. 13].

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

GCP is designed to respond to the growing scale and complexity of global human mobility, which presents both development opportunities and significant protection challenges. Its aims are for forcibly displaced people and migrants to have better access to protection, rights, services and livelihoods, and for migration to be safer, more orderly and regular.

To achieve this impact, GCP funds a portfolio of multilateral and bilateral initiatives that span a wide range of activities. These investments generate concrete outputs, including direct support to forcibly displaced individuals and their organisations, contributions to global and national reforms on nationality rights, mobilised action on forced displacement, and strengthened capacity of host governments to manage displacement and irregular migration. These outputs serve as the foundation for intermediate outcomes such as more inclusive and resilient host communities, improved protection and legal frameworks, and greater participation of affected populations in shaping the policies that affect them. Together, these changes contribute to a more coherent and effective global response to migration and displacement.

This year, the programme’s ToC saw a major overhaul of its structure. The previous ToC was written at the early stages of programme design, before the exact inputs (projects being funded) were known. Once the programme was underway, the ToC was modified to include the specific inputs planned and more precise outputs and outcomes that better reflect the connections between the inputs and impact. The ToC logic and assumptions have thus far held up against implementation experience, and therefore remain valid. See Annex A for initial and redesigned ToC.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome 1 - Forcibly displaced people and those impacted by discriminatory nationality laws contribute to policymaking and decision-making on issues pertaining to them.
Indicator 1 - # of high-level policy events with the participation of people impacted by forced displacement or discriminatory nationality laws.
Target: 16; Achieved: 46
This year, APNOR met their target of ensuring the representation of refugees in 8 relevant high-level policy events, while WRC facilitated the involvement of people impacted by discriminatory nationality laws in 38 high-level policy events, significantly exceeding their target of 8. This was largely due to national partners’ abilities to stretch a modest amount of support farther than expected, and global engagement events yielding greater national stakeholder interest than anticipated. Targets for future years should take this significant overachievement into consideration and be more carefully considered to ensure they are more realistic and prevent superficially good results. Furthermore, the definition of ‘high-policy event’ should be reviewed and agreed with the partner to ensure reporting is accurate.
Indicator 2 - # of countries where refugees, IDPs, or those impacted by discriminatory nationality laws have contributed to policy discussions.
Target: 13; Achieved: 20
This year, IDSF has exceeded its first milestone of 5 and already nearly met its second-year target. Of the 10 projects launched this year, all but one included significant constituent involvement, with the final project set to include such involvement at a later stage. WRC also exceeded its target, as the change in circumstances in Syria enabled the implementation of one extra national grant, thereby slightly surpassing the target of 8. On the other hand, APNOR facilitated the involvement of refugees in policy discussions in 2 countries this year, missing their target by one.
Due to IDSF and WRC significantly exceeding their milestones for the year, this outcome is well on track to be achieved by the end of the programme, despite APNOR’s slight underperformance. As for programme impact, reporting suggests that the events facilitated by the partners are having real impact on dialogue in the relevant countries, and are likely to lead to real change in the lives of the affected populations. For example, In Eswatini, a national dialogue convened by a WRC-funded grantee enabled undocumented individuals to share their experiences directly with policymakers, resulting in pledges for legislative reform and broader community engagement.

It is important to note that APNOR’s underperformance was not due to issues in delivery, but rather a seeming misunderstanding regarding definitions. For indicator 1, APNOR reported several events that the programme PRO did not agree qualified as high-level policy events. For indicator 2, APNOR reported engagement by refugees from several countries in global events, when the indicator was intended to measure local, country-specific engagement. It is recommended that the definition of indicators be clarified with APNOR (and other partners) before targets are set for the next year of the programme, should the partnership be extended as planned.

Outcome 2 - Increased visibility of and constructive discussions about the challenges of statelessness-causing discriminatory nationality laws and forced displacement.
Indicator 1 - # of engagement events held
Target: 54; Achieved: 146
This year, UNOSA held 40 events, significantly surpassing its target of 30. WRC and its grant-recipient partners managed to hold an impressive 103 events, far surpassing their target of 20. The reasons for this overachievement are the same as mentioned in Outcome 1. Similarly to Outcome 1, APNOR slightly missed their target of 4, having delivered 3 engagement events as judged by the PRO.
Indicator 2 - # of countries involved/reached
Target: 50; Achieved: 59
This year, UNOSA met its target by engaging with 15 countries on the challenges of internal displacement. WRC once again significantly surpassed its targets, having engaged 17 countries in dialogue on discriminatory nationality laws through both global events and national grants. Finally, APNOR achieved its target for this indicator, having engaged 27 countries through its Refugee Leadership Alliance.
Through the events held by the programme’s implementing partners, the programme has contributed to increased visibility and constructive dialogue on statelessness and forced displacement. APNOR’s global advocacy efforts, including publications in Forced Migration Review and participation in high-level forums such as the HLOM Preparatory Meeting, have amplified refugee-led perspectives. UNOSA drove systemic change within the UN and other INGOs by convening a UN Steering Group on Solutions, supporting the development of a new UN system-wide approach to internal displacement, and establishing a Development Finance Coordination Group with 23 international financial institutions and donors.

Due to UNOSA and WRC surpassing their targets for the year, and APNOR meeting and only slightly missing theirs, this outcome is on course to be achieved. Meaningful engagement was reported by all three partners, placing the programme on track to achieve its impact.

Regarding APNOR’s performance under Indicator 1, the same problem was identified as in Outcome 1, where APNOR classified certain activities as events which the PRO would not (such as publishing articles). As noted above, it is recommended greater care is taken in future to ensure partners understand the definitions of indicators they are to report against. Regarding UNOSA, although it overachieved its target for Indicator 1, only 17 the events were held after the date of the GCP contribution. Although the target set for this indicator was not intended to only monitor activities after the contribution, it would have possibly been more accurate to do so. Such considerations should be taken into account when writing or amending targets in the future.

Outcome 3 - National governments are supported to better respond to forced displacement, to realise the benefits of safe and legal migration, and to address challenges stemming from irregular migration.
Indicator 1 - # of countries assisted, Indicator 2 - # of projects funded
Target: 12; Achieved: 13
This year, IDSF exceeded its target by launching initiatives in 10 countries — 8 fully operational projects and 2 additional ones that successfully initiated key processes ahead of schedule. In parallel, MMPTF successfully launched 3 new projects this year in 3 different countries. Finally, although GCFF was initially predicted to approve a project by the end of March 2025, in-country delays meant that the project was postponed to early FY25/26. For a more detailed account, see analysis in Output 4.
This year, a standout for this outcome was the IDSF. In countries such as Ethiopia, Nigeria, and Colombia, whole-of-government solutions strategies were developed and integrated into national development plans. Costed action plans enabled governments to allocate resources and coordinate across ministries, while legal reforms and data system improvements enhanced governance capacity. These efforts help governments better manage displacement, promote safe and legal migration, and address the challenges of irregular migration in a sustainable and rights-based manner.

Due to MMPTF meeting its target and IDSF exceeding its own, this outcome is on track to be delivered despite the delay in GCFF’s activities, with multiple governments supported. Although the IDSF projects are still in the early stages, and MMPTF’s projects being too new to report achievements yet, currently available data on both fund’s performances indicate the projects are likely to contribute to the delivery of the programme’s intended impact.

Outcome 4 - More refugees are included in national service provision.
Indicator 1 - # of refugees whose integration into national systems is supported
Target: 729,000; Achieved: 729,446
This year, the INSPIRE programme launched and effectively delivered projects in 14 countries – 4 in the first wave and 10 in the second. The target number of refugee children for this indicator covered only the first wave of projects, as the second wave commenced too late in the calendar year to report results by the time the INSPIRE annual report was published. For those 4 projects, INSPIRE met its target of supporting 729,000 refugee children’s integration in national education systems. Of those children, 167,260 of were direct beneficiaries of the activities and leveraged funds, while the rest benefitted indirectly through changes in broader government programmes catalysed by INSPIRE activities and advocacy.
As INSPIRE has met its target for the first wave of projects, and with the second wave of project well underway, this outcome is expected to be delivered by the end of the programme. Due to the projects supporting refugee children’s access to education, this outcome has already contributed to the intended impact of the programme.

The target for this indicator was set quite late in the year, due to a misunderstanding between the programme team and the partner. While the programme team requested milestones and targets, the partner thought that they had requested actual results, likely due to the late stage of the projects when numbers were requested. It is recommended that the programme team ensure future requests for targets be precise and clear, to prevent such misunderstandings recurring.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis of outcome and output achievement, ToC and value for money (VfM) analysis, there is enough evidence that the programme continues to represent good VfM and deliver well against its objectives and intended impact.

The programme has been reviewed by the team in light of the new government’s priorities and wider portfolio context, and it has been determined that it still aligns well with both. This conclusion is largely based on migration being newly designated a Foreign Secretary priority, and the need to concentrate funding to catalytic-impact initiatives that maximise the impact of UK ODA.

## C. DETAILED OUTPUT SCORING

Output Title	Increased resources are channelled to refugees and those impacted by discriminatory nationality laws, strengthening their capacity to engage in international and national policy discourses.
Output number:		1	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# of organisations led by refugees, FDPs, or people impacted by discriminatory nationality laws funded.	13	14
Training provided on meaningful refugee participation.	2	2
# of capacity building activities implemented to enhance the reform advocacy ability of people impacted by discriminatory nationality laws.	18	55

Briefly describe the output’s activities and provide supporting narrative for the score.

APNOR and WRC have made strong progress in strengthening the capacity of refugee-led organisations (RLOs) and those affected by discriminatory nationality laws to engage in national and international policy processes.

Under Indicator 1.1, APNOR has provided core funding to five RLOs across four countries—Bangladesh, Malaysia, Pakistan, and Thailand—four of which are women-led. These organisations are implementing projects focused on education, mental health, youth leadership, and advocacy for marginalised groups. Although they faced initial difficulties with transferring the grant funds to three of the grantees due to local fiscal regulations and the RLOs’ restricted capacity (a recognised barrier to funding RLOs), APNOR overcame these challenges and managed to transfer the grants to all RLOs. Due to the funds being transferred only around February and March, the RLOs’ activities will not be covered in this report. WRC, through the Global Campaign for Equal Nationality Rights (GCENR), issued nine advocacy grants to organisations led by individuals impacted by discriminatory nationality laws in nine countries – Lebanon, Eswatini, Libya, Iraq, Nepal, Malaysia, Somalia, Mauritania, and Syria. This is one more than originally predicted, as the unexpected fall of the Assad regime in Syria opened up an opportunity to build momentum for legal reform in the country. These grants supported over 100 engagement activities, including the 55 capacity-building activities covered in Indicator 1.3. These activities included youth summits, legal workshops, and strategic communications training. This number significantly exceeds the milestone of 18 due to several reasons: (a) grant recipients’ ability to deliver much more than anticipated from only modest support, (b) unanticipated high number of community engagements and official meetings with government representatives in several countries, and (c) previously unforeseen opportunities arising for global-level capacity building/engagement events, such as invitations to present on the issue at events organised by others and information sharing meetings with member state missions. The scale and quality of activities delivered with modest funding demonstrate the untapped potential of local organisations when adequately resourced.

Under Indicator 1.2, APNOR delivered a two-part training sessions on meaningful refugee participation (MRP) to FCDO staff in March 2025, split over two days. Due to the delays in onboarding the permanent Programme Manager/PRO and the interim PRO needing to return to their permanent role full time, there was a delay in beginning the planning for the MRP training. Consequently, planning was somewhat rushed to ensure that activities took place within the correct FY, resulting in lower than desired attendance. Furthermore, the time pressure negatively impacted the amount and rigour of the feedback from the programme team during preparations, resulting in materials (such as case studies) not being as tailored to FCDO’s work as desired. Despite this, the training was largely a success, with feedback from participants indicated a strong increase in understanding and confidence in applying MRP principles, with average satisfaction scores of 4.25–4.5 out of 5. Within the Forced Displacement team, the training triggered an in-depth discussion on how best to support MRP within FCDO and wider HMG, resulting in a promising list of actions that will be taken in the coming year.

This output has been marked with an A+ as the milestone for Indicator 1.1 (number of organisations funded) has been slightly exceeded, Indicator 1.2 (training on MRP) has been met, and Indicator 1.3 (capacity-building activities) has been significantly exceeded. Given that these were one-year agreements, the first milestones were also the overall targets, meaning these were achieved as well.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output this year, as the logframe was only created within this timeframe.

Should our agreements with APNOR and WRC be extended to provide them with additional funds in FY25/26, this output should be amended to increase the milestones and target to include the additional activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

As mentioned above, the MRP training was not as effective as it might have been had planning started more in advance. Should the agreement with APNOR to deliver more MRP training be extended in the programme’s second year, it is recommended that planning begin as soon as possible, and training materials reviewed with more rigor and perhaps by a wider range of stakeholders.

Output Title	Global and national nationality rights reform efforts and awareness-raising initiatives funded to combat causes of statelessness.
Output number:		2	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# of advocacy grants given to national NGOs leading reform efforts	8	9
# of engagement events held	20	103
# of countries with data secured for the legal atlas	12	12

Briefly describe the output’s activities and provide supporting narrative for the score.

This year, WRC has made substantial progress in supporting national and global efforts to reform discriminatory nationality laws and raise awareness of their role in perpetuating statelessness.

Under Indicator 2.1, WRC awarded nine advocacy grants to national NGOs across Eswatini, Iraq, Lebanon, Libya, Malaysia, Mauritania, Nepal, Somalia, and Syria, exceeding its target (reasons covered under Output 1). These grants enabled locally led organisations to lead context-specific reform campaigns. For example, in Eswatini, the Youth Sustainable Development Centre (YSDC) convened a national dialogue with 56 participants including parliamentarians, traditional leaders, and UN agencies to discuss legislative reform. As a result of YSDC’s engagement, stakeholders have committed to integrate the issue into the country's key implementation plans. In Malaysia, Family Frontiers’ six-year campaign came to fruition in the final months of 2024 when a constitutional amendment was passed ensuring future Malaysian women will be able confer their citizenship to their children born abroad. The programme’s support helped Family Frontiers reach a landmark settlement that expanded upon the constitutional amendment and provided Malaysian mothers the right to obtain citizenship for their children born abroad prior to passage of the amendment (as it was non-retroactive).

Under Indicator 2.2, WRC and its partners conducted a total of 103 engagement events over the reporting period. These included national workshops, legal roundtables, youth summits, and media campaigns. A standout achievement was the Global Multistakeholder Summit on Gender-Equal Nationality Rights. This was the first global convening of its kind, bringing together representatives from 15 countries—including parliamentarians, civil society leaders, and UN agencies—to share strategies, build alliances, and commit to advancing legal reform. The summit significantly raised the profile of the issue and helped establish new champions for reform at both national and international levels. The milestone for this indicator was significantly exceeded for the same reasons as described under indicator 1.1.

Under Indicator 2.3, WRC secured legal and policy data for 12 countries where women are denied the right to confer nationality on an equal basis with men. This data will inform the forthcoming Legal Atlas on Gender Discrimination in Nationality Laws, a key advocacy and research tool aimed at supporting evidence-based reform efforts globally.

This output has been marked with an A+ as the milestone for Indicator 2.1 (advocacy grants given) has been exceeded, Indicator 2.2 (engagement events held) has been significantly exceeded, and Indicator 2.3 (data secured for the legal atlas) has been met. Given that these were one-year agreements, the first milestones were also the overall targets, meaning these were achieved as well.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output this year, as the logframe was only created within this timeframe.

Should our agreement with WRC be extended to provide them with additional funds in FY25/26, this output should be amended to increase the milestones and target to include the additional activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
N/A
Output Title	Action is mobilised within the UN system on internal displacement and engagement with development actors is catalysed at central and country levels.
Output number:		3	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# of projects funded	8	10
# of countries supported	8	15

Briefly describe the output’s activities and provide supporting narrative for the score.

This year, UNOSA made strong progress in mobilising action within the UN system on internal displacement and catalysing engagement with development actors, with IDSF being a key tool for doing so.

Under Indicators 3.1 and 3.2, the IDSF supported ten joint programmes across Somalia, Ethiopia, Nigeria, Colombia, Mozambique, Central African Republic, Chad, Iraq, Yemen, and Vanuatu—exceeding the target of eight thanks to the availability of funding allowing the early initiation of critical processes for two additional ‘smaller’ projects. The programmes were designed to support nationally owned, development-oriented solutions, with a strong emphasis on government leadership, inter-agency coordination, and inclusive planning. For example, in Somalia, the IDSF enabled the launch of the federal Solutions Pathways Action Plan, a costed framework aiming to support one million IDPs, which has since been embedded in the National Transformation Plan. In Ethiopia, five regional action plans were developed under a new national strategy, with strong engagement from federal and regional authorities. In Colombia, the Durable Solutions Strategy was elevated to a CONPES document, giving it national policy status and aligning it with the country’s development planning framework. Feedback from posts in the target countries was largely positive, particularly in Nigeria, Iraq, and Somalia. However, colleagues in Yemen reported little progress due to contextual challenges, so the programme team is advised to pay particular close attention to future reporting on this country project.
Also under Indicator 3.2, the ten countries IDSF programme countries, along with five further countries—Afghanistan, Libya, Niger, South Sudan, and Sudan—were supported by UNOSA through its work implementing the UN Secretary-General’s Action Agenda on Internal Displacement. These countries were designated pilot contexts where the UN deployed Solutions Advisers, supported the development of national strategies, and facilitated inter-ministerial coordination platforms.

Beyond its work in the pilot countries, UNOSA also conducted a range of activities that, while not counted under the indicators, have generally contributed to achieving the output as a whole. These activities included convening a UN Steering Group on Solutions, supporting the development of a new UN system-wide approach to internal displacement, and establishing a Development Finance Coordination Group with 23 international financial institutions and donors. These efforts helped embed internal displacement into the strategic frameworks of key development actors, including the World Bank and African Development Bank, both of which introduced IDP-related indicators into their corporate results frameworks.

This output has been marked with an A+ as both milestones have been exceeded. Although the milestone for indicator 3.2 was significantly exceeded, this is because it did not include any targets for UNOSA’s work. This oversight was largely due to the then-new PRO creating the logframe after UNOSA-related programme work had concluded and without being familiar with the particulars of its work. The PRO misunderstood the expected activities of the partner as being only focused on UN reform and was not aware of the planned country support. Due to this oversight, an A++ rating was deemed inappropriate, as had UNOSA’s work been included in the milestones, this indicator would have likely only slightly exceeded expectations.

Due to IDSF exceeding this milestone, and the promising financial condition of the fund, this output is considered to be well on track to achieve its end-of-programme target.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output this year, as the logframe was developed within this reporting timeframe.

If an additional contribution to IDSF is made in FY25/26, the FCDO should consider increasing the milestones and target to include the additional activities. Whether or not this is necessary depends on whether any additional funds will increase the expected output or simply ensure existing targets are reached.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Due to UNOSA’s work not being included in indicator 3.2 though it should have been, the programme team should consider amending the targets retroactively. Doing so would ensure numbers would align with the work done and not inaccurately reflect significant overachievement.
Due to the reported underperformance of the IDSF project in Yemen, the programme team is advised to pay particular attention to this project in future.

Output Title	Regional and national projects funded that promote safe migration, identify solutions for IDPs, and address root causes of irregular migration.
Output number:		4	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# of projects funded	12	13
# of countries supported	12	13

Briefly describe the output’s activities and provide supporting narrative for the score.

This year, both the IDSF and MMPTF funded and implemented a range of projects that promote safe migration, identify solutions for internally displaced persons (IDPs), and address the root causes of irregular migration.

Under Indicators 4.1 and 4.2, a total of 13 country projects were approved and commenced across both mechanisms—10 through the IDSF and 3 through the MMPTF. The IDSF projects were covered under Output 3, and so will not be expanded upon here. The MMPTF projects – in El Salvador, Pakistan, and Zimbabwe – covered two of MMPTF’s five thematic areas: (i) Thematic Area 2, Protecting the human rights, safety and well-being of migrants, and (ii) Thematic Area 3, Addressing irregular migration, including through managing borders and combatting transnational crime. Under Thematic Area 2, the new project in El Salvador will strengthen government capacities for the protection and reintegration of migrants and their families, while in Zimbabwe, partners will be working to improve the safety and well-being of unaccompanied and separated children. Under Thematic Area 3, the new initiative in Pakistan will enhance national responses to trafficking in persons and migrant smuggling. Because all three MMPTF projects commenced in March 2025, a more detailed assessment of their results will only be possible in the next Annual Report.

Also meant to be covered in this output is the GCFF, where the GCP made a contribution of £4m earmarked for Jordan. At the time of the contribution (February 2025), the next Jordan project was expected to be approved by end of March, and the programme team was assured there was only a slight delay during a monitoring visit to Amman in March 2025. However, delays in negotiations between the World Bank and between different Jordanian ministries have meant that, as of June 2025, the project has still not been submitted for GCFF Steering Committee approval. When following up with the GCFF managing unit, programme team were informed that the project is expected to be submitted by mid-July.

Although this output’s milestone was exceeded by one, due to the IDSF exceeding its target by two, GCFF’s delays meant that it has not met its target of one. Therefore, this output has been marked with an A rather than an A+, to more accurately reflect the varying results. Due to the GCFF’s predicted timeline, and the IDSF and MMPTF’s good performance and financial stability, this output is assessed as on track to meet the end-of-programme targets.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Once the decision was made on contributing to GCFF through the Jordan window and estimated timelines were given, the milestones for both indicators was increased by one to reflect the new expected outcomes. Additionally, while updating the logframe with progress following receipt of all necessary reports, the PRO realised that they had originally inputted the wrong numbers for these indicators. An incorrect number was inputted for Milestone 1 (reason unknown) and the numbers of the two indicators were switched around. The reviewer then corrected the mistakes. It is important to note that the targets remain the same, the mistake was purely clerical.

If an additional contribution to IDSF is made in FY25/26, the FCDO should consider increasing the milestones and target to include the additional activities. Whether or not this is necessary depends on whether any additional funds will increase the expected output or simply ensure existing targets are reached.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Although GCFF did not reach its target this year, it is all but certain to achieve it by the end of the next reporting period as the project is expected to be approved by the end of Q2. However, given the unexpected delays so far, the programme team should continue to be in close contact with the GCFF managing unit to ensure that any further issues are raised promptly.
Output Title	Support provided to refugee host governments and other national and local actors to improve the integration of refugees into national systems.
Output number:		5	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# of projects funded	14	14
# of countries supported	14	15

Briefly describe the output’s activities and provide supporting narrative for the score.

In its inaugural year, INSPIRE successfully initiated operations and effectively supported host governments to integrate refugee children into national education systems.

Under Indicators 5.1 and 5.2, a total of 14 projects were approved across 15 countries. The first cohort of four countries—Burundi, Chad, Ethiopia, and South Sudan—began implementation in June 2024. These grants are supporting a range of activities, including the development of costed inclusion plans, language acquisition programmes, psychosocial support (PSS), and the inclusion of refugees in skills training and polytechnic colleges. For example, in South Sudan, INSPIRE is supporting the integration of psychosocial support into teacher training by developing a tailored curriculum and impact tools, enabling teachers to better support refugee students’ mental health. In Chad, the programme is designing a per capita school grant mechanism to incentivise refugee inclusion, with early government engagement indicating strong potential for uptake into national financing systems.

A second cohort of 10 projects was selected in late 2024 and began implementation in winter 2024. These include Benin, Colombia, Democratic Republic of Congo, Jordan, Lebanon, Mauritania, Republic of Congo, Rwanda, Armenia, Poland, and Zambia. Activities range from the development of national strategies and operational plans to the piloting of refugee-informed Education Management Information System tools and large-scale assessments. Due to the date of implementation and World Bank reporting periods being misaligned with GCP’s, performance details of the second cohort of projects will only be available in the next Annual Report.

This output has been marked with an A, as indicator 5.1 (projects funded) was met and indicator 5.2 (countries supported) was slightly exceeded. Indicator 5.2 was exceeded because one of the projects covers two countries (Poland and Armenia). However, this project is less involved than the others and is only expected to produce policy recommendations (as opposed to more detailed country plans).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For an unknown reason, the milestones for indicator 5.2 were lower by one than what they should have been. This mistake was corrected and all milestones adjusted to correctly reflect the target of 14.

If an additional contribution to INSPIRE is made in FY25/26, the FCDO should consider increasing the milestones and target to include the additional activities. Whether or not this is necessary depends on whether any additional funds will increase the expected output or simply ensure existing targets are reached.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

N/A
## D: VALUE FOR MONEY

Economy: GCP has demonstrated strong economy over the review period, largely due to its design. As the majority of funds were invested through MPTFs, no costs were incurred apart from maintenance fees charged by the UN and World Bank for such funds. These fees are standard for such mechanisms, and are charged to the entire fund budget and not per contribution. For the two bilateral partners, there were no unexpected costs and both partners managed to remain within budget.

Efficiency: Overall, the GCP has delivered acceptable efficiency over the Annual Review period, as evidenced by GCP surpassing almost every target. That said, efficiency was severely limited by a number of factors. Firstly, the restricted capacity of RLOs and local fiscal regulations led to delays in disbursing funding to 60% of RLOs. Secondly, staff turnover delayed the delivery of MRP training, resulting in a lack of attendance and limiting the effectiveness of the training. Thirdly, delays due to negotiations between the World bank and the Jordanian Government has resulted in £4m of earmarked funding remaining unapproved and undisbursed. Any additional funding should be accompanied with concrete steps to both resolve existing inefficiencies and to ensure that future funding is disbursed efficiently.

Effectiveness and cost-effectiveness: GCP has demonstrated strong effectiveness and cost-effectiveness since implementation. Of the targets agreed, 100% were met and 75% were surpassed, thus showing strong progress towards the proposed outcomes and impact of GCP. That said, multiple communication issues have negatively impacted the potential effectiveness of the programme. Firstly, communication between the programme manager and APNOR has resulted in the organisation missing two delivery targets and negatively impacting the effectiveness of training provided by APNOR to FCDO staff. Secondly, communication between the programme manager and INSPIRE has resulted in no measure of effectiveness for Outcome 4. Thirdly, due to a reporting mistake, for Output 3, targets for UNOSA were omitted. Consequently, interpretation of results should be treated with caution. Any additional funding should be accompanied with adjustments to targets proportional to the increase in funding. If earmarked, or in the case of targets being significantly surpassed, specific indicators should be remodelled to continue to ensure effectiveness and cost-effectiveness.

Equity: GCP continues to provide excellent equity, as is inherent for a programme of this nature. The programme continues to improve inclusion for marginalised groups to ensure access to rights and services as a mechanism for promoting refugee self-reliance. Additionally, through the Global Compact on Refugees, the GCP works to increase inclusive refugee education, prevent gender-based violence (GBV), and increase meaningful refugee participation. Funds and implementing partners are encouraged to support activities addressing gender inequality among migrants and forcibly displaced people and take into account gender considerations in all programming. In addition, funds and implementing partners continue to disaggregate data and indicators by gender to allow for effective equity monitoring.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of outcome and output attainment, ToC, VfM and evidence analysis, GCP continues to provide good value for money. Improvements to communication with delivery partners and general efficiency (as expected as a programme matures) will ensure that this is sustainable across the lifetime of the programme.

E: RISK

Overview of risk management

The GCP was assigned a Risk Score of Moderate at approval, and this score continues to be accurate. In November 2024, the programme team revised the risk appetites across all categories. This adjustment was made to correct an earlier misapplication of the concept, where appetites had been set to reflect expected levels of risk rather than the level of risk the programme is willing to tolerate. The revised appetites now provide a clearer framework for assessing and managing risk across the programme.

Risks were reviewed every six weeks, with regular check-ins held with partners to monitor delivery and identify emerging issues. This approach has enabled the programme team to maintain oversight across a diverse set of delivery contexts and partner types, and to respond proportionately to challenges as they arose. During this review period, all risks remained within the programme’s defined appetites.

The programme encountered a range of risk types during the year, with most of them falling under the following three themes:
- Contextual: Shifts in the external environment — including US funding cuts, UK ODA reductions, and the UK election period — posed risks to the delivery of some activities. These risks were managed through continuous engagement with partners, and all were ultimately able to deliver as planned.
- Operational (Internal): A delay in onboarding the permanent Programme Manager / PRO meant there was limited programme support for an entire month. This was resolved once their transfer to FCDO was finalised and a successful handover was completed, with the outgoing PRO supporting the transition.
- Operational (External): Delays in partner-led processes, such as the establishment of the RPFF and the selection of GCFF projects, created risks to the timely delivery of those specific components. These were proactively managed: the RPFF budget was successfully deferred by one year, and GCFF decisions were made in time to allow the UK contribution to proceed as scheduled.

To mitigate gender equality risks and in line with the Business Case’s Gender Equality statement, gender sensitivity was integrated to varying degrees by all five partners that implemented projects this reporting period. WRC and APNOR demonstrated the strongest gender focus, with WRC’s work explicitly targeting gender-discriminatory nationality laws and centring women-led advocacy. APNOR, a women-led organisation with over 80% female staff, prioritised women-led RLOs in its pooled fund, with 65% of grantees led by women and 8 of 20 projects focused on women and girls’ empowerment. IDSF mainstreamed gender across all ten projects, embedding gender-sensitive planning, inclusive consultations, and support to women-led IDP associations. MMPTF, for which gender responsiveness is a guiding principle, applying a gender marker to all projects, with 100% assessed as contributing to gender equality. While the INSPIRE programme does not explicitly reference gender in its reporting, it belongs to the Foundational Learning Compact (FLC) umbrella trust fund and so is covered by its overarching commitment to gender equality. Together, these efforts reflect a strong and growing commitment to gender equality across the programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Across the first year of implementation, GCP’s delivery partners demonstrated generally strong performance in delivery and financial management, with timely reporting, responsiveness to FCDO engagement, and a willingness to adapt to programme needs. While some challenges were encountered – particularly around indicator clarity and project timelines – these were largely addressed through proactive communication and are being factored into planning for next year.

APNOR proved to be a committed and flexible partner, consistently submitting narrative and financial reports on time. While time zone differences occasionally delayed communication, APNOR remained responsive and open to feedback, readily adjusting activities to align with programme objectives. A key lesson was the need for clearer communication on indicator definitions, as misunderstandings affected reporting accuracy. Nonetheless, APNOR’s financial management was sound, and their eagerness to collaborate was evident throughout.

WRC maintained a high standard of delivery, with prompt communication, detailed and timely reporting, and a strong alignment with programme goals. WRC’s responsiveness and clarity made them one of the most effective partners this year, consistently surpassing their targets for the reporting period.

IDSF and MMPTF, both large multilateral funds, submitted their annual reports as expected. These were detailed and clear, and both managing units were responsive to FCDO queries. Feedback from posts in countries where IDSF operates was generally positive, and both funds appear to be well-managed, with active oversight and effective coordination mechanisms. Financial forecasting and asset monitoring were appropriate for the scale and complexity of these funds. In its 2024 Annual Report, MMPTF reported having raised only $8.9m of the $25m target. Given the current global climate and trends, it is likely that MMPTF will also miss its funding targets in 2025. It is recommended that the programme team take advantage of the UK’s invitation to join the Steering Committee to work with policy colleagues and MMPTF on ways to broaden the donor base (e.g. increased engagement with the private sector) to help mitigate this risk.

GCFF did not deliver the expected project within this reporting period, primarily due to protracted negotiations between the World Bank and Jordanian authorities and between Jordanian implementing ministries. While there was a reasonable expectation that the project would be approved on time when the UK contribution was made in February, earlier action by the programme team might have mitigated the risk of delay. According to the GCFF management unit, the GCP contribution helped facilitate negotiations by ensuring funds were available. Had the earmarking decision been made more promptly, the contribution could have been disbursed sooner, potentially allowing negotiations to begin earlier and the project to be approved within the reporting period.

Despite the delay, the GCFF managing unit has been cooperative, and FCDO’s participation on the steering committee has provided valuable insight into fund operations. The managing unit remains active and engaged, and the project is now expected to proceed early in the next reporting period.

INSPIRE experienced delays in agreeing milestones and targets, stemming from a misunderstanding about the nature of the data requested. Response times were inconsistent, requiring multiple follow-ups in some cases. However, the monthly meetings led by the team at Education, Gender and Equality Directorate (EdGE) and their support outside of formal channels helped maintain momentum. The annual report was submitted on time, though its level of detail was limited due to the umbrella fund structure and the small number of active projects during the World Bank’s reporting period. We expect reporting to be more detailed next year, since the programme will have been active for long enough.

RPFF has not yet begun delivery, but early engagement has been largely positive. The managing unit has been communicative and flexible, and FCDO will continue to monitor closely as implementation begins in the upcoming year.

From the FCDO side, programme management was generally effective, though the delay in onboarding the permanent PRO created a temporary gap in support. This was mitigated through a successful handover and continued engagement with partners. Going forward, the programme team could strengthen its delivery by providing clearer guidance on indicator definitions, initiating earlier planning for activities which requires their input, and maintaining regular dialogue with partners to anticipate and address delivery risks.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Monitoring activities over the past year have combined regular partner engagement with targeted field visits and stakeholder consultations, providing a strong evidence base for programme decisions. The GCP team held quarterly check-ins with bilateral partners (APNOR and WRC) and monthly meetings with INSPIRE, in partnership with colleagues at EdGE who lead on engagement with the partner. These engagements enabled ongoing dialogue on delivery progress, risk management, and alignment with programme objectives. Communications with multilateral partners was largely ad-hoc, with insights and explanations requested and received when needed, with some more regular engagement through steering committees.

The Annual Review process was desk-based and led by the current PRO, who had direct experience managing the programme and participated in the Jordan monitoring visit. Input was sought from the former PRO to ensure the review covered the programme’s entire lifecycle to date, and feedback from posts was incorporated into the analysis. While the review relied heavily on partner reporting, the inclusion of field visit insights and external feedback helped reinforce findings and strengthen the evidence base. The Value for Money section was authored by an FCDO economist outside the programme team, providing an independent perspective.

A key monitoring milestone was the March 2025 visit to Jordan, where the PRO met with representatives from the Government of Jordan (GoJ), World Bank, UNHCR, and other stakeholders to discuss the GCFF and INSPIRE projects. The positive feedback received during the visit reinforced the programme’s commitment to both initiatives and provided valuable insights into the political and operational challenges facing refugee support in Jordan. Discussions highlighted the importance of timely funding to maintain GoJ engagement and the need for more strategic donor coordination to support refugee economic integration. The visit also confirmed the value of GCFF as a delivery mechanism, despite current tensions, and underscored the importance of INSPIRE’s role in addressing refugee education dropouts and informing future policy interventions. Given the valuable insights gained from the monitoring visit, it is recommended that more in-person monitoring visits be conducted this monitoring period. Ideally, enough visits should be conducted to monitor the performance of all seven projects while attempting to minimise costs by identifying locations where more than one project can be monitored during the same trip (such as the visit to Jordan covering both GCFF and INSPIRE). Should this not be possible, a minimum of two in-person monitoring visits should be conducted, covering at least one bilateral and one multilateral programme.

The programme’s SRO also attended WRC’s December 2025 Global Summit on Gender-Equal Nationality Rights and was highly impressed with the summit’s design and execution. The summit served as a landmark convening to elevate the issue of gender-discriminatory nationality laws. It successfully brought together a diverse range of stakeholders to share strategies, build alliances, and galvanise commitments to reform – demonstrating the value of WRC’s convening power and its role in fostering collaboration on this issue.

FCDO officials, including the programme SRO, also attended a Wilton Park Dialogue in November 2024 focused on progressing the GRF pledge on refugee education. This event helped advance the goals of INSPIRE by fostering collaboration among key stakeholders to enhance refugee inclusion in national education systems. The event underscored INSPIRE’s role in offering technical support to governments for integrating refugee children into public schools and facilitated in-depth, country-specific discussions on policy reform, financing, and school-level strategies. It also encouraged the creation of tailored national roadmaps incorporating INSPIRE’s tools, promoted peer learning, and strengthened partnerships among ministries, refugee-led organizations, and international agencies.

Feedback from FCDO posts in IDSF-supported countries was also reviewed. Posts in Iraq, Nigeria, and Somalia expressed strong support for IDSF’s locally-led, solutions-oriented approach. However, concerns were raised in Mozambique and Yemen about weak UN coordination and limited progress, respectively. These insights will guide future engagement with IDSF and inform decisions on future contributions.

One aspect of monitoring that was not taken advantage of to the fullest extent was beneficiary engagement. Although implementing partners conduct beneficiary engagement in planning and throughout their interventions, the programme team itself did not directly engage any beneficiaries. It is recommended that direct feedback from beneficiaries be sought in the next reporting period, during in-person monitoring visits as well as through other methods such as surveys, where in-person engagement is not possible.

Learning
Over the past year, learning has been captured through a combination of partner reporting, internal reflection, and field engagement. Regular meetings with partners provided opportunities to identify delivery challenges and adapt approaches in real time. Field visits to Jordan and Zambia offered valuable insights into programme implementation and stakeholder dynamics, while feedback from FCDO posts helped contextualise multilateral fund performance.

For the programme, a key lesson was the importance of early and collaborative planning for activities such as the MRP training. The training delivered by APNOR, while of good quality, was less relevant than anticipated due to rushed preparation. Planning for future sessions will begin earlier and involve broader consultation to ensure content is tailored to FCDO needs.

Another lesson relates to indicator clarity. The lack of clear, agreed definitions of indicators and terms used within them led to misunderstandings which affected reporting accuracy. This highlighted the need for clearer guidance and earlier engagement on reporting expectations. This will be addressed in the upcoming year through revised indicator definitions and clearer communication with partners regarding expectations.

For wider FCDO, the programme’s early implementation phase revealed structural and process-related challenges. The transition between SROs and the absence of a formal handover created information gaps and placed significant pressure on remaining team members. As noted by the previous PRO’s feedback, this situation—while managed with dedication by all involved—underscored the need for better succession planning and knowledge transfer protocols. Ensuring that no staff member exits without a proper handover, and improving recruitment timelines where possible, are key takeaways for future programme continuity.

The programme’s complexity also posed challenges for designing a cohesive ToC. With diverse projects linked more by shared impact goals than by delivery mechanisms or geographies, the resulting logframe included indicators (e.g. “projects funded”) that were less effective at capturing meaningful progress. This experience suggests that for similarly structured programmes, more flexible or layered monitoring frameworks may be needed – ones that can accommodate diverse delivery models while still tracking impact. For this programme, it is recommended that the programme team reevaluate the logframe indicators, and attempt to identify ones that better reflect quality of delivery. While doing so, the programme team should strongly consider using disaggregated data for the indicators (where possible), as this data would more accurately reflect beneficiaries and issues of equity. This review of the logframe might necessitate a review and revision of the ToC, since it is the basis of the logframe and so should remain in sync with it.

Finally, the late start to delivery – partly due to the business case’s broad scope—meant that some activities were compressed into shorter timeframes. This affected planning and partner onboarding. Future programmes would benefit from more detailed business cases and earlier mobilisation of delivery teams to ensure smoother implementation.

Date of last narrative financial report	APNOR: 04/04/2025 / WRC: 25/04/2025 / IDSF: 08/05/2025 / MMPTF: 30/05/2025 / INSPIRE: 20/12/2024 / GCFF: 09/07/2025	Date of last audited annual statement	APNOR: 04/04/2025 / WRC: 25/04/2025 / IDSF: 08/05/2025 / MMPTF: 30/05/2025 / INSPIRE: 20/12/2024 / GCFF: 09/07/2025

Annex A: Theory of Change