## Annual Review

Title: Foundations for Infrastructure and Recovery (Business Case + addendum)
Programme Value (full life): up to £17 million		Review date: 15 August 2025
Programme Code : 400210	AMP start date: 15 August 2024	AMP end date: 31 December 2026

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0007263.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007263.odt

ABBREVIATIONS

5CM	Five Case Model - the NISTA international infrastructure business case methodology
AR	Annual Review
BC	Business Case
BIM	Building Information Modelling / Digital Construction
COE	FCDO Centres of Expertise
DBT	Department for Business and Trade
DCO	Digital Construction Office (in State Agency for Reconstruction and Development of Infrastructure
DREAM	Digital Restoration Ecosystem for Accountable Management / Public Investment Management System
EBRD	European Bank for Reconstruction and Development
EIB	European Investment Bank
FIRE	Foundations for Infrastructure and Recovery Programme
FY	Financial Year
GCIEP	Green Cities, Infrastructure and Energy programme – consortium led by PWC contracted under the FCDO Centres of Expertise
GoU	Government of Ukraine
IFI	International Financial Institution
IPA	Infrastructure and Projects Authority
MDCT	Ministry for Development of Communities and Territories in Ukraine
NAUCS	National Academy for Ukrainian Civil Servants
NISTA	National Infrastructure and Services Transformation Agency (formerly IPA)
PEA	Political Economy Analysis
PIM	Public Investment Management
PPF	Project Preparation Facility
PPU	Project Preparation Unit - Coordinating body in the Project Preparation Facilities Framework
RDNA 4	4th Rapid Damage and Needs Assessment (World Bank, UN, GoU - March 2025)
SARDI	State Agency for Reconstruction and Development of Infrastructure
ToC	Theory of Change
URC2025	Ukraine Recovery Conference 2025
USAID	United States Agency for International Development
VfM	Value for Money
WB	World Bank

## A. SUMMARY AND OVERVIEW

Description of programme

The UK support to infrastructure is based on the principle that infrastructure policies,
strategies, programmes and projects will only achieve their development objectives and deliver benefits, including value for money if they have been scoped robustly and planned realistically from the outset. Globally it is common for projects to skip the scoping and jump straight to a preconceived, possibly politically driven “solution”, resulting in sub-optimal outcomes. Changing projects in the implementation phase, or retrospectively, is expensive and may damage the reputation of the responsible authority. Early investment in evaluation and planning of projects is the best way to maximise value from the investment and demonstrate transparency in execution.

The FIRE business case recognises that FCDO broadly does not have the resources (human or capital) to invest directly in infrastructure other than the support it gives to the energy sector. However, the UK has considerable expertise (across HMG and private sector) at the early stages of the project/programme cycle (pre-feasibility, feasibility, design and publication), project financing, supervision and in the development and application of cost-effective delivery tools such as BIM, to offer Ukraine in its reconstruction.
[note] BIM – building information modelling

Damage to Ukraine’s infrastructure is immense following the full-scale invasion in February 2022. Estimates for reconstruction and recovery are such that over USD 520 billion will be needed in the coming decade, for recovery, including housing, energy, transport, water and wastewater, schools and hospitals.
[note] Rapid Damage and Needs Assessment 4 (March 2025) – GoU, World Bank, EU and UN.

To be ready for reconstruction, Ukraine needs to build its systems and capacity for project identification, appraisal and approval, design and delivery, and have a pipeline of well prepared “bankable” projects which satisfy EU accession standards including addressing climate change, environment, inclusion and accessibility.

The FIRE Business Case (BC) was designed and evolved based on dialogue with Ministry for Development of Communities and Territories (MDCT) and the State Agency for Restoration and Development of Infrastructure (SARDI). It also followed initial exploratory activities for project preparation methodology by NISTA supported by FCDO Ukraine’s Good Governance Fund programme - recognising the link between better infrastructure governance and transparency and value for money. Similarly, appetite of GoU for BIM was tested with support from the UK Government Department for Business and Trade (DBT) - recognising DBTs leadership in digital construction internationally). The programme was also designed with built in flexibility to respond to emerging needs, recognising the dynamic and unpredictable context and framed around three outcome areas: .
[note] NISTA = National infrastructure and services transformation agency – formerly the Infrastructure and Projects Authority (IPA).

1. The acceptance of the 5CM by GoU and wider donor community as standard methodology for all infrastructure project BC development at national level including demonstrator projects.
2. Adoption of the BIM standard approach by GoU with GoU ready to procure and deliver projects through BIM.
3. Creation of project preparation facilities to increase the number of bankable projects, which was added after approval of the programme.
The business case was intentionally designed to be of short duration, and to be the pre-cursor/design phase for a potential multi-year infrastructure business case. This has allowed time to: build the relationship with GoU, understand the context and priorities, and give evidence on what has worked/not worked including progress towards outcomes and the delivery arrangements.
Summary supporting narrative for the overall score in this review
This annual review gives the overall programme an A rating which is fully justified using the output scoring methodology set out in PrOF but also in terms of the implementation providing both the space and learning to consider the framing of a multi-year business case. Work on a new theory of change for the new business case is on-going and a draft is now ready for consultation and discussion. This review gives a good level of confidence that outputs are leading towards the outcomes and have performed well which in part is due to alignment with GoU priorities and objectives.

It was never expected that outcomes would be fully achieved within the first year of implementation, and at this stage it is still too early to make any significant measure of impact, but there are some positive signs of potential impact, and it is acknowledged that this area will require further work. For example, the MDCT requested the programme to support them in the development of a water supply business case based on the 5CM methodology, to showcase at the URC 2023, opening up conversations with investors. Feedback on the 5CM trainees has also been positive, with many reporting that the training has been helpful in the development of concept notes. Similarly, feedback on BIM has included participants gaining a wider understanding of how their organisation delivers projects and how this can be improved.

Key achievements of FIRE are:
- Legislation developed and adopted by the GoU which strongly mirrors the UK 5CM (referred to as Ukrainian Methodology.) This legislation requires that all major infrastructure/reconstruction projects for inclusion in the single project pipeline (SPP) has to be developed consistent with the methodology.
- Training of over 600 officials (including Deputy Ministers) in the 5CM. and the establishment of a community of practice for further learning and skill development through application.
- Providing shortened training of 5CM to reach nearly 500 officials from the 24 Oblasts including Kyiv aimed at a (more) even recovery.
- Two demonstrator projects underway using the 5CM methodology, one of which was showcased at URC by MDCT and is now attracting interest from potential investors.
- The establishment of a digital construction office in SARDI, including the development of Business Information Modelling (BIM) toolkits, templates and guides, training and workshop materials, and training of 104 officials towards the development of the SARDI BIM Strategy.
- Design and mobilisation of the GoU led/WB supported project preparation facility, and the wider coordination and governance frameworks which will enable multiple project preparation facilities to operate in a coordinated manner in Ukraine. Technical support consultant in place to support MoE staff. Three projects under first stages of project preparation.

The scoring process does not in itself capture the challenges and lessons learned through implementation processes and relationship building. Recognising that an important feature of this business case was to provide space and evidence to design a well-targeted multi-year business case, these are considered in lessons and recommendations section below.

Major lessons and recommendations for the year ahead/future BC

This programme has faced challenges both challenges and opportunities throughout this period. The first challenge was the dismissal of leaders in both the MDCT and SARDI, with posts remaining unfilled between June 2024 and November 2024. This necessitated renewed advocacy to explain the programme and achieve buy in, once new leaders were appointed. It also meant that a key ministry was not represented at the start of the PPF discussions, which caused some tension, which is now being worked through the various consultative groups led by the MoE.

The programme has benefitted from starting at the same time as public investment management reforms ramped up. There is a strong fit with improving project preparation, and resulted in the rapid move to legislate for a methodology based on the 5CM. This has also stimulated demand for the different types of training that the programme has been able to offer.

Although, the programme has been successful in terms of outputs delivered. How these have been delivered can be improved. Changes have been made throughout the implementation period to get the GCIEP consortium to take more of a leadership role across the programme, particularly with regard to the 5CM and BIM components and a new operating model which would work for the new business case is proposed. This will relieve some of the transaction burden on the SRO allowing them to take a more strategic role and input to the wider PIM reform dialogue.

Recommendations have been incorporated into the body of this report, but the following major lessons and recommendations, especially with regard to the development of a multi-year business case can be summarised as follows:
- Revise the theory of change for the multi-year business case. Having tested appetite for the methodologies and tools, demand for training, it will be important for the new BC to focus on application and impact. The real impact of this work will be on improved VfM in infrastructure, necessary for Ukraine which is already under severe budget constraints and facing the biggest reconstruction challenge since World War II. (ToC consultation due to start end of October 2025).
- Agree and finalise the programme delivery arrangements with all implementing partners, including arrangements for monitoring and reporting on the PPF for new business case. (by mid November 2025.)
- Agree and finalise oversight and monitoring arrangements for BE Kyiv in the period from December to March 2025 in the event of infrastructure adviser gaps. (By mid December 2025)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Figure 1 - FIRE TOC
The ToC (Figure 1) developed for FIRE followed the logic that “IF the 5CM Methodology is accepted by GoU and the wider donor community AND GoU is ready to procure and deliver projects through BIM THEN, methodologies for reconstruction project preparation will align with public investment management, ready for wider roll-out and delivery through digital construction methodologies.”

The logic underpinning the ToC has broadly held during the review period because GoU has embraced the need to reform systems and methodologies for reconstruction, as shown by progress on overall PIM reform process. GoU is incentivised by the need to gain confidence of investors (IFIs, donors, private sector) to finance critical projects, and therefore has been keen to comply with international best practice, including for transparency, cost-effectiveness, standards for EU accession, and requirements of funders etc. Both BIM and the 5CM help to achieve this at different points in the infrastructure project cycle.

There is room for improvement in the ToC, taking into account developments in recovery and reconstruction context, other interventions and how these lead to outcomes. For example, the ToC focuses mainly on the 5CM and BIM workstreams, but not outputs from the PPF workstream, as this was included after original BC approval under the FCDO-funded technical expertise output (Figure 1). The ToC also does not capture timeframes to implement different outputs, for example the 5CM workstream progressed rapidly, with GoU drafting legislation to mandate its use of the ‘Ukrainian Methodology’, while BIM has moved more slowly (see Section C, Output 2). Although outputs have been achieved, further time and effort is needed for full adoption and establishment of BIM. The PPF workstream, though not explicit in the ToC, has expanded significantly to include a governance framework for coordinating emerging PPFs.

The excellent progress on the 5CM model was due to a combination of factors including, strong in-country advocacy coinciding with wider PIM reform, being able to adapt to GoU priorities and supported by the provision of quality training accredited by APMG, the UK’s professional certification body. This suggests that any successor programme needs to be strongly based on GoU priorities, having enough resource to support implementation, all while, preferably, maintaining some flexibility/adaptability to changes needed in such a dynamic context.

The overall assessment of the ToC is that it has served its purpose for this project and set a good direction of travel for the interventions under FIRE but requires revision to better describe the multi-year infrastructure BC. (Recommendation 1). It is envisaged that the revised impact statement should focus more on tangible results of the number of bankable infrastructure projects prepared and implemented, to support Ukraine’s socio-economic recovery, while achieving international best practice standards, the linkage with PIM reforms and improving VfM in recovery.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome 1 is on track – adoption of the Ukrainian project preparation methodology (based on the 5CM) has been successful. The commitment to adopt the methodology was demonstrated by new government legislation and a decree from the Cabinet of Ministers dated 28 Feb 2025, which mandated that all projects for the SPP should be prepared using the methodology. This was captured as an achievement under the PIM action roadmap – Objective 3.
[note] PIM Action Road Map Objective 3 – Creation of a methodological framework for PIM. (Procedure for the preparation of public investment projects requiring budget finance).

The programme has exceeded its goals for 5CM training provision and capacity building, and whilst in early stages, it has started applying the 5CM approach to two demonstrator projects and started work on adapting the training to the Ukrainian Methodology. Demand for the training has been higher than expected/more targeted due to GoU’s fast adoption and mandate to use the methodology. It is therefore envisaged that UK expertise will continue to be needed and valued, to support the development of guidelines for investment/infrastructure projects, adapting and continuing training to the Ukraine methodology (but aiming to localise this through the NAUCS for scale-up and sustainability), and applying learning from the demonstration projects underway, for evidence-based improvements of the methodology.

The PPF is now ready to begin preparing projects and given GoU ownership and their adoption of the Ukrainian project preparation methodology, the delivery partners responsible for output 1 will liaise with the PPF to target training demands and provide support.

Outcome 2 is on track; GoU is keen to adopt the technology and established the digital construction office needed to drive the transformational change and build capacity, but it will need to work through pilot projects to start building up capability. It should be recognised that BIM is a tool that is more applicable and useful in the design, procurement, implementation, and operational stages of the infrastructure project cycle. It therefore does not fit as easily with the impact statement as worded in Figure 1, but there is still high optimism, which given the high appetite of SARDI to apply BIM effectively, that BIM would be a significant ingredient for efficient and effective delivery in the reconstruction effort.

The approach to date has been to provide rapid short-term response to GoU requests for infrastructure capacity building, but to use this to build understanding of the sector and institutions before entering a longer multi-year commitment. All three outputs have laid solid foundations for infrastructure preparation and delivery, and the UK’s efforts are valued by GoU, so the main action in the year ahead will be to decide on a multi-year BC.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
This programme has made significant progress across all three outputs and continues to represent good VfM reflected in the A assessment. FIRE was designed as a short-term intervention to understand reconstruction and GoU priorities better, ahead of a future programme. This programme plays a strong role in the 100-year partnership pillars 4 and 5, it works with and links to other departments across HMG including DBT and Cabinet Office and provides the secondary benefits of competitive business opportunities for UK private sector in the project preparation stage of the infrastructure project cycle. It is therefore recommended that the multi-year business case is developed, which will enable the activities under all three outputs to continue, with stronger programme direction in Ukraine, building GoU’s ownership and leadership of the interventions, and making use of local institutions for training to increase sustainability. (Recommendation 2.)

## C. DETAILED OUTPUT SCORING

Output Title	Staff trained in the 5CM methodology and methodology adapted for use in Ukraine including alignment with DREAM – PIM system and reforms.
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review- August 2025	Progress
1.1 Demand-led support provided to DREAM in development of project and programme guidelines.	Review of DREAM guidelines when published / Demand-led follow-up workshops (up to 2) with DREAM on topics they selected with positive feedback by DREAM	Exceeding expectations: The adoption of 5CM in Ukrainian practice and legislation led to a need for guidelines on its application to the DREAM digital pipeline. Guidelines are now written and undergoing internal review by GoU. DREAM has structured their database so that information submitted is generally compliant with the relevant order and the 5CM. A qualitative assessment is planned when the guidelines are finalised. / The team has established a strong working relationship to support DREAM resulting in five workshops (including 5CM overview, project vs programme, economic appraisal), which were well-received with positive feedback from DREAM.
1.2 Number of training units completed by officials with pass rate at 85% or over vs total number of training units given.	400 trained and certified and training materials adapted to Ukrainian methodology / Training programme submitted to NAUCS and approved / 5CM training reviewed in line with Ukrainian methodology	Exceeded expectations. / 609 trained (48.6% women). 557 certified with a pass rate of 87% (47.4% women). (Higher demand than expected led to use of hybrid courses to accommodate more people per training.) / The training programme was submitted to NAUCS. A working group consisting of the key ministries was created and we expect the programme to be approved by the end of July 2026. / The programme responded to a request from GoU to support regional capacity, increasing the reach of the programme - a short two-day training for concept notes was developed for regional officials and successfully delivered to 456 officials from 24 Oblasts including Kyiv City. / The adaptation of the 5CM training to the Ukrainian methodology is underway and will be finalised by end 2025.
1.3 Learning of application of single Ukrainian methodology in demonstrator projects contributes to GCIEP stakeholder decisions, planning, and capacities (GoU, project initiators, donors, IFIs, FCDO)	Demonstrator 1 implementation: presentation delivered at URC; project document in production for SPP submission / Demonstrator 2 implementation: project document in production / Possible Demonstrator 3 identification: engagement to identify and confirm final demonstrator (resource dependent)	Slightly below expectations. Two demonstrator projects jointly chosen with MDCT to showcase 5CM approach. / Truskavets Water Supply Project was presented at URC 2025 to generate financing interest. GCIEP developed the economic, financial and management cases for this, and DBT and GCIEP have received enquiries for information. Following completion of the business case, MDCT aims to include the project in the SPP with the ultimate aim that it will be followed up by a PPF for full preparation. / A combined heating plant project in Chernihiv was identified in cooperation with EBRD. As of mid-July, GCIEP are awaiting the technical documentation from EBRD to begin implementation. Technical partners (AFRY) have been identified to support the work. / If work progresses as planned with the two demonstrator projects, GCIEP does not currently anticipate beginning work on a third given existing resource constraints.
1.4 Learning of capacity assessment of selected institutions contributes to GCIEP stakeholder decisions, planning, and insights (GoU, IE, donors, IFIs, FCDO)	10 institutions selected for assessment and agreement from donors (June) / Implementation underway (July-Sept)	Slightly below expectations - Slight delays due to IFI discussions and GoU consultations, impacting the start of the project. But acceptable within the timeframe of project preparation to implementation stages. Work has started and findings to be delivered in time for Ukraine Donor Platform meeting in autumn 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output was delivered by both the Green Cities, Infrastructure and Energy programme (GCIEP - consortium led by PWC contracted under the FCDO Centres of Expertise) and NISTA. Two indicators have exceeded expectations with one achieving expectation and one falling slightly short. This output is therefore assessed as A+.

Progress on the 5CM based methodology has been much faster than anticipated at the outset, partly due to how it linked and supported milestones under the PIM reform action plan, but also because of GoU recognising the need for a methodology which met international standards of good practice and single approach for all infrastructure projects. UK expertise through NISTA, especially at the early stages, was extremely important in gaining traction for GoU to move forward on legislation.

Key achievements and events in this period include:
- Ukraine PM issuing Cabinet Decree 903 (August 2024) mandating the use of a concept note, based on 5CM designed by the UK team, for all projects to be considered for state funding. This resulted in over 750 infrastructure projects registered to the DREAM single project pipeline (although further work is needed on prioritisation).
- Additional legislation passed in February 2025 (Order 527, 2025) which requires all projects to use the 5CM to take their projects through the project cycle, from concept to pre-feasibility and full feasibility to completion.
- Training demand outstrips supply, with positive feedback, and majority of participants (518) wanting further training (e.g. foundation to practitioner, and targeted training such as economic and social appraisals.
- Two-day training developed and held for 465 regional officials representing 23 oblasts and Kyiv City, to enable them to submit compliant concept notes to DREAM.
- Support to DREAM on detailed guidance to sit alongside Order 527.
- Establishment of a community of practice/network for trained officials.
- Two demonstrator projects identified and in progress, with a third alternative.
- Progress on embedding the methodology in the software and operating system of DREAM.
- Flexible ad hoc technical assistance to SPILNO (the leading PPP Advisory in Ukraine) on cost-benefit analysis and further work with PPU on project prioritisation in progress.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Initially, the plan was to promote a unified project preparation method (5CM) GoU, including training and demonstrator projects. However, GoU moved faster than expected, passing legislation to mandate the 5CM and adapting it into a Ukrainian methodology. Aligning this with DREAM has required more effort but has helped grow the community and practice around it. A new activity this year is an implementation readiness assessment for the IFI PPF group, aimed at identifying and addressing capacity gaps in reconstruction. A major change was the sudden halt of USAID activities, which had supported both MDCT and SARDI and aligned with UK goals. To fill the gap, the Ukraine team for output 1 has been expanded to strengthen stakeholder outreach and support demonstrator projects, as reflected in the updated business case.

Lessons learned this year and recommendations for the year ahead
While partnering with GCIEP and NISTA was effective in initiating training and raising awareness of the 5CM, reliance on international partners for delivery and accreditation is not sustainable in the long term. Identifying and transitioning to a capable local partner—such as NAUCS—ensures continuity, builds local ownership, and strengthens institutional capacity for future programme delivery.

Recommendation 3. Complete process with NAUCS to design an effective programme to transfer training on project preparation methodology while maintaining international best practice standards and quality of delivery, including mainstreaming of gender equality, disability and social inclusion and climate and net zero.

Grounding programme methodologies in established PIM principles and aligning them with GoU Ministries enhances relevance, credibility, and institutional buy-in, which are critical for effective implementation and long-term sustainability. However, further outreach is required to ensure that GoU moves towards the consistent application of a single methodology, including through donor funded projects. Recommendation 4. Continue to extend outreach and information on the methodology to other stakeholders to scale-up application of the methodology including IFIs, donors, and possibly private sector engaged in project preparation.

Output Title	Establishment of BIM / digital construction in SARDI. / (Edited version – for full version see Annex A)
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review – August 2025	Progress
2.1. Stakeholder relationships (#stakeholders - by level, organisation including gender, #of agreements /arrangements.	8 stakeholders across priority stakeholder groups both at senior and management/operational levels. / Revised agreement between UK and GoU.	Meeting Expectations: 8 stakeholders (6 male/2 female) actively engaged across senior/strategic management and technical expertise levels including stakeholders from SARDI (national and regional levels), National Institute for the Development of Infrastructure, Obukhiv City, Eurasia Foundation. / Letter of collaboration agreed between SARDI and UK following change in leadership at SARDI, to reset the programme.
2.2 Assessment Products (e.g. reports, meeting notes, diagrams, guidance) by organisation.	30 Assessment products	Meeting expectations: 30 Assessment products produced to define current status of SARDI, BIM ambitions, existing operations, and systems/ways of working in SARDI.
2.3 Transformation outputs and BIM knowledge products.	40 outputs and knowledge products	Meeting expectations: 19 baseline BIM toolkit templates and guides provided to SARD and 21 training and workshop materials developed and/or localised. These output and knowledge products are key for change and further capacity building as the programme moves forward.
2.4 #training units completed (sessions x participants) / #capacity building summary reports.	190 participants	Below expectations: / 104 participants (65 male/39 female), six units completed (five strategy workshops delivered, to develop the strategy to introduce BIM. The strategy will be used to set up a detailed implementation plan for DCO and the UK teams.

Briefly describe the output’s activities and provide supporting narrative for the score.
The establishment of BIM in SARDI is an ambitious project with potentially high dividends for SARDI and the overall reconstruction effort, but from the outset expectations, ambitions and understanding of what BIM is, what it can do, and more importantly how to get there have varied widely amongst stakeholders. The programme aims for BIM adoption by MDCT and SARDI and therefore is set up to apply at national, organisational and project levels. It does this through four workstreams:
1. Build and maintain relationships with trust and commitment to enable multi-year collaboration.
2. Get a shared understanding of the local context, how SARDI works, BIM ambition and the stages to getting there.
3. Set up a collaborative framework to support the BIM transformation and delivery (through the use of pilot projects.)
4. Develop capacity for the change process, project delivery and asset management.
The output indicators in the first year of BIM reflect these workstreams. The output has been judged as just below expectations (B), as one indicator regarding the quantity of training delivered fell short of target, due to changeover in MDCT and SARDI leadership in 2024 plus significant staffing and capacity gaps in SARDI and exacerbated by suspension of USAID funding. This target is likely to be met and exceeded soon, due to the plan to move the training to a digital platform, with greater accessibility and reach.

Key achievements in the review period include:
- The establishment of a dedicated DCO within SARDI, embedded consultants contracted through Connecting Places Catapult (CPC) but managed by and reporting to SARDI.
- Agreement by SARDI to collaborate with the UK team, providing the necessary information resources and access to key stakeholders and staff.
- Recognition by the head of SARDI that establishing BIM as a key tool for reconstruction aligns well with his agency’s mission and objectives.
- Senior level SARDI staff participation to the series of 5 workshops across 6 weeks with positive feedback from participants.
- Identification of a pilot project (Obukhiv Social Housing Project) as a demonstrator for BIM.
- SARDI’s BIM implementation plan progressing well, due to be finalised in September 2025.
Less visible but equally important achievements include:
- Analysis of SARDI systems and processes.
- Identification of opportunities to optimize the activities of the agency beyond BIM. (e.g. improving the efficiency (delivery times) and value (quality/cost) of restoration projects (use of standardized/replicable designs, centralization of procurement and project management, quality build, whole-life operation costs and carbon reduction, modernization to international standards, supply chain innovation and delivery methods, resilience of infrastructure solutions).
- Creation of knowledge projects (BIM toolkits guides, training materials etc.) in Ukrainian for further development and adaptation, as required.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following the leadership change at SARDI, the approach to introducing BIM shifted to a “learning by doing” method, prompting the early integration of a pilot project. Due to staffing constraints, SARDI could not fulfil a prior commitment to staff the DCO internally, so CPCUK hired consultants for 11 months to support the transformation. Budget adjustments allowed this without extra cost to the FIRE programme. The Head of SARDI has since praised the programme’s impact on institutional capacity and committed additional support for BIM coordination. These updates were included in the February 2025 business case addendum and will inform future planning.

Lessons learned this year and recommendations for the year ahead
While this year has focussed on getting the DCO established in SARDI, and ensuring that the agreement (and necessary inputs by SARDI) is in place and fully understood, the programme next year will need to (bullet points - Recommendation 5)
- Deepen its engagement with national level stakeholders (e.g. MDCT.) to ensure policy and practice keep pace and align. Including standards, guidance, and legislation.
- Build SARDI institutional capacity for using BIM in its projects.
- Provide capacity building and technical assistance for the introduction of BIM (based on international standards – ISO 19650) on SARDI’s first pilot project.
- Strengthen programme communications to build mutual understanding, manage expectations, make training options available to wider audience etc.
From experience over the review period, and by comparison to output 1 which has benefited from having more Ukraine level leadership, it is also recommended that the leadership of BIM in Ukraine by the implementers is increased. (See management section – recommendation 7.)

Output Title	Projects prepared through the World Bank PPF
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress August 2025
3.1 PPF established and preparing projects to bankable status.	PPF established and preparing projects to bankable status. (implementation and finance ready.)	PPF established and working on 2 hospitals and one road pre-feasibility study.
	Expenditure of funds.	£400k design funds fully expended.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has been scored A+ as originally FCDO agreed to support WB in the design of the GoU led PPF over a period of 6 months only. This work however expanded with WB using additional staff time at their own cost to support the GoU in developing the project preparation facilities framework. This framework sets out the governance/coordination arrangements to enable multiple project preparation facilities to operate in Ukraine, aligned to GoU priorities set out in a single project pipeline. , A BC addendum was approved in February 2025 which included funding to ensure that the UK could contribute to the PPF as it becomes operational. Initial projects for the PPF were announced at URC 2025 including hospitals and roads to be considered for feasibility and pre-feasibility studies, respectively.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The two main changes in this period are: the work to support the GoU on developing the project preparation facilities framework, which links closely to PIM reforms and also output 1. And the need to make CDEL available for the WB/GoU PPF to become operational through a BC addendum.

The single project pipeline and the PIM reform process are an important workstream requiring significant input from FCDO and UK as a leading donor will participate in this through the consultative group and the Ukraine Donor Platform expert group.

Lessons learned this year and recommendations for the year ahead
This component of the BC has given strong insight into the complexities of donor coordination, prioritisation, and challenges in both the institutional and policy and legal frameworks associated with construction of both publicly funded and PPP infrastructure. FCDO commissioned a complementary piece of work on this through a political economy analysis (PEA) of infrastructure decision making through the Good Governance Fund, to build further understanding of the sector. Reflecting on this in the review, the roles of key stakeholders responsible for prioritising and evaluating infrastructure projects still needs improvement, and results of these processes require evidence-based validation. This PEA will be useful for feeding into the new ToC.

This output has a strong link to output 1 on further development of the methodology for project preparation. Particularly in ensuring that the PPF applies the methodology to remain consistent with the overall GoU effort towards a single project preparation methodology. It is therefore recommended that output 1 team continue to communicate and if necessary, provide training to both PPF staff, and PPF beneficiaries on the application of the methodology to increase uptake and improve the quality of project preparation. (Recommendation 6)

## D: VALUE FOR MONEY

Key cost drivers and performance
To date this BC has been a technical assistance programme so key cost drivers are fee rates and team sizes. Performance is monitored and assessed through separate weekly governance meetings for components 1 and 2, while output 3 – design-completion of the PPF has been an output-based assessment. In the coming year component 3 will start to deliver project preparation introducing a CDEL component – which is envisaged as being assessed through outputs/outcomes.

VfM performance compared to the original VfM proposition in the business case.

Economy - The Business Case (BC) aimed to ensure economic delivery by leveraging existing framework agreements. For Output 1, delivery partners—NISTA and the PwC consortium—were sourced through the Green Cities and Infrastructure (GCI) Centre of Expertise (CoE). The PwC consortium, selected via open competition by HQ, brings the necessary expertise at competitive rates and includes a high proportion of in-country staff, enhancing local relevance and cost efficiency. The team structure was defined through a Terms of Reference and inception report, which evolved into a fully resourced and budgeted workplan. Additionally, CPC was contracted via a grant letter from DBT, with resource rates set on a non-commercial basis, covering only project costs and excluding profit margins. The grant to the WB was given on the basis of staff inputs required to design the PPF.

Efficiency - Efficiency gains were demonstrated through the early adoption of the 5CM methodology by the Government of Ukraine (GoU), which supports infrastructure promoters in evaluating issues and options at the initial stages of the project cycle. While training has been well received, the programme is still in its early implementation phase, making it premature to fully assess efficiency outcomes. Similarly, Building Information Modelling (BIM)—which enhances efficiency across design, implementation, and operations—is yet to be evaluated, though the commitment to its adoption is promising. Operationally, improving collaboration between PwC GCIEP alliance and NISTA has made delivery more efficient. This can be further improved for the future BC. BIM was less efficient due to delays in the mobilisation phase, although these delays have now been resolved. WB PPF design was implemented as planned and on time and is therefore considered to be efficient compared to out-sourcing which would have taken longer but costing similar.

Effectiveness - Although full effectiveness cannot yet be measured due to the early stage of implementation, several foundational elements are in place. The adoption of the 5CM methodology and BIM indicates strong potential for long-term effectiveness in infrastructure planning and delivery. The partnerships and collaborative structures established—particularly between PwC, NISTA, CPC, and DBT—are designed to support effective execution. The tailored design of the PPF by the World Bank team also reflects a strategic approach to ensuring effectiveness in project preparation, avoiding delays, and ensuring alignment with programme goals.

Equity - Equity and inclusion are being addressed primarily at the project preparation stage. While it is too early to demonstrate tangible outcomes, Gender Equality, Disability, and Social Inclusion (GEDSI) principles have been embedded in the Ukrainian Methodology training. This is vital not only for inclusive project outcomes but also for meeting EU accession standards. Promoting a unified project preparation methodology across all regions of Ukraine is essential to ensuring equitable development opportunities. Women are notably well represented in both programme implementation and as beneficiaries. For instance, women make up 75% of the Digital Construction Office staff, and 48.6% of the 609 individuals trained by GCIEP between April 2024 and June 2025 were women.

Assessment of whether the programme continues to represent value for money.
This programme continues to demonstrate value for money when assessed through the lens of the 5E’s framework. However, since the primary goals and impacts—namely, the successful delivery of infrastructure projects—may take several years to materialize, it is important to place greater emphasis on evaluating the 5E’s during the interim stages. This will help ensure ongoing accountability and effectiveness throughout the journey toward long-term outcomes in future activities.

## E: RISK

Overview of risk management
The overall risk rating for this programme is assessed as “moderate”. This is within the overall risk appetite for the programme which is cautious. Risk appetite by category is set out in the table below which reflects the complex and dynamic environment in Ukraine.

FIRE Overall Risk App.	Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	People	Financial Fiduciary	Reputational	Safeguarding
Cautious	Eager	Eager	Cautious	Cautious	Cautious	Cautious	Cautious

The programme maintained its strong approach to risk management. Risks have been monitored and updated on a quarterly basis. A central risk register was maintained and focused on a sensible selection of risks, with targeted mitigation measures reviewed quarterly. Implementing partners also provided their own risk assessments and registers in their regular reporting and highlighted potential adaptations in response to risks identified.

Top risks monitored and mitigated include:
- Programme delivery: insufficient resources to deliver and increasing demands of UK programming. This risk was mitigated by requesting PwC and NISTA to engage more collaboratively and refining the work plan to reflect this. More work in this area is needed in designing the management case for the future BC see recommendation.
- Declining conditions and impact on GoU capacity to engage: this risk was partly realised following the government reshuffle of September 2024 and resulting new appointments of Head of SARDI, Minister/Deputy Ministers for Development of Communities and Territories but mitigated though robust engagement at HMA, Development Director and working levels.
- Linked to the above, GoU is disincentivised to make required reforms: mitigated by maintaining strong working relationships and open communication with implementing partners.
Following the US Aid withdrawal, the team gave due consideration to the adverse effect on our programming. For example, the US embedded advisers were able to act as advocates for the programme activities. On withdrawal greater inputs were made by FCDO and partners to cover this function. Over the review period FCDO has worked with the main partners GCIEP, NISTA and CPC to ensure that work plans are developed and more detailed so that new risks are being addressed.

While the programme has focussed on risks related to output delivery, the risk of FCDO having sufficient staff to deliver this programme is significant. Infrastructure advisers are a small cadre of people in the organisation and the post may be difficult to replace. This risk should be upgraded from moderate to major.

Key trends in risk exposure remained in the area of programme delivery, related to the ability of BEK, GoU and implementing partners to navigate a complex environment with multiple stakeholders and conflicting incentives. A prominent risk affecting programme delivery was high turnover of senior leadership in Ministry of Economy, Ministry for Development of Communities and Territories, and the State Agency for Reconstruction and Development of Infrastructure.

Due Diligence Assessment of the World Bank Ukraine Recovery Trust Fund was completed in September 2024 prior to the disbursement of funds. The relevant due diligence assessments for GCIEP and NISTA (formerly IPA) were conducted by the programme team leading the Green Cities and Infrastructure Centre of Expertise in FCDO. Similarly, the due diligence assessment of Connecting Places Catapult was conducted by DBT under their Digital Construction International programme (DCIP) into which FCDO contributed funds.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
While all partners have delivered effectively from both commercial and financial perspectives, the programme's delivery arrangements remain complex and overly dependent on the SRO and PRO. These roles are currently responsible for coordinating activities, engaging with government, IFI, and donor stakeholders, and maintaining the strategic direction of the programme. Given the constraints of not having strong country partner presence for all components or fulltime FCDO staff this has been sub-optimal. A key recommendation from this review is to collaborate with partners to strengthen the management/delivery arrangements by appointing a lead management agent with a presence in Kyiv. This agent would oversee and coordinate delivery primarily for Outputs 1 and 2, and to a lesser extent for Output 3, which will continue to require contributions from the British Embassy in Kyiv. This revised structure should be clearly defined and incorporated into the management section of the future Business Case. (Recommendation 7).

The following arrangements in place for delivery of this programme:
- Output 1 – FCDO have an MOU in place for IPA/NISTA; and a separate contract in place for GCIEP. (Both of these are held by HQ as part of the Centre of Expertise government partners and supplier arrangements.)
- Output 2 – FCDO have signed an MOU with DBT in order to buy into their existing GCIP programme, under which there is a contract with CPC and its downstream partner Gleeds to deliver output 2.
- Output 3 – FCDO signed an administrative agreement with the World Bank in September 2024 to disburse our first tranche of funding (£400,000.00) to the Ukraine Recovery Trust Fund for the design costs of the Project Preparation Facility. This administrative agreement can be amended to increase funding for future years by a simple addendum letter following the relevant approvals.
Partner narrative reporting was timely and detailed. However, financial reporting on output 2 indicates a slow burn rate for the project with delivery delays resulting in a decrease to their forecast by nearly £1m, and accruals reconciled with some delay. Going forward, the programme team aims to monitor the burn rate more closely and understand its root causes. This issue may also be helped by moving the output 2 workstream under a lead managing agent with output1 (see recommendation 7) as this would enforce commercial accountability, ensure clearer oversight of spend and allow reprofiling between multiple components.

## G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Output 1, implemented by GCIEP and NISTA has the following monitoring activities in place:
- Training Evaluation: Pre- and post-training assessments gauge relevance, quality, and participant roles, with data disaggregated by gender and disability. GCIEP attends NISTA-led sessions to ensure coherence.
- Demonstrator Workstream Oversight: Closely monitored to assess the Ukrainian Methodology’s effectiveness in project preparation.
- External Validation: GCIEP’s training programme is submitted to NAUCS for evaluation to confirm its suitability for civil servant training.
- Stakeholder Engagement: Ongoing collaboration with key beneficiaries including DREAM, MoD, SARDI, FCDO, and others.
Output 2 - implemented by CPC have the following monitoring activities in place:
- Strategic Oversight: A Theory of Change and M&E plan guide tracking of project effectiveness, outputs, outcomes, and early impacts of digital construction adoption in Ukraine.
- Workshop Evaluation: Feedback and assessments collected from sessions on BIM standards, institutional capacity building, and strategic planning.
- Performance Tracking: Consistent monitoring of progress against Logframe indicators, with findings summarised in monthly reports.
Output 3 - implemented by the World Bank and others was monitored continuously through a combination of meetings with focus on a final design of the WB/GoU PPF and the Project Preparation Facilities Framework.
Evidence
Evidence for the success of output 1, has been the speed at which the GoU have embraced the methodology and issued decrees/legislation and an increased demand beyond initial expectations for training in the methodology from a wide range of participants and central government requests.

For output 2 – the main evidence for the successful introduction of BIM is the feedback and progress from the workshops held, the increase in knowledge and understanding of what and how BIM can be introduced, and progress made on the development of SARDI’s BIM implementation strategy.

On output 3 - The design of the PPF and the framework for coordination and routing of projects to the various PPFs resulted in projects being announced at URC2025, and a technical services consultant being appointed to support the WB/GoU PPF. This means that the PPF is now ready to begin preparing the first projects, while the further work is done on the prioritisation of projects of national, regional, and strategic importance.

Learning
This programme has been a process of building up knowledge, understanding and relationships from a limited evidence base. Approach to learning has therefore been more through implementation discussion and where needed adaptation, focussing more on what is needed for project delivery than on outward dissemination. The programme to date has given lessons, on what has worked in terms of the methodology and the introduction of BIM which are now being shared with a wider audience – through the green cities and infrastructure CoE and its learning events, and with plans for further dissemination at the FCDO Climate Environment, Infrastructure and Energy cadre conference in September 2025.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A