## Annual Review

Title: Accelerating Education Attainment for Resilience in Central Asia (AEAR-CA) Programme
Programme Value £ (full life): £5 million (over three-years)		Review date: July 2025
Programme Code: 400217	AMP start date: 06/08/2024	AMP end date: 30/06/2027

Summary of Programme Performance
Year	2024/2025
Overall Output Score	A+
Risk Rating	Moderate

DevTracker Link to Business Case:	D0006221.odt
DevTracker Link to results framework:	D0007071.xlsx

A. SUMMARY AND OVERVIEW

The Accelerating Education Attainment in Central Asia for Resilience (AEAR-CA) programme is a three-year, £5 million UK initiative aiming to foster security, prosperity, and socio-economic development in Central Asia by improving education quality and English language proficiency.
The programme seeks to address low English language proficiency, teacher competency gaps, and educational inequality, particularly for marginalised groups in rural areas, by strengthening teacher training, improving quality assurance systems, and fostering links with UK higher education. It positions the UK as a key partner for regional development, aiming to boost economic growth and offer a counterbalance to other influences.

The programme is delivered through a range of implementing partners including the British Council, UNICEF, Aga Khan Foundation, and VSO. FCDO manages the programme with a flexible, adaptive approach, which included a one-year pilot phase, robust Value for Money (VfM) oversight, and a cautious appetite for financial and safeguarding risks.

Programme support complemented the UK’s existing educational engagement in the region, including through the Global Partnership for Education (GPE) and Chevening scholarships. It also contributed to UK soft power in the region through engagement with governments and partners on their objectives around growing English language capability, as well as ensuring all education is of a high standard and inclusive.

Through English language training, the UK is investing in human capital across Central Asia, contributing to improved economic development opportunities whilst growing UK-Central Asia economic and cultural partnerships. Programme interventions will contribute to evidence and learning about how education, including English language skills, could be an enabler for economic and social development.

The first year of the programme was delivered efficiently and effectively. Programme results include:

- In Kazakhstan - through British Council, 20 ELT (English language teaching) trainers were trained and five new courses produced in close partnership with the ‘Orleu’ Centre for Continued Professional Development for teachers. Additionally, a handbook for ELT course designers was developed by Norwich Institute of Language Development (NILE) and was translated into Kazakh and Russian by the National Consultants to benefit all trainers working with ‘Orleu’.
- In Kyrgyzstan - through UNICEF, funding of the printing and distribution of over 150,000 English textbooks for Grade 4 pupils, as a contribution to better teaching and learning materials and school reform, laying the foundations for longer term economic growth, benefitting both Central Asia and the UK as our partnerships continue to grow.
- In Tajikistan (and Kyrgyzstan) – through Aga Khan Foundation (AKF), 260 teachers and 255 education-sector civil servants (155 in Tajikistan and 100 in Kyrgyzstan) completed English language training.
- In Uzbekistan - through British Council support, the project developed and introduced a national 100-hour Continuing Professional Development (CPD) and teaching skills induction programme for all subject teachers and a 48-hour CPD day induction programme for English teachers.
Summary supporting narrative for the overall score in this review

The AEAR-CA programme has demonstrated a strong performance in its initial year, achieving an overall score of A+, with most outputs moderately exceeding expectations and one meeting expectations.

The programme's strong performance is attributed to its effective design and implementation, which demonstrated robust Value for Money (VfM) across the principles of Economy, Efficiency, Effectiveness, and Equity. Notable efficiencies included leveraging existing UNICEF platforms and creating analytical products including a regional Situational Analysis and Political Economy Analysis (PEA), which supported a better understanding of the context avoided duplicative work. The programme's effectiveness is evident as all planned outputs were achieved, with analytical reports already informing policy and subsequent programming phases, and the establishment of technical working groups creating sustainable national coordination platforms. Furthermore, the programme consistently focused on equity by strengthening national education systems to serve all children, regardless of background, and by explicitly reviewing teaching and learning materials for non-discrimination and inclusiveness.

Major lessons and recommendations for the year ahead

These build on the programme's foundational work and address the main challenges for future effectiveness and sustainability.

Major Lessons Learned

High Teacher Ownership and Mindset Shift: Focused investments in teacher-led innovations lead to significant uptake and positive mindset shifts among educators. A large majority of surveyed teachers (99%) intended to continue applying Human Centred Design (HCD), and many reported improved classroom management (73%), better understanding of student needs (74%), and renewed motivation for teaching (71%). This also highlighted the importance of teaching as a hands-on, practical profession in pre-service teacher training (PRESETT) curricula.

Adaptive Reform Strategies are Crucial: The programme's implementing partners, drawing on their deep understanding of the region's history and complex institutional dynamics, designed interventions to be inherently adaptive, recognising the difficulty of direct, top-down reforms in centralised, change-resistant institutions. Their approach instead empowered dynamic local actors (e.g., specific pedagogical universities, non-state partners) and cultivated flexible, voluntary platforms for professional development, thereby building momentum from the ground up, which proved effective. This proactive and context-aware design has been fundamental to the programme's early success.

Longer Project Lifespan for Systemic Impact: Achieving systemic growth, measurable impact, and long-term sustainability was significantly limited by single-year funding cycles. Such short cycles were particularly restrictive for building trust and capability, demonstrating improvements, and gathering evidence to inform and influence policy change at the national level.

Crucial Role of Leadership and Inclusive Ecosystems: Strong leadership and the creation of inclusive ecosystems within educational institutions were essential for the programme's success. This included fostering networking and communities of practice around teacher Continuous Professional Development (CPD) and inclusion themes.

Recommendations for the Year Ahead

Scale interventions: To effectively assess feasible opportunities to scale interventions, the programme should systematically leverage existing coordination mechanisms and build new partnerships. USAID’s exit from the sector, as the most significant funding and delivery partner, left a huge gap in resourcing and programming. Future effort should be focused on increasing national institutional capacity and experience and promoting knowledge transfer within the region. Action: FCDO and Implementing Partners, quarterly – by the quarterly progress reporting.

1. Enhance implementing partner technical staff co-operation: encourage and support IPs to routinely share knowledge, experience, materials, and lessons learned with each other and with external stakeholders. This will foster cross-pollination of successful strategies, more efficient resource use, and increase outreach and uptake of learning and evidence. Action: FCDO country leads, FCDO education adviser and Implementing Partners, quarterly by the quarterly progress reporting.
2. Increase coordination and collaboration in sector policy dialogue and planning: Increased and proactive participation by implementing partners and FCDO in national education fora such as Local Education Groups (LEGs) in Uzbekistan, the Kyrgyz Republic, and Tajikistan, will enable alignment of efforts and reduce duplication with other partner programmes. This coordinated and collaborative approach will also ensure that UK English Language Teaching (ELT) interventions are integrated into the broader educational landscape. Action: FCDO country leads, FCDO Education Adviser, Implementing Partners, quarterly – by the quarterly progress reporting.

Under a scenario of limited funding, prioritization must focus on interventions that offer the highest catalytic value, demonstrably build sustainable national capacity, and align with core UK comparative advantages and resourcing envelope. This might include:

Prioritize Institutional Capacity Building and Teacher Development: Focus on interventions identified as "most effective and important" from a technical perspective. This includes British Council and Norwich Institute of Language Education (NILE) support for teacher education and British Council partnerships with Higher Education Institutions (HEIs). These interventions have shown high teacher ownership and positive mindset shifts, are embedded within existing local institutions, and foster international partnerships for knowledge exchange. Investing in the ability of local teachers to deliver high-quality instruction in state schools is considered crucial and leverages UK expertise effectively.

Strengthen Assessment Systems: UNICEF’s assessment mapping and Political Economy Analysis (PEA) are effective for driving quality and are viewed as important due to the growing momentum for assessment reform. Supporting assessment systems strengthening for English assessment in countries where UNICEF is conducting mapping (Kyrgyzstan, Tajikistan, Uzbekistan) should be prioritized, based on the diagnostic findings from the PEA. This builds on a critical evidence base already informing policy dialogues.

De-prioritize Direct Material Provision: While impactful in the short term when accompanied by teacher training, direct textbook provision is unlikely to be sustainable under potentially reduced future budgets. Resources should instead be redirected to interventions that foster long-term systemic change.

Be Catalytic with Small Amounts of ODA Funding:
i. Leverage Political Will and Align with National Strategies: Use PEA findings to guide politically astute and contextually relevant interventions that "work with the grain" of existing dynamics. Aligning with broader education reform efforts and national strategies enhances the potential for sustainable impact and ensures catalytic use of funds.

ii. Focus on 'Train-the-Trainer' and Systemic Approaches: Instead of direct, large-scale delivery, prioritize building the capacity of local institutions and trainers to cascade knowledge and skills nationally. This approach maximizes reach and long-term sustainability.

iii. Generate Evidence and Learning: Even with limited funding, rigorous monitoring and evaluation should be maintained to test interventions rigorously, generate evidence, and identify successful approaches that can inform broader policy and attract larger investments from other donors or national governments in the future. This transforms small inputs into significant insights.

iv. Maximize Coordination and Partnerships: Capitalize on the UK's "unique position as an English-speaking country active in educational development in Central Asia" following USAID's withdrawal. Engaging in established coordination bodies like LEGs provides an opportunity for the UK to fill critical gaps, influence wider programming, and potentially crowd in additional funding from other partners.

These prioritized interventions, focusing on capacity building, strategic partnerships, and evidence-informed adaptive management, will ensure that even limited ODA funding can achieve significant and lasting catalytic impact.

## B: THEORY OF CHANGE & PROGRESS TOWARDS OUTCOMES

The programme's Theory of Change outlines a comprehensive approach to address educational challenges and foster development in the region. The programme is designed to tackle several interconnected issues in Central Asian education systems. These include a widespread lack of subject knowledge and pedagogical competency among teachers, particularly in English language, and the absence of robust quality assurance systems to guide improvements in teacher training, school standards, teaching, learning, and curriculum reform. Other contributing factors are poor school infrastructure, low access rates to pre-primary education, low teacher morale and motivation in some countries, and a lack of curriculum materials, including English language textbooks. Additionally, the region faces challenges with poor donor coordination, significant inequality in access to higher education (especially for marginalised women and people with disabilities), and weak linkages between universities and industries. All these factors collectively result in poor learning outcomes and perpetuate educational inequity.
The AEAR-CA programme proposes four main components to address these problems: 1. Improving Teacher Quality; 2. Strengthening Higher Education Links; 3. Enhancing Quality Assurance Systems; 4. Building Coordination Capacity. Equity and inclusion are central to all interventions, specifically targeting the most marginalised and integrating inclusive content into all materials and training.
1. Improving Teacher Quality: This involves supporting Teacher Training Colleges (TTCs), Higher Education Institutions (HEIs), and Ministries of Education (MoEs) in co-creating and reforming pre-service and in-service English language teacher training curricula, including content, pedagogy, and continuous classroom assessment. It also includes piloting the provision of English language textbooks, particularly for Kyrgyzstan, and training key education officials to improve their English proficiency.
2. Strengthening Higher Education Links: The programme aims to establish and strengthen partnerships between Central Asian and UK Higher Education Institutions, including offering scholarship opportunities for marginalised women and girls.
3. Enhancing Quality Assurance Systems: Need-based technical assistance will be provided to bolster quality assurance systems. This includes improving governments' capacity to conduct timely student assessments (both national learning and continuous classroom assessment), school inspections, and teacher assessments to facilitate evidence-informed actions for enhancing teaching and learning quality.
4. Building Coordination Capacity: The programme will build the capacities of government structures responsible for coordinating education projects and programmes. This component aims to align scarce resources, curb duplication of efforts, and enhance aid effectiveness in the sector, potentially by deploying Voluntary Services Overseas (VSO) volunteers
Theory of ChangeTOC Changes
The programme's Theory of Change (ToC) has undergone review regarding its validity, supporting evidence, and assumptions in light of initial implementation experience, and there have been several notable changes since the programme's inception. A significant change is that many specific items previously listed as "Outcome Indicators" in the original business case (e.g., partnerships, learning products, deployment of volunteers) have been reclassified as Outputs or their associated indicators in the revised logframe. All changes were agreed with the MEL team, and approved, in line with PrOF guidelines. The Ecorys (2025) report's narrative clarifies this shift, stating that the outcomes were "rewritten... to focus more on improvements to education quality than access or materials development," with a focus on "skills and learning at the outcome level, while teaching is improved at the output level". In essence, the revised ToC consolidates and refines the impact statement, and redefines the outcomes, moving some of the more direct, tangible results to the "output" level to create a clearer causal chain within the programme's logical framework. The revised Theory of Change is largely considered valid and evidence-based, with its assumptions holding up and anticipated outcomes and impacts deemed reasonable, particularly if the programme receives additional multi-year funding. This condition of sustained funding is a critical factor for the long-term viability of the ToC. UNICEF's Political Economy Analysis (PEA) is crucial for refreshing ToC assumptions and tracking stakeholder attitudes.
The programme provides substantial evidence and assurance that it is on track to meeting its commitments on gender equality and broader inclusion, aligning with the principles of the Public Sector Equality Duty. Although the term "Public Sector Equality Duty" is not explicitly mentioned in the sources, the programme's design, implementation, and monitoring practices demonstrate a strong adherence to its core tenets: preventing discrimination, advancing equality of opportunity, and fostering good relations.
The programme explicitly places equity at its centre, aiming to target the most marginalised and integrate inclusion across all interventions. It seeks to identify catalytic gaps in educational provision and provide targeted support for equitable and quality education. The programme's objectives and theory of change (ToC) underscore a focus on improving access to quality education for all, including marginalised women, girls, and people with disabilities. The overall impact aims to improve educational attainment and economic growth, which inherently supports broader equality. The British Council's logframe specifically includes the "Advancement of Initial English Language Teacher Education (IELTE) and the inclusiveness of education systems across the CA region" as an outcome.
Challenges and Areas for Continued Monitoring:
Male Participation in Training: While overall female participation is very strong, the programme notes that male participation in some teacher trainings was "relatively low (2%)". Strategies are being reviewed to address underlying barriers for male engagement, highlighting a commitment to ensuring opportunities for all genders.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This review considers the programme to be largely on track to contribute to its expected outcomes and impact, though several challenges and areas for continued attention should be noted.

The revised Theory of Change (ToC) is considered "largely valid and evidence based, the assumptions hold, and the anticipated outcomes and impacts are reasonable. This highlights a critical dependency on sustained funding for long-term success. The programme components have been running for a relatively short period, making it too early for a rigorous measurement of their long-term effectiveness. However, implementing partners have completed or made significant progress on their planned activities, demonstrating strong output delivery.

Outputs are being delivered and are effective in generating positive changes at the teacher and institutional level, as supported by the findings of the Ecorys (2025) review. The programme "provides high-quality English teacher training that is embedded within existing local institutions" and "fosters international partnerships for knowledge exchange". These activities are building capacity and promoting inclusive pedagogy, which are crucial for broader educational improvements.

It is important to acknowledge that the ultimate impact of the programme, encompassing broad goals such as improved educational attainment, economic growth, and countering disinformation, is a long-term objective to which AEAR-CA is designed to contribute, rather than fully achieve on its own. Given its initial short programme duration and the lack of guaranteed multi-year funding, demonstrating the full realisation of these overarching impacts within the planned timeframe is considered unrealistic and largely unattainable. The current results, while promising and showing strong output delivery, are therefore early indications of effectiveness and crucial foundational groundwork for future, sustained engagement

Action Planned for the Year Ahead

Foster Programme Sustainability: plan for the programme implementation lifetime, including annual review cycles, strengthening monitoring and evaluation (M&E), and continuing to work closely with local institutions.
(who/by when) FCDO education and MEL team – ongoing, scheduled in regular work planning
Streamline and Reconfigure Interventions: reflect on delivery and performance over the first year and focus on interventions proven most effective (e.g., British Council and NILE support for teacher education) while reviewing others (e.g. AKF and University of Central Asia (UCA) CPD and English language training) for relevance, effectiveness, and scalability
(who/by when) FCDO education team – by November 2025
Strengthen National Assessment Systems: building on the successful mapping and revision of assessment frameworks in selected countries, set in place a plan of work to secure endorsement and embedding in national systems.
(who/by when) IPs British Council and UNICEF, with FCDO at Post – by March 2026
Enhance Coordination with Partners: implementing partners and education leads engage more strategically and influentially with development partners and governments, through existing coordination bodies such as Local Education Groups (LEGs).
(who/by when) IPs British Council and UNICEF, FCDO education leads at Post – quarterly progress reporting
Leverage UK Brand: Capitalise on the UK’s strong reputation in education and English Language Teaching (ELT) to encourage broader UK engagement (universities, publishers, assessment companies) and address the gap left by USAID's withdrawal.
(who/by when) xHMG engagement and IP British Council – by March 2026

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The Accelerating Education Attainment in Central Asia for Resilience (AEAR-CA) programme should continue based on its merits, as it has successfully completed all planned activities for its initial phase and fully achieved all its outputs, thereby laying crucial foundational groundwork across Central Asian countries. The annual review provides strong evidence that the programme continues to represent good value for money (VfM), demonstrating adherence to the principles of Economy, Efficiency, Effectiveness, and Equity – as seen in section D.

## C. DETAILED OUTPUT SCORING

Please note - this Annual Review aligns its output reporting with the four key components outlined in the programme's Business Case, providing a consolidated view of progress. Individual implementing partner reports may structure their contributions under different internal output categorisations, aligning with their specific logframes.

Output Title	Improved knowledge and competency of teachers to conduct quality and inclusive teaching/learning for students, especially in English language
Output number:		1	Output Score:	A+
Impact weighting (%):		55%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 – #English teachers trained in English language and HCD training (AKF)	240 teachers trained in English (March 2025)	Milestone Met and exceeded with 250 English teachers trained in English.
1.2 - Availability of newly procured and printed English language textbooks (UNICEF).	Full availability complete by end March 2025), with at least 95% meeting copy quality	Milestone Met and exceeded. The programme successfully supported the quality assurance and printing of 158,700 new English language textbooks for Grade 4 students, along with 158,700 workbooks and 4,950 teacher’s guides, which were ready for the 2025-26 academic year by mid-January 2025. This direct and tangible input is expected to immediately impact classroom learning for over 158,000 students. The completion of this milestone exceeded initial targets, which had conservatively estimated around 60,000 textbooks. Related material provision efforts were also completed in Tajikistan.
1.3 - At least 80% of trainee teachers at university level (PRESETT) reported improved CPD knowledge and skills (BC)	22 trainee teachers complete training by March 2025	Milestone Met and exceeded through various British Council initiatives. Additionally, a substantial number of students have been exposed to and benefited from the new CPD materials and practices, aligning with the broader aim of the indicator
1.4 - At least 80% of 60 trained participants reported improved knowledge and skills on school based CPD (BC)	1. CPD trainings delivered in up to 100 schools in Uzbekistan. / 2. CPD trainings delivered in up to 20 schools per country (up to 80 in 4 countries) (March 2025). / 3. At least 80% of 60 trained participants reported improved knowledge and skills on school based CPD (BC).	1. Milestone exceeded: The British Council successfully piloted school-based Continuing Professional Development (CPD) approaches in 61 Uzbek schools, which joined an initial 55 schools from a previous trial, bringing the total to 116 schools where CPD approaches were implemented. This effort surpassed the milestone target of up to 100 schools in Uzbekistan. / 2. Milestone Met: While specific numbers for all four countries (beyond Uzbekistan) were not individually detailed in reports shared with the Annual Reviewer, the overall output performance was strong. / 3. Milestone Exceeded: 80% of 60 trained participants reported improved knowledge and skills on school based CPD (BC). This milestone was significantly exceeded, as 116 school-based CPD champions (SBCs) reported improved knowledge and skills on implementing school-based CPD, demonstrating performance beyond expectation.
1.5 - At least 80% of 40 trained participants reported improved knowledge and skills on conducting teacher training (BC)	Up to 40 teacher educators to complete training by March 2025. / At least 80% of 40 trained participants reported improved knowledge and skills on conducting teacher training.	Milestone Met: While the absolute number of teacher educators who completed the training (16) was less than the "up to 40" (milestone1), the programme successfully met the target percentage of completion (80%) for those who enrolled. Furthermore, the participants reported improved knowledge and skills.
1.6 - At least 5 English language training courses developed for teachers (BC)	20 master course designers trained. / 5 curriculums developed	Milestone Met: / 20 ELT professionals (19 female and 1 male) were trained as course designers in partnership with the 'Orleu' National Centre in Kazakhstan. / Curriculums Developed: This collaborative work resulted in the design of 5 new professional development courses for English Language teachers. The course titles were chosen by participants and approved by 'Orleu', with the hope they will be used by the centre.

Output 1: Outputs moderately exceeded expectation. Overall, output 1 saw a strong performance across its various indicators. While some specific numerical targets were met (e.g., 20 master course designers trained and 5 curriculums developed under indicator 1.6) or achieved their percentage goals despite lower-than-planned participation numbers (e.g., 80% of 20 enrolled teacher educators for indicator 1.5, though the "up to 40" milestone was not reached in absolute numbers), other areas demonstrated significant over-delivery. Notably:

- AKF's contributions under Output Indicator 1.1 (AKF English teachers and HCD training) met their specific HCD target of 240 (with 223 teachers trained) and also provided additional broad teacher training to 269 schoolteachers and 255 civil servants, showcasing broader achievement.
- Under Output Indicator 1.3 (BC PRESETT CPD), the number of individuals benefiting from training and reporting improved knowledge/skills (over 800 individuals, including 165 PRESETT professionals) substantially exceeded the specific numerical milestone of "22 teachers".
- Under Output Indicator 1.4 (BC School-based CPD), the number of school-based champions reporting improved knowledge and skills (116 SBCs) significantly exceeded the target of "60 trained participants".
This consistent meeting or exceeding of targets, with notable over-performance in key British Council and Aga Khan Foundation activities under Output 1, indicates performance beyond mere expectation, yet not a universal "substantially exceeded" across every single metric.

Changes to this output during the past year, and any planned changes because of this review.

Over the past year, Output 1 has seen significant expansion and positive outcomes across the AEAR-CA programme. The British Council has strengthened teacher education, engaging over 2,000 individuals, including 165 PRESETT professionals in curriculum revision and piloting CPD approaches in 61 Uzbek schools with over 600 teachers. They also established seven new partnerships with UK and Central Asian higher education institutions, fostering inclusive practices and professional development. The Aga Khan Foundation (AKF) and University of Central Asia (UCA) trained 140 English teachers in Human-Centred Design (HCD) in the Kyrgyz Republic, leading to 70 classroom-level solutions and a notable 7.5% average improvement in student English language performance, exceeding the 15% target by reaching 23% of students. Additionally, 269 schoolteachers completed TKT preparation courses and 255 civil servants engaged in Conversational English training, with schoolteachers demonstrating significant 121.4% growth in post-test scores. UNICEF also contributed by procuring and printing 158,700 English textbooks for the Kyrgyz Republic.

The implications of these changes are that the programme is largely on track to meet or exceed its intended outcomes for Output 1, demonstrating effective strategies in teacher capacity building and direct language instruction. The success in piloting innovative pedagogical approaches and the measured improvements in student learning underscore the relevance and quality of interventions.

Recommendations: a closer scrutiny of AKF/UCA interventions and recommended broadening "EL training" in the Theory of Change to simply "Training" to better reflect the diverse pedagogical and professional development activities already being undertaken (e.g., HCD, TKT, CLIL).

Within the next 3 – 6mths – a refresh of the Programmes Logframe, whereby milestones and indicators are critically reviewed to ensure ambitions of the Programme are articulated and captured in the best possible way.

Lessons learned and recommendations for the year ahead

A significant finding is the high teacher ownership and uptake of new methodologies with 99% of surveyed teachers intending to continue applying it, which highlights its practical relevance and positive impact on student engagement. The interventions have led to positive mindset shifts among teachers, with 73% reporting improved ability to manage classroom climate, 74% better understanding and responding to individual student needs, and 71% experiencing renewed motivation for teaching. Furthermore, the programme has demonstrated the transferability of practices, showing that the experience of developing CPD for English teachers can be applied to other subjects, establishing a foundation for broader good practice sharing. It has underscored the importance of emphasizing teaching as a hands-on, practical profession in PRESETT curricula, moving away from purely abstract theory. The success hinges on strong leadership and the creation of inclusive ecosystems within educational institutions, alongside fostering networking and communities of practice focusing on CPD and inclusion. Furthermore, textbook provision, while impactful, is unlikely to be sustainable under potentially dwindling future budgets

For the year ahead
Recommendations for Output 1 focus on sustaining and expanding these gains while addressing identified challenges. It is recommended the programme team consider the following:

- Continue and expand inputs focused on strengthening the CPD system, particularly leveraging the effectiveness of British Council and NILE interventions.
- Enhance effectiveness and avoid duplication, to ensure systematic coordination among AEAR-CA partners, establishing formal mechanisms for technical and implementation staff to share expertise, materials, and lessons learned.
- Maintain focus on inclusive English education, addressing barriers through sustained partnerships with local institutions, systems strengthening, and capacity building, potentially involving UK specialists in gender equality and Special Educational Needs (SEND).
- Ensure any future UK investment continues to align with broader education reform efforts and national strategies, capitalising on the strong political will in Central Asian countries for ELT and fostering international exchange.
- Ensure long-term effectiveness and sustainability, through multi-year funding planning and continuing institutional capacity building. Single year cycles limit potential for policy change and systemic reforms.
Output 2

Output Title	Classroom-level and system-level assessment conducted to course correct teaching/learning and inclusiveness
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 - Availability of the mapping and situation analysis report (UNICEF)	1 Regional Report with country specific sections (March 2025).	Milestone met - UNICEF, in partnership with Cambridge Partnership for Education, completed a comprehensive mapping and situation analysis of learning assessment systems across Kyrgyzstan, Tajikistan, and Uzbekistan. This diagnostic study involved extensive desk reviews and stakeholder consultations, providing a detailed overview of existing practices and identifying common regional challenges in assessment. The Political Economy Analysis (PEA) report was also completed in May 2025, offering crucial insights into the deep-seated dynamics that constrain education reform in the region. Both reports serve as a critical evidence base to inform policy dialogues and the design of subsequent interventions, particularly the development of national assessment frameworks.
2.2 - Number of Stakeholders consulted and government education ministries on board with approach.	Evidence of ministries from all 3 countries consulted and intending to implement recommendations (end March 2025)	Milestone met - The programme successfully engaged with ministries, setting the stage for the implementation of English language training for civil servants and other activities related to education reform. The British Council's broader engagement also involved 20 senior ministry officials and put in place agreements and commitments for collaboration across various areas of reform.
2.3 – Number of civil servants complete English language training.	200 civil servants to complete English language training by March 2025	Milestone exceeded - across both the Kyrgyz Republic (100 civil servants) and Tajikistan (155 civil servants), a total of 255 civil servants completed the English language training courses

Outputs moderately exceeded expectation - Targets for reports and stakeholder engagement were largely met and the programme notably exceeded the target for training civil servants (255 against a target of 200). Strong progress was made in establishing relationships and gaining buy-in from government ministries across Central Asia, despite some initial delays. The British Council also produced three country-specific reports on CPD practices, demonstrating a tangible output in the area of scoping and reporting.

There were some significant challenges and issues, for Output 2, which broadly covers reports, stakeholder engagement, and English language training for civil servants.

i. Significant Delays in Tajikistan (AKF/UCA activities): The commencement of AKF and UCA project activities in Tajikistan, including English language training for civil servants (Output Indicator 2.3), was delayed by protracted government approval processes and the registration of AKF’s organizational charter. This resulted in the start of major activities being postponed and initial underutilization of funds. While the team worked hard to mitigate this and ultimately exceeded its training targets, timely delivery was an issue.

ii. Quality Concerns for English Language Training (AKF/UCA): The evaluative review of the programme notes that the English language training provided by AKF and UCA "require closer scrutiny for their relevance, effectiveness and scale". The review highlights that the average contact time of 42-48 hours offered "falls far short" of the 150-200 hours typically required to advance one level on the Common European Framework of Reference for Languages (CEFR), which brings into question the ultimate impact of the training. This suggests an underperformance in the depth or quality of the language acquisition, despite the high participation numbers.

iii. Regional Participation Constraints in Tajikistan: Local authorities in Gorno-Badakhshan Autonomous Oblast in Tajikistan did not permit the participation of its schoolteachers in the English language training, necessitating adjustments and involvement of teachers from other regions. This poses a challenge to achieving full inclusive reach across all planned geographical areas.

iv. Coordination Among AEAR-CA Partners: While Output Indicator 2.2 focuses on government ministries being on board (which generally appears to be achieved), the broader programme review identifies an overarching issue with "systematizing coordination among partners" within AEAR-CA. Multiple internal stakeholders expressed a desire for greater coordination at technical and implementation levels, beyond the high-level programme board. This lack of systematic coordination could impact the overall coherence and efficiency of the programme, including the development of regional reports and stakeholder engagement efforts under Output 2.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The past year saw major changes primarily in the overcoming of initial implementation delays in Tajikistan for AKF and UCA activities, as official approval from the Ministry of Education was only secured in December 2024. Despite this tight timeline, the teams managed to accelerate implementation, enabling them to meet and even significantly exceed the target for civil servants completing English language training. Concurrently, the British Council's activities supporting Output 2 experienced a strategic expansion of regional engagement, deepened scoping studies across Central Asian countries, extension of participation in study tours and CPD awareness training beyond initial plans and securing of additional funding for more accurate data collection. These changes, while challenging, demonstrated the programme's adaptability and ultimately contributed to the successful achievement of Output 2 milestones by strengthening ministerial buy-in and broadening stakeholder consultation across the region.

Lessons learned and recommendations for the year ahead

The Political Economy Analysis (PEA) is a crucial resource in relation to output 2, providing significant lessons and insights into the deep-seated dynamics impacting education reform across Central Asia during the past year. A key lesson is the inherent difficulty of enacting direct, top-down reforms within centralized, change-resistant institutions; instead, a more effective strategy involves empowering dynamic local actors and creating flexible, voluntary platforms for professional development to build momentum from the ground up. The PEA has strongly underscored the importance of evidence as a tool for accountability, revealing how the insufficient use of data for decision-making can obscure poor learning outcomes. Furthermore, the collaborative approach taken in Tajikistan, involving various stakeholders in data review, proved that such participatory processes foster greater ownership and ensure reforms are grounded in classroom realities. The analysis also highlighted significant equity concerns, such as disparities between different school systems and regional inequalities, which the programme aims to address through targeted interventions. This foundational work from the PEA has increased the strategic value and potential impact of the initial investment. This Review notes a key lesson learned regarding the methodology of the situational analysis report: the initial intention to establish a purely quantitative baseline was revised due to the insufficient availability, quality, and comparability of existing assessment data, particularly in Tajikistan. The shift to a more qualitative and descriptive analysis ultimately "provided a richer and more actionable foundation for planning future support". This demonstrates an important programmatic adaptability.

For the year ahead

- Recommendations stemming from the PEA focus on transitioning these analytical insights into informed implementation. It is crucial to thoroughly scrutinise the PEA results to ensure they offer deep, locally informed insights, and to systematically share these findings across all programme components. Specifically, the PEA's findings should be used to gauge political will for and strategically support the strengthening of English assessment systems, particularly in countries like Kyrgyzstan and Tajikistan, building on the assessment mapping work completed
- This continuous scrutiny should directly inform the review and adaptation of the programme's Theory of Change assumptions, ensuring they remain valid and responsive to evolving contexts. The politically feasible recommendations from the PEA should serve as a clear roadmap for navigating programme risks through continuous political engagement, flexible programming, and coalition building.
In relation to Output 2, several key lessons have emerged this year. A significant insight is that evidence serves as a crucial tool for accountability; the previous weak use of data often obscured poor learning outcomes and diffused responsibility. This highlighted the programme's vital role in empowering reformers within government and civil society by strengthening national institutions' capacity to produce and utilise credible data for informed decision-making. Furthermore, the collaborative process of analysing student learning data in Tajikistan, involving diverse stakeholders like ministry officials, teachers, and experts, demonstrated that such participatory approaches foster greater ownership and ensure reforms are grounded in classroom realities. The successful establishment of technical working groups in all three countries and support for the Joint Education Sector Review in Kyrgyzstan also underscored the effectiveness of creating sustainable national platforms for coordination and coherence across the education sector.

Output Title	Enhanced networking and links across higher education institutions within Central Asian nations as well as with the UK
Output number:		3	Output Score:	A +
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 – Number of Inclusive practices/policies developed at CA universities.	At least 8 inclusive practices/policies to be developed at Central Asian universities by March 2025	Milestone Met: The Accelerating English Language Learning in Central Asia (AELLCA) programme, led by the British Council, established seven partnerships between UK and Central Asian higher education institutions as part of an "English and inclusion accelerator scheme". These partnerships focused on enhancing English language teacher education and developing more inclusive education systems. / Through these initiatives, at least 10 distinct inclusion practices have been revised or introduced across the partnered institutions. / The overall impact of these partnerships on inclusion practices was assessed as 8.5 on a scale of 1 to 10, with partners indicating that more time is needed for substantial changes but committing to continued cooperation. These initiatives are laying a strong foundation for continued growth in inclusive education across Central Asia

Outputs moderately exceeded expectation - The planned milestone for Output Indicator 3.1 for this year (ending March 2025) was for "At least 8" inclusive practices/policies to be developed at Central Asian universities. The reported progress indicates that "at least 10 distinct inclusion practices have been revised or introduced" across the partnered institutions, covering various dimensions, including inclusive pedagogical techniques, gender mainstreaming, Special Educational Needs (SEN) awareness, and cultural/socio-economic considerations, laying a strong foundation for inclusive education development.

A few challenges and issues have been identified for future sustainability these include

i. Embedding deeper transformative changes: While new inclusive practices were introduced, partners indicated that "more time is needed for substantial changes" to fully embed these practices within institutions. The impact of these partnerships on inclusion practices was assessed at 8.5 out of 10, with partners committing to continued cooperation and acknowledging the need for more time for deeper, transformative changes.

ii. Systemic Barriers to Inclusive Education: The broader environment for inclusive English language education in Central Asia faces several fundamental barriers. These include poor infrastructure, such as inadequate WASH facilities, and lack of accessibility for students with SEND in many state schools. Socio-economic factors contribute to inequality, with expensive private English tuition creating a divide between students from different backgrounds, and sometimes prioritization of boys' attendance at better-resourced schools. Additionally, there is an uneven distribution of expertise, particularly SEND specialists, in rural areas. These underlying systemic issues can impede the full adoption and sustained impact of the inclusive practices developed at universities.

iii. Governmental and Institutional Capacity Gaps: There is a recognized lack of institutional capacity within ministries and other national agencies to implement and sustain reforms, including those related to improving teacher training, curriculum development, and assessment systems.

iv. Demanding Nature of Capacity Building: Some of the training initiatives aimed at building capacity for inclusive education, such as the British Council Assured Certificate in Teacher Education (ACTE) course, were described as "very intensive and demanding," requiring more time than participants initially anticipated and leading to some dropouts. This highlights practical challenges in effectively delivering and embedding new skills for inclusivity.

Changes to this output during the past year, and any planned changes as a result of this review.

The past year witnessed significant developments characterized by both strategic adjustments and an expanded reach. The primary mechanism for achieving this output was the establishment and strengthening of partnerships between UK and Central Asian Higher Education Institutions (HEIs) under the "English and Inclusion Accelerator Scheme". While the initial plan aimed for eight partnerships, seven were ultimately established, a slight reduction attributed to time constraints.

A major positive change involved the strategic expansion of regional engagement; activities like study tours and Continuing Professional Development (CPD) awareness training, initially planned for Uzbekistan, were broadened to include other Central Asian countries, demonstrating the programme's adaptability. This broadened engagement, combined with focused work on embedding inclusion in pre-service teacher training (PRESETT), resulted in exceeding the milestone of at least 8 inclusive practices/policies, with at least 10 distinct practices revised or introduced across the partnered institutions. These changes implied a strong and growing ministerial buy-in and stakeholder commitment to inclusive education, solidifying "CPD and Inclusion" as a key area for UK partnership and laying a robust foundation for continued growth in inclusive education across the region

Lessons learned and recommendations for the year ahead

Several key lessons emerged this year. A primary insight is that more time is needed for substantial changes to fully embed inclusive practices within institutions for deeper, transformative impacts. The programme also highlighted persistent systemic barriers to inclusive English language education in Central Asia, including inadequate infrastructure (such as poor Water, Sanitation, and Hygiene (WASH) facilities and lack of accessibility for students with Special Educational Needs and Disabilities (SEND) in state schools). Socio-economic factors, like the expense of private English tuition, were also identified as contributing to inequality by creating divides and sometimes leading to a prioritization of boys' attendance at better-resourced schools. Furthermore, the uneven distribution of expertise across urban and rural populations poses a challenge to equitable access. While international travel, such as study tours to the UK, offers significant motivational benefits and helps cement networks, its sustainability is a concern. Despite these challenges, the establishment of seven partnerships (out of eight planned) between UK and Central Asian HEIs was seen as a positive achievement, laying a strong foundation for continued growth in inclusive education.

For the year ahead

Building on these lessons, the following recommendations are proposed to strengthen Output 3's impact and sustainability:

- It is crucial to systematise coordination by establishing a formal, regular mechanism for implementation and technical staff to share expertise, materials, and lessons learned, complementing the existing high-level programme board and avoiding duplication of efforts.
- The programme should also proactively engage in existing Global Partnership for Education (GPE) partnership frameworks (such as Local Education Groups and the Tajikistan Development Coordination Council) to ensure better alignment with broader education reform efforts and to leverage the UK's unique position in the region.
- Furthermore, to foster sustainability, interventions should be streamlined and reconfigured, prioritising those identified as most effective, such as British Council support for teacher education and its partnerships with HEIs.
- Maintaining a strong focus on inclusive education is vital, continuing to address barriers through partnerships, systems strengthening, and capacity building, leveraging UK expertise in gender and SEND.
- Finally, the programme should capitalise on the UK’s strong brand in education and English Language Teaching (ELT) by actively engaging UK universities, publishers, and assessment companies in programmatic planning to further strengthen HEI links and address the gap left by USAID's withdrawal.

Output Title	Reduced donor fragmentation and duplication of efforts
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 – Scoping report on TA options provided by VSO	Scoping report on Technical Assistance (TA) options provided by Voluntary Services Overseas (VSO) to be complete and deemed of satisfactory quality	Milestone Met - VSO, acting as a potential implementer of the Accelerating Education Attainment for Resilience in Central Asia (AEAR-CA) program, conducted a scoping study. The study highlighted focus areas of other partners, identify existing gaps in technical capacity, and determined how VSO can contribute to strengthening education systems. This all fed into the report.
4.2 – Coordination between each partner, and read across to GPE, delivered in part through at least quarterly lesson learning reviews and partner engagement with donor coordination mechanisms.	Quarterly lessons reviews to be conducted. / Each partner to satisfactorily advise on their engagement with other partners and the Global Partnership for Education (GPE) as relevant	There is regular coordination among implementing partners at a high level through the programme board, but multiple internal stakeholders have expressed a desire for greater coordination at other levels to share technical expertise and avoid duplication. / However, the Ecorys review (2025) noted opportunities to "better align with best practices by systematizing coordination among partners" and recommended creating dedicated mechanisms for technical staff collaboration to share expertise and avoid duplication.
4.3 – Good practice and learning generated on English Language programming, measured through lessons learned report/evidence piece.	Good practice and learning generated on English Language programming, measured through lessons learned report/ evidence piece.	Progress has included active identification and reporting of "lessons learned" and "key emerging themes" by implementing partners like the British Council and Aga Khan Foundation/University of Central Asia in their reports.

Outputs met expectation - The planned milestones for all indicators under Output 4 for this year (ending March 2025) were reported as "Achieved" in the main AEAR-CA logframe. Specifically:
The milestone for Output Indicator 4.1, "Scoping report on TA options provided by VSO," was for the report to be "complete and deemed of satisfactory quality" by March 2025. Reports confirm that VSO conducted scoping visits and produced country-specific reports and an overall scoping report, thus meeting this expectation. For Output Indicator 4.2, "Coordination between each partner, and read across to GPE," the milestone included "quarterly lessons review conducted" and partners "satisfactorily advis[ing] how engaged with other partners and GPE as relevant" by March 20252. While the logframe states "Achieved", the evaluative review notes that despite high-level coordination, there was "limited coordination with other donors, within existing coordination platforms/networks, and amongst AEAR-CA partners" and a "wish for greater coordination at other levels". This suggests the activity happened, but there were recognized areas for improvement, aligning with meeting rather than exceeding the set expectation. FCDO has acknowledged the complexity in coordinating across multiple partners as a delivery risk. Output Indicator 4.3, "Good practice and learning generated," had a milestone of "Initial evidence developed, including lessons learned from year 1" by March 20253. Both British Council and Aga Khan Foundation reports explicitly provided sections on "Lessons learned" and "Key learning identified", demonstrating that this initial evidence and learning were indeed generated, fulfilling the milestone. There is no clear indication that the outputs substantially or moderately exceeded the defined milestones, especially given the identified areas for improvement in coordination, despite the successful completion of the required tasks.

A significant challenge and area for improvement has been identified in the depth and systematic nature of coordination efforts. Specifically:

i. Limited Coordination at Technical and Implementation Levels: Despite high-level coordination through a programme board, "multiple internal stakeholders describe a wish for greater coordination at other levels" among implementing partners. This implies that while formal meetings may have occurred, the practical, day-to-day collaboration and sharing of expertise among technical and implementation staff was not as robust as desired.

ii. Challenges in Achieving Complementarity and Avoiding Duplication: The evaluative review explicitly notes that there was "limited coordination with other donors, within existing coordination platforms/networks, and amongst AEAR-CA partners". This limitation directly impacts the programme's ability to "achieve complementarity and avoid duplication" of efforts, which is a key objective of good practice in development programming. The report suggests opportunities to "better align with best practices, including by systematizing coordination among partners".

iii. Need for Enhanced External Coordination: The programme's effectiveness in mitigating risks and maximizing broader educational outcomes is tied to "greater coordination with other international actors within bodies such as the LEGs, and through Frameworks such as the Partnership Compacts". This ongoing need implies that the current level of external coordination, while present, requires strengthening to fully leverage collective efforts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A major external change was USAID's withdrawal from Central Asia, which created notable gaps in delivery, financing and existing donor coordination efforts and positioned the UK for greater leadership in English language interventions, necessitating closer multi-actor coordination. Consequently, planned changes stemming from this review include increased engagement between implementing partners, to share knowledge and avoid duplication, increasing FCDO's strategic participation in education sector fora such as Local Education Groups, and integrating insights derived from the recent Political Economy Analysis into programme adjustments.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

During the past year Output 4, saw initial progress in its milestones, with quarterly lessons reviews conducted and partners reporting on their engagement with other partners and the Global Partnership for Education (GPE). Implementing partners, such as the British Council, initiated monthly briefing sessions for all partners to ensure shared understanding and conducted individual check-ins. However, Ecorys evaluative review found that while some efforts were made, there was "limited coordination with other donors, within existing coordination platforms/networks, and amongst AEAR-CA partners", suggesting a need for greater systematisation to achieve complementarity and avoid duplication. The short initial implementation period likely limited the extent of this deeper collaboration and the rigorous measurement of its effectiveness.

For the year ahead
Similar to previous recommendations, the programme will scrutinize and integrate insights from the Political Economy Analyses (PEAs) conducted by UNICEF into programme adjustments and the refinement of Theory of Change assumptions, to work more effectively with political realities and influential actors.
## D: VALUE FOR MONEY

The Accelerating Education Attainment in Central Asia for Resilience (AEAR-CA) programme has demonstrated strong Value for Money (VfM) performance during its initial phase, aligning with the original VfM proposition in the Business Case, which is guided by the "4Es" framework: Economy, Efficiency, Effectiveness, and Equity. The Business Case also noted that VfM would be assessed by the quality of interventions, the rate at which outputs convert into outcomes and impacts, and the cost-effectiveness of this conversion, considering factors beyond just price.

The programme's interventions, particularly in teacher development, HEI partnerships, and assessment systems, aim to build national capacity, which is seen as a sustainable approach to improving overall education quality and English language proficiency. The findings generally support the programme's Theory of Change, which links improved English language learning to broader educational attainment, economic growth, and countering disinformation, provided the programme receives continued funding over multiple years for long-term sustainability. This implies that sustained investment is crucial for realizing the full strategic and economic benefits outlined in the Business Case. The programme's ability to maximise change by seeking political buy-in and demonstrating flexibility is a key enabler for its cost-effectiveness. However, opportunities remain to further align with best practices by systematizing coordination among partners and addressing systemic barriers to adoption

Economy: Getting the best value inputs

Performance: The programme successfully managed costs in many different ways: by leveraging UNICEF’s established procurement and partnership processes for large-scale activities. It also effectively used institutional contracts for technical expertise (e.g., with Cambridge Partnership for Education) and partnerships with local academic institutions (e.g., American University of Central Asia - AUCA), which were deemed a cost-effective way to access high-calibre, specialized skills. Aga Khan Foundation (AKF) & University of Central Asia (UCA): Achieved direct savings of £2,853 from a total spend of £91,244 on the project by November 2024. Specifically, £2,598 in savings were realized on programme activities (out of £63,080 spent on activities). For UCA, the programme reports utilizing £233,979 across its activities in Kyrgyzstan and Tajikistan. By December, the utilized funds were 62% of the projected amount in Kyrgyzstan and 48% in Tajikistan, indicating careful management of expenditure against plans despite initial delays. The programme team pushed to ensure overhead (Non-Project Attributable Costs) were kept as minimal as possible for the British Council work, engaging both commercial and finance colleagues. Whilst this demonstrates the team were operating using the best possible rate (available at the time, based on the criteria), this should be continually monitored to ensure ongoing value for money. The British Council also negotiated discounts for UK consultancy services from NILE and reduced rates from local vendors for accommodation and travel, and secured co-funding and non-cash contributions (e.g., venue hire, in-country travel, staff time, media coverage).

Efficiency: Maximising the outputs for a given level of inputs

The programme maximized resources by building on UNICEF’s existing country presence and operational platforms, avoiding costs associated with setting up new structures. A key efficiency was the creation of regional goods, such as the comprehensive situation analysis and Political Economy Analysis (PEA), conducted across three countries, providing evidence usable by multiple partners and preventing duplicative analytical work. In Tajikistan, analysing existing student learning data from a parallel project was highly efficient, generating critical new insights without the cost of a new study.

Effectiveness: Ensuring that the outputs deliver the desired outcome

The programme achieved all its planned outputs for the year. The analytical reports (situation analysis and PEA) are already informing policy and the next phase of programming. The establishment of technical working groups has created sustainable national platforms for coordination. The delivery of 158,700 English language textbooks for Grade 4 students in Kyrgyzstan was a direct and tangible input with immediate impact increasing access to high quality learning materials. The provision of accompanying teacher guides and training of master trainers will increase effective teaching and learning. The Ecorys review found that the AEAR-CA programme aligns with best practices by addressing key dimensions of quality language learning and promoting local ownership and sustainability. British Council's support for teacher education and partnerships with Higher Education Institutions (HEIs) were deemed highly effective and important, building national institutional capacity transferable to the broader education sector. AKF's Human-Centred Design (HCD) training helped teachers adopt new pedagogical practices, with a reported 7.5% average improvement in English language performance among students (reaching 23% of students, exceeding a 15% target in one pilot) and positive mindset shifts in teachers. UCA's Teaching Knowledge Test (TKT) preparation and Conversational English (CEN) programmes showed significant improvement in teachers' and civil servants' test performance and English proficiency levels. The assessment work (mapping existing systems and developing national frameworks) is considered important due to growing momentum for reform and existing coordination mechanisms.
The review noted that while promising, the Continuous Professional Development (CPD) and English language training by AKF and UCA require closer scrutiny for their relevance, effectiveness, and scalability. Textbook provision, while impactful, is unlikely to be sustainable under potentially dwindling future budgets.

Equity: Ensuring that the benefits are distributed fairly

The programme is fundamentally geared towards improving equity by strengthening national education systems to serve all children, regardless of background or location. The Political Economy Analysis (PEA) highlighted significant equity concerns, such as disparities between elite and mainstream schools in Uzbekistan and regional inequalities in Tajikistan. The quality assurance process for new English textbooks in Kyrgyzstan explicitly included criteria for non-discrimination and inclusiveness. Foundational analyses (situation analysis and PEA) considered how inequities related to gender, disability, and location affect learning outcomes to inform targeted interventions. AKF and UCA ensured safeguarding standards and promoted the participation of women, with 95% of participants in HCD and TKT trainings in the Kyrgyz Republic being female schoolteachers. Workshops were designed to be teacher-friendly, responsive to needs, and provided logistical support (travel, accommodation, catering for those with infants) to ensure inclusive participation. The HCD approach fostered an inclusive environment with nearly equal male and female teacher participation in Tajikistan. SPCE UCA emphasized accessibility for rural/remote areas and flexible scheduling for civil servants, including mothers and caregivers, and celebrated success stories of female participants presenting internationally. British Council's partnerships explicitly focused on inclusion, collaborating with UK universities known for expertise in Special Educational Needs and Disabilities (SEND), and revising/introducing inclusion practices covering pedagogical techniques, gender mainstreaming, and SEND awareness. Online platforms were created to encourage peer support and collaboration on inclusion.

Overall, the Accelerating Education Attainment in Central Asia for Resilience (AEAR-CA) programme has demonstrated sufficient evidence for its continuation, as it has successfully completed all planned activities for its initial phase and fully achieved all its outputs, laying crucial foundational groundwork across Central Asian countries. Recommendations have been in this annual review as to where the Programme could develop further and build on its initial successes.

E: RISK

Overview of risk management

The programme operates in a context with inherent risks, which were actively monitored and managed throughout the year, with the PEA providing a deeper understanding of their systemic nature. The PEA notably identifies five core dynamics shaping education reform, such as ‘centralised power disconnected from reality and fragmented governance,’ which underpin many of the programme's operational risks. Key risks and mitigation strategies are summarised below.

The overall risk rating for the programme is moderate. The programme team reviewed risks with the delivery partners, as part of the monthly catch-up meetings with each partner. Partners were encouraged to notify the programme team, in between these meetings, immediately if they became aware of any potential risks.

The programme team usually reviewed risk monthly with colleagues in the region, and appropriate mitigation measures were put in place for all risks. The SRO and the Development Director were usually updated every month. Additionally, the team commissioned a Political Economy Analysis (through UNICEF) and a review of the programme and ELT through ECORYS.

The main risks were around delivery in the short timeframe and coordination, specifically
the top risk was about FCDO’s legacy, and the risk that what the programme delivered would not have longer-term impact and/or was not coherent with government/ other donor plans (sustainability).  The team mitigated this by continuing to push the partners to explain how what they were doing linked up with what governments were doing, and how governments could take these forward.

linked to this risk, the uncertainty of available funds for the programme, meaning that the programme could no longer deliver the agreed objectives, and that the longer-term impact the programme was intended to have would be at risk.  The team mitigated this by securing exceptional funds (for up to six months) and bid separately to ensure sustainability/longer-term impact in the region.  The team also continued to develop a x-HMG strategy to make better use of different levers, and to draw on HMG’s (and the UK’s) technical expertise.

Fragmented implementation of programme components remains a risk, specifically possible duplication between UNICEF and British Council in Kyrgyzstan because both are training teachers. The programme team needs to ensure coherence. The team will mitigate the risk by meeting with the BC and UNICEF teams in Kyrgyzstan and engaging as part of our strategy.

Another major risk identified for the programme is the reputational risk associated with the impact of the USAID-funded teacher training in Kyrgyzstan not going ahead. This would have resulted in teachers not being able to use the English Language textbooks delivered from the programme - a risk of UK investment not having the anticipated value. The team mitigated this risk through UNICEF, by funding UNICEF to provide this training for teachers to enable them to utilise the FCDO-funded Grade 4 textbooks. The programme team has continued to monitor this risk to ensure that all the teachers are trained as intended.

As part of the Due Diligence Assessment (DDA) for each partner, the team assessed potential risks and made recommendations, setting out action plans and follow-up sessions to ensure risks were mitigated and issues addressed. The main risks identified centred around: fraud and whistleblowing, financial management including misappropriation of funds by investment recipients, and effectively managing downstream partners.

The programme team developed detailed action plans for each partner and followed up the action plans through separate sessions with partners to ensure that the identified risks were mitigated and issues addressed. For example, to mitigate any potential misappropriation of funds by investment recipients, the team undertook training with the partners, which included fraud.

The DDA did not find sufficient evidence that partners had conducted due diligence assessments on their downstream partners, for example UNICEF conducted due diligence every five years which, in the programme team’s assessment, created the risk that findings on some of their downstream partners could be out of date within that time. To mitigate this, partners developed and shared their delivery chain maps to enable the programme team to understand the risk on specific interventions. British Council also circulated the FCDO Supplier Code of Conduct handbook as well as the Code of Conduct itself for reference to downstream partners and conducted training in November 2024.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The AEAR-CA programme demonstrates a strong performance across its commercial and financial aspects, and its partners have largely delivered against contract KPIs and terms and conditions, providing sufficient evidence for continuation with strategic adjustments.

Performance of Partners and FCDO on Commercial and Financial Issues:

Quality and Timeliness of Narrative Reporting and Audited Financial Statements: Implementing partners provide regular narrative reports and final reports which consistently indicate successful completion of planned activities and achievement of outputs. These reports detail progress, headline achievements, and specific interventions. While extensive financial details and utilization rates are provided in financial reports and quarterly updates, there was no explicit evidence from data sources which detail the quality and timeliness of audited financial statements beyond FCDO's expectation that partners will maintain comprehensive inventories and undergo annual audits.

Proactive Dialogue on Risks and Updating of Delivery Chain Maps: All partners and FCDO actively monitor and manage risks. The programme operates in a context with inherent risks, which were actively monitored and managed, with the Political Economy Analysis (PEA) providing a deeper understanding of their systemic nature. Mitigation strategies are consistently outlined for political instability, limited institutional capacity, policy-practice disconnect, and lack of coordination. Partners report on specific risks such as travel/visa permissions, potential for funds not being fully spent, and staff continuity, along with their mitigation actions (e.g., rescheduling, close monitoring, FCDO support for interim staffing). FCDO's Business Case confirms that risks are managed through a risk register that is to be updated monthly, with partners required to provide risk analysis in their regular quarterly reporting. While monitoring of downstream partners is mentioned, there was insufficient explicit evidence regarding the proactive updating of delivery chain maps.

Quality of Financial Management and Accuracy of Forecasting: The programme has demonstrated strong Value for Money (VfM), as detailed in the previous section.

Forecasting Accuracy: AKF reports modest savings due to digital assessments and holding workshops at schools. The British Council reported a minimal underspend (£1,881.50) and a small variance (3.7%) in its actuals compared to planned spend by December 2024, indicating generally accurate financial management and forecasting with "no material adverse variances expected".

Open Book Accounting and Transparency: FCDO explicitly states its intention to use "open book accounting for cost transparency" and sets expectations for partners on driving VfM, using robust economy indicators. No specific "profit variance" information is applicable given the non-profit nature of the implementing partners.

Compliance with the Gender Equality Duty and Equalities Monitoring: The programme demonstrates strong compliance with gender equality and inclusion principles. It "gives due regard to advancing equality and fostering good relations". The quality assurance for textbooks explicitly reviewed materials for gender stereotypes, non-discrimination, and inclusiveness. Foundational analyses consider how inequities related to gender, disability, and location affect learning outcomes, informing targeted interventions. High female participation (e.g., 95% of HCD and TKT training participants by AKF/UCA) is consistently reported. Partners ensured gender-sensitive delivery, logistical support for inclusive participation (e.g., for mothers), and created safe, interactive learning environments. Female participants have demonstrated success in international presentations. While the term "Public Sector Equality Duty" is not explicitly mentioned, the programme's actions and reporting clearly align with its core principles by systematically addressing equality and inclusion.

How FCDO Could Be a More Effective Partner:

Addressing Funding Cycles: The review strongly suggests that the programme's anticipated outcomes and impacts are "reasonable if the programme receives additional funding in multiple future years". Single-year funding cycles are seen as limiting for achieving systemic or policy change and long-term sustainability, making multi-year funding a critical enabler.

Enhancing Coordination: FCDO should work more closely and be more directly engaged with other development partners and national governments, particularly through existing coordination bodies like Local Education Groups (LEGs) and the Tajikistan Development Coordination Council (DCC). This increased visibility and coordination would help align interventions, avoid duplication, and integrate English language support within broader education reforms.

Leveraging UK Expertise: FCDO can further capitalize on the UK's "considerable brand in education and ELT" by actively engaging UK universities, publishers, and assessment companies in programmatic planning and by making local organizations aware of UK capabilities.

G: MONITORING, EVIDENCE AND LEARNING

Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond FCDO). If there is an evaluation linked to this programme provide an update on findings (if not covered elsewhere in the AR).

Monitoring and Evaluation

Monitoring activities during the review period has been multifaceted, involving regular reporting, stakeholder engagement, and in person monitoring, together with specific assessments, which have directly informed programming decisions. The programme's design includes a strong emphasis on monitoring, evaluation, and learning, with regular feedback loops built into the implementation process. Monitoring is guided by the results framework and standard procedures, including partner reporting and assurance activities. The programme team's management tools include a delivery plan, a risk matrix, and a delivery chain map, updated monthly, with partners required to provide risk analysis in their regular quarterly reporting.

Beneficiary Feedback and Inclusivity (Leave no one Behind)
Strong compliance with gender equality and inclusion principles is evident. The programme explicitly gives "due regard to advancing equality and fostering good relations". Textbook quality assurance in Kyrgyzstan explicitly reviewed materials for gender stereotypes, non-discrimination, and inclusiveness. Foundational analyses (situation analysis and PEA) considered how inequities related to gender, disability, and location affect learning outcomes, informing targeted interventions to reduce gender inequality. High female participation is consistently reported: 95% of HCD and TKT training participants from AKF/UCA were female schoolteachers. The workshops and resources were designed to be teacher-friendly, providing logistical support for inclusive participation (e.g., accommodation and travel for those from remote villages, rooms for teachers with infants/toddlers, extra meals). Interactive HCD workshops aimed to create safe, inclusive, and conducive learning environments, especially for shy or less confident teachers. Female participants demonstrated success in international presentations after the English language courses.

The programme aims to improve equity by strengthening systems to serve all children, regardless of background or location, and addresses disparities between elite and mainstream schools and regional inequalities. Partners ensure "gender-sensitive delivery" and "created safe, interactive learning environments" [previously established]. The British Council's work explicitly focused on "English and inclusion". One key highlight is that "at least 10 distinct inclusion practices have been revised or introduced across the initiatives". These practices "contribute to embedding inclusivity in PRESETT education" covering "pedagogical techniques to cultural and socio-economic considerations". British Council partnerships explicitly aimed to embed inclusion initiatives/practices in PRESETT. Disaggregation: While gender disaggregation is strong, specific data disaggregated by age or disability are not systematically provided in the evidence for this annual review beyond general statements of consideration.

Learning Aims for the Programme for the Coming Year:

Essential:

• Maximizing change by applying lessons learned across implementers and contexts, while maintaining sensitivity to context-specific challenges. This is crucial for the programme's effectiveness and its adaptive reform strategy. The programme was strategically designed to navigate complex dynamics and build momentum from the ground up, informed by deep understanding of the region. This systematic approach supports continuous improvement and responsiveness to context.

• Generating evidence and learning on the impact of English Language as an enabler for economic/social development and wider geopolitical aims. This is a core strategic objective and rationale for the AEAR-CA programme. It underpins the programme's contribution to UK soft power and its role in countering disinformation.

• Developing learning products (case studies, policy briefs, research papers) and disseminating monitoring data, results, and VfM performance to stakeholders. This aim is essential for accountability, transparency, and informing policy and future interventions. The programme's analytical reports (situation analysis and PEA) are already demonstrating their value by informing policy and subsequent programming. It is a recommended way of working to "model a way of working that consistently emphasises the value of evidence to inform action". Dissemination of learning products and performance data is explicitly identified as a learning aim for the coming year. It directly supports the programme's VfM principles by demonstrating effectiveness.

• Systematically documenting and evaluating the programme for continuous improvement. This is fundamental to the programme's adaptive management approach. The sources repeatedly emphasize the importance of strengthening Monitoring, Evaluation, and Learning (MEL) capacity to ensure oversight of data collection, analysis, and adaptive management. This systematic process is vital for testing interventions, refining the Theory of Change, demonstrating Value for Money, and ensuring long-term sustainability.

Desirable/Nice to Have Learning Aims:

• Generating learning on cross-HMG approaches to education. Highly strategic for optimizing UK's internal and external engagement, this aim is about the internal mechanics of how the UK government and its agencies collaborate to deliver education initiatives. It supports the broader goals indirectly by aiming for greater coherence and leveraging UK assets, but it is not directly about the educational outcomes or the adaptive management of the programme's interventions in Central Asia. It's a key facilitator for "a joined-up XHMG offering that showcases UK English language assets".

Date of last narrative financial report	AKF: 30/05/2025 / BC: 24/07/2025 / UNICEF: 26/06/2025	Date of last audited annual statement	AFK: 31/12/2023 / BC: 31/3/2024 / UNICEF: 24/07/2024