## Annual Review

Title: Empowering Survivors of Sexual Exploitation, Abuse and Sexual Harassment (ES-SEAH)
Programme Value £ (full life): £15,000,000		Review date: October 2025
Programme Code: 400218	AMP start date: 26/11/2024	AMP end date: 30/09/2029

Summary of Programme Performance
Year	2025	2026	2027	2028	2029
Overall Output Score	B
Risk Rating	Major

DevTracker Link to Business Case:	D0006390.odt
DevTracker Link to results framework:	S4002185.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Empowering Survivors of Sexual Exploitation, Abuse and Sexual Harassment (ES-SEAH) business case approved spend of up to £15 million over 5 years with the aim of increasing reporting of SEAH perpetrated by aid actors and strengthening survivor-centred responses.

Key priorities include:
- Developing effective SEAH reporting mechanisms that are contextual and accessible.
- Partnering with women’s rights organisations to receive and respond to SEAH reports.
- Building the evidence base on ‘what works’ for a survivor-centred approach, informed by survivors themselves.
- Supporting UN efforts to prevent and respond to SEAH perpetrated by UN personnel.

The programme will aim to deliver on each of these priorities but, due to changes in the ODA landscape, the scale of delivery is expected to be reduced.[1]
[1] The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition. About changes to UK ODA: At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect. ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises. We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

ES-SEAH is aligned with the UK’s strategic priorities and commitment to safeguard against SEAH in the aid sector. The 2018 International Safeguarding Summit resulted in a set of four transformative commitments from the aid community, one of which was to “ensure support for survivors, victims and whistle-blowers; enhance accountability and transparency; strengthen reporting; and tackle impunity”, which ES-SEAH sets out to do. This is amplified in HMG’s 2020 Strategy on Safeguarding against SEAH. The Common Approach to Protection from SEAH further outlines the need to “encourage reporting, accountability and a victim-survivor centred approach” as a minimum standard.

ES-SEAH is made up of 2 components:

Component 1: Engaging Women’s Rights Organisations (WROs): When it comes to reporting aid-related SEAH, victims tend to have more confidence in WROs working on gender-based violence (GBV) as they are embedded within communities. WROs often provide quality support including referral to services (legal, psychosocial, health etc.). ES-SEAH aims to build a model for WROs to support SEAH survivors with a strong focus on evidence generation through participatory action research.

Component 2: Addressing the rights and dignity of victims-survivors of SEAH committed by UN personnel through supporting survivor-centred UN mechanisms: This component focuses on funding UN mechanisms to play a pivotal role in improving a survivor-centred response across the UN system.

The reduction in ODA has impacted how much the programme has been able to start under both components. This Annual Review reflects on a programme in transition.

Summary supporting narrative for the overall score in this review

The programme scores a ‘B’ for its first annual review - not all expectations have been met due to the early stages of delivery and a reduction in ODA impacting start up.

Output 1: OVRA workplan delivered on time and with quality
An MoU with OVRA was signed on 10 March 2025. The FCDO will fund 3 OVRA staff. Progress has been made in recruiting staff, but they are not yet all in place and workplans have not been agreed.

Output 2: Increased evidence on what works to support victim-survivors of SEAH, including through engagement of WROs
The FCDO has paused this component, due to a reduction in ODA. Output 2 has not been considered when calculating the score for this annual review.

Major lessons and recommendations for the year ahead

Lessons

Factor in the UN’s prolonged recruitment timetable for new positions when setting milestones. The P5 post funded by the UK is OVRA’s first position at this level of seniority and therefore the UN’s internal clearance to advertise was significantly lengthened.

Recommendations

1. FCDO and OVRA to work closely to manage any potential delays to delivering the workplan when staff are eventually on board. FCDO to consider increasing the frequency of progress meetings with OVRA to ensure any implementation issues are resolved quickly.
2. OVRA to develop VfM indicators.
3. FCDO to prioritise decision on if and how it will deliver Output 2 (working with WROs) once budgets are clarified.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change for ES-SEAH is as follows:

The theory of change remains relevant – the steps to achieving the outcome and impact are still valid. The scale of impact, however, will be significantly reduced due to budget reductions.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The theory of change outlines the significant role of UN bodies to drive change for survivors. It is unclear whether the programme will contribute further to the UN due to budget reductions. Pending budget decisions, work towards meeting the outcomes related to the WRO component is expected to start over the course of the next annual review period but decisions have yet to be made on how best to deliver it.

Actions for the year ahead include agreeing on partner(s) for delivering the WRO component and where/ how they will operate at reduced scale; and outlining what OVRA staff funded under ES-SEAH will deliver in line with OVRA’s workplan.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

ES-SEAH remains relevant. Trusted reporting mechanisms and providing support and accountability to victim-survivors remain a critical gap in approaches to tackle SEAH. The outputs support UK commitments to tackle SEAH within the aid sector and are aligned with the Common Approach to Protection from SEAH.

## C. DETAILED OUTPUT SCORING

Output Title	Support to OVRA - Improved coordinated support and assistance to victims of sexual exploitation and abuse by United Nations staff and related personnel
Output number:		1	Output Score:	B
Impact weighting (%):		100	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
OVRA workplan delivered on time and with quality	1 P5 and 2 P3 staff with workplans in place	Partially met: Progress has been made with the selection of the P3, Human Rights Officer who assumed the functions on 16 October 2025, the selection of the P5 Senior Human Rights Officer is also being finalised, while the selection process is underway for the other P3 position. The milestone was to have all three posts in place and workplans in place, which has not been fully achieved. / P3 Human Rights Officer assumed functions / P3 Programme Management Officer selection process ongoing / P5 Senior Human Rights Officer selected / Workplans under development

Briefly describe the output’s activities and provide supporting narrative for the score.

The FCDO is funding 3 positions within OVRA: a P5 Senior Human Rights Officer, a P3 Human Rights Officer, and a P3 Programme Management Officer. An MoU with OVRA was signed on10 March 2025, after which the recruitment process started.

The first phase of the recruitment process required the UN’s Executive Office to review the role profiles. This took place alongside the start of the UN80 Initiative, a major reform effort by the UN Secretary-General to make the UN more effective, cost-efficient, and responsive. As efforts were directed towards inputting into this process, major delays were subsequently caused to OVRA’s recruitment. The P3 Human Rights Officer started on 16 October 2025. Recruitment for the P3 Programme Management Officer is ongoing – 115 applications are being sifted at the time of this review. As a newly established position the P5 Senior Human Rights Officer required additional administrative steps and was finally advertised in September. The candidate was selected on 17 October 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes agreed for this output this year. Milestones for future years have been adjusted to take into account recruitment delays. Year two milestones have been reduced to ‘60% of OVRA's annual workplan delivered or is on track to be delivered’, previously 80%. A year 3 milestone has been added – ‘80% of OVRA's annual workplan delivered or is on track to be delivered’. OVRA funding is expected to go into a third year due to the delayed recruitment of staff, which is within the confines of the MoU.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first annual review of the programme. There are no previous recommendations.

Output Title	Support to Women’s Rights Organisations (WROs)
Output number:		2	Output Score:	n/a
Impact weighting (%):		0	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Increased evidence on what works to support victim-survivors of SEAH, including through engagement of WROs	No milestones have been agreed for this output	No progress against output 2 due to budget reductions pausing this work.

Briefly describe the output’s activities and provide supporting narrative for the score.

Supporting victim-survivors of SEAH through WROs remains an objective/output of the programme but there were no milestones set for this output due to pausing this work. A significant amount of work was undertaken to complete an invitation to tender but budget uncertainty during the transition to 0.3 has made it necessary to rethink how best to deliver this work.

This output has not been assessed as part of the annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The FCDO is exploring the most appropriate delivery options for this output owing to budget reductions. It is important to make a decision as soon as possible to ensure enough time for implementation within the lifetime of the business case. We expect the WRO component will require ample time to develop evidence on what works to support victim-survivors of SEAH, informed by victim-survivors themselves.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first annual review for the programme. No previous recommendations have been made.

Going forward it is recommended that a decision is made as soon as possible on how best to deliver this output.

## D: VALUE FOR MONEY

Key cost drivers and performance

Table 1: Value for Money Measures

The table below, taken from the business case, highlights the suggested value for money indicators for the programme.

VfM Measure	Indicator
Economy	Administrative operating costs as % of total expenditure / Consultant day rates against benchmarks (if applicable) / Competitive fee rates against benchmarks
Efficiency	Partners meeting targets and timelines / Cost to achieve effective reporting mechanisms that could be taken to scale
Effectiveness	% victim-survivors reporting they are satisfied with case handling / % in community, including community leaders, who have increased knowledge of SEAH (prevention) and how to report / Number of global public goods produced to strengthen understanding of a survivor-centred approach, informed by survivors / Number of member states making approaches more survivor-centred
Equity	Governance mechanism for components 1 and 2 including victim-survivor panel oversight (see Management Case) / Research conducted with consideration of vulnerabilities and informed by marginalised groups, including women, girls, children and people with disabilities. / Reporting mechanisms accessible for all. / Disaggregated data in logframes.

VfM performance compared to the original VfM proposition in the business case (above)

It is too early in the programme to use many/if any of the suggested value for money measures listed in the business case.

Of the activities that have taken place under the programme to date, OVRA reports having considered value for money during the selection process for new staff. In terms of efficiency and effectiveness, new staff will be assigned to work on areas of the mandate that have been most affected by limited capacity and serious understaffing. For example, for the selection of the Human Rights Officer position, the most suitable candidate was chosen with a consolidated legal background and demonstrated experience in advancing the resolution of paternity claims which is a priority area for OVRA. The selection of the most suitable candidates also represents the best trade-off between cost effectiveness and economy: as the selected applicant already has experience in the focus area of paternity claims and possesses a legal background, they will not need extensive supervision or training in this area, allowing the other staff member to resume functions and expand into other areas of OVRA’s mandate which have been deprioritised due to lack of resources.

In terms of equity, new staff will support OVRA’s efforts in placing the rights and dignity of all victims of sexual exploitation and abuse by UN at the forefront of the UN response, including those who are likely to have less voice and agency to bring perpetrators to account.

It is recommended that VfM indicators are agreed with OVRA for future reporting once the recruitment of all staff has concluded.

Assessment of whether the programme continues to represent value for money

The programme should represent value for money into the future provided that VfM is a key consideration in choosing the means of delivery for the WRO component. It will also be important to agree VFM indicators with OVRA for reporting going forward. The programme will need to respond to funding constraints by looking to scale down while still maximising the impact it can have against the original expected outcomes.

E: RISK

Overview of risk management

The overall risk rating for the programme remains major. The FCDO has an internal risk register which continues to be updated by the programme team on a regular basis, at least quarterly. Risks are also discussed with partners in quarterly meetings as part of programme monitoring.

The main risks identified which have materialised, or are likely to materialise, for the programme are:

Delays in recruitment of OVRA staff slowing down programme delivery. This is now being factored into the delivery timeline for Output 1. We are still only effectively providing two years of staff funding to OVRA but have accepted that the two years will start later, as will results against the workplan. This is reflected in revisions to the logframe.

ODA cuts are very likely to mean that we do not have adequate resources to deliver the full ES-SEAH ambition. A decision has not yet been made on how to deliver Output 2 (WRO component). There is a risk that this component will not have adequate time to generate credible evidence on how best to support victim-survivors of SEAH if the implementation time is too short. A lower budget will also impact the number of implementation locations, which could affect credibility in replicability. These risk factors will need to be factored into final decision-making on how to proceed with delivering the WRO component.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The FCDO programme team has changed during the reporting period. A new PRO was recruited after the previous PRO moved on and both the lead adviser and SRO have changed. This represents a significant management change for the programme, with all three programme positions being new at the same time. Other senior management in the Safeguarding Unit have stepped in to help during this transition period.
Commercially, programme plans changed significantly during the reporting period. Planned commercial tendering for the WRO component (Output 2) was put on hold centrally in FCDO, forcing the decision to rethink how best to deliver it. The majority of the budget approved for the programme was allocated under Output 2 yet no expenditure has been incurred to date. Spending during this FY and in future years under Output 2 will be shaped by the outcome of the spending review and subsequent allocations processes, expected to be concluded by the end of the calendar year.
The programme has dispersed £1.2m in its first year under Output 1. These funds were to OVRA to fund staffing costs. The three new staff members are yet to join OVRA, so the spend against funds transferred is currently minimal. Funds are allocated to staff-personnel costs, contract-services and operational costs related to general administrative expenses. Each UN grant also incurs in programme support cost which amount to 13% of the overall contribution.
Audited statements will be requested from OVRA in due course in line with UN reporting schedules.

G: MONITORING, EVIDENCE AND LEARNING

The programme has been overseen by the Deputy Head of the Safeguarding Unit, a G6 accredited Senior Social Development Advisor, as the Senior Responsible Owner (SRO), during the majority of the review period (until early October 25). In the interim period before a new SRO is in place, the Deputy Director for Safeguarding Unit has taken over accountability as the new SRO. ES-SEAH is also managed by a highly experienced PRO. Lead advisors for the programme include two G6 leads – Multilateral Strategy and Effectiveness (Output 1) and Senior Social Development Advisor (Output 2). This provides strong technical oversight.

Regular review meetings have taken place with OVRA. This has enabled the FCDO to remain aware of how UN80 has affected recruitment timeframes for staff and adjust the logframe accordingly.

There is no external evaluation for the programme in its entirety (Outputs 1 and 2). An evaluation for Output 2 was outlined in the business case but this is likely to be significantly pared back or dropped in light of ODA budget reductions.

Date of last narrative financial report	Progress report provided 29/9/2025	Date of last audited annual statement	n/a