 Central Asia Small Projects Programme Annual Review
(Template for Smaller Projects Programmes)
[note] A Smaller Project is defined as a funding arrangement with a single implementing partner normally not exceeding £250k. Such projects can be grouped as a Programme for approval and reporting purposes provided the total budget envelope does not exceed £2m. See PrOF Guide.

Summary of Programme Performance
Year	24/25
Overall Output Score	A
Risk Rating	Moderate	Choose a risk rating	Choose a risk rating

Programme title: Central Asia Small Projects Programme
Programme Value £ (full life): £2,000,000		Review Date: / 26/05/2025
Programme AMP Code: 400222	Programme Start Date: 03/06/2004	Programme End Date: 30/04/2024

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006430.odt
DevTracker Link to results framework:

## SUMMARY AND OVERVIEW

Programme description: / The objective of the Central Asia Small Projects Fund is to support development aims in the region and develop UK influence and soft power by enabling the flexible development of small projects. The overall purpose of these projects is to progress the aims of the Country Business Plans of the 5 Central Asia states under the programme (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan) and the regional EECAD business plan.
Intended policy objective(s) of projects within this programme. / Across the region the policy imperative is to ensure strong, stable and resilient states with closer relations to the UK and that meet the Sustainable Development Goals (SDGs). Central Asia is a geopolitically important region with powerful neighbours, reflecting an overall threat to the independence and sovereignty of Central Asia states. The International Development White Paper also confirms our commitment to tackle climate change and work towards the achievement of the SDGs. / The programme provides a flexible mechanism to support these aims by contributing to the Country Business plans and building the UK’s reputation in the region. Given the specific needs in each context are different, aligning with the already existing objectives of the Country Business Plans was felt to be the most effective way to ensure contextual relevance as these have already been developed with the wider policy objectives in mind. The aim of a flexible fund was also to be able to respond to diverse opportunities that may help build our reputation and build relationships through being responsive. Therefore, separate objectives were not developed for this programme but projects judged on their contribution to existing goals.
Overall Programme Score / A
Summary supporting narrative for the overall programme score in this review. / Given the Small Projects Programme is a collection of small initiatives working to a diverse set of objectives supporting the goals of five Country Business Plans, this review has focused on two Performance areas, as indicated in the Small Projects Guidance. These Performance areas are the delivery of the programme and the contribution to the relevant Country Business Plan. / To assess the delivery of the programme against budget and objectives each of the projects was scored considering how they had delivered against objectives, within the expected budget. Higher scores were given if the project had delivered above expectations. The majority of projects did deliver to the expectations in the proposal, leading to an overall score of A. / Projects were also assessed against how they had delivered against Country Business Plans. Scores were given for the relevance but also the strength on the contribution – if it would lead to lasting impacts or relationships. All projects were directly contributing to one of the Country Business Plans goals as this was the criteria used for selection. Some projects have demonstrated the potential to form lasting relationships or impacts that went beyond the initial event or activity. For this reason an overall score of A was given. Evidence was drawn from the monitoring reports of the projects. / However, the contribution in terms of developing the UK’s influence and soft power was not systematically considered. It is recommended in the year ahead to develop an understanding of exactly what we are looking for in this area and develop a flexible mechanism to be able to assess this more rigorously. Outcome mapping, using change stories, may be a useful tool for this.
Major lessons and recommendations for the year ahead / This has been the first year of delivery of the programme in its current format, with different requirements under AMP. Implementation of the programme teams has been done in some instances by policy staff without prior programming experience. Continuing to help develop the skills of staff in this area will help the smoothness of delivery and ensure more effective programmes. Lessons have focused around the need to maintain active monitoring, maintaining flexibility and the importance of senior leadership engagement to ensure strategic use of the fund. The following recommendations are made to improve the running of the fund next year.

Recommendations
No.	Recommendation	Theme	Timeframe	Action owner
1.	Programme management resourcing should be reviewed to ensure that the programme is overseen by the most appropriate individuals. This will help with ownership of the programme.	Programme management.	June 2026	SRO
2.	Consider the support needed for non-development staff to deliver the programmes effectively. Peer support should be established and training held for those staff responsible who do not feel confident in programme management. This should include gender equality and social inclusion and risk management training – this will help mitigate delivery risks.	Training	September 2026	SRO
3.	Ensure there is one focal point in each embassy.	Project ownership	End of June 2025	PRO
4.	Responsible staff should ensure a regular rhythm of meetings with implementers.	Project ownership	Quarterly	Project Leads/ Programme Managers
5.	Ensure there is clear oversight of budgets at a post level and any underspends are flagged early to ensure they could be utilised elsewhere in the region.	Finance	Monthly	HDE Finance Analyst
6.	Peer learning is encouraged to share experiences across the region.	MERL	Quarterly	PRO
7.	Include a focus on concrete delivery to the country business plan in the programme closure report.	MERL	Following commission of CBP	SRO
8.	Look at a systematic way or simple tool to track the soft power impact of projects to enable the assessment of this. Outcome harvesting could provide a mechanism for this.	MERL	August 2025	PRO
9.	Agree a clearer approach to results and how to measure them across the programme with a more targeted results framework.	MERL	September 2025	PRO
10.	Agree a proportional and clearer approach to VFM across the programme	MERL	September 2025	PRO

## PROGRAMME STRATEGY OR THEORY OF CHANGE

The objective of the Central Asia Small Projects Fund is to support development aims in the region and develop UK influence and soft power by enabling the flexible development of small projects. The overall purpose of these projects is to progress the aims of the Country Business Plans of the 5 Central Asia states under the programme (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan) and the regional EECAD business plan.

The Portfolio SRO for the programme delegates decision making to HMAs across the region for each countries’ allocated budget, via a letter of delegation. This enabled rapid decision making based on the needs within each country context. A flow chart was developed to help guide embassy teams in the steps needed to approve projects, conduct due diligence and manage agreements and payments.

Projects were selected via a variety of routes. Some embassies developed call for bids around specific objectives in the country business plans. There were also a range of unsolicited bids that were judged to fit the criteria and support the business plan objectives. In Kazakhstan an active data base of potential projects has been developed which ranks them for relevance, helping the embassy identify opportunities quickly.

Although each project did fit within the business plans some of the areas of the goals were very broad. It would be helpful in the next round to shape some criteria around how the projects can show direct contribution to the achievement of the goal. It would also be helpful to follow a process similar to Bishkek, where a lead for each CBP goal is asked to strategically consider which actions or areas of activity would contribute the most to the achievement of the goal and use this for a basis for the call for bids. This would still leave room for reactive work and unsolicited bids but might assist the process of what was the best fit and use of resources.

All embassies used a specific project proposal form which helped identify how the project supported the Country Business Plan goals. This included a brief theory of change, how it would be monitored, the ODA eligibility and the gender impacts of the programme. Once this documentation had been developed it was reviewed in most cases by a Post Projects Board, and in one case by a senior group of officers including the HMA. This board reviewed the project on its contribution to the Country Business Plan and its ODA eligibility. In some cases, projects were modified after this discussion to ensure it better fitted those two criteria.

As a final check the projects were reviewed by the Programme Advisory and Results Group in London to ensure the ODA criteria had been met. The Senior Programme Advisor in PARG acted as the PRO for the programme. This helped to identify elements of one project that did not fit the ODA requirement, developed by an embassy with less development staff to draw on for support, and allowed the redesign to better fit the requirements.

Having the programme management in London, with a long communication chain and lack of opportunity for face-to-face discussion, did lead to some difficulties in implementation. In one embassy, changes in staff led to some confusion around the fund and which projects were funded under this programme. That ultimately led to an underspend of the programme budget. To rectify this training has been provided to the embassy to help with the understanding of programme management. PARG has also reduced in size, with the loss of the Strategic Programme Advisor, which will make maintaining the same level of oversight challenging. Programme teams are also overloaded at post, but peer support may help to lessen the burden of management and facilitate shared learning. Now systems are established the process of managing should be less.

As the projects varied in their financial amount – from £62,000 to just under £500 – the way the projects have been monitored has varied, in line with the principle of proportionality. The range of methods have included feedback from attendees, wash up meetings, site visits, formal reporting from partners and collation of data on people reached. A good practice developed in Bishkek was to ensure there was a programme closure report completed by all implementers. The projects have had a vast range of impacts that cannot be unified into a single results framework.

The programme has delivered on its objective of supporting country business plans via 18 projects that covered a wide range of issues such as climate change, education, creative industries, disability support and gender-based violence. For each project there is a demonstrated link with the Country Business plan, and many have had lasting impacts. Some examples are below.
- Biodiversity support: Biodiversity was adopted in renewable energy discussions and cooperation was forged with Saudi Arabia on species conservation.
- Gender Based violence: grassroots government workers were exposed to new thinking on Gender Based Violence and trained on non-violent conflict resolution and women’s rights.
- Climate change: Climate resilient crops were introduced to communities along with biogas and training on climate resilient farming.
- Media: Practical support was provided to media organisations enabling them to operate more safely in the face of restrictive legislation and declining media freedom.
- Creative economy: A local creative economy community was founded in Turkmenistan following a forum on the creative economy which featured international expertise. This community is helping women entrepreneurs in the Arts and Crafts sector find a voice and forum for advocacy. The forum also drove an increase in Turkmenistan participation in the British Council Regional Creative Economy course.

Overall, the programme has provided a valuable, flexible resource that has enabled posts to respond to diverse opportunities in their context. At a time of increasing geopolitical competition, where the UK is trying to increase its influence in a disputed region and help Central Asian states boost their resilience, this resource provides a welcome way to boost our profile and contribute practical support on the ground. This has become increasingly important following the cuts at USAID, which has led to a reduction of their strategic input on many key topics.

## DETAILED OUTPUT OR PERFORMANCE AREA SCORING

The detailed scoring at programme level should be based on the agreed programme-level results framework.

Following the suggestion of the PrOF Guide for managing Smaller Projects in Programmes, the agreed results framework may be based on Performance Areas.

All programmes will need to score the Performance Area related to Delivery of Projects.

Your results framework may also include the Performance Areas Contribution of Projects to Programme objective(s) and Actionable Learning. If one or both of those Performance Areas are in your results framework you can score them here. If they are not part of your results framework then delete the Performance Area from the template.

Delivery of Projects

Performance area:	Delivery of projects.
Number:		1	Score:	A
Weighting (%):		55%	Weighting revised since last AR?	N/A

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

Summarise the projects that have been delivered this year. How many projects? What was the range of project budgets? What was the range of activities (e.g. events, research, communications), places or themes? If there are only a handful of projects, you may simply mention them all.

You have the option (not requirement) to attach as an annex to this programme-level Annual Review a full tabulation of projects. A suggested format is provided in this draft template.

Summarise whether the projects have been delivered according to the planned timescales, budgets and quality. Provide an assurance that risks and finances have been managed in a proportionate manner and in line with PrOF rules. This will be based on the reporting passed from the project level to the programme level.

Reflect back to the Business Case. How have the criteria and mechanisms that were put in place to select and manage projects operated in practice? Is there anything that this programme (or a future programme) could do better in future?

The rubric to score delivery of projects at programme-level is for the reviewer to weigh up whether, on balance, across all projects:

A++	Projects were delivered substantially better than expected (over delivery substantially outweighs any under-delivery).
A+	Projects were delivered better than expected (over-delivery outweighs any under-delivery).
A	Projects have been delivered as expected (any under- or over-delivery is in balance).
B	Projects were delivered below expectations (under-delivery outweighs any over-delivery).
C	Projects were delivered substantially below expectations (under-delivery substantially outweighs any over-delivery).

In 24/25 the programme has delivered 18 projects. This included; six in Kyrgyzstan, five in Tajikistan, three in Kazakhstan, two in Uzbekistan, one in Turkmenistan and one regional project. These have ranged in size from £500 to £62,000, with the outlier being the John Smith Trust, which received a grant of £250,000 to deliver a fellowship programme across the region. These projects have varied in the sectors they contributed to with three focusing on sharing UK links and expertise, three on Climate and Nature, three on supporting civil society and journalists, two giving support to the creative economies, two giving support to those with disabilities, one delivering English language training, one focusing on gender, one supporting children, one on demining and one enabling fund to allow Kazakh participation in international forums and to benefit from UK expertise.

There has also been a broad range of activities undertaken under these themes. These have included visits to the UK to access UK expertise and visits from UK or international expertise, conferences, research, advocacy work, convening like-minded actors, service provision and training. The John Smith Trust also conducted a year-long fellowship scheme for mid-career professionals which included a seven-day visit to the UK.

According to project documentation most of these projects have delivered the expected outputs to the expected budgets. There was one area of underspend in Kazakhstan when planned activity was cancelled and one project where the test results following English Language training did not meet the expected standard. There was another project that has some gaps in the reporting, but all activities were delivered. There have been seven projects where staff felt that the implementers delivered over the expected level. 12 of the projects were rated A for delivery, five A+ and one B, leading to an aggregate score of A.

The rubric used to score projects was as follows
A++	Projects were delivered substantially better than expected (over delivery substantially outweighs any under-delivery).
A+	Projects were delivered better than expected (over-delivery outweighs any under-delivery).
A	Projects have been delivered as expected (any under- or over-delivery is in balance).
B	Projects were delivered below expectations (under-delivery outweighs any over-delivery).
C	Projects were delivered substantially below expectations (under-delivery substantially outweighs any over-delivery).

This was the suggested rubric in the Small Projects Annual Review guidance.

This has been the first year of the programme and so there have been some lessons learned from the implementation of the projects. As projects were largely taken on by policy staff, who were not necessarily experienced in project management, there has been some support needed to help deliver the projects, given by development staff at post or PARG in London. One embassy has had some additional training on project management, and this might be useful for other posts to ensure consistent standards across the region. PARG also provided support in Kyrgyzstan to complete the due diligence to the required standard, which demonstrated flexibility across the network. However, capacity of development staff is limited and PARG have reduced in size so some reflection on how to effectively deliver the programme needs to be given. Peer support between those involved in delivery may be one option.

 Key lessons learned on the process are:

- It was valuable to have this flexible/agile allocation at post-level that could be directly targeted at delivering against the Embassy’s CBP in a way which complemented the programme/project activities being managed at a Central Asia regional level.
- There was a need for regular and active management of the projects to ensure delivery. One embassy suggested the need for a regular rhythm of meetings/discussions to monitor actual spend/forecasting and planned activities under the projects in order to ensure full spend and project completion.
- It was useful to have some projects that could be scaled up, based on satisfactory performance by implementors against agreed activities, which could absorb underspend when some projects did not go ahead (based on due diligence).
- Necessity of factoring in resourcing requirements for running several small projects under the SPP, assigning leads for each project to ensure adequate oversight with support from experienced project officer in the development team. There also needs to be adequate hand over when officers leave to ensure continuity in year.
- Having checks on ODA eligibility, either from within the development team in the embassy or via PARG in London, was helpful to ensure that all projects were compliant.
- Accurate forecasting is essential to manage possible underspend and there needs to be clarity on the funding lines for projects to avoid the lastminute realisation of underspends. Due to the flexible nature of the fund and the range of countries involved underspend can be easily absorbed if flagged early.
- Senior leadership engagement can help ensure more strategic projects and effective delivery. Having someone to responsible for tracking the spend and the projects will help drive consistency.
- Kyrgyzstan have developed effective systems in terms of monitoring and reporting. It would be helpful to share these across the network.
Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
1. Programme management resourcing should be reviewed to ensure that the programme is overseen by the most appropriate individuals. This will help with ownership of the programme.
2. Consider the support needed for non-development staff to deliver the programmes effectively. Peer support should be established and training held for those staff responsible who do not feel confident in programme management. This should include gender equality and social inclusion and risk management training – this will help mitigate delivery risks.
3. Ensure there is one focal point in each embassy
4. Responsible staff should ensure a regular rhythm of meetings with implementers.
5. Ensure there is clear oversight of budgets at a post level and any underspends are flagged early to ensure they could be utilised elsewhere in the region.
6. Peer learning is encouraged to share experiences across the region
7. Include a focus on concrete delivery to the country business plan in the programme closure report.
8. Look at a systematic way or simple tool to track the soft power impact of projects to enable the assessment of this. Outcome harvesting could provide a mechanism for this.
9. Agree a clearer approach to results and how to measure them across the programme with a more targeted results framework.
10. Agree a proportional and clearer approach to VFM across the programme

Contribution of Projects to Programme Objectives

Delete this page if Contribution of Projects to Programme Objectives is not one of the performance areas in your results framework.

Performance area:	Contribution of projects to the programme objective(s). [This will need to be entered on AMP as part of loading the Annual Review for approval.]
Number:		2	Score:	A+
Weighting (%):		45%	Weighting revised since last AR?	N/A

Briefly summarise how projects have contributed to programme objectives and provide supporting narrative for the score.

Recap the programme objectives according to the Strategic Case of the programme’s Business Case or approval document.

In reviewing this Performance Area, first consider whether there are reporting systems in place that enable effective and honest reporting of how projects contribute to objectives. For example, do the reporting systems capture the importance of objectives achieved, the project’s contribution, and that of others, and the sustainability of any objectives achieved.

Second, use your results framework to weigh up the reporting from projects to consider whether, on balance, there is a credible, evidence-based story of how projects have contributed to objectives.

The following descriptions can be used to assign the scoring.

A++	The programme is substantially above a trajectory to achieve the desired objectives with a wide range of strong supporting evidence.
A+	The programme is above a trajectory to achieve the desired objectives with strong supporting evidence.
A	The programme is on course to achieve the desired objectives and has supporting evidence.
B	The programme is below the trajectory to achieve the desired objectives and supporting evidence is ad hoc and contradictory.
C	The programme is substantially below the trajectory to achieve the desired objectives and weak evidence to show any meaningful change.

Across the region the policy imperative is to ensure strong, stable and resilient states with closer relations with the UK and that meet the SDGs. Central Asia is a geopolitically important region with dominant neighbours, reflecting an overall threat to the independence and sovereignty of Central Asia states. The International Development White Paper also confirms our commitment to tackle climate change and work towards the achievement of the SDGs.
The programme provides a flexible mechanism to support these aims by contributing to the Country Business plans and building the UK’s reputation in the region. Given the specific needs in each context are different, aligning with the already existing objectives of the Country Business Plans was felt to be the most effective way to ensure contextual relevance as these have already been developed with the wider policy objectives in mind. The aim of a flexible fund was also to be able to respond to diverse opportunities that may help build our reputation and build relationships through being responsive. Therefore, separate objectives were not developed for this programme, but projects judged on their contribution to existing goals.
Project proposal forms clearly made the link to Country Business plans and included elements of how the project was contributing to that objective. The reporting mechanisms for the projects varied, depending on the size and nature of the project. Some projects were assessed through feedback of participants or other methods where the spend was low. Projects that had a project closure report were able to demonstrate the impacts gained but the format of that report did not explicitly make the link back to the Country Business Plan. Adjusting the template to do this would make the contribution to the Country Business Plan delivered clearer.
The projects were also intended to support the UK’s reputation and the development of soft power. The projects have referred to several ways this has been developed. These include
- The exposure to UK expertise through study tours to the UK or UK expertise providing training and information in country.
- High profile events that have also generated interest and debate on social media
- Media reporting of project events or work
- Exposing communities that might not otherwise of heard of the UK to expertise or English language training.
The impact of developing ‘soft power’ is difficult to measure. However, it might be helpful to adapt reporting templates to try and capture some of these impacts systematically. Developing stories of change could be a useful way to capture this.
The contribution to the Country Business Plan was assessed at the end of the year using the following rubric:
A++ Activities took place and have led to a sustained and substantial impact towards the country business plan. It has generated an on-going relationship or agreement or has led to substantive concrete changes in policy or practice.
A+ Activities took place have led to positive impacts towards the country business plan. They have forged new relationships with potential for further action or generated some positive change.
A Activities took place as expected and there is some potential for follow up / sustained results in the future.
B Activities took place but there was little response or interest from those that attended / participated. No on-going links formed. No lasting impacts reported.
C Activity didn’t take place or failed to attract the expected participants

The overall score was ranked at an A+, via a weighted average based on project spend using scores derived from information supplied by post, drawing on project monitoring information. Only one project scored a B based on reflection on the effectiveness of the mechanism chosen for contributing to the CBP. The embassy team in Uzbekistan reflected on the use of sport as a delivery method for the human rights and open societies part of the business plan but reflected that there was no sustainable impact and might be better as part of a wider campaign. This provided useful information for the future design of programmes in this area.

Projects that scored A+ showed potential for follow up and laid the basis for future collaboration or work. They helped to establish relationships with key institutions or organisations or provided a training of trainers to allow for the passing on of knowledge.

Examples of these were
- The development of a Creative Industry Association in Turkmenistan as a result of project action.
- Greater relationships built with the Border Service in Kyrgyzstan.
- The ability of media organisations to operate safely and continue their work.
- Continued use of biogas and sustainable farming practices.
- Integration of biodiversity issues into the renewable energy sector dialogue.
“The small project in Turkmenistan was particularly rewarding. It helped galvanise the creative sector, which is still nascent, and push them towards establishing an Association to represent their interests. The main event, a conference, generated an authentic open policy discussion. Something extremely rare in Turkmenistan. The Head of the UNDP here said it was the best conference that she had attended and was "truly groundbreaking". John Newbiggen, Chairman of Creative England, who is lobbying to be on the FS's Soft Power Council, participated in the event and thought it extremely well-organised, praising the Embassy for its participation.”- Stephen Conlon, HMA to Turkmenistan.

Gender
One project in the programme was specifically addressing Gender issues (and so can be marked 2). Three other programmes specifically targeted marginalised groups (disabled and children). All projects were asked to demonstrate their impact on gender. Project proposal forms asked projects to identify their approach to supporting gender levels of female/ male participation were recorded where relevant. In Turkmenistan the project was focused on promoting the creative economy but included women artisans specifically and enabled them to find a voice in the Creative economy association. In order to ensure gender and social inclusion issues are fully considered in the programme, gender should be included in any programme management training.