## Annual Review Template

Title: Transforming Education in Ethiopia (TREE)
Programme Value : £110 million		Review date: February 2026
Programme Code: 400225	AMP start date: 24/02/2025	AMP end date: 31/12/2029

Summary of Programme Performance
Year	2025/26	2026/27	2027/28	2028/29
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	D0007590.odt
DevTracker Link to results framework:	S4002258.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

Education is a core priority of UK’s engagement in Ethiopia, with a focus on strengthening the government’s capacity to improve foundational learning, including for marginalised children. We are responding to a high level of need with an estimated 10.7 million children currently out of school in Ethiopia due to conflict and climate-related shocks, and approximately 90% of children experiencing learning poverty, meaning they are unable to read and understand a simple text by age 10. With an estimated 2 million young people entering the workforce each year, education is critical to Ethiopia's success.

The Transforming Education in Ethiopia programme (TREE) became effective in February 2025. It is scheduled to run until February 2029. The programme aims to build the long-term capability of Ethiopia’s education system, by working through government systems to improve foundational learning. It is the successor programme to General Education Quality Improvement Programme for Equity (GEQIP-E), GEQIP II, and GEQIP I (which was launched in 2007).

GEQIP I and II laid the foundation for quality and equitable education in Ethiopia by strengthening core system inputs and institutional capacity, such as textbook provision, an increased proportion of qualified teachers through expanding teacher training, and introduction of per-pupil school grants. Together, they helped to improve learning conditions and sector planning. GEQIP-E had a strong equity focus and shifted to results-based financing, enabling greater government ownership and implementation flexibility. It prioritised marginalized regions and schools, early childhood education, school leadership, inclusive and gender-responsive interventions, improved teacher preparation, early grade reading, and strengthened data systems for evidence-based decision-making.

Building on these three iterations of GEQIP, the Government launched the Ethiopia Education Transformation Programme (EETP) in 2023, adopting a holistic, system-wide approach to improving learning outcomes while increasing domestic resource mobilisation. The World Bank’s Ethiopia Transforming Education Operation for Learning (ETOL) programme, supports implementation of EETP through scaling up successful GEQIP interventions and leverages additional financing from partners such as Global Partnership for Education (GPE), supporting sustained sector transformation.

The intended impact of the TREE programme is Improved equitable access and learning for school children across Ethiopia. The outcome is expected to be increased equitable access and improved retention and learning outcomes in pre-primary and primary education. The programme has four components as follows.

  1. Component 1: Financial Aid (FA) to the Government of Ethiopia which is channelled via a World Bank Trust Fund. This performance-based funding (P4R) supports ETOL. Other donors include Finland, Norway and the Global Partnership for Education (GPE). The programme is described in the World Bank Project Appraisal Document.

  1. Component 2: Technical Assistance (TA) which aims to directly deliver innovative approaches to improving education quality and support the delivery of FA.

  1. Component 3: a programme-funded adviser to work with the Ministry of Education and support improved planning, coordination and budgeting for the whole sector.

  1. Component 4: monitoring and evaluation to assess programme performance, verify delivery and inform programme adaptation to strengthen delivery of both the FA and TA components.

The UK’s reduction in overseas development assistance (ODA) will result in key changes to TREE[1]. This Annual Review reflects that the programme has had to refocus and so will deliver against a new plan. There is a high likelihood of a reduction in the overall bilateral funding envelope for education once the formal ODA allocations are confirmed, particularly affecting FA and potentially reducing the scope of TA. This is expected to affect all programme components going forward. However, the intended impact and outcomes of the programme currently remain as described in the TREE Business Case.
[1] At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.

1. The team is managing a transition in its engagement approach in the education sector, with an increased emphasis on TA and policy dialogue. They have been in close discussion with the Ministry and partners to consider how FCDO can further reposition its role in the sector in line with evolving priorities and the broader funding landscape. In the medium term, FCDO Ethiopia intends to maintain a presence in the ETOL MDTF to monitor progress and advocate for UK priorities. Alongside this, work is underway to place greater focus on key binding constraints to faster progress in improving human development, including conflict and crisis, domestic financing to basic services, and weak delivery systems.
2. Ethiopia’s Minister of Education values the UK presence in the education sector not just as a funder but also for their technical expertise. The Ministry of Education sees a UK comparative advantage in improving English Language teaching and strengthening donor coordination (see recommendations below). The expertise mobilised through Centrally Managed Programmes (CMPs) to support teacher reform efforts and promote refugee inclusion in schools is valued. The UK’s continued presence as a funder and partner in ETOL is also recognised. There is a strong expectation that the UK and other partners maintain a sustained focus on improving learning outcomes.
Summary supporting narrative for the overall score in this review

This Annual Review was led by the senior education adviser in the FCDO-Ethiopia Human Development Team with inputs from the education programme team and the governance team. It was underpinned by a World Bank-led ETOL Implementation Support Mission which was conducted in December 2025. This found that the government had made overall satisfactory progress against the Disbursement Linked Indicators (DLIs) and the programme development objective (PDO). The UK is routinely engaged in these missions. These are one of the key mechanisms through which FCDO monitors progress.

There are some data gaps – particularly at the outcome level – which the team will need to address in the programme’s M&E framework. Output level indicators are mostly generated by ETOL and FCDO relies primarily on the World Bank for this monitoring and reporting. Achievement of the Disbursement Linked Indicators (DLIs) are subject to annual independent review by the Ethiopia Statistical Services (ESS), The education team should consider whether there is more that can be done to strengthen M&E in the programme.

The review judges that the programme is meeting expectations against the first-year output milestones which are summarised in the table below. As this is the first year of programme implementation, the targets are largely foundational, and not all indicators are reported on. The outputs build on progress made by the three GEQIP programmes to strengthen government systems to deliver better quality and more equitable education outcomes.
Table 1: Summary of output scoring
Output	Milestones for Y1	Assessment
1. Schooling environment better equipped to support learning (including climate resilience)	a) updated school construction standards / b) updated school grant guidelines (DLI 6) / c) updated teaching and learning minimum standards (DLI3)	A Met expectations / a) In progress / b) reported achieved / c) reported achieved
2. Improve teaching in schools	School leadership training framework approved (DLI2) / School inspection framework updated (DLI1)	A Met expectations / Approved / Approved
3. More girls and marginalised children staying in school	100 Inclusive Education Resource Centres (IERCs) established / 160,000 special needs students enrolled in ICRCS.	A+ Moderately exceeded expectations / a) Met expectations / b)196,000 (exceeded expectation)
4. Enhanced government capacity to implement reforms	a) TA to government / b) Enhanced programme monitoring	A Met expectations / Proposal in progress / Baseline commissioned

Major lessons and recommendations for the year ahead

The main lessons and recommendations are summarised in the table below.

Table 2: Lessons learned and recommendations
Lessons learned	Recommendations
Funding for education and other basic services has been declining in real terms	1. Agree with MoE, the World Bank, and other partners how to manage any gaps in funding in the ETOL programme (by next AR). / 2. Follow up with MoE and the World Bank on domestic financing of school grants (by next AR)
Ministry of Education (MoE) capacity is stretched by need to coordinate multiple programmes	3. Agree with Strategic Affairs Department how to support strengthened Ministry coordination of partner programmes (by April 2026).
MoE has identified a gap in support for English Language teaching improvement	4. Approve a partnership with the Ministry to improve English Language teaching (by April 2026).
There are some data gaps – particularly at the programme’s outcome level	5. Complete a baseline assessment of TREE and agree how to use the remaining M&E budget to strengthen M&E of the programme (by mid 2026).
Programming needs to be adapted to the modern development approach	6. Use the planned Political Economy Analysis of FCDO’s human capital programming to inform programming and policy (by April 2026).
TREE’s scope and ambition will need to be reviewed in the light of the possible budget reduction once fully known	7. Restructure the logframe to better reflect the level of effort across the four programme components, review the weightings, and ensure data can be regularly reported (by April 2026).
There have been some challenges in effectively communicating amongst ETOL partners	8.Work closely with the World Bank, MoE and MDTF donors to ensure effective programme oversight, and delivery (by next AR)
There are significant unmet needs of children affected by education in emergencies	9. Decide how education in emergencies will be supported in FCDO -policy and programming going forward. (by April 2026)
MDTF donor contribution to climate benefits of ETOL are not captured.	10. Explore whether the UK can report climate benefits from its share of funding to ETOL (before the next ICF reporting period)
Value for money indicators do not fully reflect UK investments	11. Review vfm indicators and baseline and ensure they cover all aspects of the programme (By July 2026)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

TREE’s Theory of Change is shown below. It outlines how a combination of financial aid to government alongside targeted technical assistance will result in an improvement in the school environment, better teaching and enabling access for more marginalised children in school. This in turn will lead to improved retention and learning.

Figure 1: TREE Theory of Change

The ToC rests on six key assumptions which, despite challenges related to Ethiopia’s economic and political stability, and the UK’s own reduction in development funding, are judged to still hold:

  1. Government prioritises funding for education – the sector budget has been declining over the last five years, but Ethiopia still allocates over 20% of its budget on education. The recent IMF reform package included a commitment from GoE to fund school grants from domestic resources.

  1. Other donors fund education through the MDTF – Finland, Norway and GPE all remain committed to the programme. The World Bank has additional financing for education which we anticipate will be channelled to ETOL. The GPE Systems Transformation Grant is a separate programme and UNICEF is the grant agent. Good coordination between the two is crucial.

  1. FCDO will continue to support empowerment of women and girls – FCDO is maintaining support to education in Ethiopia although scale has reduced and the Foreign Secretary has been clear that women and girls remain a priority in our development programming.

  1. There is still space within the Ethiopia allocation for support to education – the shift to 0.3 has implications for FCDO-Ethiopia’s bilateral budget for education programming. While the team has sought to maintain the core integrity of the programme as set out in the Business Case, the scale and ambition of delivery may need to be reviewed in light of the evolving resource context.
  2. The state system will continue to function effectively in most of the country – the extent of conflict and its impact on schooling has not materially changed since the Business Case was written. Government services continue to function in most of the country although Amhara region presents major challenges. FCDO is continuing to support emergency education under the Ethiopia Crisis to Resilience programme (EC2R) and through the Education Cannot Wait’s (ECW) Multiyear Resilience Programming (MYRP).

The education team should closely monitor the impact of UK funding to ETOL over the life of the programme by engaging in implementation support missions and sector dialogue. Critical will be to support the Ministry to coordinate effectively between development programming (particularly the GPE-funded System Transformation for Education (STEP)[2] and ETOL as these are key to delivering on improved retention and learning. As noted above, bridging any gap on ETOL funding is a priority.
[2] The program aims to support a strengthened, more inclusive and equitable schools and education system for accelerating girls’ education and improving learning outcomes for all children in Ethiopia

Out of school children are primarily being targeted through our emergency education programming within the broader humanitarian umbrella business case: Ethiopia Crisis to Resilience programme (EC2R). The UK is funding UNICEF to enable displaced children to remain safe until they can re-enrol in government schools. Alongside this, Save the Children are lead partner for an Education Cannot Wait (ECW)-funded multiyear resilience programme which is funded by the UK centrally. The programme-funded adviser role is designed to ensure the UK has sufficient capacity to progress these objectives.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The impact of the programme is intended to be improved equitable access and learning for school children across Ethiopia. This is measured by the indicators shown in table 3 below. The majority of these are based on national statistics reported annually in the Ministry of Education’s Annual Education Statistical Abstract. The trends are mostly positive. However, secondary school enrolment has been falling over the last three years, and the Ministry is commissioning a study to better understand why. Conflict in Amhara (with a population of 23.88m) has affected reporting on secondary enrolment this year. The World Bank has indicated that it will formally review the overall climate benefits of the programme in 2029 as per its corporate requirements. FCDO should explore whether annual reporting is possible. The next National Learning Assessment (NLA) planned for 2026/27.
Table 3: Impact indicators assessment
Indicator	Baseline 2023/24	Target	Achieved
Net enrolment rate pre-school - Grade 12 (disaggregated)	Pre school / male 46.1%; female 44.3% (SEN: 4.1% male; 3.3% female)	Pre school / male 48%; / female 46% / (SEN: 4.2% male; 3.4% female	Pre school / Male: 59.7% / Female:56.5% / (SEN: 5.1% male: 4.0% female
	Grades 1 – 8: / male 90.9%; female 85,9% (SEN: 12.8% male; 10.5% female)	Grades 1 - 8 - male 92%; / female 87% / (SEN: 12.9% male; 10.6% female	Grades 1 -8 / Male - 95.7% / Female - 88% / (SEN: 13.4% male; 10.9% female
	Grades 9 – 12: / male: 28.5%; female 26.2% (SEN: 3.7% male; 3.4% female)	grades 9 - 12: male 30% / female 28% / (SEN: 3.8% male; 3,5% female)	Grades 9 – 12 / Male: 23.1% / Female – 22.7% / (SEN: 4.2% male; 3.7% female)
Aggregated score of grade 4 and 8 National Learning Assessment and pass rate in grade 12 national examination.	Grade 4: / 41% (40F, 42M) / Grade 8: / 37% (36F,38M) / Grade 12: / 4.4%(F), 6.5%(M)	Grade 4: / 41% (40F, 42M) / Grade 8: / 37% (36F,38M) / Grade 12: / 5%F), 7%(M)	No NLA assessment conducted / Grade 12: / 7%(F), 10.2%(M)
Number of teachers and students benefiting from climate interventions	No reporting planned until 2029		No data

The intended outcome of the programme is to increase equitable access and improved retention and learning outcomes in pre-primary and primary education. There are three outcome indicators are shown in table 4 below. No reporting is available (or planned) this year for two of the indicators[3]. The third indicator – access to pre-primary education in underserved regions – has been achieved primarily through mobilisation campaigns. Of the six regions targeted, three have shown improvement in enrolment rates since 2024/25. Overall, there has been a 2.24% increase so slightly exceeding the target. See annex C for details.
[3] The TREE Business Case attributes UK aid to improving education for 1 million children. This attribution will need to be reduced in line with the likely reduced UK financial contribution.
Table 4: Outcome indicators assessment
Indicator	Baseline	Target	Achieved
Share of grade 3 students achieving functional reading level percentage – (disaggregated by gender and disability)	25%	25%	Assessment planned for 2026/27
Pre-primary average early childhood education assessment score for pre-literacy and numeracy (percentage-disaggregated)	51.4 and 64	51.4 and 64	Assessment planned for 2027/28
Increase in enrolment in public pre-primary education in the regions below the national average (DLI 4)	0	2%	Achieved

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Whilst all indicators are currently on track to meet the milestones, the outcome confidence rating for the programme has been graded as Amber due to the broader ODA reduction; these add a high level of uncertainty as to whether the programme will be fully achieved and that is dependent on the World Bank assigning additional finance. There should be clarity on the availability of additional IDA later in 2026. At that point a decision will need to be made on whether to restructure ETOL. If the programme is restructured, FCDO-Ethiopia should engage to ensure that its priorities are maintained in the programme. Education remains relevant to the UK’s broader objectives in Ethiopia, which are focused on human capital development as an engine for broader economic growth.
## C. DETAILED OUTPUT SCORING

Output Title	Schooling environment better equipped to support learning (including climate)
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this reviewme	Progress
1.1 Pre-primary classrooms constructed by the Programme with attention to climate change impacts (Number)	Updated school construction standards approved	B / Moderately not met expectations
1.2 Share of targeted schools receiving the correct amount of school grant on time (Percentage)	School grant formula approved	A / Met expectations
1.3 Inclusive Education Resource Centres (IERCs) established	100	A++ / Met expectations
1.4 Number of schools meeting minimum Teaching and learning (TLM) standards (DLI3)	Updated minimum standards approved	A / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 1.1: The Annual Review team discussed with the World Bank and with Ministry officials. Preparations are well underway for the construction of 200 primary school classrooms by December 2026 based on the existing national guidelines. A draft of the guidelines has now been received but not yet finalised.

Indicator 1.2: The government has developed national school grant guidelines in preparation for funding school grants from domestic resources (they have been fully funded by donor programmes previously). In the interim, as dependency on external financing is phased out, it is expected that ETOL resources will be utilised to implement a targeted school grants system linked to School Improvement Plans (SIPs). School grants are intended to empower schools to enhance their learning environments. Per pupil amounts and equity adjustments are summarised in the footnote[4]. The first payments should be made in the 2025/26 academic year.
[4] Pre primary(120 birr/student) primary (100 birr/student), grade 7 – 12 (120 birr/student), Inclusive Education Resource Centres (flat payment of 15000 birr/centre), minimum allocation for small school fixed at 24,000 (pre-primary, middle ansecondary) and 20,000 (primary and Alternative Basic Education Centre)

Indicator 1.3: The Ministry reports that it has established 100 new IERCs in the past year which resulted in an additional 40,000 children with disabilities benefiting from the provision in targeted schools (see output 3 below).

Indicator 1.4: MoE has established minimum teaching and learning material standards for all schools. These standards for student textbooks and teacher guides are essential to ensure quality, consistency, and effective utilisation of teaching and learning materials (TLMs) across the education system. The rationale for the introduction of this minimum standard is to ensure uniformity, improving quality, enhancing utilisation, motivating learners, expanding access, strengthening monitoring and evaluation, and establishing national standards.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output over the past year. The team should follow up on the revision of the construction guidelines as a matter of priority and review all outputs and indicators in advance of the next Annual Review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As this is the first Annual Review, there are no previous AR recommendations. The GEQIP-E Programme Completion Review noted that school grants are critical to the operation of schools but are a core recurrent cost which should be funded from government’s own resources. It is encouraging that the government has now committed to this, but the team needs to monitor the transition carefully.
Output Title	Improve teaching in schools
Output number:		2	Output Score:	A
Impact weighting %		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Share of pre-primary and Grade 1-6 teachers receiving practice-based training (Percentage)	0	NA
2.2 Key Teachers in Primary Grades Trained as School-based Trainers (Number - cumulative)	0	NA
2.3 Primary School Leaders Certified (Number cumulative) DLI 2	School leadership framework approved	A / Met expectations
2.4 Share of primary school teachers achieving minimum proficiency on subject contact knowledge. DLI 1	Updated inspection framework	A / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicators 2.1 and 2.2 – No targets for this year as no funding was planned for these activities until all the delivery systems had been established and training materials refreshed. The Ministry is responsible for identifying beneficiaries of training programmes and delivering training. The World Bank has oversight of these inputs.

Indicator 2.3: MoE has designed a new School Leadership Capacity Enhancement Framework to provide structured, hands-on, and competency-based professional development training tailored specifically for Ethiopian school leaders. It is expected to improve school leadership selection and development (thus creating a more capable and diverse leadership corps) and equip them with the skills they need to support teachers in implementing new pedagogical approaches and managing the transformation of teaching and learning in their schools through enhanced administrative and leadership capabilities. This builds directly on the FCDO funded work under GEQIP-E's TA programme: Technical Assistance to Reinforce GEQIP in Ethiopia (TARGET).

Indicator 2.4 MoE has developed a new teacher skills improvement framework to enhance pre-primary and primary school teachers' pedagogical content knowledge, instructional skills, and professional competencies. The new framework includes enhanced school inspection standards. The index in school inspection standards, which focuses on observing effective teaching practices in the classroom and discussions with teachers and additional similar index will be identified and enhanced; and a score rubric set to classify a teacher as achieving the minimum proficiency.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output this year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

As this is the first Annual Review there are no previous AR recommendations. This output is crucial to improving learning lessons and as per the recommendation in the GEQIP-E PCR, we should work with partners to advocate for approaches to teacher training that are evidence-based and fully aligned with the focus on improving foundational learning outcomes.

Effective school leadership is key to ensuring these pedagogical shifts are supported at school level and it is good to see the work started under our TA programme during GEQIP-E now being rolled out nationally. Implementation needs to be monitored closely.
Output Title	More girls and marginalised children staying in school
Output number:		3	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Students with Special Needs in the Inclusive Education Resource Centres and Satellite Schools (Number - cumulative) DLI 5	160,000	196,817 students enrolled (A+ / Moderately exceeded )
3.2 Share of teachers trained in Inclusive Education (Percentage)	0	NA
3.3 Female students enrolled in pre-primary schools with pre-primary facilities provided by the programme (number)	0	NA
3.4 Female key teachers in primary Grades Trained as School-Based Trainers (number-cumulative)	0	NA

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 3.1: The Ministry planned to establish 100 new Inclusive Education Resource Centres (IERCs) and to strengthen 300 of those established under GEQIP-E in 2025/26. This was achieved as planned. As a result, the total number of children benefitting from the IERCs increased from the baseline of 157,000 to 196,817 in 2025/26. This exceeded the target set for this year by 36,817. The attainment report has been received and is in the process of being verified.

Indicators 3.2 – 3.4: No targets for the first year of the programme as the focus was on establishing the systems to deliver these activities in the outer years.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output. We will review all outputs in advance of the next Annual Review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The GEQIP-E PCR recommended targeting scarce resources more effectively to address equity issues by working more cross-sectorally. It is recommended that the team conduct an analysis of how FCDO support to the social sectors in Ethiopia should pivot to adopt a modern development approach. Progress will be reported at the next Annual Review.

It is recommended that the logframe better captures programme-funded advisory support to EC2R, the centrally-managed programme Inclusion Support Programme for Refugee Education (INSPIRE), and the funding provided for education in emergencies by Education Cannot Wait (ECW).
Output Title	Enhanced government capacity to design, implement and / monitor reforms
Output number:		4	Output Score:	NA
Impact weighting (%):		0%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
4.1 World class advice to government to implement key reforms	TBC	Met expectations
4.2 Enhanced programme monitoring and evaluation	TBC	Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 4.1 This indicator is designed to capture progress on designing a TA programme that sits alongside our support to government through ETOL. We have now agreed with the Ministry of Education that the priority intervention area of our technical assistance will be on improving English Language teaching, particularly in Grades 7-8 when students are expected to transition into English medium instruction. Teachers are currently not equipped to deliver this shift. This is an area of UK comparative advantage and part of a broader wish to optimise cultural and people to people links between our two countries.

Indicator 4.2: Component 4 of the programme was optional in the Business Case. It is designed to enhance our M&E capacity. The team have commissioned a baseline assessment of TREE and will consider the recommendations for how they should proceed with any M&E component of the programme. The study is being conducted by the Policy Studies Institute, and this is the first time we have awarded a grant directly to them. They were involved in the Researching Systems of Education (RISE) research in Ethiopia. They have contracted two members of the Cambridge University team who were also involved in RISE to ensure the lessons are learned.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

1. There have been no changes over the past year. However, we recommend updating the logframe with clear targets against the existing indicators. We also recommended adding an additional indicator to capture the impact of our influencing work on the sector. This could include the team’s collaboration with CMPs such as the Scaling Access and Learning in Education programme (SCALE) .
2. The team should also consider adding an output to capture the impact of the Investment Programme Financing (IPF) component of ETOL. The IPF works alongside the P4R to support technical assistance activities for system strengthening and capacity building activities in support of the results of the programme. The total investment is $15 million over the lifetime of the programme and it is fully funded by the MDTF so currently 80% attributable to UK funding. It focuses on edtech solutions, managing school construction, and programme evaluation and monitoring,
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

One of the recommendations of the GEQIP-E PCR was to strengthen the government’s capacity to coordinate partners. This output is designed to provide additional support to MoE from a Programme-Funded Adviser (PFP) to strengthen oversight and coordination of UK investments in basic education from both bilateral and multilateral sources.

The PFP will also enable FCDO-Ethiopia to take forward the recommendation in the PCR to: i) work with the World Bank and GoE to mainstream the response to conflict and crises into ETOL and ii) include a focus on the response to conflict and crisis in the next phase of UK education programming.
## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The team has reviewed the VfM metrics in the TREE Business Case and agreed a final list of metrics which is reproduced in Annex B. They have also included baseline data for most of the indicators which they plan to track over the lifetime of the programme. UK funding to ETOL will be disbursed once the year 1 DLIs achievement report has been verified, so there will be a more in-depth vfm analysis in the 2027 AR. Some headlines below:

  1. Economy: an Accountable Grant was signed with the Policy Studies Institute with a total value of £162,995. The grant was awarded on a non-competitive basis due to the contracting party’s demonstrable and longstanding expertise within the education sector, as well as the value for money derived from their proven capability and timely delivery.. The team ensured the grant offered good value for money by engaging with Corporate Delivery Unit (CDU) to benchmark fee rates against international and local norms

  1. Efficiency: Drop out from grades 1 – 6 has been steadily declining since 2018/19 and now stands at 16.3% for boys and 18.3% for girls. Similarly, completion rates in grades 6 and 8 have also been improving (although not directly attributable to the programme).

  1. Effectiveness: The main measure of effectiveness is improvements in learning outcomes at pre-primary and grade 3. There is no new data for this year. Encouragingly, RISE research found that some groups of children from typically disadvantaged backgrounds (such as rural areas) were more likely to see larger learning gains over the GEQIP-II period (2012 – 2019).

  1. Equity: There has been good progress on both disability inclusion and reducing disparities between the regions. The gender parity index has also been steadily improving.

The MDTF also funds the Investment Project Financing (IPF) component of the ETOL which supports technical assistance activities for system strengthening and capacity building activities in support of the results of the programme. The total value of this component is $15 million. It is recommended that the programme team develop metrics for measuring the VfM of this component.
Assessment of whether the programme continues to represent value for money

Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, the review judges that there is sufficient evidence to continue the programme.

E: RISK

Overview of risk management

The programme has a comprehensive risk register that is maintained and updated monthly on AMP, with quarterly reviews conducted by the Programme team and PRO to ensure effective monitoring and mitigation of risks. Risk discussions are held quarterly with the SRO to address emerging issues and update mitigation measures. The programme’s risk appetite for Strategy and External Context, Policy and Programme Delivery, Safeguarding, and Financial and Fiduciary domains is classified as Receptive. The risk appetite for People, Public Service Delivery and Operations, and Reputation is assessed as Cautious. The programme’s overall risk appetite is aligned with the established office-level appetite.

The World Bank provides further oversight of UK Financial Aid through implementation support missions (ISMs) which include an assessment of fiduciary, social, and environmental risks and an agreed action plan with specific mitigation actions. The first ISM was conducted in December. Most actions were reported as completed or progressing as planned, with remaining efforts focused on strengthening regional school construction management and improving procurement efficiency. Overall progress on mitigation actions was rated “satisfactory”. Each quarter, the ETOL programme risks and the updated delivery chain maps are reviewed in collaboration with the World Bank.

Changes to programmatic risk assessment

The overall risk rating of the programme is moderate. Relevant risks are identified against each of the risk categories through the risk register and are being monitored on a quarterly basis. The last quarterly update is carried out in the month of Nov 2025.The education team jointly support the review and management of identified risks on regular basis. Risks are monitored and escalated to the Human Capital team risk register and then to the Embassy’s Delivery Committee as appropriate.

Strategy & Context The risk rating is major. There are two risks identified within the Strategy & Context section. Firstly, ongoing conflict and unrest in regions such as Amhara and Oromia is leading to displacement of children from school – an estimated 9 million are impacted. To mitigate this risk, FCDO is collaborating closely with the humanitarian team to mitigate the impacts on affected communities. Additionally, the team are working with government to see how schools can be made safer. The second major risk is the impact of UK’s overall ODA reduction, which may threaten the delivery of the programme in line with the initially envisaged scope. To address this, FCDO is engaging with other partners, such as the World Bank to adapt the programme to reflect the broader funding landscape.

Reputational Risk The major risk identified is the provision of Financial Aid in the context where the Government of Ethiopia faces constraints in allocating sufficient budget to the education sector, alongside broader challenges associated with instability and conflict. While the government has made efforts to maintain a significant share of public expenditure for education, overall resource limitations may affect the pace and scale of progress. As FCDO implements its shift from donor to investor, we will continue to engage on social sector financing and advocate for sustained investment in education. In parallel, opportunities to strengthen education financing will be explored in partnership with government, alongside continued support to the sector through targeted technical assistance on English proficiency.

Safeguarding risk The risk rating was decreased from major to moderate. The primary safeguarding risk is the reluctance of victims to report sexual exploitation, abuse, and harassment (SEAH) incidents. The World Bank reported in their December mission that there had been satisfactory progress with the deployment of specialists, maintenance of the GEQIP-E grievance redress mechanism (GRM), and continuation of gender-based violence (GBV) prevention measures. The team will assess the capacity of the TA supplier to manage safeguarding risks during procurement.

People risk This risk was changed from moderate to minor. The risk identified is that there will be challenges to FCDO in recruiting and retaining qualified personnel. A recruitment strategy is now in place, and the education team is fully staffed with an Addis-based Programme-Funded G-7education adviser expected to start work in April 2026.

Public Service Delivery & Operations-The moderate risk is the ongoing procurement delay and potential reduction in the value of Technical Assistance due to the broader ODA budget reduction, which could lead to a lack of interest from service providers and negatively affect programme outcomes. To mitigate this risk, the education team has agreed with the Ministry a revised scope of work which focuses on supporting the transition to English Medium of instruction in middle school.

Financial & Fiduciary The risk was reduced from moderate to minor. Two key risks have been identified. Firstly, the risk that the purchasing power of the programme budget could decline significantly due to the devaluation of the Birr. Transferring MDTF funds in GBP allows the government to set prices in hard currency and better reflect current market conditions reduces this risk. Secondly, the programme operates in some hard-to-reach, conflict-affected areas, which can result in a poor understanding of activities and outcomes, low budget utilisation by Regional Education Bureaus (REBs), and an increased potential for fraud. The World Bank has worked with government to reduce the risks around transfer of funds to lower levels through timely budgeting, enhanced management of School Grants (SGs) via guideline revision, cascading support and orientations, and the assignment of full-time Ethics and Anti-Corruption (EAC) officers at all levels. Progress was rated as satisfactory in the December mission.

Policy & Programme Delivery The risk rating was reduced from major to minor, the main risk is that changes in the external context—such as political instability, conflict, or climate-related shocks—may negatively impact programme delivery. This could undermine implementation efficiency and effectiveness, ultimately leading to failure to deliver the programme’s outcomes. The team are managing the risks to programme delivery by actively engaging with wider office processes such as the Partnership Principles Assessment update and the various embassy mission boards (eg stability, migration, humanitarian and human development) to monitor the direction of travel and ensure the programme is actively managed.

Update on Partnership Principles

The Partnership Principles Assessment is being updated to cover January-December 2025. The PPA captures inputs from wide spectrums of areas and sectors including education. There have been some challenges mainly due to the ongoing conflict and instability in the country. However, the Ethiopian government’s commitment to public financial management has shown improvement during the year. In recognition of these opportunities and challenges, the FCDO has introduced a series of measures at portfolio level. These include human rights and peacebuilding programme, conflict and instability tracking, third party monitoring and safeguarding arrangements.

The Federal Ministry of Education’s commitment to delivering quality education for for all remains strong, reforms are being implemented to improve teacher preparation and management, and a recent salary increase has helped to maintain morale in the teaching profession. The inclusion of refugees and IDPs into schools is a priority for the Ministry and their commitment has resulted in an additional $69 million in financing (from IDA and the Dutch) to integrate UNHCR-supported refugee schools into the government system. This funding is currently being processed.

The UK mitigates safeguarding and fiduciary risks in the education programme by channelling financial aid to the government via the World Bank. This provides an additional layer of oversight of UK funding. A recent World Bank mission (December 2025) noted satisfactory progress on financial management, procurement and safeguarding. The programme is building on financial management systems established by GEQIP-E which is providing assurance that funds are used for their intended purposes. Preparations are well underway for planned procurement in the coming year. The World Bank team advised MoE to further strengthen safeguarding by recruiting staff in the southwest and ensuring grievance redress mechanisms are functional.

Annual Statement of Progress (financial aid programmes only)

Current level of fiduciary risk and direction of travel since last ASP	Moderate Improving
Specific assessment of corruption risk and direction of travel since last ASP	Major worsening
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

The UK’s support to the TREE programme has two main components: Financial Aid that is provided through the World Bank Multi-Donor Fund using a Payment by Results mechanism (PBR); and an FCDO-managed Technical Assistance procurement, which is ongoing to complement and amplify the impact of the Financial Aid.

The UK transferred £12.7 million to the World Bank Trust Fund in the last financial year. The World Bank has confirmed that this funding has been fully committed to fund the UK’s share of an advance to government (£2.6 million), the IPF component (£1.77 million) and the payment for achievement of the year 1 DLIs (£11.97 million). FCDO made a second payment of £17.3 million to the MDTF in January 2026 to cover the UK’s share of the commitment to the payment for the achievement of the year 2 DLIs and support for the IPF component of ETOL. This brings total UK disbursement to the ETOL MDTF to £30 million.

ETOL programme delivery is progressing as expected. All the year 1 DLIs have been achieved and once the results are verified, the World Bank will make a payment to the government. Implementation Progress had an overall rating of satisfactory in the December 2025 World Bank Implementation Support Mission. As the programme started less than a year ago, an independent audit has not yet been conducted. However, satisfactory progress has already been made in implementing fiduciary risk mitigation measures. A comprehensive audit of GEQIP-E is underway, albeit delayed. The team will follow up on findings and recommendation of this audit and pursue corrective actions, including recovery of misused funds, should the final audit findings warrant such action.

The World Bank is coordinating well across its human capital programme and ETOL and it is showing leadership in improving human capital in Ethiopia. More challenging has been maintaining effective communication with ETOL partners and coordinating with the GPE-funded STEP programme. A quarterly ETOL partners meeting is helping to improve ETOL partner communication and MoE has agreed to establish Task Forces to strengthen coordination across STEP and ETOL. The World Bank is managing the GPE System Capacity Grant effectively.

Procurement of the TA component which aims to directly deliver innovative approaches to improving education quality and support delivery of FA was delayed pending confirmation of budget allocations. However, the Monitoring and Evaluation (M&E) and Programme Funded Education Advisor Components have progressed as planned. The M&E component has progressed through a partnership with Policy Studies Institute (PSI), with a work currently underway to establish a baseline for TREE. This work builds on the evidence and database developed through the Research on Improving Systems o Education (RISE) Programme. To date, £30.23 million has been spent on the programme, comprising £30 million in Financial Aid Delivered through a World Bank- managed Multi-Donor Trust Fund (MDTF) and £0.23 million allocated to TA, including a Programme funded education advisory support.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation The M&E framework for ETOL is described in detail in the World Bank Programme Appraisal Document. The UK currently has no plans to commission a separate impact evaluation of the programme but will use the TREE baseline assessment to advocate with partners for strengthened programme evaluation. The programme team have been monitoring the programme closely through participation in Bank missions, a field visit to Tigray with the humanitarian team, the Education Technical Working Group and the ETOL partners group. As coordinating Agent for GPE funding to Ethiopia, FCDO are also closely involved in the M&E for the GPE funded Systems Transformation and Girls Education Programme (STEP) which is implemented by UNICEF. The Annual Review has benefited from quality assurance from an FCDO education adviser based in South Sudan.

Evidence There are four recent pieces of evidence that are relevant to the TREE programme and UK wider objectives in the education sector in Ethiopia. These are:
- A World Bank education policy dashboard survey which found there have been improvements in foundational learning and school readiness since the last survey which was conducted in 2021.
- A study of education sector financing which found that although education still receives a relatively large share of the budget, the shrinking overall envelope has led to a sharp drop in government funding to the sector.
- A sector analysis which will underpin the next Education Sector Development Plan. The analysis highlights the major challenges faced by the sector and recommends strategic actions to address these challenges.
- The GEQIP E comprehensive exit evaluation, which outlines key challenges, lessons learned, and recommendations to sustain and enhance the effectiveness of future programmes, was concluded in July 2025. The lessons and recommendations will be considered and pursued as appropriate in the potential restructuring of ETOL and in the ongoing adaptation of the TREE programme.

Learning: The key learning so far is from the GEQIP-E Project Completion Review which was conducted earlier this year. The team have drawn on lessons in their engagement with ETOL. The recently commissioned PSI-led work on developing a baseline for the evaluation of TREE should also yield valuable insights. Finally, the office is engaging with the Governance Centre of Expertise to conduct a Political Economy Analysis of FCDO-Ethiopia's human capital programming to inform the pivots to a modern partnership approach.

Date of last narrative financial report	October 2025	Date of last audited annual statement	1st Audit of ETOL funds expected December 2026

ANNEX A: YEAR 1 AND 2 DLI INDICATORS

Year 1 DLI Targets and achievement[5]
[5] Yellow highlighted are DLIs funded by the MDTF

No.	DLI	Target	Achieved	Payment
1	Share of primary school teachers achieving minimum proficiency on subject contact knowledge	Inspection standards	Yes	$10m
2	Primary School Leaders Certified	School leadership framework	Yes	$10m
3	Number of schools meeting minimum TLM standards	Updated minimum standards	Yes	$4m
4	Increase in enrolment in public pre-primary education in the regions below the national average (Percentage)	2%	Yes	0
5	Students with Special Needs in the Inclusive Education Resource Centres and Satellite Schools	160,000	Yes	0
6	Share of targeted schools receiving the correct amount of school grant on time	School grant guideline	Yes	$10m

Year 2 DLI Targets

No.	DLI	Target
1	Share of primary school teachers achieving minimum proficiency on subject contact knowledge	baseline established
2	Primary School Leaders Certified	3000
3	Number of schools meeting minimum TLM standards	5000
4	Increase in enrolment in public pre-primary education in the regions below the national average	5%
5	Students with Special Needs in the Inclusive Education Resource Centres and Satellite Schools	180,000
6	Share of targeted schools receiving the correct amount of school grant on time	60%

ANNEX B: VFM BASELINE INDICATORS FOR TREE

TREE VfM Indicators
VfM Indicator / As stated in the BC (General)	VfM indicator aligning with TREE LF / (Specific)	BL
ECONOMY
Cost per teacher / leader trained	Cost per key Teacher in Primary Grades Trained as School-based Trainers	$400 for 10-14 days CPD incl transportation
Teaching / learning materials unit cost per grade /subject	Average cost per textbook procured	Average $5/textbook
Disability inclusion	Cost per IERC constructed
Daily rate of technical assistance / advocacy - international and local	TA fee rates for technical leadership positions	xxx international / Xxx local
EFFICIENCY
Average reduction in dropout rates for supported schools	Reduction in grade 1 – 6 dropout rates.	16%f; 18%m
Average improvement in transition rates for supported schools/students	Completion rates in grades 6 and 8	Grade 6 / F 67.1% & M 67.9% / Grade 8 / F 61.8% & M 58.8%
Number of teachers trained in improved methods	Share of pre-primary and Grade 1-6 teachers receiving practice-based training	0
Effectiveness
Number of additional marginalized children (including girls attending school or other educational opportunities~)	Increase in enrolment in public pre-primary education in the regions below the national average (Percentage)	0
Reading and numeracy scores at key grades and subjects	Share of grade 3 students achieving functional reading level percentage - disaggregated by gender and disability)	25%
Number of teachers implementing improved methods	Share of primary school teachers achieving minimum proficiency on subject contact knowledge. (proxy measure)	TBD
EQUITY
Reduce gap between regions	Increase in enrolment in public pre-primary education in the regions below the national average (Percentage)	0
Reduced gap in enrolment between girls and boys	GPI in pre-primary and primary – available from Annual Abstract	0.96 and 0.93
Disability inclusion	Number of students with Special Needs in the Inclusive Education Resource Centres and Satellite Schools	157,000
Effectiveness
Improvement in learning outcomes	Aggregated score of students on Grade 4 NLA (gender disaggregated) / Pre-primary average early childhood education assessment score for pre-literacy (Percentage)	Grade 4: 41% (40F, 42M) / Pre literacy 51.4; pre numeracy 64

ANNEX C: PRE-PRIMARY ENROLMENT IN UNDERSERVED REGIONS
	Region	EFY 2016 (2023/24)			EFY 2017 (2024/25)			Absolute Increase/ / Decrease in Enrolment	% Increase/ / Decrease in Enrolment
		Male	Female	Total	Male	Female	Total
1	Afar	13,792	12,336	26,128	14,787	13,101	27,888	1,760	6.74
2	Amhara[6]	392,996	380,526	773,522	392,996	380,526	773,522	0	0.00
3	Somali	33,376	26,990	60,366	50,598	42,478	93,076	32,710	54.19
4	Benishangul / Gumz	14,938	10,662	25,600	11,952	10,599	22,551	-3,049	-11.91
5	Sidama	86,403	85,779	172,182	87,611	85,890	173,501	1,319	0.77
6	South West Ethiopia	49,107	44,391	93,498	46,103	40,484	86,587	-6,911	-7.39
	Total	590,612	560,684	1,151,296	604,047	573,078	1,177,125	25,829	2.24
[6] EFY 2016 data have been used for Amhara, as there were no data for EFY 2017