BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Transforming Education in Ethiopia (TREE)
Directorate/ Post	East Africa	Contact name	TREE PRO
Original programme budget	£110m	Country or region targeted	Ethiopia
Cost extension value (if applicable)	N/A	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	HMT (on 19/08/2024) / Minister (on 07/05/2024)
New increased or reduced programme budget (if applicable)	N/A	Original programme start and end dates	24 February 2025 – 31 December 2029
Latest AR programme score	A	New programme end date (if applicable)	N/A
		Programme ID	400225

Detailed information
Programme summary	This programme aims to strengthen the long-term capability of Ethiopia’s education system by working through government systems to improve foundational learning. / The intended impact is improved equitable access and learning outcomes for school children across Ethiopia, with a focus on access, and learning in general education. The programme comprises four components: - / Component 1: Financial Aid (FA) – delivered through a World Bank administered Trust Fund using a Programme for Results (PforR) approach to support the Ethiopia Transforming Education for Learning (ETOL) programme, alongside Finland, Norway, and the Global Partnership for Education (GPE). / Component 2: Technical Assistance (TA) to improve education quality and amplify FA impact. This amendment changes the procurement route for this component from a competitive process to single-source contracting with the British Council. / Component 3: Programme–Funded Advisor providing advisory support to the Ministry of Education on planning, coordination, and budgeting. / Component 4: Monitoring and Evaluation (M&E) – Independent verification and learning to assess performance and inform adaptive management.
Changes	This amendment revises the procurement approach under component 2 (Technical Assistance) from a competitive procurement to single sourcing the British Council. The original design envisaged a £20 million TA contract procured competitively under the Global Development Delivery (GDD) Framework, covering four areas: teacher training, school leadership, support to marginalised girls, and English language. Early Market Engagement confirmed a capable and competitive supplier market. / However, we are narrowing the scope of the TA to a single, high-impact intervention where we will strategically prioritise English language training. This is due to: - / It’s critical role in learning outcomes during transition to English-medium instruction / A request from Government of Ethiopia, including ministerial engagement / The UK’s comparative advantage in English Language Education. / The other three areas under the original TA component will now be progressed through Financial Aid and other FCDO funded projects including potentially EC2R. / The decision to single source the British Council is justified on both strategic and value for money grounds: / Unique capability and comparative advantage: The British Council has the globally recognised English language offer, including in teacher training and assessment. The Council has had a presence in Ethiopia since the 1940s and has previously worked with the Ministry of Education on English Language teacher improvement projects. / Speed and delivery certainty: A competitive procurement would introduce significant delays, risking misalignment with the next Ethiopian Academic Calendar year. Single sourcing enables rapid mobilisation of a time-sensitive intervention. / Opportunity to Co-design and government ownership: this approach will enable the co-design of interventions in partnership with the Ministry of Educatoin, ensuring alignment, government ownership, and integration within existing systems – key factors for effectiveness and long-term sustainability. The British Council’s well-established relationship with the Ministry positions it strongly to facilitate and manage this collaborative development approach. .
Implementation	The implementation approach remains unchanged except for the procurement route under Component 2, which enables accelerated mobilisation. The delivery will focus on: / Strengthening teacher English proficiency / Improving classroom practice (including pedagogy) in English – Medium Instruction / Embedding sustainable systems for teacher development
Budget	The Country Board has now agreed all portfolio allocations, including to HCDT, and this is confirmed as affordable. The implementation timeline remains unchanged, with the business case concluding on 31 December 2029.
Impact	This amendment enables the timely delivery of a focused, high-impact English language intervention, expected to: / Improve teaching quality in English – medium settings, specially enhance teachers’ subject knowledge and pedagogical proficiency / Establish a pool of expert trainers in all regions and a system for ongoing support for English Language teaching in schools, including edtech solutions / Support student transition from middle to secondary school / Contribute to improved learning outcomes
Risk	Key risks have been identified and risk mitigation measures and put in place. The overall risk rating for TREE remains as set out in the original Business Case. The approach will mitigate the risk associated with potential delay in TA supplier procurement and limited government ownership while enhancing sustainability of impact over the long term.
Results/Monitoring and Evaluation	There are no changes to the original business case, including the theory of change, approach, or monitoring and evaluation arrangements. The English Language focused TA programme will be expected to include independent tracking and annual reporting of impact on teachers’ English Language knowledge and pedagogical competency. The TREE programme log frame will be updated to reflect specific inputs and outputs of the English language intervention, to be defined in the inception phase.