## Annual Review Template

Title: Strengthening the Global Architecture for Protection from Sexual Exploitation and Abuse and Sexual Harassment (PSEAH)
Programme Value £ (full life): £20,000,000		Review date: Sep 2025
Programme Code: [AMP ID#] 400233	AMP start date: 22/10/2024	AMP end date: 30/06/2029

Summary of Programme Performance
Year	24/25
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0007015.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400233

A. SUMMARY AND OVERVIEW
Description of programme

The Strengthening the Global Architecture for Protection from Sexual Exploitation and Abuse and Sexual Harassment (GA-PSEAH) programme succeeds the Safeguarding Innovation and Engagement programme which ended September 2024. This is the first year of the programme and first Annual Review.

The GA-PSEAH programme aims to support and develop global architecture to improve Protection from SEAH (PSEAH) in humanitarian, development and peace settings by:
- Scaling up, piloting and implementing PSEAH global tools, cross sector initiatives and approaches.
- Supporting PSEAH coordination and multistakeholder dialogue to address common challenges and to improve collective action.
- Seeking the PSEAH tools and ‘global public goods’ of the future through research and pilots to address critical gaps in evidence on what works to prevent and respond to SEAH in different contexts.
These priorities remain relevant and central to the programme but changes in the ODA landscape may impact the scale of ambition or delivery in future years.
[note] Changes relate to the difficult decision made by the UK Prime Minister to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. The UK remains committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme scored an ‘A’ for the year with all outputs meeting expected outcomes.

Despite significant geopolitical and financial challenges affecting PSEAH work and the wider international development and humanitarian system, the programme has maintained momentum in PSEAH efforts, built consensus around and support for key PSEAH tools, and deepened dialogue and cooperation with a wide range of partners to progress policy thinking and evidence. The programme plays a pivotal role in shaping global standards and driving alignment across global PSEAH architecture.

Key achievements include:
Output 1: Collective tools to drive alignment and improvements in PSEAH standards, vetting, and data analysis (Score: A+)

This output continued to expand access and improve usability of key tools:
  1. Misconduct Disclosure Scheme (MDS) gained visibility through increasing UN recognition and use, expanding to 64 new members against a target of 60 (despite 3 organisations withdrawing from the scheme) reaching a membership of 370. The FCDO is working towards joining the scheme.
  2. The Harmonised Reporting Scheme (HRS) grew by 43 organisations against a target of 25-50, representing 42% growth, to 102 organisations. The scheme improved user-interface, introduced multilingual features and held country-level pilots in Ethiopia and Bangladesh, as well as publishing quality data analysis including joint analysis with the UN. We are seeing a shift in donors beginning to accept SEAH reports via the HRS system.
  3. Humanitarian Quality Assurance Initiative (HQAI) exceeded expectations with 91 new audit partners (48% of which are local) against a target of 78. FCDO now recognises HQAI Core Humanitarian Standard certification for a significant proportion of our due diligence process and there is growing interest from other donors in this potential to align and streamline approaches to due diligence.
These global PSEAH tools are critical because they provide shared, high-quality resources that help organisations across the sector align on standards, improve accountability, and respond more effectively to SEAH risks. By addressing common challenges and filling systemic gaps, they enable coordinated action, reduce duplication, and promote consistency in safeguarding practices globally. Their collective use strengthens the overall architecture for protection from SEAH, ensuring that efforts are not only locally relevant but also globally coherent and sustainable. Their success in a challenging year, reflects their increasing relevance and value, strong strategic alignment and responsiveness to user and system needs, and increasing interest and engagement from key international partners.

Output 2: Sustained co-ordination in highest risk areas and key sectors supports improved standard and action on PSEAH (Score A)

  1. Private sector coordination continued through the Safeguarding Leads Network (SLN). Membership grew to 47, with 97% of workplan outcomes achieved.
  2. The UN Inter-Agency PSEA Capacity Project (PSEACap) deployed specialist PSEA coordinators to 10 high risk countries.
Coordination efforts were sustained and expanded despite funding pressures. SLN delivered high-quality learning and technical sessions with strong participation, grounded in the Common Approach to Protection from Sexual Exploitation, Abuse and Harassment (CAPSEAH) and practical ways in which it can be implemented by private sector organisations. PSEACap embedded PSEA into humanitarian planning and leadership structures with an emphasis on localisation and survivor-centred approaches which is enhancing sustainability and impact in fragile contexts. SLN and PSEACap both sent representatives to the April 2025 Wilton Park CAPSEAH Dialogue on PSEAH Resourcing.

Output 3: Evidence and dialogue on PSEAH resourcing priorities and models (Score A)

  1. The first CAPSEAH Dialogue on ‘Sustainable and Effective Resourcing Models to Protect against Sexual Exploitation, Sexual Abuse and Sexual Harassment’ was a success, with a technical working group, published Thinkpiece and Wilton Park Conference.
  2. Mapping of global public goods has been completed and work to establish pilots to improve strategic PSEAH partnerships at national level is progressing well.
This output delivered strategic convening and consensus-building across sectors at a critical time for the sector. The Wilton Park event successfully demonstrated that CAPSEAH can offer a framework and platform for dialogue on common challenges, and catalysed actionable outcomes, achieving broad agreement that PSEAH work is an essential, not optional cost of doing business at a time when the international system is facing significant budget cuts and difficult prioritisations are being made. It also achieved a step change in agreement that achieving efficiencies through collective approaches and coordinated resourcing is more important than ever. The mapping of and support for PSEAH ‘global public goods’ includes the tools supported by this programme, with growing consensus that these need to be supported by sustainable funding models. Work to pilot and learn what works to establish effective strategic partnerships for PSEAH at country level has the potential to translate dialogue and commitments into real actions, to drive systemic change and further alignment around collective approaches.

Output 4: Research and case studies on what works in different countries (Score A)

4.1 The Harmonised Reporting Scheme has published two biannual reports (in November 2024 and May 2025) with a collective analysis of PSEAH trends as well as two country analyses (Ethiopia & Bangladesh, in July 2025).

The HRS provided valuable global and national insights and evidence on SEAH that was previously unavailable. These reports provided comprehensive trend analysis and were widely welcomed across the aid sector, with several organisations joining the HRS following their publication. The HRS biannual analytical report is already widely recognised and is a vital asset to improve policy responses across the system, with strong (and growing) demand and sector-wide interest in this new global public good. In addition to global analysis, HRS made progress against their objective to strengthen local capacity among HRS participant organisations so they can safely collect and report SEAH data at the field level. Two pilots in Ethiopia and Bangladesh had sustained engagement with over 40 organisations and offered valuable insights into national-level SEAH reporting trends and challenges.

Lessons Learned
- The tools supported by this programme are streamlining approaches and have real potential to reduce bureaucracy and costs - there is growing recognition of the value of these tools and the key role they play in the global PSEAH architecture. Increasing alignment with other systems and tools (e.g. HRS with UN systems and HQAI CHS certification passporting due diligence requirements) is beginning to reduce duplication and fragmentation and has real potential to reduce costs. However maximising these efficiencies will require continual advocacy.
- Despite good progress, the tools are still fragile – while there is growing agreement that these tools are PSEAH global public goods, they are still reliant on funding from the UK and limited other sources. We need to continue working with the wider sector to develop sustainable funding models.
- Private Sector continues to require tailored support - The SLN’s growth and sustained engagement, despite funding pressures, demonstrates that targeted technical sessions and peer learning formats are effective in maintaining momentum.
- Localisation and sustainability depend on sustainable investment - PSEA-CAP deployments have shown that embedding coordinators within humanitarian leadership structures builds trust and systemic change. However, sustainability remains fragile without predictable funding and national capacity-building.
- With 230 endorsements and growing, CAPSEAH is increasingly recognised as a useful framework for collective action. The Wilton Park event successfully demonstrated that CAPSEAH can offer a platform for dialogue on common challenges, achieving broad agreement that PSEAH work is an essential, not optional cost of doing business at a time when the international system is facing significant budget cuts and difficult prioritisations are being made.
- Strategic alignment across forums (Cross-Sector Safeguarding Steering Group (CSSG), Technical Working Group (TWG), Development Assistance Committee (DAC), etc.) continues to be vital to underpin programme outputs and to support cross sector collaboration – success of the dialogue work demonstrates this, but also highlighted the need for consistent follow up through these fora to ensure recommendations are translated into action.
- UK leadership remains central to these efforts, but others are stepping up – our role in convening and facilitating dialogues and pilots is still needed, but we should seek to support other funders/leaders as they choose to engage and lead more.
- Collective analysis of PSEAH data and trends has significant potential to drive further alignment and collaboration - there is increasing recognition that improved data and analysis on PSEAH trends is needed and interest in HRS’s potential to fill this gap and support a move towards a more unified SEAH data architecture at both global and country levels.

Recommendations

- Adapt to financial and political uncertainty - A key lesson from this year is the need to remain agile in the face of financial and political uncertainty, and to prioritise activities that consolidate existing partnerships and maintain programme credibility. For the year ahead, we recommend focusing on strategic, cost-effective convening formats, strengthening virtual engagement, and ensuring that pilot activities are aligned with realistic resource scenarios.
- Track the impact and potential implications of ODA reductions: The full impact of ODA cuts on PSEAH funding and capacity across the international system, and its potential impact on this programme’s outputs will take time to be fully realised. Safeguarding Unit should continue to convene and use our networks to maintain momentum on PSEAH resourcing and a shift towards collective approaches, track the impact of cuts, and support coordinated dialogue to address emerging challenges in the system.
- Continue to promote collective action– we should continue to promote and sustain the PSEAH Global Public Goods supported by this programme as efficient, value for money solutions in the constrained ODA environment, and work towards a more sustainable and shared funding model, exploring pooled funding and expanding engagement with new potential funders. We should support partners to continue work to align global tools, collaborate and conduct joint analysis to ensure the programme’s potential to maximise efficiencies is achieved.
- Embed the use of tools in local contexts and ensure learning from data analysis, sector and national approaches informs global dialogue and policy thinking - SGU should maintain and deepen engagement with donors and coordination bodies to embed these tools into sector-wide and national approaches. Priority should be given to promoting their use in high-risk contexts and countries where impact can be maximised, including through the planned country pilot initiatives. Case studies should be added to CAPSEAH.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Theory of Change: The below Theory of Change (TOC) summary provides our high-level thinking behind the programme. It builds on the UK’s Theory of Change for safeguarding against SEAH in HMG’s 2020 Strategy on Safeguarding against SEAH (see Annex A).

The ToC was finalised in October 2024. In this first year of activities, given the early stages for all components, we assess the steps to achieving outcome and impact are still valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The expected outcomes and impact remain valid and are – so far - on track. The delivery of global PSEAH tools, strengthened coordination mechanisms, and strategic convening have progressed systemic change in PSEAH prevention and response. However, challenges are increasing and assumptions are weakening, with external factors, particularly reductions in ODA, deprioritisation of PSEAH and cuts to technical expertise, posing risks to sustainability and scale. However these same challenges are also driving momentum towards collective approaches and global tools so it remains to be seen how the outputs and outcome will be affected.

Despite these challenges, the programme has demonstrated resilience. Tools such as the MDS, HRS, and HQAI audits have seen increased uptake, including among national NGOs and UN agencies. Country-level pilots in Ethiopia and Bangladesh have generated valuable insights, though sustainability remains fragile due to staff turnover and limited long-term resourcing. Stakeholder feedback, gathered through quarterly reviews, technical sessions, and the Wilton Park conference, confirms the value of programme tools and approaches. Beneficiaries of its projects have reported improved capacity to report and respond to SEAH.

The programme continues to align with HMG’s 2020 safeguarding strategy. However, continued investment and strategic adaptation will be necessary to maintain momentum. Risks to impact include reduced visibility of SEAH in global agendas and constrained funding for pilot activities and convening. To mitigate this, the programme will prioritise protecting the gains made with existing global public goods, and convening systemic stakeholders to consolidate progress made.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue based on its strong performance, strategic relevance, and unique contribution to the global PSEAH architecture. In the context of ODA reductions, its adaptive, multi-partner approach to strengthening safeguarding standards through collective, aligned approaches is increasingly important and appealing to international actors. It represents good value for money, leverages modest funding to deliver high-impact tools with the potential to support systemic change across humanitarian, development, and peace sectors.

## C. DETAILED OUTPUT SCORING

Output Title	Collective tools to drive alignment and improvements in PSEAH standards, vetting, and data analysis
Output number:		1	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 - CHS - Number of organisations using the MDS	Target: 60 new orgs signed up.	Moderately exceeded expectation: 64 new organisations.
1.2 - CHS - Number of organisations using the HRS.	[25-50] new organisations signed up	Met expectation: 43 organisations since September 2024 (28 National Non-Government Organisations (NNGOs), 13 International Non-Government Organisations (INGOs), and 2 private organisations).
1.3 - Number of partners who are engaged in an HQAI audit scheme	78 partner agreements (80 by end of 2025)	Moderately exceeded expectation: 91 partners as of September 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

Misconduct Disclosure Scheme (MDS) – MDS, managed by the CHS Alliance, continued to deliver against its core workplan, expanding membership, strengthening implementation support, and increasing external engagement. The target of 60 new participating organisations was moderately exceeded with 64 new organisations bringing the total number of implementing organisations to 370 (including three de-listings due to organisational closures or inability to continue implementation). Efficiency improvements to the scheme’s IT and administrative systems are underway and aim to enhance data security and alignment with wider CHS Alliance systems.

The profile of MDS continues to grow and it is recognised as a key global tool to prevent SEAH. Following successful UN pilots, three UN agencies joined during this period. MDS was referenced in the UN Special Measures report and the UN Joint Inspection Unit Review of policies and practices to prevent and respond to sexual exploitation and abuse UN system organizations recognised the value of MDS and informally recommended UN entities should consider participation in it.

Collaboration with key initiatives remained strong, particularly synergies within CHS Alliance and through active participation in the IASC Technical Advisory Group. Engagement with PSEA Coordinators and networks also helped drive country-level promotion and uptake. Implementation data for 2024 was analysed and shared at the MDS annual meeting. These meetings enabled valuable peer exchange and feedback to inform ongoing improvements.

Harmonised Reporting Scheme (HRS) – HRS has made good progress across its three main objectives:
1. Develop a secure, multilingual, and user-friendly online platform with data visualisation tools - HRS is now available in four languages (French, English, Arabic, and Spanish). New features including a feedback button and additional options under main reporting categories fully align with participant needs. Users can analyse both their internal trends and aggregated global or country-level data to quickly identify gaps or patterns.
2. Scale up participation in the SEAH Harmonised Reporting Scheme (HRS) - the number of organisations reporting via the HRS increased to 102 (35 INGOs, 60 NNGOs, 6 private organisations, and 1 Red Cross Red Crescent Organisation). The majority are NNGOs, representing 15 countries.
3. Strengthen local capacity (see Output 4).

HRS is contributing to greater standardisation of SEAH reporting and access to reliable evidence across the aid sector. The HRS biannual analytical report is widely recognised and used by organisations to identify and validate their main gaps. The HRS team is regularly invited to present trends, demonstrating the strong (and growing) demand and sector-wide interest in this global public good. This added-value and credibility has helped the HRS to gain traction among donors and other key international stakeholders, with three major donors officially aligning with the project and choosing to use it as a means of getting reports from partners, and others in active discussions. Additionally, the UN is also aligning with HRS data fields, allowing joint analysis of data trends, and opening the potential for future interoperability.

Humanitarian Quality Assurance Initiative (HQAI) – despite concerns that use of audits would reduce due to funding constraints across the sector, HQAI made strong progress in expanding access to CHS audits, with 91 partner agreements signed against a milestone target of 78. A notable achievement is the increase in participation from local/national organisations, which now represent 48% of all audited partners, reflecting HQAI’s increasing visibility in the Global South through localisation activities such as the HQAI Facilitation Fund.

FCDO’s recognition of HQAI CHS certification for Due Diligence processes and the severe funding restrictions in the sector have equally contributed to a growing appetite among donors, intermediaries and networks for efficient approaches to due diligence and capacity assessments. The current duplication in these processes represents a challenge for all parties and puts a particular burden on local and national actors.

HQAI’s strategic outreach on this has been strong, with HQAI engaging a wide range of stakeholders, including Canada Global Affairs, DANIDA, DEC, DRA, ICVA, Norad, OCHA CBPF, SIDA, START Network, and the UN Safeguarding Focal Point Community of Practice, to promote the value of HQAI’s CHS assurance services (including independent verification and certification), and reduce duplication in due diligence.

Passporting of HQAI CHS certification (as announced by FCDO in the past year) has real potential to align and streamline approaches and drive efficiencies, however we will need to work with partners to ensure there is clarity that only HQAI CHS certification will lead to due diligence passporting. Work has begun with HQAI, CHS and RSH to map out the different levels of assessment against PSEAH standards, from self-assessment to HQAI audits, to clearly explain the benefits and limitations of each. This will allow other aid stakeholders to assess the suitability of different passporting approaches for their work.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Reductions in global ODA introduced significant uncertainty across the sector, with many partners facing funding instability and, in turn, their own partners/customers experiencing resource constraints and organisational change. The prioritisation of SEAH is under threat, with reductions to PSEAH human and technical capacity being reported from multiple sources.

These challenges this year created some uncertainty around whether the programme’s ambition for expanding membership of MDS, HRS and HQAI remained realistic. To manage this we consulted with partners throughout the year to assess progress and potential risks, ultimately agreeing that this year’s targets, whilst being delivered in a more challenging environment, were still achievable. Partners demonstrated their resilience and adaptability by taking advantage of the increasing need to maximise efficiency and interest in collective global tools and streamlined approaches to consolidate and expand these tools to deliver on this year’s targets.

As a result of HQAI exceeding expectations this year they are close to next year’s target for indicator 1.3 already. A new target will be agreed as part of the next year of programming.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first annual review of the programme. There are no previous recommendations.

Lessons Learned
- Tool uptake is strengthened by responsive design - The success of HRS and MDS in expanding membership highlights the importance of adapting tools based on stakeholder feedback, including multilingual access and simplified reporting features.
- Global tools can help local progress - HQAI’s increase in local audits and HRS’s country-level pilots demonstrate that global tools can drive positive improvements at local level. Localisation is achievable but fragile without long-term resourcing strategies and expertise/capacity to engage with in-country.
- The tools are streamlining approaches and have real potential to reduce bureaucracy and costs - there is growing recognition of the value of these tools and the key role they play in the global PSEAH architecture. Increasing alignment with other systems and tools (e.g. HRS with UN systems and HQAI’s audits passporting due diligence requirements) is beginning to reduce duplication and fragmentation and has real potential to reduce costs. However maximising these efficiencies will require continual advocacy.
- Despite good progress, the tools are still fragile – while there is growing agreement that these tools are PSEAH global public goods, they are still reliant on funding from the UK and limited other sources. We need to continue working with the wider sector to develop sustainable funding models.
Recommendations:
- Provide greater clarity on verification, audits and passporting - Passporting of HQAI CHS certification has real potential to align and streamline approaches and drive efficiencies, however we will need to work with partners to ensure there is clarity that only HQAI CHS certification is passported for due diligence . Work has begun partners to map out the different levels of assessment against PSEAH standards, from self-assessment to HQAI audits, to clearly and consistently explain the benefits and limitations of each to all customers/users.
- Continue to advocate - Work should continue across all tools to maximise alignment, reduce duplication and improve data use. Partners should continue to engage donors and coordination bodies to embed these tools into PSEAH approaches – FCDO should continue to use its convening role (as chair of various PSEAH groups) to promote and support the tools.
Output Title	Sustained co-ordination in highest risk areas and key sectors supports improved standard and action on PSEAH
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 - Evidence of growing Private Sector engagement in PSEAH efforts activities and engagement by SLN in line with the agreed workplan – including increased SLN members, CAPSEAH Private Sector sign ups, and activities and engagement by SLN	Membership is sustained despite sector-wide funding challenges / 75% of key outcomes in workplan achieved.	Moderately exceeded expectation - the SLN sustained and expanded its membership base to 47 members. / 97% of key outcomes in workplan achieved.
2.2 - Support for key PSEA coordination roles (PSEA-CAP)	Support to the OCHA PSEACap contributed to funding PSEA coordinators for 2 year postings in highest risk countries	Met expectation - As of July 2025, the project deployed PSEA coordinators to 10 countries.

Briefly describe the output’s activities and provide supporting narrative for the score.

Safeguarding Leads Network (SLN) – SLN delivered strong performance against its workplan, achieving 97% of planned quarterly outcomes and growing membership despite sector-wide funding challenges. Membership increased from 41 to 47 and 22 of 30 private sector CAPSEAH endorsers are now active SLN members. This reflects continued relevance and demand for SLN’s role in convening and supporting safeguarding leadership in the private sector.

Key activities included: technical sessions on CAPSEAH, safer recruitment, duty of care, and SEAH reporting systems; peer workshops for investigators; and monthly safeguarding catch-ups to support PSEAH leads in organisations. The SLN also developed the first private sector MDS case study, hosted high-level engagements such as the Heads of Business meeting and sent a representative to the Wilton Park CAPSEAH Dialogue on PSEAH Resourcing. Collaboration with donors, NGOs, and sector bodies (e.g., BOND, INTERPOL, DFAT, USAID) further strengthened SLN’s influence and visibility.

Based on FCDO feedback, quarterly outcomes were introduced to enhance accountability and track progress. Progress reviews with the core group are now held quarterly, with anecdotal and survey feedback integrated into planning. SLN has maintained momentum, delivered high-quality learning, and expanded its reach amid external pressures which demonstrates its strategic value in promoting PSEAH standards and action across the private sector.

PSEA-CAP – the OCHA-led PSEACap project enabled the deployment of PSEA Coordinators to ten high-risk countries (Chad, Central African Republic, Somalia, Sudan, Ethiopia, Myanmar, Colombia, Haiti, Mali, and Burkina Faso) with an eleventh deployment to Syria in progress. The project continues to demonstrate the value of sustainable, long term (at least two-year) deployments in building sustainable systems, fostering trust, and embedding PSEA into humanitarian planning and leadership structures. Coordinators worked directly with UN Humanitarian Coordinators and Country Teams to develop action plans, strengthen inter-agency networks, and integrate PSEA into strategic frameworks such as Humanitarian Needs and Response Plans. The project has also strengthened localisation through mentorship of national PSEA officers and integration with Accountability to Affected Populations and gender equality frameworks, and built synergies with other interagency deployment mechanisms on protection and gender. Coordinators also contributed to global policy discussions, such as events at the Human Rights Council and Wilton Park, ensuring their field experience helped inform system-wide strategies. These achievements reflect the strategic value of PSEACap in strengthening coordination and accountability locally in the highest-risk countries.

Following shifts in the global donor landscape in early 2025, this programme’s contribution has been instrumental in enabling PSEACap to uphold its commitments and deliver sustainable inter-agency protection from sexual exploitation and abuse (PSEA) coordination capacity in high-risk countries. While some additional contributions from other sources to the project have been made, challenges persist in securing adequate, longer-term, predictable contributions. PSEACap, an IASC (Inter-Agency Standing Committee) endorsed mechanism, continues to use the PSEACap Advisory Group to steer the project. The IASC Technical Advisory Group on PSEAH and the PSEACap Advisory Group are important opportunities to strengthen the support base for this project to seek additional resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to output indicators are proposed at this stage, but future reviews may consider milestone targets for localisation, sustainability, and donor diversification to reflect evolving priorities and risks.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first annual review of the programme. There are no previous recommendations.

Lessons Learned
- Private Sector continues to require tailored support - The SLN’s growth and sustained engagement, despite funding pressures, demonstrates that targeted technical sessions and peer learning formats are effective in maintaining momentum.
- Localisation and sustainability depend on sustainable investment - PSEA-CAP deployments have shown that embedding coordinators within humanitarian leadership structures builds trust and systemic change. However, sustainability remains fragile without predictable funding and national capacity-building.
Recommendations:
- Protect coordination capacity - PSEA-CAP should continue to be promoted to stakeholders across the system to mobilise additional funding for increased sustainability.
- Ensure future high-level meetings and strategic convenings include representative PSEA-CAP field coordinators - to share frontline experience and evidence. Their insights are critical to informing system-wide strategies, strengthening localisation, and ensuring global policy is grounded in operational realities.

Output Title	Evidence and dialogue on PSEAH resourcing priorities and models
Output number:	3	Output Score:	A
Impact weighting (%):	25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Coordinated cross-sector dialogues on common barriers and challenges builds consensus, drives progress, and scales up resourcing and best practice. (CAPSEAH & Wilton Park)	Wilton Park CAPSEAH Conference on resourcing held and recommendations agreed	Met expectation – Successful conference held in April 2025, with report published which contains agreed core messages and recommended actions.
3.2 - New pilots and tools to plug gaps, tackle common challenges and establish good practice are supported and created.	Mapping of global PSEAH tools and associated costs completed and shared. / At least 2 countries identified for new pilots to improve strategic PSEAH partnerships at national level.	Met expectation – Global PSEAH tools mapped and included in Wilton Park Report. / Potential countries for pilots identified.

Briefly describe the output’s activities and provide supporting narrative for the score.

Strong engagement and dialogue with partners from across the international system is fundamental to understanding the strengths and weaknesses in the global PSEAH architecture, spotting gaps and opportunities, and building buy-in towards collective solutions. The Common Approach to Protection from SEAH (CAPSEAH) aims to provide a basis for collective action, partnerships and collaboration, both as a guide with minimum PSEAH principles and actions, but also as an anchor for multi-stakeholder dialogue on the opportunities and challenges around taking better collective action to protect against SEAH and a framework to pilot and promote collaborative approaches. Over the year, CAPSEAH has grown and now has over 230 endorsements.

The first ‘CAPSEAH Dialogue’ focussed on resourcing for PSEAH. CAPSEAH is clear that PSEAH policies and approaches should be backed by sufficient resources, however PSEAH resourcing is consistently identified as a common challenge and barrier to progress. To address this FCDO created a small multi-stakeholder group in early 2024 to develop a system-wide understanding and mapping of PSEAH resourcing needs and challenges. A thinkpiece was published on the CAPSEAH website to generate dialogue and gather views and a Wilton Park conference was held in April 2025 (indicator 3.1).

ODA cuts in early 2025 increased the urgency of this dialogue, with the conference reframed to take stock of the impact of cuts and to agree urgent practical recommendations to protect, prioritise and streamline PSEAH work. Participants in both the working group and conference included the United Nations, donor governments, International Financial Institutions, non-governmental organisations, private sector, foundations, academia, victim/survivor representatives and independent experts.

The working group and conference successfully demonstrated that CAPSEAH can offer a framework and platform for dialogue on common challenges. This first CAPSEAH Dialogue built consensus on the need for more collective approach to PSEAH in general, and practical actions to move towards a shared and sustainable PSEAH resourcing model in particular:
- Participants agreed that PSEAH work is an essential cost of doing business and developed common core messages to use to argue the case for PSEAH funding with seniors, leaders and decision makers.
- Consensus that maximising efficiency and reducing duplication by using collective tools and approaches is now more important than ever. The tools supported by this programme were recognised as critical priorities for the global PSEAH architecture.
- Recommendations for organisations to properly resource and prioritise PSEAH costs, and for international actors to improve collaboration and collective action at global and country level, including by identifying 2-3 countries for new pilots to improve strategic PSEAH partnerships at national level (indicator 3.2). Potential pilot countries have been shortlisted and 2-3 pilots will commence in the coming year. These will aim to pilot and learn from successful PSEAH partnerships; seek to better systematise good practice; help ensure resources are prioritised where they are needed most; and test how global tools and cooperation can learn from and be adapted to national contexts. Other good practice at country level will be captured as case studies and added to CAPSEAH.
Dialogue will continue and progress updates on PSEAH resourcing will be built into PSEAH coordination bodies (e.g. the Cross Sector Steering Group, the Donor Technical Working Group, and the DAC Reference Group on SEAH) to promote the uptake of the report’s recommendations and help translate them into tangible action. Emerging learning and good practice relating to PSEAH Resourcing will be added to CAPSEAH.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output indicators are unchanged for the moment. While this output has delivered as expected this year, upheaval in the wider sector, with reducing budgets and PSEA capacity, may impact the level of ambition we can achieve in future years – e.g. scope to invest in research and to develop new tools, or to convene large-scale, in-person events such as Wilton Park, may be reduced. In this context, collaboration through our networks and PSEAH fora will continue to ensure that decisions around where to focus resources are targeted to critical priorities likely to have most buy-in and success.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first annual review of the programme. There are no previous recommendations.

Lessons Learned
- CAPSEAH is increasingly recognised as a useful framework for collective action - and can offer a framework and platform for dialogue on common challenges. The CAPSEAH website is useful to share key resources and outcomes (like the Resourcing Thinkpiece and Wilton Park Outcome Report) but an online webform questionnaire on PSEAH resourcing was less successful – useful technical engagement requires human interaction and dialogue to unpick and understand issues and build consensus towards solutions.
- Strategic alignment across forums (CSSG, TWG, DAC, etc.) is vital to underpin successful strategic dialogues and to support cross sector collaboration – success of the dialogue work demonstrates this but also highlighted the need for consistent follow up through these fora to ensure recommendations are translated into well-coordinated action.
- UK leadership remains central to these efforts, but others are stepping up – our role in convening and facilitating dialogues and pilots is still needed, but we should seek to support other funders/leaders as they choose to engage and lead more.
- Diversity of input is key to building consensus – inclusion of diverse voices strengthened the quality of the resourcing workstream’s recommendations and increased the likelihood of uptake across systems, in particular, inclusion of victim/survivor representatives and IFIs and UN.
Recommendations
- Continue to convene and use our networks to maintain momentum on PSEAH resourcing and a shift towards collective approaches, track the impact of cuts, and support coordinated dialogue to address emerging challenges in the system.
- Capture and share learning from country pilots – use our networks to feed evidence and learning from pilots into international policy dialogues and CAPSEAH.
Output Title	Research and case studies on what works in different countries
Output number:		4	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 - CHS data project grows global data set, including regional case studies	Bi-Annual reports published with collective analysis of PSEAH trends. / 2 country analyses (Ethiopia & Bangladesh)	Met expectation - Two reports were produced as planned, in November 2024 and May 2025. / In addition, two country analyses (Ethiopia and Bangladesh) were in July 2025.

The Harmonised Reporting Scheme (HRS) delivered two analytical reports (November 2024 and May 2025), each covering six months of SEAH reporting data. These reports provided comprehensive trend analysis and were widely welcomed across the aid sector, with several organisations joining the HRS following their publication. The HRS biannual analytical report is already widely recognised and used by organisations to identify and validate their main gaps. The HRS team is regularly invited to present trends, demonstrating the strong (and growing) demand and sector-wide interest in this global public good.

In addition to global analysis, HRS made progress against their objective to strengthen local capacity among HRS participant organisations so they can safely collect and report SEAH data at the field level. Two pilots in Ethiopia and Bangladesh had sustained engagement with over 40 organisations participating in train-the-trainer programmes, mentoring, and tailored capacity-building, resulting in improved SEAH incident reporting and increased platform adoption. Translated resources supported this uptake, and national NGOs reported significant improvements in their ability to prevent and respond to SEAH. Outputs from these pilots formed country-specific analyses which were completed in July 2025. These case studies offered valuable insights into national-level SEAH reporting trends and challenges.

Sustainability at country level remains fragile, with frequent turnover of PSEAH Coordinators and no long-term liaison staff. The train-the-trainer model was designed to help address this, and CHS also advocating for the HRS to be embedded in UN PSEA Network standard operating procedures to ensure continuity.

HRS is evolving quickly, and CHSA propose to update the governance structure to ensure efficient and effective coordination (the current Steering Committee is likely to evolve into a Data Contributors Group, an Evidence and Analysis Group, and an Action and Accountability Group led by donors). Discussions on this will take place in the next year of the project.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In response to feedback and strategic review, the HRS Steering Committee agreed that from 2026, the reporting format will shift to one consolidated annual trends report covering the full calendar year, complemented by shorter biannual snapshots (2-3 page infographics). These changes aim to streamline reporting, enhance accessibility, and allow for deeper thematic and country-specific analysis to better guide targeted action and advocacy. Logframe indicator 4.1 will be amended accordingly.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

This is the first annual review of the programme. There are no previous recommendations.

Lessons Learned
- Reporting and evidence is driving engagement and uptake – the biannual reports and country analyses directly contributed to increased participation in the HRS, demonstrating the value of sharing evidence.
- Country level reporting provides important contextual evidence - country pilots brought to light national level trends and provided valuable insights into gaps and challenges faced in the field. National level data also empowers local actors to take concrete measures to adjust their actions for more effective prevention and response to SEAH, which will be key to effective localisation strategies.
- There is increasing recognition that improved data and analysis on PSEAH trends is needed and interest in HRS’s potential to fill this gap and support a move towards a more unified SEAH data architecture at both global and country levels.

Recommendations
- Sustain investment at a local level - continue to strengthen local ownership through continued capacity-building such as invest in train-the-trainer models, building HRS into national approaches (e.g. through UN Standard Operating Procedures).
- Build deeper country level evidence –ensure reporting maintains thematic and country-specific insights to maintain relevance and usability in real world contexts.
- Data alignment and joint analysis - Strengthen collaboration with UN iReport and other data sources to enable joint analysis, thereby increasing the uptake, credibility, and impact of reports, and continue to move towards streamlined and aligned donor reporting practices.
- Consolidate reporting outputs by moving from two annual reports to one comprehensive report (while maintaining bi-annual infographics) and enrich these with more thematic and country-specific analysis to better guide targeted action.
- Revise the HRS governance structure to ensure more effective coordination.

D: VALUE FOR MONEY

Key cost drivers and performance
The key cost driver for projects under the programme is staff, as these roles require specialised expertise to develop and operate the associated tools. These staff also lead a variety of engagement activities to promote and train stakeholders on project tools. Other costs support cross sector engagement and dialogue. The programme team designs and plans consultation and engagement to tackle widely recognised common challenges, build thinking, evidence and consensus, and agree practical action - such as the progress made at the Wilton Park resourcing event.

In terms of performance, partners have delivered well in a challenging year. However organisations across the sector are undergoing restructuring in response to the broader ODA environment, which could affect delivery for both FCDO’s project partners and their own networks. While this has not yet impacted delivery of programme outputs, this will need to be watched closely.

VfM performance compared to the original VfM proposition in the business case

VfM performance is in line with the original business case. The programme is delivering global public goods with significant potential for long-term impact. The programme seeks to ensure cost-efficiency by funding proven organisations, coordinating across projects to reduce duplication, partnering with credible actors to promote and improve programme outputs and influence global, national, and local action.

Economy: funding was provided to organisations that have the expertise necessary to undertake the specialised work or outreach needed to drive innovation and engagement in this sensitive and technical area. Operating and other budget costs are carefully monitored.
Efficiency: all funding and activity was monitored against agreed workplans to ensure good control and oversight. Investing in global public goods and common PSEAH tools, working with other key actors to explore sustainable funding models at global and national levels, and ensuring different projects work together coherently helps improve global efficiency on tackling SEAH.
Effectiveness: alongside project monitoring, close relationships with partners are maintained so that challenges, opportunities and priorities are understood and adapted to in delivery. Partner’s expertise and credibility in this area means they are best placed to deliver projects and convene others.

Equity: SEAH is rooted in power imbalances, often gender inequality, and so this programme’s work contributed toward equity in the aid sector. This programme has helped address violence against women and girls and potential harm to other vulnerable groups, including specific work to tackle SEAH of people with disabilities. Much of the guidance produced under this programme (e.g. CAPSEAH) has undergone wide consultation with diverse groups, including with beneficiaries and organisations in developing countries, and where possible has been translated into multiple languages.
Cost effectiveness: The programme is leveraging relatively small funding amounts to influence and support a wide range of PSEAH partners and cross sector tools that reach large audiences and improve action at global, national and local levels. Increasing adoption and alignment with programme tools by influential stakeholders such as the UN is evidence of this strategy beginning to deliver.
Assessment of whether the programme continues to represent value for money

Overall, the programme continues to provide value for money. Relatively small funding amounts support projects that sustain global tools and guidance to increase knowledge and coherent/collective action across the sector, many of which would not be possible without UK funding. Projects support organisations to improve safeguarding standards and drive culture change, thus strengthening capacity across the sector and protecting more vulnerable people from harm. Work from the CAPSEAH Resourcing Working Group shows that proactive investment to prevent incidents of SEAH can save organisations the more substantial costs associated with responding to cases: investigations, legal proceedings, reparations, and the cost of rebuilding trust and credibility with communities, partners, and donors, and repairing impact on funding flows.

In the absence of other major funders there is a risk that the programme’s global tools and architecture become overly reliant on UK support. Without diversified funding, there is a danger that if UK funding levels reduce, tools will fail or that gaps emerge in global PSEAH coordination and standards. Efforts to diversify funding and move to a more sustainable funding model will form part of programme in the coming year.

E: RISK

The overall risk rating is moderate and the overall risk appetite is receptive. The level of risk is judged to be manageable, proportionate and within the Safeguarding Unit’s risk appetite given the potential high returns in terms of prevention of and safeguarding against SEAH. The Programme is designed to support PSEAH approaches which in themselves are intended to improve governance and address risk across the international sector. The highest levels of support go to previously supported projects and delivery partners with a stable and credible track record on delivery.

Risk monitoring is embedded in programme delivery. Risks are reviewed monthly by the Programme Responsible Officer (PRO) and Senior Responsible Officer (SRO), and quarterly with partners to identify emerging issues and mitigation strategies. Fraud risk remains low, with most partners paid in arrears based on verified deliverables. Two partners (HQAI and PSEA-CAP) receive advance payments due to operational needs, supported by clear justification and oversight.

The programme’s top risks have been shaped by the changes in the international operating environment.
- Strategy & Context: reductions in ODA, significant multilateral reform, and geopolitical challenges such as the rollback of women’s rights and shrinking civic space have caused significant disruption to the wider development and humanitarian architecture. This could result in weakened international commitment and/or resources to tackle SEAH. While effort is being made to ensure that PSEAH is seen as an essential cost of doing business, these shifts have already led to the loss of specialist safeguarding staff, suspension of GBV and child protection services, and weakened outreach and reporting mechanisms. Political deprioritisation and reduced funding for PSEAH threatens the sustainability of global tools and initiatives before they reach maturity and risks undermining momentum.
- Financial & Fiduciary: The impact of ODA cuts on delivery partners and the wider PSEAH sector will be closely monitored in the next year of the programme but may impact the level of ambition and capacity of organisations to adopt PSEAH approaches. This is mitigated by increased interest in achieving efficiencies through the adoption of collective tools such as those supported by this programme. In addition, as noted above, in the absence of other major funders the programme’s global tools and architecture risk becoming overly reliant on UK support. Without diversified funding, there is a danger that if UK funding levels reduce, tools will fail or that gaps emerge in global PSEAH coordination and standards. Efforts to diversify funding and move to a more sustainable funding model will form part of programme in the coming year.

SGU continues to encourage wider donor investment and sector ownership of PSEAH architecture, and to maximise our non-ODA levers such as convening and engagement to promote collective action. These efforts are critical to ensuring that PSEAH remains an essential not optional component of humanitarian, development, and peacebuilding work, even in a constrained funding environment.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

All projects are monitored by the FCDO PRO and SRO using narrative and financial reports, alongside regular meetings with implementing partners. There are no issues with the timeliness of reports and there is active and engaged communication with partners via email and meetings between review points as needed.

Partners have delivered as expected. The programme has proved an efficient means of producing important tools and guidance to tackle SEAH across the aid sector, convening key partners; and supporting organisations to reach international standards and build capacity.

There are no concerns regarding project spend or financial management by partners. MDS and CHS remain within their approved annual budgets. Some variations in projected spend have occurred due to delays or shifts in activities, such as IT upgrades and engagement visits throughout the year. HQAI’s auditor fees were slightly under budget due to the postponement of audits; this is expected to balance out as the backlog is addressed.

The SLN coordinator has relocated to Fiji. The programme team worked closely with British Expertise to develop a risk and mitigation plan to ensure continuity of performance. One consequence of the move was a reduction in salary costs, resulting in a small projected underspend.

Overall, all projects remain on track to meet their forecast expenditure for 2025. The impact of ODA cuts on delivery partners will be closely monitored in the next year of the programme.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring of the programme is undertaken through the following mechanisms:
Regular check-ins with delivery partners to discuss progress and performance against workplans;
Activity reporting, against key programme deliverables in the workplan;
- Quarterly & annual reporting, assessing programme performance;
- Delivery partners participate in broader PSEAH networks and dialogues, and ad hoc feedback on projects is received through ongoing bilateral engagement with donors etc.

This year’s Annual Review is a light-touch desk-based review, assessing the programme against the outputs set out in the business case and logframe. In addition to assessment of partners quarterly reports, the PRO commissioned partners to provide annual reports covering performance against programme indicators, finances, challenges, risks, and lessons learned. Throughout the year delivery partners monitor participation and use of the tools and gather feedback from their users and other stakeholders, either through surveys or regular engagement and outreach (or both).

Over the past year, the programme has strengthened the evidence base through publicly shared analysis from the Harmonised Reporting Scheme (HRS), offering insights into SEAH trends and reporting behaviours. Quarterly narrative reports and meetings with partners and in person events have served as key platforms for capturing learning and reflections from stakeholders. Feedback, trends, and lessons learnt will inform future programme planning and activities.

Date of last narrative financial report	Financial and narrative reports are received at minimum quarterly from all partners (along with discussions at regular intervals).	Date of last audited annual statement	Audited statements by project partners received annually, FY24 was received by June 2025