## 2024-2025 GA Logframe - CLEAN
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
Global Architecture Programme Logframe
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
Fewer people likely to be harmed as a result of humanitarian and development activities, in particular due to sexual exploitation and abuse and sexual harassment. | Clear leadership commitment to tackle SEAH from key partners across the sector. | Planned | Nil | Continued engagement in TWG, DAC, CSSG and other networks shows PSEAH commitment and action remains high. | Continued engagement in TWG, DAC, CSSG and other networks shows PSEAH commitment and action remains high. | Continued engagement in TWG, DAC, CSSG and other networks shows PSEAH commitment and action remains high. | Continued engagement in TWG, DAC, CSSG and other networks shows PSEAH commitment and action remains high. | Continued engagement in TWG, DAC, CSSG and other networks shows PSEAH commitment and action remains high. | HDP actors will deliver on their commitments and will co-operate with FCDO to agree mechanisms to track progress. HDP actors will take further action and make further commitments to show leadership in PSEAH.
Achieved
Source
TWG, CSSG, DAC Reference Group, Central Assurance and Due Diligence Assessments, Strategic Dialogues with partners, MOPAN reports.
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
HDP actors have a stronger, more aligned and more coherent approach to PSEAH. Well-established multi-stakeholder tools, dialogues, evidence, guidance and support encourages and embeds PSEAH best practice. | Global PSEAH tools drive progress and elevate and align PSEAH standards and approaches | Planned | Membership levels, funding models and status of tools at Sept 2024. | Global tools (MDS, HRS, HQAI, etc) continue to expand and evolve to meet sector-wide needs and deliver their agreed objectives. | Global tools (MDS, HRS, HQAI, etc) continue to expand and evolve to meet sector-wide needs and deliver their agreed objectives. | Global tools (MDS, HRS, HQAI, etc) continue to expand and evolve to meet sector-wide needs and deliver their agreed objectives. | Global tools (MDS, HRS, HQAI, etc) continue to expand and evolve to meet sector-wide needs and deliver their agreed objectives. | Global tools (MDS, HRS, HQAI, etc) continue to expand and evolve to meet sector-wide needs and deliver their agreed objectives. | HDP actors will continue to deliver on their commitments and will co-operate with FCDO to track progress. Stakeholders are committed to co-operation on PSEAH. Stakeholders are open to new approaches on best practice. Pilot schemes can be effectively measured for impact and scaled up
Achieved
Source
Achievement will be based on a holistic view of: progress against specific project milestones for global tools in this logframe; evidence of how tools (and their use) are evolving and expanding to meet wider PSEAH policy and delivery needs (e.g. through greater multi-stakeholder engagement, contributing to data and evidence that informs policy development etc; and whether tools widen their funding sources. Information from partner workplans, quarterly/annual reports, feedback and evaluations.
| Outcome Indicator 2 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029
| Engagement, collaborative action, and improved evidence base informs improved tools and approaches to overcome common challenges. | Planned | Nil | Actions agreed on PSEAH resourcing following Wilton Park conference. | CAPSEAH practical guidance enhanced through user feedback from 1 year stocktake. Continued endorsement and evidence of use and impact of CAPSEAH. | Continued endorsement and evidence of use and impact of CAPSEAH. | Continued endorsement and evidence of use and impact of CAPSEAH. | Continued endorsement and evidence of use and impact of CAPSEAH.
Achieved
Source
TWG, CSSG, CAPSEAH engagement. CAPSEAH/RSH website and network feedbaclk. Quarterly and annual partner reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  | 20m (over 5 years) |  |  | 100%
INPUTS (HR) | FCDO (FTEs) |  | Govt
|  |  | 5.8 |  | 6
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
Collective tools to drive alignment and improvements in PSEAH standards, vetting, and data analysis | CHS - Number of organisations using the MDS. | Planned | Memebrship as of Sept 2024 (315) | Target: 60 new orgs signed up. | Target: 60 new orgs signed up. | TBD depending on future funding decision. |  |  | The tools are effective at PSEAH. The tools can deliver data that can be used to raise standards. Large numbers of MDS members aren’t forced to close or merge due to ODA funding cuts.
Achieved
Source
MDS proposal and workplan 2024-2026. MDS quarterly reports. Milestone 1 is based on the MDS workplan (agreed before US cuts and move to 0.3). Additional objective: Updated MDS website to include a community of practice by Sept 2026.
| Output Indicator 1.2 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029
| CHS - Number of organisations using the HRS. | Planned | 59 | [25-50] new organisations signed up | [25-50] new organisations signed up | [25-50] new organisations signed up | TBD depending on future funding decision.
Achieved
Source
HRS participation tracker: the CHS Alliance will maintain updated a participation and tracker to keep track of organisations who have joined the HRS (disaggregated by type of organisation and CHS Alliance membership), organisations who are interested in joining, and organisations who have refused to join or dropped out of the HRS. The tool can be shared with FCDO on request. Logo of participating organisations are also available to the public on the CHS Alliance website.
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029
25% | Number of partners who are engaged in an HQAI audit scheme | Planned | 65 Partner Agreements as of Sept 2024 | 78 partner agreements (80 by end of 2025) | 93 partner agreements (95 by end of 2026) | TBD depending on future funding decision.
Achieved
Source
HQAI proposal and workplan 2024-2026. HQAI quarterly progress reports; minutes of donor meetings and reports, HQAI annual report. Additional policy objective - progress with HQAI passporting in FCDO and with other partners. HQAI defines 'partners' as: Organisations who have paid an HQAI application fee and are engaged in an HQAI auditing scheme. Subsidised organisations and organisations who are part of audit groups are included in this category once a signed application form is submitted.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
Sustained co-ordination in highest risk areas and key sectors supports improved standard and action on PSEAH | Evidence of growing Private Sector engagement in PSEAH efforts activities and engagement by SLN in line with the agreed workplan – including increased SLN members, CAPSEAH Private Sector sign ups, and activities and engagement by SLN | Planned | Membership as at Sept 2024 (41) | Membership is sustained despite sector-wide funding challenges 75% of key outcomes in workplan acheived. | Membership is sustained despite sector-wide funding challenges 100% of key outcomes in workplan achieved by end of 2024-2026 funding agreement. | TBD depending on future funding decision. |  |  | Private sector will act on PSEAH when better informed. Co-ordinators are able to deliver cultural change across sectors. OCHA demonstrate cross-sector coordination e.g. via endorsement of CAPSEAH Other donors contribute funding
Achieved
IMPACT WEIGHTING (%) |  | Source
25% |  | SLN quarterly reports
| Output Indicator 2.2 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029
| Support for key PSEAH coordination roles (PSEA-CAP) | Planned | 0 | Support to the OCHA PSEACap contributed to funding PSEA coordinators for 2 year postings in highest risk countries | Support to the OCHA PSEACap contributed to funding PSEA coordinators for 2 year postings in highest risk countries | Support to the OCHA PSEACap contributed to funding PSEA coordinators for 2 year postings in highest risk countries (subject to budget) | Support to the OCHA PSEACap contributed to funding PSEA coordinators for 2 year postings in highest risk countries (subject to budget) | PSEACAP is a sustainable, shared model with appropriate burdenshare across donors. At least 5 PSEA Coords are leading Strategic Multi-stakholder Partnerships.
Achieved
Source
Because this is a pooled fund, FCDO contributions can't be attributed to specific PSEA Coordinator positions - rather, the pooled fund is used to plug gaps and fill positions as need arises, and provides continuity across highest risk areas. PSEACAP quarterly reports will trackand report PSEA Coord capacity supported in countries ranked using the SEARO index, with the aim of ensuring that the highest risk contexts have long term sustainable capacity in place.
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
Evidence and dialogue on PSEAH resourcing priorities and models | Coordinated cross-sector dialogues on common barriers and challenges builds consensus, drives progress, and scales up resourcing and best practice. (CAPSEAH & Wilton Park) | Planned | Nil | Wilton Park CAPSEAH Conference on resourcing held and recommendations agreed | 1 thematic dialogue event linked to CAPSEAH/RSH (subject to budget) | 1 thematic dialogue event linked to CAPSEAH/RSH (subject to budget) | 1 thematic dialogue event linked to CAPSEAH/RSH (subject to budget) | CAPSEAH 5 year review/evaluation demonstrates that collective action has grown and is improving PSEAH impact. | Stakeholders are committed to co-operation on PSEAH. Stakeholders are open to new approaches on best practice. Pilot schemes can be effectively measured for impact and scaled up.
Achieved
Source
FCDO internal reports
| Output Indicator 3.2 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029
IMPACT WEIGHTING (%) | New pilots and tools to plug gaps, tackle common challenges and establish good practice are supported and created. | Planned | Nil | Mapping of global tools and associated costs completed and shared. At least 2 countries identified for new pilots to improve strategic PSEAH partnerships at national level. | Each country pilot has agreed shared key objectives/priority actions. | Majority of key objectives for each country pilot achieved or on track. | Lessons learned from pilots collated into best practice guide and case studies, and added to CAPSEAH | Evidence that Strategic Partnerships for collective action on PSEAH is being mainstreamed. (Metric for measuring tbd from pilot learning).
25% |  | Achieved
Source
FCDO internal project development and management process. Country pilot action plans, reports and engagement.
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 - Sep 2025 | Milestone 2 - Sep 2026 | Milestone 3 - Sep 2027 | Milestone 4 - Sep 2028 | Milestone 5 - June 2029 | Assumptions
Research and case studies on what works in different countries | CHS data project grows global data set, including regional case studies | Planned | Nil | Bi-Annual reports published with collective analysis of PSEAH trends. 2 country analyises (Ethiopia & Bangladesh) | Bi-Annual reports published with collective analysis of PSEAH trends. 1 country analsysis for phase 2 region (in either Latin America or West & Central Africa (TBC)). | Evaluation of global PSEAH data improvement and gaps (potentially to inform a CAPSEAH dialogue?) | Priorities for PSEAH data work to be expanded and improved are agreed with international partners. (TBD pending funding) |  | Approaches are impacted by country context, rather than region or social context. Research and case studies are able to capture PSEAH impact at country level.
IMPACT WEIGHTING (%) |  | Achieved
25% |  | Source
CHS Alliance website, hosting the data harmonised framework and communications with the Steering Committee. Localisation report.

## Change frame
Change Number/ ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Output 3 | Output 3.2 added | JS | 2025-07-31
2
3
4
5
6
7
8
9
10