## Annual Review Template

Title: Core Funding to UNAIDS 2024-2027
Programme Value £ (full life): Up to £24,000,000		Review date: September 2025
Programme Code: 400236	AMP start date: 26/11/2024	AMP end date: 31/08/2027

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	N/A

Glossary:

ART	Antiretroviral Therapy
GAM Global AIDS Monitoring
GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria
HLP High Level Panel
ILO	International Labour Organisation
IOS	Office of Internal Oversight Services
JIU Joint Inspection Unit
PCB	Programme Coordination Board
PEPFAR	The United States President’s Emergency Plan for AIDS Relief
PMR	Performance Monitoring Reports
RC	UN Resident Coordinator
SDG	Sustainable Development Goal
SRO	Senior Responsible Owner
SSA	Sub Saharan Africa
UNAIDS	The Joint United Nations Programme on HIV/IDS
UBRAF	Unified Budget Results and Accountability Framework
UHC Universal Health Care
UN80 UN80 Initiative
UNESCO	United Nations Educational, Scientific and Cultural Organisation
UNFPA	United Nations Population Fund
UNDP	United Nations Development Programme
UNHCR United Nations High Commissioner for Refugees
UNICEF	United Nations Children's Fund
UNODC	United Nations Office on Drugs and Crime
VFM	Value for Money
WHO	World Health Organisation
WFP	World Food Programme

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The Joint United Nations Programme on HIV/AIDS (UNAIDS) was established in 1996 in response to the global HIV and AIDS epidemic. The Joint Programme comprises the UNAIDS Secretariat (with Global Centres, regional offices and country Offices) and the 11 UN Co-sponsors: UNHCR, UNICEF, WFP, UNDP, UNFPA, UNODC, UNWomen, ILO, UNESCO, WHO and the World Bank. It is governed by the Programme Coordinating Board (PCB) which brings together the Cosponsors, member states and civil society to agree the strategy, budget and results framework for the Joint Programme.
The Joint Programme is funded through a blend of core and non-core funding[1] provided directly across the Secretariat and Cosponsors, all of which is managed and monitored through UNAIDS’ “United Budget, Results and Accountability Framework” (UBRAF). UNAIDS has served as the primary entity for catalysing and coordinating the global HIV response; it develops evidence-informed global strategies and supports the development of national strategies and interventions including treatment, care and support for those living with HIV and AIDS, as well working to optimise efforts to prevent new HIV infections.
[1] Non-core funding is earmarked to particular projects or programmes which may be provided either by the Secretariat or Cosponsors
2025 has been an unprecedented year for the HIV response, and for the Joint Programme. This year, sudden shifts from some of the biggest donors of the HIV response led to disruption in HIV treatment and prevention programmes, especially in countries with a high burden of HIV and insufficient domestic financing. These developments are occurring at a time when the rights environment is also deteriorating in many parts of the world, with a growing push back on human rights and gender equality, along with shrinking civic space. For UNAIDS, whilst donor funding for UNAIDS has reduced over time, more recent exits this year – and ongoing uncertainty from other donors – have propelled UNAIDS into a financial crisis. Across the UN more widely an initiative – UN80 – is underway to streamline operations, improve efficiency, and manage better to available financing, and will result in significant organisational restructuring across the UN system.
As a result of this financial crisis – and in tandem with wider UN reforms - in 2025 UNAIDS has undergone a series of reform processes. First, a restructure of the Secretariat is reducing headcount by 55% and will result in a smaller country footprint. Second, the High-Level Panel (HLP) requested by the PCB in December 2023 has concluded and presented recommendations for a revised operating model for UNAIDS, with the PCB approving in June 2025 a phased approach to reform through to 2030. In the first phase (pre-2028), the Secretariat will focus on delivery in four priority areas - (1) leadership and advocacy, (2) convening and coordination, (3) data and strategy, and (4) community engagement - and transfer all other activities to the Cosponsors as part of the UN80 restructuring process. In the second phase (post-2028), UNAIDS will become a smaller global hub, with UNAIDS offices possibly hosted within another UN agency, with remaining country operations folded into a reformed UN Resident Coordinator system. The PCB agreement noted that if progress in the global fight against HIV and AIDS allows, UNAIDS will close by 2030, with its functions consolidated and integrated into other UN agencies by then.
The reduction in global development assistance for health, and specifically reduced external financing for UNAIDS, has resulted in key changes to this programme. It has had to refocus resources and so will in future deliver against a new plan with new results targets. As a result, this Annual Review reflects on a programme in transition.
2025 is also the year in which UNAIDS will put forward the Global AIDS Strategy for 2026–2031 for adoption by the PCB. As shown in the Mid-term review of the Global AIDS Strategy for 2021-2026 which was conducted in 2024, key gaps remain in the HIV response. The next Strategy will guide governments, communities, civil society, donors and other stakeholders through the next phase of the HIV response.
To support UNAIDS role in the global AIDS response, the UK agreed a new business case for 2024 – 2027, with a first payment of £8m made in December 2024. For 2025, a performance agreement is in place with UK funding contingent on UNAIDS demonstrating further progress on reform and ODA availability. This annual review therefore includes an assessment of progress for 2025 against the performance agreement.
Summary supporting narrative for the overall score in this review [1-2 paragraphs]
Despite the considerable programmatic and operational challenges UNAIDS faced this year, the programme has performed well, particularly at country level, where they helped 84 countries scale up combination HIV prevention programmes, 79 countries to incorporate and expand community-led responses and 49 countries to implement interventions for key populations in humanitarian settings. There are however several indicators that have not been met during this period, including insufficient discussion and planning on lower resource scenarios for the revised operating model. An overview of what was achieved during the course of this review period (September 24’ – August 25’), and the most pressing challenges, are summarised below.
Between September 2024 and February 2025, the Joint Programme continued to deliver its core activities, albeit within a smaller than anticipated budget due to exits from two of its top five donors ($125m instead of the original revised core operating budget of US$150m). During this period this included supporting countries to scale up combination HIV prevention programmes and develop ‘Sustainability Roadmaps’, and work at the global level to secure commitments for a human-rights based response to HIV.
In February 2025, UNAIDS received a formal termination notice from its largest donor - the US Government. In response, UNAIDS commissioned a restructure of its Secretariat reducing its headcount by 55%. This coincided with ongoing discussions on a revised operating model, as part of the High-Level Panel. The Executive Director and Cosponsors responded to the findings of the High-Level Panel with recommendations which were adopted by the PCB at its 56th meeting. This focus on reform was not unique to UNAIDS; in March 2025 the “UN80 initiative” was launched by the UN Secretary General to improve efficiency, effectiveness and relevance of the wider UN system, including UNAIDS 11 Cosponsoring organisations.
With funding for the largest global instrument for bilateral HIV funding (PEPFAR) also on pause during this period, UNAIDS pivoted its efforts to support countries to manage the disruption, including by providing real-time data through the mini-Global AIDS Monitoring report and helping to protect prevention interventions during reprogramming of Global Fund grants. While reform and supporting the response to disruptions to the broader HIV response were priorities for UNAIDS during the remaining period, it also continued its business-as-usual work. For example, UNAIDS began work on the next Global AIDS Strategy with consultations with stakeholders (between January and May 2025) and a global survey (April 2025).

Major lessons and recommendations for the year ahead [1/2 page]
This has been an important year for UNAIDS.
The reform discussions taken forward through the High-Level Panel were not only timely, but essential. The recommendations being taken forward now – and subsequent decisions on the budget and workplan and the nature of the Joint Programme - will govern UNAIDS’s effectiveness in the year ahead. Recognising the challenge of managing multiple interests, some questioned the methodology of the process, and felt that the decisions made by the Panel were not transparent or consultative enough.
The recommendations endorsed by the Board at the 56th PCB in June 2025 provide an outline but it will need to be realistically fleshed out and costed. UNAIDS financial planning for the transition process made several assumptions – including a flat line of ODA from all contributors in an already uncertain context and no catalytic funding planned for Cosponsors at lower resource scenarios. This initially led to confusion among stakeholders and means that whilst the role and mandate for the Secretariat in the current operational model is clear, the role for Cosponsors – which is fundamental to the Joint Programme - remains uncertain.
The whole of the UN is undergoing a transformation. The Board endorsed recommendations were timely for UN80 discussions. We recommend the continued and full participation of UNAIDS and PCB and ECOSOC member states in the UN80 process. This will help to anticipate and account for the broader context for its new operating model as UNAIDS transitions to a new approach. During 2025 UNAIDS has actively engaged in the UN80 process and as part of this has highlighted some challenges around the role of the UN Resident Coordinator (RC) offices in protecting and promoting the rights of the individuals and communities most likely to be marginalised in the global fight against HIV. UNAIDS will advocate for a reformed RC model in the year ahead, in anticipation of the greater role the RC office will need to play in delivering the function previously delivered by UNAIDS at country level. We also recommend that FCDO’s engagement with the UN80 process should continue to take into account the changes needed to enable critical UNAIDS functions to transfer over time to the Cosponsors.
As UNAIDS restructures, it is important that it has a ‘zero tolerance to inaction’ approach and protects sufficient human and financial resources to minimise the risk of SEAH across its operations and respond effectively when it occurs. As such, we recommend that FCDO monitors how UNAIDS operationalises PSEAH at country level, and we recommend that FCDO tracks delivery against UNAIDS annual PSEAH annual work plan,
In December 2024, the mid-term review of the current Global Strategy identified ongoing implementation gaps. This takes place as many low- and middle-income countries encounter challenges in compensating for reduced international support or have yet to prioritise prevention initiatives addressing the underlying causes of HIV. The upcoming Global AIDS Strategy 2026–2031, scheduled for adoption in December 2025, represents an opportunity to re-evaluate approaches to the global HIV response. At the 56th PCB, member states, including high-burden countries, expressed interest in developing a strategy that aligns with present needs. Recommendation: Consultations on the development of the Global Strategy should be inclusive and meaningfully engage a variety of stakeholders.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The theory of change for this programme is that core funding provided by the UK will enable sustained and effective reform of UNAIDS to improve the delivery of its core mandate, contributing to sustained global progress in reducing HIV infection rates, improving access to treatment and addressing discrimination. Through this UNAIDS will deliver the Global AIDS Strategy to reduce the inequalities that drive the AIDS epidemic and contribute to ending AIDS as a public health threat by 2030.
UNAIDS contribution is founded in delivering effective support to the global AIDS response in a way that reflects the Joint Programme’s unique role, partnering with a range of organisations for effective implementation of the Global AIDS Strategy. This is underpinned by ensuring effective UNAIDS systems and policies with a realistic, fully financed and prioritised workplan delivering value for money, and continued, sustained and effective measures to address safeguarding.
The steps in this Theory of Change remain valid and all outcome and impact indicators remain relevant. However, the significant reduction in UNAIDS’s core budget may affect its ability to deliver against the outputs in future and this will need careful monitoring.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
Progress against the outcome has been assessed based on the most recent available data as set out in the 2024 Performance Monitoring Report (PMR report). This covers data for calendar year 2024 and therefore does not reflect the impact of recent disruptions in external financing for the global AIDS response. The PMR report shows that UNAIDS was on track to meet milestones for 2024 for the majority of indicators including: providing strategic information; coordination, convening and country implementation support; and work supporting countries to protect and promote human rights and gender equality. Indicators that were partially achieved included work on paediatric AIDS; work with countries to scale up youth-friendly interventions; and partnerships, mobilisation and innovation.
The impact relates to delivery of the Global AIDS Strategy. UNAIDS published the mid-term review of the Global AIDS Strategy (2021-2026) in December 2024. This showed that, despite much progress, the world is not on track to reach the goal to end AIDS by 2030 as pledged in the 2021 Political Declaration. New infections are on the rise in over 30 countries in three regions, the commitment to HIV prevention is inadequate and stigma and discrimination remain key impediments, with evidence that stigmatising attitudes are on the rise in some countries. UNAIDS is currently developing a new Global AIDS Strategy which will be presented to the PCB for approval in December 2025.
The operating context for the programme will change significantly over the second year of the programme with a new operating model and workplan and a new Global AIDS Strategy all taking effect from January 2026. The outcome and impact may need to be adapted to align with the new Global AIDS Strategy.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
The High-Level Panel concluded that AIDS remains a deadly pandemic and that the Joint Programme should continue throughout to 2030 as the world seeks to achieve AIDS goals and address the acute crises facing the AIDS response. It recommended that the Joint Programme remain multisectoral but with a sharpened focus on addressing key gaps and seizing short-term opportunities to respond to the evolving AIDS pandemic, transitioning roles to others as capacity develops. It found that the UNAIDS Secretariat is essential but will need to downsize, right size and consolidate to focus on the most essential functions and provide leadership and differentiated support to the evolved needs of today’s varied HIV epidemics, while UNAIDS Cosponsorship needs to be restructured through a differentiated model of engagement, and the role of civil society should be expanded. These recommendations have been agreed by the PCB. Continued support for the Joint Programme through this business case will contribute to implementation of these reforms.
Based on this annual review, the programme should continue, but with intensified reform efforts that will ensure effective delivery.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	UNAIDS successfully delivers effective support to the global AIDS response that reflects the Joint Programme’s unique role in the global HIV response.
Output number:		1	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1.1 Number of countries where the Joint Programme provided technical and/or implementation support to scale up combination HIV prevention programmes (UBRAF Indicator 1.2.1)	82 countries 1	Exceeded 84 countries
Indicator 1.2 Number of countries supported by the Joint Programme in activities to remove or amend punitive and discriminatory laws and policies, and/or develop protective ones affecting the HIV response (UBRAF Indicator 5.1.1)	65 countries 1	Exceeded / 72 countries
Indicator 1.3 Global AIDS Update reports, other flagship reports and annual updates to AIDS info produced and disseminated, highlighting progress and inequality gaps, and giving examples of data use by countries, communities and partners to improve programmes (UBRAF Indicator S3.3.1.)	High quality update on AIDS progress towards ending AIDS and addressing inequalities gaps provided via the Global AIDS Update report and annual update to AIDSinfo produced.	Exceeded Global AIDS Update report published in July 2025 / Mini GAM also published to cover the period between Feb – July 2025
Indicator 1.4 Number of countries having conducted studies to improve allocative efficiency, address implementation bottlenecks, or other analytical exercises to improve resource use efficiency, multi-sectorial financing, impact and equity and are implementing learning from these studies; and/or with recent HIV Investment cases (in the past three years) that are being used (UBRAF Indicator 8.2.1)	49 countries 1	Exceeded 59 Countries

Note: 1 2024 reported data in 2024 PMR

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 indicators are tracked through reporting in the Performance Monitoring Report. All data relates to calendar year 2024.
For output indicator 1.1, UNAIDS exceeded the target 82 countries (with 84 reached) in which it provided technical assistance and implementation. This included normative and implementation guidance provided to countries for combination HIV prevention interventions for and with key populations and other groups at high risk of HIV infection, in line with the Global AIDS Strategy.
For output indicator 1.2, 72 countries were supported to remove or amend punitive and discriminatory laws and policies relating to HIV. For example, in Mozambique the ILO in partnership with UNDP, the Secretariat and UN Women, supported the Government to revise the HIV legal framework.

For output indicator 1.3, the 2024 Global AIDS Update report: AIDS, crisis and the power to transform was published in July 2025 and presented to the Board. The report showed that at the end of 2024, whilst declines in the numbers of people acquiring HIV and dying from AIDS-related causes were at their lowest levels in more than 30 years, the declines were not sufficient to end AIDS as a public health threat by 2030. It identified barriers to progress including stigma, discrimination and punitive laws, and a lack of political will to provide prevention services for key and vulnerable populations. Following shifts in the international financing environment for HIV, UNAIDS increased the frequency of their monitoring through a monthly global AIDS monitoring platform[2]. This has proved helpful in identifying where service disruptions are occurring and triaging support to address this.
[2] AIDSinfo | UNAIDS
Output indicator 1.4 relates to the Joint Programme’s support to countries to ensure the sustainability of their HIV responses, including in the context of changing HIV-related financing and fiscal environments. This indicator specifically measures the number of countries who have conducted studies to improve efficiency, impact and equity. UNAIDS stepped up the technical assistance and the breadth of data tracked under this output during this review period, reflecting the increased urgency of supporting countries to transition to domestic financing. The milestone for this indicator was exceeded, with 60 countries reporting work in these areas against a target of 49.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
UNAIDS is undergoing a restructure which will reduce its headcount and significantly shift its package of support to countries. In June 2025, the PCB approved a decision to simplify the UBRAF – and therefore the reporting that is provided - to correspond with the reduced budget and workplan. A transitional budget and workplan for 2026 will be presented to the PCB for approval in October 2025. It is unclear at this stage if there will be any proposals to change the reporting format for the 2025 Performance Monitoring Report. If there are then the programme team may need to revise the indicators for this output.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This is the first year of the programme. One of the challenges of UNAIDS’s current performance reporting is that it is tracking overall good progress against most performance indicators (as shown by the reporting against this output) while at the same time the mid-term review of the Global AIDS Strategy has confirmed that the world is not on track to meet the global target to end AIDS by 2030. The PCB will be asked to approve a transitional budget and workplan in October and a new Global AIDS Strategy in December. It will be important in both cases to have tight prioritisation and robust performance monitoring.

Output Title	UNAIDS leads the Global AIDS Strategy and partners with a range of organisations for its effective implementation through strategic partnerships, global and domestic mobilisation of resources, strong coordination of partners including at country-level.
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
High-Level Panel delivers recommendations for a fit-for-purpose and sustainable Joint Programme which are endorsed as appropriate by the UNAIDS Executive Director and the Committee of Cosponsoring Organisations, implemented in a timely manner and with the support of the Programme Coordinating Board. / UNAIDS Secretariat prepares, and delivers against, a clear implementation plan by December 2025	HLP is effectively conceptualised, and a high quality HLP is delivered / Recommendations of High-Level Panel presented to the PCB. / UNAIDS Secretariat sets ambition and prepares and delivers an implementation plan based on agreed recommendations	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2 relates to activities of the Joint Programme, and specifically delivery against the reform agenda mandated by the PCB at the 53rd PCB meeting[3]. Under Output Indicator 2.1 the milestones for 2025 were broadly achieved, with the HLP being successfully conceptualised, delivered, and recommendations presented to the Board – by the Executive Director and Committee of Cosponsoring Organisations - for adoption at the June 2025 PCB meeting. Further detail on the effectiveness of conceptualisation and delivery of the HLP, including challenges which hampered overall performance against this output, are explained below.
[3] At the 53rd PCB meeting in December 2023, the PCB requested the Executive Director and the Committee of the Cosponsoring Organisations (CCO) to propose a revised operation model for the Joint Programme.
Conceptualisation
In her report to the PCB in June 2024, the ED, Winnie Byanyima, informed the PCB of the establishment of the HLP, which the ED would co-convene with the Committee of Cosponsoring Organisations (CCO). The ED and CCO chair, on behalf of the Joint Programme, recruited three co-chairs from different member state constituencies, and a series of panellists including NGO representatives, implementing countries, donors, Cosponsor and Secretariat leadership staff, and other national and global stakeholders. The Panel was largely agreed to be representative; however, some of the HLP panellists and PCB members interviewed for this review questioned the transparency of recruitment of some of the panellists.
Whilst the Secretariat made efforts to ensure external facilitators for the process and ensured that the HLP benefitted from expert insights from the chosen co-facilitators, many of those interviewed for this review agreed the process would have been better served by genuine external facilitation given the numerous, varied interests within the Panel. Nonetheless, the Secretariat successfully shared and incorporated insights gained from previous UNAIDS reviews including the 2023 MOPAN evaluation into discussions in the HLP. This helped to ensure that discussions were grounded in evidence-based recommendations for improvement of the Joint Programme.
Delivery
The Panel presented its report to the co-convenors on 5 May 2025. The report was developed after five formal meetings, four virtual consultations, and two hybrid consultations. It made six broad recommendations and 18 sub-recommendations and presented a new operating model which plans to transform the Joint Programme in two phases: immediately and in 2027. The recommendations consider preliminary discussions with the UN80 initiative, and the approach is supported by UN leadership. The new operational model will be effective from 1 January 2026 and the Joint Programme’s Workplan and Budget for 2026 will be based on the revised model, with discussion on the workplan and budget planned for a Special Session of the PCB in October 2025. A review of the operating model will be undertaken by June 2027 and presented to the PCB to inform the PCB’s decision making, leading to further consolidation and integration of the UNAIDS Joint Programme into the UN system.
Many of those interviewed cited the process as being very consultative, but also recognised the challenges posed through consultation as there were many differing – and at times - conflicting ideas. The Secretariat and Cosponsors were engaged in the HLP process, albeit from a distance, and there was a genuine interest to work together to find a workable operating model for the Joint Programme. UNAIDS maintained an outward commitment to an independent process, but this was not corroborated by many of those interviewed, who still felt UNAIDS was too close to the process and that the recommendations being made were not as radical as they could have been. For example, the Cosponsors and the Secretariat agreed on many things however where there were differences, they were fundamental, e.g. Cosponsors and the Secretariat disagreed on the need to undertake annual strategic and financial reviews of the new operating model, with Cosponsors advocating for this approach. Some felt that the first few meetings of the Panel were marred by these disagreements.
In many ways, our assessment found that the HLP was a success, setting out a clear set of priorities for the Secretariat and a roadmap for how remaining functions would be transferred out across the UN over time. A focus on four key priorities for the Secretariat demonstrated a clear interest in devising an operating model that was streamlined, focused and fit for purpose with space to transfer functions out across the UN system, as part of this transformation. However, discussions on the finances needed to make this vision a reality were less successful. Our assessment found that disagreements about the need (or capability) to provide predictable catalytic funding to Cosponsors proved fundamental and could have been avoided through improved stewardship by the Secretariat of the reform process, for example, the Secretariat consulting Cosponsors in discussions regarding scenarios and relaying this information to the Panel.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first year of the programme. The biggest shift since the business case came into effect was a change in international financing for HIV from January onwards, and subsequent uncertainty on the wider context for international ODA for HIV moving forwards. Due to concerns about the amount of resource and capacity it would require, and the sense that they had already recently instituted some organisational changes, there was some initial reluctance from UNAIDS to undergo a reform journey. In spite of this, a sudden shift in ODA propelled the reform agenda to the forefront of UNAIDS priorities.
There was some learning in relation to how the HLP was conceptualised and later delivered. During the course of the HLP, the Secretariat faced capacity constraints and competing priorities with a number of other competing processes underway. The Secretariat made efforts to present updates to various stakeholder groups – including the Group of Friends of UNAIDS – and prepared a webpage with updates on the process. Despite this, our assessment found that issues such as poor timeliness of HLP reporting ahead of meetings, and less transparency on the consultation process more broadly fostered a sense of a lack of trust in the process.
A key lesson learned was the need for UNAIDS to be agile in response to a continuously changing external context. Feedback suggested that after the changes in January, discussions in the HLP were more focused and strategic. However, despite this there was a feeling that UNAIDS was unwilling or unable to take on comments drawn from consultations once the recommendations were agreed until it was too late – notably a plan for how to manage a scenario without funding from the US government i.e. under $60m. The Secretariat should consider how best to manage its relationship with Cosponsors, as well as other stakeholders such as non-governmental organisations and community representatives, to ensure that as reforms progress, they feel involved in decisions that will ultimately impact them. Cosponsors can support the Secretariat, by providing consolidated advice which is representative of the views of all 11 organisations. As UNAIDS works to implement its new structure, it will benefit from continued agility in order to manage any further fiscal shocks as well as responsible and effective risk planning for what this might mean for its operating expenditure.

Output Title	UNAIDS is a transparent organisation with effective systems and policies in place, and a realistic and fully financed workplan, aligned with priorities and which delivers value for money.
Output number:		3	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Clear annual UBRAF reporting on the Secretariat’s results and expenditure demonstrates positive impact of Secretariat support.	Performance Monitoring Report 2024 / Learning from reform discussions informs creation of a workplan with appropriate resource allocation and clear reporting on finances and priorities which is affordable and will deliver value for money	Partially achieved / Performance Monitoring Report for 2024 was published and presented to the Board at the June 25’ meeting. / At the time of this assessment, UNAIDS is preparing for a special session of the PCB in October to discuss the workplan and Budget for 2026.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output relates to UBRAF reporting on the Secretariats results and delivery as outlined within the 2024 Performance Monitoring Report (PMR). The PMR summarises the collective results of UNAIDS – its 11 Cosponsors as well as the Secretariat – and captures progress during 2024 towards ending AIDS as a public health threat by 2030. It does not reflect recent, ongoing challenges in the global HIV response during 2025. The 2024 PMR was strong, with clear reporting on results of the Joint Programme and its achievements across a number of results areas, for example, in 2024 UNAIDS helped to secure landmark international commitments to advance rights of women and girls. There was however a discrepancy between reports of increased infections, as outlined in the July 2025 AIDS update and the PMR which conveyed uniformly good progress across UBRAF indicators, despite challenges presented. Notably, during the course of this review UNAIDS reported a continued deterioration of the HIV-related human rights environment and civic space in many parts of the world.

The report also included an overview of the Joint Programme’s budget implementation in 2024. In 2024, two of UNAIDS top five donors withdrew from the Joint Programme, contributing to a shortfall of US$ 11 million against the core budget of US$ 160 million – itself already significantly reduced from the base level of US $187 million originally set. These declines in donor contributions, in addition to resource mobilisation challenges, continued to affect the capacity of the Joint Programme to deliver on its mandate. In response to these challenges, the Joint Programme made efforts to intensify resource mobilisation and to address the funding shortfall to address the funding shortfall.

The financial outlook for the Joint Programme is concerning. In the face of a sudden drop in voluntary contributions which cut the Joint Programme’s financial resources by approximately 60%, in February 2025 UNAIDS began discussions on an organisational restructure. The restructuring, which is now ongoing, will lead to significant downsizing, reducing staff from 671 in 2024 to 280 by mid-2026, and retaining presence in 35 countries while supporting about 60 countries through multi-country offices, one-person offices, and senior officers embedded within UN Resident Coordinator offices. Some Global Centre staff will also be relocated to lower cost locations to further reduce expenses.

In its reports to the Board, UNAIDS asserted that decisions on what roles should remain were based on value for money and preserving the organisations’ ability to deliver its mandate. These decisions were scrutinised by the Board, with some querying the effectiveness of decisions made about where UNAIDS retains a geographic footprint, and the value for money of decisions made about certain positions which remained or were cut. The Board will receive an update at the PCB in June 2026 on what was implemented under resource constraints.

The HLP report, with recommendations on the new operating model, was endorsed by the Board in June 2025. The HLP was well informed by previous evaluations, including MOPAN 2023 and the report of the Joint Inspection Unit (JIU)[4]. The Secretariat prepared reports which summarised the findings of these evaluations ahead of the HLP meeting, and this helped shape discussions. During the HLP, a number of resource scenarios were presented for consideration. Our assessment found consensus on the reflection that the scenarios presented were neither radical nor realistic, given that they assumed a) that the largest donor would retain its contribution – when there was palpable uncertainty about this – and b) that voluntary contributions from all donors would remain steady through to 2030. Across the board, many shared concerns that what had been presented as the worst-case scenario by the Secretariat, within HLP discussions, was actually the most realistic. As a result, insufficient attention has been given for discussion and planning on lower resource scenarios.
[4] The Report of the Joint Inspection Unit on the Management and Administration Review of UNAIDS (2019) https://www.unaids.org/sites/default/files/media_asset/14112019_UNAIDS_PCB45_JIU_REP_2019_EN.pdf

In the worst-case (i.e. potentially the most realistic) scenario, there would be no transfers to Cosponsors. This point was not clearly communicated to the PCB, resulting in confusion before the meetings, including among Cosponsors, which was subsequently clarified at the Board meeting. Cosponsors have outlined their concerns regarding these developments. Without catalytic resources, some Cosponsors will continue addressing HIV and AIDS as part of their mandates with sufficient resources to manage a smaller portfolio, while others may not be able to do so due to resource limitations. Additionally, some Cosponsors will have a reduced capacity to carry out activities deprioritised by the Secretariat, participate in PCB governance, and advocate for retaining HIV within their mandates during the UN80 reform.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes in the external financial context for the HIV response, and subsequent changes to UNAIDS’ budget, had an impact on UNAIDS ability to deliver against its mandate during the course of this annual review. This was not reflected in the UBRAF, which measures performance across the Joint Programme during calendar year 2024, prior to the financial shock of February 2025. This is communicated within the UBRAF report and mitigated by real-time estimates produced by UNAIDS in 2025, i.e. the mini-Global AIDS Monitoring Report.

The next steps, namely how the operating model is operationalised, will be discussed at the October half-day Board. FCDO will actively take part in these discussions and, as part of the PCB, will work to support the Secretariat to prepare a transitional 2026 workplan and budget which has appropriate resource allocation and clear reporting on finances and priorities which is affordable and will deliver value for money.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This is the first year of the programme. In the year ahead, the Board will agree the workplan and budget for 2026 (October 2025), the new operating model will come into effect (January 2026), and the Executive Director will prepare a review (December 2026). UN80 discussions will progress and there will be greater clarity about the role of Cosponsors within the Joint Programme, as well as greater clarity on what a realistic budget for UNAIDS looks like within the current declining ODA context.

There are challenges presented through UNAIDS voluntary contribution model, which reduces predictability and can pose challenges for planning. A key learning for this year, however, was the need to plan for a range of realistic financial scenarios, including the most undesirable and to ensure that this is as transparent as possible to best inform decision making on priorities for the years ahead.

Output Title	UNAIDS efforts to improve safeguarding measures are continued, sustained and effective.
Output number:		4	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 4.1: Annual reporting demonstrates sustained improvement in safeguarding results.	Improvements made to Safeguarding based off of recommendations from evaluations / Revised safeguarding plan presented to PCB / Annual report to PCB	Achieved
Indicator 4.2: Country offices undertake PSEAH assessment and priority offices identified and supported.	20 countries	Not achieved / Was only able to deliver support to two country offices due to resource constraints and the resultant restructuring
Indicator 4.3: All consultants and staff recruited to UNAIDS are duly screened and provided training to know policies and accountabilities, with high compliance rates	Consultants and staff recruited to UNAIDS are effectively screened and have completed required training on safeguarding. / Update on Strategic Human Resources Management Issues report to the PCB 2025 demonstrates continued implementation of effective screening policies.	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 relates to UNAIDS efforts to improve safeguarding measures. UNAIDS Ethics Office is predominantly responsible for delivery against this output. Two of the indicators in this output are assessed as being achieved, with one indicator not yet achieved.
Indicator 4.1 relates to annual reporting on Protection from Sexual Exploitation, Abuse, and Harassment (PSEAH) at UNAIDS. The milestones related to this indicator were achieved. An annual report of the Ethics Office was presented to the PCB in June 2025. The report provided an overview of activities over the reporting period and demonstrated continued progress towards improving safeguarding and PSEAH in UNAIDS.
Recent reviews of the Joint Programme set out areas for improvement on the organisation’s safeguarding and PSEAH approach. The 2019 JIU[5] review of UNAIDS recommended further strengthening of the Ethics Office by establishing a fully independent office, with appropriate staffing and backup for the Ethics Office. Whilst a substantive head of the Ethics Office was recruited, and the Executive Director had approved the recruitment of an additional Ethics Officer, contracting of the recommended candidate was frozen due to the financial crisis the organisation is facing. UNAIDS scored well in the 2023 MOPAN evaluation on the many indicators linked to an independent ethics function, however areas for improvement were identified as; (1) ensuring that the Secretariat has dedicated resource to change the organisational culture; (2) implementing a victim and survivor-centred approach; and (3) monitoring implementation of policies.
[5] Review of the Management and Administration of the Joint United Nations Programme on HIV/AIDS, (JIU/REP/2019/7), at paras. 101–104 and 124 (14112019_UNAIDS_PCB45_JIU_REP_2019_EN.pdf).
Resource challenges have hindered progress in the first improvement area. For the second, the WHO's policy on preventing and addressing sexual misconduct — adopted by UNAIDS — remained active during the reporting period. This victim-centred policy clarifies reporting options and responsibilities, emphasising the rights of victims, accused individuals, and bystanders. In its June 2025 report, UNAIDS reiterated its commitment to this approach, noting its dependence on timely information from WHO Internal Oversight Services to protect those at risk of retaliation after reporting misconduct. Staff perceptions of these improvements were assessed via surveys such as the UNAIDS 2024 Global Pulse Survey and UN-led PSEA surveys, which showed better results over previous years for indicators like reporting knowledge and understanding consequences. However, gaps persist regarding prohibitions on sex with sex workers and minors, mandatory reporting, and retaliation concerns. To address these issues, the Ethics Office and management have established an annual work plan. The Ethics Office will prioritise more interactive staff training to ensure that participants have better opportunities for in-depth and nuanced discussion and understanding of the application and implications of the standards of conduct and relevant policies.
A UNAIDS Code of Conduct to Prevent Abusive Conduct and Sexual Misconduct at Events and Gatherings was also launched during the reporting period. It is to be shared with participants at UNAIDS events and gatherings to help them to prevent misconduct, identify it if it occurs and to report it. The code defines abusive conduct and sexual misconduct, outlines the responsibilities of event organisers, and provides guidance on how to address incidents. It also highlights the Integrity Hotline as a confidential channel for reporting cases.
As difficult prioritisations and choices are being made across the international system in response to ODA reductions and reform processes such as UN80, FCDO is clear that protection against SEAH is an essential, not optional activity. Our partners must continue to have a ‘zero tolerance to inaction’ approach and protect sufficient human and financial resources to minimize the risk of SEAH across their operations, and to respond effectively when it occurs. Subsequent to the progress so far and following the imminent downsizing, management needs to urgently clarify and strengthen the primary responsibilities of all personnel, including managers, leaders and relevant offices, in implementing the policy on preventing and addressing sexual misconduct. This clarification should aim to ensure proactive prevention of sexual misconduct, provision of fair and timely support to victims, ensuring due process for alleged perpetrators, and protection of witnesses. Recommendation: FCDO should track delivery of the annual work plan to ensure that, as it restructures, protection against SEAH remains a priority for UNAIDS.
Indicator 4.2 relates to UNAIDS support priority country offices in strengthening their overall PSEAH prevention efforts and mitigate against associated PSEAH risks. Whilst UNAIDS’ Ethics Office was able to provide direct support to two country offices the milestone, to directly support 20 countries, was not achieved because of the human resource constraints placed on the Ethics Office, and the wider financial crisis encountered by UNAIDS and the resultant restructuring during the review period. With regards to the two country offices the Ethics Office was able to support, two training sessions on PSEAH were held in Namibia and Ghana in May and August 2024, respectively. This training was informed by learning from a sexual exploitation, abuse and harassment country risk assessment tool which was launched in early 2024 to help countries identify those risk factors and implement measures to mitigate them. The two offices were provided with sample mitigation measures to help them identify appropriate actions to mitigate identified risks. Countries then included selected risk mitigation measures in their plans. The Ethics Office received positive feedback from the Country Directors after the training. Recommendation: As UNAIDS reorganises its country footprint, FCDO should monitor how UNAIDS operationalises PSEAH at country level. This includes roll out of the risk assessment tool and risks assessments at country level, as well as the appointment of PSEA focal points, as outlined in the 2025 PSEAH Action Plan.
In relation to indicator 4.3, in line with UNAIDS recruitment policy, the People Management Department hired a third-party company to conduct professional digital footprint checks for all external candidates. The milestone was therefore successfully achieved. The checks implemented assessed risk categories such as sexually explicit content, violent/ graphic content, potential substance use illegal activities, hate and discriminatory behaviour, and extreme views. Flagged digital content is sent to the Ethics Office for advice. During this period, the Ethics Office advised on flagged content for five candidates. Additionally, the People Development Department continued to implement the use of ClearCheck to screen all candidates UNAIDS intended to offer a staff position. This background check ensures that UNAIDS does not hire individuals with a history of sexual misconduct.
UNAIDS also carried out an implementing partner capacity assessment for preventing sexual exploitation, abuse and harassment at country level. The assessment is a prerequisite for entering into agreements with implementing partners and ensures that they meet the minimum standards set out in the UN Harmonized Implementation Tool. An online ‘implementing partner capacity assessment platform’ is being developed to replace the paper-based tool and is expected to be rolled out in 2025. The WHO policy on preventing and addressing sexual misconduct is part of the standard contractual provisions for all individuals and third parties who have any form of contractual relationship with UNAIDS. All commercial contracts contain terms and conditions on the prevention of sexual exploitation and abuse, which all vendors are required to abide by.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is the first year of this programme. In light of changes to UNAIDS staff structure, the FCDO programme team might consider amending output indicators that assume there is a fully staffed (2 people) Ethics Office. The scope of activities might also decrease as UNAIDS moves towards a smaller workplan budget whilst retaining UNAIDS focus on critical minimum standards. These standards must be developed and implemented in full to mitigate ongoing risk surrounding safeguarding issues within the Joint Programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first year of the programme. Despite this, 2024 surveys of staff have shown marked improvements in the PSEA approach UN-wide, including in UNAIDS.
During the restructuring process, the UNAIDS is likely to experience an increase in requests for advice and guidance as staff seek clarity on their roles, rights and the overall transition. The shifting workplace dynamics may also lead to a rise in conduct related complaints, as uncertainty and stress affect collaboration and trust among personnel.
In UNAIDS’s new structure, the Ethics Office has been retained albeit with one member of staff. Additional financial and logistical constraints will make it harder to deliver in-person training. An annual workplan on preventing and addressing sexual exploitation, abuse and harassment has been developed to address these issues but at the time of the assessment has not been presented to the PCB at the October special session of the PCB on the 2026 Workplan and Budget.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case
Economy
The steep reduction in UNAIDS core budget has resulted in significant restructuring with a 55% reduction in headcount by mid-2026 and a smaller country footprint. Staffing in Geneva will be reduced by more than 90% with some posts ending and others being moved to lower cost locations. UNAIDS will retain offices in 35 countries while approximately 60 countries will be supported through a model of multi-country offices, one-person offices, and senior officers embedded within UN Resident Coordinator Offices. The PCB scrutinized these proposals and received reasonable assurances relating to the VfM of these decisions. There will be a further opportunity to review economy during the October 2025 discussion on the budget and workplan for 2026.
Efficiency
The High-Level Panel report recommended refocusing the work of the Secretariat around 4 key functions: (i) leadership, (ii) convening and coordination, (iii) accountability through data, targets, strategy, sustainability/ resource mobilization, and (iv) community engagement. The PCB endorsed this recommendation. We assess that, together with support for human rights, these are the most critical functions needed to preserve an effective Joint Programme and that this refocusing should therefore lead to increased efficiency.
Effectiveness
As noted above, the UNAIDS Secretariat will in future focus its work around four key functions, with all other functions to be delivered through the UN Cosponsors. In principle this should be both efficient and effective. However, the recommendations which were approved by the PCB in June 2025 did not include any transfers to Cosponsors in the lowest, and currently most realistic, funding scenarios. This may challenge the ability of some Cosponsors to perform the functions previously resourced through the UNAIDS budget. It is not clear at this stage whether and to what extent there will continue to be a genuinely multi-sectoral joint programme. There is a risk that the decision to prioritise funding to the Secretariat will undermine the joint programme and therefore the effectiveness of UNAIDS. This will need to be kept under careful review.
During this review period, UNAIDS began consultations on the next Global AIDS Strategy. This strategy will be presented to, and adopted by, the PCB in December 2025. In the strategy UNAIDS will articulate what, in the context of diminished financial resource and diminishing human rights in many places worldwide, must be prioritised in order to deliver the overarching goal to end AIDS. It will be important that the Strategy also carefully articulates UNAIDS role within this as one of the key actors in the global response.
Equity
As identified in the Business Case UNAIDS has a strong offer on equity, and during the course of this review period this has remained strong. UNAIDS offers advocacy, guidance and technical support for human rights to advance the needs of communities and geographies with the greatest need. It also has dedicated work on gender equality in compliance with the Gender Equality Duty. At a global level, UNAIDS has continued to promote equity for example, its Secretariat convened a UN Human Rights Reference Group and provided other guidance and support that helped shape legal and policy reforms for more effective HIV responses. In the future, UNAIDS restructuring and reduced budget will affect this offer. Factors such as a reduced country footprint, a smaller Secretariat, and less capacity within some Cosponsoring organisations may reduce its ability to work with key and vulnerable populations living with or at high risk of HIV.
A key aspect of the High-Level Panel discussions was the unique role of UNAIDS within the wider global health architecture, and what role it will play in the future to help end AIDS by 2030. The UN80 initiative has afforded UNAIDS an opportunity to articulate its offer in the UN, especially its role in protecting and advocating on behalf of the rights of the most vulnerable and marginalised communities. In the next year, ongoing discussions on the future of UNAIDS, and how it integrates its country-level offer into UN country offices as part of its ongoing transition, will prove important in determining how, in the long term, the wider UN system continues to support those with the greatest need in relation to HIV.
Assessment of whether the programme continues to represent value for money
VfM falls within the expectations set out in the Business Case. The recent restructure will shift UNAIDS into a smaller budget and smaller footprint, effective January 2026. With this new configuration, there is sufficient cause to suggest that the support to the Joint Programme in this transitional period represents value for money.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]
The main change to programme risk over year one relates to the change in UNAIDS finances with the exit of major donors, and uncertainty regarding future contributions from other donors. The overall risk rating for this programme is Major. In February 2025, a 90-day pause in funding for PEPFAR created two risks for UNAIDS. First, it destabilised HIV funding and disrupted services, especially those targeting marginalised groups, reducing UNAIDS’ effectiveness in supporting these programmes. Second, as the largest donor to UNAIDS, the US government issued a ‘stop work’ order and set out its intention to terminate funding through PEPFAR, creating significant uncertainty regarding UNAIDS budget and impacting its ability to fulfil its mandate. The FCDO programme team began ongoing communication with UNAIDS Secretariat regarding its financial situation. The Secretariat also issued a communique to PCB members in February 2025, to update on its mitigation plans. UNAIDS launched a webpage to provide those working in the HIV response with key information regarding the disruption on HIV programmes, including modelling live HIV incidences, and regular updates on the impact on service delivery at country level. UNAIDS also attempted to resource additional financial support from traditional and non-traditional donors
Notably, following the pause in funding from the US government, the UNAIDS Secretariat commenced an internal realignment or restructure process, led by consultancy firm Accenture. The High-Level Panel, which had already met, planned additional virtual meetings to discuss the developments and implications for recommendations on a fit-for-purpose UNAIDS operating model. Ultimately, these mitigations were hampered by the wider context of uncertainty and disruptions in the capacity of key participants of the High-Level Panel. With uncertainty from key contributors to UNAIDS core budget, there is an ongoing risk that UNAIDS must respond to further fiscal shocks and that this might further disrupt its ability to effectively deliver its transition plan and its mandate. A key mitigation for this risk is that UNAIDS should plan for a variety of realistic, financial scenarios and to ensure ongoing transparency in communication of its financial status to allow PCB members to make well-informed decisions on the future of the Joint Programme.
The deteriorating human rights context in many places in the world, as well as shrinking civic space and disruptions to community-led responses, have proven significant risks to the Joint Programme’s delivery against its mandate during this year. HIV-related inequalities persist, especially for children, key and other priority populations, and women and girls. There is a risk that as UNAIDS transitions its functions across the UN and downsizes, work to protect and promote the rights of the most marginalised and vulnerable groups is affected. As part of the UN80 initiative, the UN Secretary General has created seven clusters to take forward reforms. The UNAIDS Executive Director has contributed to clusters on both ‘development in the UN System’ and ‘Human Rights’. At a country level, UNAIDS is planning work as part of its transition to integrate its country support in the Office of the UN Resident Coordinator. As part of this UNAIDS is advocating for reforms to the RC model to ensure that it is fit for purpose. It will be important to ensure that - both in principle and in practice at country level – the reformed UN system under UN80 and the UNAIDS transformation programme continues to provide protection for the rights of the most vulnerable communities living with or at risk of HIV.

After restructuring, UNAIDS is likely to face heightened ethical and operational risks, particularly in isolated or high-risk offices, due to its significantly reduced footprint and reworked organisational structure. In countries where only one staff member is present, oversight and peer accountability may be limited, increasing the potential for ethical lapses or misconduct. Isolated offices, particularly in high-risk settings, may also be more vulnerable to sexual exploitation and abuse. The risk of misconduct, including retaliation, going unreported may be elevated in environments where staff may feel isolated or fear consequences for speaking out. Implementing protective measures will be more challenging in smaller teams where separation of roles and responsibilities is less feasible.
To address increased ethical and operational risks from restructuring, the Ethics Office will implement a strategy focused on prevention, support, and accountability. This includes collaborating with management to develop an accountability framework that defines the responsibilities of all personnel in preventing and addressing sexual misconduct. The approach ensures proactive prevention, fair support for victims, due process for accused individuals, and protection for witnesses. Additional mitigation measures will include targeted training in high-risk areas, initiatives to reduce retaliation fears, digital monitoring tools, and close cooperation with senior leadership and departments for a unified response.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
FCDO is contributing core funding to a multilateral programme which is being implemented by UNAIDS Secretariat and its 11 Cosponsoring Organisations. A Central Assurance Assessment concluded in December 2022 provided assurance on the Joint Programme’s capacity and capability to deliver in line with FCDO’s expectations on delivery, commercial and financial performance.
Narrative and financial reporting has been provided by UNAIDS as part of its biannual reporting to the PCB, in June 2025. This included annual organisational oversight reports including a finance report with an update on UNAIDS Statement of Internal Control, the report of the Internal Auditor, the report of the External Auditor, and the annual report of the Independent External Oversight Advisory Committee. The reports demonstrated generally satisfactory controls.
A performance agreement is in place for this business case. Progress against the performance agreement is assessed through the Annual Review, with the performance indicators forming a sub-set of the output indicators reviewed in depth in Section C of this report. The performance indicators, and assessment against them, are summarised in the Table 1 ‘progress against performance indicators’ which also shows how this corresponds to the programme log frame. Overall, UNAIDS is assessed as having ‘met expectations’.

Table 1: Progress against performance indicators

Performance area	Log frame output indicators	Progress
Delivery against reforms including: / Conceptualisation of HLP / Quality of HLP and its delivery / Management response to reforms / Implementation plan for reforms	Output indicator 2: UNAIDS delivers against its planned reforms and using learning from these processes, effectively adapts its operations in accordance.	Met expectations
‘Right sized’ and effective workplan and budget and transparent associated processes	Output 3: UNAIDS is a transparent organisation with effective systems and policies in place, and a realistic and fully financed workplan, aligned with priorities and which delivers value for money.	Not met expectations
Safeguarding	Output 4: UNAIDS efforts to improve safeguarding measures are continued, sustained and effective	Met expectations

The expectation and need for UNAIDS to reform predates the present funding crisis. However, the financial shock experienced in 2025 dramatically increased the urgency of this. UNAIDS estimates a core funding gap of US$ 82million for 2025. They have managed the gap this year by withholding remaining transfers to Cosponsors, reducing the operations and activities of the Secretariat where possible, and drawing down on the core fund balance. They are moving to reduce costs next year through an extensive restructuring which will reduce the number of staff, reduce country office footprint, and move staff to lower cost duty stations. The PCB agreed that they can fund the costs of the restructuring by temporarily reducing the Operating Reserve Fund (ORF). The Secretariat is required to present a plan for replenishing the ORF at the December PCB.
As UNAIDS cuts its headcount and footprint for its Secretariat and withholds remaining transfers to the Cosponsoring organisations its ability to deliver will be reduced. The capacity of Secretariat staff to deliver day-to-day will be affected during the restructuring as teams are reconfigured. Some Cosponsors may have to reduce or halt Joint Programme activities pending receipt of further transfers. Overall programme activity is set to contract in the future as the new operational model comes into force in January 2026. If transfers to Cosponsors do not resume in some form, this may include significant reductions in Cosponsor activity.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The FCDO programme team met regularly with UNAIDS during the review period to discuss progress and challenges. Donor group meetings also provided an opportunity for UNAIDS to provide updates and share priorities. The donor group meetings also provided a forum for the FCDO programme team to reflect on activities and share learning with other donors and its reflections.
In relation to evidence, financial and narrative reporting is provided by UNAIDS biannually. UNAIDS also has an Independent Evaluation Office who reports to the Board annually. The last report was presented in December 2024 and detailed progress against implementation of the 2024/2025 Evaluation Plan with one evaluation completed in 2024[6]. A comprehensive Joint Programme Evaluation and a Midterm Evaluation of the Cooperative Agreement between CDC and UNAIDS was scheduled for 2025, however their status is uncertain given the respective restructuring and pause to funding.
[6] The Independent Joint Evaluation of the Global Action Plan for Healthy Lives and Well-being for All (SDG3 GAP). https://www.unaids.org/sites/default/files/media/documents/executive-summary_report_joint-evaluation-of-sdg3-gap_en.pdf
This was supplemented by annual review interviews conducted in May and June 2025 ahead of the PCB with a number of partners within the Joint Programme including UNAIDS Secretariat, Cosponsors, implementing countries, donors and community representatives.
In relation to the programme log frame, the FCDO programme team might consider revising the log frame and related milestones when the new operating model is in place so that it accurately reflects what is possible in the new model.
The FCDO programme team has shared learning from UNAIDS reform journey internally, as UNAIDS has shared learning from its journey across the UN as part of the UN80 initiative. As the initiative progresses, both FCDO and UNAIDS should take advantage of opportunities to share lessons learned on the reform process and its implications for wider UN reform.

Date of last narrative financial report	June 2025	Date of last audited annual statement	June 2025