## Annual Review Template

Title: Building organisational capability to safeguard against sexual exploitation and abuse and sexual harassment
Programme Value £ (full life): £20m		Review date: October 2025
Programme Code: 400241	AMP start date: 22/10/2024	AMP end date: 30/04/2030

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0007560.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400241

A. SUMMARY AND OVERVIEW

Description of programme

The Building organisational capability to safeguard against sexual exploitation and abuse and sexual harassment programme launched in October 2024 to provide up to £20m over 5 years across multiple countries. The programme aims to build organisational capability in the aid sector and strengthen safeguards against sexual exploitation and abuse and sexual harassment (SEAH). The two key priorities areas sitting under two components are:
1. Supporting less-resourced organisations in the sector to reach international SEAH safeguarding standards through a direct capability building programme (£15m)
2. Investing in pioneering capability-building initiatives to drive up prevention and response practices and standards through a dedicated Capability Fund (£4.7m)
The dedicated capability building programme takes forward the previous FCDO-funded Safeguarding Resource and Support Hub programme which ran from 2019 to April 2025; an A* rated programme providing both a one-stop-shop of resources, learning and materials via a global online platform and deeply contextualised support through direct training and mentorship in specific national hub settings, largely across MENA, South Asia and Africa.

The Capability Fund has been established to support best-practice capability building initiatives. The fund aims to support a range of initiatives over 5 years, including best practice prevention (e.g. adherence to international standards) and response (e.g. investigations training, reporting and awareness raising) offers and through supporting pilots/ newer approaches to test and promote their effective implementation across the sector.

Summary supporting narrative for the overall score in this review

Overall, the programme has met expectations, during what has been its design and mobilisation phase.

Given this is the first Annual Review, and activities under this programme only commenced from May 2025, the focus is largely on the programme’s mobilisation and procurement rather than delivery. It is too early to review impact or outcome levels of the Logframe.

The Safeguarding Resource and Support Hub programme (RSH) (component 1) was successfully tendered in May 2025, for up to £15m over five years to May 2030. The Logframe therefore reflects this with Inception Phase process-based indicators and targets, which capture progress during the period October 2024 – October 2025. RSH has achieved strong progress against its inception phase deliverables, with a smooth handover of the previous contract, which resulted in no break in service on the online platforms of tools, resources and support. Alongside the continuing online platforms, the programme is on track to commence direct delivery of support and services once again in six locations Ethiopia, Nigeria, Bangladesh, Pakistan, Jordan and Syria from February 2026 (when Implementation Phase begins).

The Capability Fund (component 2) has been able to support two key initiatives this year –
The Humanitarian Quality Assurance Initiative (HQAI) Facilitation Fund. We invested £400,000 covering 2 years, 2025/26-2026/27, into this multi-donor pooled fund. The Facilitation Fund supports organisations that want to access HQAI's services, and individuals in covering their auditor training costs. The Fund helps to ensure that more local and national actors are audited against the international best practice Core Humanitarian Standard (CHS) as an evidenced-based way to demonstrate quality of work and so increase their access to quality funding. The Fund is on track and performing well against targets and goals.

Interagency PSEA (Protection from Sexual Exploitation and Abuse) Community Outreach and Communication Fund. We invested £900,000 covering 3 years (2025/26-2027/28) into this multi-donor pooled fund. The PSEA Outreach Fund is a joint initiative of the International Council of Voluntary Agencies (ICVA) and UNHCR which invests in community-led efforts by local and national organisations to deliver information, education and communication materials, sensitisation and systems-building activities on PSEA to high-risk communities. The Fund aims to support the critical work that local and national NGOs do each day to prevent SEA in the sector. It helps ensure that victim-survivors and broader communities know how and where to safely report SEA, and that systems for safe reporting, referral and victim-survivors support are in place, rooted in the recognition that local capacities and expertise are essential to effectively reinforce PSEA. The Logframe delivery targets for ICVA do not cover this AR as the funding agreement was only signed in September 2025.
Major lessons and recommendations for the year ahead

A recommendation based on the lessons from the first year is to wait for clarity on the medium-term UK ODA landscape before deciding whether to continue with the Capability Fund as originally envisaged. See Risk section for further detail.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for the programme is anchored in the key long-term outputs set out below and linked directly to HMG’s 2020 Strategy on Safeguarding against SEAH ToC. The programme ToC was finalised in October 2024 using the latest evidence to set out how the planned interventions of the programme interact with the broader context. In this first year of activities, given the early stages for all components, we assess the steps to achieving outcome and impact are still valid. No changes are proposed.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track across both components. RSH has delivered against all inception targets to date and preparations are well underway to develop and prepare for implementation phase which will commence from February 2026. The HQAI Facilitation Fund has met all indicator targets so far. HQAI’s 2025 analysis of 12 organisations demonstrates that audited organisations improved their scores on PSEAH related indicators by 14.5% over their audit cycle. The funding agreement for ICVA’s PSEA Outreach Fund has now been signed.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis of progress to date and successful procurements, the programme is on track and delivering well so far. We therefore assess that the programme should continue.

Safeguarding against sexual exploitation and abuse and sexual harassment is an FCDO priority, and this programme is a key element of how the UK aims to achieve the objectives set out in the UK’s 2020 SEAH Safeguarding Strategy.

The programme has met its key indicators for the period, with signed agreements in place with key delivery partners, laying the foundations for delivery. Although in its early stages, the programme components have demonstrated a strong commitment to the pursuit of value for money and learning from previous programming and efforts.

## C. DETAILED OUTPUT SCORING

Output Title	Component 1: The Safeguarding Resource and support Hub strengthens safeguarding capability of organisations across the international aid sector (RSH 2)
Output number:		1	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
1.1 RSH 2 programme launched. Design and procurement phases completed, contract / signed.	a) Design and procurement phases completed / b) Contract signed	a) Design and procurement phases completed / b) Contract signed / Met expectation
1. 2 RSH 2 programme inception phase deliverables completed	a) Inception Plan and Quarterly Narrative Reports / b) Commenced inception deliverables; plans for the Global Assessment, Knowledge Management Stocktake, Refreshed Mentorship Strategy and Implementation Strategy (e.g. MEL, Comms and Engagement, Theory of Change) / c) Commenced Country Assessments of National Hubs and approach to New Country Selection	a) Inception Plan and first quarterly narrative report received and signed off / b) Inception deliverables kicked off and on track / c) Country assessments framework and data collection exercise underway / Met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
1.1 RSH 2 programme launched. Design and procurement phases completed, contract signed
This indicator has been met. During the design phase, FCDO took an open and consultative approach to informing the direction of the programme. FCDO conducted an early market engagement (EME) survey in May 2024. The EME survey received 34 responses from stakeholders across national and international settings to inform the programme design and commercial approach. Survey responses supported a lead supplier model, engaging with downstream and partner organisations, with many highlighting a preference to a consortium-style approach. Flexible and agile programming structures were also highlighted.
The procurement was launched in January 2025 under the new Global Development Delivery (GDD) Framework. Cowater International was selected to lead the programme, working in a consortium-style approach with SDDirect as the technical lead alongside Terre des Hommes (TdH) the International Council of Voluntary Agencies (ICVA) and the Global Women’s Institute (GWI) at George Washington University. SDDirect, TdH and ICVA bring direct experience and existing working relationships from RSH1 contract.
The programme launched in May 2025, with a smooth transition between the RSH 1 contract and this new phase contract. A successful kick-off workshop with FCDO and the consortium was held in June 2025 which discussed and agreed the programme approach, plan for inception, and fostered team cohesion.
1.2 RSH 2 programme inception phase deliverables completed
This indicator has been met.
(a) Inception Plan and Quarterly Narrative Report:
RSH developed the Inception Logframe as a first key deliverable of the inception phase of the contract, in consultation with FCDO. The Inception Logframe was approved by FCDO on 31 July 2025. The first Quarterly Narrative Report was submitted in August 2025, which included an update on all relevant governance milestones and wider programme updates.
The Executive Steering Committee (ESC) has been established with key governance, terms of reference and membership agreed. The main purpose of the ESC is to provide a strategic platform to discuss RSH progress and assess risks. It will be comprised of senior level representatives from FCDO Safeguarding Unit, SDD, Cowater, Terre des Hommes, George Washington University and the Local Affiliate Partner (LAP) cohort.
(b) Commenced Inception Deliverables: Global Assessment, Knowledge Management Stocktake, Refreshed Mentorship Strategy and Implementation Strategy (Monitoring, Evaluation and Learning, Comms and Engagement, Theory of Change)
The first Quarterly Report alongside a first Quarterly Meeting detailed the RSH’s progress against Inception Deliverables thus far, with all activities on track. The supplier is actively conducting data collection and shaping key deliverables due by the end of the inception phase in the Inception Report due at the end of January 2026.
Global Approach Paper - the programme is updating its understanding of the global context to ensure that programme strategies, support mechanisms, and learning priorities are relevant and impactful. In support of this, the global team has undertaken several focus group discussions (FGDs) and Key Information Interviews (KIIs). In addition, a sector wide survey was launched in July focused on CSOs, with questions related to the PSEAH capabilities, risks, comms and building an evidence-base. The survey received 770 responses from respondents across 34 countries, providing a rich data source to draw from. The findings will be validated in October, through two workshops with key stakeholders, and used to inform planning as the programme transitions into implementation.
Knowledge Management Stocktake – an approach paper outlining the objectives, scope, timeline, and process for assessing the RSH online platforms existing, key knowledge products was developed and discussed during the kick-off workshop in June 2025. This paper outlined the types of materials to be reviewed, the criteria for the stocktake process, and proposed actions for materials that do not meet the expected quality standards. The stocktake process began in early June and, to-date, over 200 primary products have been reviewed, together with relevant parts of the website such as the Safeguarding Essentials and RSH topics. The emerging insights will be used to inform strategies for synthesising and consolidating key materials to improve accessibility, coherence, and long-term dissemination.
Theory of Change and Monitoring, Evaluation and Learning (MEL) Framework: are in initial discussions. A coding framework has been developed for the purpose of analysis of the data collection from the Survey, KIIs and FGDs. A Theory of Change workshop will be held in November with the consortium and FCDO to test the working draft. The approach for an independent evaluation of the programme over its lifetime will also be developed during inception phase.
Comms and Engagement: A Communications Strategy is under development in stages to ensure it is evidence-based, consultative, and aligned with programme priorities. RSH is undertaking specific digital communications and technology landscape research, using a mixed-methods approach combining desk-based research with KIIs. This methodology ensures capture of both documented data and practical realities that may not be reflected in publicly available research, with local staff providing guidance toward relevant online resources, statistics, and contextual insights for target countries. A Policy Influencing Strategy will be developed at the global and at each country level. A targeted desk review has been completed to analyse the SEAH context, Gender equality, disability and social inclusion (GEDSI) impacts, legal frameworks, and service gaps for each focus-country (as a part of country data collection).
(c) Commenced Country Assessments of National Hubs and approach to New Country Selection
Ahead of the next phase of RSH National Hubs, the programme has designed and implemented a Country Assessment framework and data collection exercise to inform each Hub's strategy and better understand the power dynamics, incentives and constraints, priorities, risks, and key stakeholders in each. Data collection will consider the following in each country:
- Country legal context and service mapping for PSEAH
- GEDSI analysis
- Analysis of PSEAH risks
- PSEAH capabilities amongst CSOs and PSEAH services delivered
- Building an evidence base for PSEAH
- Digital, communication and technology landscape
Data collection will be completed in four RSH hubs – Pakistan, Bangladesh, Syria, and Jordan – which will (re)launch direct delivery from February 2026. Ethiopia and Nigeria are currently being led by a local Civil Society Organisation (CSO) as part of the RSH 1 programme pilot localisation models (Local Affiliate Partnerships or LAPs). Both locations will also carry out data collection for Country (re)Assessments to support to inform the next phase of operations, led by the CSOs.
Up to three additional country hubs will open under this new phase, likely to be one each in MENA, Africa and South Asia. RSH have agreed a country selection approach paper with FCDO. Countries will be identified using a robust, context-driven selection process that integrates PSEAH risk exposure, enabling environments for safeguarding, and operational viability. The key goal is to ensure RSH programming is impactful, locally owned, and sustainable, building on the lessons, networks, and evidence generated through the first contract phase of RSH.  The selection process reflects a deliberate balancing of need, opportunity, and feasibility. RSH will now undertake a country selection process (including informed by KIIs and analysis within a shortlist of locations) and present options to FCDO to agree the new countries by January 2026.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to this output. This will be reworked however, for the next Annual Review, as the Inception Phase will have been completed for RSH in February 2026. As part of the Inception Report due then, a draft Implementation Phase Logframe will be submitted to FCDO for review, refinement and sign-off.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The RSH consortium of partners has already enabled a strong start to strategic engagement and kick-off of activities, with strategic partners in the sector internationally and in key national settings. This has enabled the programme to quickly commence country assessments and engagements.

A key lesson learning activity for the new programme has been the final publication of the Alinea International Independent Evaluation of the first Resource and Support Hub Programme (2019-2025). This thorough end-line evaluation reviewed ‘RSH1’ programme’s effectiveness, impact, relevance, efficiency, sustainability, and value for money in strengthening safeguarding against SEAH in the sector. It focused on the extent to which the programme supported capacity-building of small less resourced national CSOs, sharing key lessons learned and 12 recommendations which were, in particular, to support to inform delivery of this next phase of the programme. For example, key recommendations focused on engaging leadership, prioritising mentorship, contextualisation and accessibility of support and sustainability. The RSH2 programme partners joined the presentation of findings of the evaluation and have reviewed the full report to help inform thinking for shaping inception and implementation actions.

Output Title	Support to best-practice initiatives that aim to improve prevention and response practices and standards, especially for local and community-based organisations
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
2.1 The Humanitarian Quality Assurance Initiative (HQAI) Facilitation Fund ensures more local/national NGOs are audited against the Core Humanitarian Standard, increased their access to quality funding. / a) Number Local /National Non-Government Organisations (L/NNGOs) supported to access HQAI services (subsidies and project).	a) N/A	Contract signed and programme making strong progress already with 14 L/NNGOs supported to access HQAI services (subsidies and project). / Met expectation
2.2 Interagency PSEA Community Outreach and Communication Fund invests in NGOs supporting community-led efforts to mobilise action to prevent SEAH. / a) Contract signed with ICVA / b) Number of PSEA Outreach Fund funded community engagement and outreach projects supported at community level.	Contract signed with ICVA / N/A	Contract signed in September 2025 / N/A / Met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Under Component 2 of this programme, The Capability Fund, two funds have been supported in 2025:

The Humanitarian Quality Assurance Initiative (HQAI) Facilitation Fund. £400,000 over 2 years 2025-2027
The HQAI Facilitation Fund supports organisations that want to access HQAI's services, and individuals in covering their auditor training costs. Applications are made to an independent committee, which grants subsidies that can cover up to 90% of the cost of an audit or training. The Fund works to ensure that more local and national actors are audited against the international best practice Core Humanitarian Standard (CHS) as an evidenced-based way to demonstrate quality of work and support to increase their access to quality funding. National organisations are prioritised, especially those in high-risk locations and with lowest annual incomes.

Interagency PSEA Community Outreach and Communication Fund. £900,000 over 3 years (2025-2028)

The Interagency PSEA Community Outreach and Communication Fund (PSEA Outreach Fund) is a joint initiative of the International Council of Voluntary Agencies (ICVA) and UNHCR which aims to support the critical work that local and national NGOs do each day to prevent SEA in the sector. The PSEA Outreach Fund responds to the need for effective and timely information, education and communication materials and outreach on PSEA, tailored to local cultural contexts, operational realities, and groups that are most at risk, while considering language, literacy, age, gender, diversity and other capacity. The PSEA Outreach Fund invests in community-led efforts community-led efforts by local and national organisations to deliver information, education and communication materials, sensitisation and systems-building activities on PSEA to high-risk communities, rooted in the recognition that local capacities and expertise, including rights holders from affected communities themselves, are essential to effectively reinforce PSEA.
2.1 The Humanitarian Quality Assurance Initiative (HQAI) Facilitation Fund
This indicator is on track. The funding agreement with HQAI was signed in January 2025. Whilst the programme is not being scored this year against the number of Local /National Non-Government Organisations (L/NNGOs) supported to access HQAI services (subsidies and project), 10 organisations are already in the pipeline for new subsidy allocations. In the reporting period the Facilitation Fund Management Committee allocated subsidies to 14 organisations from six locations: Yemen, Lebanon, Ethiopia, Occupied Palestinian Territories (OPTs), Türkiye/Syria and Benin. HQAI undertake regional outreach activities to promote the benefits of the Core Humanitarian Standard and independent quality assurance against it with the Facilitation Fund one of the key offers to facilitate audit accessibility. In January 2025, HQAI reviewed its costing model with a focus on L/NNGOs, reducing the cost of a three-year audit cycle by up to 20%.

To support L/NNGOs to prepare for undertaking these audits, the fund is also working to develop an e-learning, a tailored service for risk assessment and targeted reporting on organisation readiness to undergo a CHS audit. The piloting phase for this is now completing and it is expected that this new service will be launched at the end of 2025.

As part of HQAI’s broader aims to ensure more local actors are audited against the CHS, HQAI track the ratio of L/NNGOs amongst total number of audited partners, with an aim see at least 40% of partners being L/NNGOs. HQAI is overachieving against this goal, currently at 48%. In addition, in line with localisation ambitions, HQAI has successfully trained audit facilitators in strategic focus regions, including the Sahel. Trainee auditors from the 2024 training are scheduled to conduct their first audits under the supervision of HQAI Senior Auditors in 2025. A one-year project (A2A project) funded by Luxembourg and co-financed by the Facilitation Fund will measure organisational capacity over time (the fund specifically supports eight local/national organisations in Lebanon and Palestine) with results expected early 2026. This demonstrates HQAI’s strong commitment to this overall output in focusing support towards local and community-based organisations to improve prevention and response practices and standards.

FCDO’s Safeguarding Unit funds HQAI more broadly under the Global Architecture Programme.

2.2 Interagency PSEA Community Outreach and Communication Fund
This indicator is on track. The funding agreement was signed in September 2025. FCDO will now work with ICVA to develop logframe targets with an aim to track both the number and the effectiveness of projects funded. For example, in addition to funding these projects, all materials developed by the Fund are made available to the wider sector for their use and adaptation through a Deliverables Database. The PSEA Outreach Fund was previously funded by FCDO under our Safeguarding Innovation and Engagement Programme Fund.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to this output. Targets for the PSEA Outreach Fund will be developed for the next Annual Review now that the funding agreement is in place for ICVA.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

HQAI Facilitation Fund: A recommendation for the year ahead is that HQAI and FCDO should continue to seek qualitative L/NNGO user feedback their audit experience under the Facilitation Fund, but may need to be reduce expectations about the number and depth due to funding and related pressures on staff.

## D. VALUE FOR MONEY

Given that the programme is early in its lifecycle it is not possible to provide a full assessment of VFM. However, good VFM has been demonstrated in the design, procurement and inception phases.

Key cost drivers and performance
The main cost drivers of the programme are associated with RSH. This includes Short-Term Technical Advisor (STTA) budget, travel, and face-to-face delivery costs. We expect capability-building initiatives to be developed and delivered by those with expertise either in-house to the supplier or contracted externally. Where expert advice is procured, suppliers must evidence that daily fee rates and overall charges are competitive, benchmarked against market standards, and compliant with FCDO fee rates as outlined in the Global Development Delivery (GDD) Framework. All costs were agreed during the tendering process and fixed for the duration of the contract. Appropriate payment models will be adopted to ensure FCDO pays only for high-quality outputs. Any risks related to cost will be closely monitored as part of routine programme management.

Economy
Economy has been enhanced by fostering strong competition and constructive collaboration between potential suppliers. The main cost drivers were assessed during the procurement stage of the contracting process and savings were negotiated based on existing FCDO Framework Arrangements, for example the GDD framework where fee caps are already agreed. The competitive process and ToR for RSH focused on ensuring and measuring VFM across the programme lifecycle and asking how potential partners plan to drive VFM and inform programming decisions. For RSH, the implementing partners will develop a VFM framework during the inception phase to drive this. RSH will report quarterly against value for money indicators across the four ‘E’s’ of VFM (economy, efficiency, effectiveness and equity).

Efficiency
While it is too early to provide an overall indication of programme efficiency, the programme aims to minimise indirect costs so that they do not impact on programme effectiveness. This is monitored at both programme level as well as reviewed for each key component. All funding and activity will be monitored against agreed workplans to ensure good control and oversight. The programme engages with partners who have demonstrable expertise and are best placed to complete the work. Suppliers have been procured via FCDO’s usual competitive processes to ensure that they provide the most efficient services. We will also work closely with suppliers to ensure that the programme builds on, rather than duplicates existing work and activities, a key element of efficiency and VFM.

Effectiveness
The programme will demonstrate its effectiveness by strengthening the SEAH capabilities of aid organisations, promoting best practices, and filling evidence gaps around effective interventions. It aims to build trust in the sector – an essential foundation for both their operations and ours. Drawing on lessons from previous programmes and the EME, we work with implementing partners to design activities and outputs that are most likely to achieve meaningful outcomes and lasting impact. RSH’s model includes a technical expert pool which enables demand-led delivery, utilising a broad range of consortium experts, matched to programme need.

Equity
The programme tackles an issue (SEAH) driven by power imbalances and often rooted in gender inequality. Outputs include an aim to contribute to improving the lives of vulnerable groups, recognising that SEAH is known to particularly affect women and girls, minority groups, disabled persons and other groups who may have less power or be more marginalised. Programme outputs are therefore designed to be inclusive, equitable, and responsive to their needs. We have engaged stakeholders with relevant, demonstrable expertise to shape delivery, and where possible, disaggregate data to ensure a focus on inclusion and/or vulnerable groups are effectively reached.

The flexible nature of the programme will help to scale the resources, targeting them where the need and potential impact is greatest, and removing them from areas with lower impact.

Assessment of whether the programme continues to represent value for money
In light of the above VFM principles underpinning the programme – and already demonstrated in the early stages of the programme – the programme continues to represent good VFM.
E: RISK

Overview of risk management

The overall risk rating for this programme is Moderate. FCDO recognises that this programme covers a sensitive, highly technical subject and across a range of geographies (including humanitarian and Fragile and Conflict Affected States). The nature of work to tackle SEAH means that the locations and context are also likely to be higher risk.

All risks are actively monitored through an internal FCDO risk register (with risk appetite set against each risk category) and partner risk registers. The RSH risk register is shared by implementing partners on a quarterly basis, with key risks and progress against mitigations discussed at monthly and quarterly meetings. Partners under the capability fund are required to share and discuss key risks as a standard agenda item as part of regular meetings and within reporting.

During this first year of operations, no major risks in relation to delivery of each of the component programmes, have been identified, nor wider risks materialised. All partners have undergone relevant due diligence ahead of commencing programmes and activities, with no major risks or concerns highlighted. The programme is operating within its overall cautious (moderate) risk appetite.

External Context Risks:
The changing global landscape has had a big impact on the programme in this first year. The impacts of global rollback of rights alongside a reducing ODA landscape has seen a significant change in the global architecture for development, and therefore PSEAH. ODA reductions are severely affecting SEAH prevention and response through the loss of specialist and dedicated staff, the reduction or suspension of community outreach and reporting mechanisms, Gender-Based Violence (GBV) and child protection services, and local organisations’ presence and activities.
[note] Sustainable and effective resourcing models to protect against Sexual Exploitation, Sexual Abuse and Sexual Harassment - Wilton Park

ODA uncertainty has impacted the scope of the Capability Fund in 2025 and the number of initiatives that we have been able to consider supporting in future years. We have therefore carefully focused our funding to continue support to initiatives which have proven impact on PSEAH, including driving alignment. The contract for RSH has maintained the option for other donors or stakeholders to co-fund the programme, which was part the model for RSH1, and saw funding from others including FCDO posts and the Disasters Emergency Committee (DEC).

Wider (beyond FCDO) global ODA reductions pose risks to delivery of PSEAH capability building initiatives, as front-line partners such as CSOs and local/national organisations are increasingly constrained and/or under pressure in relation to capacity or resources as both funding reduces (creating pressures on budget allocations) and the number of active organisations reduces (as some organisations are forced to reduce scope or close entirely).

FCDO continues to encourage wider donor and sector investment in PSEAH prevention and response and capability-building initiatives too. The Safeguarding Unit will maintain non-ODA levers to drive PSEAH action e.g. convening and attending critical international stakeholder groups which advance coordination, capacity alignment, and use of PSEAH standards/tools. We will continue to use our global leadership role to drive alignment, collective action and ensure PSEAH remains an essential, not optional, component of delivering humanitarian, development, and peacekeeping work. FCDO continues to closely monitor these external context risks, working with key stakeholders and partners.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
It is early in the programme lifecycle and therefore not yet possible to fully assess delivery, commercial and financial performance. However, good progress has been made across several areas. All projects are managed and monitored by a Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO) in the FCDO Safeguarding Unit using narrative and financial reports, alongside regular engagement and meetings with implementing partners. There are no issues with the timeliness of reports and there is active and engaged communication with partners via email and virtual meetings between review points.
Resource and Support Hub
The RSH programme is delivered by a consortium, as described earlier, led by Cowater International alongside Social Development Direct as Technical and Delivery Lead, Terres des hommes (TdH), International Council of Voluntary Agencies (ICVA) and Global Women’s Institute, The George Washington University (GWI). Cowater were last assessed against the FCDO Supplier Code of Conduct in August 2025 and were marked compliant.
Supplier performance is managed using a robust performance management framework including a logframe and operational Key Performance Indicators (KPIs) built into the contract. All KPIs have been met to date.
Key programme documentation has been drafted by the lead supplier and shared and agreed with the FCDO. This includes the inception phase workplan, which provides a detailed breakdown of the key deliverables, and governance structures.
HQAI Facilitation Fund
FCDO signed an accountable grant agreement with HQAI in January 2025 to deliver the Facilitation Fund. The quarterly reporting process is in place between FCDO and the supplier, and the supplier has provided FCDO with financial forecasts alongside regular narrative updates.
ICVA
FCDO signed an accountable grant agreement with ICVA in September 2025 to deliver the Interagency PSEA Community Outreach and Communication Fund, a joint initiative of ICVA and UNHCR. The quarterly and annual reporting process has been agreed between FCDO and the supplier, and the supplier has provided FCDO with financial forecasts.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Monitoring of the programme is undertaken continuously through various means during the programme lifecycle. Broadly, monitoring is achieved through the following mechanisms:
- Regular check-ins, providing a platform for programme performance issues to be discussed using the agreed workplans
- Activity reporting, against key programme deliverables in workplans
- Quarterly/ annual reporting, assessing programme performance
- Annual Review: this year’s Annual Review is a light-touch desk-based review, largely focused on the programme’s mobilisation and procurement rather than deliver, and the inception phase of the Logframe. It is too early to review impact or outcome levels of the Logframe.

FCDO procured an external independent evaluation of the previous RSH programme contract, delivered by Alinea International from late 2024 to July 2025. It focused on the outcome level, to determine how far the programme achieved the expected results, value for money and to identify and capture key lessons and recommendations. The evaluation provided robust additional insights for design and early implementation of this new contract/ phase of RSH.

As part of the RSH contract, the implementing partners are required to commission an independent evaluation over its lifetime. During inception, the evaluation will be scoped out following a robust methodology to define the precise scope and questions which add value, including to provide new insights and ensure good value for money.

Evidence
At both the project and programme levels, decisions will be guided by robust evidence to enhance results and impact. A structured reporting process will support this, including for example, regular catch-ups between the FCDO and suppliers, quarterly or annual progress reports, an inception report, and an annual review.
End-user engagement is central to the programme’s performance monitoring. Feedback will be gathered for each programme component by implementing partners, through surveys, formal engagement and face-to-face consultations, forming a continuous feedback loop that enables ongoing adaptation and improvement. This forms part of the logframe as key indicators for the output the outcomes.
In addition to the supplier’s engagement activities, FCDO will conduct its own end user consultations through its network during quarterly and annual reviews. This will provide an additional layer of insight and validation.
Learning
The programme will focus on continual testing, adaptation, collaboration, and learning. We will seek user feedback from other donors and stakeholders and ensure we incorporate the perspective of local organisations into our learning on a regular basis.

In addition, the next annual review will be a major checkpoint with which to assess and inform the delivery of the programme. This AR and subsequent ARs will ensure that lessons learnt are integrated into future activities throughout the duration of the programme. Logframes will be reviewed annually based on performance and the PrOF and adapted where necessary.

Date of last narrative financial report	Financial narrative reports are received quarterly for RSH and HQAI Facilitation Fund. ICVA reports will be submitted annually.	Date of last audited annual statement	Audited statements by project partners received annually; 2024 statements submitted by August 2025