## BC Logframe
Building Capabillities Logframe
PROJECT TITLE | Building organisational capability to safeguard against sexual exploitation and abuse and sexual harassment
IMPACT | Impact Indicator 1 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
Affected populations are protected, respected, empowered and safeguarded against sexual exploitation, abuse and harassment | Evidence that organisations supported through the programmes have improved their knowledge, skills, understanding and practice on safeguarding against SEAH. a) RSH b) HQAI c) ICVA | Planned | N/A | N/A | a) RSH N/A (to be assessed as part of Evaluation) | a) RSH N/A (to be assessed as part of Evaluation) | RSH Impact Evaluation (either 2028 or 2029) | Capability building initiatives effectively bring about change to improve prevention and response to SEAH. The sector remains focused and motivated to address SEAH and the underlying causes e.g. norms, laws, policies, gender equality and structural inequalities - supporting to create the enabling environment for capability building initiatives to operate.
|  | Achieved |  | N/A
Source
Sources: Programme user and beneficiary feedback
OUTCOME | Outcome Indicator 1 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
Organisations working in the sector are better equipped to safeguard against sexual exploitation, abuse and sexual harassment (SEAH) | Capacity and Capability: Improved and sustainable capacity and capability to effectively hardwire safeguarding SEAH within organisations, contributing to a shift in organisational culture and strengthened accountability. a) RSH provide resources and support which are context and need specific to support organisations (particularly less-resourced CSOs) in priority hub locations b) HQAI continues to provide support through the Facilitation Fund. c) PSEA Community Outreach Fund continues to provide support. | Planned | N/A | N/A |  |  |  | Organisations in critical need of support are reached and have the capacity to invest time and resource to engage. Sufficient technical advice exists in the sector.
|  | Achieved |  | N/A
Source
Sources: RSH (Direct support e.g. Mentorship programme, resource library, E-learning and training series provided in priority locations), HQAI and ICVA Reports
| Outcome Indicator 2 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
| Endorsement: Widespread, rooted endorsement of SEAH safeguarding (at both international and local scale) beyond ‘donor compliance’, with networks across the sector engaging in more inclusive dialogue, strengthening shared learning on what works to prevent and response to SEAH in different contexts. a) Evidence of the programme components providing / supporting more inclusive peer learning, networking and exchanges b) with positive feedback from participating organisations supported through the programmes | Planned | N/A | N/A |  |  |  | Increased inclusive dialogue drives adoption of and improved SEAH safeguarding. Donor and partner appetite to tackle the issue remains.
|  | Achieved |  | N/A
Source
Sources: Partner reporting, engagement with users and beneficiaries
| Outcome Indicator 3 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
| Evidence: Contextualised and accessible evidence and learning on what works on building organisational capability and to prevent and respond to SEAH in the sector, which contributes to a strengthened regional and global knowledge and evidence base. a) RSH continues to produce, share and disseminate evidence of what works (research and learning) including RSH practice-based learning and which amplify marginalised voices b) Number of PSEA Community Outreach Fund funded community engagement and outreach products publicly available c) Learning from the HQAI Facilitation Fund | Planned | N/A | N/A |  |  |  | Research provides useful evidence which improve capability-building initiatives.
Achieved
Source
Sources: RSH (RSH-developed practice-based learning; sharing and disseminating key global research and learning; ongoing mapping of evidence base), ICVA reports Learning from HQAI Facilitation Fund
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
Component 1: The Safeguarding Resource and Support Hub strengthens safeguarding capability of organisations across the international aid sector (RSH 2) | RSH 2 programme launched. Design and procurement phases completed, contract signed. | Planned | N/A | a) Design and procurement phases completed b) Contract signed | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR. | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR. | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR. | Organisations in critical need of support are reached. Staff from organisations who engage with RSH have the influence to transfer learning into organisational change and improvements in PSEAH
|  | Achieved |  | Programme designed alongside market engagement and procurement complete with contract signed with new partners. Programme launched May 2025.
Source
Sources: FCDO inhouse reporting and RSH Quarterly Reports
IMPACT WEIGHTING | Output Indicator 1.2 |  | Baseline | 2025 | 2026 | 2027 | 2028
70% | RSH 2 programme inception phase deliverables completed: a) Inception Plan and quarterly narrative reports b) Commenced plans for the Global assessment, Knowledge Management Stocktake, Refreshed Mentorship Strategy and Implementation Strategy (MEL, Comms and Engagement, ToC etc.) c) Commenced Country Assessments of National Hubs and approach to New Country Selection | Planned | N/A | Key deliverables: Inception Plan and first Quarterly Report, Executive Steering Committee established with first meeting. Evidence of commencing wider Inception Deliverables: Global Assessment; Country Approach Papers; Knowledge Management Stocktake; Policy Influencing and Communications Plan; Mentorship Strategy; New Country Selection; MEL Framework; Theory of Change; Inception Report | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR. | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR. | N/A - Inception Phase Logframe indicator, to be developed for Implementation Phase and reported in next AR.
Achieved
Source
Sources: RSH Quarterly Reports, Evidence, Documents and Comms, discussed at quarterly meetings
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2025 | 2026 | 2027 | 2028 | Assumptions
Component 2: Support to best-practice initiatives that aim to improve prevention and response practices and standards, especially for local and community based organisations | HQAI Facilitation Fund: The Fund ensures more local/national NGOs are audited against the Core Humanitarian Standard, increased their access to quality funding. a) Number L/NNGOs supported to access HQAI services (subsidies and project). | Planned | N/A | N/A | 15 | 30 (cumulative) | N/A | Organisations in critical need of support are reached and have the capacity to invest time and resource to engage. Supporting local/national and community based initiatives helps to improve sector response to PSEAH.
|  | Achieved |  | 14
Source
Sources: HQAI quarterly reports, HQAI logframe, discussed at quarterly meetings
IMPACT WEIGHTING | Output Indicator 2.2 |  | Baseline | 2025 | 2026 | 2027 | 2028
30% | The Interagency PSEA Community Outreach and Communication Fund: The PSEA Outreach Fund invests in NGOs supporting community-led efforts to mobilise action to prevent SEAH. a) Contract signed with ICVA b) Number of PSEA Outreach Fund funded community engagement and outreach projects supported at community level. | Planned |  | a) Contract signed | b) Number TBC | b) Number TBC | b) Number TBC
|  | Achieved |  | Complete
Source
Sources: ICVA reports, quarterly meetings