## OUTPUTS
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1: 30 June 2026 | Milestone 2 | Target 30 June 2027 | Assumptions
Programme mobilisation and governance established Activities • Recruit programme team • Establish governance structures - steering group, Terms of Reference (ToR), Post buy-in • Finalise delivery plan and risk register • Operationalise Monitoring, evaluation and learning (MEL) systems | Programme governance structure formally agreed and operational (Yes/No) | Planned | No programme governance in place | Interim Approvals process established, including Post buy-in and used for all approvals Steering group established and meets at least once |  | Regular Steering Groups consistently being held with finalised ToRs | Timely recruitment approvals Key stakeholders remain engaged Sufficient data available to inform full logframe set up
Achieved
Source
Steering group ToR and meeting minutes, governance documents, records of Project approvals
| Output Indicator 1.2 |  | Baseline | Milestone 1: 30 June 2026 | Milestone 2 | Target 30 June 2027
|  | Planned | 0% programme funded roles overseas filled | Footprint agreed for programme funded roles overseas |  | ≥90% of core programme roles filled
| % of key programme funded roles filled and active | Achieved
Source
Programme organogram
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1: 30 June 2026 | Milestone 2 | Target 30 June 2027
25% | Monitoring, evaluation and learning (MEL) system operationalised | Planned | No MEL system in place | MEL Action Plan in Place Key Performance Indicators agreed for TAF |  | MEL framework approved and in use Logframe and indicators finalised
Achieved
Source
Approved logframe and MEL plan
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1: 30 June 2026 | Milestone 2 | Target 30 June 2027 | Assumptions
Delivery partners mobilised Activities • Sign funding agreements • Conduct partner inception meetings • Project activities initiated | Level of progress for the Partnerships for Growth projects relative to the planned workplan and annual allocation | Planned | 0 | ≥95% 25/26 allocation spent |  | First complete year reports received for all 25/26 projects Satisfactory performance for following trust funds/programmes: - Women Entrepreneurs Finance Initiative - TransformCare - Critical Minerals-to-Manufacturing Trust Fund | No significant project set up delays Partners able to mobilise as planned Operating context remains sufficiently stable No major access or security constraints
Achieved
Source
Finance Reports, progress reports
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Milestone 1: 30 June 2026 | Milestone 2 | Target 30 June 2027
|  | Planned |  | Programmes score at least A in their Annual Review for 25/26 Transfering Technical Assistance projects set up under JIG on AMP |  | Wind down plans in place and operational
75% | Legacy component programmes that will fall under JIG Business Case as part of the Growth, Trade and Jobs Community of Expertise delivering as expected and effective transition process in place | Achieved
Source
Annual Reviews
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## OUTCOMES
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Planned
| GDP growth | Achieved
Source
Transformational growth (diversified, productive, food security) | Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Planned
Achieved
Source
Inclusive growth (gender, vulnerable groups, pro-poor) | Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Planned
Achieved
Source
Green growth (resilient, adaptation, reduced carbon intensity) | Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## IMPACT
PROJECT TITLE | UK Centre for Green and Inclusive Growth
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Inclusive and sustainable poverty reduction and climate resilience. | Poverty headcount ratio | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| CO2 emissions avoided | Achieved
Source