Centre for Green and Inclusive Growth

Summary Sheet

Portfolio/ Business/Country Plan Summary: GIG will contribute directly to the Economic Development and Partnerships Directorate (EDPD) business plan: / Goal 1: Mobilise transparent and responsible investment – GIG will provide advice to businesses to increase quality investment, work on the enabling environment, and strengthen information flows to boost investment. / Goal 2: Provide Centres of Expertise and EDD staff capabilities to support inclusive, environmentally sustainable economic policies and regulatory frameworks - GIG will inform, advise, and influence economic policies and regulations.

Title: Centre for Green and Inclusive Growth (GIG)
Programme summary: The Centre for Green and Inclusive Growth (GIG) aims to contribute to inclusive and sustainable poverty reduction and enhance climate resilience. It will work in partnerships with governments, the private sector and civil society by providing technical assistance to firms, investors and government. It will also work with international partners, the private sector and civil society supporting the government’s ambitions to drive these relationships. GIG will support investment, jobs, women’s economic empowerment and incomes in partner countries. / GIG will provide expertise in developing countries in target sectors: mainly manufacturing and services, including agri-processing, green construction materials, textiles, electric vehicle production parts and assembly, environment-friendly packaging; and the services that complement these sectors and account for much of the value-add in the supply chain (e.g. design, logistics, e-commerce, and professional services). These are areas where the UK has domestic expertise. Focusing on these sectoral drivers of green and inclusive growth in the real economy has been shown by predecessor programmes to address a market failure in overcoming the binding constraints to green and inclusive economic growth (e.g. low private sector productivity, lack of responsible business practices, lack of inclusion - particularly women’s economic empowerment). It will provide world-class research, analysis and expertise on green and inclusive growth that is responsive, flexible and value for money. GIG will not work on infrastructure, trade, financial services, telecommunications, transport services or frontier tech which are covered by other Centres of Expertise underway. GIG supports the UK growth mission by building markets of the future for trade and investment, including using non-ODA to identify UK commercial opportunities. with DBT, securing critical supply chains while supporting global economic resilience.

What is the rationale for UK Aid spending? / GIG is strongly aligned to FCDO’s strategic priorities of driving sustainable, inclusive economic development that delivers opportunity for all, tackling the climate and nature crises, and empowering women, while helping forge a modernised development approach based on partnership and local leadership. GIG will support delivery of UK commitments to help deliver the UN Sustainable Development Goals (SDGs)[1] and the Paris Agreement on climate change. The programme will contribute significantly to HMG’s International Climate Finance (ICF) commitments and will help deliver on the government's ambition to foreground women and girls in everything we do. GIG outcomes are aligned to the SDGs specifically; gender equality (SDG 5); decent work and economic growth (SDG 8), industry, innovation and infrastructure (SDG 9) and; climate action (SDG 13). / The GIG also responds directly to ICAI’s recommendation for FCDO to renew its commitment to end extreme poverty, place vulnerable people at the heart of its work, and restore transparency and internal and external challenge to the management of UKAid[2].
Programme Value: £300m ODA funding (65%ICF); £7m non-ODA funding.		Country/ Region or Sector: Global
Department/Country Office confirmation of review processes		Director, Economic Development and Partnerships Directorate
Contact name		Team Leaders for Jobs and Inclusive Growth Team, Economic Development Department
Threshold for final approval of Business Case: Ministerial
Date of Approval of Concept Note:	21/05/2024	Name and role of Approver / Deputy Foreign Secretary and Minister of State, Minister Mitchell
Date of Approval of Business Case:	14/10/2024	Name and role of Approver / Minister of State, Minister Dodds
Programme Code:	AMP Start Date: / December 2024	AMP End Date: December 2031
Overall programme risk rating:	Moderate
[1] Goal 8 (good jobs and economic growth), as well as Goals 1 and 10 (cutting poverty and reduced inequality).
[2] https://icai.independent.gov.uk/review/uk-aid-under-pressure-synthesis-2019-2023/review/

Contents

List of Annexes (attached separately)

Annex A: Evidence that supports addressing the proposed constraints
Annex B: Climate and environmental risk assessment (CERA)
Annex C: Green and Inclusive Growth co-ordination with other Centres of Expertise and Centrally Managed Programmes
Annex D: Evidence base for GIG activities
Annex E: International Growth Centre (GIG Phase 2)
Annex F: Indicative Partners under component B
Annex G: Case studies of impact from GIG Phase 1
Annex H: Commercial options for component A
Annex I: Rationale for GIG focus on manufacturing and services
Annex J: Women’s Economic Empowerment
Annex K: Log frame (attached separately)

Acronyms

AGIL	Africa Gender Innovation Lab
AMP	Aid Management System
ASEAN	Association of Southeast Asian Nations
BB	Best Buys
BC	Business Case
BII	British International Investment
CASA	Commercial Agriculture for Smallholders and Agribusiness
CMP	Centrally Managed Programme
COE	Centre of Expertise
COP28	28th Conference of the Parties to the United Nations Framework Convention on Climate Change
CSO	Civil Society Organisation
DBT	UK Department of Business and Trade
DFI	Development Finance Institution
DFID	UK Department for International Development
EDPD	Economic Development and Partnerships Directorate
EDD	Economic Development Department
EME	Early Market Engagement
ESG	Environmental, Social and Governance
EV	Electric Vehicles
FCAS	Fragile and Conflict Affected States
FCDO	UK Foreign, Commonwealth and Development Office
FDI	Foreign Direct Investment
GDD	Global Development Diagnostic
GDP	Gross Domestic Product
GIG	Centre for Green and Inclusive Growth (this business case)
COE	Green and Inclusive Growth Centre of Expertise
HMG	His Majesty's Government
HMT	His Majesty's Treasury
HoM	Head of Mission
ICAI	Independent Commission for Aid Impact
ICF	International Climate Finance
IFC	International Finance Corporation
IGC	International Growth Centre
ILO	International Labor Organisation
IMF	International Monetary Fund
KPI	Key Performance Indicators
MA	Manufacturing Africa
MREL	Monitoring, review, evaluation and learning
MSME	Micro, small and medium enterprise
MDTFJ	Multi Donor Trust Fund on Jobs
NAP	National Adaptation Plan
NDC	Nationally Determimed Contributions
Non- ODA	Non-Official Development Assistance
ODA	Official Development Assistance
OECD	Organisation for Economic Cooperation and Development
PFP	Programme Funded Posts
RBC	Responsible business conduct
RED	Research and Evidence Department
SB	Steering Board
SC	Strategic Case
SCS	Senior Civil Servant
SDGs	Sustainable Development Goals
SEZ	Special Economic Zone
SME	Small and Medium Enterprise
SR	Strategic Review
SRO	Senior Responsible Owner
TA	Technical Assistance
TAF	Technical Assistance Facility
TOC	Theory of Change
UN	United Nations
VFM	Value for Money
WB	World Bank
WEE	Women's economic empowerment

## A. Strategic Case

The Strategic Case sets out the rationale for UK intervention in supporting green and inclusive growth in developing countries. It outlines the barriers to achieving growth that is green and inclusive and sets out FCDO’s experience in tackling these challenges. The strategic fit with UK policy priorities is set out alongside the impact and outcome we expect to achieve. Finally, this section specifies how the programme will comply with assurances on ODA spend, the Gender and Equalities Act, counterterrorism, safeguarding and climate and environment.

Strategic Context and need for UK intervention

Economic development, climate and nature and women and girls are top priorities for the new Foreign Secretary and Minister for Development, and all are addressed in this programme. This programme on green and inclusive growth aims to accelerate economic development, including by partnering with business to deliver economic growth, while foregrounding women and girls. We know that when women and girls are treated with respect and given opportunities that these feed into economic stability. The GIG will support our aim of ending extreme poverty while tackling the climate and nature crisis, and driving inclusive growth. This programme strongly supports the mission to “create a world free from poverty on a liveable planet” by supporting sustained, inclusive and green growth in partner countries. It is at the forefront of renewing our expertise and focus on supporting economic transformation and empowering women and girls. This will be achieved through a strong understanding of the local contexts and embedding this throughout the work of the programme

Context

“Growth…can spare people en masse from poverty and drudgery. Nothing else ever has.”[3] The evidence is clear that sustained economic growth is essential for sustained poverty reduction[4]. The miracle of growth has lifted hundreds of millions out of poverty in recent decades. Some go as far as arguing that ‘economic growth is enough and only economic growth is enough’[5] for ending extreme poverty and increasing basic human well-being. However, over the last decade, growth has stagnated in many parts of the developing world. Multiple overlapping social, economic and political crises mean that over seven hundred million people remain in extreme poverty, 9.4% of the global population (2022). The COVID19 pandemic pushed an additional 70m people into poverty in just one year by the end of 2020[6]. Progress against all internationally agreed Sustainable Development Goals is slow and off track. If current trends continue, over 340 million women and girls will still live in extreme poverty by 2030[7]. Supporting growth abroad is also good for the UK growth mission as emerging FCDO evidence suggests a 1% increase to global GDP above baseline in the medium-term increases UK GDP by an average of 1.6% per year.
[3] World Bank. 2008. The Growth Report: Strategies for Sustained Growth and Inclusive Development, Commission on Growth and Development. Page 1 (Link)
[4] David Dollar and Art Kraay, 2001, Growth is Good for the Poor (Link); Pritchett, Lant. 2022. Economic Growth in Five Figures (one with five variants) (Link)
[5] Pritchett, Lant, 2022, “Economic growth is enough and only economic growth is enough”, Oxford Blavatnik School of Government and London School of Economics. (Link)
[6] World Bank. 2022. Poverty and Shared Prosperity 2022: Correcting Course, International Bank for Reconstruction and Development / The World Bank.
[7] Progress on the Sustainable Development Goals 2023: Snapshot on Gender, UNWomen

Global growth has also not been distributed evenly, leaving stark and growing inequalities. Economic recovery from the pandemic was uneven and slower for Sub-Saharan Africa where more than half of the extreme poor live.[8] The Labour Manifesto recognises the growing political and economic importance of African countries, and plans to deliver a new approach to the continent to foster opportunities for mutual long-term benefit which this programme supports. Inequality also rose globally for the first time in decades and is expected to continue to rise, especially in low- and middle-income countries.[9] Inequality in some of the FCDO’s list of priority countries for investment partnerships is extremely high; In India, the richest 10% earn about half the national income, in Pakistan, Indonesia and Vietnam they earn between 40-50%[10]. 258 million people in 58 countries and territories faced acute food insecurity at crisis or worse levels in 2022, up from 193 million people in 53 countries and territories in 2021.[11]
[8] World Bank. 2024. Poverty and Inequality data Platform (PIP). Homepage (worldbank.org)
[9] World Bank. 2022. Poverty and Shared Prosperity 2022: Correcting Course, International Bank for Reconstruction and Development / The World Bank.
[10] World Inequality Database, “What’s new about inequality in south and southeast Asia in 2023”, 2023.
[11] Food Security Information Network (FSIN). 2023. Global Report on Food Crises 2023 (Link)

There is no denying the significant negative externalities that economic growth and development has had on the environment. The climate and nature crisis is one of the greatest long term global challenges that we face. Climate change is already causing widespread adverse impacts directly affecting people, economies and the climate and the environment. Across all countries and income levels, economic growth can see natural assets rapidly deplete – forests, fresh water, biodiversity, fish stocks among many others. This is often particularly acute in low and lower-middle income countries. The world has warmed more than 1°C since pre-industrial times and global warming targets of 1.5-2°C will be exceeded this century unless deep reductions to global emissions are made[12]. IPCC Working Group II highlighted that the world is already experiencing changes in global average temperature, shifts in seasons and seeing an increase in the frequency and severity of high temperatures, floods, droughts, storms and wildfires and other extreme events. and climate-related disasters. In the 20 years to 2015, they claimed over 600,000 lives, with an additional 4.1bn people injured, left homeless, or in need of emergency assistance.
[12] IPCC. 2022. Climate Change 2022: Impacts, Adaptation and Vulnerability. Contribution of Working Group II to the Sixth Assessment Report of the Intergovernmental Panel on Climate Change. (Link)

Preparing for the future not only means tackling the climate and nature emergencies, but also adapting to the changes they will bring to our environment. Climate change is a global challenge, but it is the poorest and most vulnerable who are hit first, hardest and are struggle most to recover, including young people, women and girls, and marginalised groups (e.g. people with disabilities and indigenous people), exacerbating inequalities both within and between countries[13]. Some 3.5 billion people are already highly vulnerable to climate impacts[14]. For instance, 20 million Bangladeshis will be displaced by a 1m rise in sea level in 2050[15]. Climate change is adversely affecting global food, water, and energy security, as well as physical and mental health[16]. Climate change globally also has the potential to erase development progress, undermine equality, poverty eradication, human development, and economic growth. It is clear that the effects of climate change and biodiversity loss require a significant shift globally towards more resilient and lower carbon growth. It is necessary to work with international partners, especially those at the forefront of the climate crisis.
[13] The Dasgupta Review (2021) of the Economics of Biodiversity
[14] For example, experiencing heat waves, rising sea levels, fiercer and more frequent storms, unpredictable rainfall bringing floods and droughts, acidification of our oceans and desertification.
[15] Asian Development Bank, “Climate change in Asia and the Pacific by the numbers”
[16] IPCC (28/02/22). Climate Change 2022: Impacts, Adaptation and Vulnerability. Contribution of Working Group II to the Sixth Assessment Report of the Intergovernmental Panel on Climate Change.

Approximately 2bn people live in parts of the world affected by violence, conflict and fragility. Overwhelmingly, these are also the countries most in need of economic development: by 2045, about 80% of the poorest people will live in states characterised by fragility[17]. As a result, the highest return to aid would be from actions that help fragile states escape the fragility trap, however achieving this faces many challenges. Growth is an important contributor to stability because countries tend to be more stable when the economy is growing, as long as benefits are felt by a wide range of groups. Fragility risks are being exacerbated by booming youth populations[18] in many fragile states. There is risk of a ‘demographic disaster’ if these countries cannot provide opportunities for productive work or sufficient public services[19]. Covid-19 and the Russia-Ukraine war put further pressure on fragility. The economic contraction caused by covid-19 was particularly severe in fragile states and the Russia-Ukraine war impacted global food security and energy prices. Fragile states lack the resources, institutions, capacities, political capital and often the will to respond effectively to such shocks. Evidence finds that a negative growth shock of 5% increases the likelihood of a major civil conflict by 50%[20]. Lack of economic opportunities also intensifies unplanned migration for economic reasons.
[17] ‘Who Are the Bottom Billion’. FCDO.
[18] Almost 50% of the world’s population is under the age of 24. Many of the world’s most fragile states — Afghanistan, Chad, DRC, Niger, Nigeria, Somalia and Yemen — also boast some of the highest fertility rates.
[19] Violence is strongly associated with rapid growth, especially where there are large numbers of young males.
[20] Blattman, Christopher and Miguel, Edward, 2009, Civil War. SSRN (Link).

For the purposes of this business case ‘Green and Inclusive Growth’ means growth that is a) transformational - diversified, productive, provides food security; b) inclusive of all genders, vulnerable groups and also the poor and c) green – driving climate resilience, adaptation, reduced carbon intensive emissions and supporting the global transition to net zero[21], while protecting nature. [22]Gender-inclusive green economic transformation actively promotes women's economic empowerment, recognises the interconnectedness of gender equality, environmental sustainability, and economic growth, and works to advance all three objectives.
[21] There is currently no agreed HMG definition for green growth. For the purposes of this BC we have drawn on definitions by a range of international organisations. FI (UN SDG website): UNESCAP: growth that emphasizes environmentally sustainable economic progress to foster low-carbon, socially inclusive development. OECD: fostering economic growth and development, while ensuring that natural assets continue to provide the resources and environmental services on which our well-being relies. World Bank: growth that is efficient in its use of natural resources, clean in that it minimizes pollution and environmental impacts, and resilient in that it accounts for natural hazards and the role of environmental management and natural capital in preventing physical disasters.
[22] We do not expect all interventions supported by this business case to meet all objectives simultaneously. Our approach to this is discussed further down in the business case (GIG Scope, paragraph 81)

Transformational growth: the importance of productivity

The PM has clearly stated that this government is one of wealth creation, that firmly recognises the importance of sustained economic growth to improve prosperity and living standards of working people. The criticality of growth to poverty reduction cannot be overstated. To sustainably reduce poverty, growth needs to be “transformational”. The latest evidence is unambiguous: transformative growth – growth that enhances the productivity and size of economies and creates productive jobs at scale – is instrumental to delivering most of the SDGs, including health and education outcomes.[23] Jobs can only be created at such a scale by the private sector, by partnering with business to deliver the economic growth necessary, and through large scale investment in productive sectors, transforming economic activity to more productive ends; either by expanding value chains or shifting to new production, generated at sufficient scale to create the millions of jobs needed. In 2015, the OECD forecast productivity “to be the main driver of economic growth and well-being over the next 50 years.”[24] This requires an approach that is pro-business and pro-worker.
[23] Pritchett, Lant, 2022, “Economic growth is enough and only economic growth is enough”, Oxford Blavatnik School of Government and London School of Economics. (Link)
[24] OECD. 2015. The future of productivity. Paris: Organization for Economic Cooperation and Development.

Historically it has been the growth of the manufacturing sectors that has raised the productivity of output and incomes in developing countries. In the past three decades, the services sector has grown faster than manufacturing in many developing economies and can be an additional important driver of transformation depending on which type of services. By 2019, services accounted for 55% of GDP and 45% of employment in developing economies[25]. Services can be important due to their job-creating and revenue-generating potential, because they are an increasing share of global exports, and because they are inputs into the production of goods and support the productivity and competitiveness of other sectors[26]
[25] World Bank Blogs. 2021. At your service? Developing economies bet on service industries for growth. (Link)
[26] Balchin, Neil, 2017, “Why services are important for industrialisation and economic transformation” Essay in Trade in SET Trade in Service and Economic Transformation, Overseas Development Institute (Link)

Exports and import substitution also have an important role in economic transformation. Growing sectors with strong potential for export gives access to larger markets, creates jobs, stimulates investment, attracts technology, and incentivises the domestic private sector to be more competitive. Importantly both exports and import substitution increase the quantity of forex available. This is important as industries with high levels of labour productivity rely on imported inputs, particularly in manufacturing[27], to upgrade technologies and productivity, and forex is needed to import these productivity enhancing inputs. Evidence finds that some regions, including Sub-Saharan Africa, face a binding forex constraint and alleviating this has a significant impact on growth[28].
[27] Spray, John and Wolf, Sebastian. 2017. Industries without smokestacks in Uganda and Rwanda. IGC Policy Brief. (Link)
[28] FCDO Internal Paper.

Within services, substantial investment in the care sector (incorporating paid and unpaid work caring for children, adults and the elderly, as well as household chores) is needed to underpin economic transformation and meet ambitions on women’s economic empowerment (WEE). Evidence shows that childcare availability in low- and middle-income countries has positive impacts on female labour force participation.[29] Investments in care also create jobs in a sector with increasing demand.
[29] Halim, Daniel, Elizaveta Perova, and Sarah Reynolds. 2022. Childcare and Mothers’ Labor Market Outcomes in Lower- and Middle-Income Countries. The World Bank Research Observer: lkac003.

Investments in inclusion can also double as investments in productivity – the IMF has found from macroeconomic, sectoral, and firm-level data that men and women are not perfect substitutes, but complement each other in the production process, bringing different skills and perspectives to the workplace, including different attitudes to risk and collaboration[30]. Hiring women can increase the productivity of women already employed in a firm, by reducing within-firm discrimination[31]. Studies have also shown that the financial performance of firms improves with more gender-equal corporate boards[32]. Increasing women’s participation in the paid economy therefore not only boosts growth through increasing the labour force, but also the additional productivity gains from gender diversity, resulting in both greater output and welfare gains[33].
[30] Ostry, Alvarez, Espinoza, and Papageorgiou. 2018. Economic Gains from Gender Inclusion: New Mechanisms, New Evidence. IMF Staff Discussion Note (Link)
[31] Ibid
[32] Ibid
[33] Ibid

Inclusive growth

Inclusive growth drives sustained exit from poverty through raising incomes, creating jobs, and increasing women, and other vulnerable populations’, participation in the workforce. While growth is an imperative for long-term poverty reduction, not all growth is created equal. The type of growth matters for job creation to be inclusive. Excluded groups, including women, have unequal access to quality jobs due to real and perceived skills gaps, social norms, time poverty, legal discrimination, and safety concerns, among other issues. This creates higher barriers to entry[34]. For example, in East Asia, growth in the manufacturing sector – particularly in textile and food services industries – has increased women’s wage work and improved female and child health and education outcomes, but there remains considerable occupational segregation and concentration of women in low paying jobs[35].
[34] Datta, N and Kotikula, A. “Not Just More, but Better – Fostering Quality of Employment for Women”. World Bank Jobs Working Paper Issue No.1 Fostering Quality of Employment for Women(Link) P8-9
[35] Hanmer,Lucia C.; Klugman,Jeni; Morton,Matthew H.; Singer,Dorothe. 2014. Gender at work : a companion to the world development report on jobs (English). World Bank. (Link)

Despite the known benefits of WEE, women continue to suffer significant disadvantages in economic opportunities and outcomes. According to UN Women[36], globally, 61.4% of women aged 25 to 54 were in the labour force in 2022 compared to 90.6% of men. In 2019, for each dollar men earned in labour income, women earned only 51 cents[37] – meaning that women’s share of total labour income was a mere 34%. Employment differentials, occupational segregation, often into lower productivity jobs and the higher likelihood that women will hold part-time jobs and interrupt their careers due to care responsibilities perpetuate gender labour income gaps and cement income inequalities across the life course.
[36] UN Women. 2023. Progress on the Sustainable Development Goals The Gender Snapshot 2023. (Link)
[37] Ibid

The government’s mission highlights that a strong economy can only be built on the contribution of every community and must include the many, not the few. Economic growth must support good jobs and productivity growth for many, not the few. Evidence finds that growth is strongly associated with poverty reduction when it is growth that raises median incomes[38]. This requires that growth involves large swathes of the population in increasingly productive work. This is particularly necessary in Sub-Saharan Africa and some countries in Western Asia which will drive most of the world’s future population growth[39]. The population of sub-Saharan Africa could more than double between 2000 and 2060[40]. The booming youth population here means that failure to expand employment will drag median incomes down, and would not support sufficient poverty reduction to meet the SDGs. On the current trajectory poverty is expected to become increasingly African with 90% of the poor expected to be living on the African continent by 2030[41].
[38] FCDO Internal Material.
[39] UK Government. 2023. ‘Global trade outlook 2023’, page 14 (viewed on 24 October 2023). (Link)
[40] Canning, D. and others. 2015. ‘Africa’s demographic transition: dividend or disaster?’. World Bank and Agence Française de Développement (viewed on 24 October 2023). (Link)
[41] World Bank. 2019. Accelerating Poverty Reduction in Africa: In Five Charts. (Link)

Whilst this Business Case does not include activities related to public finances, growth – resulting from a sustainable expansion of private sector activities - creates the resources needed by the public sector to improve the quality and availability of public services including education, health, food and nutrition, and economic security and resilience.

61% of the global employed population earn their living in the informal economy[42] and 90% in developing countries. Informal workers find themselves excluded from the formal economy with lower wages, lower productivity, precarious working conditions, and poor protection. Among developing countries, India has the largest number of informal workers, where these made up 84% of the total workforce (2018). India’s high levels of informality has persisted despite economic growth[43]. For inclusive growth this presents a dual challenge of expanding formal sector employment opportunities, but also of extending support to informal enterprises and workers such as access to capital, insurance, social protection, and representation[44]. In the informal sector women are vulnerable to exploitation and abuse due to gendered power dynamics, without the protection of labour laws or social protection. They routinely work for lower wages and in unsafe conditions, including risk of sexual harassment[45].
[42] Bonnet, Florence, Vanek, Joann, and Chen, Martha. 2019. Women and Men in the Informal Economy: A Statistical Brief. WIEGO, ILO. (Link)
[43] Rajesh Raj Natarajan (Sikkim University), Simone Schotte (UNUWIDER) and Kunal Sen (UNU-WIDER and U of Manchester, “Moving up or down the job ladder in India”
[44] Ibid.
[45] OECD Development Centre Studies/ ILO. 2019. Tackling Vulnerability in the Informal Economy, Development Centre Studies. OECD Publishing, Paris. (Link)

Inequality holds back opportunities for all. A range of characteristics limit people’s economic opportunity and contribution, including gender, age, disability, race and ethnicity, migration and refugee status among others. Poverty and inequality are often multifaceted and context specific with different forms of exclusion taking on significance in different countries.

Box 1: Intersectionality of poverty and exclusion in South Africa
The face of poverty and inequality in South Africa is:
Female: 41.7% of females are poor compared to 38.2% of males; 49.9% of female headed households were living below the poverty line compared to 33% of male headed households. Women still earn only 70% of what men do.
Young: 51% of children (17 years and younger) and 43.6% of youths (aged 18-24 years) were poor compared to 31% of both the 35-44 and 65+ groups,
Black: 47% of the Black African population is poor compared to 23%, 1% and 0.5% of the coloured, Indian and Asian and White population respectively. Unemployment amongst black Africans was 31% compared to 24% among coloured, 12% Asians, and 7% among the white population.
Rural: Rural poverty levels are almost double those of urban areas and historically racially segregated provinces are poorer than white or mixed ones.
(STATS SA 2016)

Young people face added difficulty finding employment in already oversubscribed workplaces. More young people are entering the workforce than the number of new jobs being created. Globally, nearly 68m young women & men are looking for a job, and more than 123m young people are in working poverty[46]. Informality is the rule for young people in sub-Saharan Africa.
[46] ILO statistics taken 25th April 2025, Decent Jobs for Youth Link

Poverty and exclusion determine people’s ability to earn a good enough income to also acquire assets and save for later life. With inadequate coverage of social protection systems (employment based or publicly funded) many workers fail to build up adequate savings and assets for economic security, leading to poverty and exclusion in old age. This is particularly the case for women who often take breaks from work (reducing income and pension contributions or savings) in order to have and bring up children or look after other vulnerable family members[47].
[47] WB SP strategy/ILO World Social protection report

More than 1.3bn people – 16% of the world’s population – have a disability, including 20% of women[48] . Globally, seven of every ten people with disabilities are not in the labour market, compared with four in ten of people without disabilities[49]. Half of the 65million children with disabilities are not in school[50].
[48] World Health Organization. 2022. Global report on health equity for persons with disabilities. Page 5 (Link)
[49] ILOSTAT. 2022. New ILO database highlights labour market challenges of persons with disabilities. (Link)
[50] World Bank Blogs. 2018. The Missing Piece: Disability-Inclusive Education. (Link)

43% of the world’s 184 million migrants and refugees (2023), live in low- and middle-income countries. Legal frameworks and policies surrounding the right to work and access to services for migrants and refugees as well as gender, age, ethnicity, skills level and type of migration (seasonal, temporary, permanent) all determine the economic and social outcomes for migrants and their families, their countries of origin and destination. Migrants and refugees can be the victims of exploitation and abuse and are in need of protection, but when managed well, migration can also have positive outcomes. Most countries at all income levels are both countries of origin and destination. To best match migration numbers, skills and movements countries need to integrate migration into their development and growth strategies[51].
[51] World Bank. 2023. World Development Report 2023: Migrants, Refugees, and Societies (Link)

Growth is private sector led, but rules of the game are set by government, and business practices are enhanced by civil society and shareholder accountability. Markets must be shaped, not merely served. It is therefore important to partner and work at all three levels to support transformational green and inclusive growth. Government is at its best when working in partnership with business, trade unions, civil society, faith groups and communities. The legislative and enabling environment, social norms and the state of civic space set the tone for economic inclusion vs exploitation, worker rights and representation, and appetite of the government and the private sector for enabling disadvantaged groups to participate in the economy. It is essential to supporting dignity and respect at work.

Green growth

Green growth is an essential component of sustainable development because it targets a range of measures of progress, encompassing the quality and composition of growth, and how this impacts people’s wealth and welfare. Green growth considers the full value of natural capital as a factor of production and its role in growth, and can be achieved through mutually reinforcing aspects of economic and environmental policy. Success depends on realising cost-effective ways to decrease environmental pressures and transition to new patterns of growth that avoid crossing critical local, regional, and global environmental thresholds. Sustainable economic growth must seek to avoid and mitigate damage to nature and the climate.

The poorest countries are the lowest emitters, and much, though not all, growth associated with ending extreme poverty would have a minimal impact on emissions, though may have negative externalities for the environment. World Bank analysis[52] showed the global emissions associated with alleviating extreme poverty are small (2.37 gigatonnes of equivalent CO2 in 2050), this implies global emissions having to reduce by 2.08 gigatonnes of equivalent CO2 per year, instead of 2.0 gigatonnes: not a significant difference for the transformation required globally.
[52] Wollburg, Hallegatte and Mahler. 2003. The Climate Implications of Ending Extreme Poverty. World Bank Policy Research Working Paper. (Link)

The focus in the poorest, low emitting countries should be on supporting an increase in productivity, to structurally transform and grow; in ways that increase their climate resilience and ability to adapt, whilst encouraging them to adopt low carbon development pathways where that will support their growth plans. The clean energy transition can represent opportunities to generate growth and developing countries should be supported to take these up. Countries should be supported to go further where it represents cost effective mitigation. We should also recognise that where they do not, the emissions increases required to alleviate extreme poverty will be marginal in the global context. Support will need to recognise that conventional growth pathways cannot be assumed as the efficient route for developing countries, and many countries need support to achieve economic growth in ways that protect and restore natural assets, and access renewable energy.

In Middle Income Countries where emissions are more significant, the necessary approach is different and requires both inclusive economic growth, and an immediate focus on transition to lower-carbon growth pathways, although the possible pace of carbon transition will depend on the context. In many cases reducing the emissions intensity of growth will also deliver significant benefits to other priority objectives, such as health.

Innovation and productivity growth is needed to avoid locking countries into high-carbon, polluting pathways, protect the environment and support greater climate resilience to climate change. The solutions (including nature-based) and innovations are not just technological, but also organisational, social, and political – including needing policies and systems to be able to deliver effectively and be informed by evidence on what does and does not work[53].
[53] Road to the SDGs: Review of Evidence and Implications for Policy. FCDO Draft Discussion Paper

Huge scaling up of private investment in clean energy and technologies is needed to accelerate the energy transition and for developing countries to pursue lower carbon growth pathways. Countries will need support to access this investment, which is required to decouple economic output from CO2 emissions. Transitions to low carbon economies create opportunities for innovation and productivity growth: both fundamental drivers of economic growth. However, both government and market failures act as a barrier to innovation and must be understood and addressed[54]. International work on this could complement and feed into the government’s planned “Clean Power Alliance”.
[54] Burgess, Robin, Caria, Stefano, Dobermann, Tim, and Saggese, Allegra. 2023. Innovation, Growth and the Environment. IGC White Paper on Sustainable Growth. (Link)

Green growth strategies can encourage greener behaviour by firms and consumers, facilitate smooth and just reallocation of jobs, direct capital towards greener activities and provide incentives and support to green innovation. Misguided policies, market constraints and distortions all lead to or arise from market failures which cause a gap between private returns from economic activity and the benefits to society. Green growth policies aim to close that gap and raise returns to “green” investment and innovation. They also aim to minimise distributional consequences of change for the least advantaged groups and manage any negative economic impacts on firms while retaining incentives for improved economic performance.

Green growth initiatives are not gender-neutral and can have different impacts on men and women. There’s a tangible risk that the climate transition will increase gendered and intersectional inequalities and that the poorest women lose out most. Gendered occupational segregation is a key issue – male dominated sectors will see the biggest increase in jobs in the green transition and women are less likely to have[55] the skills for new jobs that will be available. Women need green skills, as well as support to find, move into, and stay in, quality green jobs.
[55] Livingstone, D. and Hearle, C. 2024. Building Women’s Economic Empowerment into Climate Transitions: Pre-reading Pack for Wilton Park Conference 3302, WOW Helpdesk Query No. 88. London, UK: WOW Helpdesk

Addressing the key constraints to Green and Inclusive Growth

Innovation and rising productivity, that does not generate high levels of inequality, holds the key to sustainable, inclusive economic growth. Developing country productivity growth that is low carbon, climate resilient, protects nature and inclusive, is being held back by a range of factors that are complex, affected by social, political and cultural factors – making them context specific and impossible to solve with technical solutions alone. The box below sets out a list of the key barriers to green and inclusive growth. The evidence for these as key constraints can be found in Annex A of this Business Case.

It is worth noting that barriers that relate to developing green cities and strengthening infrastructure, overcoming trade policy constraints, strengthening financial services and improving public finance have not been included here as they are the focus of FCDO’s four other Economic Development Centres of Expertise and fall outside the remit of this programme. Activity related directly to supporting central institutions to tackle corruption and illicit finance, to enhance skills through the education system, improve provision of social protection, or address and to societal barriers to equality for women such as social norms and family relations are also addressed elsewhere in FCDO and are therefore excluded. Nonetheless, in assessing interventions we will assess whether factors under the other COEs are binding constraints to achieving GIG objectives and, if so, liaise with the relevant COEs so that they can align their own work to support addressing those constraints. Moreover, on issues related to corruption, while GIG will not directly support anti-corruption activities, we take seriously the importance of political economy analysis to underpin all delivery decisions and a political economy assessment will be included as part of the appraisal of each intervention to consider the likelihood of the proposed engagement achieving the desired outcomes (see Table 13 for more details). This will also be complemented by a Climate Risk Assessment for each.

Activities related to land and agriculture are addressed in other programmes that fall within the Green and Inclusive Growth Centre of Expertise – which this business case will also form a part of but are not within the scope of this particular business case and so have been excluded. It is worth noting that GIG analysis, to diagnose the problem and design an appropriate intervention, will consider whether factors under the other COEs or programmes are binding constraints, and to what degree. In such cases GIG will liaise with the relevant teams to discuss whether coordinated action is possible, and GIG will consider this context when determining which interventions are VfM to support.

Box 2. Key constraints to green and inclusive growth

Barriers to private sector productivity tackled by this Centre of Expertise

Public sector factors:
- Government policies and systems do not best support green and inclusive growth (i.e. labour policy, industrial policies, support to women and disadvantaged groups)
- Legislation and regulations do not best enable green and inclusive growth (i.e. “red tape” surrounding the private sector, weak legislation around responsible business or inclusion)
- Capability to design policies that support green and inclusive growth (lack of data and knowledge on green and inclusive growth)
- Weak implementation capacity for policies and regulations that support green and inclusive growth (including problems with the independence of regulatory bodies).
- Public sector elites shape policies and processes and/or allocate resources according to their own priorities for private gain (elite capture).

Private sector factors:
- Small market size results in lack of competition
- Limited capacity for efficient business practices harms competitiveness (e.g. financial and strategic capability, technical know-how such as on effective industrial processes)
- Limited knowledge inhibits productive links across firms, investors and supply chains.
- Insufficient capacity to access and adopt technologies to upgrade production.
- Limited firm incentives to invest in training programmes for their workforce
- Education systems do not equip young people with the right skills
- Weaknesses in private sector productivity mean there are too few bankable deals.
- Weak private sector capacity to develop business plans and provide the necessary documentation to attract investment as well as on financial literacy.
- Information asymmetries lead foreign investors to be overly risk averse
- Lack of suitably structured growth finance for small ticket size deals
- Lack of private sector investment acts as a significant constraint to growth

The private sector does not sufficiently embed responsible business practices including related to inclusion or sustainability

- Insufficient private sector incentives for adopting inclusive, responsible, and sustainable business practices, and lack of universally agreed measurement systems and standards to assess the benefits of RBC.
- Lack of coherence across multinational corporations’ own Environmental, Social, & Governance objectives e.g. carbon reduction plans being gender blind.
- Prevalence of loopholes that enable greenwashing by industries as a way of increasing profit without taking deep enough action.
- Lack of, or fractious consultation with local communities, civil society and worker representation leads to poorly designed operations or services, or civil unrest or strike action, lowering productivity.

Women and marginalised groups are limited in their ability to access private sector opportunities including jobs and finance

- Harmful social norms and stereotypes lead to a misallocation of resources and jobs.
- Inability to acquire the relevant skills and know about opportunities.
- Limited access to finance
- Women’s disproportionate responsibilities for unpaid domestic care work
- Discriminatory laws and regulations

What support is needed?

Many developing country partners are clear that Jobs and Growth are a top priority for them. In this context, there is a clear need to help accelerate green and inclusive growth in developing countries by focusing on attracting high quality investment into growth sectors through working with investors and the private sector, while also supporting Partner Governments to increase their capacity and capabilities to improve the investment climate, to test what works when seeking green and inclusive growth and to tackle the binding constraints to women’s economic empowerment. At the same time, there is a need to work directly with investors and firms across the value chain to support availability of information, productivity, and encourage adoption of responsible business practises. The issues that GIG will deal with therefore require both action from the public sector and private sector to deliver impact. There is strong evidence on the effectiveness of technical assistance interventions to shape behaviours of governments and to facilitate investment into businesses.[56]
[56] Economic Development Best Buys. FCDO Internal Paper.

There is also a need to include some support to individuals in terms of information provision to support jobs matching efforts, or to better coordinate training efforts with employer needs. To economically empower marginalised groups successfully, there is also a need to build partnerships between government, business and civil society and actively engage representatives of women, youth, racially and ethnically disadvantaged groups, people with disabilities and other economically excluded groups in the design, delivery and monitoring and evaluation of the programme and its initiatives. Ultimately this programme is seeking to reduce poverty and strengthen climate resilience through supporting growth. The scale of increase in private sector activity and productivity needed to generate meet the SDGs and climate transition is large and outstrips the current provision of support. Support is needed not only at national levels but at regional, district and provincial levels and across a range of firm sizes (multinationals to MSMEs) and country typologies (lower-middle income countries to fragile and conflict affected states).

Why is UK support needed?
The case for FCDO intervention and the difference we seek to achieve
The UK believes that sustainable development is fundamental to an open and stable international order[57]. The UK’s vision is to help achieve sustainable and inclusive growth in low- and middle-income countries that reduces poverty and inequality while preserving natural assets for the long-term. The UK’s goal is to help partner countries transform the productivity of their economies at a pace sufficient to meet the needs of their growing populations, mobilise domestic and international investment, provide quality jobs for an expanding workforce, and deliver public services to secure the long-term wellbeing of their citizens – all part of delivering decent work and economic growth (SDG 8). A focus on gender is imperative as we can only help build a fairer, freer, safer, wealthier and greener world, where everyone benefits and no one is left behind, if we put women and girls at the heart of our efforts.
[57] Integrated Review Refresh 2023
Fit with FCDO and HMG objectives
Economic development, climate and nature and women and girls are top priorities for the new Foreign Secretary and Minister for Development, and all are addressed in this programme. GIG will support delivery of UK commitments in the Paris Agreement on climate change and UK commitments to help deliver the SDGs[58] (specifically supporting SDE 5 on gender equality, SDG 8 on decent work and economic growth, SDG 9 on industry, innovation and infrastructure and SDG 13 on climate action). GIG will help deliver on the government's ambition to foreground women and girls in everything we do and contribute significantly to HMG’s International Climate Finance (ICF) commitments.
[58] Goal 8 (good jobs and economic growth), as well as Goals 1 and 10 (cutting poverty and reduced inequality).

The GIG responds directly to ICAI recommendations for FCDO to renew its commitment to the ending extreme poverty and placing vulnerable people at the heart of its work, and to restore transparency and internal and external challenge to management of UKAid[59]. It also helps to reinvigorate our approach to partnering with civil society and should see UK policy advice, technical knowledge, and funding become more sustainable, as the GIG drives a more locally-led approach and will be partnering with those who best understand local needs and realities, to support them to determine their own development.
[59] https://icai.independent.gov.uk/review/uk-aid-under-pressure-synthesis-2019-2023/review/

The UK government is committed to supporting developing countries to respond to the challenges and opportunities of climate change and has ring-fenced a proportion of its ODA budget to deliver on this (a minimum 65% of GIG ODA will be ICF financed). This commitment will impact the sectors of focus that GIG will work on and is further discussed in the appraisal case.

The UK is the largest investor in Sub-Saharan Africa by FDI stock, accounting for 30% (US$94.3bn).[60] In 2022 total UK outward FDI stock was £2.2trn, the fourth largest globally[61]. This puts the UK in a strategic and unique place to drive progress in these areas. Additionally, many manufacturers searching for lower cost production locations will be in the supply chains of large UK buyers such as clothes retailers and supermarkets.
[60] The UK is the largest investor in African countries by investment stock (Source: UNCTAD World Investment Report 2023). Direct investment flows from the UK into the continent were more than £2.4bn in 2022
[61] FDI intelligence - a service from the Financial Times. 2024. Top 10 countries by outward FDI stock in 2022 (Link)

Alongside supporting our partner countries, there are opportunities to identify ways this can also benefit UK businesses for handoff to the Department for Business and Trade as part of green and inclusive economic growth programming. Programmes designed to improve the affordability and availability of new goods and services, improve delivery of essential public services, drive investment into new infrastructure, tackle socio-economic challenges through tech and innovation, or improve the business enabling environment to level the playing field, can lead to an increase in commercial opportunities for UK companies to win business or grow existing investments and in a way that mutually reinforces our primary development benefit objectives.
FCDO’s comparative advantage
FCDO has experience and expertise working in this area. This programme builds upon a legacy of successful FCDO programmes on green and inclusive growth, including the current phase 1 of the Green and Inclusive Growth Centre of Expertise. Building on over a decade of evidence-based learning and progress, this programme will directly leverage the strong results achieved through the following highly successful programmes, and bring our work together into a combined Global Britain offer (see annex G for case studies of impact of GIG phase 1):

    1. International Growth Centre (IGC): The IGC (currently phase 3: 2019-2026) promotes sustainable and inclusive growth in developing countries by providing policy advice based on frontier research. It sees sustainable growth and inclusive growth as the building blocks of prosperity, and the primary route to sustainably reducing extreme poverty. The IGC was established by DFID in 2008 in response to the findings of the World Bank’s Growth Commission. The IGC identifies key issues that affect growth and uses this to shape its research. The outcome of research is fed back to policy makers through policy briefs, synthesis, and advice from experts. This model enables the IGC to achieve high policy impact. Over the last 3 years, 465 projects across IGC’s partner and engagement countries. Were found to have significantly impacted policy discussions and/or decisions. Additionally, the IGC has consistently maintained Annual Review scores of an A or above.

    1. Manufacturing Africa: A £100m, 10-year programme (2017-2027) that has been contributing to economic transformation by increasing Foreign Direct Investment (FDI) in manufacturing, with positive spill-over effects for wider economies. The programme operates in six African countries (Ethiopia, Kenya, Nigeria, Rwanda, Senegal and Tanzania) and has demonstrated success in creating direct and indirect jobs, increasing investment into manufacturing sectors through pre-investment transaction facilitation support to businesses, and delivering UK thought-leadership. For every £1 spent through Manufacturing Africa by the end of year three, £21 of FDI have been raised and this leverage ratio is expected to increase. Manufacturing Africa supported 130 firms to attract investment worth £4bn and succeeded in getting deals closed for over £718m, contributing to 85,000 jobs, of which 26,000 are direct. The technical assistance delivered – ranging from capacity building of investment promotion agencies to sector studies – unlocked policy and regulatory changes, including for example the approval of tax exemptions for the EV sector in Kenya.

    1. Growth Gateway: A £50m, 4-year programme (2021-25) has created a strong trade and investment pipeline for developing countries, with £650m of deals in commercial discussions and £62m of deals closed. The closed deals are expected to generate 7,600 jobs. In addition, Growth Gateway carried out c.6k engagements with UK businesses and c.7k with those from developing countries through platforms including events, digital, and tailored support; and over 50 market access barriers have been identified and are being addressed. There have been 12,000 visitors to Gateway digital pages.

    1. Work and Opportunities for Women (WOW): A £19m, 7-year (2016-202) women’s economic empowerment programme that pioneered work in partnership with global and British business to improve women’s access to economic opportunities in supply chains, enable UK economic development investments to deliver better economic outcomes for women, and support the UK response to recommendations for action from the UN High Level Panel for Women’s Economic Empowerment. Key results achieved include establishing 13 partnerships with major multinational private sector partners over the past 6 years, with 4 live partnerships operating in Kenya, Malawi and Indonesia. Through these activities WOW has reached 68,000 women, and many of the lessons are reflected in the guidance they launched at COP28: ‘From Risks to Rewards: overcoming the impacts of climate change on women in agricultural supply chains.’ The UK could now lead on women’s economic empowerment globally.

Additionally, and recognising that delivery of the programme will not be limited to UK suppliers/partners, UK expertise is well respected globally. This ranges from technical institutions like the British Geological Survey to the UK private sector which can play a significant role in reducing poverty and economic growth. Where UK companies expand their operations, reputationally they are often known for being a force for good. From large multinationals, to SMEs, the UK private sector has a wealth of knowledge that could be expanded to developing economies. However, there are significant barriers preventing UK businesses from investing in developing economies, especially in Africa and Asia. Local legislation, corruption, lack of understanding of local practices and operational restrictions are regularly sighted as reasons that UK companies may not take the risk of expanding to new territories. Non-ODA funding can be used to address some of these issues.

Box 3. Using non-ODA for mutual benefit

Through the Growth Gateway ODA funding was used to deliver technical assistance and analysis to the ASEAN Secretariat on building the regional capacity on financial services. By deploying non-ODA funding alongside this work, we were able to introduce UK banks and fintech companies to specific financial services opportunities across ASEAN, presenting the UK as a trusted commercial partner and building on strong existing relationships with the ASEAN Secretariat. This intervention has supported 30+ UK businesses and elevated the UK’s influence in ASEAN financial services. The potential value to the UK financial services sector is between £1.5bn and £5bn.

FCDO Centres of Expertise: a new delivery model

Traditional FCDO Centrally Managed Programmes (CMPs) suffered from a number of weaknesses in design and delivery which significantly hindered their effectiveness. These were identified in a DFID Operating Model Review in 2019. In summary these included: too many, small programmes which operated in silos, often without the knowledge or oversight of Posts, were centrally designed without input from Posts, insufficiently tailored to the local context; not addressing Posts priorities in country, nor flexible enough to adapt to emerging needs.[62]
[62] DFID Operating Model Review 2019

In an increasingly competitive and contested space, UK development and diplomacy efforts need to be more agile and supported by high quality, flexibly deployed, and demand-led expertise that is tailored to the local context and country business priorities. In response to this identified need, the concept of a Centre of Expertise (COE) was developed from 2019 with 5 new Centres of Expertise on economic development announced in 2023.

1. A Centre of Expertise is a new portfolio instrument designed within the FCDO to deploy the right kind of expertise[63] and other complementary interventions, to the right places, to address the problems our country partners want the UK to help them solve, in line with UK policy objectives and tailored to the local context. COEs are designed as complements to, rather than substitutes for, Post-managed development programming, with the added value anticipated to include:
  [63] Expertise may be internal to FCDO, external, cross-HMG or academic.
    1. Potential for economies of scale in the large multi-country set up which enables cost-efficiencies in programme management and specialist adviser time in the design, commercial and programme management of this programme. Meaning that it will be more cost effective to deliver than for each individual Post preparing (or amending) its own business case and contract.
    2. Agility to flex between and combine instruments and easily scale up or down, whilst maintaining coherence and strategic focus;
    3. Scale of the programme gives it a broader diversity of experience from which to draw lessons, and an ability to dedicate specific resource to learning and knowledge capabilities and improved use of evidence across the programme, including the International Growth Centre and broader Research and Evidence Division programmes.

In addition, this model aims to support increased local leaderships and ownership of programming by devolving resource and decision making to country while still achieving economies of scale. Effective ways to deliver this will be reviewed through procurement and GIG seeks to involve local businesses or content in delivery.

The FCDO’s Centre for Development sets out the vision for COEs, noting they, “will enable the FCDO Country Network to mobilise the right mix of world-class expertise (brought together by the UK Government) and related development programming to support FCDO’s partner governments and local stakeholders. The vision is that Centres of Expertise become posts’ first choice for channelling technical expertise, policy advice and other grant-based development programming in specific themes from the FCDO centre to the HMG country and regional network, their partner governments and local stakeholders.”

Centres of Expertise have three core functions:

- A portfolio instrument of capabilities and instruments (Technical expertise and other instruments such as Challenge Funds, systems interventions, coalitions of change approaches among others) that can support all developing country contexts to deliver bespoke, “fit for context” solutions to complex development problems.
- A mechanism to source, manage and deploy technical expertise and other resources from multiple sources, including external contracts, around a technical theme including through direct FCDO delivery and that of other HMG departments or UK bodies.
- A hub of knowledge, learning and practice managed by FCDO that convenes multiple public and private sources.
Work is ongoing to define common principles for FCDO’s COEs, led by the FCDO’s Centre for Delivery in consultation with Centre of Expertise leads across the FCDO. The Centre for Delivery has most recently proposed that COE’s should all operate according to three principles:

- COEs should be problem-driven rather than supply-driven, with interventions designed to fit into and be responsive to local country needs.
- Decisions on what COEs do and don’t support will be driven by the latest practice and academic evidence, within a hub of operational and technical knowledge. Evidence will evolve over time in the light of knowledge cultivated in the COE.
- COEs should be an interoperable portfolio, meaning that instruments within a COE should be easily combined to deliver “fit for context” solutions as a single, joined up offer of expertise (internal and external) and other interventions to country partners and Posts.

COEs are envisaged to help update FCDO’s operating model, so that the UK can be more agile and impactful in an increasingly complex, competitive and contested world, enabling the FCDO Country Network to mobilise the right mix of world-class expertise (brought together by the UK Government) and related development programming to support FCDO’s ODA eligible partner governments and local stakeholders. They help to:

      1. Improve the simplicity and efficiency at the FCDO Centre: addressing a history of complex and myriad central initiatives often difficult for posts to navigate.
      2. Empower posts and be locally led: addressing a history of central and regional initiatives operating at post without the say and ownership of FCDO’s local offices.
      3. Proactively manage scarce expertise: ensuring expertise is more strategically deployed by posts and increasing access to it.
      4. Strengthen the join up between central policy teams and geographic delivery: historically silo-ed and often disjointed from one another.
      5. Strengthen learning between centre/post and policy/research collaboration: we have not had systems to automatically synthesise operational learning from posts and disseminate it for the next iteration of interventions across posts. We have also had silos between research evidence and operational evidence and policy.
      6. Streamline design and procurement processes: history of repeated lengthy design, approval and procurement processes running in parallel in programmes under the same theme, that can take 18 months or more to complete.

Consistent with commitments on locally-led development, COEs will include local suppliers and expertise as a core part of the COE offer – potentially twinned/partnered with UK/international expertise.

The COE’s also need to play a role in shaping global institutions and generating global knowledge. As the central location for expertise in a given policy area, COEs will need to be able to engage on a global platform and have influence and reach beyond our own UK programmes and internal conversations.

The Economic Development Centres of Expertise

The Green and Inclusive Growth COE (GIG COE) is one of five Economic Development Centres of Expertise (COEs) being established at the Foreign, Commonwealth and Development Office (FCDO).

Figure 1. FCDO Economic Development Centres of Expertise

The boundaries of the 5 COEs were chosen because they cover FCDO expertise and where different parts (Divisions and Departments) of the FCDO focus and can add most value on supporting economic growth. The GIG COE is the only one that is focused on supporting the development of product markets in the real economy. The GIG COE includes an element of research funding, through the International Growth Centre. This is the only programme from the growth research portfolio which is co-funded by EDPD and included in the COE, which is because of IGC’s unique business model. The IGC approach is to translate its research findings, themselves based on long-term relationships built through its Country Office network, into high impact policy advice and support policy makers to be able to integrate evidence into effective policy on this basis. The independence of the IGC and its direct relationships with partner governments provide a powerful mechanism for policy reform and change.

Feedback from Posts

Demand for the GIG is well established. The Economic Development and Partnerships Directorate voucher scheme in 23/24 attracted requests from 20 out of 23 of FCDO’s priority countries for investment partnerships seeking GIG related technical assistance, totalling £6.5m for programmes under the current phase of GIG. Beyond the voucher scheme, Posts have ‘bought in’ to GIG 1 providing an additional £7.9m in FY 23/24. For FY 24/25 Manufacturing Africa has confirmed £6m post buy in and initial interest suggests that Growth Gateway will receive over £5.6m. Approximately £2.3m in non-ODA technical assistance has also been delivered for Posts by the GIG phase 1 (with an additional non-ODA amount of £530k received through “post buy-in”).

Demand for GIG was further explored during a series of consultations with Post that took place in February- April 2024. This consultation was held with 12 FCDO Posts to gain more detailed feedback on design and governance features of the next phase of GIG. Posts consulted were Nigeria, South Africa, Cambodia, Philippines, Pakistan, India, FCDO Caribbean (based in Barbados), Ukraine, Kenya, Somalia and Jordan. Further consultation is ongoing with other Posts across the FCDO network (e.g. with MENA Development Directors). We have established an active working group of colleagues at Post who will continue to collaborate on design of this programme. This consultation exercise focussed on the nature of demands Posts would likely make on the GIG, their priorities as per country business plans, future staffing at Post (having colleagues at Post with sufficient capacity and capability to engage with the GIG in the future is essential) and views on various governance and commercial options for the GIG.

Colleagues identified the following factors as priorities in the delivery of the GIG:

- Speed of response – windows of opportunity can open rapidly and current delivery models struggle to respond in a timely way.
  - Flexibility – likewise, learning lessons from delivery to date, interventions should be able to pause or unwind sooner if conditions in country change.
  - Country expertise – GIG needs to bring in international expertise which is much in demand, but also be able to bring in local advisors and experts to deliver work in support of developing countries’ own advisory markets (‘local content’) and to ensure further understanding of country contexts.
  - Country context and co-design – interventions must be fully tailored to country context; therefore, Posts will need to dedicate enough resource to engage and lead conversations with country government partners to understand their priorities, whilst procurement, management, in country delivery and additional supporting technical expertise (including in-sourced implementation roles) is provided through GIG.

Learning from Post feedback, GIG will address existing gaps in central programming and respond to locally owned priorities and evolving contexts. The COE approach complements Post programmes by providing a greater depth of expertise and access to greater evidence and learning. The COE activities will be co-designed with Posts in a way that makes the portfolio more visible, simpler and more efficient for Posts to navigate. In addition to central funding, it will be possible for Posts to “buy into” GIG with their own budget and will add value to Posts’ own programmes due to its breadth and scale, meaning it has the potential for commercial and programme efficiencies as well as an ability to combine activities to address evolving problems and to provide rapid support or flex, scale up and down as required.

Posts will be able to engage support across the 5 economic development COEs through a single point of contact accessed through the central Centre of Expertise Secretariat (based in Economic Development and Partnerships Directorate). The Secretariat which oversees all EcDev COEs will act as a single contact point for Posts who will triage interest to the appropriate COE. The governance is designed to be easy to navigate for Posts, however this will be actively tested and refined during inception. Posts and regional teams can choose to rely solely on this central offer, combine it with their own locally led initiatives or focus primarily on local delivery (with COEs playing a minor or negligible role).

Compliance and assurances

Development Act

All Overseas Development Assistance (ODA) spending will meet the requirements as outlined in the UK International Development Act 2002.The programme will also include non-ODA. The GIG functions might lead to a blended ODA/ non-ODA financial model depending on the types of activities needed. The ODA element will continue to abide by the terms of ODA spending under the International Development Act 2002 and the UK will remain committed to keeping aid untied in line with OECD guidelines on procurement.

Counter terrorism

The risk of funds being misappropriated for terrorist purposes is assessed to be low in general but will be monitored closely. The programme will practice robust due diligence, monitoring, and auditing of suppliers to ensure compliance with the Terrorism Acts 2000 & 2006. To ensure compliance with the UK Terrorism Act 2000, we will utilise Thomson Reuters WorldCheck to run checks against individuals and entities with whom we contract.

Gender and inclusion

In line with the UK Gender Equality Act (GEA), GIG will consider the impact of all its intervention on gender equality and will explore opportunities to promote women’s economic opportunities. Criteria will be developed to guide engagement with the private sector and will be aligned with existing frameworks such as the IFC Performance Standards which we support. These criteria will have the dual aims of a) increasing investment and b) supporting and encouraging responsible investments that can provide opportunities for women and driving gender equality as well as benefit local communities.

In terms of the mandatory Gender Equality Marker (GEM), we expect to mark the programme as “S” (Significant) as a portfolio, recognising that there will be varying levels of ambition between different initiatives supported by GIG from doing no harm, to empowering women, to transforming gender dynamics and biases. The programme will do this by focusing on sectors identified by FCDO as priority transformation entry points for gender and inclusion on economic policy and programming. Within these, we will actively examine the impact of specific interventions on different genders (female and male) and identify, monitor and evaluate measures to reduce gender inequality in project design and implementation. Data on participation will be collected and used. We will also: plan that women are well-represented in the governance arrangements for the programme and use the procurement process to seek out technical assistance (TA) providers with strong gender expertise within the team.

In line with the Public Sector Equality Duty (PSED) and the requirements of the UK Equality Act 2010, programme design will give due regard to impact on people with protected characteristics. In our assessment, no intervention will have substantial negative consequences for people with a particular protected characteristic, or is likely to attract controversy, scrutiny or challenge. Therefore, the interventions have been designed in a way that does not result in any negative consequences directly or indirectly for people with protected characteristics.

Climate and environment

This programme will align with the UK’s Nature-proofing and Environmental Protection and Paris Alignment considerations. It will also seek to contribute substantially to International Climate Finance (ICF).

Nature proofing and environmental protection. An Environmental and Climate Risk Screening has been conducted and assessed that this business case is moderate risk for climate and low for environmental factors (see Annex B). The programme is not expected to operate in or near critical habitats but an assessment of this will be made as relevant when requests for support are received. This programme will consider opportunities to enhance the environment (including where appropriate by supporting nature-based solutions) for example when working with firms on business strategies.

We do not foresee any significant direct Climate or Environmental risks as the programme will work to ensure that climate and environmental risks (e.g. waste efficiency, pollution, land degradation, biodiversity, and water resources) are addressed as part of any intervention. Our climate and environment risk assessment has identified the following indirect key risks:

1. GIG interventions could be subject to climate impacts and exacerbate climate change if climate risk is not properly considered. This will be mitigated by robustly assessing climate risk in each intervention and will form a core part of assessment criteria.
2. GIG interventions could result in environmental harm by supporting or promoting investment in projects or businesses that have an adverse effect on nature and biodiversity. This will be mitigated by promoting Environmental, Social and Governance standards with investors/businesses and conducting robust due diligence for any direct support to businesses/investors.

1. Alignment with the Paris Agreement.
      1. Shadow Carbon Pricing should ordinarily be carried out on a programme of this scale working in the sectors foreseen. As this business case is for a portfolio of predominantly technical assistance, and where the specific sub-sectors and geographies are not yet known, we judge that a quantitative shadow carbon pricing exercise at this stage would be spurious. We intend instead to carry out shadow carbon pricing during the inception phase, and in the selection of major/”deep” interventions when the specific activities and locations are known, and when any decisions to be taken as a consequence of the calculations will more realistically impact the emissions generation of the programme activities.
      2. Fossil Fuel Policy. Consistent with the HMG policy on fossil fuels, this programme will not provide any direct financial or promotional support for the fossil fuel energy sector.
      3. Nationally Determined Contributions (NDC) and National Adaptation Plans (NAP). Programme interventions will be designed to ensure that they do not undermine the ambition in countries’ NDCs or NAPs and, where relevant, will be designed to help strengthen and increase the ambition of NDCs to support greater consistency with the Paris Agreement temperature goals.

The programme has the potential to contribute to several ICF indicators:
KPI 1: Number of people supported to better adapt to the effects of climate change;
KPI 4: Number of people with improved (climate) resilience;
KPI 6: Greenhouse gas emissions reduced or avoided (Tco2);
KPI 7: Clean energy capacity installed (MW);
KPI 11: Public climate finance mobilised (GBP);
KPI 12: Private climate finance mobilised (GBP);
KPI 15: Extent to which ICF intervention is likely to have transformational impact (scorecard);
KPI 17: Hectares of land that have received sustainable land management practices.

Throughout the life of the programme, the team will review interventions and implementing partner activities on a regular basis to determine if activities meet the criteria to qualify as ICF. This Programme will not invest directly in fossil fuels nor run counter to recipient country Nationally Determined Contributions commitments. Innovation elements are expected to count towards the UK’s Ayrton Fund commitment to invest up to £1bn of ICF in clean energy innovation in developing countries.

Safeguarding

In line with the FCDO policy on safeguarding, we will ensure that all partners and contractors are aware of our policies and procedures, and especially because some of our interventions will work with vulnerable groups or with high-profile at-risk groups. Any suppliers will be required to sign up to the FCDO terms and conditions which included specific clauses on safeguarding against sexual exploitation, abuse, and harassment.

Risk appetite/escalation

FCDO’s risk appetite is receptive for Policy and Programme Delivery risk. This reflects our acceptance of the risk in order to drive long-term change in diverse and challenging contexts, building strategic partnerships to promote shared global prosperity, eradicate poverty, tackle climate change, strengthen the international rule of law and global security, and promote free, open societies. We do this in the national interest, including to protect British citizens.

## B. Appraisal Case

The Appraisal Case reviews strategic and delivery options to meet the need and rationale as set out in the Strategic case. It outlines the key elements of the preferred option, and the evidence and rationale for why they represent best Value for Money (VfM). Key metrics to incentivise VfM are provided. The logic of the programme is set out in a Theory of Change.
What are the strategic options that address the need set out in the Strategic Case?

What is done elsewhere in FCDO and is outside of GIG BC scope?

The GIG COE is one of FCDO’s five Economic Development Centres of Expertise. This business case is designed to deliver as the key element of the second phase of the UK Green and Inclusive Growth Centre of Expertise. Interventions to support Green Cities and Infrastructure, increased Trade, strengthening Financial Services and improving Public Finance are addressed by the 4 other Economic Development COEs so are outside the scope of this case. As mentioned, activity related to corruption and good governance, education, provision of social protection and to societal barriers to gender equality such as social norms and family relations, are also addressed elsewhere in FCDO and are therefore excluded. This does not mean that GIG activities will not be grounded in thorough political economy analysis. We fully recognise the importance of such analysis in informing assessments of feasibility, sustainability and impact of potential interventions.

GIG and the wider GIG COE will need to coordinate across the FCDO portfolio. There are some programmes in particular that GIG will seek to draw heavily on e.g. wider research that relates to green and inclusive growth that is done elsewhere in FCDO like the AGIL helpdesk or Growth research platform. This coordination and dissemination of research will be a central function of the GIG “Hub”.

What is part of the GIG COE but outside of the GIG BC scope?

Commercial agriculture and issues relating to land are key to transformational growth. Agriculture and Land programming (CASA and Land Facility) will continue to be delivered in separate business cases designed in HMFSD. These will sit alongside this GIG business case as part of the broader GIG Centre of Expertise but are separate to this business case. This reflects the need for agriculture and land to be strongly aligned to FCDO food security policy and programming while maintain a strong link to the economic growth agenda.

Figure 2. Green and Inclusive Growth (GIG) Centre of Expertise

CASA
Land Facility
Centre for Green and Inclusive Growth (GIG)
AGIL helpdesk
Growth Research Platform Responsive Facility
GIG CoE

The thought leadership for the wider GIG COE will be driven by GIG. The three business cases and the partners that deliver them need to work interoperably e.g. sharing/adapting to evidence and information.

Below we set out the proposed scope for the GIG. This is designed to complement wider FCDO programming, including the wider economic development Centres of Expertise listed above.

As stated in the Strategic Case, all Centres of Expertise are expected to adhere to the following three principles in their design and delivery:

- Be problem driven and responsive;
- Be evidence driven, within hubs of knowledge;
- Be an “interoperable” portfolio.

GIG scope

The objective of the Green and Inclusive Growth programme is to work in partnership with governments, the private sector and civil society, as well as partnering with other key global, regional and local organisations, to contribute to global inclusive and sustainable poverty reduction including through building climate resilience, protecting nature and supporting climate transition. The programme will aim to achieve that objective by contributing towards transformational, inclusive and green growth.

What are the cross-cutting themes?

GIG will seek to support generating quality jobs, economic inclusion and especially women’s economic empowerment, responsible business, and actions to drive green transitions as objectives across its work. These are all important elements, but we recognise the VfM risks of attempting to deliver against multiple objectives at the same time. GIG will therefore take a portfolio approach to delivering impact. The contribution of each intervention to GIG objectives will be determined using a Development Impact Scorecard approach, learning from the use of this approach across other EDPD programming and work (including Growth Gateway and BII). These have proven effective to appraise and pursue several development objectives coherently across a portfolio. Dedicated interventions under each specific area will further drive change under these cross-cutting themes, focusing where GIG can add most value. These themes reflect a range of EDPD policy priorities and FCDO’s track record in this space as set out in the strategic case.

Jobs: As set out in the SC not all growth is created equal and evidence from EED finds that growth is most strongly associated with poverty reduction when it is growth that raises median incomes. In developing countries with booming populations that will necessarily require widespread more productive employment. Furthermore, an increasing proportion of developing countries are fragile and conflict affected. While the relationship between employment and violence is not straightforward, the 2018 International Peace Perception Poll finds that “lack of jobs and economic opportunity are key drivers of recruitment for gangs and extremist groups in fragile environments.[64] Grievances around respect and social justice are drivers of violence and access to employment is a key aspect of this (though not the only one)[65]. Considering the distribution and role of employment will therefore have a particular focus when working in fragile settings.
[64] International Alert. 2019. ‘Peace Perceptions Poll 2018’. (Link)
[65] World Bank. 2011. The World Bank Development report: conflict, security, and development (English) . (Link)

Economic Inclusion: GIG will require all new partnerships and interventions to consider how to maximise their economic inclusion impact. By adding a gender and inclusion lens to advice/support to partnerships with businesses GIG will encourage them to recognise the additional constraints faced by excluded groups in their employment and supply chains, and identify levers to support them to:

- Help economically excluded groups navigate lower access to assets, finance, formal and informal networks;
- Make workplaces more accessible and safe for all;
- Improve employment terms to add flexibilities and rights for vulnerable and excluded groups; and
- Deliver employer led skills upgrading where labour supply of excluded groups is constrained
- Consider alignment with the 2X criteria and Women’s Empowerment Principles.

Women’s economic empowerment: “A critical outcome in itself, with the potential to enhance economic growth and wider development outcomes for women, their families and societies”.[66] GIG, with dedicated interventions on WEE, will constitute our flagship programme for FCDO’s new global campaign to accelerate WEE, drawing on learning from our successful Work and Opportunities for Women (WOW) programme. For example, WOW analysis has identified that despite growing research on supply chain decarbonisation, organisations very rarely explore the impact of decarbonisation on the workers in their supply chain(s). In the case of agriculture or the garment industry, many of these are women. Empowering women to take leading roles in supply chain decarbonisation will allow women to succeed economically, while safeguarding them from climate-related disasters which they experience the greatest impact from.[67] Further detail on GIG and WEE is included in Annex J.
[66] ODI. 2022. Women’s economic empowerment: supporting transformative change (Link).
[67] UN Women. 2016. “Why are women and girls more likely than men to die in a disaster?”. (Link)

Responsible business: GIG will support Responsible Business Conduct (RBC) drawing lessons from our history of successful programming including the Responsible Accountable and Transparent Enterprise (RATE) programme; the Business Partnerships for the Global Goals (BP4GG) programme; and the Releasing the Transformational Potential of Extractives for Economic Development (RTPEED) programme. GIG will encourage business partnerships and interventions to have responsible business conduct safeguards in place and to consider how to maximise their RBC impact and how they can contribute to the delivery of the SDGs.

Green: as discussed in the strategic case, huge scaling up of private investment in clean energy and technologies is needed if developing countries are to pursue lower carbon growth pathways and countries will need support to access this investment, including support to address government and market failures that act as a barrier to innovation. GIG will support investment in the capacity to manufacture inputs into renewable energy generation or final products that entail lower carbon use in consumption, as well as in production processes more generally that reduce carbon use. GIG will support development of domestic green investment plans and strategies; provide business and investment expertise on raising capital, deals and investment opportunities.

What are the sectors of focus?

GIG will focus on manufacturing (including supporting critical minerals supply chains, textiles, pharmaceuticals) and the services that complement them and account for much of the value-add in their supply chain (e.g. either as inputs such as design, logistics and e-commerce platforms; or embedded as complements such as after-sales support). These sectors, alongside agriculture and raw materials (addressed by the agriculture and land elements of the GIG COE), represent the ‘real economy’ and drive productive economic growth. Although frontier tech will not be a specific focus of the GIG, we will seek to harness tech advances and new technologies to deliver on GIG objectives across focus sectors. Annex I sets out the rationale for GIG focus on manufacturing and services.

A bespoke offer: GIG will work on a demand led basis so will focus on sectors where Post see opportunity for intervention to deliver value, in conjunction with country analytics. The GIG will draw on existing country level research to support identification of sub sectors with potential to support green and inclusive growth which are also politically tractable, drawing on expertise available at Post. Sectoral focus will therefore differ depending on the existing level of development/ product complexity, and thus what is viable in each partner country. Having identified opportunities, GIG will deliver a tailored offer that addresses specific constraints to green and inclusive growth. In fragile settings, analysis will assess the role of the economy in conflict and will work with FCDO Conflict Advisers to carefully consider conflict dynamics. In fragile states the diagnostics will always incorporate scenario analysis and in early recovery settings the diagnostics will assess how to best catalyse durable solutions building on the international humanitarian response.

GIG will seek out opportunities in sectors which best support transformation (are viable for the country to produce but also raise complexity and diversification, have supply chain linkages and support exports or import substitution), enhance food security, and contribute to the cross-cutting themes. There can be tensions across these aims e.g. between job-creation and productivity, with higher job-creation in lower-productivity (and therefore lower paid) sub-sectors, and vice-versa. GIG will try to focus on supporting these aims in tandem, assessing potential impacts using a scorecard approach and considering outcomes at portfolio level. Its approach will keep the criticality of job creation, inclusion and sustainability firmly in view (see management case for TA intervention selection criteria). For example, we would expect GIG to support agri-processing given its potential to employ a large number of less skilled workers, its supply chains linkages, that it raises complexity from focusing mostly on raw agricultural produce, and because it supports food security.

For less common opportunities in higher complexity products or services, GIG will support where opportunities arise if diagnostics find them to be high potential to support transformation, and appropriate TA support can be obtained at sufficient VfM. For instance, GIG phase 1 provided support to electronics manufacturing, given it is significantly higher complexity and its ability to boost high value country exports which support economic transformation, even if it creates fewer direct jobs for the poorest.

Manufacturing focus sectors: Based on initial scoping studies and our knowledge of Post demand from GIG Phase 1, the following sectors will be prioritised for GIG support:
- Agri-processing (e.g. food and beverages)
- Building and Construction
- Textiles and apparel
- Automotive parts and light vehicle/machinery assembly.

In line with GIG ambition on ICF, sub-sectors with clear benefits to support green transition, where there is also significant DFI interest, will also be prioritised including;
- Packaging and circular economy (e.g. plastic recycling), light equipment fabrication (e.g. assembling off-grid solar systems)
- Transport production (e.g. electric two-wheel vehicles assembly)
- Agri-processing and green fertilizers (e.g. manufacturing plant-based protein),
- Green construction (e.g. construction materials such as green steel manufactured using less carbon intensive methods)

1. Service focus sectors: Based on initial scoping and consultations, the following sectors will prioritised;
    1. Low skill tradeable and domestic services: e.g. wholesale and retail trade
    2. Higher skill business services (some of these also have positive economy spillovers): e.g. Insurance and business advisory services.
    3. High-linkage services: e.g. the Care economy, ICT, Gig economy platforms, design, logistics, e-commerce, after-sales support, information and communication; administrative services.

These sectors will be further refined during the inception stage based on further Post consultation regarding priorities and opportunities, and on the basis of EME activities indicating the level of specification required to attract the relevant expertise. Although indicative, we will want to ensure delivery partner expertise and track record in these sectors, as well as the ability to bring in in additional expertise in new areas should the need arise and to tailor interventions to specific contexts. We also recognise that the purpose of much TA to business is to attract investment in key sectors; experience from Manufacturing Africa has shown that the majority of business support is sector agnostic e.g. providing a company with analysis and support to close investment deals and providing post-deal support, investor readiness support, commercial diligence analysis, supply chain linkages and operational processes. Equally, TA on testing effective policies for partner governments to support private sector growth in certain sectors relies mostly on skills that are sector agnostic and can be applied quite widely.

GIG will not support:
- The coal industry given UK commitments on tackling climate change, and would be unlikely to support, for instance, petrochemicals on the same basis.
- financial services, telecommunications or transport services despite strong positive spillovers on capital accumulation, being inputs to production of goods, and reducing the cost of exports as these will all be covered by the other 4 EcDev COEs.
- Anything excluded from the Harmonised EDFI Exclusion List[68] which includes, for instance, materials subject to international phase-outs or bans including ozone depleting substances and certain wildlife products, cross-border trade in waste unless compliant with particular regulations, and business activities where alcohol (except beer and wine), tobacco, weapons or gambling and equivalent enterprises form a substantial part.
  [68] Harmonized European Development Finance Institutions Exclusion List (Link)
- Anything that would not qualify as ‘Paris aligned’.

What is the geographical scope?

Support will be available in principle to any ODA eligible country, but GIG will focus on the FCDO’s list of priority countries for investment partnerships. This list has been developed by EDPD and includes development, climate, geopolitical and commercial considerations. Non-ODA will also be available to these geographies to support UK focused opportunities and, in principle, to non-ODA countries if there is a strategic case for support. GIG is responding to the steer of being more demand led and so will determine its exact geographies by assessing requests from Post for GIG’s ability to respond, their fit with strategic priorities, and their likely impact against GIG objectives.

On the basis of poverty reduction, impact assessments may favour lower income countries where poverty rates are greater or middle-income countries with pockets of extreme poverty and inequality, or if their existing commercial dynamism means interventions such as investment facilitation support are likely to have higher effectiveness in terms of number of jobs and laying foundations for wider development impact. On the basis of climate objectives, many lower- and middle-income countries have most need for support on climate resilience and adaptation, while there is greater urgency to support growth to be low-carbon in the countries with the higher growth rates. The GIG will advertise the range of support it can offer (see indicative activities table below) and Posts will submit requests for support.

We expect that at least 50% of our ODA will be spent in LDCs. Our prioritisation criteria will also support work in FCAS.[69] We will assess what proportion has been spent by GIG phase 1 in FCAS to date and set this as a minimum.[70] While GIG work is dependent on demand from post, and an assessment that the right expertise can be sourced to deliver the necessary intervention, GIG will seek to focus on FCAS. Posts in fragile countries were consulted when developing the list of potential activities so we are confident it reflects their needs. Our assessment of suppliers will also include a criterion around experience and ability to deliver successfully in fragile states, or their ability to partner with or sub-contract to bring in this expertise.
[69] World Bank. 2024. FY24 List of Fragile and Conflict-affected Situations. (Link)
[70] Spend in countries that are both FCAS and LDC would count fully toward both targets.

What types of activities will GIG deliver?

The GIG will offer access to specialist technical assistance in the field of Green and Inclusive Growth. Given the high specificity of partner country growth strategies, and that COEs are aiming to be more demand led and designed in conjunction with post, the exact activities for each country are not currently known. However, we have provided a menu of indicative activities that will help Posts and policy leads to determine the best course of action to address binding constraints to growth in their Partner countries. We envisage interventions being designed using a mix of activities from this list to create a bespoke package. A table with indicative activities is set out below.

We have assessed these activities as being highly effective to support green and inclusive growth. Annex D provides further detail on the evidence base for the effectiveness of proposed activities.

Table 1. Indicative GIG ODA activities

Indicative GIG activities
Technical assistance for Governments/state entities	Green and inclusive growth policy reform/strategic frameworks e.g. expertise, advice and targeted research to inform policy making, provided to support Partner Governments on areas that deliver green and inclusive growth such as sectoral policy advice, designing green investment plans and strategies, advice on specific business environment reforms/ labour policies/ factor mobility / and reforms that support women’s economic empowerment or environmental protection. / Support partner government capacity on industrial planning, identifying resource bottlenecks and supporting government capacity to co-ordinate investment. E.g. support the planning and delivery of complex industrial projects like establishing Special Economic Zones, or attracting investment into focus sectors. / Support to develop operational systems and policy implementation mechanisms e.g. design systems, tools, processes and governance to implement policies/reform, for example systems and governance for public private dialogue to inform policy, TA on implementing policies such as National Adaptation plans, TA to help improve the efficiency of government approval processes for business requests.
Technical assistance for business/investors	Business expertise, advice, information and networking, including on responsible business and WEE e.g. providing market information, expert business advisory services, advice in technical areas (e.g. industrial design/process specialists), private sector engagement/networking (e.g. sharing knowledge of responsible business models or speaking to groups of business about market access barriers/business environment challenges they face), awareness raising of commercial opportunities, including focus on UK businesses*. / Working with firms to build research evidence on how best to improve management capabilities, improve technology, and increase access to skilled labour and electricity. / Value chain coordination and responsible (including gender sensitive) supply chains e.g. matching businesses across the VCs (e.g. back to smallholder farmers and artisanal miners as suppliers of inputs), supplier linkage and responsible supply chain support. / Investment advice to investors (e.g. expertise and advice on technical areas, information on deals, exits, awareness of investment opportunities) / Investment advice to businesses (e.g. raising capital, information on investor opportunities, engagement and requirements/standards to get investment e.g. financial analysis/modelling, marketing materials, business planning, ESG/development impact improvements, pre and post investment support, commercial due diligence analysis). / Deal/ transaction facilitation (e.g. match making investors and businesses/funds) including for climate specific investments. / Project pipeline development (e.g. seeking and finding investable companies and supporting them with knowledge and documentation that will increase their chance of locking in investment, investor engagement, DFI engagement). / Inclusion analysis and advice: Support on reducing barriers to entry and progression, and adapting jobs to meet women’s needs, such as through safe transport, toilets/changing facilities, gender-based violence and harassment policies. TA on e.g. WEE, Care, disability and inclusion may prompt businesses and investors to consider innovation or stretching ambition in these areas. / Scalable and replicable pilot projects with firms to tackle gender specific barriers (e.g. on unpaid care, discrimination, and violence in the workplace). / Government, Private and Social partnerships: Support businesses to collaborate with social actors on reforms in legislation, policy or practice required to drive inclusion of economically disadvantaged groups, responsible and inclusive business practices, innovative design and delivery of goods and services to respond to local needs and capacities. This may include support on labour mobility and jobs matching.
Knowledge sharing and influencing	Convening, partnering, knowledge sharing and influencing amongst stakeholders in partner governments, private sector, donors, civil society, workers representatives, women’s rights organisations (WROs), Business networks and FCDO to increase uptake of evidence (e.g. help facilitate champion groups, dialogues (including public-private), sponsor coalitions, workshops, making the business case for reform, mobilising influential leaders, investment fair/summit support service, coordinating between COEs and across HMG programmes, private sector partnerships, communication of ‘UK offer’ to private sector and across HMG, HMG capability offer – including community of practice, experience sharing and knowledge products created and disseminated, CRM system to track who we are working with, supporting policy dialogue and working with multilaterals (e.g. World Bank, ILO, UN Women) to better deliver GIG outcomes.
Learning and evidence	Analysis, research and evidence to improve the evidence base for green and inclusive growth (e.g. growth diagnostics, political economy analysis and engagement, investment opportunity and sectoral analysis, environmental impact assessments, literature reviews, independent research and policy advice, improve data quality and transparency, support on theory of change/results, monitoring and reviewing progress of COE and embedding lessons in future GIG advice, support on briefings/policy notes.

For non-ODA work, interventions will seek to create the enabling environment to generate secondary benefit commercial opportunities that Department for Business and Trade can prepare UK companies to compete for and secure if they are able to provide a best value for money offering.This work therefore has the potential to positively support the UK growth mission in building markets of the future by identifying and supporting UK commercial opportunities in new and emerging markets.

Country focused vs. global: We envisage that the bulk of GIG activities will be country specific interventions. However, to best deliver some of the indicative activities listed above, we judge it will also be important to support some top-down global analysis, deliver global policy influencing initiatives, and support interventions that address regional cross border issues, so the UK can continue to play a role in key global debates, retain its influence and reach, and help shape some of the global institutions that deliver green and inclusive growth, as well as generate global knowledge. This is also important in cross cutting areas such as jobs, WEE and responsible business, as well as in areas of high strategic importance such as critical minerals.
Box 4. World bank Trust Fund on jobs
FCDO have funded the Multi Donor Trust Fund on jobs (MDTFJ) in the past and our experience offers evidence that we can significantly influence the direction of the fund which significantly impacts the World Bank’s approach to Jobs and Economic transformation (JET). The MDTF was initially focused on pilots and knowledge creation without sufficient focus on how activities could have most impact on WB and other donors’ approach to JET. DfID pushed hard for the MDTF to pivot to focus on more Outcome and strategic level questions which it did. The MDTF has now fed into/ led high potential WB work strands including the new WB Jobs Flagship report (which lays out a new and strong vision for how to think about Jobs in relation to different aspects of economic transformation, which we support) which it is pushing as an approach across WB JET programming. The MDTF is also supporting the WB to introduce a new Jobs indicator into the World Bank’s corporate scorecard, including designing its methodology in a way that goes beyond “direct jobs” to consider wider economic impact. A new corporate scorecard indicator has high potential to influence the way WB programmes consider JET. The MDTF is also now considering how it can provide input/ TA at the portfolio level of the WB so that portfolios are better designed for JET objectives. / Importance of UK influence: From recent donor meetings, and the work described above, it seems that the WB MDTF is adopting a stronger focus on Jobs as part of the growth story and that meeting the Jobs challenge requires a focus on growth. This is a direction we want to support the Bank to continue with. Our input here is important as other donors seem more focused on Climate sustainability/net zero (mitigation as well as adaptation) and leave-no-one-behind, above the focus on growth. While we fully support these agendas, we feel much more focus needs to be on the issue of inclusive and sustainable growth, particularly given the lack of per-capita growth in Sub-Saharan Africa and the implications of this for global extreme poverty. Safeguarding this focus on growth in the WB direction is important to meet GIG ambitions.

Some initial proposed global level interventions are outlined in annex F attached to this business case. We have set out assessment criteria for the interventions in the management case.

Deep vs. targeted offer: GIG will deliver activities at a range of scales. This reflects the need to be more flexible to meet Post requirements, take up any opportunities for “quick wins” and potentially to work quickly to capitalise on “moments of opportunity” should these arise. Targeted work may be useful to open doors to longer-term, impactful support either delivered by FCDO or other partners in country. Given that long-term impact needs clear multi-year programming, the demand-led TA will therefore be divided between deep and targeted forms of support under the GIG, in order to better respond to country needs. Requests for support will be prioritised based on an assessment of likely long-term impact and ability to deliver the right expertise (See table 13). Guidance will be made clear to Post on what the GIG looks to support and how requests will be appraised, and the Hub will speak to Post ahead of proposal development to avoid Posts spending time on unsuccessful requests, as far as is possible.

Deep offers: The deep offers are multi-year programmes delivered in a selection of FCDO’s priority countries for investment partnerships. The secretariat will undertake active communications with posts, particularly in priority countries, to both raise awareness of offers and how to access support, and to effectively respond to support requests.

Targeted offers: Targeted offers are shorter projects, typically one-off and lasting 3-9 months. This will be open to all ODA eligible countries, including those not on the list of FCDO’s priority countries for investment partnerships. Where there is a case for impact and the expertise can be mobilised, the GIG will seek for a more agile response to new opportunities at country level (e.g. associated with a change of government or peace settlement). Speed here is important as windows of opportunity can be short, and the GIG will allow FCDO Posts to mobilise support faster than current models of delivery allow.

GIG is conscious that economic development requires long-term support, with a strategic approach. The “impact” of targeted TA will therefore be assessed for how it supports long-term change, as described in table 13. For these requests there must either be clear, notable, impact from the work itself or it must be clear how the TA will be effective in facilitating a wider portfolio of work. It is important for “targeted” requests to address what actions will be needed following the support, in order to have impact. Requests should state who is expected to take these actions forward following the intervention and should demonstrate that there is the relevant buy-in for this.

This deep vs. targeted approach has already been piloted by GIG Phase 1 programmes as part of the EDPD voucher scheme in FY 23/24, The table below sets out examples from GIG phase 1.

Box 5. Examples of GIG deep vs targeted interventions
Targeted intervention – Supporting Growth of E-mobility Sector in Kenya / Most African countries do not have a comprehensive legislative and policy framework to promote electric mobility. The taxation and import tax regimes for vehicle assembly and manufacturing in Kenya did not incentivise investment into the electric mobility industry. Electric vehicles (EVs), charging stations and components attracted the same taxes, duties and levies as ordinary vehicles powered by internal combustion engines (ICE vehicles). MA developed a memo providing guidance on tax incentives for EV companies and EVs to enable a start-up to appeal for a change of the policy regime and get a special exemption for themselves which would benefit the sector. MA also made a comparative analysis of the climate impact of importing, assembling, operating and decommissioning electric buses versus the operation of typical modern diesel bus models. This information formed the basis of the company’s engagements with the Kenyan government. In September 2023, the tax exemptions to the EV sector were enacted by the government of Kenya. With the policy framework in place, the company completed a fundraise of $5 million with BII in December in 2023. / Deep intervention – Cambodia Green (2 phases): £750k ODA (£350k ICF), £60k non-ODA / Growth Gateway’s Cambodia Green intervention has worked over two phases to support the Government of Cambodia to identify, analyse and catalyse sectors within the Cambodian economy that can help to accelerate socio-economic development and climate impact, particularly focusing on renewable energy, public transport, and agro-processing. The work developed a near-term investment pipeline worth up to $540 million and showcased this to potential investors through a number of engagements and tools - £102m of this pipeline is already in commercial discussions. A key component of the intervention has been the instrumental role Growth Gateway has played in developing the strategy and concept for Cambodia’s flagship Green Special Economic Zone (SEZ) project for sustainable and green economic development. Through Growth Gateway, the Cambodian Government has brought the concept study to the pre-market feasibility stage, selected candidate sites, and begun investor engagement. The SEZ work has led to the signing of a strategic partnership between the UK and Cambodia, highlighting the UK’s expertise in this space and significantly improving HMG’s relationship with the Government of Cambodia. Growth Gateway support on to the strategy and concept for the SEZs drew on the established literature on factors that influence SEZ success to inform design. Through the near-term pipeline and SEZ workstreams, this effort demonstrates significant development potential, including the acceleration of green expertise in Cambodia and the creation of 30K+ new jobs in more resilient, higher value sectors, including many for women – the SEZ will also test a potentially scalable model that can be replicated to boost regional development in target industries across the county, as well as building knowledge and expertise within multiple Cambodian ministries with critical development and climate responsibilities.

1. In summary, GIG will:
    1. promote cross cutting themes of quality jobs, economic inclusion (especially women’s economic empowerment), promoting responsible business, and green growth across its work;
    2. focus on manufacturing and service sectors;
    3. cover all ODA eligible countries;
    4. provide a global offer; and
    5. provide a “deep” or “targeted” country offer of TA for Governments/state entities, TA for business/investors, knowledge sharing and influencing, and learning and evidence services.

What are the delivery options that address the need set out in the Strategic Case?

This section will appraise the “way” in which we deliver GIG support. There are multiple different approaches for FCDO to consider in order to contribute to overcoming the identified binding constraints to green and inclusive growth. We will focus on delivery options for an effective Centre of Expertise model.

As set out in the Strategic Case, the Centre of Expertise model sets out to address the key problems with the CMP delivery approach (e.g. maximising portfolio coherence and coordination, providing a clear and visible central offer that is easy to access and being more tailored for country contexts). The GIG will need to work seamlessly across the broader GIG COE, acting as the central focal point as well as coordinate with other COEs and some centrally managed programmes as relevant (Annex C). We are aware that this will require significant resource also from FCDO staff and bring management challenges. Our approach to managing this is set out in the Management Case.

A “do nothing” counterfactual in the form of drafting new business cases and contracting for a set of successor programmes that are identical/near identical to our existing suite of programmes was considered but discounted early on due to strong feedback from Post that improvements could be made to the existing FCDO operating model. In this option, tried and tested technical support through centrally managed programmes could be relied on to provide some of the envisaged GIG activities. However, there would be gaps in provision for service sector work and the wider partnering, convening and knowledge sharing aspects. There would also be less scope for a more demand led function and ‘targeted’ interventions. Given that this ‘status quo’ would fail to deliver the full vision for a Centre of Expertise, would not drive VfM improvements in FCDO’s delivery model (significant duplication of effort on procurement and programme management), would involve a slower reaction time to new opportunities, would hinder maximal learning and use of in-house technical expertise, and not deliver on the full ambition for COEs, this option was discounted.

Four feasible options to deliver the GIG Centre of Expertise have been identified and are set out below.

The four options are:
- Option 1 – Design successor programmes as in the “do nothing” option plus channel additional funding to other FCDO programmes working in the economic development area (e.g. PACT, the other economic Centres of Expertise) to deliver GIG aims.
- Option 2 – Use existing centrally procured framework contracts, fund additional FCDO staff, agree a range of partnerships managed from FCDO headquarters, and draw on x-HMG expertise.
- Option 3 – Design and contract delivery of all objectives to a consortium programme management office as a single facility.
- Option 4 – Set up a new programme that brings together a consortium managed GIG facility, agrees a range of partnerships and funds additional FCDO staff – preferred option.

Descriptions of each option are provided below. These descriptions are followed by an assessment of each option against a number of appraisal criteria.

Option 1 – Scale-up of existing FCDO programmes to deliver GIG’s aims.

Under Option 1, FCDO’s Economic Development Dept. (EDD) would channel its budget through a combination of existing FCDO programmes (these would include both designing successor phases of existing EDD programmes as well as “buying into” wider aligned programmes e.g. UK PACT and the other economic centres of expertise- See Annex C) that deliver green and inclusive growth objectives. EDD would assess programmes against their ability to be able to deliver results that support the GIG ToC and assess their delivery partners to identify which can accommodate additional support and are able to scale to best deliver results. Programmes would be supported to apply lessons from their existing experience, as well as other evidence to guide their expansion. Programmes would be supported to deliver and expand to support a wider set of geographies based on demand from Posts.

Pros: Funds can be rapidly deployed under this option where delivery partners exist; where proven, successful initiatives have contract headroom, these can be scaled or replicated in new programmes including on women’s economic empowerment. New geographies or areas that the programmes would scale to would be able to apply evidence and learning generated from previous activities. Channelling money through other FCDO divisions could possibly support greater co-ordination and alignment of objectives. Posts understanding of central programming would continue to build on the same programme “brands” which Posts have become familiar with through the work over the last year with the EDPD “vouchers”.

Cons: There is a missed opportunity to provide a more ‘problem centred’, demand led approach to green and inclusive growth challenges, ensure less siloed learning and cross working and integrate new sectors/themes (e.g. services). This option would retain WEE as a relatively small element of the EDD driven GIG programming in standalone programme with inconsistent integration of WEE and economic inclusion into other programmes that are less under our control. This would not deliver sufficiently against ambitions for FCDO’s new Global Campaign on WEE. Existing EDD programmes would require a new set of business cases and/or contract extensions to absorb supplementary budgets and, extend timelines. There are also a range of activities that GIG will consider and source expertise to deliver, if Post request them and they represent VfM, which are not offered under our current programmes. This option would therefore not be able to offer the wider range of types of support Post say may be necessary to respond to partner government priorities and needs to deliver GIG or to support the quality or pace of firm growth in context.

This approach is unlikely to resolve many of the fundamental challenges levelled at centrally managed programmes, nor implement the principles of the Centres of Expertise without considerable changes to existing programmes, which this level of redesign would cost time and money. Continuing to deliver through a number of disparate programmes, managed from different divisions in FCDO requires close engagement from the different leads to drive coherence and coordination, including across COEs. Without additional staff, management burdens would increase and activity would be less coordinated than it is currently. It is also unlikely that management could get separate programmes to tailor their work in different countries to best to complement each other to meet Posts’ needs. The impact will depend on how flexible the existing programmes are to adapt and embed the necessary changes. This impacts the feasibility of delivering at scale through this option. Some existing programmes have limited geographic coverage currently and significant redesign may be necessary to enable expansion where their geographies were predetermined (e.g. IGC or MA). This option would also not support activities of global/regional organisations or activities delivered directly by HMG where FCDO lacks an existing mandate.

Option 2 – Use existing centrally procured framework contracts, fund additional FCDO staff, agree a range of partnerships managed from FCDO headquarters (including drawing on x-HMG expertise).

Under this option, FCDO would deliver green and inclusive growth objectives by accessing TA services through existing centrally procured framework contracts, using additional technical advisers (e.g. Economists, Private Sector Advisers, and Social Development, and programme management Expertise) including programme funded posts, and agreeing a range of partnerships e.g. with multilaterals and HMG service offer, managed from FCDO headquarters. The additional advisers would be based in country offices and specialists based in FCDO’s central or regional departments. Advisers in country would work to understand the market and seek out investors and high potential businesses where TA would be effective, and provide small aspects of deal facilitation and TA directly where they have the capacity and expertise. Advisers would also have authority to spend EDD budget using centrally procured existing framework contracts (the most relevant and likely to be used by GIG would be the Global Development Delivery (GDD) framework) to allow teams/Posts to undertake relatively rapid procurement for either “deep” or “targeted” pieces of work and work on a demand led basis. This option would also be able to draw on expertise from non FCDO sources, including from across HMG, multilaterals. A set of partnerships in specific technical/thematic areas would be established and managed from FCDO headquarters, assessed against table 10.

Pros: The addition of staff, including through programme funded posts could help increase coordination, effective targeting and uptake of evidence across GIG work. This would also help to build FCDO’s expertise, capacity and global profile and position across this agenda- this model incentivises institutional learning and building in-house capability which supports stronger FCDO programme design and delivery, and global leadership long term. These extra advisers would support consistency with FCDO’s strategies for economic development, inclusion and climate action. For the activities that require a supplier to deliver TA, this option provides a relatively low procurement burden as it would utilise new central FCDO agreed framework contracts which are specifically designed to be demand led. These models are quicker to deliver through as there is no tender process. Co-design with Post on a project-by-project basis would be easily built in.

This model would also facilitate support to the activities of a number of global/regional organisations through “Partnerships”. Unlike TA these would not be focused on implementation of bilateral interventions. Post views regarding useful global, regional and local partnerships will be valuable, but Partnerships will not be intended to respond to direct, specific, demands from post rather to support broader useful initiatives in pursuit of green and inclusive growth. Partnerships could have significant reach and impact where FCDO lacks influence or existing mandates, e.g. in relation to WEE and Economic Inclusion, and delivering through other organisations alongside global partners can be more powerful and drive the UK’s policy agendas. Depending on the type of partner, if they are also already providing resources to working on green and inclusive growth globally then we will be able to influence a larger amount of spend than just our own, increase the benefits of economies of scale, and potentially support crowding in of other donors due to their increasing impact. Where other organisations have particular expertise or economies of scale, using our funds to support these partners can offer strong VfM. FCDO would also be able to exert influence over the work and spend of other globally important institutions (e.g. the World Bank) to align with GIG objectives more strongly. It would also enable FCDO to support key global public goods. Lastly, while local leadership will be supported through how the commercial supplier delivers TA, Partnerships would allow FCDO to take this agenda further, by building local partnerships in country and allowing FCDO to support civil society both globally and locally.

Cons: Finance devolved to advisers creates a significant time/management cost for teams to undertake procurement, even under existing frameworks. While using centrally procured framework contracts would avoid the need for a tender, it would still require a contract and a range of commercial requirements for each piece of work. Some degree of bundling activities may be possible, but this will be partly limited by GIG’s aims to be responsive to demands from Post. This continuous contracting could be more cumbersome than, for instance, tendering for supplier(s) to oversee the range of GIG TA. Additionally, a “round robin” approach is taken to assigning work to the different suppliers within the framework for low value contracts (under £7m). This means GIG could not select which supplier is best suited for a given piece of work. This is particularly important for GIG as Posts have stressed that the impact of some of its activities depends critically on the reputation and expertise of the supplier. This option would also still involve a project-based approach which makes cross learning and “interoperable” working challenging and require a heavy FCDO management burden. As with option 1 it is unlikely this project-based approach would be able to achieve sufficient coordination for the GIG portfolio to deliver impact as envisioned, especially across a wide variety of potential project partners – e.g. the GDD framework has 41 potential suppliers. Ability to provide locally led expertise in specific technical areas may be difficult to agree within the framework contracts.

This option puts a high burden on FCDO staff to seek out opportunities, and regularly design interventions, write concept notes, contract GDD, and potentially to deliver more TA support directly for smaller pieces of support where it would not be worth the process of drawing down on the GDD. Lack of consistency in the delivery partner under GDD would mean frequent need to explain GIG aims and model, ToRs and support them to upskill. This option places the highest demands on advisers regarding the variety and flexibility of expertise needed (e.g. a variety of private sector expertise, economist, social development, programme management). There is currently a dearth of social development advisers in FCDO with economic development expertise or vice versa economists with enough economic inclusion expertise. Given known capacity limitations in development and private sector expertise within FCDO, this approach would likely limit the potential impact, or at minimum take notable time to build this capacity, and could be more expensive than admin budgets allow for, unless external recruitment into programme funded posts were possible. For in-house advisers in admin roles, it is likely that other demands may often be made on their time including surge requirements thus limiting their impact. The in-house approach limits the potential for a clean exit strategy during the course of the programme as staff remain a contingent liability of EDD.

In terms of partnering with external organisations, there could be a challenge in ensuring strategic alignment (dependant on how aligned partners are with GIG aims already), flexibility of partners to working with FCDO and the extent that FCDO funds can be earmarked (for example when working with multilaterals). As such it would be important to have a strong and transparent approach for choosing the appropriate multilateral/CSO/academic partners, as well as retaining the flexibility to change partnerships if/when appropriate.

Option 3 – Design and contract delivery of all objectives to a consortium programme management office as a single facility.

Under this option, FCDO would establish a fully integrated facility, delivered by a consortium of partners to carry out all proposed activities. We considered a range of partners, including multilaterals to manage such a facility, but determined that a commercial supplier would be the best option in terms of capability, level of ‘UK branding’, having the right expertise, and ability to direct our resources to the priorities as we see them. The facility would deliver the full scope of the programme activities as outlined above (i.e. “deep” and “targeted” TA support and advice to partner Governments and private sector, networking, convening, analysis, and learning).

The consortium bidding for GIG facility would be asked to set out its approach to effective engagement of social actors to support locally led and relevant growth strategies and proposals and to drive voice and representation of economically excluded or disadvantaged groups. Direct participation of civil society partners and locally led expertise in bidding consortiums will be strongly encouraged. The GIG will stay up to date with evidence on how to best engage local leaders and social groups in decision-making.

Pros: This option provides a strong response to the challenges identified in the strategic case. It would provide significant support to Posts in their objectives by delivering interventions and supporting policy needs of Post and central teams. Whilst the initial procurement would be complex, thereafter procurement burden would be limited. It could provide bespoke expertise for individual TA interventions, undertake rapid evidence reviews, work with MREL partner to track and measure inclusion elements, provide training, and build capability to drive economic inclusion objectives across programme components. Working through a single facility would enable a stronger portfolio level vision with coordination and coherence across activities, which Posts have feedback is important to maximise impact, and would support cross learning across the GIG. The EDD programme team would have greater control and flexibility in the allocation of resources during delivery relative to Option 1, allowing for risk adjustment in relation to financial flows and areas of operation, including scaling components up and down and phasing their delivery to allow successful initiatives to be scaled up. It would also have more control and flexibility relative to option 2, assuming that it was possible to develop an effective relationship with the commercial supplier who is responsive to requests through delivery, and there could be greater fungibility between activities. There is also likely more control in this option given it doesn’t involve “Partnerships” which can be harder to influence the direction of.

The Consortium would be asked to set out its approach to effective engagement of social actors to deliver locally led and relevant initiatives in responding to the needs and potential of economically excluded groups. It will also need to set out how it will draw on locally led expertise. This option would support more consistent and robust tracking of inclusion objectives relative to Options 1 or 2, as a single approach could be defined and required across activities, without needing to regularly upskill a new supplier on this (as would be the case under Option 2). EDD would be able to monitor economic inclusion objectives and hold commercial partner to account for delivering these, whilst also driving lesson learning and sharing across geographies, sectors, and delivery partners. The Facility could stand up a cross cutting economic inclusion advisory service to support generic GEDSI approaches across its work as well as the wider COE. FCDO could dictate the criteria to screen requests and include screening of requests against inclusion objectives, do no harm and safeguarding risks. The ability to draw on a roster of experts would strengthen its ability to consider gender and WEE, disability inclusion, youth employment, working with people on the move (migrants, refugees & asylum seekers) and others as required, in its work.

Cons: There would be a limit to the number of organisations able to deliver such a complex programme. Most of the technical work would be outsourced so in-house technical capabilities would not be deepened, including on economic inclusion approaches. Whilst procurement demands would be limited, ongoing programme management and oversight of such a complex programme would be considerable, in addition to a high burden on strategic leadership to ensure a facility of this size and breadth continues to deliver VfM for FCDO. EDD may lack sufficient capacity to provide strong oversight and close engagement with partners to drive coordination across all the components and to share lessons across the wider COE and other Economic Development COEs. It is worth noting that commercial and management burdens would likely be lower than under Options 1 or 2, however this would still be highly challenging to do well without additional FCDO resource. EDD and Post would need to help the consortium partner to establish or strengthen relationships with the partner governments for the programme to be effectively delivered and respond to priorities. It is unlikely the consortium partner would have the degree of relationship needed to deliver effectively, at least in the near term. It would also not be possible to draw on wider partnerships, including access to HMG expertise, under this model. There would be no scope to take advantage of the existing mandates, reach, expertise and comparative advantages of multilateral or CSO partnerships, the benefits of which are laid out in Option 2.

Working with consortia carries its own risks. For example, if the lead supplier doesn’t draw down on more niche expertise of other consortium partners, e.g. who are better suited to work in FCAS or have access to specific industrial expertise or the breaking down between consortium partners and impacting programme delivery. GIG is conscious of these risks and will seek commercial advice particularly to design contracts to mitigate these risks when using consortium.

Option 4 – Set up a new programme that brings together a GIG facility, agrees a range of partnerships and funds additional FCDO staff – preferred option.

Under this option, FCDO would utilise existing in house advisory and programme management capacity with additional programme funded advisers, agree a range of partnerships, and establish a consortium managed facility to deliver one component of the programme. This option consolidates the delivery mechanisms described under options 2 and 3, recognising the comparative advantages of each.

Pros: This option would overcome most of the constraints identified and enable that the right delivery method to be utilised for each component to maximise impact, including drawing down on the right kind of technical and local expertise. Despite the need for a complex tender process for the facility, implementation of other elements of the programme should be able to begin relatively quickly through bringing on board in-house advisers and programme funded staff, as well as contracting partnerships, some of whom are likely to be organisations with whom FCDO has an existing relationship (subject to appraisal). Retaining this ability to partner with global/regional organisations means the programme could have significant reach and impact where FCDO lacks influence or existing mandates in relation to WEE and Economic Inclusion, and support partners with comparative advantage and economies of scale in certain activities. As discussed, Partnerships would allow FCDO to give a global voice to our policy work, influence wider global processes and build alliances through these fora. It would also support partnerships to drive a localisation agenda. By including partnerships within this business case, this will allow the FCDO the option to continue a number of global partnerships that already exist as well as consider new ones, in a way that best supports experience sharing and lessons learning, to drive coherence and impact. This also avoids a proliferation of smaller separate business cases to fund individual partnerships in a way that don’t sufficiently cohere or learn from each other. As in Option 3 the facility could provide bespoke expertise for individual TA interventions, undertake rapid evidence reviews, work with MREL partner to track and measure inclusion elements, provide training, and build capability to drive economic inclusion objectives across programme components. This retains the advantages of the flexibility, responsiveness, and access to a varied range of expertise brought by a consortium of implementing partners and their sub-contracted experts across inclusion, manufacturing, services, and green growth issues.

Additional FCDO programme funded staff would sit centrally and at country level. Central staff would undertake actions to help improve co-ordination with the wider COE and other Economic Development COE, support “interoperability” and cross learning, and act as the conduit to Post. This would increase value for money by supporting important lessons to be disseminated and used within and beyond the GIG, for instance driving uptake of lessons from our “Partnerships” by the GIG facility supplier. Experience finds that FCDO often does not deliver on cross-learning objectives because this isn’t sufficiently designed into the business case. Deploying in house advisers as part of a joint team will also help raise capability levels in FCDO as well as FCDO profile in country. The existence of a facility means that we would not need as many in house advisers as option 2, and that they would not need to spend time engaging with procurement frameworks.

Cons: Whilst this is the case with all the options, this approach will require considerable time and expertise to design, oversee and deliver. Realising the benefits of a complex private sector led flexible facility, alongside a range of partnerships in a new programme will require considerable oversight, advisor, and programme management time. This is a risk in a context of scarce development expertise and pressures on workforce. EDD will need to ensure its current configuration of advisers and programme management staff can be appropriately configured to address the commercial and management requirements, as well as engage with the facility supplier to keep focus on activities that are VfM and support lessons learning and dissemination in a “joint team”. As discussed, the Secretariat and Hub will need to ensure that it communicates and manages a clear and straightforward offer and process to Posts, despite the complexity of the underlying programme. This will be actively tested and refined during inception. EDD will need to ensure it has sufficient staff capacity to manage the potential number of smaller partnerships, engagement with which could take a disproportionate amount of time.

Table 2: Features of the different appraisal options

Option	TA Activities are coordinated by delivery partner	TA Activities defined by Post demand	EDD selects strong TA supplier via new tender	Includes Partnerships	Coordination and management required from FCDO staff (comparative)	Extra FCDO Programme funded staff
Option 1	No- Many suppliers under different programmes	Partly -based on activities offered under past programmes	No	No	High	No
Option 2	No- Many suppliers engaged separately under central framework	Yes	No	Yes	High	Yes – High numbers of new staff required
Option 3	Yes- single “facility” with 1-2 tier one suppliers	Yes	Yes	No	Low / (Central staff act as conduit to Post and linking to wider FCDO/ HMG work)	No
Option 4	Yes- single “facility” with 1-2 tier one suppliers No – Activities delivered by facility (with 1-2 tier one suppliers) , partners, HMG expertise, FCDO expertise. Coordination is by joint FCDO/Supplier hub	Yes	Yes	Yes	Medium / (Central staff act as conduit to Post and linking to wider FCDO/ HMG work plus drive coordination with GIG “Partners” and support uptake of any evidence between TA facility and Partnerships)	Yes – low numbers of new staff required

Assessment of delivery options

The options outlined above have been assessed against a set of criteria to determine the most appropriate delivery option to achieve the aims of the programme (see table 2). These criteria are based on available evidence of successful approaches to delivering green and inclusive growth. Aspects of VfM are assessed and embedded across the criteria to enable GIG design and delivery to integrate economy, efficiency, effectiveness, and equity considerations from the outset.

The table below presents the results of the analysis. This builds on the discussion of the pros and cons of each option above. Each criterion is marked on a scale of 1 to 5, with 5 being the highest score. A maximum score of 40 is possible, with options scoring above 28 (i.e., >70% score) considered most favourable. No additional weighting has been applied, though a sensitivity analysis finds that adjusting weightings would not impact on the relative ranking of options.

Table 3. Assessment of delivery options against criteria (1-5, with 1 the lowest and 5 the highest)

Criteria	Option 1 – Scale-up existing FCDO programmes	Option 2 – Advisers and partnerships	Option 3 – Single facility	Option 4 – Facility, partnerships, and Advisers
Effectiveness: quality of outputs and their ability to drive outcomes / address constraints, consider whether impact on ability to deliver on key themes.	2	4	3	5
Efficiency: particularly in terms of timely delivery, agility of the model, flexibility to scale up / down	1	3	3	4
Economy: cost	3	1	1	3
Equity: how likely is it that inclusion objectives are met? How fairly are benefits distributed?	2	3	3	5
Sustainability: will outputs drive outcomes/results in the long term at scale, including once the intervention is complete? Will the option support institutional knowledge and learning?	2	4	3	4
COE alignment: (FCDO strategic alignment) – how does the option deliver on the COE vision	1	3	5	5
Control & risk: what is the management and delivery burden?	3	3	3	3
Local and national ownership: Consideration of political and institutional factors, e.g. to what degree is government ownership and leadership reinforces or undermined, builds local capability?	3	5	3	5
TOTAL	17	26	24	34

The preferred delivery option based on the multi-criteria analysis is option 4. This option reflects the strongest aspects of options 2 and 3 which also scored as relatively favourable, compared to option 1. This combination would provide the basis for addressing the constraints identified in the strategic case through a range of interventions with the agility to respond to the particular nature and conditions associated with different enabling environments across FCDO geographies.

The preferred option

This new programme would be aligned to deliver on the GIG programme scope (see para 81). GIG would be delivered through 3 main components:

GIG hub and Technical Assistance Facility (TAF) (£205m ODA, £7m non-ODA): The TAF will deliver integrated TA activities across GIG’s themes and on a demand-responsive basis, subject to criteria and strategic alignment with GIG. The TAF provides TA directly to firms (likely minimum 50% direct to businesses) and on the broader business environment. The TAF’s work would be firm/ investor led, though there would be scope for the TAF to inform policy and strategy, by conducting high-level “path-finding” and diagnostics at the government level. Activities will be delivered at a range of scales (deep vs. targeted). The Hub and GIG TAF will also deliver part of the learning and evidence function for GIG and include monitoring, review and learning (assessing GIG’s impact, performance and VfM and provide continual learning over the period of the programme) as well as active co-ordination with the other FCDO Centres of Expertise and relevant Centrally Managed Programmes. The component would also help to drive integration across the GIG COE and wider FCDO programme portfolio. This component will be delivered jointly by commercial supplier(s) and FCDO staff, including Programme Funded Posts. The TAF would deliver both ‘deep’ and ‘targeted’ interventions co-designed with Posts and in response to country demand. Both types of interventions would contribute to, and adapt, in response to the learning and evidence function.

International Growth Centre (£70m ODA): This component will deliver demand-responsive, evidence-based policy advice and support to developing country governments and support their capacity. It will stimulate wider policy debate (international and in country) and deliver world class research outputs, policy briefs, responsive policy advice and synopsis papers. Whilst both components will deliver demand responsive advice, this component differs from the TAF described above in that the advice will be grounded in the IGC’s research and long-term relationships formed with government partners through a country office network. These features will support new growth policies and reforms leading to an impact of higher and more sustainable investment and economic growth. Drawing on its strong track record, the IGC will include a country programme element, research programme element, and a networking and communication element. The IGC will also play an umbrella role to maximise the impact of other RED economic development research programmes and its country office infrastructure. The IGC does not advise business and its model of drawing in world class academics limits how far it will work on issues of implementation support, which the TAF will be more able to support. Thus the IGC and TAF will act as complements to each other.

Partnerships for Growth (£25m ODA): This component will also support a range of GIG activities, delivered by key strategic partners. These could be multilaterals, academia, CSOs or private sector partnerships. Partnerships that deliver against cross cutting themes will be scoped at programme start-up phase. GIG will be able to engage new partners throughout the lifetime of the programme in response to emerging priorities, evolving contexts and demand from Post. These will build on and learn from the number of partnerships with these organisations that FCDO has had in recent years through existing GIG projects and other related projects.

There are several further parameters to be considered under the preferred option:
  1. Delivery of the hub
  2. Delivery of the Technical Assistance Facility’s services
  3. Delivery of the International Growth Centre
  4. Type of partnership organisations and methodology for selecting them
  5. Post commitment and role (inc. Post ‘buy-in’)
  6. Delivery approach to provide flexibility

GIG Hub

The GIG Hub will sit at the heart of the GIG COE. Due to the nature of GIG, it will have a thought leadership role across COEs and FCDO tools. GIG Hub will coordinate across work strands within GIG and the wider GIG COE, specifically the CASA and Land Facility programmes. The GIG Hub will also work across FCDO, for example with British International Investment (BII) and other COEs, to support wider FCDO portfolio fit of GIG activities. It will also have an important HMG capability building role (e.g. supporting policy development by delivering a helpdesk function) and will link into the International Academy. The Hub will proactively synthesise/disseminate and use the evidence generated to communicate with both internal and external audiences to support the GIG objectives. As mentioned, this is important as the VfM of some past programmes have been limited by assuming that evidence generated will be automatically disseminated and used, but not planning resource to support this. More focus on FCDO’s ability to absorb and use the evidence it generates is important for VfM and a key improvement of the COE model. GIG Hub ways of working are set out in the management case.

We assessed the option of a Supplier delivered Hub vs. one delivered solely by FCDO. Based on evidence from current delivery models, GIG Hub will follow a hybrid model and be a joint FCDO and commercial supplier team. The GIG Hub will build on evidence generated by the Growth Gateway model and combine the benefits of a commercial supplier – availability of widespread expertise and speed of deployment (important when responding to Post demand that is time sensitive) – with the benefits of an in-house unit – maximising the use of FCDO expertise and building this up, using FCDO staff to triage Post requests to the right partner, keep control over strategic planning to retain a clear focus on VfM during programme delivery, quality control, having a clear contact point for country teams, ability to coordinate with wider FCDO programmes and COEs, and low-cost advisory inputs e.g. in preparing Concept Notes and Terms of Reference. Having the programme delivery team sit within a Hub provides an opportunity to bring together all components of the programme to help them be coherent and mutually reinforcing.

Table 4. The GIG Hub – a joint FCDO-Supplier(s) team

FCDO	Supplier
FCDO team provides cross-GIG programme management function, risk management and is responsible for results measurement and reporting. / The FCDO element of the team would include managing the Partnerships for Growth component, representation, and leadership of wider GIG COE and ensuring join up between programme components and wider FCDO and cross-HMG programmes and policy. / The FCDO team would work with the Delivery Partner(s) and would provide strategic input/quality assurance for interventions, helping to align interventions with UK Government policy, help triage Post requests to the right GIG partner if more than one, navigate cross-Government networks, and be responsible for internal Government communications. / The FCDO team would be the ‘client’ for interventions relating to activities focused on strengthening FCDO policy and programmes e.g. helpdesk on jobs and WEE, literature reviews, policy support to be delivered by the commercial supplier. / A network of in-country/region advisers (based on the very successful Manufacturing Africa model) would be programme funded and coordinate delivery of relevant interventions in their region. This would involve working with posts and local partners to create a pipeline of potential interventions (both ODA and non-ODA funded), quality assuring possible activities and overseeing delivery on the ground. / The GIG hub will be able to draw on in house FCDO expertise, e.g. on working with civil society and women’s rights organisations, to support the work of the delivery partner and on x-HMG expertise where relevant (e.g. potentially DBT, Competition and Markets Authority, Companies House, Insolvency Service).	The Delivery Partner designs, costs, and delivers interventions, including focused interventions on the cross-cutting themes, and provides detailed reporting on results. To do this the Delivery partner will provide expertise and TA from the consortium or subcontracts more specialist expertise where necessary. / The Delivery Partner collaborates closely with posts and in-country advisers to understand needs and design cost effective interventions. The Delivery Partner provides a costed menu of intervention options to support appraisal and VfM. / The Delivery Partner supports the FCDO team to deliver information sharing and learning ambitions. The supplier will be expected to show how it draws on its own learning and evidence to improve intervention design. / The Delivery Partner stands up a cross cutting economic inclusion advisory service to support generic GEDSI approaches across GIG COE, support screening of requests against inclusion objectives, do no harm and safeguarding risks and track and measure inclusion objectives across GIG COE. It would provide bespoke inclusion expertise to individual TA interventions (e.g. rapid evidence reviews, convening, learning and dissemination events, training and building capability on economic inclusion etc.). / The Delivery partner would support innovative ways to drive civil society engagement across GIG.

The FCDO GIG team will include programme managers, specialist advisers, a Senior Responsible Owner, and in-sourced roles (including regionally based roles). In-sourced staff will support country or regional level delivery, and coordination and lesson learning to maximise the impact from GIG interventions. While these in-sourced roles could be delivered through the commercial contract, they require not only technical expertise but FCDO specific expertise. More details on the proposed staffing arrangements are included in the management case.

Technical Assistance Facility

The technical assistance facility will have access to a range of expert consultants who will support FCDO to design and scale up activities that contribute to GIG. As set out earlier in the appraisal case, the facility will look to deliver ‘deep’ and ‘targeted’ programmes of work. These interventions would be demand led and able to scale up or down in response to FCDO emerging priorities, contextual opportunities or further develop opportunities unlocked by partner organisations. We will look to commercial suppliers to set out how best to deliver the TAF in their bids and in response to our Terms of Reference. We will appraise bids on technical criteria. This is further set out in the commercial case.

Services will be drawn down on by FCDO leads either at HQ or Post and delivered to private sector firms, or with partner country governments. Working across HMG will also be important so that wider equities can be reflected and opportunities for secondary benefits using non-ODA can be identified and acted upon. TA will be delivered under a ‘T’ shaped model – ‘deeper’ long/medium term projects alongside shorter more ‘targeted’ interventions. GIG interventions will need to be based on strong local knowledge/contextual understanding so will be co-designed wherever possible (subject to capacity/capability at Post).

Analysis of constraints and enablers to success, including political economy analysis and robust climate risk assessments, will be fundamental in informing how and where GIG operates to prioritise bids for support with strongest evidence of tractability and impact, and to not deliver activities where the political economy or other factors makes impact unlikely. When working with the government this would include an assessment of political will and the political environment. When working with firms this would include assessing the operating environment. For example, GIG would not use resource trying to support investment or commercial expansion of firms in countries or sectors where prevalence of state-owned enterprises effectively stop this from being successful. Going beyond using political economy to assess the likelihood of success of requests, Posts will also be expected to have designed concept notes strongly led and informed by political economy analysis, to focus on interventions that can best drive GIG objectives within the given circumstances. For instance, while noting that reformist governments are important for the business climate, this will not always be necessary to deliver effective support to the private sector and in such settings supporting a strong private sector to grow that creates inclusive jobs becomes possibly even more important. Analysis could also help identify, for instance, particular ministers as champions of change and their agendas that GIG can support, or inform whether GIG should work at a national sub-national level etc.

The diagram below depicts an example user journey of the GIG TA.

Figure 3. Example user journey

International Growth Centre (IGC)

The FCDO’s IGC programme is now in its third phase and continues to score well in Annual Reviews. EDD analysis has found that the IGC represents excellent value for the GIG COE, as it can attract top-tier researchers at concessionary rates. IGC is effective in generating rigorous, policy relevant research, and providing world-class economic experts and academics to offer key policy advice to partner government policymakers, with whom it has built strong relationships. New business needs of FCDO post-merger have brought an increase in requests from Posts for high-impact high-profile policy advice in specific circumstances, technical assistance and capacity building work from IGC. During phase three, in addition to IGC’s core work on research and planned policy support to partner governments, IGC have delivered a small number of such requests, but these have been ad hoc.

1. Important elements in delivering this kind of policy influence have been found to be:
    1. The IGC’s network of country offices has allowed it to benefit from economies of specialisation, with long-term country expertise and long-standing independent relationships with policymakers ensuring a level of trust that facilitates the uptake of findings.
    2. IGC’s Research portfolio, embedded in an academic setting and on which policy advice is predicated, strengthens the quality of its advice and its ability to give an independent view to partners (which in turn also builds trust); the research portfolio also attracts top tier academics further strengthening quality and credibility.
    3. IGCs ability to draw on this research, and relationships to deliver independent, high impact advice.

In line with the principles of Centres of Expertise (discussed above) we considered the extent to which we can design the next phase of the IGC offering to be even more responsive to Post / partner Government requests, to enable it to deliver even more impact. This consideration was balanced against the potential risks to the IGCs model (the three elements above) and reputational cache which IGC has built over time amongst researchers and policymakers.

Three approaches were evaluated, as alternative ways in which adding a specific policy responsive function to the IGC could be delivered:

Ring-fencing a budget for policy advice and delivering this advice through the TA function of the GIG Hub: using a consultancy-style model providing rapid, short-term responses to all requests. While this approach offers flexibility and could deliver a high volume of policy advice, it may not be firmly grounded in academic research, potentially leading to a significantly lower development impact. It also risks lower quality of expertise, as world-class academics may not be incentivised to work on projects with little promise of published work from consultancy-style projects. Furthermore, this model may incur higher costs, as academics would likely charge consultant rates rather than the concessionary rates currently offered by IGC.

Retaining the IGC as a separate offering, and building in a ring-fenced budget for policy responsive work; but also recognising that IGC advice is grounded in research and the country office network, limiting the policy offer to geographies and themes where the IGC has a comparative advantage. This approach would maintain access to top-class academics and maintain the development impact of outputs. With this offer the IGC’s responsive unit will deliver short-term activities such as workshops, impact assessments, and policy advice in countries where the core IGC model has a footprint (for example an existing country office) and in policy areas which are aligned with existing IGC research themes. This approach would allow the comparative advantage of the IGC to be leveraged to increase the efficiency of value for money. However, this approach it means the responsive unit would be unable to meet a significant number of requests from FCDO posts which lie outside its core geographical coverage, reducing its overall effectiveness. This option will also prioritise quality over quantity regarding activities, meaning the volume of requests met will be constrained by the capacity of IGC experts to deliver them without reducing the quality and impact of IGC’s core activities.

The final option considered is to combine the second approach with a triage function for the GIG hub. When the IGC is deemed the most relevant partner in the GIG COE to deliver a request, but the request is outside the footprint of the IGC’s country offices, the GIG hub would first reconsider if a member of the consortium in component 1 of the COE can deliver to the research standards required. Where this is not possible the GIG hub can draw on IGC expertise and the FCDO’s Chief Economist’s office to identify alternative ways to meet demands. This could involve leveraging the IGC’s position as a world class research body to reach out leading research institutions and experts who are not part of the IGC cadre but are accessible through the IGC's network. Posts would then be given access to these experts who may be able to deliver activities akin to those in option 2 but in geographical areas or on themes without IGC presence or expertise. This will result in minimal additional spend while extracting greater value from the IGC. This approach offers the best balance between leveraging the IGC’s strengths and meeting the diverse needs of FCDO posts.

In conclusion, the third option presents the most promising approach to maximising the value for money of the IGC’s responsive function within the GIG COE. By combining the IGC’s comparative advantages with the flexibility offered by the GIG hub and IGC network, the IGC can continue to deliver high-quality, impactful research while expanding its reach to support a broader range of FCDO posts. The final delivery mechanism will be subject to legal and commercial advice and communicated to potential implementing partners once finalised.

In alignment with the growth-focused approach of GIG, the next phase of the IGC will prioritise generating substantial research and empirical evidence on economic growth across its thematic areas of focus. We envisage the IGC component will include a country programme network, research programme, and an element of networking and communication. As with all aspects of the GIG, the IGC will also aim to maximise the impact of other RED research programmes and its work. Supporting this would involve:

- Feeding in-country policymaker interests and questions to the RED programmes (where they are relevant to the other programmes’ agendas) to help shape their commissioning.
- Supporting contacts between researchers & policymakers to increase research uptake.
- Supporting & hosting joint dissemination activities such as events and conferences.
- Supporting the generation of research communication products and dissemination, particularly through VoxDev, of which IGC is one of three key stakeholders.

IGC’s research focus, and consequently its expertise and scope for generating evidence-based policy advice is guided by its research themes. The GIG will incorporate a comprehensive consultation process involving academics, policymakers, and leading experts to reevaluate and update the key research themes that the IGC component of GIG will take forward. Following approval of the Business Case, and prior to bringing suppliers on board, GIG will undertake this consultation process to critically examine whether the IGC’s current themes remain optimally aligned with promoting economic growth or should be updated. It will identify emerging themes that are crucial for fostering growth and explore strategies to accentuate the growth perspective within existing research themes. Through this rigorous prioritisation process, the IGC’s research agenda will be refined, ensuring that it remains at the forefront of generating actionable insights and supports evidence-based policies that drive sustainable investment and economic growth within developing economies.

As with activities of the commercial supplier, the IGC will offer different formats of engagement. What it can offer to countries will depend on the research themes (see above) as well as its depth of its presence and expertise in the country. The countries where the IGC has a stronger presence will be able to benefit from a more comprehensive range of offerings, as follows:

- Full country Programme – Deep and broad, permanent on the ground team, country director, research commissioning, short term interventions incubates longer term research, strong relationships built over time with government partners. Research agenda linked to the partner government’s priorities.
- Broad country engagement – Not quite a full country programme – no country director, but a small team of economists based in country, building relationships with the partner government, demand-led research being produced.
- Targeted flexible arrangement – Countries where there is no IGC full programme. This can take several forms from the very short-term light touch to the much more in-depth activities that can lead to a full IGC programme being established.

Please see Annex E for further detail on the IGC Component.

Partnerships for Growth

It is envisaged that GIG will seek to maximise its impact through strategic partnerships (component 3). As discussed above, to best deliver some of the indicative activities envisioned, we judge it will be important to deliver some top-down global analysis, interventions that address regional cross border issues, and policy influencing initiatives, as well as to work with organisations that have significant expertise or existing mandates related to aspects of GIG such as women’s economic empowerment, so the UK can continue to play a role in key global debates, retain its influence and reach, and help shape some of the global institutions that deliver green and inclusive growth. This includes using partnerships to support a local ownership and leadership, considering partnerships in country and engaging civil society. GIG partners will have the expertise and capability to extend FCDO’s comparative advantage on GIG in specific thematic areas or geographies or deliver a global approach. This partnership approach also allows an expansion of the types of solutions and approaches available to FCDO to address the key constraints that inhibit GIG. Through partnerships FCDO will give a global voice to its policy work, and partnerships provide FCDO the chance to influence wider global processes and build important alliances. It may also allow for influence to leverage change in larger sources of multilateral spend (e.g. with the World Bank). These partnerships may be less flexible in type but complement the more flexible TAF and together can enhance impact of the programme across GIG.

The relative merits of potential partner organisations (including non-governmental organisations, think tanks, development banks, multilateral agencies, academic institutions, civil society organisations and private sector) will be assessed against a range of relevant criteria. These criteria and a list of expected partners are mapped in the tables 9 and 10 in the Commercial Case, with further detail on indicative partnerships in Annex F. When assessing partners we will first consider if they are able to deliver something that cannot be achieved through FCDO’s bilateral intervention, or can deliver a particular set of activities at a significantly higher VfM. The criteria to assess Partnerships will include assessing whether they have unique expertise that can’t be attained through a commercial supplier, established geographical reach and economies of scale in existing delivery related to GIG that make delivery through them better VfM for certain activities or in certain geographies, or established global leadership with existing support from a wider pool of partners that allows us to maximise our influence and impact by taking part in their agendas. For instance, current UN Women pilots are seen as crucial to the Care agenda as the UN is leading thinking on models of the Care economy. The Extractive Industries Transparency Initiative (EITI) works to promote accountable management of oil, gas and mineral resources, in a way that supports local leadership by having strong local engagement in each country. This makes a significant contribution to green and inclusive growth, but could not be delivered efficiently or so effectively through a separate FCDO bilateral initiative. Working as part of broader coalitions may also allow FCDO more influence and impact on some issues, than if it sought to deliver bilaterally. To note, the work supported under Partnerships is not intended to respond to specific TA demands from Post but rather to further FCDO’s global policy agenda through partnering with, supporting, and influencing the work of others. This component does not intend to focus solely on global analysis but will likely include support to leading providers of global analysis as a global public good in these niche areas e.g. the World Bank on Jobs and UN on responsible business and care, and/or subscriptions to the Donor Committee on Enterprise Development who are the global leaders. As outlined in the criteria in table 10, options will be assessed to ensure FCDO draws on existing research before funding any new partnerships, and GIG will focus on supporting the highest value global public goods to avoid a proliferation of similar work and entities.

Partnerships will offer FCDO a chance to capitalise on the economies of scale of our Partners or support their unique global contributions. The commercial case also outlines the options in terms of how we would partner with these organisations. The GIG envisions funding ~7-10 Partnerships, many of which are partnerships that FCDO has already had in recent years. The number will be capped at this level by the quantity of funding that has been set out for Partnerships, and by explicitly assessing the management burden and degree of available resource when appraising Partnerships. The impact on management burdens will be taken seriously when considering each additional Partner.

A key risk is proliferation of agreements so ensuring the right staffing will be critical. The policy leads/thematic leads will be the points of contact, overseen by the GIG SRO and supported by the Hub and FCDO programme managers. The GIG Hub team will help manage these Partnership relationships including, for example, facilitating regular meetings and workshops to allow greater learning between partnership organisations, dissemination across broader FCDO and elsewhere (e.g. HMG, externally) as well as opportunities for shared activities which could improve VfM. The GIG hub ways of working will be set out in the management case.

Post commitment and role (including Post ‘buy-in’)

The approach in terms of geographical scope is to have a facility with a global remit, subject to ODA rules, that has the flexibility to respond to future changes in FCDO/HMG strategy as well as evolving global and national contexts. Regardless of geographic focus or size/area of intervention, all support mobilised under GIG must show evidence of:

1. Genuine commitment from Post – demonstrate fit with Country Plan and Post priorities, have a member of staff assigned in country to lead the work with GIG.
2. Genuine commitment from Partner Government or target organisation – ambition to deliver in this area, including on inclusive and climate elements.
3. Delivering against GIG objectives – the intervention must be able to directly contribute towards the GIG log frame.
4. Scoring at the baseline of GESI and climate scorecard – GIG will use a rigorous scorecard approach to appraise GESI and climate impact on each intervention regardless of whether it is the specific focus of the intervention.[71]
  [71] Similar to BII and MA dev impact score and GEM markers could score interventions against Do no harm (1 point), inclusion (2 points) and Transformational potential (3 points)

A detailed set of criteria to prioritise which Post requests to service, including the elements above, is set out in the Management Case. This will be used when considering specific proposals for the Technical Assistance Facility. This will enact a strong triage process to ensure that the GIG delivers across its objectives at portfolio level e.g. of placing a sharp focus on economic transformation and also of supporting climate compatible growth and hitting ICF targets. The criteria and appraisal process will be made clear to Post from the outset to ensure that transaction costs in terms of time spent developing proposals is kept to a minimum. Initial conversations will also be had between Post and GIG to ensure that expectations are aligned and clear, and give an early indication of whether a request is likely to be something GIG could support, again aiming to reduce any unnecessary process time being spent by Post.

As set out in the Strategic case, the COE voucher process run in FY23/24 demonstrates high demand for GIG services. We explored this further in our consultations with Post which took place in Feb-April 2024 and specifically asked about plans for ‘buy-in’. As a result of a wider country scoping and increasing demand, we expect up to 20% of GIG funds to come from Post (e.g. under the new Ukraine recovery and reconstruction business case). This will be supported by proactive comms making Post aware of the scope of the programme as well as detailed guidance on the ‘buy in’ process.

We expect that Posts with an ODA or non-ODA budget will be able to buy-in directly to GIG. Each request will be considered on a case-by-case basis. GIG support (see para 105). Evidence of strong Post commitment and ability to take forward interventions will be required to ensure sustainability.

Theory of Change for Preferred Option

The diagram below sets out the Theory of Change (ToC) for this programme.
 Figure 4. Theory of Change
At impact level, the ultimate objective is to contribute to inclusive and sustainable poverty reduction, low carbon growth and climate resilience in FCDO partner countries. These impacts will be achieved beyond the lifetime of the programme.

At outcome level, the programme will contribute to transformational, inclusive and green economic growth. These outcomes are aligned to the UN Sustainable Development Goals (SDGs) specifically; gender equality (SDG 5); decent work and economic growth (SDG 8), industry, innovation and infrastructure (SDG 9) and; climate action (SDG 13). It is envisaged that non-ODA will be deployed, alongside ODA, to deliver growth benefits to the UK, for example the UK builds influence to be considered a key strategic partner on GIG and increased UK commercial opportunities alongside helping strengthen relationships with the Global South. Outcomes will be measure at economy wide level.

GIG’s Intermediate outcomes contain a number of objectives, reflecting the breadth of expected activity under GIG, and relate to the specific businesses or sectors in which we will work;
1. New policies and reforms that support GIG for the country context are introduced
2. Governments/States are better able to successfully implement policies and reforms that support GIG
3. Growth in domestic firms in focus sectors/sub sectors
4. Increased investment in focus sectors/sub sectors
5. Greater number of more productive Jobs
6. Increased labour market participation and better conditions for women and vulnerable groups
7. Care work recognised, redistributed, and rewarded
8. More responsible business models

The main outputs that arise from GIG activities are that Governments/agencies are better able to identify, introduce and implement policy frameworks, policies and reforms that support green and inclusive growth; TA leads to improved firm productivity and productive supply chain linkages, there is greater awareness and active participation in commercial, and separately also of investment, opportunities which promote positive climate and development impacts; HMG is better able to deliver green and inclusive growth and world class research and knowledge products are created and shared with relevant stakeholders to support green and inclusive growth.

Evidence and assumptions

The table below describes a range of assumptions that are relevant to the programme. The strength of the evidence base is also assessed. It is scored strong, moderate, weak. The strength of evidence varies, this is in part due to some of the areas of work flagging up as weak evidence though high potential. The areas where evidence is weak will be a key part of the MEL approach for this programme and programme flexibility will allow it to scale these activities up or down in response to MEL results.

Table 6. Key assumptions and associated evidence behind the Theory of Change

	Key Assumptions	Strength of Evidence
Inputs to activities	FCDO is the sole funder of GIG (this programme). / Accurate planning and forecasting to maintain stable and predictable budget. / Sufficient HMG capacity and capability to deliver the programme, including at Post. / FCDO Posts seek to buy-in to programme. / Ability to procure an efficient and effective partner with sufficient capability that delivers VFM.	Post capacity to deliver will be assessed during intervention selection. / Consultations within FCDO and the COE voucher exercise have identified demand for TA support – Strong. / We will further assess strength of evidence during EME activities.
Activities to Outputs	Availability and buy-in of key partners (policy makers, firms, academics, experts etc) / Expertise is relevant and applicable to a variety of contexts. / Commitment to tackle exclusion and willingness to challenge gender stereotypes and segregation in the economy, and recognise care work. / Activities work with wider FCDO tools and Posts remain engaged. / Activities anticipate future challenges and can adapt to external events.	Buy-in from key partners will be assessed during intervention selection. / We will further assess strength of evidence during EME activities.
Outputs to Outcomes	Effective communication/usability of outputs / Political appetite to adopt recommendations (policy, implantation etc) / Firms bought into process and apply TA, act on information/support to raise productivity and increase new commercial opportunities / TA to the private sector leads to increased domestic supply chain linkages / Firms bought into process and apply TA, act on information/support to deliver investment. / TA to private sector will lead to increased investment across a sector not just for specific firms. / Impact of increased FDI on economic development and transformation / Policy can support benefits of FDI and ensure pro-poor spillovers. / Policies are implemented effectively to deliver against GIG objectives	TA, research, and policy recommendations leads to implementation and reforms (ensure not superficial EcDev Best Buys (BB)) – Strong / Policy reforms lead to a better investment environment – Strong. / Increased investor awareness of opportunities – Medium / Increased pipeline of investable deals leads to increased investment – Strong. / Improved data and evidence improves quality of investments – Weak. / Responsible business interventions (BB – low evidence) – Weak / Investment in firms (BB – high potential) – Weak / Management interventions (BB – high potential) – Weak
Outcomes to Impacts	Transformative economic growth leads to poverty reduction. / Economic Growth can help meet climate goals. / Absence of exogenous shocks such as extreme natural disasters, health events / Absence of instability, fragility or conflict which entirely impedes growth. / Absence of other necessary market conditions that prohibit growth (market failures)	Policy reforms supports economic development – Strong. / Increased FDI produces transformational, inclusive, green growth – Strong. / Transformative economic growth leads to poverty reduction – Strong (evidence from Economic Development Best Buy) / Economic Growth can help meet climate goals- Medium [Evidence from Jayachandran (2022) unsustainable economic development can have dire consequences on the environment. As economies become richer and technologies advance, it will increasingly become possible to transition to greener growth paths that don’t compromise on economic gains and environmental quality. The IGC highlights developing countries can leverage rapid technological advancement to leapfrog old technologies and begin employing the latest green innovations to reduce their emissions as they grow (green growth paradigm). Renewable energy is an opportunity e.g. off-grid solar (Burgess e al. 2022) is an alternative to expensive diesel generators – dramatic declines in the cost of off-grid electricity, notably solar, have eroded the global electrification frontier whilst supporting green growth (Burgess et al. 2020)

### V. Summary Value for Money framework for preferred option (inc. measures to assess VfM)

GIG is designed to deliver a new approach to FCDO programming – reducing duplication of effort; supporting central programmes to provide more of a service to Posts and devolving leadership to countries; strengthening FCDO ability to respond to new reform opportunities; and drawing on specialist expertise (and oversight) that is only available in central teams. The project is lengthy however, Annual reviews of the existing programmes on which GIG is built are clear that longer-term support over a number of years better contributes to end outcomes and impacts given the complexity of the issues addressed. Working with the private sector and investors, it can take several months to build a pipeline, and 18-24 from deal support to deal closure. It then takes a longer period for the investment to impact on jobs and growth. It is therefore key to have long term financial commitment to build and leverage a healthy pipeline of deals to support for investment.

The effectiveness of the International Growth Centre component of GIG particularly depends on being long term, building relationships with government and using those to incubate longer term research, which is based on short term research. The value for money increases over time, as top academics are attracted by longer term research which leads to rigorous outcomes. This means the top academics accept a daily rate at a fraction of their standard market rate for shorter term technical assistance. Furthermore, Impact requires not just advisory support but also follow up through diplomacy on implementation. These processes take significant time.

The contract/agreement will have explicit review points and break clauses. Continuation beyond these will be contingent on meeting agreed performance expectations across a range of categories, and at FCDO discretion.

The flexibility of the GIG model will enable Posts to mobilise short term specialist advice quickly and respond to opportunities and interests identified in consultation with partner governments. This will have a positive secondary impact in supporting and strengthening key relationships as an important part of our development diplomacy toolkit and part of thinking and working politically. However not everything can or will be supported, and the prioritisation and quality assurance processes will aim to focus on those with the greatest potential development impact ensuring that projects contribute to truly transformational growth.

The optimal approach to VfM across components will become clearer as the programme develops. As the programme is and will be led by emerging evidence the programme will go into launch and operation with a view to redesign if necessary. The table below outlines several measures which could be used to measure and monitor value for money. These build on the VfM indicators used in other relevant FCDO programmes and have therefore been used successfully and validated through external review. The programme will also require that delivery partners put in place plans for specific beneficiary engagement and feedback mechanisms and consultation of civil society organisations representing marginalised groups to develop programming options.

Table 7. Indicative VfM indicators

Economy	Unit cost of inputs and outputs (such as average unit cost of the TA by type) / Unit costs of majority of outcomes (directly attributable only)
Efficiency	Overhead cost vs. overall programme cost / Savings through management process efficiency compared with bilateral programmes / Per unit full-time equivalents (FTEs)- Measures how many employees are required to fulfil a unit of output/outcome / Speed of response (time from agreed ToR to consultants being deployed)
Effectiveness	Number and % of TA interventions achieving intended results / Posts, partner governments and regional organisations’ satisfaction with the quality of support / Number of policy changes implemented / £ investment mobilised / No. of jobs created in more productive sectors
Equity	Number and % of interventions which improve impact of reforms on economically excluded groups / Data from scorecards records number of approved projects scoring highly on inclusion / Benefits proportionately weighted across male and female dominated sectors, and driving opportunities for women in male dominated industries / Disaggregated data collected to measure impacts on excluded groups, monitor any negative impacts / “Additionality” of driving investment into poorer and more challenging markets, of reaching/including harder to reach workers, entrepreneurs, regions and sectors (e.g. Care) / Use of consultants from partner countries

Commercial Case

The Commercial Case sets out the preferred delivery partners and further delivery details. It sets out the commercial approach for GIG, including the cost drivers for each component along with a more detailed overview of the commercial aspects of each component. It explains how VfM will be achieved when sourcing suppliers, drafting contracts and non-contract agreements, and proportionate management and oversight of suppliers in delivery. It also highlights the safeguarding responsibilities suppliers will need to uphold and the key commercial risks that can be expected from the proposed delivery arrangements. Lessons from the delivery of similar interventions have been outlined in the figure below.

Successful delivery will require commercial arrangements that support suppliers to cooperate with a variety of entities and enable support to be channelled to a range of organisations. The programme will need to provide the flexibility required to engage with private sector entities in a dynamic context. Successful programme implementation will require delivery arrangements that facilitate effective cooperation. Delivery arrangements also need to be flexible and responsive, to be able to create, identify and seize opportunities and work effectively in partnership with a range of Posts and other entities, and support flexible and adaptive management.

Preferred delivery mechanism

This section provides a high-level assessment of the potential institutional delivery routes for each component under the preferred option 4. It sets out the thinking behind the preferred delivery modalities across the various GIG components. The proposed approach to delivery is summarised in the figure below.

Figure 5. GIG approach to delivery

Component 1: GIG hub and Technical Assistance Facility (£205 million)

Preferred delivery partner – Commercial supplier to lead the consortium (joint delivery with FCDO team). This component will require a direct procurement to identify a supplier(/consortium) that will support delivery of the Hub and Technical Assistance Facility as part of a joint FCDO and commercial supplier team. This will deliver integrated activities across GIG’s themes and on a demand basis, subject to criteria and strategic alignment with GIG. Activities will be delivered at a range of scales (deep vs. targeted).

The Hub and GIG TAF will deliver part of the learning and evidence function for GIG and include monitoring, review and learning (assessing GIG’s impact, performance and VfM and provide continual learning over the period of the programme). The component would also help to drive integration across the GIG COE and wider FCDO programme portfolio. Processes for knowledge management and effective use of information for learning will be developed during the inception phase. The supplier will be expected to show how it draws on its own learning and evidence to improve intervention design. Via this learning and evidence function the supplier will be expected to remain live to emerging questions around Green and Inclusive Growth, for instance, the role of manufacturing, trading in a fragmented world, the impact of an expanding digital economy on potential growth paths, and its interventions be informed by the latest learning and evidence on these.

We propose contracting out £169m of the budget for this component to deliver the GIG hub and TAF. We anticipate there being interest from several of the large global consultancy firms to act as the lead for a consortium bid including some of those with whom we already have programmes. There will be an expectation that the lead supplier will use SMEs and encourage the use of local partners.

The balance of the budget for this component would be used for the Programme Funded Posts (£21m) and the x-HMG technical assistance (£15m). There will be a select number of programme funded technical advisory positions based at Posts and we envisage one or 2 delivery focussed roles to sit alongside the commercial supplier to ensure 1) evidence, analysis and research is at the heart of the GIG approach 2) effective coordination, consultation and engagement with the range of stakeholders – particularly posts 3) ensure we maintain the focus on results and delivery by being embedded in the delivery team. Cross-HMG expertise may include expertise from DBT, Competition and Market Authority, Met Office, Companies House and the Insolvency Service.

Rationale for the identified delivery route

The GIG hub and TA facility will be sourced competitively by contracting a supplier/s via an open procedure. There is no option to deliver through a multilateral organisation or a civil society organisation. Given the complexity of the programme and large number of stakeholders, this component will need to contract a supplier with the ability to source specialist skills and experience. However, this will be determined during the mobilisation phase. Similar interventions like the Growth Gateway have also demonstrated the effectiveness and suitability of a commercial contract, sourced through open procurement, to deliver this work.

A commercial supplier is best placed to deliver on the key requirements for this component which include:

- the need to work closely alongside the GIG FCDO team to drive coherence, collaboration and integration through the hub and the wider technical assistance both the deep and targeted offers to Post.
- the need to ensure active management of downstream partners and capability.
- the ability to source in technical expertise to work across the different thematic areas of GIG as and when required.
- The flexibility, agility and responsiveness required for the hub and TA facility to meet the demands of Posts and wider stakeholders.
- Fund manager programme delivery excellence – including across financial management, risk, commercial and downstream partner management on behalf of FCDO.
- to drive lesson learning and sharing across geographies, sectors, and delivery partners.

This delivery modality provides a tailored response to the challenges identified. It will provide significant support to teams to deliver interventions and support policy development. This will also limit the programme management and procurement burden. Under this component, the commercial entity and FCDO teams will need to find ways to work with smaller organisations/entities including CSOs. The Fund Manager should conduct a light touch supply chain analysis to identify risks (including safeguarding risks) down the delivery chain and demonstrate how performance will be managed. The programme will continue to ensure a balance of in country and international expertise and work with consortiums to build this capacity where possible. There will be an expectation that the lead supplier will use smaller partners and encourage the use of local partners. This will be assessed in supplier bids. We will consider ways to incentivise using and building local capacity, evaluating social value criteria, and potentially including defining a percentage of TA that can be delivered by the lead supplier or stating an expected proportion of work delivered by local organisations which will be determined within our Terms of Reference.

Given the level of ambition under component 1, the design team considered the use of two (instead of one) commercial suppliers to deliver this component. The final assessment was to proceed with one commercial supplier which presents better VfM and which will be better able to deliver on the COE operating model ambitions of greater coherence and coordination across the range of consortium partners, interoperability and the ability to tailor the intervention mix to the demands and context of Post. The details of this are included in Annex H and assumptions for this decision will be tested during the early market engagement activities.

In considering commercial and performance risks of a single, larger contract, a smaller contract size was considered. However, the £169m contract planned is less that the current size of the programmes under GIG 1 combined, with this expected to be topped up through Post buy-in. A smaller contract would involve significantly reducing FCDO delivery on green and inclusive growth, relative to current delivery, which is not in line with strategic ambitions and was therefore discounted. This case is conscious that there is a trade-off between the ability to deliver on these COE operating model ambitions, the ability to maintain FCDO’s current scale of delivery on GIG objectives, and commercial risks of using a single contract to tender a consortium to deliver the activities encompassed under GIG component 1 which has not been done to date. The programme prefers to take this commercial risk than not deliver COE operating model ambitions or reduce FCDO delivery on green and inclusive growth. This is informed by experience from other FCDO programmes which indicate that there are existing suppliers who have experience of delivering contracts in consortia of this size and because steps can be taken to mitigate commercial risks. The approach to mitigating these risks is set out in paragraph 196.

Additionally, a phased contract approach was considered but was discounted as it creates some incentives to front load delivery, means results frameworks can only be considered and set over shorter time frames and so disincentivising long-term approaches and interventions, as well as risking biasing bids for support that the supplier advises we accept. Commercial advice has been sought and it was raised that phased contracts can also introduce risks that suppliers have greater bargaining power to raise costs when the second phase is agreed. However, break clauses will be included within the contract to support supplier accountability, performance and VfM with results and performance being measured before proceeding to the next period. These would allow for contract termination (in addition to Standard Terms and Conditions which already allow this), and continuation would be based on sufficient demonstration of results as well as continued demand. These will also be opportunities to review scale and scale up or down as represents best VfM in which we will ensure there is explicit provision to do so (subject to budgets and FCDO approvals)

VfM for this approach

Utilising a range of experts on call down contracts within the facility limits the costs of having experts when they are not needed, whilst a core team can ensure cross learning across the GIG COE. FCDO’s EDD would have greater control and flexibility in the allocation of resources during delivery, allowing for risk adjustment in relation to financial flows and areas of operation, including scaling components up and down and phasing their delivery to allow successful initiatives to be scaled up.

The approach will seek to achieve value for money across the five E’s in FCDO’s value for money guidance:

    1. Economy: this will be achieved by pursuing a competitive route to the market which will drive down supplier costs, commercial assessment of bids and commercial criteria in the assessment of bids, and benchmarking of fees and costs.
    2. Efficiency: will be achieved through management of the supplier, best practice in the contract model to incentivise delivery and impact, including potential use of an output-based contract or payment by results. The contract manager will complete the appropriate CMCP training (expect this to be Gold).
    3. Effectiveness: through staff oversight of interventions and through the programme theory of change, which will be continually tested and adapted, when necessary, in order to ensure programme activities support policy reforms and increase firm productivity and investment; and can demonstrate public funds are being used to deliver results. Lessons learned from previous programmes will also be applied.
    4. Equity: will be achieved through KPIs which incentivise equity, a Gender and Social Inclusion Strategy to guide implementation, assigning and procuring relevant expertise on economic inclusion and equity to GIG Hub and TAF, a partnership model of implementation which emphasises engagement with representatives of economically excluded groups and drives benefits for their constituents.
    5. Cost-effectiveness: will be achieved through overall programme impacts, and monitored through monitoring agreed KPIs and the log frame. This will result in growth that is both transformative, inclusive and green.

Cost drivers and cost control

The primary cost driver will be the fees for managing the hub and TAF as well as the costs for sourcing of expertise (TA). Additional cost drivers will include the costs of setting up regional or country hubs and travel costs for programme management and monitoring. Several options will be considered in order to balance Management Costs and TA costs, including the assessment of commercial bids which may include evaluating the maximisation of the TA budget in the commercial criteria, and setting expectations in the ToR around how the budget should be split between programme management and TA. Management fees will also be made relative to the level of TA delivery and therefore if TA is scaled down for any reason the management fees paid will also be relative to that. This will also be addressed through the payment mechanism set out in our tender for example programme management may be paid on a fees and expenses basis with a minimum percentage of payment retention linked to KPIs for reporting, collaboration, timeliness of invoicing and quality of reports etc. Payment and performance management will be further developed in our Sourcing Strategy to be approved and detailed within our tender documents.

Lastly, evidence from past programme suggests significant VfM of costs to impact as MA has raised £21 of FDI for every £1 spent and expects this ratio to increase. The approach to management costs will consider and be sensitive to the fact that there is a trade-off between addressing the identified weaknesses of past approaches to centrally management programming and the costs to suppliers to address these points and will seek to maximise overall value relative to cost.

On sourcing expertise, programme delivery requires a balance of country experience, private sector and commercial experience, and development, social and environmental expertise. Increasingly, as the market for nature-positive investment develops, these skills are becoming easier to source, which may help to reduce costs. To increase programme impacts and effectiveness, support the development of a wide and diverse pool of expertise, and align with national priorities, delivery teams should include local suppliers where these are available and reflect the nationalities of the countries where the programme is operating, and this may also reduce the costs associated with sourcing international expertise. Phase I experience will support benchmarking, along with benchmarking with fees for the delivery of other FCDO programmes focused on private sector engagement.

Delivering activities under Component 1 in country will involve some modest transaction costs in terms of staff time at Post, as interventions must be fully tailored to country context; and so, Posts will need to dedicate enough resources to engage and lead conversations with country government partners to understand their priorities, whilst procurement, management, in country delivery and additional supporting technical expertise (including in-sourced implementation roles) is provided through GIG. Clear communication and guidance will be utilised to support posts during the bidding processes and to facilitate understanding of the programme’s criteria to help ensure resources are not wasted. These costs should be far smaller than, for example, the alternative of setting up and running new bilateral programmes themselves (which would include the costs of writing their own contracts and developing their own business cases) but Posts will be more involved than they typically are in a traditional Centrally Managed Programme (CMP) which have a much more central delivery model. However, despite some transaction costs for staff at Post, these should be kept significantly lower than were they to manage such programme themselves, and will be kept to a minimum. The programme will develop a feedback form to collect Post views including on time spent on the GIG throughout implementation as well as KPIs e.g. through the AR process on the level of transactions costs and whether these are acceptable or overly burdensome, and we will be prepared to revise the process if need be, keeping in mind the importance of Post leadership and active engagement in order to address the challenges identified with traditional CMPs.

Partner delivery requirements

This component will be managed by the FCDO GIG team however the commercial supplier will be expected to manage the agreements and oversight for consortium partners as well as the performance of the TA facility. The supplier will be expected to conduct any due diligence, risk management processes, grant management capacity to deliver against the terms of reference. The commercial entity and consortium will work in close collaboration with the FCDO team and operate as a joint delivery unit. The use of Programme Funded Posts will support this delivery model. In addition, a quarterly and annual reporting framework will be established by FCDO, in consultation with the supplier, and FCDO will participate in the programme oversight, management and decision-making arrangements. Further details are provided in the Management Case. The team is conscious of the challenges of managing a large TA contract but will reach out to other FCDO teams with this experience to seek best practice advice whilst taking steps to ensure our team are fully qualified to manage the contract.

Partner and supplier management

Supplier performance will be managed in line with FCDO requirements. Noting that a large commercial contract brings risks, contract models to incentivise continuous improvement and drive performance will be used, and options will include an output-based contract or payment by results. TA will have milestone payments for specific TA offers and TA may be agreed by FCDO on a case-by-case basis (using a ToR, particularly for deep offers). Noting the importance of political economy to success, an approach will be developed to test assumptions made about political economy and keep these under review during delivery, in order to adapt or scale down as necessary if they cease to hold. Poor performance will be managed through improvement plans, escalation as required, and potential termination of the contract. Key performance indicators to support effective contract management will be agreed with the supplier. There are likely to include performance based on Annual Review scores, and potential process improvement KPIs including KPIs linked to delivery at Post, working with the consortium and FCDO including on collaboration, engagement with stakeholders, speed of approval and mobilisation, ability to drive coordination and ensure coherence across the wider GIG programme and key stakeholders (primarily Posts), indicators on learning, ability to drive uptake of robust evidence analysis and research as well as financial management and forecasting, in addition to achievement of output and outcome-level KPIs. Given the COE attempts to be more responsive to Post and demand led, the programme will consider a governance board mechanism for Post to be involved in the approval of KPIs and milestones. These will be drawn out in the ToRs before we issue our tender. To drive effective delivery mechanisms we will also seek Post feedback on the above issues, as well as on the relative effectiveness of different lengths of TA support. This will be a Gold award contract. An early market engagement will be used to build competition of the tender process. FCDO will work closely with the supplier to manage the consortium partners – in particular to ensure the right balance of different partners with different technical skills, expertise and local experience.
Key commercial risks
The primary commercial risks relate to the procurement process, and the need to identify a capable supplier in a timely manner; the time to mobilise and establish the team and systems required to deliver the programme; and the performance of the contractor during implementation. Another key risk relates to potential poor performance, any need to terminate the contract early and having to run an entirely new procurement process, which would set back the delivery significantly. To mitigate these risks, flexible and alternative delivery mechanisms will be explored in the sourcing strategy to ensure continuity. Delivery chain mapping and due diligence and monitoring will be used to manage delivery risk during implementation. Details of contract management arrangements will be provided in the sourcing strategy (post business case approval).
Programme sourcing strategy and supplier terms of reference
Procuring via an open procedure is the preferred approach due to the specialist skills required and the desire to attract the widest range of bidders, who could bring those skills together in their bids. An open competition will therefore ensure the eligibility of the best equipped organisations and increase the ability of the FCDO to access the best expertise in the supplier market. Interest is expected from several general international development service providers, as well as interest from a more specialised set of service providers focused on the manufacturing, inclusion and the climate change agenda. This assumption is made from initial internal market analysis done with FCDO data.

Following business case approval, early market engagement will be held to gauge the level of interest more concretely, inform the market about the contract scope and requirements, and inform the development of the terms of reference for the contract. A draft ToR will be shared with the market for feedback. Tender evaluation criteria and weighting will be developed in conjunction with the terms of reference for this work, balancing the quality of the team, relevant experience, ability to deliver the required range of services and commercial aspects of the bid. Evaluation criteria and terms of reference will be agreed in consultation with FCDO Commercial advisers.

The size of the contract and financial management requirements may deter smaller firms from bidding in an individual capacity. However, partners will be able to join forces, enabling them to add value to each other and participate as a consortium. This would enable them to each bring their expertise and skills together in a single proposal. And means that there will be opportunities for specialised suppliers and organisations to engage through consortia or as downstream partners.

As adopted in current EDD programmes, it is expected that an output-based contract model will be used to manage supplier performance through the life of the intervention, to be confirmed in consultation with FCDO’s Commercial Delivery team. Tender evaluation criteria and weighting will be developed in conjunction with the terms of reference for this work, balancing the quality of the team, relevant experience, ability to deliver the required range of services and commercial aspects of the bid.

Key to the COE model is flexibility and the ability to scale up and down. Options to scale-up or scale-down the contract will be set out in the terms of reference with guidance from Legal on wording. The contract will also have provisions to allow for extension options (both time and value).

The intention to offer “Post Buy in” i.e. a means of combining central programme funding with funding from posts; and the potential to collaborate with other donors, means that a flexible contracting mechanism will be required. The expectation of post demand and buy-in is based on communications already held with post through regional teams – in the absence of any cross FCDO comms campaign advertising the GIG availability. The secretariat will maintain close links with Post via these regional teams, regularly offering advice, support and updates to help facilitate post ‘buy in’.

The Centre of Expertise principle of “interoperability” between suppliers/Partners will be appraised – taking account of the need to balance requisite skills and expertise with effective management and oversight. As set out in the appraisal case, GIG will support 3 main components to deliver on the theory of change.

Component 2 – The International Growth Centre (£70 overall: £40 million EDD £30 million RED)

Preferred delivery partner

The model that has proven effective to date has three key elements, all of which must be provided by the preferred delivery partner:
- Long term expertise in country, building trusted relationships with policy makers;
- Research embedded in an academic setting, a mechanism which ensures both quality and independence (importance for trust of partner governments).
- Engagement and oversight from world-class academic experts, which also contributes to credibility and trust of partners.

1. In response to demand from Posts, the GIG will also formalise and augment a responsive Policy Advice function delivering IGC-style advice via the GIG hub. This means that in addition to the above key elements two further capabilities will be designed into the model to enable the CoE to meet increasing demand from FCDO posts for more reactive policy advice to partner governments. These will be central to the COE model and build on lessons learned from the existing IGC programme:
    1. Flexible short-term response to immediate policy needs of partner governments, including where there is no current IGC country office; and
    2. Capacity to field experts across a range of policy areas.

It is expected that some of these short-term policy advisory activities will create opportunities for relevant longer term IGC research led by the academic experts. These further research opportunities are beneficial as they create a greater incentive for academic experts will take up these engagements. The delivery partner will also be expected to build and maintain close working relationships with other organisations working in related fields that are also part of the suite of COE delivery partners. In addition, the delivery partner will build relationships across other partners, particularly those in the Research and Evidence Division’s suite of growth research programmes.

Our intention is to run a competitive process to identify a lead supplier for this Component to be delivered under an Accountable Grant. The lead supplier will be charged with overall delivery against a log frame. The lead supplier may run a competition to sub-contract separate components of the IGC. For example, as with previous phases, it is expected that the Research Component will award grant financing to research projects via a commissioning board process. It was considered whether the size of the IGC component could be scaled up given its strong track record however, working with the FCDO Chief Economist, it was felt that only limited scaling is possible within the model given that advice is based on long-term research and engagement.

Lessons have been learned from the previous three phases of the IGC programme relating to the institutional structure that can meet FCDO’s needs. To date the IGC has been procured as a programme rather than as an organisation in its own right. Several posts independently made separate arrangements for work delivered by IGC through separate Accountable Grants, including an additional country office. These were not part of the centrally managed contract. Whilst this is a legitimate model given the circumstances, it will be more efficient and straightforward for all the IGC work to be managed under a single agreement in the future and we intend to do this under the GIG.

Rationale for identified delivery route

There are two delivery options for the IGC component. Either a commercial contract, tendered through open competition, or through an Accountable Grant. Each option has pros and cons. On the one hand, a commercial contract lends itself to stronger controls over the funds spent on services or works that FCDO can directly benefit from, and focused on specific outputs. An Accountable Grant, however, is suitable for activities that align with FCDO policies and benefit the public good. FCDO would not take direct ownership of the activities if the IGC was procured through a grant, and therefore the liability would lie with the grant holder. Given that the USP of the IGC that has been built over the past 15 years comes primarily from its independence, autonomy and the strong public good elements of its outputs, we conclude that an Accountable Grant would be the preferred delivery route for this component. An additional benefit from procuring through an Accountable Grant is the flexibility this provides in changing the scope/priority themes for the IGC to take forward.

Previous phases of IGC were procured through a commercial contract. This proved restrictive in enabling us to respond to new Ministerial priorities. A grant arrangement would enable FCDO to confirm its policy priority themes after the work begins, and even to change those themes during the grant period. Previously the contract’s financial limit has meant that when FCDO wishes to increase spending throughout the lifecycle in response to business needs, a contract amendment process must be completed, and this can take many months. A grant would enable us to extend the funding envelope in response to business need much more easily. Overall, a grant will provide more flexibility in the face of uncertain political and economic contexts. It is our intention to go out to competition for the Accountable Grant, ensuring all activites are grant-appropriate, and we will use the Early Market Engagement process to assess the strength of competition in the market to provide the IGC. The team is drawing on advice from the Commercial Grants Hub through this process.

VfM for this approach

Suppliers will be requested to provide detailed cost breakdowns for the proposed project deliverables. Their submissions will be evaluated against the value for money criteria of economy, efficiency, and effectiveness.
- Economy – This aspect involves assessing the fees, daily rates, overhead costs, and unit prices of specific inputs. The assessment will encompass costs related to accommodation, travel, and other expenses. Suppliers will be required to provide a breakdown of their overhead costs.
- Efficiency – This criterion will examine the number of days proposed for delivering the outputs, as well as the inclusion of recommendations aimed at improving the delivery process. Specifically, suppliers will need to outline their plans to ensure that the IGC is more responsive to partner country priorities and can scale up or down to achieve greater impact.
- Effectiveness – This aspect focuses on evaluating the elements of the proposals that could potentially improve the overall impact of the project.
- Equity is addressed throughout the lifetime of the programme and refers to how fairly benefits and costs are distributed and the ability of the programme to reach marginalised groups and address structural and system inequalities. GIG will work with some of the most disadvantaged groups in developing countries.

Salaries and costs proposed by the suppliers will be benchmarked against the current supplier and other similar FCDO programs.
Cost drivers and cost control

The costs of the country programme component will be primarily driven by the cost and location of partner country programmes and the country projects. To manage the risk of cost overruns, FCDO will be required to approve all country programmes in addition to country programme budgets.

Table 8. IGC cost drivers

Component	Key cost drivers
Research programme	Number of research projects commissioned; these costs will again be managed by requiring FCDO to approve all calls for proposals.
Responsive policy unit	Number and location of policy engagements, this will be managed through workplans with FCDO and regular meetings to monitor outturn against forecast. Monitoring procedures will also encompass an assessment of demand across country offices, enabling reallocation of budgetary resources to align with areas of highest need.
Networking and communication component	Driven by the number of events, locations of events, and the community channels adopted by the programme. Costs will be managed through the agreement of a networking and communications strategy, with large events agreed and signed by the FCDO.
Management and administration	Conditioned on the number of posts, number of days charges for each post, fee rates, monitoring and evaluation, and overheads. These costs will be managed through programme and respective fee rates which are agreed upon by FCDO and the supplier, these will be reflected in the schedule of prices in the procurement agreement. There will also be strict agreements on the number of days against all post.

Partner delivery requirements

The research outputs will be delivered through a commissioning board wholly managed by the delivery partner. The themes for the research will directly build on the shorter-term research outputs that are ongoing and carried out by the country office teams. Embedding the research bids in the preliminary research carried out at country office level is the key to ensuring policy relevance and a close relationship with policy makers. The IGC delivery partner is the interface between the country-based experts and the wider research community.

The Responsive Policy Unit is designed to respond to demand from FCDO country posts for a range of advisory activities to support economic growth and take forward reform activities in priority policy areas. This will be a significant part of FCDO’s offer to support partner governments. Demand from FCDO posts is expected to be high, estimated at 10-15 requests annually. FCDO posts will be able to buy-into the service and fund their own requests.

The IGC will also play an umbrella role in bringing frontier research and evidence, generated through RED Economic Development Programming, to policy making.

Partner and supplier management

Work plans and budgets will initially be approved every 6 to 12 months with regular monitoring of forecast budget against outturn. Monitoring procedures will also encompass an assessment of demand across country offices, enabling reallocation of budgetary resources to align with areas of highest need. Financial and fraud risk is expected to be moderate in these allocations.
Key commercial risks
Finalising the supplier for this component will be key to ensure the UK’s investment in the IGC to date is sustained and the key successes are maintained. Additional details will be provided in the sourcing strategy.
Component 3 – Partnerships for growth (£25 million)

Preferred delivery partners

We expect to enter into a number of MoU’s/Accountable Grants with a range of multilateral partners, CSO’s, academic institutions, think tanks and private sector including where skills and expertise have been established and where these facilities have been operational for several years. Under this component, FCDO will set up and manage a range of partnerships managed by the GIG FCDO team. A set of partnerships in specific technical/thematic areas would be established. These partners will have the expertise and capability to extend FCDO’s comparative advantage on GIG in specific thematic areas or geographies. This partnership approach also allows an expansion of the types of solutions and approaches available to FCDO to address the key constraints that inhibit GIG. These partnerships will complement the more flexible Technical Assistance Fund.

An initial list of likely partners is provided below in table 9. When finalising the initial set of partners under this component, the relative merits of potential partner organisations will be assessed against a range of relevant criteria listed in Table 10 below.

Table 9. Potential Partnerships for growth (GIG component 3)

Potential partner	Partnership type
World Bank	Trust Fund
UN Global Compact	MoU
UN Women	Trust Fund
Extractive Industries Transparency Initiative (EITI)	Accountable Grant
Natural Resources Governance Institute (NRGI)	Accountable Grant
Donor Committee for Enterprise Development (IFC)	Trust Fund

Table 10. Considerations to assess Partnerships

Considerations	Explanation
Alignment of Objectives	Activities of partner are focused on supporting at least one of GIG objectives. / Economic Transformation potential / Impact on the quantity of productive jobs / Inclusion Impact (including accountability to affected populations) / Ability to accelerate climate transitions
USP of partner	Partner has sufficient / Expertise / Geographical reach and economies of scale / Global leadership and support from other donors/ partner governments / that means that delivery through them offers best value for money relative to alternative routes for FCDO to achieve its objectives. / Assess whether any other partner delivers the same objectives with greater impact or lower cost? If the partner’s USP is research oriented, consider whether other organisations already produce research of a similar calibre that is publicly available that FCDO could draw on instead. Select organisations to support global public goods of highest value but avoid proliferation of similar work and entities.
Impact on UK “thought leadership” role	Does it provide a valuable forum for FCDO to input to a global conversation, and is it value add for FCDO to expend effort on shaping those conversations? If FCDO doesn’t join, are there risks of FCDO missing out on significant global discussions and does that matter? Are there significant reputational risks of not joining an initiative seen as valuable by our global allies?
Degree of impact	Work of Partner makes a meaningful global contribution to at least one of GIG objectives, and does no harm on others. / Economic Transformation potential / Impact on the quantity of productive jobs / Inclusion Impact (including accountability to affected populations) / Ability to accelerate climate transitions
An evidence-based approach	On average there is a clear, evidence-based case that the activities of the Partner offer best VfM to address the problem, relative to other potential approaches FCDO could take (i.e. the GIG scaling up work under components 1 or 2 instead)?
Track-record	Has the partner got a strong track record of delivery?
Additionality	To what degree are Partner activities already funded and will UK funding be additional rather than displace the funding of others?
Cost/ VfM	How much funding is needed to deliver on FCDO objectives for the Partnership? Are the benefits worth the cost (relative to alternative uses for the funds)?
Impact on GIG management	How much extra management capacity would adding this Partner take-up, and is that worthwhile/ the best use of FCDO staff time to drive GIG objectives?
Risks	What are the risks associated with working with this organisation? / Is it likely that FCDO will need to actively influence the direction of the Partner (in terms of objectives and/or approach to delivery), in order for Partner activities to represent strong VfM. / If influencing the direction of this partner is likely important to deliver VfM, how far does evidence suggest influencing this partner is possible? / Are there any notable risks associated with the activities of this Partner. / Are mitigating actions adequate?

To note that alignment of objectives will be a necessary criteria. Additionality will be a necessary criterion except where there is a strong case to be made on the basis of thought leadership criteria. The level of risk must be commensurate to the intended benefit (within risk appetite). The other criteria will be considered in the round. This set of criteria will be used to assess potential with future partners throughout the lifetime of the programme.

Rationale for identified delivery route

This option provides a relatively low procurement burden as it would largely build on partnerships with existing partners. It would use MoU’s and Accountable Grants to channel support to a select number of pre-agreed partners. As discussed, this model allows FCDO to work through global/regional organisations who have: unique expertise; established geographical reach that goes beyond what would be VfM to deliver through a commercial supplier; economies of scale on certain activities; or established global leadership with support from a wider pool of partners, that allows us to maximise our influence and impact.

VfM for this approach

The value for money of each partnership will be assessed on a case-by-case basis and is embedded into the appraisal criteria set about above. Depending on the type of partner, they may also be able to bring further resources to invest in GIG to drive efficiency in the long run. To ensure economy, fees will be scrutinised along with other costs and will be monitored routinely. Assurance over efficiency will be provided by tracking the performance against progress of delivery partners.

Cost drivers and cost control

This will include the costs of bringing in international expertise as well as working with international organisations many of which have high overhead, and international travel costs. Costs will be controlled through frequent review of expenditure and spend for this component. Where possible FCDO will look to share management costs with other donors and will look to promote greater coordination and coherence between initiatives. This component will look to draw on benchmarking data where possible.

Partner delivery requirements

FCDO will be supporting the work of existing organisations and partners which are responsible for delivering against the outputs and outcomes in the theory of change. Responsibility for delivery will be delegated to the partner organisation. The relevant EDD FCDO teams will participate in relevant governance arrangements, including programme boards and steering committees for the programme. The selected partners will be expected to engage with the wider GIG components and stakeholders through the relevant mechanisms set out in the management case – to drive the GIG COE approach.

Partner and supplier management

Performance will be managed through KPIs set out in MoUs and AG agreements. Clear terms of reference outlining the scope of work along with results frameworks will be agreed prior to signing any agreements. FCDO oversight of activities through steering committees and other governance arrangements, direct engagement with partners and monitoring of field activities. Quarterly and annual reporting regimes will also be established by FCDO. The policy leads/thematic leads will be the points of contact, overseen by the GIG SRO. The GIG Hub team will help manage these Partnership relationships including, for example, facilitating regular meetings and workshops to allow greater learning between partnership organisations, dissemination across broader FCDO and elsewhere (e.g. HMG, externally) as well as opportunities for shared activities which could improve VfM.

Key commercial risks

For multilateral partners the key risks relate to partners ability to flex and adapt in light of the wider contextual shifts that may occur. Setting-up the right management and governance arrangements will be important. The primary commercial risks for AG’s relate to partner capabilities. Due diligence assessments will be conducted before awarding any new grants. In addition, delivery chain mapping and due diligence and monitoring will be used to manage delivery risk during implementation. Across MoU’s and AG’s FCDO will ensure a clear set of deliverables and monitor progress routinely.

A key risk is proliferation of agreements. The team will ensure any decisions for new partnerships are considered alongside resources and management capability. The policy leads/thematic leads will be the points of contact, overseen by the GIG SRO. The GIG Hub team will help manage these Partnership relationships including, for example, facilitating regular meetings and workshops to allow greater learning between partnership organisations, dissemination across broader FCDO and elsewhere (e.g. HMG, externally) as well as opportunities for shared activities which could improve VfM. The GIG hub ways of working will be set out in the management case.
Overall VFM for delivery of intended outcomes across all 3 components

The approach will seek to achieve value for money across the five elements identified in FCDO’s value for money guidance: Economy (are we buying inputs of the appropriate quality at the right price?); Efficiency (how well are we converting inputs into outputs?); Effectiveness (how well are the outputs of an intervention having the intended effect?); Equity (how fairly are the benefits distributed, in particular amongst marginalised groups?); and Cost-effectiveness (what is the intervention’s ultimate impact on our foreign policy objectives, relative to the inputs that we or our agents invest in it?).

Economy	Will be achieved through working with the pricing and fee rates agreed under the framework.
Efficiency	Assurance over efficiency will be provided through the track record of delivery partners, which are suppliers with experience of delivering MEL services.
Effectiveness	Enhanced understanding of the theory of change will be provided through studies and assessments which seek evidence of transformational change and progress towards programme outcomes and impact.
Equity	Management oversight of efforts to ensure equity impacts will be informed by data and evidence generated for programme interventions to maximise development impacts and data to support tracking of these impacts.
Cost-effectiveness	Will be achieved through overall programme impacts, contribute to transformational, inclusive and green economic growth in order to contribute to sustainable poverty reduction and enhance climate resilience in FCDO partner countries

Cost drivers and cost control

The primary cost driver will be fees for technical assistance and fund management fees along with any other fees. Is likely to be the sourcing of expertise and associated fees. Additional cost drivers will include costs associated with travel, and programme management and monitoring costs. On technical assistance, the programme will require a range of skills including international and local expertise. Costs will be controlled through using fee rates agreed under the contract.

Partner delivery requirements

A delivery schedule of thematic studies and evaluative products will be agreed with the Supplier. A quarterly and annual reporting regime will be established by FCDO, in consultation with the supplier, and FCDO will participate in the programme oversight, management and decision-making arrangements. Further details are provided in the Management Case.

Partner and supplier management

Supplier performance will be managed in line with prevailing FCDO guidance and practice. Contract models to incentivise continuous improvement and drive performance will be considered, including an output-based contract. Poor performance will be managed through improvement plans, escalation as required, and potential termination of the contract. Contract manager will complete the appropriate CMCP training. Key performance indicators to support effective contract management will be agreed with the supplier but are likely to include performance based on Annual Review scores, financial management and forecasting, in addition to achievement of output and outcome-level KPIs.

Key commercial risks

The main commercial risks relate to the procurement process, and the need to identify a capable supplier within the timelines specified to ensure a smooth transition to mobilisation. Another key risk is the time needed to mobilise and establish the team and systems required to deliver the programme, as well as the performance of the key commercial supplier during implementation. The latter includes the need to work with all GIG stakeholders and delivery partners and suppliers. One way to mitigate this risk will be by including wording in the ToRs for each agreement across the contracts, AG’s and MOU’s which specify the need for collaboration, information sharing and the need to delivery through a portfolio approach to ensure effective coherence across the entire GIG COE (including with the MEL supplier). More broadly, the transition from existing programmes may pose a general risk of a gap in programming. The team will look to closely manage procurement timelines to help mitigate against this risk.

Overall VfM of commercial strategy for the delivery of intended outcomes

It is expected that the combination of the different delivery routes across the three GIG components will achieve VfM delivery of GIG’s intended outcomes. The rationale behind using the differentiated delivery routes is set out in the preferred delivery options section of the commercial case above. The VfM assessment of programme using the FCDO ‘4Es’ framework can be found in the Appraisal Case. To help advance VfM through delivery, the FCDO programme team will draw on FCDO Procurement PrOF guidance, guidance from the Managing Projects Authority (MPA) as well as close working with the relevant commercial advisor. Lessons and experience from previous programming will also be used to inform how best to engage the market, chape the supplier terms of reference and how to best monitor partner and supplier performance. The team will use commercial competitive processes where possible – which will increase the value for money. However, the use of MoU’s and grants will be critical to deliver on the breadth of GIG’s work. A direct award may be required in cases where there is a very small skillset or very few partners are able to deliver the work. Where there is lack of technical expertise across the market and where there is the need to partner with specific programmes/organisations (as they are the only entities that deliver the outcomes needed), we will work with commercial colleagues to ensure VfM criteria are applied.

Award and mobilisation of contract and non-contract agreements

Mobilisation and procurement will commence following business case approval. The use of different funding instruments across components means that some activities have potential to start quickly, supporting delivery of early results, while long-term arrangements (for example the commercial contract) are delivered. Each component is likely to have a different timeline for mobilisation and implementation. Component 1 will require a tender process which is expected to take approximately one year following approval of the business case. Following start-up, this component will require a substantial inception phase to ensure the governance and management arrangements are designed well to ensure interoperability, coherence and coordination across the FCDO team, PFP’s, Posts and partnerships component. The MEL work will be a subcomponent of component 1 to ensure impartiality and independence from the rest of the programme. FCDO will maintain close oversight over this work to ensure any lessons, findings and recommendations are routinely fed back into programme delivery across the whole of GIG. Baselines will be developed. A midterm review will look at progress and any implications for design and delivery for the remainder of the programme and inform the next phase.

Due diligence of suppliers

Due diligence will be undertaken prior to entering into agreements, to ensure that partner organisation policies meet FCDO safeguarding, fiduciary and commercial requirements. This will include an assessment of procurement capability, where the organisation may be required to procure goods and services, to ensure alignment with FCDO’s commercial requirements, guidelines and best practices. Due diligence will also cover the supplier’s governance structures and controls, capability to deliver and financial stability. Suppliers will also be required to undertake their own due diligence on any sub-contractors/grantees that it intends to appoint to support programme delivery, and cascade safeguarding requirements down where necessary. To ensure that this due diligence is sufficiently robust, due diligence requirements of downstream suppliers will be specified in contract and non-contract agreements.

Key terms in contracts and non-contract agreements

Following due diligence checks and appointment, suppliers will be awarded contracts or non-contract agreements that accord with prevailing FCDO guidance and practice. Contracts will be awarded that will use the standard FCDO terms and conditions. This ensures key provisions and requirements which are oriented towards incentivising performance, continuous improvement, value for money and acceptable levels of risk for FCDO. MoU’s and AG’s will be under components 2&3 will be awarded in line with FCDO’s standard template, and that meet FCDO requirements. All these agreements will include the standard key provisions and requirements to advance value for money and acceptable risk. Terms of Reference will include any bespoke clauses required for contracts, grant agreements and MoUs. These will be considered for addition into standard FCDO templates under the guidance of FCDO Commercial specialists. Additional clauses may include those relating to rules for appropriate sub-contracting/granting, use of funds for travel and expenses, cooperation with ICF annual review/results collections processes, expectations for collaboration between component suppliers and requirements for engaging with Posts and government counterparts. Additionally, a PBR or output-based contract model may be used for Components 1 to manage supplier performance through the life of the intervention. Contract models and all additional clauses will be decided in consultation with legal and commercial advisers in FCDO.

Outputs, outcomes and KPIs

Outputs and outcomes will be specified – in line with contract/grant guidance – within contracts and non-contract agreements to provide FCDO with line of sight on progress against intended outcomes. Corresponding to these outputs and outcomes, appropriate KPIs for contracts and non-contract agreements will be finalised following market engagement and agreement with the eventual suppliers. This set is likely to include KPIs related to technical delivery of output and outcome level KPIs, Annual Review scores, financial management and forecasting, information management and broader social value. These KPIs, in combination with the management processes discussed below, will be used to assess supplier performance, and advance the overall VfM of contracts, AG’s and MoUs. KPIs will facilitate the monitoring of the overall progress of GIG and assess performance against objectives.

Managing suppliers/partners and contract delivery to ensure VfM

FCDO contract management team

The contracts and non-contract agreements used in GIG will be managed by an FCDO team. The structure and responsibilities of the FCDO programme management team are discussed in the Management Case. The PRO will be a professionally accredited contract manager in line with the Government Commercial Function (GCF) Contract Management Professional Standards for Gold contracts. At a minimum, the SRO will also complete Practitioner Level training of the Contract Management Capability Programme (CMCP). FCDO Commercial Advisers will also provide support on contract and non-contract matters as required.

Supplier management processes

Standard FCDO programme management approaches will ensure supplier performance is managed effectively and ensuring ongoing value for money. GIG will also draw and learn from best practice of other programmes (e.g. Growth Gateway) with regards to effective supplier management. For example, splitting the programme into workstreams and ensuring there is a supplier counterpart assigned to each workstream. Regular workstream meetings will also be held to update on progress alongside other wider scope meetings discussing elements of programme management such as budget forecasts and risk etc. Performance will be managed through KPIs set out in contract and non-contract agreements, results frameworks agreed between FCDO suppliers and partners. FCDO oversight through steering committees and other governance arrangements, direct engagement with suppliers, and monitoring of field activities. Quarterly and annual reporting regimes will also be established by FCDO and the range of partners. This will be complemented by informal monitoring. Poor performance will be escalated to management and will be managed through improvement plans and potential termination of the contract. Further details of programme governance arrangements are provided in the Management Case.

Safeguarding responsibilities

GIG and any downstream suppliers will, (in line with FCDO requirements), ensure they have adequate safeguarding policies, procedures, and measures in place to protect beneficiaries and staff. Organisations contending to be suppliers of programme components will be required to provide their safeguarding policies and a clause will be included in contracts and non-contract agreement to ensure that safeguarding requirements, along with whistleblowing and complaint procedures, are adequate. Additionally, the capacity of partners to install, monitor and respond to safeguarding measures will be assessed as part of the due diligence checks that will take place prior to the signing of contract and non-contract agreements. Contracted suppliers will also be expected to adhere to the FCDO Supplier Code of Conduct and other standard FCDO safeguarding policies. The FCDO Programme team will draw on FCDO guidance and the expertise of safeguarding champions to ensure that best practice is followed. The FCDO programme team will ensure that they complete all mandatory safeguarding and SEAH training and fully understand their roles and responsibilities in respect to safeguarding.

Contract flexibility, amendments and extensions.

GIG will operate as a flexible programme. GIG will look to combine central funding with contributions from Post and will look to forge partnerships, respond to country level demand, and collaborate with range of partners to be effective. As a result, it will not be possible to prescribe a set of fixed activities and outputs required of all suppliers and partners from the outset. Agreements will need be agreed with sufficient built-in flexibility to enable learning, pooled funding, and scale-up and down as appropriate. Dimensions of flexibility will be set out clearly in terms of reference and the contracts/agreements across all components will contain clear, precise provisions to amend and extend (both in time and value). FCDO Legal and Commercial Advisers will be consulted for guidance on wording in both the terms of reference and contracts. In practice, contract amendments and extensions will only be considered if they clearly represent VfM, the reference and scope of the programme components remain consistent with the original procurement, and amendments can satisfy FCDO commercial rules and procedures.

Owing to the complex nature of the COE model and the focus on outputs/outcomes as a measure of success, this programme will put an understanding of the local context at the centre of delivery. Owing to the Post focussed nature of this programme, in Component 1, emphasis will be placed on strong political economy and contextual analysis of opportunities, constraints and enablers, to drive design and delivery. The programme will need to remain agile and to significantly adjust/course correct in light of the evolving context. The collection, collation and analysis of disaggregated data will be key to monitor inclusion outcomes and equity of benefits derived from the programme and propose timely course correction where necessary.

A key lesson from adaptive and flexible programming includes the need to ensure this requirement for sufficient flexibility is translated into our commercial approach and in particular, how we manage the commercial/procurement process and funding agreements with Posts. This will require enough delegated authority for the GIG FCDO programme team particularly in managing cost & time extensions, personnel changes as well as changes to milestones. A large fund will require the ability to scale up and down and be directed where the opportunity allows in a proportionate and timely manner. The nature of GIG’s work will make it critical to work in this way.

Delegated authority for a number of these decisions (including the need to increase the value of the components with additional funding from Posts and the programme, changes to budget lines, workplans, milestones and components) will sit at SRO level within the limits of HMT approvals and in close consultation with the in country-based Commercial Advisor. Any contracts will include the provision for periodic review points/break clauses to encourage supplier accountability. These will centre around the annual review, HMT approvals as well as strategic mid-term reviews. This will allow the team to ensure the programme remains on track to deliver against the log frame. Key milestones will be met to move to the next phase.

Commercial requirements under this programme will continue to need to operate flexibly and include the need to single source (with evidence) and target downstream partners to deliver select pieces of work where required. The programme will continue to encourage market growth including through existing suppliers and create opportunities (through KPI’s) to partner with local organisations.

Contract Management (Performance/Partner Management)

The programme team will develop a robust Terms of Reference (ToR’s) to guide selection and implementation of the preferred supplier. Building on the success of previous contract management, the contract awarded to the supplier will include the requirement of a performance management framework. This will include milestones and targets against Key Performance Indicators (KPI’s). These will include a combination of technical and management criteria that will also be incorporated in the workplan to assess performance against both specific programme-based indicators and process improvement indicators. In addition, this will require effective management of risks and progress against logframe results to ensure outcomes are achieved. This will be linked to a payment schedule and reporting (to ensure some form of payment by results). This will also ensure all payments are made on the basis of robust evidence of delivery and progress towards the programme’s broader objectives. This will be developed jointly by the FCDO and implementing partner. This approach will help to ensure value for money through a periodic review and assessment pf the partners performance.

Early market engagement

GIG builds on long standing development programmes. There is a strong delivery partner base, however Early Market Engagement (EME) will test the current market and look beyond existing suppliers. As part of the design, the team will conduct an initial EME to test the approach and assumptions. A second follow up event is planned after the business case is approved to generate interest and to test the market and to refresh our understanding of potential supply partners (including ability to source local content in intervention countries) as well as the constraints and challenges in delivering a programme of this scale/magnitude.

### V. Programme Funded Posts

During the programme design it was agreed that there was a critical need for FCDO expertise and capacity to support the programme at posts along with the need for FCDO to build close relationships with key stakeholders. The programme has been structured so that implementing partners are well equipped to deliver across the components. The PFP’s will support these partners to effectively support and collaborate with posts, and coordinate with other organisations.

FCDO will look to deploy approximately 12 PFP’s in advisory and some delivery positions. The majority of these positions will be based in-country (likely those countries where we agree “deep offers”) and the small number of UK based positions will most likely be housed within the commercial supplier and sit as a subcomponent within component 1. The roles of PFPs, centrally and based in-county, would cover supporting relationship management and engagement with stakeholders, overseeing programme activities and delivery, supporting posts to engage with GIG, coordinating partners, supporting coordination with other HMG programmes and driving the research, analysis and evidence sharing across the programme. Advisers in country will focus more on supporting and overseeing activities and delivery in country, supporting engagement with Post, and coordination at country level.

Experience from Manufacturing Africa’s country-based advisers demonstrates the importance of the role in overseeing coordination between Centres of Expertise activities in country, in generating deep sectoral and country-based knowledge and in providing detailed political economy and contextual analysis to ensure technical assistance is appropriate and effective. Central advisers will focus on supporting portfolio level coordination and dissemination and uptake of learning across the GIG COE and other HMG programmes. Regardless of location or focus area, all advisers will be expected to support lessons sharing and coordination. We are aware that the FCDO policy on PFPs is evolving and so the final number of positions will be assessed during programme inception in accordance with the most recent guidance. The ToR’s for these positions will be agreed with Posts. These posts will also work closely with the FCDO Senior Responsible Owner and the Programme Manager, advisers and policy leads, as well as focal points at Posts (alongside the rest of the delivery team) who will be responsible for the day-to-day management of the contract. VfM for PFPs has been indicated through prior programme experience (MA). An extensive VfM assessment for GIG PFPs has also been carried out, determining that PFPs demonstrate good VfM.

The Programme Funded Posts are not management costs. They do not manage they programme, but contribute to delivery, in complementary and additional ways to consultants and therefore rules around PFPs state they cannot be used by UK Missions for more than 10% of their time as they must remain focused on delivery of programme’s KPIs.

Financial Case

Programme Funding profile

The total value for this Programme is £300m ODA funding over 7 years (2025 – 2032); a minimum 65% ICF of this allocation will be for ICF and £7m of non-ODA funding. Proposed costs are indicative, and the budget profile may be modified during mobilisation and as we learn more about Post interest in “buying in”. We will use PCDs experience to bring down costs where possible without compromising on quality of deliverables. Budgets have not yet been agreed for the next SR period but this programme will be prioritised for funding from any EDPD allocation.

Table 11. Indicative funding profile for GIG’s £300m budget

Overview of funding flows

Funding will be allocated to programme components as follows:
- Component 1 GIG hub and Technical Assistance Facility £205million ODA + £7m non-ODA
- Component 2 International Growth Centre - £70million (£40million GIG allocation & £30million RED allocation)
- Component 3 Partnerships for Growth - £25million

Funds will flow from FCDO to Tier 1 suppliers for each programme component, and then from these suppliers to downstream Tier 2 and Tier 3 partners engaged in project delivery (Figure 6).

Figure 6: Flow of funds in GIG

Component 1: GIG Hub and Technical Assistance Facility

Funds will flow to a Tier 1 commercial supplier appointed through an open procurement. The appointed supplier will run subsequent procurements to identify partners and also:
- issue grants
- provide technical assistance and consultancy services
- source other organisations to deploy TA and expertise

Tier 2 suppliers under Component 1 will likely include consortium partners and/or sub-contractors. FCDO will conduct due diligence on the Tier 1 supplier prior to signing the contract, and the supplier will be responsible for establishing due diligence procedures, financial management and risk management systems to ensure good management of public funds and value for money for all other partners and organisations under this component. Component 1 will also deploy PFP’s to ensure technical and delivery expertise is embedded within the commercial supplier and that work closely with the wider consortia. This approach will help to drive value for money to ensure efforts to delivery outcomes and impact are prioritised and to drive delivery and coordination. TA support for GIG activities to HMG partners will also be included in this component. Whilst the MEL component will likely be sourced by the commercial supplier. The FCDO team will oversee the design and results emerging from this work, including ownership of the logframe targets and indicators.

Component 2: International Growth Centre

Funds will flow through an Accountable Grant to the selected partner. The primary partner may provide sub grants to downstream partners to deliver on the functional areas within the IGC. Partners under this component may include research and academic institutions as well as TA service providers. FCDO will conduct due diligence on the Tier 1 partner prior to signing grant agreements and ensure that these grantees have adequate policies and systems in place to manage sub-granting and ensure value for money.
Component 3: Partnerships for Growth

Funds will flow to a select number of strategic partners including multilaterals such as UN agencies, think tanks and academic organisations through a series of MoU’s and Accountable Grant agreements. Some of the tier 1 partners under this component will be organisations that convene and manage funds on behalf of other donors. These partners may issue sub-grants to delivery partners, such as consultants undertaking analysis and developing knowledge products, and service providers supporting implementation of collaborative actions. FCDO will conduct due diligence on the Tier 1 partners prior to signing agreements and ensure that the grantees have adequate policies and systems in place to manage sub-granting and ensure value for money.

Cost categories
Costs directly incurred by FCDO: The FCDO team will work with a range of organisations to deliver this programme. Delivery costs will be incurred directly by partner organisations alongside FCDO through the PFP’s. Agreements will be made in GB pound sterling. The costs incurred directly by FCDO are PFP costs, as well as staff within EDD as well as within Posts for the programme’s management, oversight, and monitoring. The Management Case provides detail on the expected FCDO staff resources required to manage GIG.
Financial aid to governments: There is no financial aid to government planned under this programme.

Pooling of funds
Country office funding: “Post Buy-in”: This programme will engage closely with Posts to maximise the programme’s impact. Approximately £60million of contributions is expected from Posts budgets.
These funds will be used to deliver activities that align with both the objectives of GIG and those of Posts. The preferred method for Post to contribute additional finance to the programme will be set out in the sourcing strategy post BC approval. The team will consider options which present the best VfM and which also consider the management burden for delivery teams in line with the FCDO PrOF Guide to Post Buy-in. This approach will follow agreed provisions for accounting for spend and results at posts.
As discussed, the value included for Post buy-in in the business case is based on communications already held with Post – in the absence of any cross FCDO comms campaign advertising the GIG availability - and we are still confident that over a 6-year period there will be at least the level of Post interest assumed in this business case. The experience of the Cities and Infrastructure and PFM Centres of Expertise has also been to receive higher levels of interests from Post to buy into central offers than has been anticipated. However, it is worth nothing that the TAF could operate on the EDPD budget alone (subject to the Spending Review) in the case that Post demand to “buy-in” did not materialise, so long as there was the agreement and engagement of Post and that represents VfM and fits within the Post country strategy. The contract will be clear that flexibility to scale up and down is necessary. This is therefore not perceived as an undue risk to programme delivery or VfM.

Cost profile and affordability
Budget timeframe and obtaining budget from future Spending Reviews: The concept note for GIG was approved in May 2024 for a £300m programme with up to seven years of spend. The longer programme cycle reflects evidence of the time required to procure, implement and achieve impact in the growth sector. To ensure that Ministers have oversight of spend and strategy over this length of programme cycle, financial approvals will be set out in line with the HMT spending review limits and timeline. This Business Case seeks approval for a seven-year funding envelop of £300 million as per the budget breakdown above.

Budget classification

Funding for GIG will come from the budgets of EDD, RED and Posts and will be classified as a combination of Official Development Assistance (ODA), non-ODA and International Climate Finance (ICF). The programme budget will be made up of both RDEL and CDEL. FCDO funding will be used by the suppliers to provide goods and services for technical assistance, research, monitoring and evaluation, knowledge dissemination and stakeholder engagement, communications, and management. The asset delivered by the CDEL is all research.

Estimated budget and cost profile

The cost profile is set out in Table 12. The following assumptions have been made:
- The Business Case is fully approved by Ministers and HMT in 2024 and runs for a period of seven years.
- Timeframe divided into two tranches (as discussed above), with approval for a second tranche secured in 2026-27 via a Business Case addendum.
- Procurement of contracts for Components 1 will start once the Business Case is approved and will take up to 12 months, followed by a one-year inception period. There is thus limited spend envisaged in 25/26.
- Recruitment for the programme funded posts envisaged will start once the Business Case is approved. Recruitment could take up to 6 months, potentially longer if successful candidates come from HMG departments outside of the FCDO (though we note that xHMG recruitment will be less likely in the current workforce climate).
- Negotiation on non-contract agreements for components 2& 3 will start when the Business Case is approved, with mobilisation of agreements expected to take three to six months.

Table 12. Provisional cost profile

£m	25/26	26/27	27/28	28/29	29/30	30/31	31/32	Total
RDEL	3.8	23.0	46.0	48.0	50.0	49.4	26.8	247
CDEL	0	5.1	10.4	10.4	10.6	10.8	5.7	53
of Which EDD CDEL	0.0	2.2	4.5	4.5	4.5	4.6	2.4	22.7
of Which RED CDEL	0.00	2.9	5.9	5.9	6.1	6.2	3.3	30.3
Total ODA	3.8	28.1	56.4	58.4	60.6	60.2	32.5	300
Non-ODA	0	0.7	1.4	1.4	1.4	1.4	0.7	7

As discussed in the Management Case, the Monitoring Learning and Evaluation component is estimated to be between 3-5% budget including for a mid-term review and any buy-in from GIG to a COE wide evaluation. This represents a significant commitment to support active, evidence-based management based on continuous learning, as befits this new approach to delivering centrally managed programming.

Rationale for budget and cost profile

The existing programmes that GIG will supersede have an FCDO baseline ODA allocation in FY2024/25 of £72,9m (£32.4m RDEL, 40.5m CDEL) (including finance at risk, co-funding from RED for the IGC, and additional funding amounting to £7.9m absorbed in 23/24 by Manufacturing Africa and Growth Gateway for International Climate Finance spend and from Post which we are using as indicative of future demand for Post Buy in).  GIG will deploy both ODA RDEL and CDEL.

Table 13. Baseline Programme budget 24/25

Baseline Programme budget 24/25	RDEL £m	CDEL £m
Work and Opportunities for Women	1.9	0
Manufacturing Africa	11 (including 1.3 to support programme funded advisers)	30
International Growth Centre (including budget contributed by Research and Evidence Division)	3.5	10.5 (including 6 co-funding from RED)
Post funded Accountable Grants with IGC (annual average)	2	0
Growth Gateway	7.9	0
Post buy in transfers received by GG and MA (23/24 level used as indicative number)	3	0
Responsible Business programming	3	0

The non-ODA allocation in 2023/24 was £2.3m (with an additional non-ODA amount of £530k received through “post buy-in”).  While the business case(s) ceiling has been set to absorb similar allocations in subsequent years, implementing modalities will be designed to flex according to available resources. As mentioned above, the programme has significant capacity to scale up and scale down as necessary, the programme can therefore also remain operational in the absence of non-ODA funding. However, without non-ODA funding there will be fewer opportunities to identify and support synergies with commercial opportunities in the UK.

A key element of the COE model is that Posts will co-finance GIG by ‘buying-in’, and this will be a critical element of demonstrating success. To allow the COE to achieve its full impact through allowing Posts to “buy in” to GIG using the GIG Business Case and contract12, we propose to build in flexibility by setting contract financial ceilings at a level that exceeds the expected central programme budget. This approach will also retain flexibility should there be a return to 0.7% ODA spending in future Spending Reviews.

Based on prior experience of allowing post buy in through Growth Gateway and Manufacturing Africa, and on conversations with post about appetite to buy in to the COE the main motivations for buy in would be: access to UK-centred expertise and knowledge (e.g. through COE partnerships), access to UK investment expertise and networks, ability to use existing contract to provide targeted technical assistance in the absence of post business cases, ability to blend ODA and non-ODA funding to promote increased UK impact. For 24/25 Manufacturing Africa has confirmed £6m post buy in and initial interest suggests that Growth Gateway will receive over £5.6m. The anticipated demand by posts is therefore up to £15m per annum across the life of the contract.

These indicative figures will be refined at the inception phase. A clear learning will be the need to ensure flexibility within the business case and funding agreements to scale up and scale down particularly between components. Funds used in this programme will be ODA-eligible RDEL (resources funds) and CDEL (capital funds). Funding for this will be considered as part of the SR work and it will be prioritised from any EDPD allocation. Approval will be sought from His Majesty’s treasury (HMT) for costs beyond the current spending review. The programme will also deploy £7m in non-ODA.

Financial management, monitoring and reporting arrangements
#### Payment arrangements and triggers

As laid out in the Commercial Case, funding will be provided via a mixture of contracts, grants and MoU’s. Payments made in accordance with contracts will be based on milestones agreed within the terms of the service contract. Grant funding will be provided with no expectation of the supplier making a financial return, with eligible costs and a schedule of payments being outlined in the grant agreement.

Payment triggers will be defined and agreed as part of the contracts and non-contract agreements with selected suppliers. By default, programme funding will be paid to suppliers in arrears on a quarterly basis. If the supplier makes an exceptional request for an advance payment this will be considered on a case-by-case basis to ensure that it is not in ‘advance of need’ and represents good value for money. Payment claims from the supplier will be checked by FCDO programme team, and funds will only be released if sufficient evidence is provided. Disbursement requests will detail the funding needs, cash balance and liquidity position to avoid payment being made in advance of need. In accordance with any applicable terms in the contract or non-contract agreements, payment may be withheld in instances of poor performance.
#### Financial reporting and asset management

As is standard practice for FCDO ODA programming, spend for GIG will be monitored in line with the payment schedules agreed with suppliers using the established and robust programme management processes used within FCDO. A quarterly and annual financial reporting regime will be established by FCDO, in consultation with the suppliers. Partners will report regularly to FCDO to account for how funds are being used. Tier 1 suppliers will need to provide audited financial reports, that separately identify FCDO funding, disbursements, and unspent financial resources.

Payments will be made through the FCDO payment system, so that they can only be made to registered suppliers. All forecast and actual payments will be recorded in AMP/HERA so that progress can be monitored and payments to the programme can be easily separated out. FCDO accounts will be monitored through audits.

Assessment of financial risk and fraud

FCDO has a zero-tolerance policy towards fraud and corruption, money laundering and the financing of terrorism. Delivery partners must take appropriate measures to prevent fraud and corruption in connection with the use of FCDO funding. This means adopting appropriate fiduciary and administrative practices and institutional arrangements to ensure that the funding from FCDO is used only for the purpose for which it was given.

FCDO is committed to the international fight against terrorism, and in particular, against the financing of terrorism. Delivery partners must comply with appropriate policies, procedures and controls such as: compliance with applicable national laws and regulations for anti-money laundering and combating the financing of terrorism; a written policy on anti-money laundering and combating financing of terrorism policy; appointment of an anti-money laundering and combating financing of terrorism officer; due diligence requirements; record keeping reporting of suspicious transactions; anti-money laundering and combating financing of terrorism training for all their staff.

Programme funding for contracts and grants will be paid in arrears, or under exceptional circumstances in advance, to ensure that disbursements are based on demonstrated need and avoid the build-up of unspent cash balances. Financial reporting and transparency requirements, as well as rigorous due diligence and auditing will help to mitigate the risk of corruption and fraud in the partnership and grants managed by suppliers. Regular monitoring will also help to identify risks and facilitate early corrective action. All beneficiaries of the programme will apply the standards and best practices required by FCDO. The FCDO’s requirements will be codified in agreements and contracts.

The overall financial and fraud risk is assessed to be Moderate, with the following identified risks:

- Risk relating to the uncertainty of funding owing to GNI/0.7 commitments and the economic climate in the UK may mean further reduction to funding. The team will aim to stay on top of developments relating to the wider FCDO budget envelope through finance colleagues and senior management.
- Risk of supplier/partner fraud in procurement, leading to misuse of funds is assessed to be Minor. Due diligence and monitoring reduce the risk of fraud in procurement of goods and services in the programme. Suppliers/partners will be encouraged to report to FCDO any instances of fraud or potential fraud, in part to demonstrate that their monitoring systems are working.
- Fraud and misuse of funds by Government is assessed to be Minor, as no funding is expected to flow directly to government.
- The risk of underspend and/or overspend relating to forecasting and spend has been assessed as Moderate. The FCDO team will pay invoices on the basis of need and in some cases in advance where necessary. Any delays in activities due to unforeseen event will impact FCDO’s payment schedule directly. Forecasting will be varied in the first year of the programming owing to start up activities but should be more predictable as the programme matures.

If fraud is detected, FCDO will require full remedial action including repayment in full if the fraud involves diversion of UK funds. Continued disbursement of funds will be contingent on adequate financial oversight mechanisms.

Financial performance will be monitored through annual reviews and by financial audits to determine the accounting standards and practices put in place. Spot checks for FCDO owned assets and financial spot checks will be undertaken as appropriate. FCDO will also consider undertaking full delivery mappings to be clear on funding flows and where the weaknesses lie.

To mitigate on fiduciary and fraud risks; (a) an independent project audit will be commissioned annually, (b) the tier 1 partners will be expected to conduct routine spot checks, (c) risk and assurance checks on all downstream partners, (d) expenditure will be tracked, invoices rigorously scrutinised against activity reports, and (d) regular monitoring will be undertaken to ensure quality of delivery of activities. The Fund Manager risk and assurance team or an independent auditor will carry out additional spot checks and risk assessments of partners before contracting, during implementation and a final audit on all downstream partners at the end of the project. Finance and progress reports will be signed off by FCDO. Tier 1 partners will provide FCDO with a summary of annual audited statements and due diligence assessments updated on a quarterly basis. These will include details on weaknesses identified in the internal controls, mitigation measures, and progress in implementing audit recommendations.

Monitoring, reporting & accounting for funds

The Programme Team will ensure a robust financial monitoring and will consider output-based payments and payment by results for this programme. Fees and expenses will largely be input based. A performance framework, milestones and linked payment values will be developed and agreed during the inception phases with partners and on a quarterly basis. Metrics proposed in the appraisal case will be used to assess VFM performance. The tier 1 partners will oversee finances and have accountability for spend by downstream partners. FCDO will ensure adequate controls are in place and that these are replicated in downstream partner arrangements. The Programme team will be given delegated authority to vire funds between different components of the overall business case. The Director will sign off on any decision to shift focus between outputs and or components and approve the submission to HMT/MAG to authorise funding beyond the HMT spending period.

Asset management

All partners will be expected to develop and maintain an asset register of all items purchased to through programme funds (including for downstream partners). FCDO will carry out activity and asset spot checks least once a year during the project duration.

Management Case

The Management Case provides an overview of how EDD will deliver and oversee GIG to ensure it performs to a high quality, achieves VfM and manages risks within appetites (governance and management arrangements). It sets out a risk appetite statement which covers each of FCDO’s seven risk categories and summarises with an overall appetite. An initial indicative logframe and MEL approach is included specifying what success looks like and how we will know we have achieved it. The logframe will be reviewed and updated in the inception phase.

Key Structures

The Economic Development Centres of Expertise and Coordination

1. The Economic Development COEs reflect a step change in how FCDO designs and delivers economic development programming. A core element of the new approach is that central programmes, such as GIG COE, are providing a tailored service to Posts and delivering programmes that directly support country priorities.
2. All the Economic COE along with other relevant parties such as Centre for Delivery and xHMG interlocutors are members of a COE working group overseen by EDPD Strategy team, which discusses and works through working level issues and feeds up to the overarching COE Steering Board. To mitigate the challenge of five COEs which sit in five different FCDO departments all with their own reporting lines, the Investment Partnerships Steering Board at Director level will be the governing body that outlines priorities and ensures coherence across the full COE system.

The majority of support provided by different COEs is distinct and has distinct objectives. However, there are some potential areas of overlap, particularly between the GIG COE and the Trade COE on support provided to firms who export; and between the GIG COE and Partnering for Accelerated Climate Transition (PACT) programme for example around support for partner country growth strategies which entail climate transition; or to firms working in green sectors. In practice in some of these areas it will not always be possible to neatly separate partners’ requests for policy advice and TA into our different COE and we will put in place clear agreed processes and strong communications links to ensure there is no duplication or conflicting support provided, or any confusion at Post.

Annex C sets out in detail the different areas of responsibility of each COE, potential areas of overlap, and sets out how GIG COE will interact with other COEs and other centrally managed programmes managed by Research and Evidence Division and the Energy, Climate and Environment Division (in particular the PACT programme). The GIG design team have worked closely with all relevant teams to minimise overlap in design and develop processes to mitigate risks of duplication in delivery, including through shared governance arrangements (e.g. including Trade COE SRO on GIG Steering Board).

Figure 7 below shows the process through which a request from Post would go, in a situation where the request could potentially be supported by more than one COE/CMP. As standard practice Post will reach out to the COE Secretariat with requests for support, the Secretariat who will identify overlap with the scope of other COEs, or other HMG programmes, at this initial point of contact. The Secretariat will then channel the request to the relevant COE or HMG programme(s) and put the relevant leads in touch to coordinate on responding to the request. If Post has a pre-existing relationship and opts to make a request directly to a specific COE it will be the responsibility of that COE to bring in other relevant COE for discussion, and ultimately the responsibility of Post to decide which COE offer best fits with its own strategy in country. Any disagreements or divergence from the agreed process would be addressed up by the Governance structures in place - the Investment Partnerships Steering Board and through having other COE sit on each other’s governance oversight boards.

Figure 7. Coordination process across Economic Development CoEs

The GIG Centre of Expertise (GIG COE)

The GIG COE will build on the successes of current programmes and is structured based on experiences from other FCDO-led centrally managed programmes, integrating in-house expertise into a more streamlined and joined up approach to ensure more impactful support. The full package of GIG COE services will encompass all activities set out under this BC (GIG), alongside those of the existing CASA and Land Facility programmes.

The overarching GIG COE will be overseen by a Steering Board (SB) – composed of DDs (EDD, GFALD), GIG SRO, country representatives, senior SDA, Trade COE SRO[72]. The SB will provide senior oversight to the GIG COE and sign-off the criteria that will be applied when selecting interventions and partnerships. It will also aim to support coherence and reduce duplication between the work of GIG with other COE or Post interventions. There are legitimate wider perspectives and enabling growth factors relevant to the BCs objectives, notably the other Economic COE and PACT as well as others. The Steering Board will meet quarterly to drive coherence, review progress and help shape strategic priorities as well as engagement with Ministers. There will be a standing agenda to scrutinise performance against the cross-cutting objectives (inclusion, climate, jobs), including periodic review of the balance of impact across the portfolio, while allowing space for evolving discussions. The process to deliver coordination across programmes for impact will be developed further during inception. To streamline governance for the Post buy-in process, the governance structure will include country representatives sitting in the GIG steering board.
[72] The Trade COE is the COE with most potential for overlap with GIG activities (GIG support to exporting firms). Sitting on each others governance boards aims to improve coordination.

An Advisory Challenge Board (ACB) of external/independent experts will critically appraise GIG COE performance and decision making, ensuring evidence, including cutting edge/emerging evidence, is effectively shaping decision making. The ACB will be composed of independent experts/academics including civil society selected for expertise in economic transformation, inclusion, green growth. It is envisaged that the ACB would meet twice yearly, with Secretariat support provided by EDD analysts.

In countries in which GIG COE delivers ‘deep’, multi-year offers, a system of Country Oversight Committees (COC) will be created. We would anticipate such committees to cover all economic development COE operations in country to ensure coherence. This is in line with governance plans set out in other economic development COE BCs. The COCs will be co-chaired with the Post lead, and we anticipate a six-monthly review of progress, including identifying any key learning, issues or risks that require action. The country lead for the commercial delivery partner would also join this Committee.

Figure 8. GIG COE Governance structure

GIG COE Steering Board
Country Oversight Committee (Post A)
Country Oversight Committee (Post B)
Country Oversight Committee (Post C) etc.
GIG COE Evidence/challenge advisory board

The Centre for Green and Inclusive Growth (GIG)

From the “GIG Hub”, the GIG working level team (set out in the resources section below), will oversee program implementation, appraisal and approval of country requests, management of day-to-day activities, evidence challenge function (to drive use of latest evidence across interventions), communications and working in close coordination with Posts and as part of a hybrid FCDO-Supplier team. This team will be responsible not only for GIG, but also for coordination and leadership across the broader GIG COE.

Figure 9. GIG Governance structure

EDPD Governance / CoE Governance

Other CoEs
GIG CoE Steering board – DD, SRO, Country reps
Strategic guidance, sign off criteria

# GIG CoE
Posts
Oversight in country, concept, demand generation

GIG BC: Working level team (SRO, PM, advisers, thematic/policy leads,)
(Approval of country requests, programme implementation, including joint delivery of GIG Hub)

# CASApproval of country requests, A

Aligned programmes [e.g. RED programmes, other HMG services, other regional]
# Land

A
GIG Hub, TAF
B
International Growth Centre
C
Partnerships for Growth

Approval process for technical assistance under component 1

The GIG team will make available to post a set of guidance resources to make sure expectations are clear. This will include an outline of the process to bid for support and the criteria on which bids will be assessed including the appraisal process to determine the bids impact on transformational economic growth. This pack will make clear that not all requests for support will be approved to avoid instances of commitments being made by post before approval is granted and to minimise any time spent by post on submitting bids and concept notes that are unlikely to receive approval. Posts will be encouraged to have an introductory call with the GIG Secretariat or relevant COE before starting the request process, to discuss and ensure aligned expectations. This will also help identify early on if support from more than one COE or FCDO programme may be relevant, so these can coordinate.

The steps below outline the anticipated process for mobilising support from GIG under component 1. This provides more detail to Figure 7 showing how GIG will co-ordinate with other COE. This process maximises the chances that good technical advice is implemented, matches what is needed, arrives at the right time and is delivered by the best suited organisations.

Step 1: Bid for support. Requests for support from GIG will be made by colleagues at Post, through a short concept note, this will ordinarily be through the COE Secretariat within the EDPD Strategy team which will serve as the entry point for all economic development COEs. However, where colleagues at Post are already actively working with GIG COE, for example where there is a resident GIG adviser, they may approach GIG team directly and the concept note would be worked up jointly.

Step 2: Concept Note. Post will develop a concept note, setting out the support required, the rationale for the work, the objectives, results and alignment with Post business plan priorities. Where appropriate, GIG advisers will support development of the CN, though it will be owned by Post. This intends to avoid posts with less human resource or experience to write an effective concept note missing out on support where such support would constitute VfM.

Step 3: Co-ordination. The GIG team will engage directly with Post to ensure the rationale for, and scope of the request is fully understood. An initial screening will identify whether the request falls within GIG’s scope, including whether the requisite expertise is available/can be contracted through the GIG TAF, or should be passed on elsewhere in FCDO. The request will also be appraised to determine what impact the support will have on economic transformation as well as the GIG’s wider developmental objectives. Where the request for support may be relevant to more than one COE, the Secretariat or the GIG team would share with other relevant COEs for views and a discussion on division of labour.

Step 4: GIG (or other COE) sets out .potential support which could be provided to Post, whether through the Commercial supplier or the IGC.

Step 5: Post and COE work together to refine the CN request for support, and where more than one COE proposes an intervention, Post decides which offer of support is most appropriate to fit with the context and Post strategy for the country.

Step 6: Appraisal. FCDO staff in the GIG Hub team will appraise CNs against the criteria laid out below to assess the relative value for money (VfM) of Post bids for GIG COE TA support. As mentioned, a Development Impact Scorecard approach will be developed to assess the “Expected impact” criteria, in terms of contribution to different GIG objectives. Careful consideration will be given to handling trade-offs between the three core impact objectives (transformation, inclusion, climate). As mentioned, we will seek impact at portfolio level and will not require all interventions to support all objectives. However where, for example, a bid scores very highly on transformation potential but weakly on inclusion and/or climate, the relevant experts within GIG will be deployed to seek opportunities to strengthen impact in these areas, where that can be done while retaining the VfM of the intervention.

If the decision is that GIG support is best placed delivered by the IGC the approach to appraising this is discussed below in paragraph 300.

Agreeing country-based interventions between Post and Centre – we will develop service level agreements signed by DD from the relevant COE’s department and HOM, setting out how Post strategy aligns with broad COE offer plus final individual concept notes signed by HOMs.

Table 14. Proposed criteria for technical assistance

Criteria	Considerations	Explanation
Feasibility / (is it possible?)	Post capacity and track record	Does the Post have the capacity to develop ToR and support implementation? Is there a named colleague who will be responsible for this intervention? Has the concept note been approved by the Head of Mission? Does the country/ regional organisation have a track record of achieving results in the area? Have these results been sustained? If working with partner governments does Post have existing relationships with senior government champion?
	Risks	What are the risks associated with working in/ with this country or organisation? Risks in the particular sector? Are mitigating actions adequate?
	Political economy	Does analysis suggest the political economy is conducive to success? Will it achieve sufficient political support/traction? Is it in line with country government priorities? Is there evidence of political will?
Strategic fit / (is it the right thing to do?)	Diagnostic evidence	Is there a clear, evidence-based case for intervention in this area? / Good underpinning evidence for the project, clear understanding of gaps, risks and strategies to address them, with high potential for results. A good M&E approach is proposed, or one may be developed if not available now.
	Post country plan	The project is highly aligned to regional/national/sub-national priorities and needs and aligns (and does not conflict) with Post strategy and priorities
	Compatibility with wider UK/FCDO agenda	Is the country a priority for UK development or other support? Is the country situated in a priority region?
	Accountability	How will accountability to ultimate beneficiaries be ensured? Is there credible evidence of responding to identified need?
	UK comparative advantage/value add	Does the country or organisation have enough support from others? Is there a gap? Would UK support add value? Does the UK have a comparative advantage?
Expected impact / (will it work?)	Economic Transformation potential	Does the evidence support this intervention as likely to deliver high potential for economic transformation (either directly or indirectly by supporting transformation through exports, import substitution, or facilitative services)?
	Impact on Jobs	What is the impact of this intervention on the quantity and productivity of employment?
	Inclusion impact	Is there clear evidence of impact on inclusion? What else needs to happen to ensure this is realised?
	Ability to accelerate climate transitions	Will the intervention support appropriate climate transitions in the country, in line with country’s own NDP?
	Sustainability	Is there a credible exit plan? Does anything need to happen following this intervention to achieve impact? Who will follow up recommendations? Can Post/ partner government identify who will provide follow-on support including on implementation; this may involve collaboration with multilaterals and other actors, or further bilateral work. There will need to be indication of commitment to this follow up.
Coherence with other work	Is there sufficient value-add?	Looking at who else operates in this space in country, is there sufficient value-add relative to the work of others? E.g. For countries where UKPACT or other COE work there should be an explicit discussion of programme focus to avoid overlap.
	Complementarity with other work	Will this intervention complement the work being done by others?
Delivery and VfM	Can GIG source the right expertise?	Is the right expertise to deliver on this request, to a high enough quality, available to GIG?
	VfM	How much resource will it take to deliver against this request relative to its impact? / Can GIG effectively cost the proposed intervention using a menu of delivery options, without having to discuss budget with delivery partners?

Do no harm	N/A	Proceed / Stop	Proceed – The project does not present risk of harm to people or the environment as per PrOF guidance. / Stop – The project presents high risk of harm to people or the environment as per PrOF guidance.
Security management	N/A	Proceed / Stop	To be used for projects proposed in areas with security risks. If No, the project does not proceed unless an alternative suitable partner is identified, at which point screening should recommence. / Not applicable – the project is not delivering in an area with security risks; this criterion is not applied. / Proceed – The project is within HMG security risk in country and the proposed delivery partner has experience working in the location, has appropriate duty of care, evacuation and security management policies, and all staff are trained appropriately. / Stop – The project is not within HMG security risk in country and/or proposed delivery partner does not have appropriate experience to deliver in the project location and/or lacks appropriate security management policies and procedures and/or staff are insufficiently trained.

Including an assessment of opportunities, constraints and enablers, and including political economy assessment and a climate risk assessment, as part of the appraisal of interventions also aims to reduce risks of “optimism bias” in the concept notes submitted by Post. This will be further supported by the GIG Hub drawing on the experience of GIG delivery partners and the experience of in country and regional programme funded posts when assessing the likelihood of a proposal being successful. The Hub will also refer to relevant diagnostics, including FCDO’s own inclusive growth diagnostic where available, and research to assess the likelihood of the intervention in supporting desired outcomes. Critical assessments of tractability will be incentivised by implementing payment by results to the commercial supplier, and by the value the IGC places on its strong reputation. GIG will only act where it feels there is sufficient evidence of the necessary conditions being in place that traction is likely. Lastly, it is expected that the time and resource requirements made of Post to support implementation related to step 8, and in some cases Post’s financial buy-in, would also limit optimism bias in requests.

As discussed, the GIG will seek to deliver both deep and targeted offers, given the relative merits of each. GIG expects TA funds to be split ~70% for deep offers and ~30% for targeted. This is based on experience from existing GIG programmes of the demand for and cost of deep and targeted offers. For GIG phase 1, the average deep offer cost ~£1m per year while each targeted intervention was ~£400k in total. The significantly lower cost of targeted pieces of work means that 30% of budget should allow GIG to deliver against its responsive, demand led functions and capitalise opportunities where a small amount of financial support can have notable impact, while retaining the majority of the budget to deliver long-term engagements which are necessary for long-term change. On this basis, we therefore expect to be able to deliver ~30 multi-year deep offers total (depending on how many years interventions operate for) and ~21 targeted offers per year.[73]
[73] This is assuming that 5 years of active delivery noting an inception stage and time to set-up activities.
The ratio of deep to targeted will be harder to control for the IGC given that much of its work relies on a deep level of academic expertise and it will only respond to targeted requests where it has the requisite capability.

To ensure a more strategic approach to decision making, VfM, and to minimise burden on staff time, the FCDO GIG team will open bi-annual windows for bids from Posts for targeted offers, rather than assessing bids on an ongoing, rolling basis. These windows will be accompanied by Q&A engagement calls with Posts. If a decision is made not to support the proposal, the SRO or PRO will notify the colleague at Post with the rationale, including the completed scoring template. If a decision is made to support it, the FCDO Team will contact the commercial provider to discuss the concept note. For deep offers, bids will be sought early in the programme to determine the majority of our deep offer Partner countries. It is possible some small portion will be held back to run one further bidding round the following year in order to capture the highest impact opportunities.

Step 7: Terms of Reference. The GIG FCDO team, Post leads and commercial provider will collaborate to produce a Terms of Reference for the work. This will be proportionate, with less detail and lighter touch approvals required for lower value support. The ToR will set out results to be achieved, budget and milestones. A ‘double tick’ system will be implemented with TORs only finalised once both Post lead and the relevant GIG SRO approve it.

Step 8: Implementation. Commercial supplier will mobilise support. During implementation, colleagues at Post will support on programme oversight in contact with relevant central/Programme Funded adviser.

Step 9: Completion. Post will be responsible for drafting a completion note on completion of the work, outlining results achieved against plan, lessons learnt, and how any recommendations/next steps will be taken forward. These notes will inform GIG Annual Reviews.

Discussion on management of the commercial supplier has already been provided under the Commercial Case.

Management of Component 2: IGC

The IGC component is managed jointly by FCDO staff in the GIG Hub from both EDD and RED. Following Step 5 above, if GIG support is determined to be best provided through the IGC, the IGC team in the GIG Hub will appraise it.

In addition to the criteria set out in Table 14 above, proposals submitted to IGC will be further evaluated to ensure they deliver the greatest value and align with IGC's comparative advantages. This assessment will consider factors such as the presence of IGC country experts in the relevant region and the existence of previous IGC work in the requested themes. Moreover, the evaluation process will take into account potential reputational risks, selecting activities that maintain incentives for academics to collaborate with IGC and preserve IGC's standing as an impartial entity among policymakers.

Processing the requests requires economics expertise and experience in political economy of country contexts. It also requires excellent coordination skills to reach out to experts across FCDO and among the academic community. The most experienced academic experts are incentivised by the prospect of the advice leading to or complementing longer term research and publication. The GIG hub will maintain a close relationship with the IGC staff to take these requests forward efficiently. The higher cost internally of processing the requests by a dedicated team will ensure FCDO posts get their requested inputs faster, and FCDO has tighter control over the content and quality of the requests. The coordination function in the GIG Hub will ensure requests are strategically aligned, coordinated with relevant parts of FCDO (EED, RED), and properly risk managed. This will increase the transformational impact of those requests that are taken forward.

Management of component 3: Partnerships

Programmatically, the partnerships will be managed by the team of programme managers in the GIG Hub, and under the oversight of the GIG SRO. The GIG M&E adviser and Climate and Inclusion advisers would also have responsibility for providing their expertise into our relationship with the partnership. Strategically, each Partnership will each be led by a specific FCDO adviser who also leads on relevant policy outside of the GIG (e.g. Jobs, Critical Minerals, Responsible Business etc). The Advisers will be the first point of contact for the Partnership on issues of substance, responsible for monitoring delivery, representing FCDO on Governance boards and at Steering meetings, and for providing substantive engagement and e.g. scrutinizing reports, comments on activities, policies and other documents, for reviewing review data and outputs, and taking a strategic approach to the management of the partnership.

Proposals for Partnership agreements are expected to come from within EDD policy teams who will be asked to put together a concept note setting out the rationale for funding that particular partner. These proposals will be assessed against the criteria set out in Table 11 in the Commercial Case above. If a proposal is successful the policy team/adviser in question will liaise with the Partner to draw up the relevant MOU, grant agreement with clear TOR setting out results to be achieved, budget and milestones.

Relationships with commercial suppliers and partners

All delivery partners will produce annual fully costed workplans that set out their priority objectives and activities. Each workplan will detail how the partner will coordinate with other GIG, COEs or HMG programme partners, updates to the ToC, private sector engagement strategy, or other delivery plans. GIG and the delivery partners will consolidate workplans into short country specific workplans for posts’ review and approval in each country.

All delivery partners will submit the following reports to the programme team. The programme team will hold delivery partners accountable based on these reports and associated discussions.
- An annual progress and financial report, which will cover the performance of the project’s activities and the results achieved against the project’s annual workplan and results framework. The reported results will be quality assured by the programme team and MEL commercial supplier and input into the programme logframe. An independently audited financial report will be provided for each 12-month period and discussed in-depth and approved by the SRO.
- Quarterly progress reports, which will provide an overview of activities that occurred that quarter, financial expenditure, and planned activities for the next quarter. Each report will be discussed during an in-depth quarterly meeting and approved by the SRO.
- Reporting schedules will be agreed with partners based on an overall reporting plan for GIG to ensure partners’ reporting is synchronised - the programme team will develop this post-Ministerial approval of this business case. This will aim to synchronise partners’ annual reports so all relevant information is available to inform GIG’s annual reviews, and smooth the submission of quarterly partner reports to reduce burden on the programme team.
Annual and quarterly reporting will be supplemented by regular monthly meetings with each partner. These meetings will be attended by the SRO, PRO, and other programme team members. They will allow GIG to stay abreast of each projects’ delivery, finances, and risk management.
The programme team will undertake an annual review of GIG in line with FCDO processes. It will assess performance and achieved results against logframe milestones, value for money, ToC validity, and programme risk management, and provide recommendations to improve delivery. GIG will be scored following standard FCDO scoring procedures. The annual review timing will be set post-business case approval and consider partner reporting timeframes as noted above. The annual review will be approved by the DD for GIG COE and made publicly available.

Partnership Principles - No assessment of Partnership Principles will be required as no financial aid will be provided.

Resourcing

GIG will be overseen and managed, by a team in the FCDO Economic Growth Department including programme funded roles. The team that oversees this BC (GIG) will also provide leadership and oversight for the overarching GIG COE (which includes separate BCs for agriculture and land).

There is likely to be a need for re-organisation of structures within EDD ahead of GIG COE implementation stage, the details of which are beyond the remit of this BC, but we recognise the need to avoid any automatic shrinking of FCDO resourcing compared to management of the current suite of EDD programmes. We note the QAU finding of ‘bundled’ BCs tending to underestimate management capacity and will reflect this risk in the GIG risk register.

The FCDO delivery team will be responsible for:
- Overall strategy - including setting annual budgets and allocations; determining selection criteria for deciding which requests from Posts should be supported.
- Contract management, including procurement regulations and contracting, due diligence and performance management of the commercial supplier, understanding our commercial levers as well as leading on any contract reviews, extensions, negotiations including on pricing reviews. We recognise the need to have enhanced capability here and a senior member of the programme team would be accredited contract manager in line with Government Commercial Function (GCF) Contract Management Professional Standards.
- Programme management, including financial management and payments; programme monitoring (e.g. annual and completion reviews; disseminating learning points); programme adjustment as required mid-course, including updating the logframe; keeping the supplier informed of UK policy updates; risk management.
- Implementation support, including raising awareness of the GIG COEs services and building demand among Posts; processing requests for services from FCDO Posts, partner governments and regional organisations; allocating budgets, including rationing services if demand exceeds available supply.
- Advisory support, including through programme-funded posts, for example, advising colleagues at Posts on preparation of terms of reference for services; quality assurance of products delivered; bringing together learning from the GIG COE with learning from other programmes (FCDO, other UK Government and external programmes).

Within this BC, we envisage the following key FCDO central and programme funded roles:

Table 15. FCDO Central and programme funded roles

Role	Grade	FTE	Type of role	Overview
Senior Responsible Owner (SRO) – PSD Adviser/ Economist	Grade 6	1	Existing role	Responsible for overall programme compliance with FCDO ODA rules and policies and GIG governance processes. / Lead relationships with partners and ensure they delivery HMG priorities, including on economic growth, transformation, and inclusion. / Lead GIG’s coordination with other COEs and integration within other HMG activities. / Ensure GIG has sufficient human resource, working with others in ECED, and risks are appropriately managed.
Senior Social Development Adviser	Grade 6	0.4 FTE	Existing role	Provides strategic oversight on inclusion objectives and delivery. / Internal challenge function to maximise inclusion impact / Advisory support to intervention design
Thematic advisers - Advisers on specific thematic areas	Grade 6/ 7	6 FTE	6 FTE x existing roles (NB Advisers also have wider policy responsibility so will not work 100% on GIG. 6FTE is the cumulative amount of time required from a larger number of staff.	Provide additional technical expertise to GIG. / Support GIG’s delivery and alignment with wider HMG transformational and inclusive policy objectives and commitments. / Lead on relationships with Partnerships / Provide policy support to GIG’s and its delivery partners / Advise SRO on strategic direction of workstream and approval of interventions / Adviser on non-ODA
Programme Responsible Officers	2 x Grade 7/ 1 x HEO	3	3 existing roles	To include one professionally accredited contract manager in line with the Government Commercial Function (GCF) Contract Management Professional Standards / accountable to SRO(s), day to day delivery of programme including effective management of contracts, risk, compliance, objectivity about performance and design and adaptation of programmes to uncertain or changing context.
Programme Managers and Additional PM and commercial support	HEO/SEO/EO	6	6 existing roles	Providing programme management support to the FCDO staff PRO.
Monitoring and evaluation adviser	Grade 7	1	1 x existing role	Help establish GIG’s MEL activities, support ongoing engagement with the MEL commercial supplier and accountable for driving identification and integration within and beyond COE
2 Programme Funded G7 cross cutting advisers – inclusion and climate and environment adviser	Grade 7	2	2 x new Programme Funded Post	to ensure inclusion, climate and environment objectives remain central, identifying opportunities to strengthen the impact of interventions and challenge all workstreams to strengthen impact.
10 x Programme-funded G7 advisers, to be based within Posts	Grade 7	10	5 existing roles, 5 x new Programme Funded Post	These roles will provide a link between the Centre and Posts particularly with respect to programme management and engagement with country stakeholders. They will also ensure connection between programmes and real economy in country

The number of existing roles at each grade in EDD is sufficient to cover all the Admin funded roles envisaged to manage GIG. Not all EDD roles will work on GIG, as EDD also has policy responsibilities so the table above does not include 100% of FTE who are currently, or will in future be needed to work in EDD. For the Programme Funded roles we anticipate a need for 7 new PFP roles over above existing 5 EDD PFPs. GIG will be a large, complicated and ambitious programme and will requires at least as many staff as we currently have managing the legacy programmes. GIG will be at least as complex if not more given the interoperability and evidence requirements.

New Programme Funded Posts to implement specific elements of the COE are envisaged to be appointed in accordance with all HMG guidance and rules and will be agreed with posts. GIG will set clear terms of reference for programme funded positions, agreed with posts, and ensure they enhance the programme’s delivery. These will build on the success of Manufacturing Africa’s country-based Advisers.

The programme has multiple components. To build synergies across various components and increase FCDO’s advisory and influencing ability in different workstreams, the working level team will bring together all component work strands for strategic coherence and efficiency in delivery. The team will work closely together and will focus on proposed strategic issues and directions of the programme. Specific roles and responsibilities will include:
Outside GIG BC

    1. Accountability for programme delivering its agreed outcomes and development impact.
    2. Driving coherence amongst the components and further work needed from other FCDO programmes.
    3. Assess performance against work plans and adherence to the programme objectives; and ensure value for money.
    4. In-year monitoring, review and learning will inform whether and how GIG should adapt to contribute to outcomes.

Monitoring, Evaluation and Learning

A robust monitoring, evaluation and learning function will be integrated into delivery, with monitoring and learning embedded in supplier KPIs. FCDO will be responsible for developing and final sign-off of the GIG logframe (see Annex K). The logframe will remain a live management document to be regularly reviewed and adjusted in line with new evidence and learning.

While the COE model is relatively new and untested, GIG builds on FCDO’s established track record delivering successful programming in the economic development space. Learning from experience of what works is embedded in the design of this BC. We will ensure regular review of activities, but it is not deemed good VfM to conduct a separate, independent evaluation of GIG activities alone, but rather GIG would anticipate participating in Secretariat-led evaluation of the overarching economic development COE architecture. This is in line with previous QAU annual reports have highlighted the need to ensure a robust rationale of evidence gaps or how findings will be used to justify independent evaluation.[74]
[74] QAU annual reports on evaluations

The intention by EDPD Strategy Team is to carry out an evaluation of the Centres of Expertise as a model.  We have included £4m in our budget line for MEL for this programme which we envisage being focused on outcome assessments and results. This sits under component 1.  We are not envisaging a formal evaluation within GIG as our activities are unlikely to be sufficiently novel such that an evaluation may not add to existing knowledge in this area.   We will liaise with FCDO’s Evaluation Unit to develop a MREL plan following business case approval.

International Climate Finance (ICF)

Based on experience of existing programme, GIG is expected to be minimum 65% ICF and to contribute to UK ICF results. A full results framework will be designed following business case approval and the team will seek to develop and expand ways to reach the minimum 65% target during the inception phase, but it is expected that this programme may contribute to some or all of the following ICF KPIs:

  1. ICF KPI 1: people supported to better adapt to the effects of climate change
  2. ICF KPI 2: people and social institutions with improved access to clean energy
  3. ICF KPI 4: people whose resilience has been improved
  4. ICF KPI 6: tonnes of greenhouse gas emissions reduced or avoided
  5. ICF KPI 15: extent to which ICF intervention is likely to lead to transformational change
  6. ICF technical assistance KPI 1: countries supported by ICF technical assistance
  7. ICF technical assistance KPI 2: individuals and organisations supported by ICF technical assistance

The reviewers will examine programme results at output and outcome levels, reassess the assumptions and coherence of different components.

Risk management

The Risk Register will be a live document that will form part of the Delivery Plan.[75] An initial risk register for GIG is set out below. The SROs, PROs and programme manager will use that Delivery Plan as a basis for continuous risk identification and management throughout the life of the programme. The Governance arrangements of the Centre will include a number of processes to ensure that all programme risks are proactively managed and addressed.
[75] Using FCDO Risk Matrix tool to assess risk and best practise from FCDO PrOF to manage risk.

The overall programme risk is Moderate. It is within the FCDO risk appetite. The main risks are:
1. Policy and Programme Delivery: Mismatch of demand and supply; (a) quantitative - lack of demand from Posts, and; (b) qualitative – divergence between Post and GIG capability. Mitigation strategies will include regular, open consultation with Posts to understand and respond to needs, periodic external review to assess uptake and outline corrective action, as required.
2. Policy and Programme Delivery: COE is so large, diverse, and flexible that it becomes overly time consuming to manage, we underestimate PM time required, can’t recruit enough PMs or GIG overlaps with other COEs, confusing the offer. This will be mitigated by drawing on learning from existing programmes, selecting the optimal number of delivery channels to manage transaction costs and retaining close links with other COE leads during design and implementation.
3. Design Risk: Scope is either too broad that GIG loses focus and fails to identify suitable delivery partners, or too narrow such that Posts do not consider it a viable delivery mechanism for their specific needs. This will be mitigated through Early Market Engagement exercises, broad consultation and clearly defined principles for selecting which opportunities to support.
Table 16 – GIG risk register

Category	Risk	Gross Risk	Residual Risk	Mitigation
Strategy and context	Political economy in focus countries is not conductive to successful GIG interventions	Major	Major	Rigorous political economy analysis by FCDO/GIG to inform geographic priorities, ensuring we work in countries that have political commitment to deliver GIG. GIG designed to scale up or down in response to changes in political contexts. Joint sign off with Posts before proceeding with interventions.
	Economic shocks reduce overall outcomes	Major	Moderate	GIG designed to scale up or down or adapt in response to economic context changes. MEL framework will be adapted as required to best measure relative impact of interventions, taking account of shifting counterfactuals.
Policy and Programme Delivery	TAF procurement - We do not receive bids from well-qualified suppliers to run GIG technical assistance facility	Moderate	Minor	Early Market Engagement (EME) via the procurement portal during BC design including wider partners like universities and NGOs. Run an EME workshop following BC approval to generate interest and support formation of consortia. / Clear terms of reference drafted setting out requirements and expectations of suppliers (as part of invitation to tender)
	Lack of FCDO demand for support from the facility and Post ‘buy-in’.	Major	Moderate	Regular contact with all Posts to keep them informed of the services available, and promoting GIG offer.
				Support contingent on alignment with Post Country Plans.
				Annual reviews of the facility to assess use of the facility, providing an opportunity to take corrective action.
	Demand for the facility is greater than predicted leaving the Facility unable to meet demand.	Major	Moderate	Be prepared to re-allocate funding from other components/subcomponents if there is a strong case for additional funding to the facility.
				A governance structure has been put in place to review proposals. If there are excessive proposals, some can be ruled out on the basis of agreed criteria.
				Flexibility to accommodate range of Post funding levels through buy in model
	Partnerships fail to deliver programme objectives; partnership work at cross-purposes to each other undermining programme coherence; Partnerships fail to unlock co-investment from other donors leaving FCDO with a disproportionate burden.	Major	Moderate	Partnerships to be appropriately managed and assessed against log frame indictors by Hub with regular meetings and review points. External review to be considered to assess overall performance of these elements.

	Excessive FCDO Adviser time is absorbed by managing interventions	Moderate	Minor	If the anticipated areas of programming are not developing as planned, reach out to partners and global experts to develop new proposals. Monitor the time required and make adjustments as necessary. If time requirements are excessive, seek to reviews ways of working.
	Too many disparate / unconnected interventions result in an overall lack of coherence across the GIG portfolio and at country level.	Moderate	Moderate	GIG Hub will consider bids/concept notes against clear assessment criteria to ensure coherence across the portfolio of interventions
				Hub will work with leads at Post to strengthen coherence at country level and ensure all work feeds into country business plans.
				Programme results dashboard to monitor how each intervention fits into GIG portfolio and driver programme results.
	Cross cutting themes are deprioritised.	Major	Moderate	Scorecard approach is used in design and monitoring of GIG interventions to ensure all consider cross cutting themes.
				There will also be dedicated interventions for delivering cross cutting themes.
	Unable to support projects that maximize economic transformation as too constrained by ringfenced budgets for ICF, LMICs and FCAS.	Major	Moderate	The TA assessment criteria and scorecard approach will help maximize effectiveness and support strategic portfolio management. / FCDO team will be clear in communicating the constraints and trade-offs to manage expectations on results. / FCDO team will explore metrics with the ICF team, particularly regarding TA that supports adaptation, to explore ICFability of wider GIG work.
	Proliferation of governance bodies making the whole architecture ineffective and in efficient.	Moderate	Moderate	Coordination and joint governance functions are in place across COEs where appropriate and will be regularly reviewed.
Operational	FCDO (EDD) lacks staffing resources to manage the resource centre	Major	Moderate	EDD continues to prioritise across the diverse workstreams to ensure highest professional competence and appropriate staffing resource for technical and programmatic oversight of GIG.
	FCDO Posts lack sufficient technical expertise so central support will not be sufficient to generate a major scale-up in programming	Moderate	Minor	FCDO-wide action to ensure appropriate advisory skills in these areas. Responsibility for this lies outside the programme, however the GIG will also undertake on a FCDO capability function to support institutional learning.
				GIG will have PF roles that place expertise in country to support delivery of GIG.
Safeguarding	Supplier(s)/Partners acting on behalf of FCDO does not act in line with UK government policy or breaches safeguarding expectations	Moderate	Minor	Through robust due diligence we will ensure that the supplier(s)/Partners have a safeguarding policy and the capacity to act on allegations, demonstrating how this applies to downstream partners and that a due diligence is also carried out on downs team partners.
	Partners on interventions do not act in line with FCDO safeguarding standards (e.g. Government official, businesses)	Moderate	Minor	Establish a risk register with explicit risks and mitigation measures for safeguards. Through the technical assistance provided the programme will also ensure that safeguards are specifically referenced, where appropriate.
	Funds are misappropriated	Minor	Minor	Robust due diligence of supplier(s)/Partners is carried out during the procurement/agreement processes, including demonstrating internal due diligence process for any downstream partners.
				Rigorous financial management processes will be in place, in line with FCDO PrOF guidance.
Financial and fiduciary	Supplier selected to manage the Centre fails to perform and deliver the high standards of quality required of FCDO programmes	Major	Moderate	Base the contract on milestones as far as possible to create performance incentives. FCDO Hub team to be in regular contact with Post team receiving support from the facility to gauge their views on performance. FCDO to develop a strong relationship with the Supplier and meet regularly to discuss performance. Rigorous performance assessments after each Contract break clauses to be included.
	GIG does not represent good VfM	Moderate	Minor	VfM is a key concept in the design and delivery of GIG, including providing services in a rapid and cost-effective way to FCDO Posts; economies of scale associated with a broad range of services being provided through one instrument.
	The pool of consultants managed by the facility do not have the right diversity of skills to meet Post demand.	Moderate	Minor	The Supplier contract(s) allocates the risk associated with an inadequate pool of consultants to the Supplier(s).
				Annual reviews will pick up on this and FCDO to take corrective action if necessary. Ensure effective monitoring strategy is in place to monitor and track requests for TA support.
Reputational	GIG fails to differentiate itself from other centres of expertise and/or fails to be recognised as an expert entity across HMG and/or by key multilateral partners.	Major	Moderate	Identify programme areas/offers that will deliver quick wins for the GIG.
				Develop and implement engagement strategy to ensure buy-in and support from key departments/teams across HMG.
	GIG facility delivers low-quality services which tarnishes the UK’s reputation as an international leader on green and inclusive growth.	Major	Minor	Actively manage delivery and fiduciary risks as set out above.

Risk Appetite Statement

We will retain a receptive appetite for strategy and context, and programme delivery risks, in line with the FCDO risk appetite. The GIG takes an innovative Centre of Expertise approach, with services supplied according to demand, rather than determined in advance. This adds a degree of unpredictability and uncertainty, with a risk of mismatch between demand and supply. However, the ability to mobilise expert services rapidly as opportunities arise could help unlock key reforms or support investment where otherwise support would be limited or non-existent.

We will retain a cautious appetite for people risk, in line with FCDO risk appetite. EDD will continue to strive to ensure the highest possible professional competence and appropriate resource to manage our diverse areas of work and reprioritise to ensure effective in-house oversight and programme management for the GIG, including when resources are constrained.

We will retain a minimal appetite for fiduciary, reputational and safeguarding risk, in line with the FCDO risk appetite. In terms of minimising these risks, and in line with good practice: the commercial contract will be on the basis of payment in arrears; supplier bids will be scored on the basis of sound safeguarding/do no harm policies and procedures; and the EDD programme team will work closely with the FCDO Posts and the supplier to develop the ToRs for individual interventions - agreeing the approach and requirements of any delivery personnel/sub-contractor, in order to mitigate risks at the country level.

## References