## Annual Review Template

Title: Climate Resilience in the Sahel Programme
Programme Value £ (full life): £19,500,000		Review date: September 2025
Programme Code: 400298	AMP start date: 26/11/2024	AMP end date: 30/11/2028

Summary of Programme Performance
Year	2025
Overall Output Score	B
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400298
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400298 Documents

A. SUMMARY AND OVERVIEW

Description of programme

The Climate Resilience in the Sahel Programme (CRiSP) is a £19.5 million programme that is helping vulnerable people in protracted crisis contexts live a dignified life in displacement, be more resilient to climate stressors and be less reliant on humanitarian assistance. The programme is helping refugees and host communities in areas where land degradation exacerbates food insecurity, and to restore and manage their ecosystems, as an entry point to secure the natural capital essential to their subsistence and livelihoods.

CRiSP provides a platform for the UK to learn, engage with resilience stakeholders, and demonstrate how people-centred, complementary approaches and innovative partnerships in protracted crises and fragile contexts, can respond to immediate needs while also building long-term resilience and addressing climate and environmental drivers of vulnerability. This is also delivered with governments and communities, and in line with national climate strategies.

CRiSP is delivered by the UN World Food Programme (WFP) through their Integrated Resilience Programme (IRP). FCDO funding contributes to existing IRP sites[1] and supports project delivery in Chad (Lac, Ouaddai, and Logone regions), and Mauritania (Hodh Ech Chargui, Guidimakha and Assaba regions). CRiSP funded the IRP between December 2024 and March 2025 during the 2024–25 financial year. As there was an announcement of a reduction in Official Development Assistance (ODA) from 0.5% to 0.3% of gross national income (GNI), FCDO funding to IRP was paused from April to July 2025, due to uncertainty around the Sahel’s bilateral budget. As a result, this annual review will focus on assessing progress made during the initial four months of delivery (December 2024 – March 2025). Funding resumed in July 2025, and activities undertaken from that point onwards will be covered in the 2026 annual review.
[1] Following the 2024 elections, reductions in ODA, and the Spending Review, the FCDO was unable to commit to multi-year contributions, and the CRiSP contribution agreement was signed on a single-year basis, which limited the UK’s ability to support the opening of new sites. Contributing to existing IRP sites helped ensure minimal disruption to beneficiaries and partners in case of early exit.

Summary supporting narrative for the overall score in this review

The programme scored a B during the reporting period. There was some good progress on the output indicators, in particular on immediate support through food assistance for assets (FFA) and home-grown school feeding (HGSF) as well as on longer term resilience building activities such as land rehabilitation, water systems strengthening and smallholder market support (SAMS) / income-generating activities (IGA). However, the programme has scored a B in the first year as the target number of beneficiaries outlined in the proposal were not met.

The CRiSP business case was approved on 20 October 2024, and the programme successfully secured a £4 million allocation from the FCDO Resilience and Adaptation Fund (RAF). Given the scale of the financial commitment to WFP and the limited delivery timeframe, there was significant pressure to begin activities quickly, particularly in the context of the deteriorating humanitarian crisis in Chad. As a result, there was insufficient time to develop a full results framework for the first tranche of funding covered in this review.

As a formal results framework was not in place, specific milestones and targets were not established, especially given time constraints for this tranche of funding. Instead, progress was assessed against the results outlined in the implementing partner’s proposal for financial year 2024-25 funding. However, this proposal did not include targets or milestones indicators for key outputs such as assets created, or qualitative outcomes such as improved integration or strengthened partnerships. Whilst this meant the annual review could only be scored a B, the review draws on WFP’s 2024-25 annual reporting to illustrate progress on these broader outcomes in the output section — while noting that the timeframe and scope of WFP’s reporting extend beyond both the UK’s contribution and the current review period.

Major lessons and recommendations for the year ahead

A key lesson for FCDO is that building resilience requires dependable multi-year funding. Funding uncertainty limits the ability to commit meaningfully to communities and asset-building, secure resources for research and evidence generation, and set clear targets and milestones for reporting. These constraints hinder learning on ‘what works’[2] to avert humanitarian needs. Going forward, FCDO’s investment in resilience in the Sahel should be structured to optimise delivery through multi-year funding commitments.
[2] ‘What Works’ is based on the principle that good decision-making should be informed by the best available evidence. If evidence is not available, decision-makers should use high-quality methods to find out what works.

Recommendation 1: Finalise the CRiSP logframe for financial year 2025/26, including indicators for outputs, outcomes and impact statements, as well as incorporating value for money indicators.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Climate Resilience in the Sahel Programme (CRiSP) theory of change was developed as part of the business case in 2024:

The existing theory of change was designed for a long-term, multi-year programme with built-in flexibility through a phased approach. This structure anticipated a review in early 2026 and adaptation in Phase 2. However, with a shortened timeframe, and anticipated closure in March 2027, the programme will now focus on delivering a reduced set of outputs during the transition period and prioritising learning at both the output and outcome levels[3]. This shift will enable CRiSP to contribute meaningfully to the design of the new Sahel programme portfolio while ensuring a responsible and informed programme closure.
[3] CRiSP was designed as an adaptive programme and did not begin with a comprehensive results framework. Instead, technical assistance was secured from the FCDO Centre of Delivery (CfD) Solutions hub to help design an adaptive results framework using tools such as outcome maps and actionable learning monitoring. This work took place between December 2024 and March 2025 but was paused due to uncertainty around future funding of CRiSP. The FCDO Sahel team will develop a standard results framework for the remainder of CRISP and look at the opportunities to integrate adaptive programming approaches in the future portfolio depending on monitoring, evaluation and learning (MEL) support available.

A key recommendation is therefore to finalise the logframe for the remainder of CRiSP including the indicators for the outputs, outcomes and impact (Recommendation 1).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As only four months of the programme is being assessed, it is too early to provide specific results on outcome indicators, which also need to be finalised. However, the programme has made good progress so far on output activities and is generally on track to deliver the outcomes:

- Increased household and community resilience to crises and shocks through ecosystem-based approaches
- People-centred approaches embedded in local and national policies
- Integration and convergence between humanitarian, development and peacebuilding stakeholders and better evidence on resilience programming

Increasing household and community resilience through ecosystem-based approaches

Through food assistance for assets (FFA) activities WFP supported communities in bringing their landscapes back to life, enhancing their natural resource base and developing community infrastructure. Through accompanying cash, voucher or food transfers, communities can address their immediate food needs. At the same time, the assets built combined with agricultural support and technical training improves food security, livelihoods, resilience to natural disasters of communities in the long-term as well as social cohesion.

People-centred approaches embedded in local and national policies

The programme works with the communities, who take ownership of their own transformative journey at all stages: in design, planning and implementation; in tracking progress and changes against their community plans; and in strengthening communities’ self-help capacities as well as community-based organisations. This is done through the tools of community-based participatory planning.

Integration and convergence between humanitarian, development and peacebuilding stakeholders and better evidence on resilience programming

The programme contributed to increasing the capacity of governments in the Sahel to maintain and scale up resilience gains. For example, WFP worked closely with UN agencies and the Government of Chad to implement national policies that address humanitarian needs while promoting peace and development through a humanitarian-development-peace nexus approach.

CRiSP contributes to integration and convergence between stakeholders through its approach to partnership working which ensures efforts are coordinated and resilience building activities can be scaled up. WFP collaborated with national non-governmental organisations (NGOs), government, and other international cooperation and UN agencies and has continued to improve coordination and cooperation with other stakeholders, supporting integration and convergence with Nexus actors in the regions of intervention

In the year ahead, the FCDO will develop a comprehensive results framework with indicators at the outcome level. This will build on WFP’s Resilience Monitoring and Measurement (RRM) and will help to inform the future Sahel programme portfolio as well as feed into learning on ‘what works’ for resilience as part of the FCDO Resilience and Adaption Fund (RAF) community of practice[4].
[4] WFP already monitors outcome level indicators such as Dietary Diversity Score, Consumption-based coping strategy index, Resilience Capacity Score (RCS), etc. The FCDO will also consider indicators on social cohesion and conflict prevention.

In 2025-26 CRISP will contribute to evidence on the cost-benefit analysis of IRP (CGIAR-CIAT[5]), the climate adaptation outcomes of IRP (UNU), and the WFP / UNU-EHS[6] study on the long-term impact of IRP’s asset creation on climate adaption. CRISP is also drawing on the FCDO centrally managed Land Facility to fund an assessment of land governance in the East of Chad to inform conflict-sensitive land restoration.
[5] Consultative Group on International Agricultural Research (CGIAR) and International Centre for Tropical Agriculture (CIAT)
[6] United Nations University – Institute for Environment and Human Security

In 2025-26, CRiSP will also fund the WFP REUNIR network of universities, a partnership between WFP and the Sahel University Network which promotes resilience research in the field[7]. This funding contributes to enhancing roles, capacities, and networking of universities to increase the capacity of national actors to maintain and scale up resilience gains. One of REUNIR’s pillars is to promote the deployment of Masters and PhD students from universities to WFP integrated resilience sites to conduct research for their theses. This allows students to gain practical experience and promote action-oriented research that can inform resilience programming, improve the technical quality of interventions and capitalise on concrete solutions for food security and resilience in the Sahel.
[7] The network includes six universities from five countries: Abdou Moumouni University of Niamey (Niger), Dan Dicko Dankoulodo University of Maradi (Niger), Universite de Diffa (Niger), Nazi Boni University of Bobo Dioulasso and Université Yembila Abdoulaye TOGUYENI (Burkina Faso), University of N'Djamena (Chad), University of Adam Barka Abeche (Chad), Gaston Berger University of Saint-Louis (Senegal), and the Rural Polytechnic Institute (IPR) of Koulikourao (Mali).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

It is recommended that the programme continues in financial year 2025-26[8]. CRiSP supports progress across all the FCDO objectives in the Sahel, in particular, the first pillar of the Sahel strategy which aims to ‘save lives and build resilience to climate and conflict shocks’ by: (i) lifting vulnerable people out of crisis through protection and assistance in areas of most acute humanitarian need; (ii) restoring natural capital and make vulnerable people more resilient to climate stressors; and (iii) supporting locally-led conflict prevention and resolution, and sustainable use of land. Although in its early stages, it has already shown good results and contributions to the intended outcomes.
[8] The programme was designed to be flexible and agile, allowing it to scale up or down depending on future funding allocations. It was initially structured in two phases: Phase 1 (2024–2026): Delivered by the World Food Programme in eastern Chad (bordering Sudan) and eastern Mauritania (bordering Mali). This phase was intended to generate learning to inform potential scale-up, geographic expansion across the Sahel, or adaptation in Phase 2. Phase 2 (2026–2028): Planned as a continuation or expansion based on lessons from Phase 1. However, this two-phased approach is no longer applicable due to the reduction in ODA from 0.5% to 0.3% of GNI. The Sahel programme portfolio is now expected to transition by the end of financial year 2026-27, with a planned closure of CRiSP within that timeframe.

## C. DETAILED OUTPUT SCORING

Output Title	Improved short-term food, nutrition, and water security for refugees, returnees and host communities, in protracted crises in the Sahel reduces hardship and negative coping strategies
Output number:		1	Output Score:	B
Impact weighting (%):		100%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of beneficiaries (individuals) supported through food assistance for assets (FFA) activities in Chad and Mauritania	60,560 beneficiaries (individuals) supported through FFA activities (59,060 Chad; 1,500 Mauritania)	46,074 beneficiaries (individuals) supported through FFA activities: / 42,288 Chad (21,990 female; 20,298 male); 3,786 Mauritania (1,855 female; 1,931 male). / Moderately did not meet expectations
Number of beneficiaries supported through home-grown school feeding (HGSF) activities in Chad	46,071 beneficiaries (individuals) supported through HGSF activities in Chad	46,071 beneficiaries (individuals) supported through HGSF activities in Chad: / 46,071 children (22,250 female; 23,821 male) / Met expectations
Number of beneficiaries supported through smallholder market support (SAMS) / income-generating activities (IGA) in Mauritania	7,520 beneficiaries supported through SAMS / IGA activities in Mauritania: 2,000 market gardening activities; 5,520 water pump installation	3,155 beneficiaries (individuals) supported through SAMS / IGA activities in Mauritania: 3,155 market garden activities (estimated 2,524 female; 631 male); 0 water pump installation / Substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Two of three indicators under this output did not meet expectations, and so this output scores a B.

From December 2024 – March 2025, the FCDO contributed to the UN World Food Programme (WFP)’s Integrated Resilience Programme (IRP) in targeted areas in Chad and Mauritania to expand on and reinforce existing resilience interventions for vulnerable refugees and host communities affected by protracted crisis, food insecurity, and displacement. In the first four months, the FCDO contribution supported beneficiaries in Chad and Mauritania, reaching a total of 95,300 beneficiaries, and contributed to building and maintaining community assets and supporting food security and resilience.

1.1 The number of beneficiaries (individuals) supported through FFA activities in Chad and Mauritania were exceeded in Mauritania as the project reached 3,786 beneficiaries compared to a target of 1,500, however, overall this indicator did not meet expectations. The overall target was 59,060 beneficiaries in both Chad and Mauritania and the project reached 46,074 beneficiaries in total, and so this moderately was not met. This is because WFP use community-based planning in a highly fragile and rapidly changing context (both in terms of refugee flows and funding cuts) as part of their target setting. Given that the annual review is measuring only 4 months, this reflects only a partial measurement of 12 months implementation period.

FFA includes providing conditional cash-based transfers to households who participate in asset creation activities. This allows households to purchase locally available goods, boosting the economy and reducing reliance on imported commodities. Asset creation activities include crop land rehabilitation to enhance and diversify production systems, as well as the development of community infrastructure. The productive assets and infrastructure will contribute to agri-food activities and jobs creation which small-scale farmers, women and young people will benefit from.

An example of the success of FFA in Chad is in the Dossoloum valley, where 150 hectares of land had remained unexploited due to an intercommunity conflict. A project proposal was submitted to WFP by the Provincial Delegation of Agriculture and the National Consultation Framework of Rural Producers (CNCPRT) and through FFA activities, 150 hectares of land were cleared and prepared for crop production, restoring access to productive land and also enabling participating households to meet their immediate food needs through cash-based transfers. Many used this assistance to invest in small-scale income-generating activities, contributing to the economic revitalisation of the area. Beyond improved food security, the intervention strengthened social cohesion and marked a significant step toward durable peace and community-led recovery in the Lac province.

FFA is also integrated with initiatives aiming to enhance agricultural productivity and create alternative livelihoods, including through linkages to HGSF.

1.2 The number of beneficiaries supported through HGSF activities in Chad met expectations by reaching 46,071beneficiaries during the reporting period.

The objective of HGSF is to 1) provide nutritious balanced diets to children, enhancing attendance, retention and academic performance, which over the long term will enable a conducive environment for safe, adequate and nutritious food intake and utilisation and 2) to support local production and market systems development the local economy.

46,071 children (48% girls) in 83 schools benefited from a daily meal over 60 school days. The meals were enriched with local vegetables and cereals produced by parents in community gardens. This direct intervention supports the core objective of improving their nutrition but also attendance, school retention, and learning outcomes. As part of this effort, WFP provided take-home rations to 3,267 adolescent girls to advocate for their enrolment and sustained involvement in school and prevent early drop-out. Additionally, 668 women cooks received monthly incentive payments of 15,000 FCFA. In Lac province, 100% of the cereals and vegetables served in school meals are sourced from nearby farms, creating a reliable market opportunity for smallholder farmers and laying the foundation for increased resilience.

The HGSF model, benefitting from specific SAMS activities, represents an important economic opportunity for local smallholders, and contributes to diversify school meals, enhancing dietary diversity.

A good example of this integrated approach between school feeding and local economy is the work carried out in Chad’s Lac province, where a powerful partnership between schools and smallholder farmers has been established. Today, 100% of the cereals and vegetables served in school meals are sourced from nearby farms, creating a reliable market opportunity for smallholder farmers. Combined with land rehabilitation, capacity strengthening, and access to tools, this opportunity has been a game-changer for local farmers. Farmers invested in rice hullers, mills, and pickup trucks, reducing processing time by 60% and doubling their yields on rehabilitated land. Participant cooperatives like Yassour have expanded their activities and created 15 new jobs, reinforcing local livelihoods and self-reliance. This school meal initiative is now at the heart of a thriving local value chain. Through integrated, community-driven integrated resilience initiatives, WFP’s intervention is empowering families, revitalising local markets, and laying the foundation for a stronger, more resilient future in Chad’s Lac province.

1.3 The number of beneficiaries supported through SAMS / IGA in Mauritania substantially did not meet expectations with 3,155 beneficiaries supported compared to a target of 7,520 beneficiaries.

As part of the integrated resilience approach, WFP implements smallholder agricultural market support (SAMS) activities, focusing on sites where FFA assets have reached a certain stage of maturity. SAMS activities included capacity-building sessions on farming and market gardening techniques, as well as training on cooperative governance, asset management, and good nutritional practices. WFP supports smallholders to increase their incomes and livelihoods by developing value chains and access to markets. With assistance from WFP and partners, smallholders optimise the use of assets and produce generated from gardens and rehabilitated sites, focusing on the creation of (agri-)businesses and linking farmers with markets. Encouraged to form associations, they are able to negotiate better, sell more, lower their transaction costs and extend their customer base.

The water pump installation was not completed during the reporting period due to a short delivery timeframe, and therefore the target 5,520 beneficiaries was not met. However, WFP were able to acquire 30 solar pumps, which will be ready to be deployed in the next reporting period 2025-26, which is expected to reach the number of beneficiaries planned for 2024-25 (5,520). WFP were able to reach 3,155 beneficiaries (in comparison to the target 2,000 beneficiaries) through market gardening activities across 10 villages. This primarily targets women’s cooperatives and so it is estimated that up to 80% of beneficiaries are women.

Additional results achieved as a result of activities

The FFA, HGSF and SAMS activities contributed to a range of other outputs from the CRiSP theory of change which we are not formally reported on (due to the lack of agreed milestones). A summary of these activities are provided below in recognition of their contribution to other elements of the theory of change at the output level.

FFA supported ecosystem restoration and land and water systems rehabilitation activities to address specific resilience challenges faced by communities and improving access to and the quality of water, which in turn supports food security and livelihoods through increased natural capital and ecosystem services.

This included:
- In Chad 983 hectares of land have been rehabilitated, including 390 hectares for agricultural purposes. 170 hectares of vegetable gardens were created, 10,000 hectares of sand dunes were stabilised, 500 linear meters of dikes were constructed or rehabilitated, and 44,000 linear meters of soil and stone bunds were created as part of anti-erosion efforts.
- In Mauritania, 6,312 households participated in the creation and rehabilitation of community assets, including the rehabilitation of 357 hectares of degraded land, much of which was previously classified as ‘lost’ for production, as well as the stabilisation of 50 hectares of dunes. In addition, 1,867 linear meters of dikes were constructed or rehabilitated, and 600 linear meters of soil and stone bunds were created as part of anti-erosion efforts.
- In Chad, 20 small dams and water retention basins were constructed, enabling the irrigation and protection of 1,300 hectares of crops and directly benefitting 2,600 households (15,600 individuals).
- In Chad, 5 storage warehouses with a capacity of 105m³ were constructed to support post-harvest storage and reduce food losses at community level.
- In Chad 9 wells, 8 solar-powered communal pumps, and 12 solar-powered irrigation systems were created, improving communities access to sustainable water sources for agricultural and household use. In Lac province, 20 small dams and water retention basins were built, enabling the irrigation and protection of 1,300 hectares of crops and directly benefiting 2,600 households or approximately 15,600 individuals.
- In Mauritania 30 solar pumps are ready for installation and will be deployed progressively across sites based on community needs.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output 1 will be revised as part of the finalisation of the CRiSP logframe in 2025-26.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A key lesson for WFP during the reporting period was the value of concentrating investments in fewer, strategically selected sites, particularly in the Lake area where WFP have strong opportunities to build on existing, mature projects to complement activities related to SAMS. For the next reporting period (2025-26), WFP will focus on deepening activities in existing locations where strong foundations have already been established, such as valorising polders in the Lake area, and supporting business opportunities in terms of transformation and value chain strengthening in IRP sites in both East and Lake under the SAMS approach. This approach will allow for more intensive support, better coordination, and greater overall impact. The longer implementation period of year 2 (2025-26) provides the flexibility to pursue this strategy more effectively. It also creates an opportunity to strengthen value chains and promote economic opportunities in areas where WFP has already built relationships and infrastructure.

Recommendation 1: Finalise the CRISP logframe including indicators for outputs, outcomes and impact statements, as well as incorporating value for money indicators.
## D: VALUE FOR MONEY

Key cost drivers and performance

CRiSP funded the Integrated Resilience Programme (IRP) component only in financial year 2024-25. The key cost drivers were the direct expenditure for cash-based transfers and related costs £1,756,409 (£1,656,059 Chad; £100,350 Mauritania); and costs related to capacity strengthening activities £2,168,065 (£1,395,187 Chad; £772,878 Mauritania).

VfM performance compared to the original VfM proposition in the business case

The business case proposes building in key VfM considerations, indicators and benchmarks into the finalised logframe. This is part of Recommendation 1 for 2025-26. The business case proposes the following indicators for consideration:

Economy

The Sahel is a challenging place to work, with three main operational challenges affecting costs: (i) access and logistics: poor road infrastructure with many places only accessible by air; (ii) insecurity: unsafe access for actors with costs increasing as risks increase; and (iii) high administrative costs: human resource, finance and administration. The costs per beneficiary for IRPs is around USD 110 (depending on the country/region). A large proportion is spent on cash and food transfers, ensuring most of UK investment is directly supporting beneficiaries. WFP’s estimation is that for every 1 USD invested in resilience, there is a return of approximately 3 USD in benefits and savings in 5 years period.[9] Proposed indicators to measure economy are unit costs / ROI resilience vs humanitarian response; and unit / per capita costs of land restoration.
[9] For more details see WFP’s: Modelling a Cost-Benefit

Efficiency

FCDO systems and experience of working across organisations (e.g., UN agencies, NGOs, multilateral development banks (MDBs)) and in different locations across the Sahel ensures it has the evidence base to determine inputs required to reach expected results, at what cost, and at what speed. For example, the FCDO have developed a detailed understanding of overheads, amounts, and effort required for delivery of digital cash, and the costs of remote monitoring and implementation). Building on their IRP will enable WFP to implement CRiSP cheaper and quicker than the other options that were considered as they have established procurement processes and frameworks in place. For example, during the reporting period, the FCDO contribution to the IRP supported interventions that were aimed to complement ongoing resilience-building activities funded by other donors within the same communities. This provides value through economies of scale. Proposed indicators to measure efficiency are % cash vs in-kind; % direct programme activities / organisational overheads; and local food purchase vs. imported food. In Mauritania, WFP is planning to strengthen the capacities for local production of fortified flour and salt working with a female-led company.

Effectiveness

The programme will build on the current programme that WFP are implementing in the region to strengthen innovation, partnerships, research and evidence and new approaches to achieve maximum results. WFP have developed a tailored Resilience Monitoring and Measurement framework to monitor results across a range of outcomes. Along the resilience continuum, WFP will consider opportunities to strengthen existing systems or develop them towards attaining longer-term objectives and by putting coalitions in place for enhanced coordination, synergies and resource mobilisation for resilience. WFP’s IRP use a satellite imagery and landscape monitoring software, the Asset Impact Monitoring Service, to monitor the long-term landscape changes of Food Assistance for Assets and engineering projects, which offers a useful tool to monitor sustainability of UK investment in the long-term and impact on land regeneration. Proposed indicators to measure effectiveness are % food security and nutrition (FSC-N); % positive beneficiary responses on the quality and effectiveness of assistance; and % adopting negative coping mechanisms.

The IRP approach and resilience sites also closely align and integrate with WFP’s work on social protection and anticipatory action expanding the impact and co-benefits from UK funding.

Although the FCDO does not have UK-funded site-specific data, results from the WFP IRP Annual Report shows a high sustainability rate for assets created through IRPs. The FCDO will aim to refine its ability to monitor sustainability of assets (which WFP monitors through AIMS) in the upcoming results framework.

Equity

The CRiSP will deliver on UK's commitments to provide humanitarian aid and climate finance to those that need it most. In practice, this means prioritising and ensuring assistance goes to the most vulnerable populations – those in hard-to-reach areas, refugees, returnees and host communities, and those who have difficulties accessing assistance (nomadic pastoralists). The CRiSP will facilitate the participation of high-risk populations groups in intervention planning, design, and implementation. Ensuring data on programmes is disaggregated, inclusive and that participatory programme tools are utilised (for example community based participatory planning) and informed by inclusion and gender analysis, with strengthened engagement with civil society organisations (CSOs). Proposed indicators to measure equity are partners adapt programming based on inclusion analysis and targeting; evidence of partner engagement with CSOs, women’s organisations, etc; needs addressed in areas currently deemed to be “hard-to-reach”; and evidence-based targeting ensures humanitarian assistance focused on the most vulnerable.

A key factor in the sustainability of these initiatives was the early and active engagement of communities. WFP employed community-based participatory planning and conducted multiple rounds of focus group discussions, to ensure a deep understanding of each community’s unique needs. This approach empowered communities to identify their priorities and propose actionable solutions. To promote comprehensive and inclusive development plans, WFP also ensured the participation of all community members to the discussions, including women, youth, and people living with disabilities.

Assessment of whether the programme continues to represent value for money

Given the short timeframe of the reviewed period, it is too early to fully assess value for money (VfM), however, the assumptions made in the business case are still valid. Improving the VfM of climate resilience investment and of the humanitarian response in the Sahel is at the heart of CRiSP design through investing in short-term food security while restoring the natural capital that will contribute to increase long-term resilience. CRiSP investments in longer term solutions for vulnerable rural and internally displaced communities, are justified by a strong VfM rationale aimed at reducing future humanitarian needs.

The nature-based solution approach is low cost and can be more cost-effective than traditional approaches, particularly in the long term. CRiSP will support communities through cash transfers where the market is operational and food assistance where food availability/access is limited. Cash supports the purchase of goods and services relevant to the varied needs of beneficiaries and local economies and generally provides a more efficient mechanism of value transfer than in-kind assistance.

E: RISK

Overview of risk management

The overall risk rating for CRiSP remained ‘moderate’ over the reporting period. The programme is delivering in a challenging context with conflict, population displacement and climate-related shocks. Global reductions to donor aid budgets are also a risk to the programme’s ability to deliver effectively.

CRiSP’s risk register is reviewed and updated at least quarterly by the FCDO Sahel team. Risks outside of the FCDO’s appetite level are escalated to department / directorate level to consider appropriate mitigation strategies. Risk levels have not gone beyond appetite and therefore no risks were escalated during the reporting period. The risk appetite for Safeguarding was increased from Cautious to Receptive following a recommendation from an internal FCDO audit that a Receptive appetite would better reflect the operating context of the Sahel. The region is one of the poorest and most fragile in the world, with high rates of gender inequality and social exclusion, meaning that sexual exploitation, abuse and harassment (SEAH) is a high risk. The risk appetite for CRiSP is summarised below:

Risk appetite category	Climate Resilience in the Sahel Programme
Strategy & Context	Eager
Policy & Programme Delivery	Receptive
Financial & Fiduciary	Receptive
Safeguarding	Receptive
Public Service & Operations	Cautious
People	Cautious
Reputational	Minimal

CRiSP has risks under the following categories:

Strategy & Context

CRiSP operates in a region with growing insecurity, which has been exacerbated by the civil war in Sudan, with thousands of refugees crossing the border into Eastern Chad. The risk that political instability and conflict jeopardises FCDO capacity to deliver climate resilience programming in the Sahel remained moderate during the reporting period. This risk is mitigated through the implementation areas of the programme, which are currently more secure locations and also across two countries so that if one country is more affected by conflict the programme can readapt.

Policy & Programme Delivery

The risk that a deteriorating political and security situation in Chad and / or Mauritania leads to a lack of access for FCDO field monitoring, which produces a lack of results to prove concept and enable future phases of the programme remained moderate during the reporting period. This risk is mitigated by delivering CRiSP in areas where the FCDO currently has access to carry out field monitoring. Field monitoring is planned for 2025-26.

The risk that the implementing partner does not support delivery of the FCDO outcome discussing convergence across the nexus (i.e. working with other development actors) remained minor during the reporting period. WFP has already demonstrated strong partnership working. This risk is also mitigated by FCDO oversight. The logframe, once finalised in 2025-26, will include indicators to monitor progress on convergence efforts.

The risk that the implementing partner does not share timely updates (both budget and narrative) with the FCDO, resulting in a lack of oversight and clarity about how to manage the programme from the FCDO's perspective, remained minor during the reporting period. This is mitigated by close working between the FCDO and WFP, which ensures regular updates.

Safeguarding

The programme has a zero tolerance for safeguarding risks related to sexual exploitation, abuse and harassment (SEAH). The risk that the implementing partner and their downstream partners do not apply a safeguarding policy, leading to an increased risk of harm and abuse through programme funded activity, remained moderate during the reporting period. This risk is mitigated by ensuring FCDO safeguarding policies are reflected by the implementing partner and other downstream partners, and are understood and implemented all the way down the delivery chain, as well as ensuring that effective reporting mechanisms are available for staff and programme recipients through established and functioning grievance mechanisms and due diligence process assessments. The FCDO’s due diligence assessment showed that WFP has a strong approach to safeguarding provisions and practices with safeguarding mechanisms in place, and has invested in developing and strengthening its safeguarding against sexual exploitation, abuse, and harassment (SEAH) reporting systems for both WFP and its partners.

Financial and Fiduciary

The risk that a reduction in the FCDO budgets affects the finance for the programme in the outer years and produces a drop in performance increased from minor to major during the reporting period due to the possibility of reduced funding for the programme due to changes to UK Overseas Development Assistance (ODA) spending.

The risk that fraud and / or aid diversion occurs due to weak systems of governance and accountability, detracting from the effectiveness of the programme and potentially causing reputational damage remained moderate during the reporting period. This is mitigated by the delivery partner WFP’s robust monitoring systems and oversight processes.

People

The risk that the FCDO does not have management or advisory capacity to engage effectively with the programme beyond the first phase due to ongoing FCDO restructuring remained minor during the reporting period. This risk is mitigated as the programme is delivering through an established delivery partner. The FCDO continues to hold expertise through the Climate and Environment Adviser and Development Counsellors.

Reputational

The risk that programme does not integrate conflict-sensitivity mitigation strategies and there are reports of harm or deterioration of the context due to programme implementation remained minor during the reporting period. This is mitigated through working closely with the delivery partner through meetings and monitoring reporting to ensure conflict-sensitive approaches integrated into programme delivery. Conflict-sensitivity is part of WFP’s risk management, and the programme includes dialogue and peacebuilding activities as well as strengthening community-based mechanisms for conflict prevention and management.
Conflict-sensitivity

As CRiSP is operating in conflict-affected environments, there is a risk that the programme has a negative effect on conflict dynamics, resulting in the programme inadvertently worsening the situation. Conflict-sensitivity is one of the key cross-cutting outcomes of CRiSP and so it is anticipated the programme will have positive a positive impact. Conflict and displacement disrupt livelihoods and markets and heighten the pressure on ecosystems and natural resources, often having a dire impact on food security. In fragile areas, resilience-building activities can contribute to addressing the root causes of hunger, inequality and conflict, serving as a buffer to instability and restoring hope. During the reporting period, 1,080 people participated in capacity-strengthening activities focused on inclusive governance, community-based resource management, soil and water conservation, assisted natural regeneration, and cooperative governance, supporting community resilience and social cohesion.

WFP supports a conflict-sensitive and peace-positive approach by prioritising data collection and analysis to enhance its understanding of protection, gender, and conflict sensitivity risks, ensuring a context-specific and risk-informed response. This includes through Integrated Cross-Cutting Context Analysis and Risk Assessment (I-CARAs) – one in Lac province and another focusing on the Sudanese emergency in the East.

To strengthen accountability to affected people (AAP), WFP developed tailored communication plans addressing targeting exercises, pipeline breaks, and nutrition education. Consultations with communities identified barriers to women’s participation in feedback mechanisms where cultural norms limited their ability to voice concerns. These insights are guiding updates to WFP’s community engagement strategy and the development of an action plan for 2025.

In 2025-26 CRISP will further invest in conflict-sensitivity to strengthen programme outcomes. WFP will be working with TetraTech (funded by the UK Land Facility) to lead research on land tenure and conflict-sensitive land restoration practice to inform CRiSP programming as well as the FCDO portfolio programming more broadly.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

In 2024-25, CRiSP was delivered through the Integrated Resilience Programme (IRP) component. This is a programme delivered by the UN World Food Programme (WFP) through a Contribution Arrangement. The Arrangement for the first tranche of funding was from December 2024 – March 2025. There was a pause in the funding in financial year 2025-26 while the FCDO confirmed its budget, and the programme resumed in July 2025.

In 2024-25 the FCDO contributed £4,000,000 to the IRP, of which £3,000,000 was allocated to activities in Chad, and £1,000,000 to activities in Mauritania. The £4,000,000 budget was from the FCDO central Resilience and Adaption Fund (RAF).

WFP has been an efficient, responsive and flexible implementing partner on this programme, both at the level of the Regional Bureau in Dakar, Senegal, and in Country Offices.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The programme was monitored during the reporting period through the FCDO annual review, the delivery partner annual progress report, and FCDO / delivery partner meetings. This year’s annual review was conducted by the Senior Responsible Owner and the Programme Responsible Owner.

Evidence

CRiSP is delivering through the Integrated Resilience Programme (IRP) component, which is a programme that has been delivered by the WFP since 2018. Although there has been no holistic independent evaluation published on the impact of IRP on long-term food security, according to WFP’s own evaluations (based on their Resilience Monitoring and Measurement (RMM) approach) after five years of implementation, the Sahel Integrated Resilience Programme demonstrates significant results on the reduction of negative coping strategies and humanitarian needs , as well as on nutrition outcomes, educational outcomes, social cohesion, social inclusion and women empowerment. WFP estimates that in both 2022 and 2023, including when Niger faced its worst food security crisis in a decade, about 80% of WFP's resilience villages, located in communities identified by the government as extremely vulnerable and representing more than half a million people, did not require humanitarian assistance, resulting in savings of about USD 30 million per year. This resilience capacity has also been demonstrated in villages that have not received cash or food transfers since mid-2021.

Ecosystem restoration also contributed significantly to natural regeneration. A study conducted by USAID and NASA demonstrated the impact of WFP interventions on vegetation greenness, with an average increase in vegetation indicators of almost 50 percent. Communities reported improved land and water access, enabling them to increase and diversify crop and/or livestock production, and eat a healthier diet.
The school feeding programme helped improve children’s overall health and nutrition, enabling them to learn and perform better in school. School feeding also empowered girls by encouraging parents to give them the same opportunity to complete their education as boys. Households indicated that the assets created had reduced daily hardships - many of which are traditionally borne by women and girls - and reported improved access to markets and basic services such as water, sanitation, health and education.

Learning

As the IRP has been delivering since 2018, WFP are in the second phase of their programme (2024 – 2028), which is a scale-up of the first phase. The FCDO Sahel team will also consider how learning from the CRiSP can inform the overall resilience approach, which is a UK priority in the Sahel. In addition, in 2025-26 WFP will be working with TetraTech (funded by the UK Land Facility) to lead research on land tenure and conflict-sensitive land restoration practice to inform CRiSP programming as well as the FCDO portfolio programming more broadly.

One key learning from the reviewed period relates to the challenge of monitoring UK spend within integrated interventions, particularly at sites where the UK is one of several contributors. This has proven difficult in contexts where implementing partners face pressure to reprioritise resources at short notice, combined with the high capacity demands of meeting multiple donor reporting requirements, each with distinct results frameworks.

The FCDO initially proposed aligning UK funding with BMZ (Germany) funding to streamline reporting. However, the team opted against this to retain flexibility in the geographical focus of UK implementation. This decision, while strategic, has increased the reporting burden on the partner, as FCDO request out-of-cycle reporting for activities delivered at co-funded sites.

Going forward, the FCDO will need to integrate these considerations into the development of the results framework to ensure more coherent and manageable reporting expectations.

Date of last narrative financial report	31/07/2025	Date of last audited annual statement	N/A – due 31st March 2026 (covering 1st January 2024 – 31st December 2025)