Business Case

Summary Sheet

Business Plan Summary / The fight against large-scale international corruption and illicit finance is a UK Government priority. In the 2022-2025 Economic Crime Plan, the Government committed to ‘combating the threat that economic crime poses to national security and prosperity by detecting and disrupting money laundering, increasing asset recovery and deterring corrupt actors from using the UK to launder money’. The Foreign Secretary has indicated his high level of ambition for FCDO to address the geopolitical challenges caused by illicit finance, corruption and kleptocracy. This includes advancing collective international security by tackling kleptocracy and hostile state activity; facilitating economic growth by ensuring a secure financial system and by increasing investor confidence; and by tackling the grand corruption challenges to global development and the achievement of the Sustainable Development Goals (SDGs). The forthcoming Anti-Corruption Strategy[1] will reiterate these Government commitments across domestic and international dimensions. / As part of the Directorate Business Plan, the Illicit Finance and Anti-Corruption Department is following through on these commitments by working to make the UK more hostile to corrupt money and illicit finance from other countries, and by tackling the corruption challenges to achieving the SDGs. To this end, IFAC works in partnership with other government departments, law enforcement agencies, the private sector and developing countries. The UK Action Against Corruption Programme (UK ACT) will contribute to these Government commitments by tackling international corruption in the UK connected to developing countries. It will do so by holding corrupt actors to account, restricting their ability to benefit from corruption, and by recovering and returning the proceeds of their crimes to the victim countries for use in development.
[1] Joint Home Office and FCDO strategy to be published in due course, subject to Ministerial approval

Title: UK Action Against Corruption (UKACT) Phase 3
Programme summary (100 words maximum): / UKACT will reduce incentives for corrupt actors to use the UK to launder money stolen from developing countries or for UK nationals or companies to bribe in developing countries. The Programme will achieve this outcome by supporting UK law enforcement to investigate money laundering and bribery cases in the UK which relate to developing countries; and to restrain, recover and return stolen assets to those countries.
What is the rationale for UK Aid spending? (200 words maximum): / Combatting corruption and illicit finance is essential for achieving the Sustainable Development Goals (SDGs). Large-scale corruption drains resources from developing countries, threatens their economic growth and financial stability and hurts the poorest the most. Limiting the crime facilitated by corruption and illicit finance will help ensure more secure borders, reduce the impacts of organised crime and other sources of illicit finance in the UK, and will lead to greater national and economic security for developed and developing countries alike. / UKACT Phase 3 will combat corruption affecting developing countries by tackling the UK ‘supply’ end of corruption and by recovering and returning funds for use in sustainable development. FCDO (and previously DFID) has given long-term support to this programme because of the demonstrable benefits to developing countries, to the global fight against corruption illicit finance, and to international economic security.
Programme Value: Up to £39million		Country/ Region or Sector: / UK/ Developing countries
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		[REDACTED]
Threshold for final approval of Business Case: / Director General
Date of Approval of Concept Note:	14/10/2024	Name and role of Approver / [REDACTED], Director General, Humanitarian and Development
Date of Approval of Business Case:	18/05/2025	Name and role of Approver / [REDACTED], Director General, Humanitarian and Development
Programme Code: / 300597	AMP Start Date: 1 July 2025	AMP End Date: / 31 March 2030
Overall programme risk rating:	Moderate

ACRONYMS

BCIU – Bribery, Corruption and Intelligence Unit
CPS – Crown Prosecution Service
IACCC – International Anti-Corruption Coordination Centre
ICU – International Corruption Unit
IFAC – Illicit Finance and Anti-Corruption
LIC – Low-Income Countries
LMIC – Lower-Middle-Income Countries
MLA – Mutual Legal Assistance
NCA – National Crime Agency
ODA – Overseas Development Assistance
OECD – Organisation for Economic Co-Operation and Development
PEPs – Politically Exposed Persons
POCD – Proceeds of Crime Division
SDGs – Sustainable Development Goals
SFO – Serious Fraud Office
StAR – Stolen Asset Recovery Centre
UKCA – UK Central Authority
UMIC – Upper-Middle-Income Countries

Strategic Case

Background

UKACT is a long-standing programme that began in 2006 to tackle the UK end of grand corruption and bribery affecting developing countries. This is where corrupt actors have used the UK to launder funds stolen from developing countries, or where corrupt actors with a UK connection have bribed or otherwise engaged in corrupt activities affecting developing countries. The current phase began in 2020 and will end in June 2025. The programme supports dedicated UK law enforcement agencies to investigate money laundering and bribery cases in the UK which relate to developing countries, and to restrain, recover and return the stolen assets to those countries. The Programme funds the International Corruption Unit (ICU) and the Bribery and Corruption Intelligence Unit (BCIU) at the National Crime Agency (NCA), and the Proceeds of Crime Division (POCD) in the Crown Prosecution Service (CPS).[2] The Programme supports these key parts of law enforcement in order to achieve impact in developing countries by tackling impunity and returning funds for use in sustainable development, to make the UK a more hostile place for corrupt individuals and to increase international economic and border security. UKACT has become a globally recognised example of innovative anti-corruption work, unique in the OECD.
[2] In early phases of the programme, the Metropolitan Police and City of London Police delivered the programme. However, a Ministerial Anti-Corruption Board decided that the police teams should be merged into a new International Corruption Unit housed at the NCA
From 2006 to 2024, 64 money laundering and 98 bribery cases have been concluded, and over £1.5billion assets have been frozen, confiscated or returned to developing countries. Over the past year alone, the ICU has secured bribery charges against high-profile individuals including the former Minister for Petroleum Resources for Nigeria, and the Chief of Staff to the President of Madagascar, the latter of which swiftly led to a successful conviction in February 2024.
The Programme has achieved A and A+ scores consistently in Annual Reviews since 2015.

The need for FCDO intervention

Combatting corruption is a vital part of achieving the Sustainable Development Goals (SDGs) and addressing geopolitical challenges. Large-scale corruption drains resources from developing countries, threatens their economic growth and financial and political stability and hurts the poorest the most. In some settings, there is a vicious circular link between illicit finance and conflict and insecurity, enabling and further fuelling violence and instability through organised crime, corruption and bribery. Limiting these harms facilitated by corruption and illicit finance will lead to improved economic growth and financial stability, it will help ensure more secure borders and will lead to greater national security for developed and developing countries alike.

Tackling corruption and illicit finance affecting developing countries requires action on several fronts. Actions at country level include long-term interventions to reduce scope for corruption, for example through strengthened institutions, better public financial management, and improved transparency and accountability. Some FCDO posts actively support these areas of work. At the same time, corruption and illicit finance are often international crimes, through which corrupt actors are able to move and hide stolen assets by exploiting regulatory and enforcement loopholes in the international financial system. Any response must therefore include international action to address cross-border money laundering and bribery by foreign nationals and by companies. The Fighting Corruption Globally Programme, another IFAC centrally managed programme, supports this international area of work.

For the UK to play its part in supporting developing countries to fight corruption and tackling international corruption and illicit finance, it has a responsibility to deal robustly with cases where UK entities directly engage in corruption or facilitate corrupt activity. This means taking action in the UK: firstly, to ensure that UK nationals and companies, who engage in bribery or other corrupt practices in developing countries, are held to account; secondly, to recover assets stolen from developing countries and laundered through the UK and to bring the perpetrators to justice; and thirdly to return stolen assets to the affected countries for use in constructive development work. Tackling these aspects of corruption, for which the UK has a direct responsibility, is essential for sustainable development and to maintain the UK’s credibility as a reputable financial and commercial partner. It also contributes to the UK leadership to limit international harms from corruption and illicit finance, by working to ensure increased economic and border security.

FCDO intervention is needed to support developing countries to address three principal challenges of tackling this kind of cross-border corruption. First, developing countries often lack the specialist expertise required to investigate complex economic or financial crimes and obtain the necessary evidence domestically or from other countries. Second, their law enforcement systems are often weak and corruptible (i.e. those under investigation can pay, or place pressure on the authorities, to ensure a favourable outcome) and for this reason, cases taken in the developing country either never make it to court or often end in failure. Thirdly, corruption offences in developing countries often involve offences in other countries, including money laundering through major financial centres, such as the UK.

Competing policy priorities create pressures within UK law enforcement, often meaning that responses to economic crime or corruption in other countries, particularly developing countries, are de-prioritised. Government departments and agencies must balance a range of different priorities which can result in them prioritising cases from countries that pose the greatest risk to the UK, rather than where there may be the greatest harm to developing countries. Although there is overlap, FCDO’s development objectives are focused on addressing poverty reduction and FCDO funding can ensure the extra time and effort is put into identifying, investigating and pursuing cases from developing countries. In this programme, FCDO funding will be ring-fenced for investigating cases relating to the developing countries which are eligible for ODA. Taking these cases has been shown to bring big dividends, not only in the financial value for developing countries, but in the symbolic value of tackling impunity. Without FCDO funding and intervention, it is unlikely that cases from poorer, developing countries would secure adequate attention in the UK law enforcement and justice system.

Failure to act on corruption cases has costs for UK economic and security goals. With the importance of the financial sector to the UK economy, it is vital that corrupt individuals are not allowed to use UK financial systems with impunity and that reputable investors are not deterred because of weak implementation of safeguards in the UK. Where money laundering through the UK and overseas bribery by UK businesses continues unchecked, there is a cost to the UK in reputation and credibility as a development and commercial partner.

Intended Outcomes and Impact for beneficiaries
The intended outcomes are:
1. To tackle impunity by ensuring that individuals and companies committing corruption offences in the UK which relate to developing countries, are brought to justice;
2. To recover assets stolen from developing countries and laundered in the UK; and
3. To return stolen assets to the victim countries for use in constructive development work.

These outcomes will primarily benefit people in developing countries but will have a secondary benefit of maintaining the UK’s credibility as a reputable financial and commercial partner and lead to more secure economic and financial systems.

Summary of what the Programme will deliver

The intelligence and investigation teams at the NCA will identify and investigate a portfolio of anti-corruption cases with a UK nexus, leading to criminal and civil actions through the courts. They will work with Border Force, Sanctions Directorate (FCDO) and other parts of UK Government to disrupt and deter corrupt individuals and companies from using the UK for their crimes. They will work to prevent corruption through communications and outreach work, such as with the financial sector, lawyers and accountants. Following successful convictions by CPS prosecution teams (not FCDO funded), the specialised CPS team funded by this Programme will pursue the confiscation of assets. In the first year of the Programme, we will identify an additional partner to work with developing countries to ensure their requests for mutual legal assistance in corruption cases are not undermined by insufficient expertise in working with the UK legal system.[3]
[3] In the previous phase of the Programme, the FCDO provided funding for two staff from the UK Central Authority, (UKCA) in the Home Office, to develop and carry out work on mutual legal assistance. However, COVID 19 budget reprioritisation and Home Office headcount constraints meant that after two years, this work had to stop. Now that FCDO resources are available again, the Programme Team is looking to re-start this work and will consider a range of possible partners for this work.

Assurances

Counter Terrorist Financing
The risks associated with terrorism and criminal financing in this programme are considered low. A fundamental part of the work is based on NCA intelligence sources, and any cases found to have links with terrorism and criminal financing will be passed to the teams in the NCA or police working on these areas.

Public Sector Equality Duty
UKACT Phase 3 is unlikely to impact negatively on protected characteristics. This programme does not directly address gender inequality and does not gather data on the impact of gender. Academic research into the gender dimensions of corruption, including the impact of anti-corruption interventions on women and girls, is thin and in many cases anecdotal. The research on whether female politicians are more or less corrupt than their male counterparts is inconclusive and there has not yet been a significant academic study on the gender dimensions of grand corruption.

Climate and Environment
There are no climate or environmental risks identified in this programme. In terms of the Paris Alignment and International Climate Finance, the Programme is not climate sensitive.

Partnership Principles
UKACT Phase 3 does not intend to use Partnership Principles for programme management and monitoring based on the Programme Operating Framework (PrOF) guidance. We will however ensure that there is robust management and monitoring of the programme during its life cycle.

Safeguarding
UKACT Phase 3 will follow the FCDO’s ‘do no harm’ policy and ensure that safeguarding plays a role in promoting sustainability and good value for money. Partners are OGDs and have strong processes regarding safeguarding in both domestic and international settings. Commitments to safeguarding will be kept under review throughout the programme.

Appraisal Case

The strategic case outlines that developing countries need support to address the challenges of tackling cross-border corruption. The nature of corruption in developing countries is that many cases involve offences in other countries, yet those same developing countries often lack the specialist expertise to pursue complex cross-border economic crimes. This is often due to a combination of a lack of technical capacity, politicised rule of law agencies, or political interference. Major financial centres such as the UK are often used by corrupt individuals involved in money laundering and bribery to move or hide corruption gains as financial or physical assets. We will address this need by continuing to provide FCDO funding for dedicated law enforcement teams in the NCA and CPS, and by providing additional support to a partner on mutual legal assistance.

The current UKACT Programme will have provided up to £32m[4] from 2020/21 to 2024/25 to UK law enforcement authorities, primarily to the ICU, to investigate money laundering and bribery cases with a UK nexus which relate to developing countries. The ICU has first and foremost an investigation function which seeks to achieve criminal justice outcomes in the UK, specifically prosecutions for bribery, money laundering, and related crimes. Case selection relies on several factors such as: the jurisdiction of UK courts; the location and accessibility of evidence; the likelihood of being able to bring suspects to trial in the UK; and the public interest and deterrent effect of any potential case. [REDACTED]. Providing funding for outreach to the regulated sector, civil society, international networks, domestic and overseas authorities, trade associations, are also important features of this programme.
[4] This was reduced from £39 million over 5 years as a result of COVID 19 related budget reductions.

The evidence of the direct impact of the earlier phases of this Programme is impressive. As of November 2024, and since the Programme began in 2006, £1.5bn of assets stolen from developing countries have been restrained, confiscated or returned. Such successful prosecutions of corrupt individuals and companies send a strong message that impunity towards corruption in developing countries can and will be addressed by the UK; and that assets can be recovered and returned. The 2018 independent evaluation of the Programme confirmed this assumption, and a case study of Nigeria indicated that the UKACT Programme had made the UK less attractive to corrupt Politically Exposed Persons in Nigeria as a place to launder money.

This Programme aims to reinforce UK law enforcement, and to achieve this objective, the supplier must also be drawn from UK law enforcement. There are alternative law enforcement partners other than the NCA, which could deliver some or part of the programme, such as the Serious Fraud Office, the City of London Police, the Metropolitan Police and regional police forces. However, the SFO has a focus on large complex corporate cases, predominantly in the UK, the London police forces have a region specific rather than national or international role, and regional police forces lack the same level of access to international networks and proactive intelligence collection mechanisms. Although this limits delivery choices, the Programme team commissioned a Lessons Learned Assessment to explore how to improve the effectiveness of the Programme, and to generate ideas to include in the next phase. This exercise has demonstrated that the NCA and CPS teams remain the most appropriate delivery organisations for the new phase of FCDO support.

The Assessment also confirmed the high performance of the Programme against its log-frame targets but noted that given the scale of the global corruption problem, a significant increase in impact would only be possible if Programme achievements are leveraged in new ways, and if a wider range of anti-corruption tools were used more effectively. The Assessment therefore recommended doing more to leverage the wider UK anti-corruption ‘ecosystem’ to increase the impact of the new phase of the Programme. By ‘ecosystem’, the Assessment referred to the range of organisations within the broader UK anti-corruption network ranging from professional regulators and other government departments through to civil society. As well as more strategic collaboration and outreach to a wider range of partners, the Assessment recommended increasing existing anti-corruption civil recovery work, and other disruptions to corrupt activities that complement both BCIU’s intelligence work and ICU’s criminal investigative work. The Programme Team believe these recommendations align with existing proposals developed with the teams at the NCA for more civil recovery and outreach work and they will consider the additional ideas to leverage greater impact.

Feasible Interventions at the NCA

Based on discussions with delivery partners and the recommendations of the Learning Assessment, the Business Case has considered increasing capability at the ICU to deliver an increase in the current portfolio of criminal and civil cases; increasing targeted outreach work; and increasing technological capacity.

On an increase in capability: Currently, the FCDO funds 52 posts in the ICU and 14 posts in the BCIU, with 4 potential new posts. However, there are significant resourcing constraints at the NCA that FCDO is unable to alter, in particular, the competing law enforcement priorities. [REDACTED]. There is also an extremely competitive market for well-trained staff that makes recruitment and retention challenging, even without headcount constraints. Increasing the ICU’s headcount by more than a small incremental amount is therefore unlikely in the early years of the next phase of the Programme. Discussions on a 25% larger FCDO budget of £50 million are therefore unrealistic for NCA, and now also for FCDO after the reduction of the ODA budget to 0.3% of GDP. [REDACTED]. Sustained senior engagement from FCDO with NCA and HO management will be needed to support the continued provision of adequate NCA staff resource to the ICU and BCIU.

On increasing capability by delivering increased civil recovery cases, the ICU & BCIU continue to assess intelligence sources, such as from the regulated sector into the FIU, for opportunities to deploy civil recovery options. They are also aiming to increase the use of account freezing/forfeiture or listed assets orders against PEPs who have transferred misappropriated assets to the UK. For more complex civil recovery matters, such as property freezing orders and unexplained wealth orders, the ICU continues to work closely with a sister department within the NCA.

The ICU will aim to recruit four more staff at a cost of £300k per annum over 5 years to cover an increase in civil and criminal capability. Additional funds will be allocated in the budget should a greater increase be possible in outer years.

On an increase in targeted outreach work, most UK businesses and nationals operating in developing countries aim to do business cleanly. However, following investigations under this Programme, some UK businesses and nationals have been convicted of paying bribes to secure lucrative contracts and to facilitate corrupt procurement in developing countries. Proactively pursuing overseas bribery and corruption cases such as these is a critical part of tackling corruption to maintain pressure on UK companies to do business cleanly and to send a message that the UK has zero tolerance for overseas bribery and corruption by its own companies and nationals. Building relations with global partners, industry, regulated sectors, other law enforcement and civil society is also a critical part of this work.

[REDACTED] ICU staff have continued to undertake outreach work on an ad hoc basis. The impact of this work has been significant. For example, the ICU is a member of the OECD Working Group on Bribery, and in this role, they have: provided experts for many peer reviews, including South Africa, Brazil, and Japan; advised on law enforcement matters by providing expertise on trends and modern investigative techniques; and been part of regional OECD networks supporting developing countries on asset recovery techniques and mutual legal assistance matters. Following the successful convictions under the Madagascar case, mentioned above, the ICU has increased engagement with the domestic and international extractives sector, to increase the sector’s knowledge of bribery and corruption risks, and to improve access to law enforcement action. [REDACTED].
The Learning Assessment and discussions with delivery partners have led to the conclusion that both the ICU and FCDO need enhanced outreach and communications capacity to leverage greater impact for the Programme. The ICU will investigate reinstating their previous outreach post and FCDO will introduce a programme-funded post. The ICU-based role would focus on outreach and networking with developing countries, the regulated sector and with UK businesses; and include case-work related interventions and mentoring, where relevant. The objective would be to share knowledge and expertise, as well as to encourage reporting of offences and to create stronger relationships with stakeholders such as civil society and regulators.

The programme-funded staff member in the FCDO will leverage the anti-corruption ‘ecosystem.’ The base in the FCDO will be able to increase the impact of the Programme across HMG by working more effectively with key parts of government, such as the Sanctions Team, the Home Office Passport Confiscation Team, HMRC tax investigations, and teams working on professional enablers. This role would also draw on the range of existing preventive and disruptive work aimed at strengthening in-country initiatives on beneficial ownership and PEPs, monitoring high value procurements (especially in strategic minerals, oil and gas, energy and transport) and supporting extractives industry transparency initiatives, strengthening parliamentary oversight and media outreach assisted by civil society.
The ICU and FCDO roles would be complementary and co-ordinate with the Joint Anti-Corruption Unit in the Home Office. It is also envisaged that the two outreach roles would include developing a communications strategy and delivery plan to leverage greater impact. The Programme Team are planning to introduce the FCDO programme-funded role from FY26/27 once the details are worked out with the Centre for Delivery. A Business Case addendum will then be submitted at that stage. The budget for the programme funded posts are set out below:

FCDO programme-funded post – 4 year costs
	2026/27	2027/28	2028/29	2029/30	Total
1 x HEO outreach and engagement officer (salary, onboarding costs, travel)	£100,000	£100,000	£100,000	£100,000	£400,000

On the proposal to increase the technology capability of ICU. Currently, the FCDO funds 52 posts in the ICU and 14 posts in the BCIU, with 4 potential new posts. However, there are significant resourcing constraints at the NCA that limit how many new posts FCDO can fund. However, as ICU cannot grow significantly in terms of staff numbers, it needs to work more smartly to achieve greater results. Improving its technology capability is the key to this [REDACTED] Successful implementation of these projects could save investigators in the region of 20-40% of their time and generate savings on contracting expensive legal teams to review material. [REDACTED]
The following table shows a forecast across the next five years for the NCA’s ICU and BCIU. Due to ongoing work on the Spending Review, the UKACT 2025-2030 Business Case approval process was delayed. Therefore, the 2020-2025 Business Case was extended until 30 June to cover funding for Quarter 1 of FY25/26.

NCA International Corruption Unit and Bribery and Corruption Intelligence Unit – 5 year costs
	2024/25	Q1 2025/26	Q2 – 24 2025/26	2026/27	2027/28	2028/29	2029/30
Staffing costs	£4.95m	£1.36m	£3.94m	£5.38m	£5.54m	£5.36m	£5.48m
General operational costs[5]	£1.3m	£340k	£1.16m	£1.52m	£1.56m	£535k	£550k
Funding per financial year	£6.25m	£1.7m	£5.1m	£6.9m	£7.1m	£7.25m	£7.4m
[5] FCDO currently pays for general running costs of both Units, including but not limited to: staff pay and allowances, travel and operational costs, premises, training and development, and transport.

Feasible Interventions with CPS Proceeds of Crime Division (POCD)

The level of asset recovery work by the CPS and their POCD is linked to the level of activity of the ICU. As ICU investigations are expected to increase, CPS will require one additional specialist prosecutor post from FY2027-28.

The cost of a London-based Specialist Prosecutor including costs is expected to be approximately £105,000 in FY25/26.

Crown Prosecution Service – 5 year costs
Q1 FY25/26 / 1 FTE	Salary costs 2025/26 / 3 FTE current resource +2%	Salary costs 2026/27 / 4 FTE +2%	Salary costs 2027/28 / 5 FTE + 2%	Salary costs 2028/29 / 5 FTE +2%	Salary costs 2029/30 / 5 FTE +2%	Total
£105K	£310K	£420K	£540K	£550K	£560K	£2.485m

Feasible interventions to build capacity on mutual legal assistance (MLA).

The cross-border nature of the ICU’s investigations means that international requests for evidence are an essential part of the work. This includes evidence requests made by the ICU to other countries, but also evidence requests to the UK from overseas law enforcement agencies. The UK Central Authority (UKCA) in the Home Office handles these incoming and outgoing MLA requests, many of which need extra work and support to enable developing countries to build their capacity to use the international and UK systems. Without this support, progressing ICU investigations would be far more difficult. It is therefore proposed to fund up to two new posts to provide training and capacity building to developing countries with cases being investigated by the ICU. One option being explored is providing staff at the UKCA, together with funding for travel to meet overseas partners to advise on preparation and submission of MLA requests. However, Home Office staff constraints and the outcome of the spending review will not be known before the start of the Programme, so the Programme Team will explore other options, such as a partnership with the International Anti-Corruption Centre (IACCC) or the International Centre for Asset Recovery (ICAR), whose work also involves capacity building on MLA with developing country partners. The World Bank’s Stolen Asset Recovery Centre (StAR) or a stand-alone procurement contract / commercial tender with the private sector, are also options. Outputs would be reflected by a new measure in the log-frame to assess progress on the number and quality of ‘international letters of request’.

Mutual Legal Assistance work – 4 year costs (for FCDO staff)
	Salary costs / 2026/27	Salary costs 2027/28	Salary costs 2028/29	Salary costs 2029/30	Total
Staff costs	100k	£200k	£200k	£200k	£700k

Options for UK ACT Phase Three

Discontinuing support to this flagship Programme is not a viable option. Doing so would almost certainly end the UK’s capability at scale to recover stolen assets from developing countries and to tackle UK bribery in developing countries. It would also fail to deliver on the Foreign Secretary’s high ambition for tackling international corruption and illicit finance. The following three options offer a 25% smaller programme by the end of 5 years, a standstill programme, and a 20% bigger programme (recommended).

Option 1: A gradual decrease of programme funding over a five-year period from the current allocation of £6.65 million to the NCA and CPS (based on FY24/25). This gradual decrease would allow for the completion of current cases already in the process of investigation or already in the courts. It is estimated that a gradual decrease to a 25% smaller programme of £4.8million per year could be achievable by the final year of the programme in 2029/2030.

This option would gradually decrease funding from the 2024/5 level of £6.65 million per year down to an estimated £4.8 million per year. The decrease in budget would allow for the completion of the existing portfolio of cases over the next 2-3 years and limit the new cases added to the portfolio. If this option is chosen, it is essential to understand that withdrawing from cases early would potentially lead to financial penalties against the NCA, for example for wrongful arrest and imprisonment, and would also require any seized funds to be returned. This could lead to a far greater cost to HMG than continuing the cases to completion.

This option is not recommended because it would not align with the Foreign Secretary’s ambitions to push the UK system to achieve more on anti-corruption and illicit finance. Such a reduction in the budget of one of the UK’s flagship anti-corruption initiatives would also attract significant negative media attention and criticism from well-placed civil society and international organisations.

Table 2. Option 2 - Maintain funding at current levels (2024/2025 budget) by providing up to £31.47m over five years with approximately £30million of the budget allocated to ICU and BCIU in NCA (£6.25million per year); and £1.92million to POCD in CPS (£405k per year).[6]
[6] The figures in brackets show the Q1 FY25/26 amounts that have been funded through the existing programme.

This option would maintain funding at 2024/5 levels. This option is not recommended because: it would not enable any increase in staff capacity or in the number of criminal cases investigated; it would not include funding to increase NCA capacity in civil cases; and it would not enable much-needed to work to improve mutual leadership assistance (MLA). Such a real-terms reduction in the budget of one of the UK’s flagship anti-corruption initiatives would not align with the Foreign Secretary’s ambitions to push the UK system to achieve more than in recent years on corruption and illicit finance. This effective budget reduction would also attract significant negative media attention and criticism from well-placed civil society organisations and parliamentarians.

Table 3: Option 3 (Recommended) - Provide up to £39million over five years with approximately £34million of the budget allocated to ICU and BCIU in NCA; nearly £2.4million to POCD in CPS; £700k for a new partner on MLA work; and up to £400k for a dedicated outreach post based in FCDO.

This would maintain the existing level of work and taper up to provide an additional £1.9million by the final year of the programme which would:

- Maintain current levels of funding to ICU, BCIU and CPS POCD to deliver the work;
- Provide additional funding for a small increase staff capacity at the ICU, BCIU and CPS POCD to deliver additional asset recovery cases, civil recovery cases and disruptions;
- Add new technological capability in ICU and BCIU to increase capacity and effectiveness;
- Provide new support to MLA work with developing countries in years 2-5 of the Programme.
- Provide new resourcing on outreach and engagement with business, the financial sector and other potential corruption enablers, to incentivise prevention and disruptions; and to increase the impact of the Programme in the UK and developing countries. This resourcing will include a programme funded staff member from FCDO.

This option would increase the overall disruptive capacity of the NCA teams by approximately 20% on current levels, leading to a higher number of both criminal and civil cases. This in turn would lead to an increase in assets eventually available to return to affected / source countries.

Option 3 would also be the most effective at delivering the Programme outcome: by increasing the reputational risks, decreasing the financial rewards and reducing public tolerance for corruption, incentives for corrupt individuals to engage in money laundering, bribery and corruption in the UK will be reduced. The work will also reduce outgoing money laundering, bribery and corruption by UK companies and nationals.

This overall outcome will lead to the desired programme impact: The culture of impunity for corruption is reduced in developing countries by the UK taking action to recover and return assets in the UK stolen from developing countries; and by pursuing UK-linked companies and nationals who bribe in developing countries.

Value for Money Statement

The first four years of the current phase of the Programme have demonstrated excellent value for money, with over £441m of assets subject to restraint, against current programme spend of approximately £28.6m. In addition, since 2020, 27 individuals or entities have been charged, and 25 individuals or entities have been successfully prosecuted (including charges from before 2020). We expect a new phase to achieve similar results commensurate with the proposed increased level of resourcing.

Theory of change

IMPACT: the culture of impunity for corruption is reduced in developing countries by the UK taking action to recover and return assets stolen from developing countries; and by UK Action to pursue companies and national who bribe in developing countries.

.

OUTCOME:
Incentives are reduced for corrupt individuals in developing countries to use the UK to launder money: or for UK business and UK nationals or their agents to bribe in developing countries.

Output 2:
The sustained level of prevention and disruption of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting LICs, LMICs and UMICs and with a connection to the UK. This includes prevention and disruption activity targeting professional enablers and efforts to deny access to proceeds of corruption and recovery of assets using civil powers

Output 1:
The sustained level of investigation of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting LICs, LMICs and UMICs and with a connection to the UK. This includes the investigation of related activity by professional enablers and efforts to recover assets using civil powers

Output 3:
Sustained level of stolen assets frozen, recovered and returned to developing countries by HMG or leading to referrals to other agencies

Output 4:
Enhanced tactical and strategic intelligence on UK-linked corruption affecting developing countries to initiate new investigations and to inform existing ones

Output 5:
Increased ICU capacity and leadership enhances UK and developing country capacity to fight global corruption and the effectiveness of international law enforcement activity in AC.

Commercial Case

This section sets out the arrangements for implementing this programme and achieving value for money under Option Three – a total cost of up to £39million.

The programme will be delivered through partner organisations: Initially this will be NCA and CPS and then a partner on the MLA work will be determined in the first year of the Programme. FCDO has strong existing relationships with the CPS and NCA through the existing phase of UKACT and these established relationships will aid effective coordination during implementation of the new phase of programming.

This section outlines where we will continue existing approaches and where we will take further action to maximise economy, efficiency, effectiveness and equity. Some of the usual commercial considerations are not applicable: due diligence is not required for delivery through HMG organisations; incentives such as payment by results will be inappropriate; and rule of law principles of judicial and police independence preclude FCDO’s involvement in operational decisions. It is important to recognise that some fundamental barriers to the achievement of quick results are not inherently undesirable: while cases may take several years to progress through the justice system aspect of defendants seeking multiple appeals, due legal process is a central tenet of the rule of law and a strength of the UK legal system. The additional funding will include a small increase NCA capability to pursue developing country assets through faster civil recovery routes where appropriate and be a potential multiplier on the overall number of cases pursued.

Delivery Mechanism

As NCA and CPS are Other Government Departments, we will set up new Memoranda of Understanding (MoUs) with each organisation following approval of this new programme. Each MoU will set out what each organisation will deliver to realise the programme outcome and how they will deliver it within the agreed budget for each year, consistent with arrangements in place covering the 2025- 2030 period. When the MLA partner is decided, we will set up an MoU or contract, depending on the partner.

Core competences of organisations to deliver

CPS and NCA have a track record of delivering on anti-money laundering, intelligence and economic crime (NCA) and asset recovery (CPS). The former Department for International Development had successfully partnered with the CPS since 2011 and with NCA since 2012. FCDO also funded UKCA through the current phase of UKACT in FY20-21 to FY21 - 22 to increase their capacity to work with developing countries on MLA cases. FCDO also funds the IACCC and ICAR through the Fighting Corruption Globally Programme.

These organisations have demonstrated clear capacity to deliver, but they are not isolated from the external context in which they work. Corruption cases are complex. The time taken to investigate, prosecute and, if successful, secure and recover assets spans several years. CPS has seen and will continue to see a general increase in the complexity of cases prosecuted and the time taken to conclude cases. The NCA has the expertise required to work on these cases but there are competing demands on their time and resources, which continues to pose some risks to their consistent ability to deliver at full capacity.

Programme governance and oversight
FCDO’s role in managing internal delivery risks to the NCA and CPS caseload is limited, as we ensure operational independence is maintained. However, the UKACT High Level Meeting of senior leaders from each delivery partner, and the regular reporting allows us to monitor and manage the higher level contextual risks, monitor the processes partners have in place to manage slippage or fiduciary risk with third parties (a small proportion of costs which will include procuring training, travel, vehicle leasing and overheads), and risks of internal corruption. Where needed, we will also use levers outside of the High-Level Meeting to drive improvements in capability to deliver, and to escalate significant risks.

Delivery of outputs

For each organisation, the same management principles will apply, namely: invoices will be paid quarterly in arrears on the basis of satisfactory narrative and financial reports. Payments will be made on the basis of an agreed budget to cover staff salaries (costs are predominantly linked to specific teams and posts in each organisation). The NCA and CPS teams were established to deliver the specific work of this programme and are monitored to ensure the funding is not used for other work in the organisation. The new work on MLA will be designed to ensure work undertaken is tapers up to two full time staff. Progress with all partners will be checked through monthly phone calls, quarterly reporting, High Level Meetings, annual reviews and other evidence of progress against the agreed milestones. This will be specified in the MOU with each partner.

Programme-funded costs

The Programme would fund new resourcing for an HEO outreach and engagement officer based within the FCDO. This will complement an existing role, currently unfilled, in the ICU. Improving outreach and communications for the UKACT Programme has been a consistent recommendation in Annual Reviews and is essential to maximising the deterrent impact of the programme’s achievements. The last Annual Review noted that there is potential for significantly greater impact at a strategic level from a more systematic and coordinated cross-HMG approach to outreach, and that successful outputs in FY23/24 make a strong basis for investment in engagement and outreach. A robust coordinated outreach strategy would consider how best to deliver UKACT’s impact statement to reduce the culture of impunity in developing countries towards corruption. The programme-funded cost for this post is estimated to be £100k per annum and has been included in the disbursement schedule.

Opportunity to reduce costs

Use of mechanisms such as payments by results or short-term break clauses to drive efficiency in delivery would set up perverse incentives and be inappropriate as the principal costs of the programme are salary costs for staff in UK government agencies on agreed terms and conditions.

However, FCDO will continue to carefully review the detailed annual and quarterly budgets proposed by the organisations and push for improved economies where these are possible. The possible economies relate to the percentage spent on overseas travel and procurement. For example, the ICU has now moved to more effective systems of procurement on car leasing: they lease rather than purchase cars as efficiency savings can be made.

Financial Case

The existing UKACT Programme for 2020-2025 has been extended for 3 months while the funding for the new programme under this Business Case is considered as part of ongoing work on the Spending Review. The first quarter of 2025/26 has therefore been funded by the existing UK ACT Programme.

Profile and forecasting

Funding for UKACT will be sourced from the Illicit Finance and Anti-Corruption (IFAC) Department programme budget (RDEL). The budget is profiled as pipeline on the FCDO financial management system (HERA) and the Aid Management Platform (AMP). The tables below show the annual budget for each implementing partner for the final year of the Programme (FY2024-25 and Q1 of FY25/26); and indicative annual budgets for 2025-30 for Options 2 and 3. As Option 1 involves a gradual decrease to programme budgets, this is difficult to predict and therefore forecasted allocations have not been included here.

Table 1. Current Programme Phase budget: 1 April 2024 – 30 June 2025

	2024/2025	2025/2026 Q1
NCA	£6,250,000	£1,700,000
CPS	£404,547.40	£105,000
Totals per financial year	£6,654,547.40	£1,805,000

Table 2. Option 2 - Maintain funding at current levels (2024/2025 budget) by providing up to £31.47m over five years with approximately £30million of the budget allocated to ICU and BCIU in NCA (£6.25million per year); and £1.92million to CPS POCD (£405k per year).[7]
[7] The figures in brackets show the Q1 FY25/26 amounts that have been funded through the existing programme.

	2025/2026 Q1	2025/2026 Q2-Q4	2026/2027	2027/2028	2028/2029	2029/2030	Total
NCA	(£1.7m)	£4.55m	£6.25m	£6.25m	£6.25m	£6.25m	£29.55m / (£31.25m)
CPS	(£105k)	£300k	£405k	£405k	£405k	£405k	£1.92m / (£2.025m)
Totals	(£1.805m)	£4.85m	£6.655m	£6.655m	£6.655m	£6.655m	£31.47m / (£33.275m)

Table 3: Option 3 (Recommended) - Provide up to £39million over five years with approximately £34million of the budget allocated to ICU and BCIU in NCA; nearly £2.4million to CPS POCD; £700k for a new partner on MLA work; and up to £400k for a dedicated outreach post based in FCDO.[8]
[8] The figures in brackets show the Q1 FY25/26 amounts that have been funded through the existing programme.

	2025/2026 Q1	2025/26 (Q2-Q4)	2026/27	2027/28	2028/29	2029/30	Total
NCA	(£1.7m)	£5.1m	£6.9m	£7.1m	£7.25m	£7.4m	£33.75m / (£35.45m)
CPS	(£105k)	£310k	£420k	£540k	£550k	£560k	£2.38m / (£2.485m)
MLA Partner			£100k	£200k	£200k	£200k	£700k
FCDO Outreach officer (HEO)			£100k	£100k	£100k	£100k	£400k
Baseline and Evaluation		£100k				£100k	£200k
Totals	(£1.805m)	£5.51m	£7.62m	£7.94m	£8.3m	£8.56m	£37.43m / (£39.235m)

The final year-by-year profile for UKACT will be agreed prior to the start of the programme in consultation with all
implementing partners. Indicative allocations are based on consultations with implementing partners on their future funding requirements over the next five years. This will give us flexibility to respond to changing needs, as well as allowing FCDO to respond to internal budget pressures that may emerge.

Funding

The key cost drivers will be salary costs of operational officers and lawyers. However, the NCA will also use funding to cover general administrative costs, training and development, travel, conference costs, technological capabilities, and to improve outreach and engagement.

The FCDO will assess performance in line with funding agreement terms and conditions. The principal monitoring and reporting mechanisms for this programme will be as follows:

- Regular communications with each agency to determine forecasting, to approve large purchases, and on key issues that arise;
- Reporting against progress by partners on a quarterly basis and discussed at quarterly meetings;
- Quarterly High-Level Meetings with senior staff in each implementing agency (chaired by IFAC DD and attended at similar levels).
- Annual reviews by FCDO.

There are no anticipated tax liabilities that should arise as a result of FCDO’s support to the above organisations. We have confirmed that VAT is not payable.
Approval

The Concept Note has been approved by the Director General under the delegated authority of the Minister of State. The anticipated amount of programme spend will be reviewed and approved at Director-level, in accordance with the delegated authority rules.

Assets
The NCA will be required to maintain a complete, accurate and up-to-date inventory of assets which will be reviewed quarterly. At the end of the programme period, the team will, in consultation with the NCA agree how best to dispose of any assets in line with HMG asset policies.

Financial and Fraud Risk Assessment

The financial risk in this programme is assessed as low. The programme only disburses funds to UK law enforcement agencies, and the fraud risk relates to FCDO’s finances being misused by the law enforcement partners. As a government agency, the NCA and CPS have rigorous procedures in place to prevent fraud and FCDO monitors this risk through the risk register, and through regular discussions with partners.

Management Case

Management arrangements for implementing the intervention

The Programme will be managed by the Illicit Finance and Anti-Corruption (IFAC). IFAC holds the policy leadership for FCDO’s investments in worldwide efforts to tackle corruption and illicit finance and promote accountability. IFAC operates at both the international and UK levels but also supports HMG teams on corruption agendas and FCDO country offices to deliver their anti-corruption programmes and approaches.

IFAC Resources (Core Team)	Grade	FTE
Deputy Director	SCS	2%
Programme leadership SRO	Grade 6	10%
Programme leadership PRO	Grade 7	50%
Programme day to day management	HEO	70%

The Programme will have an overall Grade 6 Senior Responsible Owner (SRO)., who will be accountable for the programme meeting its objectives, delivering the required outcomes and making expected contributions to higher-level objectives. The SRO will be supported by the Programme Responsible Owner (PRO) at Grade 7 and a Programme Manager at HEO. The PRO, supported by the Programme Manager, will be accountable for driving the delivery of programme outcomes, effective risk management, relationship management, financial control of the programme and compliance with PrOF rules. These posts will form the programme leadership and management for UKACT.

Following approval of the Business Case, new MoUs will be agreed with NCA and CPS before the start of the next phase of the programme to ensure the continuity of staffing, resources and investigations with minimal disruption. As this next phase of programming proposes a scale-up in staffing resource, technological capability and outreach and engagement, the first two years of the programme will likely not see it operating at full capacity. This has been reflected in budgets, anticipated results and monitoring. We will agree revised log frame results with indicators and milestones with partners and finalise reporting arrangements as part of the MOU.

The PRO will convene quarterly meetings to track results, risks, strategic and technical issues and report any significant issues arising to the SRO and Head of IFAC. Regular contact with implementing partners will ensure the programme stays on track. The programme delivery plan will set out how the objectives will be pursued, with the logframe outlining the expected results and the activities being undertaken against core spend. We will carry out annual reviews and build on the HQ-led thematic evaluations or research, making any necessary adjustments to the programme. We will dedicate time to monitoring activities over the life of the programme to achieve results more effectively and improve performance. All agreements will contain an exit clause allowing a termination should partners consistently fail to deliver results and/or where fraudulent or unethical activities occur.

Risk identification and management

Overall, the programme risk is moderate. In line with the FCDO overarching risk appetite statement, UKACT has a cautious appetite for external context risk corruption (reputational, policy and programme delivery, strategy and context, and people) as we work in challenging circumstances to end corruption. This is complemented by our minimal appetite for fiduciary, safeguarding, and public service delivery risks, which are managed through our active engagement with programme partnerships, consistent documenting of our successes and adherence to PrOF rules.

Risks have been identified and assessed based on their likelihood and impact and each risk rated (minor (green), moderate (yellow), major (amber) or severe (red), and under the following broad areas: external, delivery, operational, safeguarding, fiduciary and reputational. The Programme team will continue to track all risks associated with this Programme in an internal risk register, which will be reviewed quarterly by the SRO, Programme and Programme Manager, as well as at Annual Reviews. If any risks increase beyond our risk appetite, or an adverse event happens whether it has previously been identified or not, the FCDO procedures will be followed to escalate and take controlling actions as appropriate. The Programme’s current Risk Register is set out below:

Risk Description	Gross Risk	Mitigation	Residual Risk
Progress of cases slow and / assets not returned in a timely way because of delays in the justice system caused by the pandemic and other factors.	Moderate	Regular high-level meetings between FCDO, CPS and NCA will provide evidence to monitor the delays and level of risk. However, the delays are outside the control of the Programme and partners, so the risk remains high. / Escalate risk to cross-HMG / fora.	Moderate
Staff in the ICU are surged or otherwise moved by the NCA into other roles because of high demand on other policy areas, thus undermining the work of ICU.	High	High level meetings between FCDO and NCA keep the situation under review. Issues escalated to Ministers where necessary.	Moderate
Difficulties in recruitment due to small pool of financial investigators, and current staff moving to private sector. Headcount restrictions in NCA.	Moderate	ICU have explored expanding remote working options and posting staff living outside of London. Exploring potential to use technology to mitigate.	Moderate
Uncertainty of resourcing for the Programme (FY25/26 – 29/30).	Moderate	High ministerial priority; strong concept notes from ICU/CPS	Minor
Prioritisation of geopolitical and strategically important countries, to the detriment of LMICs. An increased focus on Russia and Ukraine, could detract NCA resources away from LMICs.	Minor	Ensure ODA criteria and focus on LMICs continues. Ensure that OGDs non-ODA contributions to NCA and CPS maintained despite resource constraints. / Monitor staffing levels in ICU.	Minor
Lack of communication on impact of programme reduces deterrent impact	Minor		Minor
Fraud and corruption risk from partners misusing programme funds.	Minor	Both partners are OGDs, and therefore also have zero tolerance to fraud/corruption. However, there are safeguards in place for approving payments and ensuring SRO approval. The Programme Team provide any conflict of interest returns as and when they arise. We alert partners to Aid Diversion Standards and encourage regular discussion about risk.	Minor
Partner organisations do not have robust safeguarding procedures in place, and this results in staff being at risk.	Minor	Although enhanced due diligence checks are not required due to partners being OGDs, the Programme Team regularly engage with partners to check understanding and compliance; and to request regular updates of partner risk registers and review. NCA staff are required to be subject to regular and detailed vetting.	Minor

Monitoring, learning and communications

The log frame for the current phase of the Programme (2020 - 2025) with results up to FY23/24 is available on the DevTracker website (DevTracker Programme GB-GOV-1-300597 Documents). Annex 1 shows the logframe for FY24/25 (1 April to 31 March) which uses FY23/24 results as a baseline and indicates targets.

A log frame for Phase 3 will be reviewed before the start of the new phase and regularly throughout the life of the programme to provide sufficient flexibility to adapt to changing conditions. Progress against targets will be verified during quarterly reporting and annual reviews.

An extensive evaluation of the programme was completed in 2018/19, and a lesson-learning review was conducted in 2024. A baseline study will be conducted at the beginning of the Programme and an evaluation towards the end of its five-year term.