## Sheet1
PROJECT NAME | Building Smart (Safer, Greener and Sustainable) Health Care Facilities in the Caribbean and Beyond STRENGTHENING THE SMART AFTER-CARE PROGRAM AND PROMOTION OF THE ‘SMART’ STANDARDS AS A BLUEPRINT (Business case # 400370-401)
Version: May 21 2025-final
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (August 2025) | Target (February 2026)
Reducing mortality, morbidity, and economic losses from disasters in the Caribbean, though the growing incorporation of the most feasible climate-smart and safety standards in selected health facilities in English-Speaking Caribbean to improve their resilience to disasters and reduce their impact on the environment.I | Share (%) of retrofitted facilties in disaster impacted area with minimal damage | Planned | ‘Gold SMART standard’ resilient health facility sites survived hurricanes in 2017 and 2022 and a volcanic eruption in Saint Vincent in 2021. Damage was minimal and critical community services were delivered. Improved functionality also made upgraded sites useful to local COVID-19 pandemic responses. 3 of 22 upgraded facilties in path of Beryl in 2024 reported damage. |  | At least 50% of retrofitted facilities in the impacted area with minimal damage.
Achieved
Source
OUTCOME | Outcome Indicator 1.1 |  | Baseline: (February 2025) | Milestone 1 (August 2025) | Target (February 2026) | Assumptions
Increased adoption and incorporation of climate and disaster resilient standards using the 'SMART' hospital initiative blueprint . | Implementation and maintenenace of the 'Smart' hospital resilience standards and upgrades in retrofitted and new healthcare facilities | Planned | At end of 2024, Vulnerability and adaptation assessments conducted at over 415 health facilities and 55 health centres and small hospitals upgraded in seven countries (Belize, Dominica, Grenada, Guyana; Jamaica; St Lucia; Saint Vincent and the Grenadines) to better ensure safety of patients and staff and secure the continuity of crucial healthcare services after a natural disaster. 30 of the 55 facilities reached the new ‘gold SMART‘ standard, while others were retrofitted to reduce critical vulnerabilities, including weak roof and windows, no back-up power or water provisions or poor flood and fire management. |  | 4 additional countries have included 'Smart' hospital/health facility infrastructure resilience related targets in their Health National Adaptation plans (HNAPS) and/or capital investment plans. Smart standards implemented in 4 new countries. At least 20 additional facilities being upgraded to achieve a higher ‘SMART’ resilience standard (HSI/GREEN assessment score). PAHO and FCDO to use network to engage with senior country leadership and help boost action priorities identified by the global Alliance for Transformative Action on Climate and Health (ATACH) for climate resilient and sustainable low carbon health infrastructure. This includes particularly conducting vulnerability analysis and implementing adaptation measures of facilities by a set target date and to lobby for strengthening of greening benefit tracking, like utility savings, at facility level to support behavioural change and ensure sustainability. | 1. Political buy-in :There is strong political support and keen interest on smarting health facilities in the selected countries; Governments and key decision makers are willing to provide the necessary local support needed; 2. Ministries of Health adopt the Climate Smart Model Policy (initially developed in 2012) with action and investment plans to ensure the initiative continues and 'smart' techniques are implemented in health facilities. No major catastrophic disasters.
|  | Achieved |  |  |  | RISK RATING
|  |  | Source |  |  | MODERATE
Health care facility surveys. HNAPS and national budgets or statistics
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
| £250k |  | tbc | ? | 100%
INPUTS (HR) | FCDO (FTEs)
0.25-0.5 FTE (Advisor and programme manager)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: (February 2025) | Milestone 1 (August 2025) | Target (February 2026) | Assumption
Smart hospitals toolkit revised and updated incorporating lesson learnt and new technical guidance as well as usability improved for Ministry of Health planning purposes |  | Planned | Current toolkit and dashboard link: https://www.paho.org/en/smarthospitals | Updated Smart hospitals toolkit includes a).Improved usability and workflow; b).Strengthened green checklist to include latest advances; c) Smart checklist for design of new planned facilities as well as d).Enhanced wastemanagement strategies. The following draft annexes are added: i. Ventilation / Heat management improvements using latest technology advances; ii. Preventive maintenance guidelines; iii. Fire safety; iv. Base isolation use for earthquake safety; vii. Check Consultants importance and use; viii Infection control (e.g. used in COVID-19) sneeze guards / patient flow and their practical implications; viv. Lessons identified from hurricane Beryl | Smart Hospitals toolkit updated including user feedback and peer review and published on PAHO/ WHO /ATACH knowledge platforms | 1. Appropriate human resources are available and committed. 2. Alignment with Leadership in Energy and Environmental Design LEED) and BRE Environmental Assessment Method (BREEAM), with technical review and endorsement by inter alia the Disaster Mitigation Advisory Group (DiMAG).
Achieved
|  | Source |  |  |  | RISK RATING
|  | Updated SMART Toolkit and ATACH global platform links / reports available from PAHO and MOH |  |  |  | Low
IMPACT WEIGHTING (30%)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: (February 2025) | Milestone 1 (August 2025) | Target (February 2026) | Assumptions
Capacity for application of the rapid vulnerability assessments using the SMART toolkit strengthened at country level | Capacity increased on the application of the updated Smart Hospitals tools, including the Hospital Safety Index (HSI) and Green Checklist on-site | Planned |  | A subregional training course is conducted in September in Jamaica with participation from 2 participants from at least 7 countries | A total of at least 14 persons (M/F) trained to conduct smart assessments and work mentored/vetted by PAHO Smart technical experts at one site per country. Results/vulnerability data will be incorporated into the PAHO dashboard and the countries geospacial databases. | 1. Govt agreement and approvals are promptly achieved to allow sufficient time to execute these training sessions; 2. Availability of suitably skilled persons to participate and to be deployed to conduct assessments; 3. No major impacts to the Health Sector is experienced during the project period (hurricane season).
Regional 'Smart' hospital technical expert team expanded with additional trained persons
Achieved
IMPACT WEIGHTING (20%) |  | Source |  |  |  | RISK RATING
INPUTS | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: (February 2025) | Milestone 1 (August 2025) | Target (February 2026) | Assumptions
Preventative maintenance / SMART resilience 'aftercare' training course established and offered by PAHO technical experts and Caribbean based community college | PAHO conducts Smart aftercare hands-on training. Collaboration with academic institution for maintenance training establshed as part of the sustainability strategy. | Planned | Preventative maintenance manual produced during Smart (phase 2) project | A Smart aftercare training session prepared for in BVI in close collaboration with the Community College with 2 participants trained from at least 7 countries | At least 14 additonal (M/F) persons trained from 7 countries in maintenance; Pilot course established at BVI Community college.
Achieved
|  | Source |  |  |  | RISK RATING
IMPACT WEIGHTING (20%)
INPUTS | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline: (February 2025) | Milestone 1 (August 2025) | Target (February 2026) | Assumptions
Increased advocacy for integration of SMART blueprint approach within broader health resilience developments. | Increased advocacy to promote “Smart” standards at national, regional and international levels. | Planned | Smart (Phase 2) project PR tools and deliverables | Assessment of status of SMART blueprint approach post 2023 conducted (further upgrades, inclusion in HNAP, climate financing bids etc ) and list of key stakeholders and advocates compiled. Influencing plan developed. | 100% of the project influencing plan implemented for the defined target groups;# of strategic partners (see influencing plan) mobilised to advocate for use of the SMART blueprint through media coverage, forum particpation and meetings with decsion makers | Campaigns are well targeted, structured and effective. Good use of networks. Multi-sectorial and multi-disciplinary buy-in and participation
Achieved
|  | Source |  |  |  | RISK RATING
IMPACT WEIGHTING (30%)
INPUTS | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
Note on A39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reworded to be more specific about what is new rather than just state after care training offered.