## Annual Review

Title: Economic Development in the Caribbean
Programme Value £ (full life): £25,000,000.00		Review date: / 26/11/2025
Programme Code: [AMP ID#] 400374	AMP start date: / 26/11/2024	AMP end date: / 30/09/2029

Summary of Programme Performance
Year	2025	2026	2027	2028	2029
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400374/summary
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400374/summary

A. SUMMARY AND OVERVIEW

Description of programme

This programme supports inclusive economic growth and builds economic resilience in the Caribbean, enabling the region to better respond to economic and climate shocks. The programme is structured around four pillars: 1) small-medium business development focusing on key growth sectors and business environment improvement; 2) macroeconomic and debt sustainability to generate fiscal buffers and strengthen government capacity; 3) women’s economic empowerment and 4) strategic, inclusive economic development interventions on policy themes including green finance and data.
This programme delivers UK goals to accelerate sustainable and inclusive investment and growth in the Caribbean; while supporting economic transformation, tackling unsustainable debt, empowering women and girls and unlocking climate finance. The programme supports sustainable and inclusive economic transformation, driving sustained exit from poverty through raising incomes, creating jobs, and increasing women’s participation in the workforce, and increased public and private investment. 30%-50% of this programme’s budget will be counted as International Climate Finance (ICF).
EDC comprises four components:
  1. Caribbean Regional Technical Assistance Centre - CARTAC (Phase VI): Up to £7,500,000.00 to the International Monetary Fund (IMF) for the Caribbean Regional Technical Assistance Centre Phase V (CARTAC). CARTAC provides demand-led, short-term technical assistance and capacity building services to governments in the region to strengthen macroeconomic policy making, public financial management (PFM), tax and customs administration, financial sector surveillance, regulation and supervision, anti-money laundering, debt management and statistics.
  2. Other donors are Canada (USD$11,000,000.00), European Commission (USd$2,400,000.000, The Netherlands (USD$2,100,000.00), Caribbean Development Bank (USD$2,000,000.00), China (USD$2,000,000.00) and Eastern Caribbean Central Bank (USD$2,000,000.00).
  3. Compete Caribbean Plus Programme (Compete+): Up to £9,500,000.00 for Inter-American Development Bank (IDB) Compete Caribbean Partnership Facility (Compete +). Compete + is jointly funded with the Inter-American Development Bank (IDB) (US$5,000.000.00), the Caribbean Development Bank (CDB) (US$1,000,000.00), and the Government of Canada (CAD5,000,000.00). comprises:
    1. Pillar 1: Promoting Competitiveness, Climate Action, and Inclusiveness - focuses on helping Caribbean businesses to become more competitive, climate-smart, and inclusive. This work will improve businesses’ ability to integrate climate action and foster economic growth while providing expanded employment opportunities for vulnerable groups, particularly women.
    2. Pillar 2: Strengthening regulatory capacities to support a dynamic, climate smart private sector - Improve governance for private sector development with climate action, policy frameworks that stimulate businesses to including legal and take climate action.
    3. Pillar 3: Promoting Research and Development for Climate Innovation - This pillar is dedicated to advancing climate innovation through research and development (R&D). It strengthens the capacity of Caribbean research organizations to produce actionable knowledge, fostering innovative solutions for both the public and private sectors.
  4. Supporting Women’s Economic Empowerment: Up to £4,000,000.00 for Women’s Economic Empowerment. It istackling core barriers to growth and key gaps in support for women-owned and women-led businesses. The two primary areas of focus will be as follows:
    1. Improving access to finance – this may include a variety of mechanisms, including exploring new/innovative financing models for women-led businesses, providing direct grants and working with and incentivising development and other financial institutions to make a better offer to women-led businesses (e.g. through appropriate policies, processes and products and reducing actual or perceived risks).
    2. Supporting business growth – this area will address key knowledge, technical and mindset gaps through technical support and training and support for mentoring and networking; and improve the capacity to trade (both helping to build the pipeline of export-ready women-led businesses and supporting those who are export-ready with the skills to access new markets).
  5. Inclusive Economic Development Strategic Fund: Up to £4,000,000.00 through a Strategic Inclusive Economic Development Fund. This is flexible funding that can be quickly programmed in response to unanticipated challenges or opportunities that deliver toward EDC’s theory of change. Policy areas may include: social inclusion, trade promotion, green finance, skills and data.

It must be noted that there has been continuity of UK support on the critical issues of public financial management and private sector competitiveness in the region. The Caribbean Economic Development Programme (CEDP, 2017-2025) was the predecessor to EDC, and the signing of formal agreements and initial disbursements for CARTAC Phase VI and Compete+ were completed under CEDP by April 2025. UK support to CARTAC Phase VI and Compete + continues under EDC.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Through the first year of the Economic Development in the Caribbean Programme (EDC), the team focused on:
- mobilisation by the two main programme implementing partners for Component One and Component Two: The International Monetary Fund and the Inter-American Development Bank;
- and on progressing interventions using existing FCDO central programmes with the Trade Centre of Expertise (the SheTrades Commonwealth + programme delivered by the International Trade Centre and with WorldPop (University of Southampton).
The mobilisation of CARTAC Phase VI and Compete Caribbean Partnership Facility (Compete+) has included (i) developing workplans based on funds received and committed (ii) developing results frameworks in collaboration with donors and beneficiaries.

Major lessons and recommendations for the year ahead [1/2 page]

The flexible design of the programme ensures EDC will start delivering results on the ground over the rest of this financial year and over the course of the next financial year for FCDO, despite the budget uncertainty. Implementing partner plans have been agreed at steering committee meetings which set out robust proposals with clear deliverables and priorities for the year ahead. These plans for EDC include:
- Continue to mobilise and implement interventions under Pillar Three and Pillar Four and establish robust governance and reporting mechanisms which align the Caribbean business plans with emerging priorities.
- Ask Compete+ to identify additional clusters and projects, thereby increasing the four cluster projects under Pillar 1 and six projects under Pillar 2 already identified for approval in December 2025. This assumes additional disbursements from donors.
- Ensure CARTAC’s delivers on and sustains progress on bridging its budgetary shortfall which then informs their activities and adjustments to the results framework, and continuing progress on the CARTAC reform agenda on better results-based management, mainstreaming of climate and gender, and financial sustainability.
Given ongoing uncertainty on multi-year budgets, the programme will need to consider how it can best adapt to different scenarios. This will be key to maximising impact in this space.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The theory of change for EDC remains as set out in the business case.

In line with the Caribbean Development Team Strategy – Approach to Resilience, EDC feeds primarily into the Fiscal and Economic Resilience strands; along with also supporting the Environmental, Climate/Disaster Resilience; and regional integration resilience strands.
There are two primary constraints to economic development in the Caribbean: a private sector that lacks dynamism and a weak ‘doing business’ environment, and a public sector that struggles to maintain sustainable public finance management practices and lacks resilience to shocks. Also, specific barriers and constraints prevent groups from contributing to, and benefit from economic development, such as women, youth and persons with disabilities. EDC targets, macroeconomic challenges, and the lack of productivity in the private sector, as well as driving growth and ensuring it is inclusive which includes, but is not limited to, supporting women’s economic empowerment and improving data. Tackling these issues together should contribute to inclusive, sustainable economic growth in the Caribbean to ensure economic resilience against future shocks and help promote economic opportunities and benefits for all. The programme’s theory of change is set out in the diagram below:

Figure 1 EDC Theory of change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The outcomes and Impacts from the logframe are listed below. This was a startup phase for the programme and no milestones were expected to be delivered during this review period:

- Impact - Inclusive, economic growth in the Caribbean, to ensure economic resilience against future shocks, at the regional, national level, firm-level and community/individual level and to provide opportunities and benefits for all.
  - Outcome 1 - Reforms and systems that promote economic stability, sound public finances and private sector-led inclusive growth as evidenced by:
    - 1. improved gender-equitable and sustainable growth, and climate resilience of Caribbean countries’ private sector, measured by productivity growth of firms and WOF, and the cumulative amount of additional financing mobilized to climate goals.
    - 2. reinforced research institutions and surrounding ecosystems to produce knowledge that supports climate-smart and gender-responsive public and private sectors
    - 3. increased equitable access of targeted firms/Caribbean governments/research institutions to climate solutions and/or finance for competitiveness
  - Outcome 2 - Improved economic and financial sector policy making at national level and Increased access to concessional finance
Next year, we expect the programme to move into full implementation.

CARTAC is facing a funding shortfall for its sixth phase following offcuts to donor funding; this may require CARTAC to reduce ambition and scale, which will have an impact on overall impact and outcomes achieved. The UK will engage with CARTAC to ensure that the quality of CARTAC’s services offered to authorities in the region is not reduced.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above analysis of outcome and output achievement, theory of change and VfM analysis, there is enough evidence that the programme continues to represent good value for money. This programme contributes towards the UK’s growth objectives in the Caribbean region. Strong economic fundamentals, such as a competitive private sector, and stable macroeconomics are paramount for wider UK objectives in the region, such as UK growth and trade, security and climate objectives. UK investment in the region, including from UK Export Finance (UKEF), and British International Investment (BII), and UK trade depends on stable and growing economies in the Caribbean region. Importantly, strong economic fundamentals are a critical platform to support the resilience of the Caribbean and the well-being of its people.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Increased business development capacity for SMEs, leading to productivity growth in Caribbean owned and led firms; new innovative growth clusters created.
Output number:		1	Output Score:	Not applicable
Impact weighting (%):		0	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
1.1	# of firms supported (Compete) - Total number of firms that have benefited from Compete Caribbean, (directly from the innovation plan work AND indirectly through institutions that support competitiveness and engagement up/down the value chains)	0	See information below
1.2	Caribbean Women Owned Firms that benefitted from the Program with gender-responsive solutions for climate adaptation and mitigation that drive competitiveness	0
1.3	Number of gender-inclusive ecosystem of innovation plans developed that support the production of climate-smart solutions and strengthen institutions that support climate-smart entrepreneurship and innovation plus the gender-inclusive ecosystem of innovation plans under implementation	0

Briefly describe the output’s activities and provide supporting narrative for the score.]

The focus for this review period has been selecting the initial projects to support. 47 proposals were received during the first call for cluster and value chain opportunities, launched in December 2024 and closed in February 2025. At least 1 proposal was received from all thirteen beneficiary countries except for Antigua & Barbuda and The Bahamas. 7 proposals from the 47 received, have been selected to receive technical support from a competitively selected consulting firm to develop their Cluster Development Plan (CDP). The CDPs are expected to be completed by November 2025 using the information gathered during missions as well as virtual follow-up meetings. The CDPs will increase revenue growth through local and export sales, enhanced climate resilience, innovative green business models, product and service development and greater inclusion particularly among women-owned firms upon implementation.[1]
[1] Compete Caribbean+ Trust Fund Partnering for a Competitive, Equitable and Climate-Smart Region PROGRESS REPORT Date of Report: October 13, 2025 Reporting Period: January 1, 2025 – September 30, 2025
CDPs implementation will begin with the independent Investment Panel process which is scheduled to begin in December 2025. The Investment Panel is an independent assessment governance mechanism for CC+ Pillar 1 private project proposals. It serves the main function of evaluating the project proposals (CDPs and pitches) towards making recommendations for funding. The Investment Panel will be comprised of 5 panelists, representing the private sector (3 panelists), IDB (1 panelist) and IDB Invest (1 panelist). Panelists will be appointed based on the sectors and firms to be evaluated. FCDO is invited as an observer. Panelists will use the following criteria to evaluate the CDPs and pitches:
1. Mainstreaming Climate for Competitiveness (25%)
2. Revenue Generation (Sales & Export) and/or Job Creation (15%)
3. Project Feasibility (35%)
4. Sustainability (10%)
5. Gender, Diversity and Inclusion (15%)
The consulting firm will also deliver capacity building training on clustering for the regional private sector. The first webinar was held in August 2025 with the second occurring in October. The CC+ team also directly delivered capacity building support through workshops for selected clusters to provide guidance on next steps and to un-selected clusters to provide general feedback to improve the quality of future applications.
Building on the lessons learned from the previous Technology Extension Services (TES) pilots under CCPF, CC+ is designing a new TES mechanism aimed at strengthening SME competitiveness through digital transformation, climate resilience and gender-responsive innovation. This mechanism finds solutions to persistent structural constraints in the Caribbean such as small market size, geographic dispersion and vulnerability to climate change. Implementation Steps Taken: Two consultants will contribute to the design an integrated TES delivery mechanism which combines digital transformation and climate adaptation technologies. The mechanism design consultant was onboarded in July 2025, has since completed the inception phase of the consultancy and commenced the design phase. The climate resilience consultant is expected to be onboarded in October 2025. These consultants will deliver a new draft TES mechanism by November 2025 and a validated refined TES mechanism along with an implementation roadmap by February 2026. The mechanism is intended to support the adoption of digital technologies such as Artificial Intelligence (AI), Internet of Things (IoT) and automation while embedding climate-smart solutions and inclusive access for women-led businesses and disadvantaged sectors[2].
[2] See footnote above.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
A results framework for EDC was included in the approved business case. This was expanded into a logframe which was shared with Compete+ on 7 November 2024. They responded with operational indicators suggested for 2025 at the output level, based on their workplans and budgets as at December 2024.Further refinements to the logframe were completed after Compete+ Program Advisory Group meeting in February 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Lesson Learned:
It is important to maintain flexibility in project planning, to allow for activities to scale up or down depending on the inputs that are available.
Recommendation: Given ongoing uncertainty on multi-year budgets, Compete+ and FCDO will need to consider how the programme can best adapt to different scenarios. This will be key to maximising impact in the private sector, while also delivering on key gender equality and wider inclusion objectives.

Output Title	Business friendly economic reforms drafted; and improved doing business environment.
Output number:		2	Output Score:	Not applicable
Impact weighting (%):		0	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
2.1	Combine 1)Number of policy and/or regulatory reforms (gender and climate responsive) drafted with Compete Caribbean support that are submitted to government for approval. / and 2) Number of gender-responsive policy/regulatory reforms drafted that promote competitiveness and/or climate action. Number of gender-responsive policy/regulatory reforms submitted to government for approval that promote competitiveness and/or climate action.	0	See information below
2.2	Number of institutions that support private sector competitiveness and development, which are strengthened by Compete: Number of institutions that have benefitted from (i) New improved tools; (ii) Advice on institutional design; (iii) Design of new IT or other operating systems; (iv) Legislative advice, and (v) gender-audits	0

Briefly describe the output’s activities and provide supporting narrative for the score.

A Call for Projects to enhance Government Capabilities to Support Climate-Smart and Gender-Responsive Businesses was launched on January 14, 2025 and closed April 30, 2025. 48 project proposals were received, with at least one submission from 12 eligible countries (except St. Vincent and the Grenadines). Compete Caribbean worked with government focal points to promote the call and identify priority projects, ensuring Government commitment of the project.
The COMPETE Caribbean+ Pillar 2 Call for Projects was formally launched through a Virtual Climate Change Needs Assessment Regional Forum, which served as a key platform to introduce the Call and engage regional stakeholders. The Forum featured a presentation on the CC+-commissioned research study, “Climate Change Technical Assistance Needs and NDC Assessment Report,” which highlighted the principal challenges, opportunities, and recommendations identified across Caribbean countries. The event fostered dialogue on critical climate change policies, technical assistance priorities, and actionable pathways to accelerate achievement of Nationally Determined Contributions (NDCs) and enhance regional climate resilience. The Forum culminated in an interactive panel discussion featuring representatives from the public and private sectors, civil society organizations, and regional institutions. The discussion emphasised policy recommendations to strengthen public-sector climate strategies, amplified private-sector perspectives and challenges, and showcased regional best practices in building resilience through public-private-community partnerships.
Following the regional launch, a dedicated Application Clinic with Q&A Session was convened to clarify the requirements of the Pillar 2 Call and to assist applicants in identifying and structuring project proposals aligned with the objectives of the CC+ Programme. These sessions attracted strong participation, with over 150 attendees representing the public and private sectors, as well as regional organizations and development partners. In addition to promoting the Pillar 2 Call, these engagements were successful in contributing to the visibility of the CC+ Programme and provided an interactive platform for dialogue and regional stakeholder engagement on the challenges and opportunities for climate-smart and gender-responsive private sector development.[3]
[3] See previous footnotes
The CC+ team undertook several missions and strategic engagements to promote the programme and the Pillar 2 Call by participating in regional fora targeting the public sector. These events provided an opportunity to capitalize on information gathering, knowledge exchanges and networking with relevant partners and regional stakeholders.

During the reporting period, CC+ participated in the following major regional events:
1. Latin American and Caribbean Network of Environmental Funds (RedLAC) Congress hosted by the Caribbean Biodiversity Fund and held in St. Lucia October 7-9, 2024;
2. Caribbean Coastal Conference, hosted by the Caribbean Development Bank in Jamaica, December 9-10, 2024;
3. 3rd Caribbean NDC Investment Forum and Marketplace hosted by the OECS Commission in Grenada, March 31-April 2, 2025,
4. Global Sustainable Islands Summit 2025, hosted by Island Innovation Llc., and the Government of St. Kitts and Nevis (May 27-29, 2025).
5. Sub-Regional Policy Dialogue on Private Sector Development and Economic Diversification under a Climate Resilient Framework. October 15-16, 2025. Bridgetown, Barbados
The events enabled the CC+ team to promote open Calls and identify synergies with complementary regional initiatives, as well as opportunities for partnerships and scaling up climate investment and policy innovation.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Once ODA budgets were received in July 2025, FCDO engaged with Compete+ to understand what changes would occur with their workplans, once additional disbursements were contemplated. This process of consultation continued until September 2025 and directly led to the latest formal updating of the EDC logframe in October 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Lesson Learned:
It is important to maintain flexibility in project planning, to allow for activities to scale up or down depending on the inputs that are available.
Recommendation: Given ongoing uncertainty on multi-year budgets, Compete+ and FCDO will need to consider how the programme can best adapt to different scenarios. This will be key to maximising impact in the private sector, while also delivering on key gender equality and wider inclusion objectives.

Output Title	Capacity building activities (technical assistance and training) to support effective public financial management, and robust macroeconomic statistics. (CARTAC)
Output number:		3	Output Score:	A
Impact weighting (%):		34	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
3.1	Number of countries where PFM training such as Strategic Budgeting and Cash Basis IPSAS, is delivered by CARTAC	1	Met: St. Vincent and the Grenadines (Review of Treasury Financial Instructions, November 4 to 15).
3.2	Number of countries where Fiscal Risk Statements and Strengthening of Fiscal Risk Management of SOEs training is delivered by CARTAC	2	Exceeded: / Bahamas October 1-8 2025 In-Person Priority Fiscal Risks including State-owned Enterprises / Suriname (Developing a Fiscal Strategy Paper, March 10 - 18): / Barbados (Supporting Fiscal Risk Statement - Macroeconomic Shocks and Climate Change, / December 4 to 10)
3.3	Number of countries which have implemented System of National Accounts 2008	0
3.4	Number of countries which compile and publish Quarterly GDP.	0

Briefly describe the output’s activities and provide supporting narrative for the score.

Over the first four months of calendar 2025, CARTAC delivered 37 missions, 9 workshops and 3 virtual webinars, across our 23 Caribbean members. Advisors from nine workstreams actively delivered technical assistance to core public institutions in member countries and brought together officials from member countries to participate in topical regional workshops.
Details of Missions Completed (Indicators 3.1 & 3.2)
Saint Vincent and the Grenadines (3.1):
CARTAC supported the development of Financial Instructions (FIs) to guide the preparation of Annual Financial Statements (AFS) using IPSAS cash-basis standards.
Result: Draft FIs are ready for imminent adoption and will be used for 2024 IPSAS-based financial statements, improving compliance and transparency.
- Suriname (3.2):
  Mission produced draft text for the national Fiscal Strategy Paper (FSP) and delivered training to strengthen the Medium-Term Fiscal Framework (MTFF) and improve communication of fiscal policy.
  Result:
  - FSP will become the Ministry of Finance’s flagship document, enhancing budget credibility and outlining hydrocarbon revenue management for internal and external stakeholders.
  - Training covered:
    - Sensitivity Analysis: Assessing how macroeconomic changes affect fiscal targets (e.g., primary balance >2.3% of GDP; debt-to-GDP target 60%).
    - Fiscal Risk Analysis: Evaluating risks and impacts of past economic shocks on fiscal planning.
- Barbados (3.2):
  Continued engagement with the Ministry of Finance to meet IMF Extended Fund Facility and Resilience & Sustainability Fund benchmarks. Conducted a workshop combining training and hands-on analysis of Barbados data.
  Result:
  - Developed a populated fiscal risk register and heatmap to inform the 2025 Fiscal Risk Statement.
  - Workshop focused on:
    - Macroeconomic risks
    - State-Owned Enterprise risks
    - Environmental and climate risks
    - Plus other risks (legal cases, guarantees, institutional).

For the first half of FY2025 (May 2024 to April 2025), CARTAC executed 46 percent of its capacity development (CD) workplan in resource person days . Fiscal affairs: tax administration, public financial management, and customs administration, accounted for 50 percent of the total delivery for the period, while both the Statistics and Financial Sector programs represented 23 percent each. Together, the Debt Management and Macroeconomic programs executed 10 percent of total CD delivered.
All CARTAC members received bilateral CD during the first half of FY2025, with the 10 ODA eligible members receiving 60% of the total CD activities in resource person days. This breakdown of resource person days by member country highlights the prioritization in FY25, of ODA-eligible countries, currently comprising 10 of the 23 CARTAC members. This focus on ODA eligible members is expected to increase in FY26.Revisions to the FY2025 workplan were presented and endorsed by the mid-year Steering Committee which was held in December 2024.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
A results framework for EDC was included in the approved business case. This was expanded into a logframe which was shared with CARTAC in November 2024. They responded with operational indicators suggested for 2025 at the output level, based on their workplans and budgets as at December 2024.
Further refinements to the logframe were completed after the June meeting of the CARTAC Steering Committee and once ODA budgets were received in July 2025, we engaged with CARTAC again. This process of consultation continued until September 2025 and directly led to the latest formal updating of the EDC logframe in October 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lesson Learned:

The new Country Based Reporting Templates are an effective way to communicate high level results. These should be continued and all Member Countries should be encouraged to complete them.
Recommendations
Efforts should be continued to mainstream gender and climate across workstreams.

Output Title	Capacity building activities (technical assistance and training) to support: / i) Strengthened tax revenue Administration management and governance arrangements; strengthened core tax administration. / ii) Comprehensive, credible, and policy based budget preparation - BPR and improved public investment management / iii) Develop/strengthen banks’ regulation and supervision / frameworks
Output number:		4	Output Score:	Not applicable
Impact weighting (%):		0	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
4.1	Number of countries where PFM training such as Strategic Budgeting and Cash Basis IPSAS, is delivered by CARTAC	0	See information below
4.2	Number of countries where Fiscal Risk Statements and Strengthening of Fiscal Risk Management of SOEs training is delivered by CARTAC	0
4.3	Number of countries which have implemented System of National Accounts 2008	0

For the first half of FY2025 (May 2024 to April 2025), CARTAC executed 46 percent of its capacity development (CD) workplan in resource person days. Fiscal affairs: tax administration, public financial management, and customs administration, accounted for 50 percent of the total delivery for the period, while both the Statistics and Financial Sector programs represented 23 percent each. Together, the Debt Management and Macroeconomic programs executed 10 percent of total CD delivered.
All CARTAC members received bilateral CD during the first half of FY2025, with the 10 ODA eligible members receiving 60% of the total CD activities in resource person days. This breakdown of resource person days by member country highlights the prioritization in FY25, of ODA-eligible countries, currently comprising 10 of the 23 CARTAC members. This focus on ODA eligible members is expected to increase in FY26.Revisions to the FY2025 workplan were presented and endorsed by the mid-year Steering Committee which was held in December 2024.
Over the first four months of calendar 2025, CARTAC delivered 37 missions, 9 workshops and 3 virtual webinars, across our 23 Caribbean members. Advisors from nine workstreams actively delivered technical assistance to core public institutions in member countries and brought together officials from member countries to participate in topical regional workshops.
No Milestones were expected for this review period.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
A results framework for EDC was included in the approved business case. This was expanded into a logframe which was shared with CARTAC in November 2024. They responded with operational indicators suggested for 2025 at the output level, based on their workplans and budgets as at December 2024.
Further refinements to the logframe were completed after the June meeting of the CARTAC Steering Committee and once ODA budgets were received in July 2025, we engaged with again. This process of consultation continued until September 2025 and directly led to the latest formal updating of the EDC logframe in October 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations
Efforts should be continued to mainstream gender and climate across workstreams.

Output Title	Women-led businesses supported to grow their businesses and to trade.
Output number:		5	Output Score:	A
Impact weighting (%):		33	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
5.1	Number of women-owned businesses (or women entrepreneurs) supported	Dual Lock Agreement (DLA) between The Trade Centre of Expertise (Trade COE) and FCDO Caribbean Development Team (Post) signed by end of October 2025.	Substantially met: Agreement was reached on both sides on the final text of the dual-lock agreement in October. Formal signature by both sides was completed by 13 November.
5.2	Amount of finance leveraged for women entrepreneurs ($USD)	0
5.3	New innovative finance model created to support women	0

Briefly describe the output’s activities and provide supporting narrative for the score.
Given budget uncertainty, work on this output during the review period focussed mainly on scoping viable and impactful interventions in line with the strategic objectives of Pillar 3, that could potentially be undertaken in 2025-26. FCDO Caribbean team discussed areas of strategic interest to support women entrepreneurs in the region with UK staff working on the ITC’s SheTrades programme at ITC headquarters as well as at the SheTrades regional hub at the Caribbean Development Bank. These discussions focused on A proposal from SheTrades was initially approved in July 2025.
The proposed work to be undertaken in 2025-26 is expected to deliver:
- Strengthening of SheTrades Caribbean Network Focal Points and associated BSOs through information, tools and training (including on digital access & literacy and on building resilience)
- Improved capacity of women-led businesses (WLBs) to trade and to improve their competitiveness and resilience (training on crisis management and risk assessment toolkit for climate-related shocks; quality compliance, standards and certification support; training on packaging requirements and sustainable packaging solutions)
- Increased connection of Caribbean WLBs to markets, with a strong focus on UK markets (through trade missions and company visits, direct market-linkage with selected UK importers and increased access to markets through trade/market Intermediation)

The ITC is already implementing the FCDO centrally funded SheTrades Commonwealth + programme, which aims to increase economic growth and job creation in Commonwealth countries by enabling the increased participation of women-owned businesses in traded. Considering this, discussions were also held with the FCDO team managing that programme to maximise efficiencies. It was subsequently decided that given the strategic alignment of the She Trades Commonwealth + programme with the SheTrades proposal under Pilllar 3 of EDC, it would be most efficient to deliver the inititiative under the central programme. As a result, an agreement between the FCDO Caribbean Development Team and the central FCDO trade team was developed and signed to facilitate implementation and management of the support by the central team, in partnership with the Caribbean team.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Given the budget uncertainty and constraints on this output for most of the review period, the only feasible milestone for the time of the review as to have a process indicator to capture the administrative arrangements to facilitate the work for the rest of 2025-26 under this output, name the Dual Lock Agreement (DLA) between the central trade team and the Caribbean Development Team. It should be noted that going forward, results of the work under that agreement will be reported as part of the She Trades Commonwealth + programme, and not directly under the EDC. However, future work under Pillar 3 beyond 2025-26 will be reflected in EDC revised logframe indicators and reported under EDC..
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Lessons learned:
Strong relationships are critical in allowing development work to advance even in the face of prolonged uncertainty.
Recommendations
Further scoping work on interventions under Pillar 3 should be followed up quickly and strategically once multi-year budgets are known. This will give clarity on the final trajectory and scope of the pillar and allow for efficient establishment of the required implementation arrangements and effective delivery of results.

Output Title	A strategic economic policy fund to support impactful interventions to support inclusive economic growth, including data and green finance that complement other pillars of EDC.
Output number:		6	Output Score:	A
Impact weighting (%):		33	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
6.1	A regional approach to modelled demographic data and its characteristics developed and countries census activities supported	Amendment of the Memorandum of Understanding between the Foreign, Commonwealth & Development Office (“FCDO”) and University of Southampton (WorldPop group) signed by end of October 2025	Met – Amended MOU fully executed on 2 October 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

So far, the project selected under this EDC strategic fund will strengthen capacity of population statistics generation in the Caribbean, which will support governments in stronger evidence-based policy making, disaster risk management and inclusive economic growth. Following initial discussions between FCDO CDT and University of Southampton (WorldPop group), a proposal for support was approved by the EDC Programme Board in July 2025. Following this, in August 2025, further discussions between FCDO CDT and WorldPop group began and an amendment to the MOU between FCDO Statistics, Global Statistics, Centre for Data & Analysis, Analysis Directorate and WorldPop, was signed to include the Caribbean project Data for Development: Enhancing Statistical Capacity for Caribbean Economic Growth and Disaster Risk Management. WorldPop will work collaboratively with the UK Office of National Statistics (ONS).
The impact of Caribbean support (MoU Amendment No. 6) will be measured by:
- A clear inception report, setting out regional and national activities and clear deliverables for 2025-26.
- Accuracy of modelled population estimates, assessed through validation exercises comparing model outputs to full household listings in the number of Enumeration Areas (EAs).
- Technical documentation of the population modelling process.
- Level of local capacity built, evaluated through participation in and feedback from training workshops and technical collaboration with Caribbean regional and ONS staff.
- Workshop materials and participant feedback from capacity-building sessions.
- A final synthesis report summarising cost savings, scalability potential, and implications for the Caribbean countries.
- Recommendations for follow up work.
Given the delays in funding allocations and the time taken to build understanding of needs and the support being provided by other donors, the FCDO, WorldPop and the ONS have taken a realistic approach to what can be achieved to build statistical capacity and the availability of data on populations and demographic traits.
Taking a few weeks to build that understanding will ensure that efforts are focussed, and avoid duplication, however, has shortened the window to deliver the agreed outputs. Given the remaining four months to deliver, the monitoring and reporting on progress will be discussed every two weeks, to allow any slippage to be identified quickly.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Based on the timing of this Annual Review, signing of the amendment to the MOU was the only feasible measure of progress for this version of the logframe.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

## D: VALUE FOR MONEY

Key cost drivers and performance. VfM performance compared to the original VfM proposition in the business case

Suggested VfM measures and metrics from the Business Case are captured in the table below.

4E Framework	Example VfM Metrics
Economy	Average cost over a fiscal year of a Capacity Development-day. / Competitive/open procurement of consultancies and goods.
Effectiveness	% of milestones rated as fully achieved or largely achieved in programme or project or workstream or country / % of Outcomes rated as fully achieved or largely achieved in programme or project or workstream or country / % of Objectives rated as fully achieved or largely achieved in programme or project or workstream or country / Successful Impact Stories / Case Studies / Number of economic reforms / business environment reforms implemented through parliament / Improvement of the World Bank’s ‘Business-Ready’ ratings.
Efficiency	Average cost of a participant day (training) / Amount of counterpart finance raised for projects
Equity	Gender and social inclusion Capacity Development delivered in programme or project or workstream or country / % of participants/ beneficiaries of capacity-building support that are female% from disadvantaged or under-represented groups / % of women-owned firms supported in mainstream private sector development activities / Number of women entrepreneurs or women-owned firms supported to grow their businesses.

The complementarity achieved through multi-donor trust funds allows donors to influence for better VfM throughout the programme cycle. The identified International Financial Institutions (IFIs) for Pillars One and Two have a strong track record of delivering UK-funded programmes.

Slow implementation is a chronic issue in the Caribbean, and we are confident that these partners will be able to deliver results quickly. Experience based on lessons learnt, shows that working through existing regional bodies that operate across multiple Caribbean countries, and using tried and tested regional programmes that benefit from an existing strong reputation and political relationships within the region, maximises efficiencies. Working through regional programmes also supports our Caribbean partner governments in minimising transaction costs, and simplifies points of contact, given the acute limited capacity of Caribbean governments to engage on multiple development programmes.

Economy (Buying inputs of the required quality at the lowest cost)

Compete Caribbean’s main cost driver is the procurement of consultancies. All of Compete Caribbean’s consultancies (individuals, firms), and the procurement of goods, follow IDB competitive procedures which are designed to secure Value for Money. The IDB applies standard matrices to consultants’ relevant experience, level of education and place in which they are providing the service. While the FCDO Caribbean team has no scope to challenge these costs, the UK sits on the board of the IDB and drives VFM at that level and is content that competition results in lower costs.

CARTAC have sought opportunities where feasible to minimise unit costs and maximise the number of inputs with its available budget. Examples include:

CARTAC has a hybrid delivery model i.e. a combination of face to face and virtual modes of delivery. The cheaper virtual mode of delivery reduces the effective cost per workday charged to the budget without significant reductions in training quality. CARTAC continues this modality in certain areas. CARTAC also benefits from efficiency savings derived from using the extensive training catalog already developed by the IMF Institute for Capacity Development and the use of joint missions with IMF staff members.

Short term experts conducting back-to-back missions. Where possible experts are expected to complete multi-country technical assistance missions. This reduces travel costs from home base, and ensures that short term experts spend the maximum time in field. Countries also benefit from cross country knowledge and best practices.

Hosting regional events. Regional workshops and seminars maximise use of the CARTAC budget and also they support regional approaches and peer learning. Typical workshop format involves pre-assigned tasks (e.g. data collection), theory, assembling models using real country data, and follow up actions.
Agreements and engagement with partners for work under Pillars 3 and 4 include VfM aspects, so the relevant economy considerations are taken into account. ITC (implementer of SheTrades) is an established implementing partner for FCDO programming so is well-experienced in managing costs in line with FCDO’s VfM standards.

Efficiency (Producing outputs of the required quality at the lowest cost)

Compete+ continues the rigorous project approval process from previous phases. There will be opportunity to discuss with Compete potential unit cost metrics which should help demonstrate how the programme is achieving good value for money. These could include:
- Jobs created per USD invested
- Increase in exports per USD invested
- Financial leverage ratios
- Business reform legislation/policy enacted per USD
- Technical assistance field person weeks delivered per USD
For Compete, a key way of driving efficiency in the use of project funds is ensuring project beneficiaries are also committed to driving value for money. For example, firm and cluster beneficiaries must contribute counterpart resources to direct assistance projects from Compete

The IMF are making a concerted effort to reduce some of their key cost drivers. Some of the other methods CARTAC are using to drive efficiencies include.

- maximising short-term experts missions per trip to the region in order to avoid funding multiple trips, e.g. experts coming from Europe/US are requested to do back-to-back missions
- using good short-term experts repeatedly because of their familiarity with the region, which reduces preparation time; and
- monitoring and managing mobile telephone/data roaming costs.
Options to address contingencies (short term) and to improve financial sustainability of the model (medium-long term) that could be explored further include reducing the number of short-term experts hired to complement the delivery of the Center’s resident advisors, increasing the share of CD delivered virtually as was done during the Covid-19 pandemic, or re-prioritising the work program in close consultation with all the Center’s stakeholders.

CARTAC will also continue to prioritise the implementation of any recommendations or innovations that emanate from the IMF’s Capacity Development Strategy Review, or any other related IMF institutional changes, which relate to the funding model for all externally financed vehicles.
Agreements and engagement with partners for work under Pillars 3 and 4 include VfM aspects, so the relevant efficiency considerations are taken into account. The work with SheTrades under Pillar 3 harnesses ITC’s global network and the SheTrades Caribbean regional hub to maximise efficiencies.

Effectiveness (How well Outputs produce Outcomes)

CARTAC also represents an excellent VFM proposition on effectiveness. For example, CARTAC technical assistance helps countries make better use of limited fiscal resources and improve countries debt management processes. Through their work on tax administration, CARTAC also helps countries improve tax collection and limit revenue wastage.

Compete has experience and a track record in supporting successful legislative and regulatory business reforms in the Caribbean. Improving the doing business climate encourages direct foreign investment and allows companies to expand more quickly and create jobs. Compete have demonstrated in previous phases that they can provide essential support for these reforms.

Under Pillar 3, the work contemplated for 2025-26 is being delivered by a partner (ITC She Trades) with a strong track record of delivery of trade programming for women-led businesses across the Commonwealth, including the Caribbean, and have had good tangible results.

Equity

Compete’s work has a strong focus on promoting a more gender-responsive business environment and on providing support to women-led businesses, and supporting job creation for women and youth. CARTAC’s work on gender and inclusion is at an earlier stage of development, but there has been some progress in implementing gender-focused interventions and working towards better gender mainstreaming overall in its work. Pillar 3 is by design focused on promoting women’s economic empowerment, and the products of the initial statistics work should be a helpful resource for understanding the status quo and progress for specific population groups and designing appropriate policies and programmes to address their needs.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme has already demonstrated good VfM potential and delivery to date and should be continued. With effective implementation, the programme will produce valuable economic results for the Caribbean which in turn will support delivery of other work in the portfolio on climate and security and contribute to meeting the UK’s overall objectives in the region.

All implementing partners are engaged on VFM issues. (e.g. The IMF will provide unit cost metrics to evaluate VFM and the IDB can continue tracking and reporting against unit costs as the current phase progresses.)

Over the next year, FCDO will continue to engage implementing partners on VFM. FCDO will also seek to improve and expand key indicators to track and measure VFM in the programme.

Assessment of whether the programme continues to represent value for money

Progress under the programme thus far and the experience from the previous phase of the programme gives confidence that the programme continues to represent value for money. The FCDO’s Caribbean Development Team will continue to drive VfM through regular discussions with both Compete Caribbean, CARTAC and all other implementing partners under EDC, including new partners like WorldPop. Regarding the 2025-26 work under Pillar 3 (women’s economic empowerment), the FCDO central trade team overseeing the SheTrades Commonwealth+ programme will continue to engage with ITC (implementer for SheTrades) on relevant VfM issues.

E: RISK

Overview of risk management

Overview of programme risk:
The initial risk assessment and risk appetite for EDC was finalised in November 2024. It was informed by the risks identified in the business case along with discussions with the implementing partners. The risk assessment completed as part of the business case found the programme to have an overall risk rating of “Moderate”. The vulnerability of the Caribbean to external events such as natural disasters and global economic recessions remains the underlying theme of all risks. Mitigation strategies are in place for all individual risks identified. These strategies have reduced the impact and probability ratings for these risks, thus the current net risk is lower than the original gross risk. Quarterly checks of all risks in the risk register identified changes to any assumptions, underlying conditions or actions which would alter the likelihood or impact of the risk.
EDC has an Eager appetite for strategy and context risks. EDC has a Receptive appetite for delivery risks and for operational risks in terms of staff safety and programme oversight. EDC has a Cautious appetite for reputational risks, fiduciary risks, safeguarding risks and people risks.
These ratings highlight the vulnerability of the Caribbean to external events such as natural disasters and global economic recessions.
All risks remain within the risk appetites for all categories and there was no need for any risk escalations during the reporting period.
Due Diligence Assessments (DDAs) were completed in March 2024 to enable new agreements to reflect the FCDO’s financial contributions to Compete Plus and CARTAC Phase VI. No major risks were identified, and a plan is in place to engage with implementing partners on areas where further action is required. Interventions under Pillar 3 and 4 are managed under existing arrangements between central programmes and implementing partners, which includes DDAs being completed.
A selection of key EDC risks and mitigation strategies are outlined in Table below.

EDC key risks and mitigation strategies (as of November 2025)
Risk Description	Mitigation Strategy	Residual Risk
Strategy & Context
External Economic Shock: A sudden decline in tourism and other exports following a protracted period of slower growth in advanced economies; global economic downturns or price shocks such as fuel price inflation or food inflation impacts the pace of progress towards outcome; acute fiscal or external financing pressure leads to a debt default.	Focus EDC technical assistance in strengthening economic preparedness and risk management e.g. building fiscal buffers; IFI emergency facilities available to weather economic storms linked to reform; engagement at senior official, ministerial and IFI Board level to encourage regional authorities to deliver on key economic reforms.	Moderate
Policy & Programme Delivery
Natural Disasters: a natural disaster leads to a re-prioritisation, the pace economic reform slows, and the private sector gets knocked back	Economic stability and economic growth are priority goals for the region unlikely to be deprioritised; FCDO, other donors, regional response organisations and the IFIs have facilities to provide a rapid response in the event of natural disasters and undertake projects to improve the resilience of key facilities. Compete Caribbean will deliver support to firms to increase their resilience to natural disasters and climate shocks. CARTAC will deliver technical assistance to embed climate risk into economic planning.	Moderate
Financial & Fiduciary
Fiduciary: Risk of fraud or corruption in the use of UK funds	UK funds are mostly being delivered through IFI financial systems which we consider to be robust. All partners receiving resources from the project will be subjected to a due diligence assessment which will include policies and procedures as a fiduciary, clear financial procedures, separation of responsibilities and approvals, and regular internal and external audits on procedures and balances. FCDO will engage in regular monitoring of transactions and disbursements, and checks will be conducted to ensure compliance by partners.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

EDC was approved in November 2024 which is financial year FY24/25 with a budget of £25mn. 50% of that budget has been badged as ICF. The original budget for FCDO FY25/26 was £5m.

Under EDC, the FCDO paid £2.5mn to Compete and £2.5mn to CARTAC in December 2024, and afurther £800k was paid to CARTAC in March 2025. That last payment reduced the EDC forecast in FY25/26 from £5m to £4.2m.

The UK Prime Minister’s announcement on 25 February to increase UK defence spending to 2.5% of GDP by 2027 to address the imperative of national security required hard choices, one of which was to reduce UK ODA spending to 0.3% of GNI by 2027.

In this context, deliberations within the Caribbean Development Team re finances, reduced the requested EDC budget for FY2526 from £4.2mn to £2.5mn in April 2025. ODA spending plans for FY25/26 were reassessed and revised allocations received in July 2025. Once the £2.5m for EDC within the budget settlement for FY25/26 was received at this time, implementation plans for EDC were resumed.

CARTAC
CARTAC Phase VI will run from May 2024 until April 2029. UK contributions to CARTAC are entered into the CARTAC Subaccount of the Framework Administered Account for Selected Fund Activities created by the IMF. The SFA Framework Account was created for the purpose of the administration of funds contributed by (i) donors and (ii) contributors.

CARTAC posts (i) a financial statement regarding the operations and transactions under the Subaccount2, (ii) a progress report, and (iii) a list of key decisions taken at the annual Steering Committee meeting, once a year on the IMF’s donor gateway[4] to which each contributor has access.
[4] The donor gateway is a secure web-site that Contributors may access through https://extranet.imf.org/.

Financial progress can now be checked on an ad-hoc basis through the IMF Donor Gateway, while formal reporting and discussion will occur through the semi-annual Steering Committee meetings. The operations and transactions conducted through the Subaccount during the financial year of the IMF will be audited as part of the IMF’s Framework Administered Account for Selected Fund Activities (SFA). CARTAC is also subject to audits by the IMF’s internal audit office and complies with IMF procurement practices and other applicable IMF policies, practices, and procedures.

Compete
The CC+ Trust Fund Facility was approved by the IDB Board of Executive Directors June 2024 with a value of US$14.89 million IDB cash and In-kind contribution totalling US$5 million. Donor contributions were expected to be USD$9.89 million.

FCDO and other donors can request and review the audited financial statements for the IADB through the Annual reports containing external audited financial statements. Additionally, information on money received and disbursed by Compete can be mined from the Compete Caribbean Administration and Reporting System and provided to FCDO. The reports generated can show the level and recipients of disbursement of FCDO funds. The reports are used to ensure actual spend is broadly in keeping with the work plans prepared and agreed by the PAG.

The Due Diligence assessment and historical evidence of previous phases of Compete provides us with great confidence that the financial and procurement management processes and procedures within the IADB; and by extension; within Compete as a Project Executing Unit are consistently and correctly applied.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The EDC programme will employ a robust monitoring and evaluation (M&E) framework that includes
- Completed Delivery chain maps with funding flows, risks and assumptions included for all components.
- Setting up a schedule of field visits based on the workplans of each partner so that we can visit each component in one country in one trip.
- Follow the Inclusive Growth Team monitoring strategy and ensure the type of monitoring identified is appropriate, and document actions and decisions taken using the delivery plan and other project records

 Monitoring

The FCDO Caribbean Inclusive Economic Growth team has a monitoring strategy built around systematic collection, analysis and use of information about programme and project progress. Results, activities/schedules, PrOF compliance, finances, beneficiary engagement, risks and context are all areas which will be tracked, reviewed and mitigated.
FCDO actively participates in the regular project-level monitoring and oversight arrangements for the different EDC programme components.

FCDO participates in the biennial Steering Committee of CARTAC, which occurs in May/June and December of each year. The purpose of the Steering Committee is to review recent progress and agree forward workplans. The Steering Committee consists of representatives from 21 member countries and the funding partners (currently Canada, FCDO, the Netherlands, CDB, the ECCB and the EU). The CARICOM Secretariat also observes these meetings.

FCDO attends Compete’s Programme Advisory Group (PAG) meeting, usually held every February and October. The PAG comprises Compete Caribbean Donors, representatives from the Inter-American Development Bank Caribbean Country Department, Competitiveness Technology and Innovation Division, One Caribbean; and Grants & Co-Financing Management unit, along with the Compete Caribbean+ Facility Coordination Unit. Compete also hold technical level PAGs every few months to discuss programme issues and progress with donors. An Annual Progress Report is submitted to the PAG. This report will present the highlights and achievements of the previous year.

For Compete+, Two independent program evaluations (midterm and final) will complement the continuous M&E of projects. The midterm evaluation will be performed three years after the program begins or when 50% of the funds have been disbursed, whichever occurs first. The final evaluation will be performed when disbursements have reached at least 95% or at the end of the fifth year, whichever comes first.

As has occurred in previous phases, it is expected that CARTAC will also commission an independent evaluation at the midpoint of the current phase.

Internal mechanisms are in place to ensure regular reporting and monitoring of initiatives under Pillars 3 and 4 of the EDC. The central trade team has primary responsibility for monitoring the work to be delivered in 2025-26 under Pillar 3 through the SheTrades Commonwealth + programme, though the FCDO Caribbean Development Team will participate in this process as well.

Monitoring missions

Beneficiary monitoring missions will be made to all ODA-eligible countries throughout the lifecycle of the programme. The Inclusive Growth Team (one or more members) will make a minimum of 2 trips per year and will engage with a range of beneficiaries to receive feedback on the various components. An inclusive approach will ensure beneficiaries from across the spectrum of support are consulted. This includes senior government officials and politicians, business owners and entrepreneurs, and particular targeted or under-represented groups.

Learning

Lessons learnt from previous economic development programming were included in the business case and is repeated here for ease of reference.

Lessons Learned from previous, relevant FCDO programming
Lessons learned relating to economic policy technical assistance	It is important to communicate results at the outcome and impact level, to show stakeholders in the region, and development partners the impact of sustained capacity development in the region. Specific examples including evidence such as amount of tax revenue generated, or time reduced in processes are particularly helpful in highlighting value for money.
	Hybrid working is a good way to control costs in some instances i.e. a combination of face to face and remote delivery of technical assistance, including training, workshops and training.
Lessons learned from supporting the Caribbean Private Sector	Nascent sectors with impeding or incomplete regulations slow down project implementation. Blue economy (or agri-tech) firms require much greater efforts towards capacity building, resulting in slower projects with smaller disbursements. New or absent regulation slows down work on blue economy clusters including seaweed, coral restoration and tuna. These sectors require increased focussed engagement (more direct people time), longer time frames and flexibility in resources.
	Lower than expected implementation capacity of regional executing agencies hampers speed of delivery. Working in nascent sectors also leads to delays in sourcing firms with the technical capability to implement specialized consultancies. This can lead to delays in procuring consultants and, by extension, disbursements.
	SMEs cite lack of affordable finance as a key barrier to growth, along with the lack of relevant skills, and burdensome government regulation.

Date of last narrative financial report	CARTAC – June 2025 / Compete+ - March 2025	Date of last audited annual statement	CARTAC – May 2025 / Compete+ - March 2025