## UC Logframe
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
OUTCOME | Outcome Indicator 1 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
Key Albanian state institutions become more transparent and effective, and more trusted both by Albanian citizens and the UK (and other governments) for cooperation in tackling serious and organised crime emanating from Albania. | Reform strategies drive forward public sector transformation, towards enhanced efficiency and effectiveness. | Planned | GDT delivering a mid-term reform strategy, and police preparing a draft police law (but not implemented). | N/a | Domestic institutions adopt >5 reforms to drive forward public sector transformation on revenue management and police/judicial reforms.
|  | Achieved |  |  | 15 rreforms adopted across all benficiary institutions.
Source
| Outcome Indicator 2 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Citizen engagement in public sector reform plans drive stronger trust in the tax, policing and judicial administrations | Planned | Citizen trust in the public sector organisations responsible for tackling SOC is limited. | N/a | >2 public communications and engagement plans implemented.
|  | Achieved |  |  | Tax and Police implement communications/engagement plans. 69% increased tax payer knowledge, 67% increased tax payer trust.
Source
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
Albanian State Police improves its internal practices in line with the latest international best practice | Strategic Planning and Governance. Improved approaches to Strategic Planning and Governance drive forward ASP's transformational change. | Planned | ASP's approach to Strategic Planning and Governance holds back systemic reforms of the ASP. | ASP implements a new approach to Strategic Planning and Governance, including the management of risk. | N/a
|  | Achieved |  | ASP confirmed support for MoRiLE and AlbSTRA. Operationalisation in early stages (eg, ASP request for National Decision Making training for regional officers, MoRiLE integrated into Community Policing SOP). Training not yet delivered. SOP not yet implemented
Source
| Output Indicator 1.2 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Human Resources and Workforce Planning. Better provisions for the ASP workforce place human resources at the heart of its systemic police reforms. | Planned | Regulatory/legislative provisions undermine ASP ambitions to provide terms and conditions fit for a modern police service. | New legislation/protocols provide more improved and fairer terms and conditions for ASP staff. | N/a
|  | Achieved |  | July 2024 Police Act, and subsidiary legislation, demonstrates evidence of inclusion as a result of project influence (eg, on gender equality, and union representation on the ASP board).
Source
| Output Indicator 1.3 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Financial Management and Compliance. Dynamic and strategic management of ASP resources provides a platform for the ASP to be more responsive to priority/emerging resourcing needs. | Planned | The ASP does not deploy systems of financial management which allow for strategic or dynamic resource management. | The ASP implements a pilot of dynamic resource management to demonstrate 'proof of concept' success. | N/a
|  | Achieved |  | Forensics directorate financial lead in advanced discussions to introduce a pilot ‘Financial Business Partnering’ concept. Pilot pending to end of year.
Source
|  |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Vetting and Counter-Corruption. A robust vetting and counter-corruption strategy is mainstreamed through all ASP reform efforts. | Planned | ASP implements a basic vetting process for in-coming recruits; evidence of minor independent police oversight function to counter corruption. | ASP adopts a strategy for timely vetting of all officers, and adopts and resources a counter-corruption strategy. | N/a
|  | Achieved |  | Limited evidence of progress.
Source
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
45% | Communications and Engagement. A progressive communications and engagement plan drives forward stronger ASP relationships with citizens. | Planned | ASP's current approach to communications and engagement with the public limits public trust in the ASP. | ASP adopts and starts implementation of a progressive strategy on communications management. | N/a
|  | Achieved |  | Communications SOP adopted; training to operationalise it an adequate indicator that implementation commenced.
Source
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
Increased capability and capacity of recently appointed/in-training Albanian judges and prosecutors | Judicial Curriculum. Final versions of the training modules are approved and adopted by the SoM. Modules are integrated into the continuous training program | Planned | School of Magistrates continuous training programme in need of update. | N/a | Final versions of the training modules are approved and adopted by the SoM. Modules are integrated into the continuous training program
|  | Achieved |  |  | Three training modules approved and adopted by the SoM and delivered in Albania by UK judges, and UK forensic experts.
Source
| Output Indicator 2.2 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Judicial Training. At least 80% of participants report improved competence in courtroom management and judgment writing, and better usage of forensic methods in post-training surveys within 3 months after the training. | Planned | Refresh required of forensic evidence and other areas. | N/a | At least 80% of participants report improved competence in courtroom management and judgment writing, and better usage of forensic methods in post-training surveys within 3 months after the training.
|  | Achieved |  |  | 80% of trained judges improved their understanding of how to assess forensic evidence in court, as well as their knowledge of human rights and the legal framework of the European Court of Human Rights.
IMPACT WEIGHTING (%) |  | Source
10%
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
Improved systems and capabilities for data collection, analysis, management and communication catalyse existing General Directorate of Taxation capability to tackle informality, prioritising the construction and tourism sectors. | VAT tax payers. Number of registered VAT tax payers | Planned | 1% increase in VAT registered taxpayers targeteed by >GDT, disaggregated. | N/a | 5.5% increase in VAT registered taxpayers, disaggregated.
|  | Achieved |  |  | 5.2% increase in VAT registered taxpayers, disaggregated.
Source
| Output Indicator 3.2 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Income Tax. Number of individuals declaring and paying personal income tax | Planned | 1% increase targetted by GDT in the number of individuals declaring and paying personal income tax, disaggregated (annual declaration). | N/a | 3.5% increase in the number of individuals declaring and paying personal income tax, disaggregated.
|  | Achieved |  |  | 27% increase in the number of individuals declaring and paying personal income tax, disaggregated.
Source
| Output Indicator 3.3 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Revenues. VAT revenues. | Planned | 7% increase in VAT revenues targetted by GDT (Baseline: 62.231.104.000 leke) | N/a | 9% increase in VAT revenues (Mar 2026 compared to Mar 2025)
|  | Achieved |  |  | 16% increase in VAT revenues (Mar 2026 compared to Mar 2025)
Source
| Output Indicator 3.4 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Personal income. Personal income tax revenues (PIT) | Planned | 10% increase in PIT targetted by GDT (Sept 25 vs Sept 24). Baseline: 50.370.116.000 leke | N/a | 13% increase in personal income tax revenues (2025 compared to 2024)
|  | Achieved |  |  | 18% increase in personal income tax revenues (2025 compared to 2024)
Source
| Output Indicator 3.5 |  | Baseline (01 July 2024) | Milestone 1 (30 June 2025) | Target (30 April 2026)
| Social and Health. Social and health insurance contributions | Planned | 10% increase targetted by GDT in social and health insurance contributions (Sept 25 vs Sept 24). Baseline: 114.787.212.000 leke | N/a | 12% increase in social and health insurance contributions (compared with Mar 2025)
|  | Achieved |  |  | 9% increase in social and health insurance contributions (compared with Mar 2025)
IMPACT WEIGHTING (%) |  | Source
45%

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.