## Annual Review Template

Title: British Euro-Atlantic Language Training
Programme Value £ (full life): up to £5m		Review date: 24/11/2025
Programme Code: 400383	AMP start date: / 25/11/2024	AMP end date: / 01/11/2027

Summary of Programme Performance
Year	2025
Overall Output Score	A+
Risk Rating	Minor

DevTracker Link to Business Case:	BELT BC
DevTracker Link to results framework:	BELT Logframe

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

Following a Prime Ministerial commitment this is the first annual review of a 3 year, £5m programme being delivered by the British Council. BELT aims to support Ukraine to move forward issues related to EU accession and associated strategic reform agendas, through improving English language in the Ukrainian civil service. The programme provides English Language Training (ELT) for civil servants working on EU and NATO accession negotiations and reforms, working in 1 year cycles of lessons (September to July). It was expected to reach 1400 officials in its first year, and in fact British Council’s tailored lessons and workshops supported over 1700 civil servants. The programme also set out to improve Government of Ukraine (GoU) capacity to teach English to Civil Servants – ‘systems support’. The approach to systems support was pivoted to focus on deepening the FCDO’s understanding of this space, before commissioning any external consultation – in particular building the FCDO relationship with the National Agency of Ukrainian Civil Service (NAUCS), the body responsible for Civil Service Learning and Development (L&D). Progress was made with NAUCS now formally recognising BELT as a certified programme for which completion will provide credits for civil servants. One of the biggest challenges faced in the successful delivery of BELT in year one is the number of students who kept up their studies and completed the course they were on. NAUCS recognition should be beneficial in improving completion rates in year 2. The performance of the delivery partner, British Council, was strong throughout year 1. The FCDO team delivering the programme benefitted from bringing together political and development programming expertise, due to the number of ministries the programme would be reaching and the desire to ensure ELT was provided to the right students in the right ministries.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme has scored an A+ (moderately exceeded expectations) because of the strong progress made against the expected results for the English Language training part of the programme. Both the high level of commitment to the programme from a large number of ministries (55 ministries), and the impact of the ELT that was accessed by the students in each ministry exceeded initial expectations of the programme. The change in approach to the systems work saw positive results that will benefit the overall delivery of BELT, although did move away from the planned activities of the logframe. Building on these in year 2 will be important for the successful trajectory of the programme.

Major lessons and recommendations for the year ahead [1/2 page]

- Systems support redesign: The design of the systems work in the business case was not rigorous enough to take into account the context. Within the first 6 months of year 2 the SRO should redesign this element of the programme, setting out the appropriate level of ambition to match resource and time available. This should be updated in the theory of change and logframe by May 2026.
- Improve completion rates: this will likely be achieved through a combination of targeting the right civil servants with the right intervention; changing the model of EOL delivery; and working closely with NAUCS so that accreditation becomes a motivation for completion. Improvements by November 2026 (next AR).
- Driving results and VfM through targets and milestones: The logframe, theory of change, and VfM indicators should be reviewed and updated within the first 6 months of the next programme year, ensuring all are aligned and accurate. Weighting of outputs and milestones for year 2 should be decided by SRO by May 2026.
- Refreshed approach to equity and GESI: This should be considered and redesigned for the second year, in particular increasing the data gathered that will inform the equity of the programme. British Council to lead, with plan in place by end of Q4.
- More targeted institution selection: ELT will always be desired amongst institutions, but BELT should specifically target the institutions and individuals that will benefit Ukraine’s Euro-Atlantic future. Year 2 should include indicators for the relevance of institutions – to update in the logframe within 6 months.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

BELT is on track to deliver its Theory of Change within the programme but with a slower timeline on the GoU capability stream – see Annex A for the full ToC. BELT’s impact statement is to see ‘Ukraine supported to move forward issues related to EU accession and associated strategic reform agendas’. It looks to achieve this by seeing English language proficiency and communication skills of Ukrainian civil servants improved in the global arena, as well as through increased capability within the Government of Ukraine to deliver training programmes in ELT. These are two separate but related streams within the programme. The biggest change to the programme in year one is an adjusted timeline on the systems support. This decision is ultimately to ensure the quality and relevance of the output, and to provide better options for delivering it – see section C for more detail. This will not change the outcome or impact indicators.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The Outcome of improved Civil Service English Language proficiency is highly likely to be achieved, as we are already seeing progress towards this. Outcome indicators demonstrated the following results this year:
- 90% of the 104 managers who responded to the end of Y1 survey said their staff have gained skills that will be useful in their work during the BELT course.
- 92% of all respondents are confident in their newly acquired language skills and have used them in their work.
- An average of 75% of students who completed a course across closed groups and English Online Learning (EOL) have moved up one CEFR level. Note that this is not a measurement used in the one-to-one classes which are more tailored to needs. 75% was the target for year 1.
We will continue this work as planned for year 2, taking into account the lessons and recommendations from this review. For the year ahead, we will revise the systems strengthening part of the theory of change to reflect what we have learned about the system, and the reality of how much we can shape and support this system. We will still work to increase the capability of the GoU to provide ELT, but we will adjust our approach and the actions/inputs provided to reach it. Within the ToC we note the assumptions that are made around the impact of the programme, namely that this programme will be one of many leavers, and that the GoU will need have the resource to take on the delivery of ELT. The former is important to bear in mind in terms of overstating the success of the delivery of the ELT training we are providing – it is a helpful contribution, but one of many ongoing contributions. The latter is one of the issues that has made us pivot on our approach to systems strengthening in the GoU ELT provision.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme is on track to deliver impact, with outcomes already looking positive. VfM is good, and continues to be closely monitored throughout the year to ensure optimum use of funds and maximised delivery against the outputs. The programme compliments the wider British Embassy Kyiv portfolio, bridging between different sections of the embassy. Successful delivery of BELT is already contributing to successful delivery of other parts of the portfolio, as a secondary impact. The programme should continue.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	High quality English Language Training delivered to targeted groups
Output number:		1	Output Score:	A+
Impact weighting (%):		75	Weighting revised since last AR?	N/A

	Indicator 1.1			Indicator 1.2		Indicator 1.3	Indicator 1.4
Course type	Enrolled (number of students)			% of successful completion vs enrolment		% attendance of those who completed	% of students satisfied with the course*
Closed groups	1222			58%		78%	96%
	% M	39		%M	55	78
	% F	61		%F	59	79
One to ones	88			73%		91%	100%
	% M	73		%M	77	91
	% F	27		%F	63	90
Professional Skills	287			85%		100%	100%
	%M	39		%M	78	100
	%F	61		%F	89	100
English Online (EOL)	186			12%		36%	98%
	%M		38	%M	7	35
	%F		62	%F	15	38
Total	1783			58%		78%	98%
	%M		41	%M	56	78
	%F		59	%F	59	78

*No gender disaggregation was possible due to the anonymous nature of the feedback survey. This has been noted to be changed in the survey for next year.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is the core of the programme, providing ELT for civil servants through four formats: closed groups, one-to-one tuition, Professional Skills training, and English Online (EOL). The provision is given for one year (academic year), renewed each summer to reassess which ministries and students are on the course. The ELT has been hugely successful in terms of filling a gap in civil service training at a time when English Language proficiency has become more crucial than ever for Ukraine’s civil service. The qualitative feedback and results show this – from the former Deputy Prime Minister Stefanishyna feeding back to the UK Ambassador on the success and appreciation of the programme, to participants feeding back that they will definitely recommend the course to their colleagues, ‘especially those who regularly work with international partners and are involved in the process of European integration.’. The programme was designed in response to the number of requests for ELT support, and has provided a good level of reach and quality. The overall aim of the programme was to provide ELT for 1400 Civil Servants and so the enrolment numbers well surpass this target. However, the numbers of those who completed the course are below the target – only 1033 or 58%. Attendance levels surpassed the target of 75%, and satisfaction rates were high at 98%. This narrative justifies an A+, ‘moderately exceeds expectation’, surpassing the target number of participants by 27%. Focus should now turn to completion rates. British Council were very aware from the outset of the challenges in any ELT programme surrounding completion rates, and put in place a number of mechanisms to support – the agreements signed with each ministry and the delegation to points of contact in each ministry, the close level of support from the Cabinet of Ministries, maintaining the power to close groups and classes if engagement is not meeting required levels. This last point may have backfired on the results (i.e. they are numbers who did not complete), but it prioritised value for money in the provision of lessons to those who were going to make best use of them. EOL has also negatively impacted completion rates – the model used for this past year has not provided VfM. The British Council team are already changing the approach for the year ahead by: (a) reducing the overall cost of EOL from £800 per person to £600 per person; and splitting it into 3 x £200 modules in which a participant has to complete the first to get to the second. This should greatly impact VfM for EOL next year.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes have been made to this output this year. It should be noted that there was a government reshuffle which will have impacted (in the run up to the reshuffle) student numbers, as people who left roles also left their group classes. For next year, the balance between the 4 modes of delivery will be adjusted to reflect best value for money. Milestone targets will be added for next year to reflect the recommendations outlined below.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned this year:
- Recommendation: increase the successful completion milestone to 1400. Improving the successful completion rates of the closed groups will be key to achieving this. (FCDO, by May 2026)
- The model of EOL did not prove value for money, but as set out changes have been made for this academic year already to improve this. It is also important to flag that most of the classes’ dropouts happened due to the ministerial changes that took place over the academic year, which is challenging to mitigate. The flexibility of EOL enables some senior participants that would otherwise not have the time, to access ELT. EOL may also have been more accessible – it did have the highest percentage of female participants for example, who are typically more likely to be caregivers. Further disaggregation on age and disability would help to ascertain whether EOL does improve accessibility. With the change to EOL approach, we should see better VfM next year. The inclusion of a tech approach to ELT is important as we explore what does and doesn’t work from a systems and sustainability perspective. Recommendation: Maintain EOL but increase it’s VfM and monitor it’s success including with better data – review at each programme board. (SRO and PRO, every programme board)
- The gender split between all four learning formats is stable, with around 60% female participants and 40% male – this weighting is as expected reflecting the makeup of the civil service in Ukraine currently. However, 1:1 lessons are an outlier, with 73% male participants. This may reflect the fact that 1:1 lessons are usually reserved for more senior members of staff, and may suggest that there are more men in the senior levels of the Ukrainian civil service. Recommendation: Look into the gender balance of more senior levels in the civil service and determine whether BELT should aim for at least 50% female participation in 1:1 lessons. (FCDO and British Council, review in Q4 programme board).
Output Title	GoU and relevant institutions and agencies are formally involved in the programme
Output number:		2	Output Score:	A++
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

The purpose of this output was to ensure ministry engagement in the programme, which we knew was key to having civil servants supported to participate in BELT. In consultation with the Cabinet of Ministers the British Council originally approached 59 institutions. 3 of them declined and 1 appeared to have lost the status of the governmental body around the project start. The remaining 55 all signed corporation agreements with the British Council and had students participating in BELT. See Annex B for the final list of Ministries. The number of Ministries supporting participation well exceeded our initial expectations for the programme. We knew anecdotally that given the stretch of the civil service, it can be hard to maintain links with all Ministries with a risk that ELT drops down their priorities. Meeting with representatives from many of the institutions in the summer graduation event enabled us to see the spread of topics relevant to Euro-Atlantic integration that they covered, and their enthusiasm for maintaining BELT participation.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Following the start of the programme, a couple of new institutions were added part way through as new requests arose which were considered high priority – for example, NAUCS were added. For next year, we expect the list of Ministries to decrease, become more targeted where ELT will most closely support Ukraine’s Euro-Atlantic future.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned this year:
- Having the agreements signed between Ministries and the British Council, and the points of contact. Recommend updating the logframe to reflect just one output indicator – the second is duplicative. (SRO and PRO, by May 2026)
- The choice of the institutions to partake in BELT was largely based on Cabinet of Ministries recommendations. Though this resulted in a very diverse group of participants, the recommendations for the next year (which is already considered by the programme board) are to exclude the organisations with low attendance rates and provide more group and 1-2-1 opportunities for institutions of strategic importance to Urkaine’s Euro-Atlantic future. As a result, 38 institutions have already been sent out agreements for AY 2025-2026. It is also recommended to think of the “relevance” rating of the institutions involved to have a more in-depth understanding of how helpful the choice of institutions is for BEK’s wider strategic impact. Recommend updating the logframe to reflect the relevance of the institutions selected. (SRO and PRO by January 2026).
Output Title	Systems
Output number:		3	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

The design of the systems work in the business case was not rigorous enough to take into account the context. British Council did prepare to undertake the planned initial consultation of GoU to understand the best interventions, but the FCDO put this on pause in March. The approach to systems was pivoted to instead focus on three areas:
- Building our relationship with and understanding of NAUCS. They hold the responsibility for all GoU L&D, and so it was essential to work with them rather than carry out a study of them. Our success in this relationship included bringing NAUCS into the BELT programme as participants halfway through the year, and NAUCS formally recognising BELT meaning that participation from Civil Servants will now provide credits towards their formal L&D. This could be hugely impactful on completion rates.
- Building our understanding of other GoU education initiatives. For example, there are ongoing reforms within Higher Education, as well as ongoing development of a unified digitalised solution for civil servants’ L&D by the Ministry of Digital Transformation.
- Building links with other donor programmes supporting Civil Service L&D. Most notably, the EU’s work on Public Administration Reform and the trainings that they provide to civil servants. Conversations begun in this space on aligning selection of participants.
A more consolidated plan for systems support needs to be created, so the output therefore could not meet expectations as originally set out. But good progress was made, and the team prevented a rushed or misdirected study on ELT systems that could have produced a siloed result and poor VfM.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The formal side of this work was pivoted. A plan for systems support needs creating – and ultimately a plan for the sustainability of ELT provision in GoU.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation for this work to progress, but with time put into redesigning an approach - with logframes and ToC updated accordingly. The impact weighting of this output will grow over the coming years. (SRO and PRO, by May 2026)

D: VALUE FOR MONEY [1 page]

Key cost drivers and performance

As set out in the Business Case, the key VfM indicator for this programme is cost per head of the individuals trained (a) overall, (b) by method of teaching, and (c) by academic progress made using the CERF framework. Cost drivers include teacher salaries, access to EOL from British Council (which costs per student), participation and advancement of students in ELT. We were not clear from the outset whether VfM would be measured against numbers that took part (i.e. originally enrolled), or numbers that completed the course. This should be clarified for the next year.

VfM performance compared to the original VfM proposition in the business case

Expected VfM in Business Case	Cost over full academic year, (GBP)	No. taught over academic year	VFM indicator 1: cost per student taught, GBP		Expected CEFR level increase	VFM indicator 2: Cost per level increased
Closed group courses	£590,400	900	656	1		656
One-to-one courses	£162,000	45	3600	0.5		7200
Professional Communication Skills workshops	£75,000	350	215	NA		NA
EOL subscriptions	£112,000	140	800	1		800
Total	£939,400	1435

Actual VfM	Cost over full academic year, (GBP)	students taught (enrolled & completed)	VFM indicator 1: cost per student (GBP)	CEFR level increase (no. students)	VFM indicator 2: Cost per CERF level increased
Closed group courses	520,320	Enr. 1222	426	706	737
		Comp.704	739
One-to-one courses	244,605	Enr. 88	2780	NA*	NA
		Comp. 64	3822
Professional Skills	50,000	Enr. 287	174	NA	NA
		Comp. 243	206
EOL subscriptions	104,000	Enr. 186	559	21	4952
		Comp. 22	4227
Total	918,925	Enr. 1783
		Comp. 1033

*Most one-to-one classes were focusing on individual needs of the student, such as conference presentation, specific report or partner meeting. Therefore, CEFR level increase was not measured for the majority of participants of this format.

VfM indicators are consistently better than intended for cost per student for enrollment except for professional skills, but worse than intended for cost per student who completed. This suggests weaker than anticipated VfM for those who completed, but the level of those enrolled suggests positive signals to cost drivers falling over time. The VfM for EOL in particular stands out as poor (£4952 per level increase) in comparison to for example closed group session’s cost per CERF level increased (£737 per level increase). As we did not set out whether we are aiming for cost per student enrolled or completed, it is difficult to make an overall judgment. However the key conclusions we can draw are:
- The professional skills workshops were strong VfM against the indicators. Their model is efficient and effective (intensive 2 days, 1 teacher with a group of 12, high completion rates, positive feedback from participants). They should continue with little change to their model.
- Closed group courses and 1:1 courses were relatively similar in their VfM. To become more efficient and effective, they need to increase the number of completion rates. We would consider the 1:1 lessons to score more highly on equity given the flexibility of the style of teaching, location, and timing of classes.
- EOL demonstrates the poorest VfM. It has been mentioned already that the high number of dropouts is considered closely linked to the impact of a government reshuffle. We do not have the data to back that up. However, we also understand from participants and Ministries that EOL is considered highest on the equity front. It provides the highest level of flexibility and autonomy for the learner.
Assessment of whether the programme continues to represent value for money

The programme should continue but with the following adjustments to increase VfM:
- Revised VfM indicators, reflecting rates of completion. (PRO by May 2026).
- Given 1:1 lessons are the most expensive, greater detail on their VfM should be obtained i.e. tests to show increase in ability, data disaggregation to understand accessibility. (British Council by May 2026.)
- The British Council team are already changing the approach for the year ahead by: (a) reducing the overall cost of EOL from £800 per person to £600 per person; and splitting it into 3 x £200 modules in which a participant has to complete the first to get to the second. This should greatly impact VfM for EOL next year. EOL attendance and rates should be closely monitored in every programme board. (FCDO and British Council.)
- New data to support understanding of equity should be collected as part of monitoring and evaluation work. This should be worked on with a GESI adviser, but should look at gender, disability, and ages of those who enrol in each mode of teaching, vs those who complete. This will inform whether EOL courses are in fact supporting greater equity. (to be decided by Programme Board in Q4).
Finally it is worth noting that there is a proposal in the upcoming Ukrainian budget that teachers will receive up to 50% salary increase. If this were to go ahead, it would push up the costs of the programme therefore impacting VfM. This might make year on year comparison challenging.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The programme is within BE Kyiv Risk Appetite for all seven risk categories and overall risk is considered to be minor. Risk appetite has remained the same and we have comfortably delivered within it – no changes are necessary. The biggest risk to the programme has remained the capacity of Civil Servants and Ministries to engage in the programme. This is reflected in the completion rates of the results being so much lower than initial participation rates. However, results were still good, so mitigations to some extent were successful – more should be looked into for next year. The recruitment of enough teachers was an initial high risk (highlighted in the Due Diligence Assessment), however this was rapidly overcome through the work of the team at the British Council to successfully recruit all the required teachers. The context of the programme being delivered in a country at war remains a risk, in particular on the people side. This risk became prominent this summer as the British Council building was damaged in an air strike. Thankfully all staff are safe. The remaining risk from this event which is now on the risk register is that the British Council no longer have an office to deliver their Professional Skills workshops from. Rapid work from the British Council team and the kindness of the National Agency of the Ukrainian Civil Service has secured space within NAUCS offices for now.

On gender and equality, in the Business Case we set out that selection of participants would be based on need, but that British Council would aim for 40% female participation. In reality the number is higher for female participation this year (as expected with the current make up of the civil service), but as set out already this threshold isn’t met in the one to one classes. This should be looked into to ensure any equality issues are addressed. From the DDA, all recommendations have been followed up on. Note that one recommendation, around further defining the work on systems to enable more accurate outer year budgeting, is being pivoted and so no longer applies. The programme continues to be low risk against the Counter Terrorist Financing and anti-money laundering guidance and Climate and environment obligations with no specific mitigation measures required.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

British Council worked extremely efficiently and to a high standard throughout the year. They effectively managed risk, finance, and delivery, escalating any issues to the FCDO at the earliest opportunity. The FCDO were very involved in the government engagement part of the programme at times, and so close working between the FCDO team and British Council team was crucial – and successful. Within the FCDO, we brought together a working team of political and development expertise, due to the number of ministries we would be reaching and the desire to ensure we were targeting the ELT at the right students in the right ministries. This collaboration between development and political colleagues was incredibly beneficial and contributed to the success of the programme – it is a model that should be consider for other programmes working closely with multiple parts of government.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
British Council’s Monitoring and Evaluation team advised and led on the evaluation for the ELT part of the programme. This consisted of entry tests and surveys for all participants, and exit surveys for all participants – and tests for some of the participants to ascertain increase in CERF level. The methodology was thorough and rigorous and has provided a detailed insight into the strengths and weaknesses of the first year of delivery, enabling recommendations for the year ahead. Field visits took place from the FCDO team to see the professional skills workshops in action, including engagement with participants. The summer graduation event was also an opportunity to engage with a broad range of participants. Meetings between the FCDO and Cabinet of Ministers only (without British Council) took place to enable any feedback or raising of issues. None was raised at any point. For the systems support, the logframe indicator was simple – and wasn’t achieved due to a pivot in approach. Recommendation to review and update the logframe and theory of change. It could also be considered to introduce light touch Third Party Monitoring, and perhaps also a Gender, Equality, Disability, and Social Inclusion adviser to observe classes and materials to look for further improvements.

Evidence
The evidence – and lack of evidence – around equity will impact how we approach monitoring, evidence, and learning next year, including considering a specific gender target for 1:1 lessons. The quality of evidence gathered has been very thorough and useful in assessing the impact. Harder to measure, but mentioned by a number of participants and institutions, has been the professional development that comes with the ELT – building networks of civil servants working on similar areas that has contributed to Ukraine’s Euro-Atlantic integration in other ways. We are being asked, and are considering, to look at events for the BELT network, in particular senior participants. This includes looking at professional coaching through links with the UK FCDO, and policy talks in English on euroatlantic themes which we are discussing with the EU. Both of these have been asked for, and are no or low cost opportunities. The BELT team should consider whether to incorporate these new elements into the BELT programme, and if so, what they would look like for the programmes theory of change and logframe – how would success be measured.

Learning
The key lesson learned in this review is the importance of having a formal check in point within the first 6 months of the programme, to assess whether the ToC and logframe remain fit for purpose or need updating. Equally looking at ways to more formally monitor VfM indicators throughout the programme, so that more targeted pivots can be made during the year. The second key lesson to pull out is the benefit of close collaboration between political and development teams on programming. The combination of expertise has underpinned the success of the first year of the BELT programme, and should be more formally incorporated into other programmes across the FCDO.

Date of last narrative financial report		Date of last audited annual statement

Annex A – BELT Theory of Change
Assumption: this programme will be one of many leavers to drive the impact.
Assumption:
Ukrainian institutions have the resource to take on the delivery of ELT.

*No gender disaggregation was possible due to the anonymous nature of the feedback survey. This has been noted to be changed in the survey for next year.

Annex B – Ministries, Agencies, and Institutions receiving ELT through BELT
Antimonopoly Committee
CabMin
DSNS
Economic Security
Min of Agrarian Policy and Food
Min of Community Development, Territories and Infrastructure of Ukraine.
Min of Digital Transformation
Min of Economy
Min of Education and Science of Ukraine
Min of Energy of Ukraine
Min of Environmental protection and Natural resources
Min of Foreign Affairs
Min of Health
Min of Internal Affairs
Min of Justice
Min of Reintegration of Temporarily Occupied territories
Min of Social Policy
Min of Veterans
Min of Youth & Sport
Min Strateg Prom
MinFin
National Energy & Utilities Commission
National Police
NAUCS
RNBO
Security Service of Ukraine
St Agency of Energy Efficiency
St Agency of Restoration & Development of Infrustructure
St Agency of Water Resources
St Agency Tourism Development
St Border Guard Service
St Comteleradio
St Customs
St Export Control
St Film Service
St Fin Monitoring
St Forest Agency
St Geo Nadra
St Geocadastre
St Labour Service
St Nuclear Regulatory Insp
St S. of Specials Communication and Info Protection
St Service maritime,shipping
St Service of Ethnic Affairs & Freedom
St Space Agency
St Statistic Service
St Tax Service
State Agency for melioration, fishery and food programs
State Audit Service
State Avia Service
State Drugs Service
State Environmental Inspectorate
State Migration Service
State Service on Food Safety
Supreme Court