## Annual Review Template

Title: SPIRIT (Social Protection for Inclusion, Resilience, Innovation and Transformation)
Programme Value £ (full life): £25 mln.		Review date: 7 October 2024 – 30 September 2025
Programme Code: 400388	AMP start date: 29/10/2024	AMP end date: 07/10/2026

Summary of Programme Performance
Year	1
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400388 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400388 Documents

A Summary and Overview
B Theory of Change and Progress towards Outcomes
C Detailed Output Scoring
Output 1	Social Recovery Office (formally Project Management Unit)
Output 2	Small Scale Grants Mechanism
Output 3	World Bank Partnership

D Value for Money
E Risk
F Programme Management: Delivery, Commercial and Financial performance

G Monitoring, evidence and learning

SUMMARY AND OVERVIEW

Context and Strategic Importance

Russia’s full-scale invasion has reversed 15 years of development gains in Ukraine, deepening inequalities, exacerbating demographic decline, and compounding social vulnerabilities. Socio-economic consequences are becoming more evident with mass displacement, growing poverty, increasing disability, a declining workforce, and falling household resilience. Soviet-legacy social protection systems - and under-developed social services - are under unprecedented strain with rapidly growing war-related expenditure and an increasing proportion of Ukrainians in need. With social spending approximately 14-17% GDP, second only to defence for Government of Ukraine, this poses a serious risk to Ukraine’s long-term prosperity, stability and equity.

Government of Ukraine (GoU) has identified reform of social protection systems and services as an urgent priority given their critical role in securing Ukraine’s future prosperity, equity, and stability. These reforms are essential to bolster resilience against Russian aggression, accelerate human capital development, strengthen social cohesion, empower the most vulnerable, support EU accession, and enable the gradual transition from humanitarian assistance to national Ukrainian systems that can meet needs at scale.

Programme Overview

This is the first annual review of Social Protection for Inclusion, Resilience, Innovation, and Transformation (SPIRIT), a £25m two-year programme delivered in partnership between FCDO, UNICEF and the World Bank. The review assesses programme performance between October 2024 and November 2025.

BE Kyiv’s Humanitarian and Resilience Team vision is to ensure the most vulnerable people impacted by Russia’s full-scale invasion of Ukraine are supported to meet their basic needs, exercise their rights and strengthen their resilience. SPIRIT is fundamental for delivery of this vision as well as our ambition to support gradual transition from humanitarian assistance to national systems and services that meet needs of the population at the necessary scale.

SPIRIT is the UK’s flagship social recovery programme in Ukraine, combining programme delivery, policy leadership, and development diplomacy. It focuses on building the capacity, sector coordination, and evidence base needed to drive reform Ukraine’s social sphere and lay the foundations for a more inclusive, effective, and efficient social protection system. With an emphasis on empowering the most vulnerable and war-affected groups—including women, children, persons with disabilities, and veterans—SPIRIT advances the UK’s commitment to a rights-based recovery while promoting fiscal sustainability and alignment with EU standards.
Delivery Model and Partnerships

SPIRIT is delivered through a multi-partner structure led by FCDO in collaboration with implementing partners the World Bank and UNICEF, working closely with the Ministry of Social Policy, Family and Unity (MoSPFU) and other key government ministries. This model brings together the leading Ministry, UN agency and IFI with the mandate for social policy in Ukraine. The programme is delivered through three interlinked components that combine technical assistance, policy development, institutional strengthening, and local service provision: the Social Recovery Office (SRO) led by UNICEF, the Small Grants Mechanism (also known as the Social Service Pilot) also led by UNICEF and supported by Administrator Isar Ednannia, and a strategic partnership with the World Bank.

SPIRIT is underpinned by values of localisation, inclusion and participation. The delivery model strengthens the capacity of local Ukrainian actors in parallel with national government systems, structures and stakeholders. With this approach, SPIRIT is successfully laying foundations for the reform of Ukraine’s social protection systems and bolstering future readiness for investment at scale. The programme’s multi-partner structure - and delivery of early results - has helped secure donor confidence and paved the way for a new US$500 million reform-oriented Investment Project Financing (IPF) operation backed by UK loan guarantees.

Summary supporting narrative for the overall score in this review

The review process was conducted by the Humanitarian and Resilience Team with the support of both programme and advisory staff within BE Kyiv. The assessment has drawn upon partner reporting, ongoing partner engagement, and wide-ranging interviews with key stakeholders. Security restrictions prevent the SPIRIT team from directly engaging with down-stream beneficiaries as part of this review but the multi-level monitoring architecture for the Small Grants Mechanism – including forthcoming third-party monitoring – will help mitigate the impact of these restrictions.

The overall score awarded for this review period is an A reflecting implementation is broadly on track with the majority of assessed outputs meeting expectations and outputs under the SGM notably exceeding expectations. SPIRIT has consolidated the UK’s reputation as a social protection thought leader and partner of choice for Ukraine and continues to develop as a galvanising platform that fosters sector coordination and brings coherence to the efforts of diverse stakeholders in the international community across government, multilaterals, IFIs, donors and civil society. In a context which continues to be characterised by uncertainty, the programme has helped provide continuity for the social protection reform agenda, mitigated impacts of US Aid cuts, and responded effectively to government administration shifts.

In line with the UK’s reinvigorated approach to international development, SPIRIT has allowed the FCDO to act as a strategic investor that leverages resources with UK expertise and leadership to drive larger-scale impact and policy change. The UK acted as a first mover in the social sector to successfully unlock additional funding from International Financial Institutions and the international donor community, using combined instruments including loan guarantees, technical assistance and political engagement. SPIRIT has successfully catalysed a $10 million World Bank Grant to progress implementation of social reforms, a $30 million investment in inclusive education, and laid the groundwork for a $200million EU backed ‘Together Ukraine’ Project. Encouragingly, Germany has also requested to ring-fence a dedicated proportion of their Ukraine Recovery Trust Fund (URTF) investment directly into SPIRIT. While VFM is challenging to quantify for long-term social reform efforts, SPIRIT’s work on pension reform presents a unique opportunity to estimate potential return on investment - preliminarily indicating a positive return up to USD $2.4 billion by 2060 (see VFM section).

Partner performance has been relatively strong, with clear evidence of co-creation across majority of interventions. In practice, this means SPIRIT partners have attempted to model a collaborative approach, working together from the earliest stages with a commitment to transparency, flexibility and equity. Rather than a rigid role delineation of the donor as funder and the partner as implementer, together FCDO, UNICEF and the World Bank have strived towards shared ownership, collective decision-making, and mutual accountability across the programme’s design and delivery. This approach recognises that the combination of donor technical and financial resources with partner expertise can lead to more creative, impactful and innovative interventions –building stronger and more sustainable relationships that have potential benefits beyond the programme’s scope. This trust enables greater transparency and helps deliver on the UK’s commitment to ensure money pushed through the multilateral system is used to greatest impact.

Collaboration between partners has strengthened over time and delivery has reportedly benefited from active donor engagement. In Annual Review assessment, Ministry of Social Policy, Family and Unity described SPIRIT as ‘transformative’ and ‘absolutely critical’ for Ukraine’s social reform agenda. However, relationship management, technical oversight, and the maintenance of an enabling environment for co-creation has required significant capacity and resource from SPIRIT partners. For the FCDO, this has been alongside political engagement requirements and development diplomacy efforts to maximise SPIRIT’s impact and attract new actors and investment into the social sector. As SPIRIT moves into the second year, the FCDO will need to consider how limited internal resource is used to maximum effect and balance of priorities across oversight of programme delivery with FCDO modern development ambitions to act as a policy leader, sector convenor and catalytic investor.

The first year of the programme has built the necessary foundations and robust partnerships required to deliver the programme outcomes, including the modality for direct cash transfers to strengthen national and local ownership and delivery. However, the programme must adapt to lessons learnt over the first year to refine components and formalise ways of working to ensure sustainability and impact. This includes scaling back on projects not related to SPIRIT ‘core’ mandate of strengthening shock-responsive and inclusive social protection systems and services, as well as strengthening opportunities for alignment and transition with humanitarian partners and bolstering capacity building support for local actors.

Major lessons and recommendations for the year ahead

Overall Recommendations
#	Recommendation	Owner(s)	Deadline
1	Programme Governance: By April 1 2026, protect programme continuity and resilience with a comprehensive review of SPIRIT governance structures and resource capacities, and implement a codified governance model that clearly defines roles, decision-making authority, and accountability mechanisms. Formalize and publish updated protocols and SOPs for planning, change control, risk management, and partner engagement for focal points and workstream leads. Establish a centralized portfolio repository accessible to all partners, containing 100% of core programme documents, onboarding kits, and decision logs by March 31 2026. Formalise monthly partner meetings and implement standardized process for documenting key decisions and agreements—including those with GoU—so that 100% of decisions have clear ownership, timelines, and deliverables logged within 48 hours of approval.	SRO, PRO	End FY
2	Monitoring, Evaluation and Learning: By end of FY, review and revise SPIRIT programme’s logframe and MEL approach to validate assumptions, incorporate lessons learned from delivery—including strategies to mitigate administrative and regulatory bottlenecks—and ensure the framework supports adaptive management while maintaining deliverability. Engage with partners to agree on any revised outputs, milestones, and their weightings for both the official logframe and the World Bank supplementary framework. Finalize and secure formal approval of the updated MEL framework by March 31 2026, ensuring 100% alignment with donor reporting requirements and programme objectives, and embed mechanisms for real-time learning and quarterly reviews to maintain adaptability.	PRO, MEL Adviser	End FY
4	Humanitarian-Development Nexus: By June 30, 2026, strengthen synergies across BE Kyiv’s humanitarian and resilience portfolio by mapping overlaps and integration opportunities between the Cash Pilot, BLOOM, SPIRIT, and PULSE initiatives, focusing on protection, inclusion, localisation, and service delivery priorities. Ensure active co-chairing of the Task Force on Social Protection and Humanitarian Cash Linkages to drive alignment and shared learning. Complete a comprehensive analysis of administrative and regulatory bottlenecks and incorporate mitigation strategies into programme design. Develop and submit a recommendations paper for the next phase of delivery, including options for HARP and SPIRIT extension, by June 30, 2026, ensuring stakeholder validation and alignment with donor priorities.	SRO, SDA, Humanitarian Adviser	Q3 2026
6	Strategic Communications: By June 30 2026, mitigate risk to design and delivery of sustainable social reform agenda, working with BE Kyiv Head of Strategic Communications, MoSPFU and implementing partners to design a strategic communications approach for SPIRIT. Identifying needs and gaps in public communication of reforms, opportunities to ensure population voices heard and needs met, and providing recommendations for delivery of clear, consistent and inclusive messaging as policy designs are finalised.. Mobilize in-house capacity or additional resources as needed.	PRO and BEK Head of Strategic Communications	Approach agreed by end Q2 2026
7	Social Recovery Office: By April 30 2026, drive increased efficiency, effectiveness, and evidence-based decision-making within MoSPFU by completing a review of the SRO’s project management framework, operational tools, and governance architecture. Provide actionable recommendations to ensure time-bound, accountable, and effective delivery, and improve ways of working, including communication and forward planning. Support the development of a dynamic workplan incorporating shared indicators, milestones, risk registers, an agreed monitoring cadence, and a sustainable exit plan for the SRO, including a transition framework agreed with MoSPFU. Integrate learning and best practices from FCDO Governance Cadre and Centres of Expertise into the design and recommendations.	SRO, Governance Adviser, working with BEK Governance Team and Delivery Unit specialists.	End FY
8	Small Grants Mechanism: By April 30 2026, explore and define opportunities to increase capacity-building support for local authorities and community service providers, including social services knowledge, needs assessments, and budgeting, to strengthen sustainability, align with government priorities, and meet FCDO commitments on localisation. Finalize scoping recommendations for potential geographic expansion, including frontline hromadas, by May 15, 2026. Follow up on recommendations from monitoring and assessments—such as the use of digital solutions and peer-to-peer implementer networks—and integrate these into the capacity-building plan. Ensure all findings and recommendations are documented and validated with stakeholders by the end of Q2.	SRO, PRO, Governance Adviser	Q2 2026
9	World Bank Partnership: By March 31 2026, review and refine the World Bank supplementary logframe to prioritize projects with clear value-add, strong VfM, and alignment with BE Kyiv and SPIRIT strategic priorities. Streamline the breadth of activities to focus on socially sustainable economic growth, including support for more effective, efficient, and inclusive social protection systems and human capital development. Ensure the design and delivery of the Project Appraisal Document for the new UK-backed lending instrument is completed in timely manner, embedding lessons learned from SPIRIT and incorporating strategies for scaling interventions. Secure stakeholder validation and donor alignment for the revised framework and PAD by the deadline.	SRO, BEK Economist, EECAD Economic Support Team	Q1 2026
10	SPIRIT Extension: By January 31 2026, apply learning from the annual review to develop a brief options analysis framework for a potential SPIRIT extension, identifying areas for refinement, opportunities to scale successful interventions, and potential alignment or transition pathways across the HART portfolio. Complete identification of any further scoping requirements by March 31 2026, and prepare a Business Case amendment based on findings, ensuring stakeholder validation and alignment with donor priorities. Embed mechanisms for evidence-based decision-making and adaptive planning in the framework to support next-phase delivery.	SRO, PRO, SDA, Governance Adviser	Options analysis by end January 2026; BC Amendment Completed by April 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The SPIRIT Theory Of Change (TOC) development was supported by the BE Kyiv MEL Advisor. The TOC sets out that if improved capacity and coordination within and across GoU and key development actors helps build foundations for evidenced-based reform and with revitalisation of community-based services for the most vulnerable with new, innovative, participatory and locally led model then Ukraine will be better able to develop and sustain inclusive, efficient, shock-responsive social systems that meet the needs Ukrainians in all their diversity - thus, laying the foundations for long-term socio-economic recovery and supporting the path to Euro-Atlantic integration.

SPIRIT is on track to deliver its Theory of Change within the programme. While the steps to achieving outcome and impact are obviously not comprehensive of all potential enabling activities, they remain valid and the ToC logic, supporting evidence and most assumptions have held up to implementation experience. Concerns about sufficient FCDO resource and challenges in SRO staff recruitment have particularly held true. Data, evidence and learning continues to be disaggregated by age, sex, disability, geography. The programme is fully compliant with PSED and equalities commitments and implementing partners have reported on GESI requirements and currently assessed at expected minimum of Category C (meaning project includes some contribution to gender equality but does focus on addressing root causes of inequality).

At the time of design, SPIRIT was foreseen as a ‘high risk, high reward’ programme and the TOC was designed with the lead MEL Adviser to recognise this uncertainty with pragmatic and relatively broad milestones. All outputs have been met to minimum expectations and remain relevant, though options for refining or expanding scope of delivery should be considered based on component assessment. This includes adapting Output 3 - while language of ‘Small scale service providers/civil society organisations are supported by small scale grants’ does allow the flexibility to increase support to Local Authorities as Municipal Entities, a proposed adjustment of language to ‘Local communities and service providers are supported by small scale grants’ should be considered to endorse increased support across both municipal providers and civil society as programme learning indicates this is what local need demands. For Input 1, a drawn-down modality has been developed to support capacitating of Ukrainian organisations which will be further progressed in the next phase of the programme. While minor adaptations to the programme have been required to respond to contextual developments and lessons learnt, there are no significant changes to the outcome or impact level of results framework indicators expected and there is no material change to programme design.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

With implementation of recommendations, the programme remains on track to contribute to its expected outcomes and impact within the allocated time and budget. Mobilisation is fully underway and results are being reported across all components. Based on interview feedback and detailed reporting from stakeholders, SPIRIT has met minimum expectations for key outputs—including establishment of the Social Recovery Office, operationalisation of the Small Grants Mechanism, delivery of World Bank support for cross-sector initiatives, and effective provision Better Care technical assistance catalysing reform. These achievements have already contributed to the overarching goal of enabling Ukraine to develop and sustain more inclusive, efficient, and shock-responsive social protection systems that meet the needs of the most vulnerable.

While contingent on Ukraine’s resilience, political will for reform, and the broader fiscal and security context, the timely, accountable delivery of outputs should continue to drive progress towards envisaged outcomes and impact. Where any output indicators are performing below expectations, recommendations have been made to ensure they are quickly on track for delivery. Risk management will remain a priority to mitigate factors within SPIRIT’s locus of control. There are no changes to expected outcomes on equalities. However, based on inclusion analysis and learning to date, both UNICEF and the World Bank have gone beyond logframe commitments by expanding their focus on disability inclusion across programme interventions.

As expected, changes in government administration impacted delivery and delays were experienced. However, strong output delivery and confidence in the theory of change indicates that SPIRIT is well-positioned to achieve its intended outcomes if recommendations are implemented. For the year ahead, the programme will focus on refining delivery modalities, building upon programme successes, and adapting interventions based on monitoring, evaluation and learning across the programme’s life course. This includes an increased focus on bolstering local capacities, entrenching and formalising organically developed ways of working, and increasing alignment with humanitarian interventions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Ukraine remains the UK’s top foreign, security and development priority and SPIRIT supports FCDO to deliver on our Euro-Atlantic and Security priorities - helping Ukraine win the war and lay the foundations for a resilient and sovereign peace. As the only donor programme focused on driving social reform at scale in Ukraine, SPIRIT continues to provide a unique value proposition. While the context in Ukraine continues to evolve – politically, militarily, economically and diplomatically – the rationale for SPIRIT’s development persists and its theory of change remains sound. Despite US peace efforts, there is little sign of the war ending. Russian aggression and the impacts of war continue to disproportionately effect the most vulnerable and places further strain on underdeveloped public services and social protection. SPIRIT’s targeted investment in people—and the systems and services they rely on—is fundamentally an investment in Ukraine’s future. SPIRIT recognises Ukraine’s population remains one of the country’s greatest resources for resilience against Russian aggression and that modernisation of social protection systems is essential for long-term stability, prosperity, and equity.

SPIRIT’s approach aligns with FCDO’s reinvigorated international development agenda and the Minister for Development’s ambition for a modern UK partnership. Baroness Chapman has encouraged ‘genuine partnership not paternalism’ and transition from acting as a donor to a catalytic investor. SPIRT has worked towards this and the associated recommended shifts in development approach with success, delivering on steers to support countries build systems that will ultimately help them transition from international assistance. SPIRIT brings together the UK’s technical expertise in social protection, its reputation as a thought leader and convenor across the humanitarian-development nexus, and its position as a trusted partner for the Government of Ukraine, UN agencies, IFIs and the international donor community. This combination of policy leadership, development diplomacy, and programme activities is a robust example of FCDO’s modern development model – recognising the biggest impact we can have is not by simply spending money but instead utilising UK expertise, leadership and political engagement to drive transformative policy change.

SPIRIT has delivered on UK commitments to inclusive growth and a more coordinated approach between humanitarian assistance and social protection system strengthening. In lockstep with FCDO’s humanitarian portfolio, this is helping drive the shift from an international, heavily UN-supported response in Ukraine to one led by government, reforming its policies to protect the most vulnerable, supported by local civil society. Alongside opportunities for further alignment with humanitarian systems through ‘HARP’, SPIRIT connects across the Ukraine portfolio - bolstering human capital development alongside BE Kyiv’s economic recovery efforts and working with the governance portfolio to refine our work on delivery units to support government on reforms, institutional resilience and EU accession. The programme remains central to UK objectives and remains the UK’s primary vehicle for delivering social and inclusion commitments, including those under the BE Kyiv Country Business Plan, the UERRD Recovery and Reconstruction Strategy, and the 100-Year Partnership with Ukraine. On this basis, it is strongly recommended that SPIRIT continues.

## C. DETAILED OUTPUT SCORING

Output Title	Project Management Unit (Social Recovery Office - SRO) established to progress priority strategies, policies, and plans for GoU
Output number:		1	Output Score:	B
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 The Social Recovery Office for social protection, social services and social inclusion reforms is established and operational	SRO is established and fully operational[1]	Established April 2025 but not fully operation due to delays in recruitment of national staff and reduction in UNICEF’s resource allocation. Project management architecture and operational protocols need further development. Restructiring conversations with Ministry ongoing. / SCORE: B - moderately not met expectations
1.2 Adaptive and phased workplan for the SRO on social protection, social services and social inclusion reforms is developed and implemented in collaboration with the Ministry of Social Policy	Workplan developed with inputs from MoSPFU and implementation commences on priority deliverables[2]	Initial workplan finalised with MoSPFU April 2025, updated workplan under refinement with new administration, but further development required to ensure functional as adaptive and operational mechanism to drive reforms. / SCORE: B - moderately not met expectations
1.3 Number of priority reforms in the Roadmap aimed at enhancing disability inclusion and/or gender-responsiveness of social protection or social services policies/programmes in Ukraine	0[3] for this review (2 for September 2026)	The ‘Roadmap’ included a focus on five priority reform areas[4]. Of these, one is targeted specifically on ‘Disability Inclusion’ to support reform of disability assistance and benefits. Evidence generation for this is underway with ‘Mapping and Recommendations Optimising Disability Support in Ukraine’ and a ‘Review of Child Disability Benefits and Services in Ukraine’ assessed as 50% complete. / SCORE: A+ - moderately exceeded expectations
1.4 National Social Services Strategy is developed by the Ministry of Social Policy in consultation with key stakeholders / NB: The final target for this indicator may need to be amended to an integrated social assistance and services strategy pending negotiations with the new MoSPFU leadership.	Scope for the Strategy is defined and consultations started[5]	Scope for the Social Services Strategy defined by UNICEF and downstream partner Centre for Economic Reform[6] and initial consultations held. First draft presented to MoSPFU in December 2025. However, concerns raised by FCDO with regards tp meaningfulness of participatory approach, quality of technical work produced and gaps in expertise. Stocktake underway and requires agreement of risk mitigation measures with clearly communicated implementation plans and opportunity for QA. / SCORE: C – substantially did not meet expectations
1.5 Support is provided to the Ministry of Social Policy to establish the new sectoral working group on social protection	Terms of reference, concept note and workplan developed and agreed with MoSPFU[7]	Refreshed SWG was launched with the SRO functioning as the Secretariat. During reporting period key deliverables have been: (a) convening meetings of the SP SWG; (b) advancing the setup of thematic task forces; and (c) supporting the coordination of technical assistance related to social protection. SWG recognised as one of highest performing and utilised by Ministry to communicate reform priorities with the international community. Outcomes of SWG and task forces have assisted in reducing duplication and improving alignment and facilitated bridge building between humanitarian and development partners. / SCORE: A+, moderately exceeded expectations
1.6 Number of evidence-generation and advocacy products to inform cogent reforms and system adaptations related to social protection, social services and social inclusion	3[8]	Three products have been finalised in Q4 2025 and provided for review, two more have been launched, and an additional three are at ToR drafting stage. Training provided to MoSPFU on products and examples of learning being embedded within legislative, policy and programme development. / SCORE: A+, moderately exceeded expectations
1.7 Two pilots on inclusive interventions delivered to inform reforms and system adaptations related to social protection, social services and social inclusion with the aim to reach the most vulnerable	Concept note for two pilots developed	One concept note has been developed for a shock-responsive social protection pilot with the proposal to streamline and merge the second. Delayed by ministerial changes, concept is currently under refinement and implementation of the pilot is expected for the first quarter of 2026. / SCORE: A - met expectations (with agreement of adapting milestone with FCDO to one pilot)
[1] Source of information: Ministry of Social Policy physical office space exists; contracts for SRO staff available; and SRO implementation reports (through field monitoring and programmatic visits/spot-checks)
[2] Source of information: Workplan document exists; meeting minutes capturing agreement (on the workplan and key milestones/priority deliverablesis) with Ministry of Social Policy
[3] Source of information: The number of priority reforms in the Roadmap specifically aims to enhance disability inclusion and/or gender-responsiveness.
[4] Strengthening Social Protection Systems for Demographic Resilience; Child and Family Welfare Reform in Support of Future Generations; Disability Inclusion; Demographic Recovery and Social Cohesion; and Enhancing the Social Services System (Social Services Strategy, Digital Solutions & Resilience Centres).
[5] Source of information: Milestone 1 - Strategy partially drafted, which includes that the Social Services Strategy development process has started and a zero draft exists; Final Target - Strategy finalized (document exists) and Strategy presented to the Cabinet of Ministers of Ukraine.
[6] CER was contracted following an open competitive tender and was chosen among three candidate organisations as the highest rated according to the following criteria: 1. Clarity of activities and expected results. 2. Sector expertise and experience. 3. Project Management experience 4. Cost-effectiveness.
[7] Source of information: Terms of reference, concept note and workplan exist; documented agreement by MoSP to the terms of reference, concept note and workplan; meeting minutes (with participant lists); and online coordination tracking tool exists
[8] Source of information: Evidence-generation and advocacy documents exist.

Briefly describe the output’s activities and provide supporting narrative for the score.

Based on indicator weightings, the Social Recovery Office Output scored a ‘B’ overall –moderately exceeding expectations for three indicators, meeting expectations for one indicator, moderately not meeting expectations on two indicators and substantially not meeting expectations on one indicator.

The Social Recovery Office (SRO) has emerged as a strategic hub within the Ministry of Social Policy of Ukraine (MoSPFU), driving evidence-based reforms and improving sector coordination. Over the past year, the SRO achieved several milestones and provided legislative, analytical and project implementation support for Ukraine’s social reform agenda. It secured endorsement from the Ministry and established a dedicated physical presence, which has accelerated engagement with senior leadership and improved delivery timelines. Recruitment advanced significantly, with 15 national experts onboarded and additional specialists in Disability Inclusion and Digital Transformation joining the team. These experts now work across ten MoSPFU teams on priority reforms, including pension reform, social assistance system redesign, child and family protection, disability inclusion, and IDP reintegration. An initial Strategic Workplan was agreed with MoSP in April 2025, marking a critical milestone for cooperation in support of policy coherence. Alongside a new TOR, the Workplan is under revision with MoSPFU to reflect the strategic shifts of the new administration and improve ways of working.

Evidence generation has progressed at pace, with three major analytical products nearing completion—such as a microsimulation tool for social assistance investments and an assessment of Ukraine’s contributory insurance system—and five more in development, including disability system mapping and a baseline evaluation of social assistance and services. These outputs have informed priority reforms from assessment to legislative drafting, including pension reform and child and family policy laws. Disability reform has progressed through mapping and legal analysis in partnership with R2P and the World Bank. The SRO has also strengthened MoSPFU’s technical capacity by training civil servants on evidence tools, enabling data-driven decision-making. Progress has been made defining the scope of the national Social Service Strategy, completing consultations, and conducting a full-scale expenditure analysis of over 500,000 budget lines to identify funding gaps. Recommendations have been provided to improve the design of the Digital Case Management 2.0 system, with a substantial draft presented in December 2025. However, FCDO raised concerns about participatory approaches, technical quality, and donor engagement, and discussing risk mitigation measures and improved QA processes with UNICEF.

Coordination has strengthened through the launch of the Social Protection Sectoral Working Group (SWG) and its task forces, which have been recognized by the EU Commission as a model of good practice and a trailblazer for humanitarian-development cooperation. The SWG now convenes quarterly meetings and supports alignment between donors, implementers, and government priorities. Development of an online mapping tool is underway to improve transparency and gap analysis.
The SRO also co-designed a shock-responsive cash pilot to establish a government-led mechanism within MoSPFU for large-scale shock-responsive transfers through national systems, reducing reliance on parallel humanitarian systems and bolstering fiscal sustainability. The concept note was presented to FCDO and ECHO in June 2025, and after delays due to administrative changes, implementation is expected in Q1 2026. UNICEF and FCDO agreed to streamline the initial plan from two pilots to one.

Following the Ministry reshuffle, UNICEF successfully rebuilt relationships with the new administration, with the Minister publicly endorsing the SRO as a central mechanism for deploying experts under one coordinated structure. The SRO and MoSPFU have begun revising its structure, deepening cooperation, prioritizing capacity building, and agreeing on more targeted KPIs. However, despite these achievements the SRO is not yet fully operational as a delivery unit and gaps persist. Recruitment delays caused by UN-wide freezes, resource constraints, and ministerial changes have slowed progress. National staff recruitment is incomplete, restructuring negotiations continue, and clarity on roles and responsibilities is still evolving.

The next phase will focus on consolidating these gains and addressing these operational gaps. Priorities include finalizing the project management framework and governance architecture, completing recruitment, and developing standard operating procedures to ensure accountability and effective technical support. A dynamic workplan will be implemented, incorporating shared indicators, milestones, risk registers, and an agreed monitoring cadence. Additionally, a sustainable exit and transition plan for the SRO will be agreed with MoSPFU to secure long-term impact. Operationalizing the evidence pipeline, delivering priority analytical products, expanding the capacity building draw down mechanism for Ukrainian partners, and implementing the shock-responsive cash pilot in early 2026 will be critical. Strengthening communication, improving quality assurance processes, and deepening donor engagement will ensure the SRO evolves into a fully functional mechanism that drives evidence-based social reform and supports Ukraine’s recovery agenda.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

FCDO and UNICEF have agreed that it is more cost-effective to consolidate Output Indicator 1.7 by merging the two proposed pilots into a single streamlined pilot, scheduled to commence in Q1 2026. If successful, this pilot could be scaled up in line with FCDO’s commitment to system strengthening and accelerating the transition from humanitarian assistance to Ukrainian-led recovery. It was also agreed to pause development of the Social Service Strategy. This indicator is expected to be updated to reflect an integrated social assistance and social services strategy aligned with MoSPFU’s new approach. However, concerns raised during the first phase must be addressed to ensure effective delivery. Communication challenges have arisen, such as the SRO commissioning branding without prior FCDO approval and contrary to branding guidelines. While mitigation measures have been implemented, this highlights the need to formalise and standardise communication protocols to build on trust-based relations and ensure programme continuity. It is also recommended to bolster delivery capacity on both sides to reduce risks of miscommunication during personnel changes and rotations.

Output Title	Small scale service providers/civil society organisations are supported by small-scale grant mechanism
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1. Number of community-based social service providers that have benefitted from small scale grants to provide social services	35 (100 for programme lifespan)	Active outreach and robust methodology has resulted in 118 community-based social service providers with grant agreements (above milestone target of 35 and progamme lifespan target of 100). Of these, 88 providers are funded via SPIRIT, plus 30 through complementary funding catalysed by SPIRIT and allocated from UNICEF discretionary funds. In the first two weeks of service implementation, these 88 providers reached 1,086 unique beneficiaries across seven service types, with balanced regional distribution and no major gaps. / SCORE: A+ - moderately exceeded expectations
2. A National SGM Project Office based in the State Fund for Social Protection of Persons with Disabilities is operational and has strengthened the capacity of the Fund to serve as the Purchasing Agency for MoSP	The project office is operational	The National SGM Project Office was established within the Fund, with core staff hired and systems strengthened to position the Fund as a capable purchasing agency for MoSPFU. Financial and compliance foundations established to allow receipt of a Direct Cash Transfers finalized and approved, and the first tranche disbursed to fund effectively. / SCORE: A - met expectations
3.a) Number of new social services established at municipality level, in line with national priorities and community needs through small-scale grants mechanism	15 (30 for programme lifespan)	Exceeded expectations, introducing 137 new services at the community level against a target of 15 for milestone and 30 for programme lifespan. This includes introduction of both pre-existing services that are new to hromadas and a limited number of new service types that had been identified together with certain pre-existing services as the minimum package of services required for vulnerable children and families in Ukraine . / SCORE: A++, output substantially exceeded expectations
3.b) Number of available social services strengthened at municipality level, in line with national priorities, community needs through the small-scale grants mechanism	20	Initial data shows 35 social services have already been strengthened at municipal level with evidence to be provided on quality changes after monitoring conducted in future reporting. By end of programme lifespan, 120 providers will deliver 222 social services to around 30,000 citizens significantly exceeding initial targets. / SCORE: A+ - moderately exceeded expectations
3.c) Percentage of social services delivered through the small-scale grants mechanism that are gender responsive and disability inclusive	20 (60% over programme lifespan)	Minimum target of 20% met. As expected, uneven GESI capacity apparent among potential grantees with significant expertise and experience gaps across providers. In response, UNICEF with GESI experts developed methodological and educational materials for providers including development of a GESI checklist, guidance for grantees on strengthen practical application of gender and social inclusion principles during implementation, and an expanded focus on inclusion with a full training programme for grant recipients. As implementation progresses, predicted increases are expected to be identified during monitoring for next stage of reporting. / SCORE: A – met expectations
4.1 Better Care[9] projects, designed and implemented to strengthen gender responsive and disability inclusive child protection and social care systems in Ukraine and generate evidence for the Better Care Reform's further scaling up, have been implemented in accordance with the "Strategy for Ensuring the Right of Every Child in Ukraine to Grow up in a Family Environment," resulting in a number of Better Care pilot projects.	2 (4 across programme lifespan)	Significant progress was made and the milestone target of 2 projects has already been surpassed and met the programme lifespan target of 4 projects. These are: / Positive Parenting Support Programme / CSO Capacity Building and Partnership Formation / Mentorship Program / Interregional Exchange of Experience / The initiatives strengthen partnerships, build capacity, and promote inclusive, family-based care models in line with the National Strategy. / SCORE: A+ – moderately exceeded expectations
[9] ‘Better Care’ is the deinstiutionalisation and care reform agenda in Ukraine.

Briefly describe the output’s activities and provide supporting narrative for the score.

The Small Grants Mechanism (SGM) moved from concept to full operationalization during the review period, exceeding expectations in scale and scope and laying the foundation for a sustainable model of local social service procurement. Despite administrative delays and capacity gaps requiring adaptive management, the SGM is delivering tangible benefits to vulnerable populations while strengthening Ukraine’s institutional capacity for long-term reform. Originally planned to reach 100 grantees over two years, the SGM has already secured 118 agreements across 10 regions—surpassing the milestone target of 35—with 88 providers funded through SPIRIT and 30 through UNICEF. These providers will deliver 222 social services to approximately 30,000 citizens, including 137 new services (against a target of 15 at Annual Review and 30 over the programme) alongside 90 existing services. First tranches have been disbursed, and service delivery is underway.

Initial targets were conservative due to the limited availability of providers, but strong outreach, simultaneous regional launches, and political prioritization of resilience services drove higher-than-expected engagement. of pilot was designed with limited evidence at the outset. Emerging data now demonstrates significant untapped potential, confirming that the operating environment offers far greater scope than originally projected. Over 900 hromadas expressed interest, generating 262 community applications and 228 provider applications from 160 communities. Demand focused on services for families in crisis, early intervention, and orphan care. A proactive information campaign reached over 10,000 stakeholders through national media, civil society platforms, and a dedicated landing page, with 1,500 participants in sessions, 5,784 enrolled in an online course, and 3,000 reached by field teams.

Governance structures were established, including onboarding the Administrator (ISAR Ednannia), forming an inter-sectoral working group, and launching a Steering Committee with government and civil society representation. The National SGM Project Office was operationalized within the Fund, supported by financial, IT, and regulatory frameworks, including Cabinet Resolution No. 40 and compliance with UNICEF’s HACT standards. The first tranche of funds was successfully disbursed following approval of KPIs and budget.

Applications reflected strong alignment with national reform priorities, and resource savings combined with UNICEF’s additional funding enabled support for 120 applicants instead of 100. Providers are initiating activities at an even pace nationwide, with balanced distribution across regions and service types. Additional measures—such as vehicle procurement, branded materials, and orientation sessions—are expanding coverage and visibility. These achievements position the SGM as a cornerstone for scaling social services and advancing Ukraine’s social protection reform agenda.

A multi-tiered monitoring system was launched, combining baseline studies, alignment of Administrator and Fund frameworks, methodological guidance for NSSU, and adaptation of the “Say it like it is” hotline for Accountability to Affected Populations (AAP). The system integrates monitoring visits, third-party reviews, and UNICEF programmatic checks, but routine assessment will be needed to ensure compliance and service quality without overburdening providers. Early monitoring has already enabled adaptive management—for example, rapid deployment of early intervention specialists to address gaps in provider expertise.

Of the 222 services funded, a significant share supports people with disabilities, including early intervention, day care, and inclusive education, alongside respite care for parents in six communities. These services reduce caregiving burdens—particularly for women—and enable greater social and economic participation. Gender Equality and Social Inclusion (GESI) principles were systematically embedded across all frameworks, agreements, and tools, supported by a dedicated GESI expert. Outreach targeted organizations representing women, children, and persons with disabilities, and all materials were developed in accessible formats. Tailored training and guidance were provided to address uneven GESI capacity among grantees, supported by a roster of experts and pre-designed monitoring templates for gender- and vulnerability-disaggregated reporting. UNICEF and partners also completed safeguarding and PSEA training, strengthening institutional capacity.

Challenges in this first phase included building a shared vision among stakeholders with overlapping mandates, lack of specific regulations, and limited capacity of local authorities to conduct accurate needs assessments. Delays in staff recruitment and system procurement, VAT ineligibility, and administrative burdens required adaptive contracting and flexible grant mechanisms. Despite these hurdles, UNICEF and partners established a robust institutional and financial framework, enabling FCDO to pilot Direct Cash Transfers as a modality for government system support. Provider selection exceeded expectations, and UNICEF successfully leveraged additional funding from BMZ/KfW to expand training and cover extra grants—demonstrating strong donor confidence and positioning the programme for scale.

Better Care

Through SPIRIT, UNICEF has provided technical support to the Coordination Center for Family Upbringing and Childcare Development to advance the Government of Ukraine’s “Better Care” reform agenda in pilot regions. This component represents FCDO’s flagship initiative under the Global Campaign on Deinstitutionalisation and Care Reform, which SPIRIT helped shape and secured endorsement from Olena Zelenska. Following approval of the National Strategy on Child Protection and Family Upbringing, Regional State Administrations (RSAs) began developing Regional Action Plans (RAPs) with active support from UNICEF and the Coordination Center. Inclusive planning was prioritized through consultations with civil society and community stakeholders across nine pilot regions, engaging 370 participants early in 2025. By September, 24 RSAs had officially approved RAPs, demonstrating strong institutional commitment and laying the foundation for evidence-based pilot projects to inform national scale-up.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Several adjustments were introduced during the year to strengthen delivery. First, the importance of timely documentation of decisions became clear after informal agreements led to uncertainty during operational phases. A structured process for recording decisions, milestones, and shared action points has now been implemented to ensure continuity and accountability. Second, gaps in technical and legislative expertise highlighted the need for a standing roster of specialists to respond quickly to emerging issues. This proactive approach will reduce delays and strengthen policy engagement.

Early feedback also revealed limited understanding of gender and disability inclusion among local actors. Training materials were revised to include practical examples and case studies, and dedicated sessions were added to onboarding webinars. Ongoing technical support for inclusive service delivery will continue in the next phase. Additionally, uneven capacity among hromadas to justify and procure social services underscored the need for accessible methodological guidance and a community of practice for implementers.

Finally, balancing the programme’s focus on civil society with government priorities emerged as critical for sustainability. While the SGM was designed to strengthen CSOs, UNICEF mobilized an additional US$600,000 to extend support to public and private providers, creating a more inclusive provider landscape. Moving forward, greater support for local authorities—particularly frontline hromadas—will be prioritized to strengthen needs assessment, budgeting, and regulatory navigation. Flexible funding strategies and early alignment with government priorities will maximize coverage and value for money, while partnerships with humanitarian actors will help transition protection service providers into the national system.

## C. DETAILED OUTPUT SCORING

Output Title	World Bank Partnership supports the development of more inclusive, effective and efficient cross-sectoral systems and services focusing on vulnerable groups
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of policies and procedures with enhanced citizen engagements are implemented	0	N/A - September 2026 Target – 1
5.2 Number of assessments of Healthcare needs of veterans and their families prepared and disseminated	0	N/A - September 2026 Target – 1
5.3 Draft bill for a more equitable and financially sustainable pension system is prepared and submitted to the GOU.	0	N/A - September 2026 Target - 1
5.4 Enhanced coverage and access to adequate social assistance and services for low-income and vulnerable families	Number of families benefiting from the GMI programme: 227,000.00 / Number of people benefiting from social services financed from the state budget: 2,000.00	Number of families benefiting from the GMI program Milestone 1 (Sep 2025) Actual: 227,118 / Number of people benefiting from social services financed from state budget. Milestone 1 (Sep 2025) Actual: N/A as the national data is not available yet and will be provided in the next reporting period. / SCORE B – Output moderately did not meet expectations (noting that (noting that first indicator met expectations and second indicator delayed due to data availability)
5.5 Number of key analytical assessments and policy recommendations completed to enhance employment services for vulnerable groups	0	N/A - September 2026 Target - 1
5.6 Number of key stakeholders with enhanced understanding of ECPE implementation and inclusive educations, Opportunities, Challenges, and Actionable Steps to Improve Access for Marginalized Populations and FLFP	20	Milestone of 20 (Sep 2025) and 100 (Sep 2026) surpassed at 140 stakeholders reached. / SCORE A++ - Substantially exceeded expectations
5.7 A framework paper and a report summarizing the distributional analysis of the new social sustainability model	0	N/A September 2026 Target – 1

Briefly describe the output’s activities and provide supporting narrative for the score.

Under the Ukraine Recovery Trust Fund framework, only SPIRIT logframe indicators on social assistance and education were formally assessed. However, the World Bank provided FCDO with a supplementary logframe and detailed progress review, showing strong catalytic impacts despite some delays. Key achievements include laying the foundation for the $200 million Together Ukraine Project, securing $30 million additional financing for ECPE, triggering the UK-backed SPIRIT operation, and advancing policy reforms on pensions, social assistance, disability inclusion, and human capital development. FCDO recommends streamlining activities to focus on depth over breadth, prioritizing social protection, inclusion, and human capital aligned with SPIRIT and BE Kyiv objectives.

SPIRIT catalysing a new reform-oriented £500 million investment operation for Ukraine

SPIRIT has been pivotal in positioning Ukraine for large-scale investment in social protection. Through technical assistance, policy development, and piloting key reforms, the programme demonstrated Ukraine’s readiness and built donor confidence, enabling the UK guarantee and paving the way for the new £500 million World Bank-financed Investment Project Financing (IPF) operation.

This four-year IPF will build on SPIRIT’s foundations to deliver inclusive, resilient social protection systems for over 1 million vulnerable Ukrainians, including low-income households, families with children, older persons, and people with disabilities. It will enhance efficiency, accessibility, and quality of social assistance and services, while modernizing disability support in line with WHO standards.

SPIRIT’s multi-partner structure—combining UK FCDO financing and World Bank expertise—created a platform for coordinated donor engagement, critical to structuring the UK guarantee. Its achievements underpin IPF components: scaling the BSA programme, improving targeting and case management, expanding community-based services with NGO/private sector engagement, and transitioning disability support to the ICF model with assistive technologies. The use of Performance-Based Conditions ensures accountability and reinforces donor confidence in Ukraine’s reform trajectory.

Annual Review Indicators:

Social Assistance (Indicator 5.4)
Work toward introducing the Basic Social Assistance (BSA) program is progressing, with draft legislation and a strategic integration paper expected by December 2025. Next steps include detailed policy dialogue on BSA design, linking benefits to labor market policies and social services, and ensuring coherence with pension reform to avoid unintended incentives. Efforts remain focused on improving coordination, expanding coverage, modernizing financing, and transforming care systems for vulnerable groups.

Early Childhood and Pre-School Education (Indicator 5.6)
Analysis of ECPE implementation is underway, with recommendations due by March 2026. SPIRIT supported consultations on eNursery and eSadok voucher programs and provided feedback on the ECPE Strategic Framework. Challenges include shortages of specialists, fragmented service quality, and lack of standardized diagnostic tools. In response, SPIRIT refocused deliverables to strengthen inclusive pedagogy and facilitated consultations with over 140 stakeholders. These efforts catalyzed $30 million in additional financing for ECPE reforms, ensuring alignment between SPIRIT-supported analysis and upcoming World Bank operations.

Please note the following summary of additional progress of World Bank activities under SPIRIT is based on supplementary logframe progress provided on an informal and voluntary basis and therefore cannot be assessed under the Annual Review evaluation period:

Inclusive Recovery Theme

Under this theme, two workstreams advanced Ukraine’s recovery agenda: citizen engagement and regional development, and veteran reintegration.

The citizen engagement and regional development workstream advanced the design of the US$200 million Together Ukraine Project, completing a review of policy, legislation, and relevant EU acquis. Preparations are underway for a pilot to embed scalable participation and accountability mechanisms into local recovery planning and the DREAM system. A readiness assessment methodology for hromadas has been developed, with implementation scheduled for November 2025 and final reporting by July 2026. In parallel, the methodology for investment selection under the State Fund for Regional Development was refined to include citizen engagement screening, and Terms of Reference for thematic workshops with hromadas have been prepared, pending endorsement by the Ministry for Development of Communities and Territories.

Veteran reintegration progressed despite leadership changes at the Ministry of Veterans Affairs, with a new technical assistance plan agreed in September 2025. Activities through June 2026 include strengthening Veteran Support Specialists via e-learning and training, assessing veteran entrepreneurship programs, preparing operational manuals, and enhancing training modules. Preparatory work is also underway for a comprehensive health needs assessment of veterans and families, covering mental health, rehabilitation, and service gaps, to guide integration of tailored services into existing systems aligned with universal health coverage principles.

Social Protection and Labour

SPIRIT strengthened transparency and donor coordination in employment policy, convening a Vienna meeting that established a structured coordination group with partners such as ILO, GIZ, TBI, and Helvetas. This unified approach provided the Ministry of Economy with a clear picture of ongoing engagements. Key activities included assessing State Employment Service procedures for vulnerable unemployed groups, reviewing legislation for work-ability assessments, and preparing a qualitative study on employer barriers to hiring persons with disabilities and veterans. The team also produced an analytical note and video on barriers to female employment, showcased at the June 2025 Ukrainian Women in War conference, informing World Bank operations and IFC’s Women Rebuild Ukraine initiative. Further progress was made on active labour market programs, including extending the SkilLab job platform pilot and completing its impact evaluation. Work on SES digital readiness continues, with an in-depth IT assessment guiding development of client-centered platforms, a roadmap for a Labor Market Information System, and policy dialogue on a digital occupational classifier in partnership with EBRD.

The World Bank partnership is advancing a comprehensive agenda to prepare Ukraine’s social safety net for the introduction of the Basic Social Assistance (BSA) program. This includes developing recommendations for integrating existing benefits, evaluating pilots, and drafting legislation informed by international best practices. A strategic paper on social safety net integration is expected in December 2025, while draft BSA legislation—drawing on Italy’s experience of linking beneficiaries to services—is anticipated in November 2025. In parallel, work on social services, in partnership with UNICEF, aims to create a modern, efficient, and client-centred system that promotes community-based delivery and addresses individual needs. Activities include assessing social benefits and services to improve and digitize processes, refining the financing model for social services, supporting implementation of the new Social Services Strategy, and resetting the long-term care system. Two pilots—resilience centres and output-based payments for IDP social services using a “money follows the person” approach—are being assessed, with results expected by March 2026 to inform national scale-up. The next phase will involve detailed policy dialogue on BSA design and establishing links between BSA, active labour market policies, and social service provision.

Disability Inclusive Social Protection

Significant progress has been made toward a roadmap for multi-sectoral and cross-ministerial disability assessment and delivery of benefits and services. The World Bank has completed an advanced analysis of healthcare business processes, including disability assessments for adults, children, and defenders, as well as support provided through multidisciplinary rehabilitation commissions. A parallel review of social sector processes is underway with UNICEF and Rights to Protection, covering both the legal framework and actual practices. Once finalized, these reviews will form the basis of the roadmap. Additional work includes a rapid assessment of the assistive technology ecosystem through workshops, provider visits, and interviews with service users, complemented by ongoing data analysis using administrative records from the Fund for Social Protection of Persons with Disabilities. A comprehensive assessment of the social protection system for persons with disabilities has begun, supported by an analytical framework comparing EU benefit systems. This framework will guide a meta-analysis of European countries and later be applied to Ukraine’s system. Policy dialogue on disability and needs assessment reform is ongoing, informed by international best practices such as WHODAS and Lithuania’s model. The team is also developing the concept for independent assistive technology services, defining service types, financing mechanisms, and implementation steps.

Pensions

Pension reform efforts aim to create a transparent system with clear wage-benefit links, rationalize special pensions, improve adequacy, and ensure capacity to accommodate war-related benefits. Activities to date have focused on intensive policy dialogue supported by quantitative analysis and projections, stakeholder engagement, and coordination with technical advisors. The World Bank is providing legal assistance to address ongoing court cases and conducting due diligence on emerging policy ideas to prevent future litigation. Consultants are advising the Ministry of Social Policy on a communications strategy for this complex reform. Legislation is expected by mid-2026, with implementation beginning in 2027. A pension reform conference will be organized to build a shared vision among stakeholders and agree on a detailed implementation plan, with the aspiration that the government appoints a reform plenipotentiary empowered to deliver.

Monitoring Evolving Living Conditions

A new round of the Listening to Ukraine Survey was conducted between July and September 2025. Preparatory work included refreshing the sample and updating the questionnaire with revised migration and activity modules, as well as new modules on self-employment, willingness to work as self-employed, and social norms. A SPIRIT-specific module was introduced to measure aspects of social cohesion such as trust, engagement with local governments, perceptions of corruption, and government performance, along with questions on vulnerable groups including IDPs and veterans. This module was randomly assigned to one-third of the sample each month. Under this pillar, the World Bank identified new priority areas to address the social agenda amid rising fiscal pressures. Preparations are underway for a Social Public Expenditure Review to assess social programs delivered by multiple ministries, identify opportunities to improve effectiveness, reduce fragmentation, and find potential savings. A poverty update based on analysis of new quarterly survey data is also in preparation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While World Bank Global Practices working on SPIRIT have largely adhered to the results and activities identified at programme initiation, several adaptations were made in response to contextual shifts and lessons learned, as agreed with FCDO. These changes ranged from updating terminology in deliverables to reflect correct product names, adjusting delivery timelines, and introducing new activities to address emerging needs and priorities, including engagement with additional donors and partners. In consultation with the SPIRIT FCDO team, resources were rebalanced across thematic areas to respond to government requests and World Bank country management priorities. For example, when the Ministry of Social Policy requested a Social Expenditure Review, this was added to take stock of all social programs across government. Resources for this task were secured by focusing Theme 5 on its core deliverable—the Listening to Ukraine Survey—and supplementing activities with financing from other sources.

Looking ahead, SPIRIT will scale back some thematic areas (e.g., education, inclusive recovery) to allow greater depth of focus on targeted priorities around social protection, social inclusion, and inclusive growth. A fully updated logframe reflecting these adjustments will be co-created with FCDO in Q1 2026.

## D: VALUE FOR MONEY (1 page)

The SPIRIT programme continues to deliver exceptional Value for Money, surpassing the original Business Case proposition. Operating in a complex, high-risk environment, SPIRIT demonstrates that strategic design, adaptive delivery, and strong partnerships can achieve systemic impact at scale while maintaining cost efficiency, equity, and accountability.
Economy – Leveraging Systems and Reducing Costs

SPIRIT’s economic performance is driven by its ability to maximize impact while minimizing duplication and overheads. By partnering with UNICEF and the World Bank, the programme avoided costly parallel structures and leveraged existing systems and expertise. This approach generated significant savings, including approximately £1 million through VAT exemptions and optimized procurement processes.

The Social Recovery Office (SRO) exemplifies this principle. Instead of hiring all 110 consultants initially requested by the Ministry, UNICEF conducted a needs analysis and prioritized 15 key roles, with 99% filled by national experts. This reduced costs, ensured contextual knowledge, and strengthened sustainability. Additional technical needs were met through short-term research assignments, avoiding unnecessary overhead.

World Bank procurement standards further reinforce VfM through competitive selection, standardized documentation, and rigorous oversight, ensuring transparency and reducing life-cycle costs.

Efficiency – Delivering More with Less

Efficiency has been a defining feature of SPIRIT. Centralized coordination through the SRO and structured platforms such as the Social Protection Sectoral Working Group (SWG) have reduced transaction costs and accelerated implementation timelines. The SWG now coordinates technical assistance valued at USD 404 million over a decade, ensuring strategic alignment and avoiding duplication.

The Small Grants Mechanism (SGM) illustrates SPIRIT’s ability to scale rapidly and efficiently. Originally targeting 100 communities, the programme reached 261 communities and 228 providers, each delivering an average of 2.3 services—more than double expectations. This was achieved through early intervention, streamlined grant agreements and built-in assurance mechanisms.

The Cash Pilot for Frontline Areas further demonstrates efficiency, integrating humanitarian, development, and government funding streams to avoid parallel systems. Its projected Total Cost Transfer Ratio of 83% reflects a highly efficient model for delivering assistance.

Effectiveness – Catalysing Systemic Reform

SPIRIT’s effectiveness lies in its ability to translate technical assistance into systemic change. The SRO strengthens evidence-based policymaking, while the SWG aligns priorities across ministries and donors. Evidence products such as microsimulation tools and disability mapping inform policy decisions, enabling reforms that are inclusive and sustainable.

The programme has already catalysed or laid the foundation for major investments:
- $30 million for inclusive education
- $200 million for the Together Ukraine programme
- £500 million for a new social protection instrument backed by UK loan guarantees

These outcomes underscore SPIRIT’s role as a platform for reform and investment, amplifying the impact of relatively modest inputs.

Equity – Inclusion at the Core

Equity remains central to SPIRIT’s design and delivery. Gender equality, child rights, and disability inclusion are embedded across all components. The SGM is funding 120 providers to deliver 222 social services, many focused on children with disabilities and vulnerable families—far exceeding the original target of 35. Monitoring frameworks include sex- and disability-disaggregated indicators, ensuring reforms promote fairness and inclusivity. World Bank activities complement this approach, integrating gender and disability considerations into policy design and piloting inclusive education and labour market reforms.

Cost-Effectiveness – High Returns on Strategic Investment

SPIRIT exemplifies the high-risk, high-reward proposition envisioned in its Business Case. Pension reform alone could generate USD 2.4 billion in savings by 2060, alongside efficiency gains from early retirement adjustments and streamlined entitlements. These fiscal benefits are complemented by catalytic impact: SPIRIT has mobilized additional donor investments and positioned Ukraine to access large-scale financing for social reform.

Assessment Against VfM Criteria

- Economy: Met – Leveraging systems and VAT savings
- Efficiency: Exceeded – Higher-than-expected uptake and service delivery
- Effectiveness: Exceeded – Strong systemic impact and investment leverage
- Equity: Exceeded – Deepened commitment to inclusion and rights-based approaches
- Cost-Effectiveness: Met – High return potential and catalytic impact

In summary, early indications suggest SPIRIT delivers strong VfM by combining strategic partnerships, adaptive delivery, and inclusive design. If delivered effectively, interventions should meet immediate objectives while laying the foundation for long-term systemic reform, ensuring sustainability and impact well beyond the programme’s lifespan. Programme interventions will continue to assess VfM on a regular and case-by-case basis to ensure principles are adhered to across the programme.

E: RISK [½ to 1 page]

Overview of Risk Management

SPIRIT was designed as a high-risk, high-reward programme, operating in a country at war and within a sector undergoing profound structural reform. Over its first year, this proposition has been tested by political volatility, operational bottlenecks, and reputational sensitivities. Despite these challenges, the programme has remained within FCDO’s risk appetite, with residual risk assessed as moderate. This reflects not an absence of shocks, but SPIRIT’s ability to adapt rapidly and maintain strategic alignment with Ukraine’s EU accession agenda.

The operating environment remains unstable, and several risks identified in the Business Case have materialised alongside new ones. Through proactive mitigation and adaptive delivery, SPIRIT has continued to progress against its objectives. Risk monitoring has been systematic and collaborative. UNICEF initially provided monthly updates, later streamlined to align with AMP risk register reviews, reducing administrative burden while maintaining quality. Emerging threats were addressed promptly in weekly technical meetings. The World Bank exceeded its annual reporting requirement by providing a mid-year update and supplementary progress report, alongside active participation in weekly technical discussions and rapid escalation of risks. The SPIRIT Board has remained an effective forum for addressing high-level risks and agreeing on decisive actions.

Key Risks and Mitigation Measures

Political turbulence and institutional resilience have been among the most significant challenges. The merger of the Ministry of Social Policy with the Ministry of Unity and the appointment of a new leadership team posed a major risk to reform continuity. SPIRIT’s adaptive design and strong diplomatic engagement ensured momentum, with previously agreed priorities largely preserved. However, volatility and personnel changes continue to threaten centralised relationships. To mitigate this, the programme has prioritised early engagement with new leadership, embedded priorities in the Ukraine Facility Plan, strengthened multi-level relationships across ministries, and documented decisions and milestones to safeguard institutional memory.

Internal capacity and resource constraints have also affected delivery. Recruitment delays, UNICEF restructuring, and rigid contracting slowed progress, reducing agreed resources including the Head of SRO role. While milestones were met through resequencing and resource reallocation, gaps in senior leadership and knowledge management remain critical. SPIRIT’s success has relied on intensive development diplomacy to convene actors and catalyse reforms at scale. Mitigation measures include maintaining implementer flexibility through adaptive contracting, appointing a national Head of Reform Office for day-to-day delivery, securing full-time leadership for the SRO, and exploring options to backstop capacity through resource reallocation, additional hires, or adjusting programme ambition.

The transition from relational to systemic approaches presents another risk. Strong, trust-based relationships have enabled partners to go beyond standard donor-implementer norms, such as the World Bank ring-fencing funds and UNICEF co-creating TORs. However, reliance on informal goodwill makes this approach vulnerable to personnel changes. To address this, SPIRIT is formalising governance structures, codifying protocols, implementing a shared portfolio repository, and broadening engagement to reduce single points of failure.

Local authority capacity and readiness remain a concern. Initial SGM prioritisation exposed significant gaps among municipalities in regulatory frameworks, budgeting, and service oversight. Without systemic support, sustainability is at risk. SPIRIT has responded by delivering targeted training and guidance to local authorities, expanding support to communities for ownership of reforms, introducing stricter templates and standardised methodologies, and exploring digital tools to streamline procurement and monitoring.

Political economy and reputational exposure also require careful management. Reforms to pensions and benefit consolidation remain politically sensitive and risk backlash if poorly communicated. SPIRIT is mitigating this through development of a strategic communications plan with MoSPFU and continued deployment of development diplomacy to maintain consensus and a rights-based approach.

Sustainability and Responsible Exit Planning

Ensuring sustainability is critical to mitigate harm for vulnerable beneficiaries and deliver value for money for UK taxpayers. SPIRIT is developing a sustainability strategy within the SRO Project Management Framework, including a phased integration plan and clear indicators of institutional ownership such as budget allocations and staffing commitments. The programme is strengthening local authority capacity to ensure continuity of services and a responsible exit from SGM support, empowering local actors to implement and drive reform. Completion of the Project Appraisal Document for the new World Bank lending instrument will ensure that investment components scale modalities piloted through SPIRIT and avoid introducing interventions that could fragment an already fragile landscape.

Financial Discipline and Safeguarding Assurance

Fiduciary risk remains moderate and within appetite. UNICEF and the World Bank maintain robust financial controls, and ISAR’s due diligence of grantees has been proportionate to grant size. No misuse of funds was reported during the period. The main friction lies in quarterly disbursement cycles and administrative constraints, which occasionally delay payments to the Fund. Mitigation includes tighter forecasting and partial post-payment buffers. SPIRIT will engage in the Embassy’s Financial Risk Assessment currently underway.

Safeguarding measures are embedded in delivery. All Small-Scale Grant agreements include a child safeguarding clause and refund mechanism for violations. Fund and Project Office staff have completed training on Protection from Sexual Exploitation and Abuse, and safeguarding Training of Trainers has been delivered. CSO onboarding is being rolled out. An Accountability to Affected Populations feedback hotline and a joint monitoring model with the National Social Service Agency are in place to capture and escalate concerns. No safeguarding issues were flagged during the reporting period.

Equalities

SPIRIT is committed to a rights-based approach, embedding principles of equality, non-discrimination, and participation across all components. It combines targeted interventions for marginalised groups with mainstreaming inclusion throughout reforms. Key priorities include gender equality, child rights, and disability inclusion, addressed through projects on childcare and early intervention reforms, accessible social assistance and service provision, GBV policy strengthening, assistive technology, inclusive employment, and deinstitutionalisation efforts. While progress on embedding expertise within MoSPFU has been slow, the Small Grants Mechanism has already met gender and disability targets and expectations of GESI-sensitive design and delivery. UNICEF has adapted its reporting to meet HMG’s disaggregation requirements, providing data by age, sex, disability, and geography where applicable. The World Bank does not apply disaggregation due to the nature of its deliverables but provides thematic equalities reporting.

Climate Considerations

Climate risk remains low, and digitalisation of case management is expected to reduce the carbon footprint of service delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Commercial performance

In line with the approved Business Case, FCDO proceeded with direct contracting of UNICEF and the World Bank to deliver the three pillars of SPIRIT. Where additional support was required, partners conducted tenders for contractors in accordance with their procurement policies. Grantees under the Small Grants Mechanism were selected competitively by a multi-stakeholder Selection Committee comprising representatives from the Fund for Social Protection of Persons with Disabilities, UNICEF, FCDO, the Coordination Centre for Families and Children, and civil society. This process ensured transparency and that the best value for money was achieved for FCDO throughout procurement and grant allocation.

Financial Performance

Agreements with partners were signed within two months of Business Case approval, enabling swift commencement of implementation. While some delays occurred due to requests from the Ministry of Social Policy to adjust activities and ensure ownership, overall financial performance has remained close to planned allocations across two financial years.

Programme spend	Planned		Actual
	FY 24/25	FY 25/26	FY 24/25	FY 25/26 (Q1-3)
UNICEF	£4 mln.	£5.5 mln.	£1.2 mln.	£14.8 mln.
World Bank	£1.3 mln.	£2 mln.	£4.1 mln.	£0 mln.
Administration and Scoping budget (including operational pilots)	£0.1 mln.	£0.3 mln.	£4.5K	£0.03 mln.
Total	£5.4 mln.	£13.3 mln.	£5.3 mln.	£14.83 mln. *

* may need to be adjusted at the end of the financial year, pending the receipt of reports.

Budget amendments have been managed to maximise programme impact. For example, UNICEF requested a reallocation of funds saved from a temporary hiring freeze, enabling £2.1m to be redirected to the pilot budget line. This allowed the development of a substantial shock-responsive cash assistance initiative while UNICEF guaranteed sufficient capacity to deliver planned activities and outputs. However, delays linked to SRO recruitment indicate that further capacity strengthening by UNICEF will be required.

Reporting and Assurance

Reporting arrangements have remained consistent with Business Case commitments. UNICEF provided quarterly reports, while the World Bank submitted a six-month update and, on a voluntary basis, a detailed supplementary report in addition to URTF reporting for the Annual Review. Reporting quality has been high, offering clear progress updates and coverage of cross-cutting themes. UNICEF reports follow ISF formats, providing detailed indicator-level data, while World Bank reporting focuses on progress against the supplementary logframe developed specifically for SPIRIT. This tailored reporting is not standard for World Bank trust fund mechanisms and reflects the success of SPIRIT’s development diplomacy approach, secured through letters of assurance.

These reports have provided a robust evidence base for assessing delivery performance. Overall, programme delivery is rated as good. Most milestones have been achieved, and while some activities experienced delays due to risk realisation, mitigation measures are in place. Partners and MoSPFU have demonstrated strong willingness to collaborate, ensuring that risks do not significantly impact SPIRIT’s trajectory.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring

Throughout the review period, the Programme team maintained close and consistent engagement with implementing partners, combining day-to-day interaction with planned check-ins at least every fortnight. These updates covered progress against key milestones, financial performance, summaries of recent activities, and emerging risks. In December 2024, the team convened consultations with representatives from the Ministry of Social Policy, other ministries, UN agencies, and civil society to ensure technical feedback was incorporated into early-stage programme design and delivery.

A major milestone in the first year was the inaugural SPIRIT Strategy Board meeting, which brought together FCDO, UNICEF, the World Bank, and the Government of Ukraine to provide joint strategic oversight and leadership. Guided by an agreed Terms of Reference, the Board serves as a high-level platform for coordination, decision-making, and collective accountability. It enables structured discussions on implementation progress, challenges encountered, proposed solutions, and agreement on next steps.

To strengthen monitoring and reporting, the Programme team worked with partners to develop tailored logframes and reporting templates. Notably, the World Bank introduced a supplementary logframe for its country office, alongside semi-annual updates and an annual reporting format, offering a more detailed and results-oriented framework than standard URTF reporting. These monitoring activities—structured engagement, strategic oversight, and customised reporting tools—have directly informed programming decisions by identifying implementation challenges early, aligning efforts across stakeholders, and sharpening the focus on measurable outcomes.

Annual Review

This Annual Review marks the first formal assessment of SPIRIT and has adopted a light-touch approach. The process began with clear definition of objectives, roles, responsibilities, and timelines. Evidence was gathered through interviews with stakeholders and beneficiaries, including implementing partners, representatives of MoSPFU, the Fund for Social Protection of Persons with Disabilities, and ISAR Ednannya (SGM Administrator). Insights from these interviews were triangulated with lessons and data provided in partner reporting to ensure a comprehensive and balanced assessment.

Learning and Adaptation

One of SPIRIT’s defining strengths has been its ability to adapt programming to Ukraine’s rapidly changing context. In a system characterised by frequent ministerial changes and shifting priorities, the programme has remained flexible and responsive, adjusting to evolving government requests while safeguarding alignment with SPIRIT’s overarching objectives. This adaptability has been critical for maintaining relevance and continuity, particularly for SRO work and World Bank activities that generate evidence for reforms and pilot innovative approaches.

Flexibility was exemplified in the agreement between FCDO and the World Bank that overall outcomes under the supplementary logframe would remain unchanged, while deliverables and outputs could vary in response to ministerial priorities and contextual analysis. This approach proved vital during the review period. For instance, instead of producing a broad report, the programme delivered a targeted Social Expenditure Review at the government’s request.

Similarly, new priorities emerged around the second pillar of the pension system and disability support within the education sector. FCDO’s responsiveness enabled the World Bank to act swiftly, reinforcing relationships with new ministers and sustaining momentum in a volatile environment.

Adaptation was equally evident in UNICEF’s implementation of the Small Grants Mechanism. Initially designed to strengthen CSOs as primary service providers, the mechanism was adjusted when MoSP prioritised a more inclusive approach that also developed public and private providers. UNICEF mobilised an additional $600,000 from complementary funding to broaden coverage without losing focus on civil society. The key lesson is the importance of flexible funding strategies and early alignment with government priorities to maximise responsiveness, coverage, and value for money.

Further flexibility was required to manage regulatory sequencing risks. Since the SGM launch depended on an official Resolution subject to political dynamics, the Programme Administrator aligned planning with the Resolution’s timelines rather than the project cycle, reducing the risk of wasted effort and ensuring compliance with evolving requirements.

Learning was actively embedded into delivery through targeted sessions, feedback loops, and adaptive training. FCDO conducted a GESI session with UNICEF to strengthen understanding of gender and social inclusion principles, complemented by UNICEF’s learning sessions for grantees on service provision and ISAR’s webinars on operational procedures and reporting.

Capacity-building extended to NGOs on compliance with national social service standards and to municipalities on budgeting and financial management. Feedback revealed gaps in applying gender-responsive and disability-inclusive principles, prompting adaptation of training materials with practical examples, case studies, and step-by-step guidance, alongside dedicated onboarding sessions and ongoing technical support.

Date of last narrative financial report	25 Sep 2025	Date of last audited annual statement	Statement as for 31 Dec 2024 provided on the 30 Jun 2025