## Logical Framework
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | SUPPORT FOR THE CDEMA EMERGENCY RESPONSE TEAMS
IMPACT | Impact Indicator 1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
Timely restoration of critical systems, services and quality of life in Participating States of CDEMA severely impacted by hazard events to save lives, reduce suffering and protect dignity of those in humanitarian crises |  | Planned | Estimated as 50% based on experiences of past events though there is significant variation by country and by type of services | At least 60% based on total number of service units |  | Humanitarian partners (national, regional and international) have necessary information and resources to make quick, effective and efficient decisions respond to needs of the affected population including the most vulnerable. Affected countries are able to provide information on total service units pre-impact.
| Percentage of essential services (power, water, health and waste management) fully operational 28 days after a major impact | Achieved |  | Power: Number of electricity distribution zones, substations, or households served. Water: Number of water supply zones or households connected. Health: Total number of hospitals and clinics in the affected area. Waste Management: Number of neighborhoods, wards, or collection routes.
Source
OUTCOME 1 | Outcome Indicator 1 |  | Baseline April 2025 | Target March 2026 |  | a) Adequate provisions for accommodation and transportation to enable the teams to be able to effectively carry out their functions b) Available accommodation and logistic support for response teams to carry out their tasks. c) Effective systems for relief tracking and feedback. `
The Regional Response Mechanism (RRM) support addresses key national disaster management gaps and boosts the immediate humanitarian effort to the CDEMA Participating States most severely impacted by hazards | Level of satisfaction with the response support provided by CDEMA of the National Disaster Management Offices/Authorities (NDMOs) and beneficiaries emergency surge teams | Planned | 50% | At least 75% satisfaction
Achieved
Source
Real time / After action rapid reviews and beneficiary feedback systems
| Outcome Indicator 2 |  | Baseline April 2025 | Target March 2026
| Percentage of requested surge teams provided to impacted states | Planned | (100% of surge teams requested by the government of the impacted state)-In total 11 teams deployed for Hurricane Beryl in 2024 to SVG and Grenada ( 6 with UK support). These deployments reflect fully addressed requests of the impacted countries. | 60% (based on request from government and available funds)
Achieved
Source
Real time / After action rapid reviews and beneficiary feedback systems
| Outcome Indicator 3 |  | Baseline | Target December 2019 | Target December 2020
| Outcome Indicator 3 |  | Baseline April 2025 | Target March 2026
| Number of gaps/weaknesses identified through Real time/After Action reviews addressed / mitigated in a timely manner | Planned | Following the 2022 and 2024 after action reviews - the main changes made were: updates to emergency plans and procedures to address multi-island and multi-state impacts necessitating cross-border coordination; and advancement of the CDEMA Logistics Programme to address growing complexities in emergency logistics and supply chain disruptions | 2 Issues (identified weakness in the RRM) addressed within 6 months of a Comprehensive Regional After Action Review
Achieved
Source
Real time / After action rapid reviews and beneficiary feedback systems
INPUTS (£) | UKFCDO (£) |  | Govt (£) |  | UKFCDO SHARE (%)
INPUTS (HR) | UKFCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
National Emergency Operation Centres (NEOCs) in affected states strengthened for coordination and management of response to hazard events through fast, effective and principled deployed surge teams | Initial teams requested deployed within 48 - 72 hours of request |  | Achieved in 2024 | Teams deployed within 48 hours |  | Reports and support meet agreed performance standards Suitable qualified surge staff available in sufficient numbers for rotations
|  | Achieved |  |  |  | CDEMA has suitable logistics arrangements in place for team to deploy in time and gather relevant information.
Source
Informal surveys of NDCs and beneficiaries post response
Output Indicator 1.2
| Level of positive feedback collected from NEOCs through AARs and surveys regarding support to NEOCs during emergencies, including through deployment of telecommunications equipment and expertise | Planned | Generally positive feedback from NEOC staff based on experiences of past events (through national AARs), though there is variation in experience by country and by event. No actual survey information available. 70% is an estimation. | Majority of feedback is positive and no major complaints - (at least 80% of survey respondents satisfied or highly satisfied)
Achieved
Source
Output Indicator 1.3
| Timely completion of needs assessment reports and progress to address needs is tracked and communicated | Planned | Daily reports typically provided by the RNAT team, with a consolidated report typically available within 10 days | a) Rapid Needs Assessment report provided per impacted state where RNAT is deployed within 7 days of impact; b) The Caribeban Logistics System provides regular summary tracking data for the CDEMA sitreps on relief supply progress.
Achieved
Source
Available Needs Assessment reports; CDEMA sitreps
IMPACT WEIGHTING (%)30
INPUTS (£) |  |  | Govt (£) |  | UKFCDO SHARE (%)
RISK RATING
INPUTS (HR) | UKFCDO (FTEs) |  |  |  |  | minor
OUTPUT 2 | Output Indicator 2.1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
Coordinated and secured distribution of relief supplies to affected populations (including most vulnerable) with strong accoutabibilty chains | Percentage of relief supplies distributed received by the intended beneficiaries and logged on Relief Supplies Tracking System | Planned | a) Minimum of 75% of relief supplies delivered to intended beneficiaries | a) Minimum of 90% of relief supplies delivered to intended beneficiaries as identified by NEOCs b) Distribution maps updated daily with information (including beneficiary disaggregation where possible by sex, age, disability and geography) from field and shared with partners |  | a) Adequate support for management of relief distribution to prevent disorder and/or loss of supplies; b) Need assessment information on required supplies; c) Accurate information available on the locations of the most vulnerable affected persons; d) Availability and use of tracking system for distribution. e) Reporting of distribution to beneficiaries undertaken
Achieved
Source
Relief monitoring maps, Available Reports of the Special Coordinators in the affected states.
IMPACT WEIGHTING (%) 20
INPUTS (£) | UKFCDO (£) |  | Govt (£)
RISK RATING
INPUTS (HR) | UKFCDO (FTEs) |  |  |  |  | minor
OUTPUT 3 | Output Indicator 3.1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
Support to damage assessment and needs analysis provided through CARICOM Disaster Assessment and Cordination (CDAC)Team if deployed | Sectoral damage assessments produced as requested | Planned | n/a | High quality sector damage asessment reports requested are produced within 2 weeks of deployment |  | Suitable conditions on the ground to allow for the assessments to be undertaken
Achieved
Source
Availabile Sectoral Damage Assessment reports; CDEMA SitReps, Partner Meetings
IMPACT WEIGHTING (%) 30
INPUTS (£) | UKFCDO (£) |  | Govt (£) |  | UKFCDO SHARE (%)
RISK RATING
INPUTS (HR) | UKFCDO (FTEs) |  |  |  |  | moderate
OUTPUT 4 | Output Indicator 4.1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
Additonal surge team capacity and capability to respond is available | Increase in numbers of adequately trained surge teams providing support to impacted states and categories of personnel responding | Planned | RNAT (18 persons) CDRU (36 persons) COST (2) CDAC (6) teams ( 65 persons on roster) CETT (2) persons Psychosocial support personnel (at least 2 availalable through CANPA) 1 cash programming support officer | RNAT (18 persons) CDRU (36 persons) COST (6) CDAC (6) teams ( 65 persons on roster) CETT (4) persons SAR (12) Psychosocial support personnel (at least 2 availalable through CANPA) 2 Cash Programming Support Officers |  | Trained persons available in the region to provide the required surge support and CDEMA continues ot boost capacity. Exact numbers for increases in surge support are still under consideration. Given the increase in the range of sectors to be covered, the RNAT will likely need to expand, and the SAR will likely expand in accordance with INSARAG Light Level Standards. The CETT is new and may require larger deployments to support both the EOCs and team deployments.
Achieved
| Output Indicator 4.2 |  | Baseline April 2025 | Target March 2026
| Number of response personnel that have completed approved Safeguarding Training | Planned | in 2024 all persons deployed by CDEMA received appproved training on safeguarding of beneficiaries as part of deployment orientations. | All deployed teams confirm received safeguarding training, including any updates - example. new child protection policy
| Output Indicator 4.3 |  | Baseline April 2025 | Target March 2026
| Number of emergency response staff evaluated and receiving phychocial support | Planned | In 2024, all CDEMA deployed RNAT, COST and CETT personnel (63 persons) received post-deployment psychosocial support. | At least 80% of surge team and NEOC officers receive Psychosocial evaluation and support if required post deployment or impact
Source
CDEMA reports
IMPACT WEIGHTING (%) 10
INPUTS (£) | UKFCDO (£) |  | Govt (£) |  | UKFCDO SHARE (%)
RISK RATING
INPUTS (HR) | UKFCDO (FTEs) |  |  |  |  | minor
OUTPUT 5 | Output Indicator 5.1 |  | Baseline April 2025 | Target March 2026 |  | Assumptions
Sustainability of CDEMA financing for emergency support enhanced | Multi Source Trust Fund (MSTF) established to support CDEMA emergency teams | Planned | CDEMA is pursuing MSTF establishment - MSTF Steering Group established. Consultancy for establishing MSTF framework, and Consultancy to Undertake Organisational Restructuring have been prepared. | MSTF Governance and Management Options Report; MSTF Implementation Roadmap and MSTF Final Design and Operational Plan available. |  | Support provided to CDEMA to develop viable options for sustainable financing and Participating States endorse proposals
Achieved
Source
CDEMA Council reports
IMPACT WEIGHTING (%) 10
INPUTS (£) | UKFCDO (£) |  | Govt (£) |  | UKFCDO SHARE (%)
RISK RATING
INPUTS (HR) | UKFCDO (FTEs) |  |  |  |  | major