## Annual Review

Title: Caribbean Humanitarian Response Platform
Programme Value £ (full life): up to £10.0 million		Review date: June 2025
Programme Code / AMP ID# 400391	AMP start date: 15/07/2024	AMP end date: / 30/03/2029

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0007069.odt
DevTracker Link to results framework:	Results will be based on an agreed emergency event response plan.

A. SUMMARY AND OVERVIEW

Description of programme

The Caribbean Humanitarian Response Platform (CHuRP) is a multi-year programme designed to strengthen FCDO agility in preparing and responding quickly to newly arising disasters across the Caribbean. It will do this by channelling funds to pre-agreed capabilities, arrangements and partners that can deliver rapid assistance to the most vulnerable, crisis-affected populations in a region that is highly vulnerable to climate and other shocks. It will primarily support both the independent Overseas Development Assistance (ODA) eligible countries and ODA and Non-ODA eligible UK Overseas Territories in the Caribbean. However, it can be used for emergency responses in the Americas if required, albeit with limited activity scope.

This platform programme was approved via Ministerial submission in July 2024 and following the Programme Operating Framework (PrOF) rules for rapid onset humanitarian response, the Business Case was subsequently approved in February 2025. The programme takes an on-demand approach with new response activity projects added as approved and then managed by relevant teams responsible for the associated budgets.

To date this platform has been used to manage UK emergency support provided following the passage of Hurricane Beryl in July 2024. This hurricane was a deadly and destructive tropical cyclone that impacted parts of the Caribbean, the Yucatán Peninsula, and the Gulf Coast of the United States in late June and early July 2024 and was the earliest-recorded Category 5 hurricane in the North Atlantic Ocean.

Hurricane Beryl: June 28 – July 11, 2024

Figure 1: Satellite image of Hurricane Beryl as well as its track across the Caribbean region

From 1-5 July Hurricane Beryl severely impacted the islands of Grenada (Carriacou and Petit Martinique) and Saint Vincent and the Grenadines (Mayreau and Union) as well as several Jamaica parishes (Clarendon, Manchester, and St Elizabeth). More than 3 million people were impacted by the Category 4 hurricane in the three countries, including 15 deaths, 102 injuries reported and close to 1,770 people displaced in shelters at the height of the storm[1].
[1] phsahurricane-beryl-finalfinal-1.pdf

Following appeals for international assistance from the impacted countries, the UK moved swiftly to agree a package of support. On 5 July, the Foreign Secretary announced that the UK had approved a package of support up to £500,000 for Caribbean countries most impacted by Hurricane Beryl. UK emergency funds were primarily used to support the Caribbean Disaster Emergency Agency (CDEMA) surge response teams deployed to St. Vincent and the Grenadines (SVG) and Grenada (GRN); to deliver relief supplies to SVG and GRN; and to provide cash transfers to impacted vulnerable populations in Jamaica.

The FCDO Caribbean Development Team managed the Hurricane Beryl projects and worked alongside the Humanitarian Response Group (HRG) - now Humanitarian Crisis Response Department during the initial six weeks of UK emergency support.

Summary supporting narrative for the overall score in this review

This review specifically covers the cash grant support provided in Jamaica to 1,117 people (51% women) including 113 persons with disabilities through the World Food Programme (WFP) and the delivery of emergency relief supplies (800 shelter kits capable of supporting up to 4,000 people and 1,620 buckets) to Grenada (GRN) and St. Vincent and the Grenadines (SVG).

Funding also covered deployments by HRG of a Procurement and Logistics Expert to help with the transportation and delivery of regionally prepositioned core relief items through CDEMA to the national disaster offices in Grenada and Saint Vincent and the Grenadines as well as restocking of new items at the Antigua-based warehouse[2], and a Humanitarian Affairs Officer to help manage information and undertake needs analysis in Jamaica. Moreover, a UK expert was included as part of the UN Disaster Assessment and Coordination (UNDAC) mission to affected Caribbean states to support their humanitarian assistance coordination.
[2] 1320 coverage/ shelter kits and 1728 solar lanterns prepositioned for 2025

Under the pre-arranged MoU agreement with CDEMA, emergency surge teams of first responders (over 203 experts) were deployed over a period of 10 weeks to GRN and SVG with UK support to assist their respective national disaster offices with emergency operations, telecoms and relief, security and logistics; in addition, rapid sectoral damage assessments for Hurricane Beryl were conducted. This agreement, which expired in March 2025, has now been brought under the umbrella of the CHuRP as of May 2025.

The UK emergency response plan, encompassing the elements described here, was delivered as expected, which justifies the annual review score of “A”.
Major lessons and recommendations for the year ahead

Flexibility in programme design
Post-disaster conditions often disrupt planned delivery mechanisms, requiring rapid adaptation to effectively reach those in need. WFP collaborated with the Government of Jamaica on vulnerability assessments, registration processes, transfer values, tranche planning, and beneficiary communication. However, several elements of WFP’s original cash programme design had to be modified.  Digitized tools developed for handheld tablets prior to the storm were not immediately usable due to electricity access challenges. Cash grant amounts were adjusted, and instead of transferring funds to the Government of Jamaica, WFP activated an existing agreement with Western Union to deliver cash assistance directly to beneficiaries following a feasibility assessment.

Recommendations:
- Design programmes with built-in flexibility, contingency or alternate delivery mechanisms to allow quick pivots when needed.
- Maintain close coordination with government counterparts to adapt targeting, registration, and communication strategies as needed.

Regular checks of prepositioned emergency stocks and logistical delivery support
A brief delay occurred in transferring prepositioned relief items from Antigua due to minor water damage discovered during pre-shipment inspections. Port structure/facilities in the smaller islands also posed challenges. The items were consigned to CDEMA for delivery to national disaster offices, but we relied heavily on our logistics expert for information on progress as well as engagement with the new Caribbean Logistics System (CLS). CDEMA’s 2024 after-action review highlighted significant issues with relief stores, noting that many National Disaster Management Agencies had expired items or incomplete inventories. The hurricane’s early arrival further complicated preparations, and responsible staff were often volunteers or emergency planning officers rather than logistics professionals. A comprehensive assessment of high-frequency relief items across nine Caribbean countries has recently been completed, alongside enhancements to the CLS online database. These efforts will inform the FCDO Caribbean relief supply plan which is updated annually.

Recommendations:
- Conduct annual quality checks of relief stocks in the region
- Continue to assess last mile delivery challenges and integrate solutions into the supply chain plan
- Continue strengthening the CLS through partnerships and participation in the CDEMA Multinational Caribbean Coordination Cell (MNCCC) and the Caribbean disaster management development partner group.
- Consider early deployment of logistics experts to assess and support supply chain readiness which is an option provided in our supply chain plan.

Strong relationships with key partner ministries and parishes
Strong technical collaboration between the implementing partner and beneficiary government agencies is critical to ensuring design and delivery effectiveness. WFP’s lead role and partnership with the Ministry of Labour and Social Security (MLSS) led to well informed decisions on transfer mechanisms, values and targeting criteria, enhancing the overall reach and suitability of the cash transfer programme.  Engagement with parish offices and robust communication efforts reduced concerns about fraud, fostering trust among beneficiaries to collect their assistance.

Recommendations:
- Prioritise early and sustained engagement with key ministries (e.g., social protection, disaster management).
- Leverage local community or parish offices and implement strong communication campaigns to build trust and counter misinformation.

Community Feedback Mechanisms (CFMs) essential
Early deployment of staff to support CFMs is crucial to ensure delivery partners are sensitized to potential issues and solutions in their programme design. As the programme transitioned to cash delivery, WFP scaled up its CFM team, enabling rapid responses to queries (over 12,000 calls) and timely programme adjustments. One case of domestic violence was identified among beneficiaries, which WFP addressed in coordination with Jamaican officials and relevant UN agencies.

Recommendations:
- Deploy CFM teams at the start of the response to gather real-time feedback and address concerns.
- Ensure CFMs are equipped to escalate and respond to sensitive issues, including protection concerns or gender-based violence.

Strengthen Beneficiary Monitoring for Relief Items
Conditions, especially in the immediate aftermath of a disaster, often hinder the collection of distribution data or beneficiary disaggregation. While spot checks and teams are deployed to help address this, data is generally incomplete. HRG is developing new templates to improve monitoring of Core Relief Items (CRIs), moving beyond just consignee delivery confirmation to track actual distribution and usage where feasible. Bolstering relief supply tracking systems including use of digital solutions and protocols was also a recommendation of the CDEMA 2024 Regional Response Mechanism After Action Review.
Although detailed data on our shelter kit distribution was unavailable, the Grenada national disaster office reported distribution of the buckets to specific communities and facilities[3]. Physical confirmation of use was obtained through staff visits to Carriacou, Union and Mayreau islands, where some undistributed kits were also flagged in one location. In contrast, the cash transfer programme in Jamaica provided disaggregated beneficiary data by sex, age, disability, and geography.
[3] Buckets provided were distributed to persons from the fishing community of Windward, the farming communities of Belair and Dover, as well as from the communities of L'Esterre and Harvey Vale. Some were specifically distributed at the Top Hill Senior Citizens Home.

Recommendations:
- Develop and implement enhanced monitoring protocols that go beyond delivery confirmation.
- Conduct regular spot checks and field visits, especially in remote or hard-to-reach areas.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The CHuRP impact statement is “Reduced suffering of vulnerable, crisis-affected people in the Caribbean”, with one intended outcome - Timely, proportionate, accountable response to most vulnerable populations, delivered in an effective, inclusive and principled way.

To achieve this, CHuRP defined three outputs:
  1. Rapid life-saving assistance and protection to crises and early recovery;
  2. Regional and bilateral partnerships to enhance readiness and coordination; and
  3. Anticipatory action to reduce severity of shocks.

Delays in the arrival of humanitarian assistance increase the risk of human suffering and death. To mitigate against this, this programme was designed to be flexible, and to enable timely and targeted, high-quality assistance by having protocols and arrangements in place in advance of shocks; FCDO resources, capabilities and partnerships on standby; and access to accurate and up to date analysis of potential and emerging humanitarian situations.

The programme made progress towards the stated outcome as there is clear evidence that it delivered emergency assistance to affected vulnerable populations in an effective, proportionate and inclusive way. There were however some challenges with timeliness given some relief stock stored in the warehouse in Antigua was damaged, which delayed its deployment. Despite this, the UK emergency supply stocks were still among the first to reach the affected populations in Grenada and St. Vincent and the Grenadines.

In addition, completing the Jamaica Household Disaster Impact and Needs Assessment and verification exercise also took longer than expected due to a range of factors including significant challenges in accurately targeting beneficiaries due to prolonged power outages from widespread storm damage, difficulties in locating individuals, and inaccurate contact information.

The theory of change (see figure below) and related assumptions have not changed and remain valid, however, only two inputs - (i) Rapid life-saving assistance and protection to crises and early recovery and (ii) Regional and bilateral partnerships to enhance readiness and coordination - were funded in 2024.

CHuRP active: protocols & partners (WFP)
Inputs
Process
Outputs
Outcome
Impact
Reduced suffering of vulnerable, crisis-affected people in the Caribbean
Decision Point:

Identification & assessment of rapid or slow onset crises meeting criteria for response

Appropriate delivery options for response linked to country & context

Funds mobilised from regional funds &/or HCR
Regional Funds & Humanitarian Crisis Reserve
HRG capabilities on standby
Response partnerships (e.g. CDEMA)
Early warning & analysis
Anticipatory action to reduce severity of shocks
Rapid life-saving assistance and protection to crises and early recovery
Regional & bilateral partnerships to enhance readiness & coordination
Timely, proportionate, accountable response to most vulnerable populations, delivered in an effective, inclusive and principled way

 Figure 2: Theory of Change of the Caribbean Humanitarian Response Platform

The assumptions underpinning the theory of change include:

- Sufficient funding is rapidly made available from relevant sources
- Response plans support the UK’s humanitarian framework and priorities, for example:
  - The use of multi-purpose cash transfers where possible and appropriate.
  - Maximising inter-agency coordination and accountability to affected populations.
- Development and assessment of response plans is contingent on expert staff time and capacity
- Country and regional preparedness plans are regularly updated, including pre-identified delivery partners; and posts and desks undertake regular crisis training and exercises.
- Security in the affected countries will allow field monitoring.
- Responses will be adapted based on learning and best practice; and
  1. Early response, made feasible by pre-agreed protocols and partnerships, will save more lives and represent good VFM compared to a late response.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This programme is a multi-year platform for on-demand humanitarian support. Based on its performance against the agreed activities in the year under review, as well as the fact that pipeline funding for the FY2025 hurricane season is available to support agreed emergency response plans if required, the programme remains on track.

Planned outcomes under the World Food Programme/Jamaica Hurricane Beryl Response which were effectively tracked and reported on are provided in the table below:

WFP Planned Results	Indicator(s)	Baseline	Targets	Progress to Date[4]	Achieved/ / Not Achieved
Outcome 1: / Crisis affected populations are able to meet their food, nutrition and other essential needs in the aftermath of shocks.	% of target population with an acceptable Food Consumption Score	0	Over 70% of targeted population achieve an acceptable food consumption score	88%	Achieved
[4] Reference: FCDO Humanitarian Funding Report (updated) submitted by WFP on 17 April 2025

Where an evaluation is planned, set out what progress has been made.

Though funded under a separate programme, the humanitarian actions provided through the CDEMA surge teams in 2024 for several disaster events including Hurricane Beryl but also wildfires in Belize and an oil spill off Tobago, were evaluated by way of national and regional after-action reviews in February 2025. The final report of this activity remains to be completed and circulated to stakeholders.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Extreme weather and other events continue to threaten and impact the Caribbean, coupled with the region’s heavy reliance on external assistance following significant disasters. Rapid, life-saving, flexible humanitarian assistance will continue to be a critical need.

Humanitarian assistance remains a top priority of the Foreign Secretary and the CHuRP programme is aligned with UK strategic goals, as the criteria under which future projects will be added to the platform programme are:
- Prioritise urgent lifesaving assistance to people in greatest need.
- Protect civilians, displaced persons, marginalised people and especially women and girls.
- Enable early recovery and restoration of essential services and livelihoods of the poorest.
.
In terms of the wider context, the UK continues to be a leading partner supporting preparedness and building resilience in the region. This includes improved Disaster Risk Finance (DRF) strategies and investing in insurance in the Caribbean or global funds to enable communities to recover more quickly. These complement the emergency response activity delivered through CHuRP.

Prearranged disaster risk finance initiatives that UK supports[5] which were activated for Hurricane Beryl in 2024, included:
[5] We may not have a say over activation
- The UN Central Emergency Relief Fund and Red Cross Disaster Relief Emergency Fund were both triggered and provided around £4.61m for humanitarian efforts.
- The Caribbean Catastrophe Risk Insurance Facility (CCRIF) through which Caribbean islands currently transfer £1.3bn of risk[6]. CCRIF paid out over US$84.0m for 10 policies across five countries due to the passage of Hurricane Beryl. Grenada received US$55.5m, the largest ever CCRIF payout within the expected 14 days following the event, after triggering their cyclone, excess rainfall, fisheries and water and electricity utility parametric policies. Less insured SVG received US$1.86m. In 2023 we provided US$25.0m to set up the Caribbean Water Utilities Insurance Collective (CWUIC), which paid US$2.2m (EC$5.95m) to the National Water and Sewerage Authority (NAWASA) in Grenada who were the first to sign up to this latest CCRIF product.
  [6] UK was a founder donor in 2017 -See https://www.ccrif.org/ for more details
- The UK also supported small-scale producers of nutmeg and cocoa in Grenada who received $1.45m through the Natural Disaster Fund set-up with UK (£25m) and German funding.

UK has championed Climate Resilient Debt Clauses (CRDCs) too, which defer principal, interest and other loan charge payments following a significant disaster building on the leadership of Grenada and Barbados, and in particular of PM Mottley’s Bridgetown Initiative. We were the first bilateral creditor to offer CRDCs and we are calling for all bilateral, multilateral, and private sector creditors to offer CRDCs by the end of 2025. CRDCs allow borrowers to pause debt repayments for a pre-agreed duration in a net present value-neutral way when a pre-agreed shock hits. Hurricane Beryl became the first “test case” of disaster clauses: In a world first, Grenada activated the debt clause in its government 2015 bond saving the country around US$12.5 million in repayments due November 2024 giving them much needed breathing space unlike in 2004 when Hurricane Ivan hit. SVG formally requested deferral of debt service from the World Bank on 24 July of approximately US$4.19 million (roughly 0.5% GDP).

The Caribbean Development Bank, where the UK is one of the largest shareholders and a founding member, provides a range of disaster response grants and loans to any affected Borrowing Member Country (BMC) under its Disaster Management Strategy and Operational Guidelines (DiMSOG, 2021). A US$5.0m Immediate Response Loan (IRL) was provided to both SVG and Grenada for the purpose of cleaning, clearing and emergency restoration of infrastructure and essential public services damaged by Hurricane Beryl[7]. SVG also applied for a US$30m Disaster Risk Management (DRM) policy-based loan[8] from CDB’s Ordinary Capital Resources. It will help implement its ongoing DRM reform programme. Prior actions for the DRM Sector PBL have been satisfied. This reform programme also forms the basis for a new WB Catastrophe Deferred Drawdown Option (CAT-DDO) of US$20.0m which was presented to their Board of Directors in March 2025.
[7] The IRL is funded through CDB’s Special Funds Resources; repayments in quarterly instalments commencing five (5) years after the date of the Loan Agreement; Interest 0.75% per annum on the amount of the Loan disbursed and outstanding. The UK pledged £21m to the Caribbean Development Bank’s Special Development Fund (SDF) creating SDF 10 (2020-2030).
[8] DRM loan is provided at 5.6% interest rate per annum variable and an amortization period of 12 years following grace period of 5 years

## C. DETAILED OUTPUT SCORING

Given the flexible, reactive nature of the platform programme to humanitarian emergencies, there is no overall logframe against which to measure outputs. As previously indicated, only two inputs in the Theory of Change were funded in 2024 - (i) Rapid life-saving assistance and protection to crises and early recovery and (ii) Regional and bilateral partnerships to enhance readiness and coordination. This led to the following summary of the status of results for the planned outputs:

Output Number	TOC Programme Output	Status of Results
1	Rapid life-saving assistance and protection to crises and early recovery	Results achieved and described below
2	Regional & bilateral partnerships to enhance readiness & coordination	Results achieved and described below
3	Anticipatory action to reduce severity of shocks	N/A. Future Annual reviews will report progress if used.

TOC Output 1: Rapid life-saving assistance and protection to crises and early recovery

During 2024, the CHuRP responded to the Hurricane Beryl impacts in the Caribbean using various modalities. These included support to World Food Programme humanitarian efforts in Jamaica, the provision of core relief items; technical assistance support to CDEMA and to the British High Commission Jamaica; as well as support to the UNDAC mission to Barbados.

World Food Programme (WFP) Results

The FCDO partnered with the WFP offices in Jamaica to provide £160,000 in support of their cash assistance program which targeted the most vulnerable persons affected by the disaster. This accounted for 9% of the total direct assistance provided to Jamaica through the WFP. The FCDO support facilitated the WFP in surpassing their target number of beneficiaries. Assistance prioritised households that had lost livelihoods or suffered home damage or destruction, with a focus on vulnerable groups, including individuals with disabilities, the elderly, and children.

The planned and actual results for the WFP/FCDO response in Jamaica following the passing of Hurricane Beryl are:

Planned Results	Indicator(s)	Baseline	Targets	Progress to Date[9]	Targets Achieved/ / Not Achieved
Output 1.1 / Targeted populations receive food assistance and other necessities to cover their immediate needs and preserve their nutrition status.	# of persons who received cash or voucher assistance	0	1,100[10]	1,117	Achieved
	% of persons who expressed satisfaction with the cash and voucher assistance	0	90%	97%	Achieved
[9] Reference: FCDO Humanitarian Funding Report (updated) submitted by WFP on 17 April 2025
[10] During the response, a needs assessments carried out by Jamaica’s Ministry of Labour and Social Security (MLSS) resulted in the reduction of the original target of 2,135 persons to be assisted to 1,100 persons across the most affected parishes of the country.

A breakdown of the beneficiaries is provided in the table below.

Beneficiaries were identified using the Jamaica Household Damage Impact and Needs Assessment (JHDINA) tool, a survey designed to guide post-disaster relief efforts by assessing the impact and needs of affected individuals. While handheld tablets for collecting beneficiary data were not initially utilized in the field due to challenges with access to electricity, between July 12 and August 9, 2024, WFP and MLSS were able to digitize 11,617 assessment forms. A verification exercise using Computer-Assisted Telephone Interviews (CATI) was conducted, reaching 6,018 households. With this 57% response rate during verification, the digital approach proved effective in generating real-time, accurate data to guide relief efforts. The deployment of the JHDINA tool and verification processes formed the backbone of the government’s response, enabling more efficient resource allocation.

WFP and the MLSS successfully launched a two-tranche cash transfer programme, reaching 1,117 persons across the most affected parishes. A 93 percent redemption rate was achieved for tranche 1 and a 98 percent rate in tranche 2 of the programme.

Post-distribution monitoring highlighted the effectiveness of the cash-based approach, with beneficiaries reporting significant improvements in their ability to repair homes and replace damaged assets (69%), enhance food consumption (51%), and meet other household needs (19%). Notably, the intervention played a critical role in stabilizing food consumption patterns, with 88% of recipients achieving an acceptable food consumption score - preventing further deterioration in dietary quality and mitigating the risk of deepening food insecurity.

WFP was also able to collect beneficiary feedback by establishing a strong Community Feedback Mechanism (CFM) that enabled beneficiaries to share feedback, aligning with global Accountability to Affected Populations (AAP) standards. The CFM infrastructure included transferring tablets to the Jamaica Office, purchasing SIM cards for calls, creating a dedicated email line, and employing four (4) monitoring assistants to manage a helpline at the UN Common Premises. From the CFM the WFP was able to collect data from beneficiaries to establish that 97% were satisfied with the assistance received.

Other emergency support

Other support to impacted countries provided through HCRD arrangements included:

Core Relief Items (CRIs)

In the response to Hurricane Beryl, the FCDO provided 800 emergency shelter kits and 1,620 buckets prepositioned in Antigua to the affected islands of St. Vincent and the Grenadines (Mayreau and Union) and Grenada (Carriacou) They were split evenly (i.e. 400 shelter kits and 810 buckets) to GRN and SVG.

The CRIs were consigned to CDEMA, for distribution by the National Disaster Management Office in a joint response. These relief items arrived 7 July 2024 in Union Island/Mayreau and 8 July 2024 in Carriacou.

The prepositioned stocks were replenished in Antigua from the UK by 11 July 2024.

Figure 3: Delivery of UK prepositioned relief items in Antigua to Carriacou, Union and Mayreau islands; Infographic report provided by HSOT

Technical Assistance

A UK procurement and logistics specialist, was deployed and contributed the following to the response efforts:

- Monitoring and updates on FCDO CRIs and deliveries to impacted islands.
- Drafting of an MoU for FCDO and CDEMA for release and delivery of FCDO CRIs.
- Update of an MoU for FCDO and Antigua & Barbuda Ports Authority for storage of FCDO CRIs in Antigua; and
- Support and advice to CDEMA and WFP during Beryl response on the design of pipeline, delivery management records and reporting.

Support to UNDAC

The UK government provided a team member on the UNDAC team via the International Humanitarian Standby Partnership (IHSP) who supported the relief coordination efforts in the Eastern Caribbean. Some of the costs associated with this UK team member’s deployment were covered under the CHuRP programme but our contribution also included two generators from stocks held in the UK to ensure continuous power for their temporary base camp.

Humanitarian Officer

A UK Humanitarian Affairs Officer was deployed to Jamaica following the passing of Hurricane Beryl, to assist with humanitarian information management and mapping impact of storm and humanitarian needs. He was based at the British High Commission offices in Jamaica from 5 to 12 July 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Not applicable as this programme supports emergency activities over a period of no more than 6 months.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Not applicable as this is the first Annual Review of the programme.
TOC Output 2: Regional & bilateral partnerships to enhance readiness & coordination

During the 2024 Hurricane Beryl response, the UKFCDO partnered with the World Food Programme by way of a Contribution Arrangement which commenced on 3 July 2024 and expired on 31 March 2025 and provided support totalling £160,000 to relief efforts in Jamaica.

In addition, the UKFCDO agreed a new MOU with the CDEMA to replace the one agreed from 2018-2025. The UKFCDO and CDEMA signed the MOU on 28 May 2025, which will remain effective through the 2025 hurricane season and expire on 31 March 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two further potential delivery partnerships for CHuRP through the United Nations International Children's Emergency Fund (UNICEF), and the International Organization for Migration (IOM) will be added in 2025, and the required updating of their due diligence assessments is now underway.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Not applicable as this is the first Annual Review of the programme.

D: VALUE FOR MONEY (VfM)

The main guarantor of VfM in this programme is its explicit link to the FCDO humanitarian principles and intervention criteria. These inform our decision to respond and funding levels. It includes consideration of vulnerability, the scale of the shock, needs and ability to cope as well as the international and national responses, the level of humanitarian access and the UK comparative advantage - whether a UK response can be timely, meets a critical gap and provides added value. It also considers what disaster finance mechanisms are triggered and what other donors provide support.

The recommended approach to measuring VfM in rapid response is to look at the humanitarian VfM triangle of cost, quality and speed, because speed is of the essence in rapid response to save lives and reduce suffering. Using the triangle enables analysis of VfM trade-offs between the three variables which change over time during a response.

The main cost drivers for the CHuRP during the review period have been the WFP support for the cash assistance programme in Jamaica (£160,000), the UNDAC deployment (£17,389.68), deployment of UK logistics specialist (£4,037.67) to support the coordination response with CDEMA and the mobilisation funds (£50,000) provided to CDEMA under the 2025/2026 MOU.

Under the WFP Hurricane Beryl response in Jamaica, strong value for money was demonstrated through targeted cash assistance, data-driven decision-making, and efficient resource allocation. The use of digital tools, such as the Jamaica Household Disaster Impact and Needs Assessment (JHDINA), streamlined data collection and verification, reducing administrative costs and improving targeting accuracy. This minimized the risk of misallocated cash support, ensuring that assistance reached the most vulnerable households.

The initial plan to support 2,135 individuals at $2 per person per day for a period of two (2) months was revised to assist approximately 1,100 beneficiaries over two months. Transfer values were recalibrated based on household size: US$120 per month for households of 1-2 persons, US$240 for 3-5 persons, and USD$340 for six or more. This adjustment to variable tranches concentrated funding on a smaller number of beneficiaries but prioritized those in greatest need and maximized impact within budgetary limits.

By leveraging Western Union’s existing infrastructure, WFP reduced logistical expenses while ensuring timely and secure cash transfers. Western Union also agreed to reduce its transfer fee to 2.5% (instead of 3%).

Additionally, the project strengthened Jamaica’s disaster response capacity, creating long-term cost savings by modernizing assessment and aid delivery systems. The high beneficiary satisfaction rate of 97% and significant improvements in stabilizing food consumption patterns underscore the cost-effectiveness of the approach, reinforcing its potential as a scalable model for future humanitarian responses.

In addressing equity, the WFP activities targeted direct beneficiaries and were able to reach a total of 552 males (49%), and 565 females (51%). From the overall total, disabled persons totalled 113 (10.12%) of which were 75 females (6.7%) and 38 males (3.4%).

Cost-effectiveness was achieved through a multi-dimensional humanitarian response and assistance to the most vulnerable in areas affected by disasters that involved close working, coordination and policy engagement with the donor community. FCDO team members regularly attended and participated in meetings of the Caribbean Development Partner Group for Disaster Management chaired by CDEMA, with the national disaster offices and UN, and utilised the network of posts to gather information and communicate its efforts.

Assessment of whether the programme continues to represent value for money

This programme allows the UK to provide direct and almost immediate assistance to impacted countries in the region. It continues to represent VfM as it strengthens FCDO agility in preparing and responding quickly to newly arising disasters across the Caribbean by channelling funds to pre-agreed capabilities, arrangements and effective partners.

Whilst the Caribbean region has some of the highest levels globally of prearranged financing (PAF) for disasters including contingency reserves, and regional risk pool insurance protection it is still generally a small amount of the crisis finance needed for a country to recover.

In January 2025, the High-Level Panel on Closing the Crisis Protection Gap published a new report– Crisis Protection 2.0: Future-Proofing Our World[11]. It sets out ten strategic recommendations for making the finance system more coherent so it can achieve the highest impact in the countries where the finance gap for protecting against disasters is biggest and growing most quickly – Least Developed Countries, Fragile and Conflict Affected States (FCAS), and Small Island Developing States. It called for 20% of crisis finance to be pre-arranged by 2035. Today, it’s under 2% globally. The UK is supporting this ambition.
[11] High-Level Panel on Closing the Crisis Protection Gap

E: RISK

Overview of risk management

The overall risk rating for the programme remains moderate, taking into account the mitigating actions, and remained within the FCDO appetite. The key risks remain loss of humanitarian access, fraud and increased sexual exploitation and abuse. FCDO conducts rigorous due diligence assessments and does regular monitoring to assess partner capability and risk management practice. Due diligence assessments for CDEMA, UNDP and WFP have all recently been updated/refreshed. FCDO is also ensuring that the partners have robust mitigation measures, that feedback and complaint mechanisms are implemented and follow up action is taken.

The programme’s Implementing Partners (IPs) have experience working in complex emergencies and are assessed as well equipped to manage these on-going risks. Risk management is well established in the programme through regular identification, assessment, and escalation protocols, where necessary.

During the review period a significant risk emerged related to the budgetary and staff cuts across the United States Government including the closure of the US Agency for International Development which played a lead role in humanitarian aid. The cuts could impact the effectiveness of various implementing partners and organisations involved in monitoring for climate/environment related disturbances (hurricane, earthquakes, tsunamis, etc) that threaten their target populations – USA, Caribbean. Such cuts could result in the:

- Cessation or reduction of forecasting and/or international reporting for hurricanes that are unlikely to impact the USA;
- Reduce data analysis and/or data collection for hurricanes that are deemed unlikely to impact the USA (e.g. reduced hurricane reconnaissance flights); and
- Reduce data collection and/or analysis that informs global climate modelling, impacting international understanding to climate change and future threats.

This in turn may affect international warning and informing and would reduce the evidence base for understanding the likely strength, trajectory, secondary impacts and timing of hurricane strikes in the upcoming 2025 season.  By extension, this would reduce confidence to make decisions to undertake anticipatory action that limits the impact of events.

Various mitigation measures were identified to reduce the severity of this risk to the overall programme objectives, including:
- The UK Met Office are embedded within the UK Disaster Management Oversight Committee (DMOC) Caribbean arrangements. This limits the potential impact of these risks to UK hurricane response operations.
- The Met Office routinely produce their own modelling and compare this against NHC and multiple other international forecasting centre models. This will continue to provide authoritative analysis to inform UK response planning and actions.
- CDEMA assessing impacts and alternate options including through EC Copernicus.
- Caribbean and UK to lobby USA to maintain quality of service provision by NOAA/NHC as the international authority on hurricane forecasting and key contributor to global climate modelling. This was done and the service continues currently.
OTD exploring support: a) for CDEMA to fill gap left in regional forecasting/ reporting/warning and informing; b) directly support OT meteorologists, and the Antigua Meteorological Service who provide warning and informing on behalf of several OTs.

With the addition of Support to CDEMA to the CHuRP Portfolio, there is one moderate risk related to financial stability of the Agency. However, CDEMA is in the process of establishing a Multi-Source Trust Fund (MSTF), to boost its sustainability which is being actively monitored by FCDO. The three broad cost areas to be covered by the MSTF are:
  1. Administrative costs of a restructured CDEMA Coordination unit (CU);
  2. Emergency response through the Regional Response Mechanism: and
  3. Programme delivery by the CDEMA CU in alignment with the Strategic Planning Cycles.

Climate and Environment

The Caribbean remains highly vulnerable to significant climate and environmental disasters. As evidenced by the very early formation of Hurricane Beryl as a Category 5 storm, climate change is exacerbating the intensity of storms that affect the region, which potentially contributes to a higher humanitarian caseload through increased food insecurity, health risks, and loss of shelter and livelihoods.

CHuRP seeks to mitigate against significant loss due to humanitarian crises by providing rapid funding to the impacted countries for critical and urgent post-disaster needs. The significant FCDO portfolio supporting climate and disaster resilience also helps increase preparedness and reduce risk.

HRG have been working to improve the sustainability of our supply chain for relief items by reducing packaging, eliminating single use plastics, including recycling, purchasing materials with a lower carbon footprint and promoting local procurement. Use of renewable energy is increasing, and our new pre-positioned stocks include solar lanterns. HRG recently updated our hygiene kits to ensure they meet SPHERE[12] standards, are inclusive, and are more environmentally aware.
[12] The Sphere standards are a set of principles and minimum humanitarian standards in four technical areas of humanitarian response: Water supply, sanitation and hygiene promotion (WASH), Food security and nutrition; Shelter and settlement and Health.

Where applicable, the environmental sustainability of programme activities will be assessed, including in terms of the protection of forest and water resources and opportunities for the programme to contribute to the Paris Agreement and UK COP26[13] commitments.
[13] COP26 – Conference of Parties, 26th session

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

During the period under review, the programme successfully selected and mobilised two partners – the WFP and HRG-HSOT arrangements. CDEMA was added in the last quarter.

The WFP Contribution arrangement was agreed in July 2024 and ended 31 March 2025. The WFP provided reports in accordance with the Contribution Arrangement and recently agreed FCDO reporting templates and requirements, as well as provided useful weekly updates to the Caribbean partners during the response. They were also very responsive to queries we had. A final project report was provided on 1 April 2025. Per the agreed Contribution Arrangement, the WFP was not required to provide audited or special financial statements, however, in accordance with the WFP/FCDO Framework agreement, the WFP is required to submit a final provisional uncertified financial report in the WFP Annual Country Report or standard Trust Fund format.

The Humanitarian and Stabilisation Operations Team (HSOT) is implemented by Palladium and provides the FCDO and the Office for Conflict Stabilisation and Mediation (OCSM) with capacity and specialist expertise for effective UK response to sudden-onset disasters, protracted crises and complex emergencies. To aid in the Hurricane Beryl response, HSOT provided a highly competent Procurement and Logistics Specialist who worked with CDEMA to coordinate the delivery of the UK core relief items to impacted beneficiary countries. After being deployed to the regions, within 3 days the first relief supplies were delivered to one of the impacted countries. Further, within one week the stocks used were replenished at the storage facility in Antigua and were therefore available in the event that another disaster struck the region.

The CDEMA MOU for CHuRP was signed in May 2025 and the Agency has received an agreed mobilisation fee of £50,000.00. However, under the previous arrangement with CDEMA submission of narrative, financial and audited reports were delayed and required amendments and resubmission before they were accepted. The outstanding audited reports have taken a long time to complete as the process requires the review and recommendation of approval by their finance sub-committee, followed by their Management Committee of Council, and thereafter approval by their Council. It is expected that the approved documents will be available to submit to FCDO following their Council meeting on the 27 June 2025.

FCDO performance

The FCDO humanitarian team and liaison officers in the Caribbean Development team ensured close monitoring of the situation with partners submitting regular situation reports (SitReps), information notes or briefing to the Crisis leads and FCDO posts.

Finance

For Hurricane Beryl £472,913.05 of £500,000.00 was fully spent. An amount of £181,427.35 was channelled through CHuRP which comprises the support to WFP, the payments for UNDAC and HSOT expert support. £216,345.00 was disbursed through Project AMP ID 300733-101 for CDEMA and the amount of £74,913.05 to purchase and ship replacement relief supplies to Antigua.

A further £50,000.00 for the mobilization amount has been transferred to CDEMA under the 2025/2025 MOU, bringing total spend under CHURP to £231,427.35 to date.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Throughout the review period the FCDO engaged regularly with the partners to gather feedback on the situation on the ground in impacted countries, receive general programme updates and to inform programme decisions.

The Annual Review process was based on a review of programme documents and was conducted by the Climate Change and Disaster Risk Management Team, led by the Climate Change and Disaster Resilience Adviser (SRO) and including the Climate and Renewable Energy Advisor (former Senior Programme Officer and PRO on the project), and the Programme Officer.

Date of last narrative financial report	n/a	Date of last audited annual statement	n/a