## Annual Review

Title: Verification and Technical Assurance Programme, Ukraine (VERITAS-UKR)
Programme Value £ (full life): £15m		Review date: / November 2025
Programme Code: 400393	AMP start date: / November 2024	AMP end date: / December 2029

Summary of Programme Performance
Year	2025
Overall Output Score	B
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006435.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007401.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Since the full-scale Russian invasion, FCDO has scaled up its ODA programming to address the devastating consequences and impacts of heavy fighting, air-raids and strikes on civilians, communities and infrastructure. British Embassy Kyiv’s (BEK) programming is often in hard-to-reach areas, where the needs are greatest and security threats are heightened. BEK staff cannot travel to directly to verify the delivery and assure the quality of programmes, even where these are away from the front line.

As the Independent Commission for Aid Impact recognised in its rapid review[1], the ‘impressive aid response’ has positioned the UK as an influential champion of Ukraine’s needs and responsive partner to the Government of Ukraine. At the same time, the context and travel restrictions for BEK staff presents the risk of aid diversion, fraud and safeguarding failures. It also limits the ability of BEK to demonstrate – and improve – the results and value for money achieved by the ODA portfolio.
[1] UK aid to Ukraine - Independent Commission for Aid Impact
VERITAS addresses these challenges and opportunities by providing vital verification, assurance and evidence to improve the quality and integrity of BEK’s ODA programming. It has four workstreams:
1. Third Party Monitoring (TPM),
2. generating portfolio-evidence on topics of cross-cutting interest (Portfolio Research),
3. transparency (supporting monitoring initiatives in civil society) and
4. programme-funded staff-post for monitoring and results.

Outcomes of the programme include a higher level of assurance for BEK programmes’ delivery and contribution to outcomes than could otherwise be achieved, and programmes adapting their approach through lessons learnt about delivery and citizen needs. TPM and Portfolio Research is the most effective way to obtain structured evidence critical to the delivery of development programming from otherwise inaccessible areas.

During its first year the VERITAS programme has funded TPM activities through a contract held by the Eastern Europe and Central Asia Directorate (EECAD) with a consortium led by Ecorys.

However, the focus of the programme’s first year has been dedicated to mobilisation: Contracting a dedicated commercial supplier for BEK to deliver on the first three workstreams and successfully recruiting programme-funded monitoring and evaluation experts to BEK. The new supplier will improve the breadth of services and local expertise available to BEK and build on the lessons from the Ecorys contract.

Summary supporting narrative for the overall score in this review.

The output score for VERITAS during the inception year is B (outputs moderately did not meet expectation). By using the EECAD contract and recruiting Monitoring and Evaluation advisors to support BEK programmes, VERITAS has partially delivered against its own outputs and outcomes.

However, planning assumptions which informed the programme logframe were over ambitious. The commercial onboarding of the new supplier has taken longer than expected, with delays to releasing the tender for a commercial supplier, which have been beyond the control of the BEK team. Specifics surrounding the delays and issues involved in the contracting process are detailed below in Major lessons and recommendations for the year ahead.

Continued use of the legacy EECAD contract for TPM was the mitigation measure for the tender delay. However, the EECAD contract was designed to address the breadth of monitoring and evaluation needs across the wider region rather than the specific requirements of Ukraine. As such, our ambition for the role TPM can play for the portfolio is partially met, and we have also been unable to fulfil the Portfolio Research workstream of the programme.

Major lessons and recommendations for the year ahead

A key lesson learned for the VERITAS programme relates to the timeline for the procurement of the critical supplier, and the complexities of operating in hard-to-reach areas. The expectation that the tender for a commercial supplier would be issued within the Commercial Pillar’s aim of 100 days to contract for open-tender-contracts proved to be overly optimistic, with unforeseen delays arising that were outside BEK’s, and in some cases, the FCDO’s control. This highlights the importance of factoring the risk of procedural or external setbacks into procurement timelines during programme planning. However, the challenges associated with appointing a supplier able to operate effectively within the unstable context also helps to demonstrate the unique value proposition provided by TPM to gather evidence in an otherwise inaccessible area.

Recommendation 1: The lessons from the procurement process (what caused the delays, their impact, and how they were navigated) should be documented thoroughly and shared with other relevant FCDO teams. [FCDO Lead MEL Adviser, by March 2026].

The TPM activities that were completed under the EECAD contract highlighted useful lessons. The timing of data collection in some cases reduced the immediate usefulness of TPM findings and affected participant recall, while security issues and data-sharing protocols limited the representativeness of samples. TPM tools lacked tailoring for specific project contexts, resulting in less actionable recommendations. These experiences are already informing the approach to the final round of TPM activities under the EECAD contract.

These lessons build on and confirm the learning from the longer history of BEK’s TPM in Ukraine, which were captured in a Synthesis Report. The headline lessons relate to the importance of close engagement with partners, adaptive fieldwork design, strong local presence, mixed-method approaches for robust analysis, and targeted dissemination activities. A keen focus on monitoring for Fraud and Safeguarding concerns is also key.

Recommendation 2: The lessons from previous rounds (specifically the detailed Synthesis Report) should be shared proactively with the new VERITAS supplier to inform their approach and design. [FCDO Lead MEL Adviser, January 2026]

Recommendation 3: Revise outcome indicators to capture impact of changes made as a result of TPM on programme effectiveness and value for money, including through future capture of change stories and instructions for synthesis reports to report on potential impact. This process will be informed by the latest round of programme annual reviews and the supplier evaluation process. [FCDO Lead MEL Advisor, January 2026]

Abbreviations and acronyms

5Es framework	Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness
BEK	British Embassy Kyiv
DDA	Due Diligence Assessment
EECAD	Eastern Europe and Central Asia Directorate (the parent Directorate for BE Kyiv)
EQUALS	Evaluation Quality Assurance and Learning Service
HARP	Humanitarian Assistance, Recovery and Protection Programme
HAVEN	Humanitarian Action through Volunteers, Enablers and Networks
ME(R)L	Monitoring, Evaluation (Results) and Learning
ODA	Official Development Assistance
TPM	Third party monitoring
UNHCR	United Nations Refugee Agency
UNICEF	United Nations Children's Fund
VERITAS	Verification and Technical Assurance Programme (the programme under review)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory and the assumptions are elaborated in detail in the diagram at Annex A and can be summarised as follows:
- IF VERITAS provides BEK with greater assurances for programme delivery
- AND BEK programmes not only learn lessons but have the ability to modify or adapt interventions based on TPM and Research findings
- AND VERITAS enhances BEK’s knowledge of programme operations and Ukrainian citizen needs on the ground
  - THEN BEK will be improve its decision-making to strengthen its portfolio delivery, such that it leads to better humanitarian and development outcomes.

The key assumptions for VERITAS are that:
- The commercial suppliers will be able to access project sites unbiasedly while maintaining duty of care obligations.
- There will be sufficient engagement between stakeholders (the VERITAS supplier, BEK programme teams, implementing partners) for activities to be implemented.
- VERITAS products and services are of sufficient quality and depth to meet user needs, and if not are taken through quality control processes until user needs are met.
- Stakeholders (individual programmes and portfolio decision-makers) have the capability, opportunity and motive to use evidence from VERITAS in decision making.
Evidence from the first year of the programme suggest the logic is valid, and that these assumptions have been correctly identified as important to reaching the programme outcome.

Experience through the EECAD legacy contract confirms the feasibility of TPM activities in the in Ukraine, and provides lessons on the necessary quality and depth, as described in more detail in Section C.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The expected impact of the programme is BEK's portfolio performance in a high-risk environment is maintained and improved leading to strengthened humanitarian and development outcomes for the people of Ukraine, as measured by two key indicators.

Impact Indicator(s)	Baseline	Progress (October 2025)
FCDO Ukraine Portfolio Quality Index	110.7	106.4
% of BEK programmes with Green outcome confidence ratings	50%	29%

The overall expected outcome of the programme is improved decision-making: more informed strategic planning and integrated programme delivery within BEK. This is measured by three indicators, which have not been measured for this Annual Review, other than to inform a baseline:
- # of BEK programme annual reviews that use TPM findings and recommendations to inform programme level decision making
- # of tangible examples of BEK programmes making adaptations based on evidence and learning from VERITAS
- % of BEK TPM customers reporting that VERITAS products provided actionable insights on their programme
These indicators will be reviewed, and targets and milestones will be set during the inception period of the VERITAS supplier projected to start in January 2026. This will include the addition of new indicators to capture the impact of changes made as a result of TPM on programme effectiveness and value for money: Successful TPM could potentially lower OCR where it leads to the identification of false assumptions or unreported issues in programme delivery. We will also strengthen the logframe through this process to support evidence gathering that can help mid-programme adaptations and shape strategic direction across the portfolio.

Despite the longer than expected mobilisation phase for the programme, the underlying logic of the programme remains valid, and the appointment of a new, dedicated TPM supplier for Ukraine provides an opportunity to build on and learn from the work under the EECAD contract, and provide a bespoke service for BEK. Accordingly, there is good reason to believe that the programme outcome can be achieved.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The VERITAS programme should continue. The rationale presented in the Strategic Case for the programme continues to stand. BEK’s ODA portfolio is high risk and spans a range of delivery partners in Ukraine. BEK staff are extremely limited in their ability to travel across Ukraine to directly monitor programme delivery, particularly to higher-risk areas. VERITAS should therefore continue to be BEK’s “eyes and ears on the ground.”

Despite slower than expected publication of the tender for BEK bespoke contract evidence collected from TPM rounds via the EECAD legacy contract, funded by the VERITAS programme, proved useful in the monitoring and verification of ODA activities within Ukraine, as well as monitoring for instances of fraud and safeguarding.

## C. DETAILED OUTPUT SCORING

Output Title	BEK has a higher level of assurance on programme delivery, improved compliance and risk management
Output number:		1	Output Score:	B
Impact weighting (%):		100%	Weighting revised since last AR?	N/A – first AR

Indicator(s)	Milestone(s) for this review	Progress
Subcontractor for VERITAS is selected and onboarded	Subcontractor in place	B: Below expectation. / On track for commercial supplier to be onboard by January
Number of programme-specific TPM rounds completed on time (both ISF and baseline)	1 (VERITAS funding via EECAD MERL contract)	A: As expected. / 1 round.
Number of partner-specific TPM reports prepared	3 (HARP)	A: As expected. / 3 partner-specific reports
Number of overall synthesis reports prepared.	1 (HARP)	B: Below expectation. / This was not produced.
Number of programme-specific TPM briefings delivered to implementing partners and BEK teams	4 (HARP: 1 to FCDO and 3 to partners)	B: Below expectation. / 3 briefings delivered or planned.

Briefly describe the output’s activities and provide supporting narrative for the score.

For this mobilisation year, output 1 reflects both progress towards mobilising the dedicated commercial supplier for VERITAS, and TPM activity in Ukraine funded by the VERITAS programme and delivered through an existing Monitoring, Evaluation, Results and Learning (MREL) contract held by the FCDO’s Eastern Europe and Central Asia Directorate (EECAD).

Indicator 1: At the time of this Annual Review the commercial tender for the VERITAS supplier has closed but the contract has not yet been awarded. The best-case timeline is that activity will begin in January 2026.

Indicator 2: A round of TPM for the Humanitarian Assistance, Recovery and Protection Programme (HARP)[2] was funded by VERITAS through the EECAD contract led by Ecorys. This is known as Ukraine TPM Round 6. Previous rounds were funded directly by the programmes in question.
[2] DevTracker Programme GB-GOV-1-400176

Indicator 3: Round 6 monitored the quality and effectiveness of three projects in the HARP programme, as summarised below. In each case a partner specific report was produced:

the HAVEN project aims to strengthen humanitarian and civilian response structures in frontline territories to provide sustained services to war-affected communities and is delivered by a large consortium. FCDO funding to date exceeds £20m.

Project activities under an agreement with UNHCR, with a focus on winter cash assistance, shelter and housing (including emergency repairs and materials such as insulation and windows). FCDO contributed over £11.3m to UNHCR programming.

the £5m project Ukraine Winter Response for Vulnerable Families with Children, implemented by UNICEF, which focussed on heating, water, sanitation and hygiene for conflict affected civilians.
The customers for these monitoring exercises – the FCDO programme teams - were satisfied with the efficiency of the process, the timeliness of the reports and the clarity with which they were written, and the responsiveness of the supplier. In cases of poor clarity or differing expectations on output, programme managers were satisfied with the receptiveness of the supplier to design edits. Overall, the exercise provided additional assurance that UK ODA was used as intended. Some common themes were noted for future consideration.

Timing played a part. When data collection was conducted months after activities were completed (as was the case for UNHCR and UNICEF), this negatively affected the recall of some participants and also removed the opportunity to use TPM findings to directly improve project implementation in the short term.

Security concerns made it difficult to achieve a representative sample. This was compounded by issues with data sharing protocols (in the case of UNICEF) and mismatched expectations about independent data collection (in the case of UNHCR).

The customers also reported that the TPM instruments appeared designed for mainstream humanitarian aid distribution. Time and resources did not allow for more specific tailoring and this in turn led to missed opportunities to provide more actionable and specific recommendations for FCDO and partners.

Indicator 4: Lessons from Rounds 1 to 5 of FCDO’s third-party monitoring in Kyiv were formally documented in two synthesis reports. The first documented lessons about the projects and programmes reviewed, and the second documented lessons for how to conduct TPM. BEK decided that the marginal additional of a further synthesis report after Round 6 did not represent value for money.

Indicator 5: There is qualitative evidence that TPM findings and recommendations are explicitly used to inform FCDO’s management of its partners. Briefings were held with FCDO and multiple partners, as well as stakeholders across HMG. For example, TPM findings have played a clear role in strengthening FCDO assurance measures, most notably in relation to safeguarding and aid diversion, where it has been instrumental in strategic enforcement of systemic controls and due diligence frameworks to ensure comprehensive oversight leading to increased levels of compliance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

These indicators relate to the mobilisation phase of the programme, and a set of activities under the Ecorys contract. The new supplier will develop during their inception phase a results framework to better capture the quality and timeliness of TPM services, and how recommendations are used. This will be informed by the lessons we have learnt from previous delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

A key lesson learned for the VERITAS programme relates to the timeline for the procurement of the critical supplier. The expectation that the tender for a commercial supplier would be issued within the Commercial Pillar’s aim of 100 days to contract for open-tender-contracts proved to be overly ambitious, with unforeseen delays arising that were outside BEK’s, and in some cases, the FCDO’s control. This highlights the importance of building realistic procurement timelines into programme planning, factoring in the potential for procedural or external setbacks wherever possible.

Recommendation 1: The lessons from the procurement process (what caused the delays, their impact, and how they were navigated) should be documented thoroughly and shared with other relevant FCDO teams. [FCDO Lead MEL Adviser, by March 2026].

Lessons from the Rounds 1 to 5 of FCDO’s third part monitoring in Kyiv were formally documented in a Synthesis Report. In brief, these lessons are:

- Identification of and engagement with partners. Close involvement between FCDO and partners is essential.
- Design of fieldwork: Developing a tailored, partner focussed TPM approach is key.
- Fieldwork: Ecorys’ Ukrainian local partner, Kyiv International Institute of Sociology (KIIS), provided a robust network of Ukrainian enumerators across the country.
- Analysis and reporting: Triangulation of methods and sources contributes to a versatile TPM approach and high-quality findings.
- Dissemination: Engaging dissemination targeted at the selected audiences is one of the elements holding the greatest potential.
They remain relevant and are consistent with the experience of Round 6, described above, and are already informing Round 7. Annex B gives more detail on the lessons and how they have already informed the terms of reference for the new VERITAS supplier.

Recommendation 2: These insights have proven critical in ensuring effective third-party monitoring and should be shared proactively with the new VERITAS supplier to inform their approach and maximise programme impact. [FCDO Lead MEL Adviser, January 2026]

VERITAS is designed with two additional outputs which for the mobilisation year are weighted zero and not reviewed.

Output Title	BEK pilots the use of CSO-led TPM to improve transparency of its portfolio and develop innovative, locally led approaches to conducting TPM
Output number:		2	Output Score:	N/A
Impact weighting (%):		0%	Weighting revised since last AR?	N/A – first AR

Output Title	BEK uses research to develop increased understanding of programme operations and Ukrainian citizen needs on the ground
Output number:		3	Output Score:	N/A
Impact weighting (%):		0%	Weighting revised since last AR?	N/A – first AR

## D: VALUE FOR MONEY (1 page)

VfM proposition

This programme delivers value for money by providing independent, credible evidence of programme performance in hard-to-reach areas where direct monitoring is not feasible, thereby enhancing assurance of BEK programming on accountability, effectiveness, and equity across humanitarian and recovery interventions.

Individual BEK programmes remain responsible for ensuring sufficient monitoring in place to provide performance oversight and support decision making (PrOF Rule 19[3]). VERITAS delivers better Value for Money than alternative options for achieving this purpose.
[3] FCDO Programme Operating Framework: overview - GOV.UK

As evidenced by existing Annual Reviews for BEK programmes, the complexities of accessing hard to reach areas have made evidence gathering in some key areas impossible. Implementing partners’ own systems for monitoring and reporting are necessary but do not provide sufficient assurance. Without a collective supplier, each programme would need to engage its own supplier of third-party monitoring and research services. This would create additional administrative costs, risk duplication, and miss the opportunity to generate Portfolio Evidence.

The anticipated £3m annual cost of VERITAS is 1.5% of BEK’s £200m ODA budget in 2024-25. This is in line with the average of 1-3% for TPM and research programmes in other FCDO offices operating in hard-to-reach programming contexts. Effective competition for this contract will ensure the greatest value for money in procurement.

VfM Performance and Assessment

The VERITAS Business Case uses the FCDO 5Es framework to propose actions to ensure value for money will be achieved, and indicators to measure progress. These are reproduced in full in Annex C and largely relate to the forthcoming implementation stage of the programme. This Annual Review focusses on the key VfM actions related to the mobilisation phase, designed to drive economy, effectiveness and equity, which have been undertaken as planned.

Economy: the commercial process used a competitive process, including a well-attended Early Market Engagement exercise in Kyiv.

Effectiveness: The terms of reference for the supplier drew on range of sources and expertise to ensure high quality and maximise the chances of achieving programme outcomes. These sources included quality assurance by EQUALS[4], explicit incorporation of the lessons from the EECAD and other FCDO TPM contracts, and challenge from expert advisers.
[4] EQUALS is the Evaluation Quality Assurance and Learning Service and provides independent technical quality assurance to FCDO Evaluation Quality Assurance and Learning Service (EQuALS) - IOD PARC

Effectiveness: The VERITAS programme also funds two FCDO staff roles (monitoring and evaluation experts at Grade 7 and HEO) who in line with PrOF Rule 26[5] to deliver work essential to delivery of BEK programmes that offers better value for money) than the outsourced alternative.
[5] FCDO Programme Operating Framework: overview - GOV.UK

Equity: The technical criteria for selecting a supplier placed significant weight upon inclusive data collection and research, to ensure that services delivered reflect the voices of the marginalised.
Looking ahead, the commercial supplier will propose during their inception period a more complete approach to measuring the value for money that VERITAS achieves by contributing to improvements in the effectiveness of the BEK portfolio. The approach will be quality assured and approved by BEK to ensure it will support delivery against the VfM statement, and SRO defined requirements. Measures of effectiveness will relate to the outcomes of VERITAS – improving the design and cost effectiveness of the BEK portfolio, capturing the impact of recommended improvements, and minimising fraud and safeguarding risks.

E: RISK

Overview of risk management

The programme’s risk appetite has been reviewed and continues to be in line with FCDO’s Risk Appetite Statement and as such not included in this report]. The VERITAS risk appetite is summarised in the table below. There is little scope for the programme to go above these defined risk appetites, however, if the need did arise, a sufficient governance structure is in place to seek escalation beyond the current appetites.

Risk Category	VERITAS programme level of appetite
Strategy and Context	Eager
Financial and Fiduciary	Cautious
Policy & Programme Delivery	Eager
Public Service Delivery & operations	Receptive
People	Receptive
Safeguarding	Cautious
Reputational	Cautious

During the inception phase for the dedicated VERITAS contract, these appetites will be reviewed to better reflect the state of the programme and the expected increase in activities.

The risk profile and risk exposure, and subsequent responses to risk, have remained relatively flat throughout the year. This is expected given the current activity on the programme, and the focus on mobilisation. One major risk which has required agile and pro-active responses has been delays to contracting owing to external impacts beyond the control of the programme team. The key mitigation was to extend BEK’s uses of the EECAD contract with Ecorys.

In respect of the Paris Climate Agreement, climate and environmental risks were reassessed and deemed to continue to be low. Once an inception phase is completed this risk will be reassessed as activity increases.

The implication for VERIATS of the Gender Equality Duty and Public Sector Equality Duty is outlined in the Business Case as follows:

“BEK is committed to setting a portfolio that is inclusive in meaningful ways, with a strong emphasis on targeting the most vulnerable in a genuine way and adjusting programming to meet their specific needs, all while remaining accountable to Ukrainian citizens as well. VERITAS will play an important role to support this ethos, by embedding into the TPM approach beneficiary feedback that provides vital insights from as many disaggregated groups as is feasible - alongside verifying targeting of assistance to vulnerable groups, including whether interventions and activities are disability inclusive. VERITAS-UKR will also ensure compliance with the Public Sector Equality Act 2010.

“What this means for Ukraine is to carefully manage a balanced representation of male and female monitors, given ongoing conscription and mobilisation laws that potentially prevent employment and/or deployment for TPM of male-monitors. The programme will seek to promote equality of opportunities as safely as possible in this context.”

The programme remains committed to this approach. A core assumption that gender balance could be promoted within the EECAD legacy contract field monitors did change throughout the year, given the enforcement of this contract and its design was outside the scope of the VERITAS programme management team. However, this assumed approach will continue to be embedded as far as possible into the operations of the bespoke BEK contract.

Given the status of the programme in mobilisation a programme specific Due Diligence Assessment (DDA) has not yet been required. Due Diligence for the Ecorys contract is handled and reported by EECAD.

Any information that is not suitable for publication has been recorded appropriately on AMP as part of this Annual Review.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

During the year VERITAS has funded some activity through the legacy EECAD contract with the partner Ecorys. The performance, timeliness of delivery, and the financial performance of this contract will be rightly covered under a separate Annual Review.

The process of awarding the dedicated contract for the VERITAS programme and BEK is underway[6]. Programme delivery is designed around a Core Team who lead the three main workstreams of VERITAS, plus demand-led Tasking Orders that provide the flexibility needed to respond to changes in the Ukraine context and the BEK portfolio. The tender documents detail the approach to managing delivery and financial performance, including Key Performance Indicators and quality control measures. These will be refined during inception and reported on at the next AR. As a programme team, we hope to foster an open and honest working culture founded in psychological safety to promote dialogue on risks and effective delivery.
[6] Verification and Technical Assurance Programme - Ukraine (VERITAS-UKR) - Find a Tender

VERITAS also delivers through programme funded staff, otherwise known as in-house delivery roles (as mentioned in Section D). These are roles that are essential for programme delivery, whose work would (and could) be sourced externally if not delivered in house. During the year, the programme successfully recruited two programme-funded staff, at HEO grade and Grade 7.

To date, these staff have been managed by the programme SRO and strengthened the monitoring of BEK programmes by developing and implementing tools such as a Results Tracker and Portfolio Mapping, as well as quality assuring partners’ reporting of results, third party monitoring arrangements and Annual Reviews.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
This Annual Review was led by the Monitoring, Evaluation and Learning Adviser for BEK. The process was light-touch and relied on document review and key informant interviews with BEK colleagues who use TPM products and the EECAD supplier.

A results framework monitoring plan to incorporate the TPM, CSO pilot and Portfolio Research strands of the programme will be developed by the supplier during their inception phase. An independent evaluation of VERITAS is not planned. However, ad hoc quality assurance of VERITAS products via the EQUALS service remains an option.

Evidence
Changes within the operating landscape within Ukraine have, and will continue, to fluctuate with implications for the programme, including access to programme locations in Ukraine. This provides the opportunity to apply and learn more about remote monitoring (telephone, satellite imagery) and CSO-led approaches (for which a pilot exercise is planned).

Learning
The key lessons in relation to TPM in Ukraine were synthesised, as documented in Section C.

Beyond the immediate work of the inception phase, where the VERITAS supplier will need to learn about the BEK portfolio, there are two learning priorities for the year ahead. First, to capture and share with other FCDO teams lessons and know-how from the process of mobilising the VERITAS supplier.

Second, for the BEK team to exchange knowledge with other international partners’ MEL specialists, such as the Swiss Agency for Development and Cooperation.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

Annex A: Diagram representing the theory of change.

Annex B: Lesson from previous rounds of TPM and how they informed the terms of reference for the dedicated VERITAS supplier.

Identification of and engagement with partners. Close involvement between FCDO and partners is essential to ensure the smooth implementation of TPM and to reduce the burden resulting from the time constraints and intensity of the exercise for all parties involved.

The supplier’s inception phase will be used build understanding of, and relationships with, BEK programme teams and their implementing partners. A 12-month rolling workplan will be developed to allow sufficient lead times.

Design of fieldwork: Developing a tailored, partner focussed TPM approach is considered one of the most important achievements of the TPM monitoring exercise throughout the five Rounds. The requirements for the VERITAS prioritise the ability to deploy a wide range of expertise corresponding to breadth of the BEK portfolio.

Fieldwork: Ecorys’ Ukrainian local partner, Kyiv International Institute of Sociology (KIIS), provided a robust network of Ukrainian enumerators across the country. It helped access distant and rural locations with more ease and overcome language barriers while engaging with programme participants. Our commercial requirements have emphasised a strong presence in Ukraine, including among the core team.

Analysis and reporting: Triangulation of methods and sources contributes to a versatile TPM approach and high-quality findings. The dedicated supplier is therefore to be selected based on their ability to offer a range of services, including in person fieldwork, remote monitoring (such as telephone, SMS and imagery) and compliance checks.

Dissemination: Engaging dissemination targeted at the selected audiences is one of the elements holding the greatest potential to be more developed and put to better use in future monitoring rounds. Round 6 will include partner-specific events and dissemination and uptake are a core requirement for the dedicated VERITAS supplier.

Annex C: Business Case Proposed Actions and Indicators relating to Value for Money
Actions for the Mobilisation Phase emphasised.

	Indicators	Actions to ensure value for money
Economy	Average consultancy rates & expenses / Supplier management fee	Use competitive procurement and benchmarks (with other, similarly designed TPM programmes, including within the EECAD MEL contract) at contract negotiations. At contract negotiation stage, ensure the management fee does not exceed 10%.
Efficiency	Indicators of efficient delivery mechanisms e.g. number of verifications per field visits; cost per verification; number of verifications not completed as planned; number of verification and learning reports delivered on time. / Engagement and coordination between implementing partners, FCDO and the supplier to identify areas in need of verification and to identify appropriate adaptations.	Use of digital technology where possible to save costs and improve efficiency in data collection and processing. / Use of suitable KPIs to monitor efficient delivery by suppliers. / BEK will engage and coordinate with other donors TPM to ensure lessons are shared and duplication is avoided.
Effectiveness	Feedback from users on the quality and usefulness of the reports. / Use of the outputs by BEK staff to manage risk or inform decisions; number of adaptations made in response to TPM findings	Oversight from the SRO/lead adviser, by seeking external technical challenge from EQUALS and other BEK advisers and learning lessons from other contracts. / The programme team will disseminate learning across BEK and other donors working in Ukraine. / An independent mid-term review will stress test assumptions and provide recommendations for improvements. / User engagement to ensure that the outputs meet their needs and are used.
Equity	Proportion of enumerators who are women and other marginalized groups. / Proportion of beneficiaries interviewed who are women, people living with disabilities etc.	Consider how VERITAS-UKR’s Terms of Reference (TORs) at tendering can enable opportunity for different social groups. / Ensuring TPM reports and data-collection tools include requirements to disaggregate data and/or produce analysis of inclusion issues. Specific questions will also be included in data-collection tools targeting feedback or verification of assistance to the most vulnerable. / Ensure The data quality assessments include requirements to assess inclusiveness of MEL partner systems.
Cost Effectiveness	Assessing the cost of delivering outputs which have informed programme decisions or risk management.	Ensure ToRs clearly articulate that the aim of VERITAS-UKR is to: improve the quality and VfM of BEK’s portfolio; and to meet the requirement to have sufficient monitoring in place to provide performance oversight, manage risks and support decision-making at all appropriate levels.