## Logframe
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
IDA21 | Milestones are for World Bank Financial Years which run from 1 July to 30 June
IMPACT | Impact Indicator 1 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28 | Note that there would be a data lag of around 2/3 years for the data on the scorecard for our impact and outcome indicators. We will work with the Bank for the latest posible data and this is also expected to be improved as the WBG CSC becomes more mature in its operation. We will continue to assess the situation and might update these indicators in later version of the logframe.
IDA contributes to global poverty reduction, shared prosperity, sustainable growth and emissions reduction | Percentage of global population living in poverty at $3/day and at $8.3/day | Planned |  | Reducing | Reducing | Reducing
|  | Achieved | 35%/84.8% (2024)
Source
World Bank Corporate Scorecard (IDA filter on)
| Impact Indicator 2 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Global average income shortfall from a prosperity standard of $28/day [The average factor by which individuals’ income or consumption needs to be multiplied to bring everyone to the prosperity standard of $28 per day as expressed in 2021 PPPs] | Planned |  | Reducing | Reducing | Reducing
|  | Achieved | 10 (2024)
Source
World Bank Corporate Scorecard
| Impact Indicator 3 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Global greenhouse gas emissions (including removals) (Gigatons of CO2 equivalent) | Planned |  | Reducing | Reducing | Reducing
|  | Achieved | N/A
Source
World Bank Corporate Scorecard
OUTCOME | Outcome Indicator 1 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28 | Assumptions
IDA21 countries make progress on long term sustainable development goals | Percentage of population in fragile and conflict affected countries living in extreme poverty | Planned |  | Reducing | Reducing | Reducing
|  | Achieved | 47.2% (2024)
Source
World Bank Corporate Scorecard
| Outcome Indicator 2 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Percentage of Children under five stunted | Planned |  | Decreasing | Decreasing | Decreasing
|  | Achieved | 31.4% (2024)
Source
World Bank Corporate Scorecard
| Outcome Indicator 3 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Percentage of wage and salaried workers, (% total employment and % female employment) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 28.2%, 19.9% (2023)
Source
World Bank Corporate Scorecard
| Outcome Indicator 4 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Percentage of youth not in education, employment, or training (female % only) | Planned |  | Decreasing | Decreasing | Decreasing
|  | Achieved | 35.4% (2024)
Source
World Bank Corporate Scorecard
| Outcome Indicator 5 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Percentage of population with acces to electricity | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 67.5% (2023)
Source
World Bank Corporate Scorecard
Outputs are from World Bank CSC
OUTPUT 1 | Output Indicator 1.1 |  | Baseline - FY25 | FY26 | FY27 | FY28 | Assumptions
Delivering IDA in FCS countries on key development aspects, including climate, jobs, health serivces, investment, and ensuring the Bank is providing sufficent resources in FCS countries. | Total private capital moblised | Planned |  | 10.4B | Increasing | Increasing
Achieved
Source
World Bank Corporate Scorecard (With FCS filter)
| Output Indicator 1.2 |  | Baseline - FY25 | FY26 | FY27 | FY28
| New or better jobs (% total, % female, % youth) | Planned |  | Increasing, increasing, increasing | Increasing, increasing, increasing | Increasing, increasing, increasing
Achieved
Source
World Bank Corporate Scorecard (With FCS filter)
| Output Indicator 1.3 |  | Baseline - FY25 | FY26 | FY27 | FY28
| IDA Commitment to FCS countries (USD million) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 14500
Source
World Bank Annual Report
| Output Indicator 1.4 |  | Baseline - FY25 | FY26 | FY27 | FY28
| FCS facetime index (Index/number of days) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 1/183,968
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
| Output Indicator 1.5 |  | Baseline - FY25 | FY26 | FY27 | FY28
| People receiving quality health, nutrition, and population services | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 225.4m
Source
World Bank Corporate Scorecard (With FCS filter)
| Output Indicator 1.6 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Percentage of FCS countries with strategic objectives reflecting how the WBG programme will help addressing FCS drivers and sources of resilience based on Risk and Resilience Assessment or other FCS diagnostics. | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 50%
Source
IDA21 Policy Commitment no.14 CPFs/CENs for IDA FCS and FCS Envelope countries will have strategic objectives that reflect how the WBG program, in collaboration with relevant partners, will help address FCS drivers and sources of resilience based on Risk and Resilience Assessments (RRAs) or other FCS diagnostics
| Output Indicator 1.7 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Beneficiaries with enhanced resilience to climate risks | Planned |  | 208.4m | Increasing | Increasing
|  | Achieved | 104m
Source
World Bank Corporate Scorecard (With FCS filter)
IMPACT WEIGHTING (%) | Output Indicator 1.8 |  | Baseline - FY25 | FY26 | FY27 | FY28
25% | Benwficiaries of social safety net programmes in FCS countries | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 59.9m
Source
World Bank Corporate Scorecard (With FCS filter)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline - FY25 | FY26 | FY27 | FY28 | Assumptions
IDA supports climate adaptation and resilience and crisis preparedness and response in IDA countries. | Percentage of IBRD projects with Climate Co-Benefits (agreed target at 45%) | Planned |  | >45% | >45% | >45%
|  | Achieved | 42%
Source
World Bank Climate Finance Fiscal Year Snapshot, also IDA21 policy commitment No.9
| Output Indicator 2.2 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Net GHG Emissions impact from IDA operations per year (Megatons of CO2 equivalent/year) (negative means a net reduction, positive means a net increment) | Planned |  | Net Reduction | Net Reduction | Net Reduction
Achieved
Source
World Bank Corporate Scorecard
| Output Indicator 2.3 |  | Baseline - FY25 | FY26 | FY27 | FY28
| GW of renewable energy capacity enabled | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 4.8GW
Source
World Bank Corporate Scorecard
| Output Indicator 2.4 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Beneficiaries with enhanced resilience to climate risks | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 104m
Source
World Bank Corporate Scorecard
| Output Indicator 2.5 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Support at least 50 countries on adaptation and resilience policies and/or climate preparedness interventions. | Planned |  | 16 | 33 | 50
Achieved
Source
IDA21 Policy Commitment no.16 Support at least 50 countries on adaptation and resilience policies and/or climate preparedness interventions. This support will be reflected in relevant new Country Partnership Frameworks and informed by Country Climate and Development Reports (CCDRs) in alignment with Nationally Determined Contributions (NDCs), Long-Term Strategies (LTS) and National Adaptation Plans (NAPs).
| Output Indicator 2.6 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Hectares of terrestrial and aquatic areas under enhanced conservation/management | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 39.3m
Source
World Bank Corporate Scorecard
IMPACT WEIGHTING (%) | Output Indicator 2.7 |  | Baseline - FY25 | FY26 | FY27 | FY28
25% | Investment in nature in support of the Kunming-Montreal Global Biodiversity Framework | Planned
Achieved
Source
IDA21 MTR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline - FY25 | FY26 | FY27 | FY28 | Assumptions
IDA supports evidence based policy making, job creation, and economic development | New or Better Jobs (% Total) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | N/A (new indicator)
Source
World Bank Corporate Scorecard
| Output Indicator 3.2 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Total private capital mobilised | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | N/A (new indicator)
Source
World Bank Corporate Scorecard
| Output Indicator 3.3 |  | Baseline - FY25 | FY26 | FY27 | FY28
| Private capital enabeld | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | N/A (new indicator)
Source
World Bank Corporate Scorecard
| Output Indicator 3.4 |  | Baseline - FY25 | FY26 | FY27 | FY28
| People and business using financial services (% total) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 44.4m
Source
World Bank Corporate Scorecard
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline - FY25 | FY26 | FY27 | FY28 |  | Moved down from the FCS output.
15% | IDA Private Sector Window utilisation rate (utilised/allocated) | Planned |  | Increasing | Increasing | Increasing
Achieved
Source
IDA Management's Discussion and Analysis
OUTPUT 4 | Output Indicator 4.1 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28 | Assumptions
IDA supports progress being made in gender equality, including in areas covering health, education, and economic development | Millions of new or better jobs, - of which (%) for women | Planned |  | Increasing | Increasing | Increasing | Indicator 4.6 - the target is 250m by FY30. The target was announced in FY24, hence the targets are divided linearly across the years.
|  | Achieved | N/A (New indicator)
Source
World Bank Corporate Scorecard
| Output Indicator 4.2 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Number of countries addressing Sexual and Reproductive Health | Planned |  | 11 | 23 | 35
|  | Achieved | N/A
Source
IDA Policy Commitment No.11 Implement the WBG Gender Strategy in all IDA countries with an emphasis on Gender-Based Violence, Economic Participation, and Sexual and Reproductive Health (SRH). SRH will be addressed through WBG interventions in 35 countries.
| Output Indicator 4.3 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| Students supported with better education | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 100.8m
Source
World Bank Corporate Scorecard (With female filter on)
| Output Indicator 4.4 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| People receiving quality health, nutirition, and population services | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 225.4m
Source
World Bank Corporate Scorecard (With female filter on)
| Output Indicator 4.5 |  | Baseline - Mid FY 24 (to be updated to end FY24 once data is available) | FY26 | FY27 | FY28
| People benefiting from actions to advance gender equality, and the number of actions that expand and enable economic opportunities | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 191.8m
Source
World Bank Corporate Scorecard
IMPACT WEIGHTING (%) | Output Indicator 4.6 |  | FY25 | FY26 | FY27 | FY28
15% | Female beneficiaries of Social Security Netowrk Programme (cumulative) | Planned | 71.4 | 107.1 | 142.9 | 178.6
Achieved
Source
World Bank Operations Update
OUTPUT 5 | Output Indicator 5.1 |  | FY25 | FY26 | FY27 | FY28 | Assumptions
IDA is efficient, financially sustainable and effective | IDA Budget Anchor (%, expenses over loan revenue) | Planned |  | <=100 | <=100 | <=100 | Indicator 5.2, 5.3 and 5.4 - it combines IBRD and IDA as one collective disbursement ratio for FY25 data. Indicator 5.5 - IDA/IBRD/IFC for 5.5. However, after internal discussion, it was agreed to use this as a proxy indicator for tracking IDA's engagement with other institutions.
|  | Achieved | 67%
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
| Output Indicator 5.2 |  | FY25 | FY26 | FY27 | FY28
| IDA Disbursement Ratio (%) | Planned |  | 20% | 20% | 20%
|  | Achieved | 24%
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
| Output Indicator 5.3 |  | FY25 | FY26 | FY27 | FY28
| IDA preparation time from AIS to approval | Planned |  | Decreasing | Decreasing | Decreasing
|  | Achieved | 12.8
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
| Output Indicator 5.4 |  | FY25 | FY26 | FY27 | FY28
| IDA satisfactory outcome of World Bank operations | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 85%
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
IMPACT WEIGHTING (%) | Output Indicator 5.5 |  | FY25 | FY26 | FY27 | FY28
20% | $ Mobilised through co-financing (US $billions, 3-year rolling average) | Planned |  | Increasing | Increasing | Increasing
|  | Achieved | 3.78
Source
World Bank Group Operational Effectiveness and Efficiency Dashboard
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What priority did this outcome match onto? I'm assuming this is the main outcome for gender? I would have also thought that we would want this to be decreasing not increasing.

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10