## Annual Review – Governance Reform Programme

Title: Governance Reform Programme (GRP)
Programme Value £ (full life): up to £38m		Review date: 23/12/2025
Programme Code: 400398	AMP start date: January 2025	AMP end date: / June 2028

Summary of Programme Performance
Year	2026
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400398/documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The Governance Reform Programme (GRP) was launched in January 2025 to provide Technical Assistance and other support to Ukraine’s reform pathway, which is crucial for its wider Euro-Atlantic integration. It specifically focuses on advancing reform in two complex areas: anti-corruption (which includes modernising government services through digitalisation) and rule of law. It also aims to embed political economy analysis (PEA) across HMG’s portfolio through the establishment of a PEA research centre.

In January 2025 the programme set out to:
- Advance rule of law reform through collaboration with IDLO.
- Strengthen anti-corruption efforts by working in partnership with USAID on the flagship Pro-Integrity programme implemented by DAI.
- Continue our longstanding partnership with USAID on digital transformation, which started in 2016, by co-funding the next iteration of the well-known Transparency and Accountability in Public Administration and Services (TAPAS) Programme: USAID’s Digital Transformation Activity led by the Eurasia Foundation.
- Launch a competitive tender to establish a Political Economy Analysis (PEA) Research Centre.

However, USAID’s withdrawal at the start of the year required the programme to rapidly pivot its focus (details provided below). To address critical gaps left by reduced funding a bridging programme was introduced, enabling the UK to maintain support in priority areas.

This review will therefore concentrate on the components delivered in FY 2025/26:
- IDLO’s work on rule of law reform (£1.5m), and
- Eurasia Foundation’s work to sustain digitalisation efforts (£8.9m)
Due to the pivot, the substantial anti-corruption component and PEA component were not progressed.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Despite the highly challenging context, the programme met expectations. USAID’s withdrawal created significant gaps in support to Ukraine’s governance landscape. This had a major impact on GRP, resulting in the termination of two flagship components: anti-corruption and digitalisation. In response, the Governance Team undertook a rapid process to identify the Government of Ukraine’s most urgent needs in a fast-changing landscape and determine where UK support could be most effective, both through GRP and the ongoing Good Governance Fund.

Though GRP did not achieve what it had initially hoped to achieve, the establishment of DIGIT – which picked up work on digitalisation and anti-corruption – meant the programme was able to deliver results despite the drastically changed environment. In addition, the work on rule of law made good progress. Feedback from partners praised the UK for the efficient response, reaction, and reprioritisation of our support through GRP following these events. The programme therefore helped to bolster the UK’s reputation in Ukraine as a trusted partner that delivers.

It is important that this programme continues to fill critical gaps, encourage reform, and strengthen the existing – strong – reputation the UK has built in this space.

Major lessons and recommendations for the year ahead [1/2 page]
One of the main lessons for the programme team is the importance of real time updates to the logframe and indicators, and a record of the changes. Despite the amount of change in the context this year GRP delivered a huge amount, but the logframe did not keep up which makes it more challenging to measure that success at review points.

Key lessons from the past year include:

1. Flexibility and responsiveness: The context is shifting rapidly – progress should not be taken for granted, rollback can occur, and the programme should be able to adapt to these changes and respond to windows of opportunity when they arise. One of the most positive feedback points was the rapid pivot following USAID’s withdrawal. This ability to adapt must remain a core feature of GRP programming.
2. Strategic focus: The UK is now the second largest donor working on governance reform in Ukraine and has the potential to be hugely influential. But with less money available for implementing reforms, donors are not going to be able to meet every request. GRP should prioritise and target areas where the UK can deliver meaningful results, supported by UK political priorities.
3. Short-termism has a cost: Abrupt changes in donor funding and programme structures can disrupt institutional memory, delay activities, and undermine trust built between technical experts and government counterparts. Though the bridging programme was necessary, the programme should look to provide implementing partners more certainty over future direction and budgets for the remaining lifecycle of the programme.
Recommendations for the year ahead:
1. Use Q1 (January to March 2026) to make decisions on GRP’s core components
With no FY2026/27 commitments, the Programme Team should use the start of the year and reflections from the past year to define GRP’s future shape, to transition the programme from short-term bridging arrangements to longer-term partnerships with predictable funding.
- Development Director to take final decisions on the future of anti-corruption, rule of law and digitalisation work in Q1 2026 once presented with options from the SRO.
- Team Leader to decide on the shape of UK support to the emerging opportunity to support the design and delivery of a Delivery Unit for the Prime Minister’s Office in Q1 2026.
- PRO to develop a delivery plan for mobilising and delivering in the final 2.5 years in Q1 2026.
2. Align activities to Ukraine’s most pressing needs and coordinate closely with other international partners
GRP interventions should address critical gaps and be strategic by focusing on areas where UK engagement adds clear value, in spaces where other donors are engaging less.
SRO, with PRO and team, to ensure future activity focuses on areas where UK engagement adds clear value, that help Ukraine win the war (where possible) and secure its future as a democratic, open, society. This should involve the development of a supporting narrative by end of Q2.
3. Ensure strategic alignment with EU governance reform efforts
GRP should complement and reinforce EU-led governance reforms, and the UK should explore opportunities for joint programming to maximise impact.
SRO to coordinate agreement on an approach to working with the EU on governance reform in Ukraine with sign off from the Development Director in Q1 2026.
5. Restart Political Economy Analysis (PEA) work
PRO to restart the tender in Q1 2026, aiming for supplier mobilisation and delivery by summer.
6. Ensure all programme management and compliance reflects these changes
As new components are initiated the programme team should ensure full compliance with legal, transparency, risk management and performance requirements.
- In Q1 2026, PRO to conduct a comprehensive review and update of the theory of change, log frame and risk register to reflect revised components – as both our, and partners, capacity and funding has changed.
- PRO to include 1-2 indicators from our funding of Wilton Park and secondees to the OECD and Ukraine Donor Platform to capture their contributions.
- PRO to undertake a comprehensive review of the VFM of the GRP and update the Dec Director in Q1 with recommendations for practical steps that can be taken to track and improve VFM in future programming.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
The BC summarises the theory as: IF GoU better harnesses digital opportunities to deliver higher quality services and prevent corruption AND Ukraine’s institutional anti-corruption capabilities are strengthened at the national and sub-national levels AND Ukraine has improved judicial reform legislation and strengthened rule of law AND the UK is better able to track and influence reform conversations THEN in the long-term Ukraine will be further along its Euro-Atlantic Integration, with reduced corruption and improved rules-based systems that deliver for Ukrainian people and business.

This theory of change remains relevant for the next year of programming. Once decisions have been taken on future components, it will need to be updated.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
The programme remains broadly on track toward its intended outcomes of strengthening governance and judicial integrity, despite a challenging political and security environment.
- Digital transformation: on track. Major milestones have been achieved, for example DREAM has become fully institutionalised in Ukraine’s Public Administration System and a Minimum Viable Product was launched for Ukraine’s eExcise system, which will help the Government to collect more revenue from goods such as alcohol and tobacco. The team need to make some early decisions on how digitalisation work continues.
- Anti-corruption: off track. DIGIT was able to pick up some anti-corruption pieces, for example conducted thematic research into anti-corruption risks in support of the National Agency for Corruption Prevention’s (NACP) new anti-corruption strategy, as well as delivering the much-awaited Transparency Register, which will collect and publish data on individuals engaging in lobbying, thereby helping to discourage hidden influence. But the approach was far from the scale we were hoping to achieve under Pro-Integrity. We still have no standalone anti-corruption programming in place and a priority for the year ahead is getting this set up.
- Judicial: On track. On Rule of Law, IDLO supported the Service of Disciplinary Inspectors to review and clear a backlog of 9,000 complaints, ensuring judges are held accountable under the law and helping to meet targets set by the Ukraine Facility.
- PEA: PEA research centre is off track following the decision to pause.
- Other small components were successful including holding Wilton Park conference and overseeing the secondments to the OECD and Ukraine Donor Platform.
The Outcome on anti-corruption is the most off track – until programming decisions are made, the UK is providing little support to strengthen anti-corruption capabilities at national and sub-national level. Without a functional PEA Research Centre, we are also missing an opportunity to strengthen our ability to track and influence reform conversations.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
This programme should continue. The UK has an opportunity to support Ukraine on some of the most complex areas of reform to help keep Ukraine in the war and lay the foundations for long-term stability. The programme outcomes have shown distinct progress despite the context, due to our flexible approach following the USAID withdrawal. Following rapid redistribution in this context, the programme has strong evidence of effective use of funds and maximised delivery against the outputs. The programme complements the wider British Embassy Kyiv portfolio, bridging between different sections of the embassy.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Ukraine's institutions better harness digital opportunities to deliver high quality services and prevent corruption
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1. Prozorro Market functionality updated	At least one functionality updated	Met expectations - one functionality developed (e-claims for Prozorro Market)
1.2. Increased transparency and streamlined operation of excise tax administration through the successful development of the eExcise system	eExcise developed and piloted	Met expectations - eExcise system MVP developed and piloted and at 90% full functionality
1.3. Number of new digital services launched or current services fully modernised on the Diia platform	At least 2 Diia eServices launched or modernized	Met expectations – 2 new Diia eServices were launched
1.4. Number of draft legal acts developed alongside corresponding sector-specific roadmaps targeting priority technology sectors	4	Moderately exceeded expectation - 5 legislative initiatives were drafted
1.5. Number of regulatory acts developed to enable digital traceability and align fisheries and forestry governance with EU legislation	at least 6	Met expectations - 6 regulatory acts developed (4 on fisheries and 2 on forestries). 4 adopted.
1.6. % of planning documents covered by the Urban Planning Cadaster	40%	Moderately did not meet expectation – 10%
1.7. Number of claims categories in the Register of Damage for Ukraine (RD4U) developed and added to the Diia platform	At least 6	Moderately did not meet expectation - 4 damage categories and a service for managing applications by individuals. While the original target was six categories, the scope was strategically adjusted to prioritize urgent functionality for managing applications submitted by individuals across all categories.
1.8. Number of SME representatives trained in digital skills	500, of which at least 200 are women or individuals from vulnerable groups.	Substantially exceeded expectation - 775 SME representatives were trained in digital skills, including 103 women veterans and 672 women from socially vulnerable groups.

Briefly describe the output’s activities and provide supporting narrative for the score.
The abrupt USAID withdrawal in early 2025 caused severe disruption, reducing the programme from $240m to £8.9m and forcing rapid prioritisation of critical activities. In response, the team launched UK Digitalisation for Growth, Integrity and Transparency (DIGIT) in March 2025 to sustain essential work originally planned under DTA and Pro-Integrity.

DIGIT provided comprehensive support across an impressive range of areas, and the log frame provides a partial snapshot of what was achieved. UK support through DIGIT proved decisive in sustaining momentum on revenue-generating initiatives such as the development of the minimum viable product (MVP) for the eExcise system, which could allow the Government of Ukraine to generate an additional £150mn a year in revenue. Other successes include the advancements to Ukraine’s eQueue system, where work has begun to develop the service for passenger vehicles which will combat the paying of bribes at the border. To help Ukraine’s economic modernisation, DIGIT supported digital deregulation in key sectors, including agriculture and natural resource management. It also focused on inclusive digital training and workforce development, exceeding the number of business representatives trained in digital skills.

There were two areas targets were not met: the % of planning documents covered by the Urban Planning Cadaster and the number of claim categories developed for the Register of Damage for Ukraine. The former was delayed due to the delayed rollout of necessary software and unclear accountability between local authorities. And the latter was slowed by institutional uncertainty and uneven local capacity, compounded by power outages. Progress on the draft law for customs clearance remains slow, creating uncertainty for related digital reforms, and leadership changes have delayed eConstruction, requiring renewed engagement to maintain momentum. Other delivery risks relate to the funding reductions, staff retention and institutional capacity constraints in the Ministry for Digital Transformation.

Overall DIGIT has been extremely positively reviewed by the Ministry of Digital Transformation and key stakeholders, including in DPM Fedorov’s office who outlined UK support as ‘timely and crucial’.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
The transition from the US-UK jointly funded programme to DIGIT has brought substantial changes. As Eurasia Foundation noted, ‘the ground continues to shift’ reflecting the dynamic operating environment. The BEK team was required to drop several outputs due to significant downsizing, including eGambling, broader work on eForest and eFish (forestry and fisheries regulation), and wider Diia support. Looking ahead, we are assessing the shape and scope of our work on digitalisation, ensuring continued impact and alignment with Ukraine’s reform priorities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
There are no previous recommendations given this is the first year. The team should carefully consider how the embassy supports the Ministry of Digital Transformation in such a crucial time of need and maintain a remit of digital work that fits within the reform focus of GRP.

Output Title	Digital Restoration EcoSystem for Accountable Management (DREAM) are active, integrated into GoU plans and providing a holistic, data-driven approach to reconstruction oversight.
Output number:		2	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
% state-level projects and programs (for non-CNI) requiring or receiving state budget funding managed and reported through the DREAM platform	100%	Met expectation - 100%
Institutionalisation of DREAM as Ukraine’s Public Investment Management (PIM) system in accordance with the 2025 Budget Code legislation	DREAM is formally institutionalised	Met expectation - DREAM became fully institutionalised
DREAM PIM minimum viable product tested and implemented, supported by extensive documentation and user training for government and community users.	DREAM PIM tested and implemented	Met expectation - All PIPs and programmes for the 2026 Single Project Portfolio submitted, evaluated, and approved exclusively through the platform.
A questionnaire on Gender Equality, Disability and Social Inclusion (GEDSI) principles mainstreaming into public investment projects is integrated into the project submission flow in the DREAM system.	GEDSI questionnaire integrated into DREAM	Exceeded expectations – gender equality and human rights principles integrated into DREAM

Briefly describe the output’s activities and provide supporting narrative for the score.
DREAM (Digital Restoration Ecosystem for Accountable Management) consolidates public investment and reconstruction data into a single, accessible system, embedding transparency and enabling evidence-based decision-making across all stages of project implementation. The UK has been a committed partner since DREAM’s inception, when it was a civil society-led concept, and has supported its evolution into a fully institutionalised government delivery mechanism. Today, DREAM is transforming Ukraine’s reconstruction process by rebuilding trust between citizens and the state, a cornerstone for long-term recovery and democratic resilience.

By December 2025, Output 2, delivered by the Open Contracting Partnership, achieved strong results. DREAM is now Ukraine’s mandatory public investment management system, with 100% coverage of state-level projects and compliance embedded in the Budget Code. The Minimum Viable Product for Public Investment Management (PIM) was successfully tested and implemented, supported by upgraded functionality and institutionalised training through the DREAM Academy. In line with commitments to gender equality and human rights, gender and human rights principles were integrated at the project design stage, enabling ministries and local governments to self-assess alignment with SDGs, ESG criteria, and gender-responsive planning practices.

Implementation did face some bureaucratic hurdles, particularly due to challenges in decentralisation reform: the Ministry of Finance budget to hromadas reduced from UAH 50bn to UAH 2bn and they kept complicated requirements in place for small hromadas. However, learning is happening and the team are confident this will lead to improvements going forward.

These achievements have secured DREAM’s role as the single digital system for transparent, rule-based reconstruction planning, meeting expectations for this reporting period. Implementers noted challenges, including funding constraints that have placed some areas on hold. Looking ahead, priorities include simplifying requirements for hromadas and reinforcing political coordination to sustain momentum and ensure continued progress.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There were no significant changes made to this output over the past year. Looking ahead, following consultations with the Recovery and Economic Growth (REG) team in BEK, a strategic decision has been made to transfer DREAM to the FIRE programme starting April 2026. This shift reflects its strong reconstruction and public investment management focus and will ensure better contextual alignment for future delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
As stated above, the plan from the start of 2026 is to gradually transition DREAM to FIRE and support both DREAM and REG teams in the process.

Output Title	More transparent, accountable, and corruption-resistant GoU strengthened through institutional reforms.
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1. Anti-corruption programming plans beyond September 2025 are finalised, agreed and successfully mobilised, with a clear rationale for decisions and priorities, close	Multiyear programme in place and meets parameters outlined in the indicator.	Partially met expectations - Programming has been extended up to March 2026 and being scoped further at this moment
3.2. Transparency Registry is developed and transferred to the NACP	Transparency Registry is developed and transferred to the NACP	Met expectations – Transparency Registry developed
3.3. Number of anti-corruption strategy research pieces completed	6	Moderately exceeded expectations - 7 pieces of research completed
3.4. Recommendations on GESI developed to inform anti-corruption activities	5 by March 2026	Deadline not reached yet.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focused on supporting critical pieces of work initiated by Pro-Integrity in support of the NACP and progress against indicators reflects strong delivery overall. A major achievement was the successful development and operationalisation of the National Agency for Corruption Prevention’s (NACP) Transparency Registry. The registry has already registered 122 lobbying entities toward a target of 150 and attracts approximately 115,000 monthly views, significantly enhancing transparency and public oversight of lobbying activities.

DIGIT also supported the NACP in drafting the next phase of the National Anti-Corruption Strategy through seven in-depth research pieces covering eight thematic areas, including prosecution, law enforcement, customs, construction, and healthcare. Three pieces have been finalised following public consultations, with the remaining four undergoing revisions. This work exceeded expectations by delivering more thematic coverage than planned. On gender equality and social inclusion (GESI), recommendations are in development to inform anti-corruption activities, with delivery expected by March 2026.

On the first indicator – programming plans beyond September 2025 - the team has engaged in extensive consultations with government stakeholders, donors, and implementing partners to define priorities and options for a multi-year programme. Options have been developed but final decisions are still needed before new programming can be mobilised.

Overall, this output met or exceeded expectations on most indicators, demonstrating successful work to strengthen a critical part of NACP's work.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
The ambition under this output was scaled back this year following the closure of the Pro-Integrity Programme, which had aimed to work beyond anti-corruption agencies to engage multiple ministries and deliver comprehensive regional support for local administrations preparing for reconstruction. After a year of mobilisation, Pro-Integrity was positioned to deliver at scale, so the log frame was significantly altered to respond to this change. The updated activities and the log frame were adjusted to reflect the new political and operational context and include the anti-corruption work successfully delivered through DIGIT. Looking ahead, once decisions are finalised on the UK’s future contribution to anti-corruption efforts, outputs will be updated to reflect the revised scope and strategic direction.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Over the past year, Ukraine has faced significant anti-corruption challenges, including attempts to dismantle key institutions such as NABU and SAPO, and the emergence of a major energy-related scandal. “Operation Midas” - the most significant scandal since Russia’s full-scale invasion. These developments underscore two critical realities: first, the persistent need to strengthen anti-corruption efforts; and second, the resilience and progress that remain possible thanks to the strong public demand for accountability and the continued effectiveness of Ukraine’s anti-corruption institutions. With reduced donors in this space, it is more important than ever for the UK to maintain its engagement. There is still substantial work to be done, and the UK is well positioned to contribute meaningfully. The key challenge will be identifying areas of engagement that leverage the UK’s unique strengths while remaining proportionate to our available capacity and resources. The UK should also consider whether they should play a greater role in coordinating other donors on anti-corruption going forward.

Output Title	A transparent, merit-based, and institutionally supported judicial selection and qualification assessment system established to enhance integrity and efficiency in the judiciary, with positive implications for public trust and confidence.
Output number:		4	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
4.1. Personal integrity profiles concerning 100% of the judgeship candidates that reach the SJM stage are produced by the PCIE Secretariat and submitted to the PCIE	50%	Substantially exceeded expectations - 72%
4.2. % of pending (older) complaints of the existed backlog are reviewed by SDI	50 %	Moderately did not meet expectation - 44%
4.3. % of complaints deemed eligible and transferred to HCJ for which SDI inspectors produce draft decisions.	40%	Data is pending
4.4. % of the cases (complaints) presented by SDI inspectors are considered by the HCJ disciplinary chambers.	30%	Data is pending
4.5. Number of judges and judgeship candidates' profiles reviewed by the new composition of PIC	200	Exceeded expectations - 211

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 demonstrated good progress against its milestones, though data is still pending for two of the indicators.

On the first indicator, the Public Council of International Experts (PCIE) Secretariat, with support from IDLO, substantially exceeded expectations by producing integrity profiles for 72% of candidates reaching the practical assignment stage of the High Anti-Corruption Court (HACC) competition. This achievement ensures readiness for PCIE interviews scheduled for February 2026. The work directly supports merit-based judicial selection, a critical EU conditionality under the Facility Plan.

Although the target set for the review of backlogged complaints by the Service of Disciplinary Inspectors (SDI) was moderately below target (44% vs. 50%), performance should be viewed in context. The SDI processed over 9,000 complaints in 2025, balancing backlog reduction with new cases to prevent future accumulation. This approach was widely endorsed by stakeholders and exceeded the EU-Ukraine Facility benchmark (20%) by more than twofold.

Unfortunately, data for indicators 4.3 and 4.4 is pending due to internal reporting cycles. But preliminary evidence suggests progress is on track, with systemic improvements in disciplinary case handling expected to materialise in early 2026.

For indicator 4.5, the number of profiles reviewed by the Public Integrity Council, the new composition of the Public Integrity Council (PIC) exceeded expectations by reviewing 211 profiles against a target of 200. This was enabled by rapid donor mobilisation from the UK and institutional support, which ensured PIC’s operational continuity and improved performance compared to previous years.

Beyond the results captured in the log frame, Output 4 delivered systemic reforms acknowledged in the European Commission’s 2024 Enlargement Report (Chapters 23 and 24). Key contributions include:
- Establishing the SDI within the High Council of Justice to address a backlog of over 10,000 complaints.
- Supporting PIC’s reconstitution and operationalisation, introducing KPIs for members, and enhancing integrity oversight.
- Advancing competitions for judicial and leadership positions, including the HACC selection process, which now attracts 3.2 candidates per position (up from 0.3 previously).

Furthermore, in the absence of donor support, IDLO stepped up to the selection processes of important government agencies undergoing reform, notably the Head of the Customs Service and Asset Recovery and Management Agency (ARMA).

These achievements collectively strengthen Ukraine’s judicial integrity architecture and governance reform more broadly and reinforce compliance with EU conditionalities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Over the past year, Output 4 has undergone several adjustments to align with evolving priorities in Ukraine’s judicial reform context. Notably, the vetting process for the High Administrative Court has been postponed to spring 2026 due to delays in the broader HQCJ process. In response, activities were reprioritised to focus on time-sensitive tasks linked to legislative requirements and EU conditionalities. These included the ARMA Head selection, the ARMA audit, and the selection of the SAPO Deputy Head, all of which became critical to maintain reform momentum and compliance with international commitments.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The work in the judicial sector this year was also impacted by USAID withdrawals, which provided a significant portion of funding in this sector. Growing interest by internationals in judicial reform in this space means the UK must remain a key actor in this space. UK programming was critical for picking up high-profile areas of work in this space. Moving into the year ahead, it is crucial that our priorities are assessed to ensure they remain critical, and in-line with existing UK strengths. The priorities currently remain relevant and very important for Ukraine’s publicly stated goals on Euro-Atlantic integration; we should be ready to flexibly respond to the various judicial appointment procedures that may require additional funding and continue our support to the key bodies responsible for the vetting of Ukrainian judges.

Output Title	Deepened UK understanding of the political economy of reform agendas in Ukraine leading to increased UK influence on reform agendas. Indicators to be updated once the contract is in place.
Output number:		5	Output Score:	C
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 PEA contract successfully tendered, procured, mobilised and initiating work	Contract in place	Substantially did not meet expectation – no supplier in place
5.2 # high-quality pieces of PEA analysis and accompanying reporting produced in line with BEK team needs and agreed requirements, and disseminated in line with agreed plans	N/A	Substantially did not meet expectation – 0
5.3 Number of concrete examples of BEK team use of PEA analysis to develop or adjust plans, make significant decisions and/or influence reform agendas	N/A	Substantially did not meet expectation – 0

Briefly describe the output’s activities and provide supporting narrative for the score.
This output reflects the work to establish a PEA Research Centre for the Embassy. Though Terms of Reference have been written and Early Market Engagement occurred, the tender for the PEA Research Centre (PEACE) did not happen due to the changing context which led to a shift in priorities and internal capacity constraints.

However, this outcome also includes wider support the programme provides to help the UK track and influence reform agendas – the hosting of the Wilton Park conference and secondees to the OECD Paris and Ukraine Donor Platform in Brussels. With the support of GRP for example, the UK and Germany, were successfully able to host the second Wilton Park Conference on Ukraine since the full-scale invasion. The UK brought together the Government of Ukraine and key partners to agree on next steps for planning and preparing a more inclusive and accountable recovery, with a focus on recovery investments. Building on these discussions, we are now developing a reform roadmap to sequence and coordinate necessary reforms, potentially supported by LSE and Germany has committed financing for the next UK-Germany co-hosted working platform on social recovery reforms in March 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The programme team will focus on updating the Terms of Reference and holding another Early Market Engagement in Q1 2026 as the context has changed significantly since the last one (August 2025).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
British Embassy Kyiv would still benefit from a PEA Research Centre. Ukraine’s political settlement is being reshaped by profound internal and external forces, creating a fast-changing and complex environment. UK engagement has grown rapidly since the full-scale invasion, opening major opportunities but also significant risks, especially as we operate in new areas with limited ability for staff to travel. A dedicated Political Economy Analysis (PEA) Research Centre is needed to help ensure our policy and programmes are evidence-based and politically sensitive. This will help mitigate risks of unintended consequences, deliver value for money for the British taxpayer, and strengthen the effectiveness of UK support. Demand for PEA remains high, including as a priority for Baroness Chapman, so establishing the facility in the first half of this year is critical.

The log frame should also be adjusted to capture the achievements of the wider activities that are included under this fourth component.

D: VALUE FOR MONEY [1 page]

Key cost drivers and performance
The key cost driver is fees for international experts and payment to downstream partners due to the heavy focus on technical assistance and the operational set up of DIGIT. Despite the significant challenges posed by the operating context - in particular the USAID withdrawal creating increased need with little notice; the security context; and the shortage of in country expertise, the GRP team have continued to look for opportunities to drive down costs where possible whilst ensuring high standards of delivery are maintained.

For example, the creation of DIGIT was done with VfM and cost-cutting measures. Following the end of DTA and the continuation of the partnership with Eurasia Foundation we stopped funding requests for equipment, unless it is crucial for functioning of the service, i.e. servers for the Transparency Register. We also renegotiated overheads and day rates to bring them into line with Embassy benchmarking. The rollover of the partnership with Eurasia Foundation helped to avoid start-up costs and leveraged existing delivery partners.

On judicial reform, IDLO staff fees align with Embassy benchmarks. We also undertake rigorous cost-sharing with other partners for the selection processes and audits. For example, ARMA Head selection is co-funded with GIZ. This spreads risk and drives efficiency.

Going forward, we will continue to seek joint delivery models to enhance coordination. As we learned from partnership with USAID, drawing on USAID project management freed up FCDO staff time to focus on technical and strategic inputs. It also allows us to deliver joint messages to the Government on sensitive issues, improving our impact in the more challenging reform areas. We will also aim to maximise the fund flows to NGOs. Wherever possible, we will seek to work with local partners or implementing organisations directly. Not only does this often demonstrate better value for money in terms of immediate costs, but by using local expertise we are more likely to cement government buy-in and produce more sustainable results.

VfM performance compared to the original VfM proposition in the business case
The original Business Case envisioned joint delivery with a USAID programme, which offered excellent value for money (VfM), with the UK contributing 10% of the funding while maintaining an equal voice in decision-making. Over the past year, performance has been harder to compare and does not demonstrate the same level of VfM as outlined in the Business Case. However, building robust programming options takes time, and a rapid response offers different VfM to the VfM provided via a structured setup achieved through Pro-Integrity and DTA in partnership with USAID. Looking ahead, it will be important to reassess what VfM for the Governance Reform Programme should look like within the current reform landscape.

Assessment of whether the programme continues to represent value for money
The programme should continue, given the importance of the reform agenda, the results achieved this year, and the value for money (VfM) demonstrated. At design stage, the programme offered strong VfM, with the UK contributing less than 10% of the USAID budget while securing an equal role in decision-making and full co-branding rights. Following USAID’s withdrawal, it is essential to align our priorities with long-term ambitions and broader political objectives in governance reform to maintain VfM. Many early decisions were driven by the need for immediate action to retain key staff and deliver on core programme objectives. Significant efforts were made to minimise costs, including reducing UK DIGIT project staff by 50% (from 48 to 23), prioritising activities, and lowering overheads compared to previous USAID-funded arrangements. With new components coming online in Q1 2026 GRP will have further opportunity to strengthen its approach to VfM.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]
Risk management within GRP has been proactive and structured, with a central risk register maintained and reviewed quarterly to ensure alignment with BE Kyiv’s risk appetite. While major risks exist, they remain appropriately mitigated and within tolerance levels, so no changes to the overall approach are required. Over the past year, the unexpected withdrawal of USAID funding materialized as a significant risk event, testing the programme’s resilience and response mechanisms. This experience has informed future activity design and highlighted the importance of understanding delivery partners’ risk appetite, given the speed at which the funding landscape can change. The most persistent and heightened risk continues to be the willingness of Ukrainian institutions to implement reform, compounded by emboldened vested interests and declining international and domestic support. This has slowed legislative progress and limited UK leverage, though mitigations have enabled continued delivery of results despite contextual challenges. While the likelihood of another abrupt donor withdrawal is low, the programme remains exposed to the inherent risks of operating in a country at war, particularly regarding personnel safety.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
The operating context in Ukraine remains highly challenging and uncertain, making strong, constructive relationships essential for the successful delivery of GRP. Despite these difficulties, delivery and reporting have been timely across all partners, supported by proactive and transparent communication channels. This approach has enabled GRP to maintain smooth implementation and adapt effectively to evolving circumstances. Lead implementers Eurasia Foundation and IDLO received positive feedback from beneficiaries and other stakeholders for their efficiency, high standards, and strong management capabilities. Their ability to manage risk, finances, and delivery - while escalating issues promptly to the FCDO - was particularly commendable. Close engagement by the FCDO, combined with strong collaboration between development and political teams, proved critical to the programme’s success and should be considered a best practice for future programming.

Looking ahead, greater attention is needed to refine GRP’s strategic direction - specifically in balancing priorities, optimising delivery mechanisms, and strengthening partnerships with other donors to maximize impact.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
While implementing partners maintained robust logframes and reported effectively on results, the programme team did not sufficiently update the overarching logframe or record changes as the context evolved. This meant that, despite GRP delivering a substantial amount in a year of significant change, the annual review cannot fully capture its main achievements. A key lesson is the importance of real-time updates to the log frame and indicators, along with maintaining a clear record of changes to ensure success is measurable at review points. The approved GRP Business Case also envisages Third Party Monitoring and independent evaluation as part of the MEL plan, which will be further detailed during the inception phase of BE Kyiv’s VERITAS programme.

Evidence
The programme’s evidence base is strong, with clear deliverables such as progress reports, draft legislation, and strategic documents that provide quantitative data and are straightforward to assess. However, capturing evidence on the broader political and institutional context remains more challenging, as factors like vested interests, limited political will, and wider political dynamics can undermine progress. Close engagement with political colleagues is therefore essential to provide this contextual insight and ensure the programme adapts effectively - for example, in response to protests in July or ongoing debates on the effectiveness of certain selection processes. Moving forward, the team should continue to integrate political and programmatic perspectives into both evidence-gathering and overall programme design to strengthen responsiveness and impact.

Learning
The programme team can do more to capture learning throughout implementation – though a balance should be found given the high workloads the team and implementing partners face. At a minimum we should ensure implementing partners are engaging in regular context analysis and holding reflection sessions. In addition, the Business Case commits that ‘learning objectives’ will be agreed with each delivery partner and provides example questions – as new components are set up these should be agreed. The programme team should also capture and document learnings more regularly, such as at quarterly review points.

This annual review was conducted by the Second Secretary, Political, at British Embassy Kyiv following interviews with the key partners, and their downstream partners, alongside reviews of the documents provided over the year assessing delivery against programme priorities.