Prosperity Fund / Indonesia / Renewable Energy Programme / Full Business Case / October 2019

Contents

1. Summary
2. Recommendation
3. Next Steps
4. Programme Summary
5. Commercial Case
6. Financial Case
7. Management Case
8. Annexes

List of Abbreviations

BEIS – Department for Business, Energy and Industrial Strategy
BEJ – British Embassy Jakarta
DFID – Department for International Development
DIT – Department for International Trade
FBC – Full Business Case
FCO – Foreign and Commonwealth Office
GoI – Government of Indonesia
HMG – Her Majesty’s Government
IIOC – Investment, Infrastructure & Operations Committee (FCO)
JFU – Joint Funds Unit
LCP – South East Asia Low Carbon Programme (Prosperity Fund)
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation and Learning
PSAB – Procurement Strategy Approval Board (FCO)
PF – Prosperity Fund
PFDU – Prosperity Fund Delivery Unit (FCO)
SDT – Sustainable Development Team (British Embassy Jakarta)
UK – United Kingdom
VfM – Value for Money

Summary
The Prosperity Fund (PF) Indonesia Renewable Energy Programme (IREP) will reduce poverty and support inclusive economic growth by accelerating and expanding access to clean and affordable energy. The programme supports national and regional energy policy and regulatory reform; increased external investment in renewable energy projects; development of bankable commercial models through demonstration projects to attract increased private sector investment; and international best practice and knowledge transfer.

The programme will create commercial opportunities for international and UK businesses of increased investment in the renewable energy sector, working closely with DIT Indonesia’s Energy Team (including resources funded from the PF non-ODA budget). The Programme has been identified by JFU Social Development Advisers as a good practice example of mainstreaming gender equality and social inclusion in its design and procurement.

This Full Business Case (FBC) updates the Outline Business Case (OBC) (Annex 1) following conclusion of a procurement exercise to identify a delivery partner for the Indonesia Renewable Energy Programme (IREP). Palladium International Ltd are the preferred bidder.

1. The Contract Award Recommendation Report (Annex 2) was approved by the Procurement Strategy Approval Board (PSAB) on 22 October 2019. Pending approval of this FBC by the Infrastructure Investment and Operations Committee (IIOC), assuming no challenge is raised, a contract will be signed with Palladium following the statutory ten day commercial standstill period.
2. A condition of OBC approval was for the Prosperity Fund (PF) Framework to be further tested to determine whether it could elicit 4-6 viable bids against the Programme’s delivery and commercial principles. The majority of PF Framework Energy Lot suppliers submitted responses to a written questionnaire and met with the Procurement Team in August 2018; this process confirmed the PF framework would unlikely elicit sufficient numbers of viable bids and recommended an OJEU process as optimal.

1. The Procurement Team identified a Competitive Procedure with Negotiation (CPN) as the optimal OJEU route to market. This was approved by PSAB in October 2018. A CPN allowed the Procurement Team to negotiate with bidders following initial bid submission. Bidders may then submit improved tenders following negotiations. The process can be repeated until the client is satisfied it has identified an optimal tender.
2. An OJEU Notice was published in November 2018. Thirteen bidders responded to a Standard Questionnaire (SQ) seeking responses to basic capability, capacity and due diligence questions. Four SQ respondents were invited to submit initial tenders and negotiate. Following submission of initial tenders, two rounds of negotiations were held. The third tender was declared final following full evaluation and moderation in October 2019.
3. Palladium’s tender was evaluated as the most economically advantageous and scored highest under both technical and commercial evaluations. The overall tender score was higher than other bidders’ scores by a margin that provides a high degree of confidence that Palladium are the optimal delivery partner. The average day rate is £419 per day against an average day rate of £619 for other PF Procurements. The competition elicited savings of £1.44m from the procurement ceiling of £10m. The £1.44m will be rolled back into the Programme to increase volume of delivery and impact on the same pricing basis as the rest of the Contract.

Sub-contractors to Palladium are Hivos (a NGO specialising in community led renewable energy projects, gender equality and social inclusion and networking and collaboration) with a sub-contract value of £1.06m; Castlerock (An engineering firm specialising in infrastructure delivery and renewable energy technology), with a sub contract value of £1.86m; and Economic Consulting Associates (specialising in financing infrastructure projects) with a sub-contract value of £0.26m. This reflects the Programme’s requirements for delivery to be predominantly owned by the prime contractor, avoiding a managed service model and deep and complex supply chains (sub-contractors are not engaging their own sub-contractors). As required, Palladium have not applied margin on margin to sub-contractors’ charges. The fixed margin charged by Palladium is £0.75m.

Further details of the procurement are set out in this FBC’s Commercial Case and Award Recommendation Report (Annex 2).
## Recommendation
This FBC recommends IIOC approves awarding a contract to Palladium in line with the next steps set out below.
## Next Steps
Bidders will be notified of the outcome of the procurement process, beginning the ten day standstill period. Following standstill, assuming no challenge is raised, FCO will award the contract to Palladium. Palladium will begin mobilisation (deploying staff etc.) and the Programme will begin delivery in November/December 2019 with full service delivery beginning in January 2020.

Programme Summary

To increase renewable energy generation share nationally and improve access to clean energy for poor communities in eastern Indonesia, reducing poverty and supporting economic growth IREP aims to:

Improve renewable energy policy, regulation and financial instruments through technical assistance to national and regional government (the latter with a focus on eastern Indonesian regional governments).

- Increase investment in renewable energy by bridging the gap between available external finance, technology and viable projects through brokerage.
- Accelerate development and innovation in renewable energy by enabling innovative, replicable business models via demonstration projects.
- Networking and collaboration between domestic and international renewable energy sectors to develop domestic innovation, best practice and knowledge transfer.

The interventions above will be delivered through four interlinked programme strands:

The Policy Strand will work with national level government and public institutions, including the Ministry of Energy and Mineral Resources (with which British Embassy Jakarta has signed a Memorandum of Understanding covering low carbon work) and other ministries, and the state-owned electricity company PLN, and sub-national authorities to address renewable energy policy, regulatory and fiscal issues.

The Collaborating and Networking Strand will support domestic and international knowledge transfer of renewable energy best practice, including technologies and business models; it will support coordination among low carbon donor activities, promote public messaging on renewable energy and economic development and raise awareness of other programme activities.

The Brokerage Strand aims to leverage £500m+ (Palladium confirmed they would commit to delivering £500m rather than the original £150m target) of new investment in renewable energy projects from public, private and multilateral sources, with a focus on eastern Indonesia. This Strand includes a suite of activities to bring projects and finance together, including technical assistance to support bankable project development and reach financial closure, raising awareness in the domestic, regional and international markets of project opportunities in Indonesia, and active matchmaking between project developers and financiers.

The Demonstration Project Strand will fund the development replicable off-grid business and cost recovery models. This strand will showcase the importance and opportunities of community engagement, mainstreaming GESI, demonstrate replicable business models to attract private sector investment, and showcase renewable energy as a vehicle for supporting productive uses of energy in supporting commercial activities, for example cold storage for fishing communities or solar irrigation.
Tender	Preferred Bidder	Total Contract value inc. taxes (four years)
Indonesia Renewable Energy Programme – Implementing Partner	Palladium International Ltd	£8.56m

Commercial Case

The Award Recommendation Report (Annex 2) was approved by PSAB on 22 October 2019 and incudes full details of the procurement process and should be read in tandem with this Commercial Case. The Statement of Requirements (SoRs), Evaluation Criteria, Approach to Procurement and Invitation to Negotiate (ITN) are annexed to the Award Recommendation Report.

Requirements

The requirements in scope of the commercial case are expressed in capability terms, namely the delivery of:

- Energy Policy and Regulatory Reform.
- Renewable Energy Infrastructure Brokerage (Technical assistance, matchmaking and promotional activities to leverage external funding).
- Renewable Energy Demonstration Projects (demonstrating viable technologies, community engagement, replicable business models and local economic and commercial opportunities)
- Enabling Technology (Productive uses of power and social inclusion projects embedded within Brokered Demonstration projects).
- International Knowledge Transfer and domestic and international collaboration.

Intervention	Purpose	Required Expertise	Outcomes
Brokerage of Renewable Energy Infrastructure and Enabling Technology Funding	To leverage untapped external funding of c£150m (minimum) over the lifetime of the programme to deliver renewable energy and associated enabling technology (e.g. solar irrigation, cold storage etc.) to provide inclusive and affordable power and technology for productive use.	Knowledge of funding sources with potential to support renewable energy infrastructure in Indonesia from all of domestic, regional and international public, private, multilateral and other sources. / Capability to meet funders’ requirements to draw down funding. / Experience and track record of securing and dispersing funding and increasing project bankability where necessary to access finance.	At least £150m worth of RE infrastructure delivered in eastern Indonesia, but with a stretch target to of £500m plus (to which Palladium have committed to delivering).
Renewable Energy and Enabling Technology Demonstration Projects	Delivery of renewable energy projects in a locale or community using enabling technology and community engagement including a social inclusion and gender equality focus. Projects will provide data to demonstrate the potential for renewable energy as a means to reduce poverty and stimulate economic development in order to support the Programme’s policy stand.	Experience and track record of delivering RE Infrastructure. / Ability to identify an appropriate site or sites/communities, and reach and credibility with those communities. / Experience of delivering enabling technologies. / Experience of community engagement including social inclusion and gender equality around the productive uses of power.	Demonstrate that renewable energy can drive poverty reduction, economic development, social inclusion and gender equality, using viable business models and technologies that can be replicated elsewhere in the country.
Policy and Regulatory Reform	To support GoI’s aim to increase the renewable energy generation share to 23% by 2025 (currently 10- 11%).	Understanding of the current policy and regulatory framework. / An understanding of international best practice in RE policy and regulation (and financial instruments – how RE is funded and available sources, private and public sector). / An ability to transpose international good practice into an Indonesian context and an understanding of the political economy.	RE policy, regulatory and financial instruments that ignite the RE sector, particularly private sector investment in Indonesia and shows uplift in the percentage energy generated from renewable sources.
Collaborative Network of Domestic and International experts and Stakeholders	To inform and support delivery of each programme strand. The network will also transfer international knowledge to the RE stakeholders in Indonesia.	An organisation who can connect with RE sector leaders, innovators, and businesses globally and help disseminate and transfer knowledge to the Indonesian RE sector.	Indonesia becomes a global leader and innovator in RE.

Make or Buy Decision

The make or buy decision (I.e. what might be delivered from within existing staff resources, and what might be procured externally) was based around the Programme’s requirements and FCO’s core capabilities. Recognising the specialist nature of the requirements and given the limitations of FCO’s in-house capacity and capability to deliver them, the decision was made to outsource delivery.

Commercial Deal Principles

SDT identified a range of commercial principles used to guide the construct of the contract. There are a number of fundamental commercial principles that are required in this specific contract. These include the following:

- No margin on margin – sub-contractor costs are passed through at cost.
- Implementation of a shallow value chain (i.e. no more than one layer of sub-contracting).
- Direct client access to sub-contractors.
- Pass through costs are to be broken down to component levels e.g. staff costs (what they are paid), accommodation, IT, travel etc. with margin separately identified.
- The prime contractor must have a demonstrable track record and current footprint of RE delivery in Indonesia, including in eastern Indonesia.
- The supplier must be able to demonstrate experience of policy development and support for implementation of RE regulation.
- The contract must be with (and delivered primarily by) Indonesia based offices and staff if the supplier is an international organisation – SDT wish to avoid any remote management of service delivery and contractual responsibility which is known to be sub-optimal.
- The supplier must be able to demonstrate partnership arrangements with Stated Owned Enterprises (SOEs), Development Banks, Equity firms, bilateral donors, UN or other multilaterals that disperse RE infrastructure funding to ensure the brokerage strand can deliver at the very least £150m of funding over the contract lifetime (they will be assessed on the basis that more is better).
- The supplier must have a demonstrable track record of delivering in social inclusion and gender equality projects in Indonesia.
- Brokered projects are open to international, including UK companies to promote a diverse and innovative supply chain.
- Ability to deliver demonstration projects in a locale within 12 months of project start date and deliver uses of power, community empowerment and social inclusion (including gender equality) projects.
- Ability to carry out primary research and MREL baselining in remote communities.
- Proven communications and online promotion capabilities.
- Experience in setting up special purpose vehicles and funding mechanisms to mainstream funded activities beyond life time of programme, including fundraising capabilities.
Route to Market

The SOBC identified the delivery options and requirements and concluded that service delivery under a grant to an NGO was the preferred option but also noted a commercial route to market had potential. Following market engagement, the OBC identified a commercial route to market as optimal. The preferred route was via an OJEU process should the Prosperity Fund framework be expected to be unable to source 4-6 good quality bids. This approach was approved by IIOC.

FCO issued a questionnaire to framework suppliers to examine whether they:

- Had a footprint in Indonesia.
- Had a proven track record in delivering comparable programmes in Indonesia or internationally
- Could directly deliver as much of the requirements as possible.
- Would use a shallow value chain.
- Could accept the proposed commercial deal principles.
- Intended to bid.

The questionnaire elicited 16 responses in total (of 23 framework suppliers), a representative response rate of 69%. 12 suppliers completed the questionnaire (52%). WSP UK Ltd, Steer Davies Gleave and Crown Agents confirmed that they did not intend to bid for the opportunity and did not complete the questionnaire. Oxford Policy Management expressed interest in bidding but declined to complete the questionnaire, citing time constraints. Others did not respond.

The table below sets out the areas of expertise of PF Framework Energy Lot Suppliers, the number of Suppliers in each category and those responding to the questionnaire.

Area of Primary Expertise	Number of Framework Suppliers	Suppliers Responding to Questionnaire
Technical /Engineering / Infrastructure Providers (inc. technical consultancy providers)	7	Mott MacDonald / AECOM Ltd / NIRAS Consulting Ltd
Consultancy/Strategy/Policy	10	PwC / McKinsey & Co / EY / Deloitte / IHS Global Ltd / ICF International
International Development	6	Adam Smith International / DAI Europe / Cardno Emerging Markets

1. A series of bilateral meetings was then held with all Framework suppliers that had responded to the questionnaire. These were held over three days in Jakarta, concluded by end July 2018. FCO CPG, SDT and Commercial Leadership Ltd participated in the market testing.
2. The framework providers demonstrated mixed capabilities and experience. While there were a good number of suppliers that said they were likely to bid and expressed appetite, there were very few that provided full assurance that they have the necessary footprint, experience, track record or willingness to accept the commercial deal principles or, in some cases act as the prime supplier. It was concluded that use of the PF Framework would likely have elicited one strong and one adequate bid which would not have provided sufficient bids to hold for a viable competition.
3. The exercise also re-enforced the OBC’s conclusions that best value for money and highest quality service would be achieved by appointing a supplier that can deliver as much of the service as possible from within their own resources and with specific and relevant experience of successful renewable energy and social inclusion delivery in Indonesia. Use of sub-contractors was deemed necessary but minimised to a shallow specialist supply chain.

The Procurement Team then considered OJEU routes to market and concluded a CPN would be optimal. A business case for using a CPN approach was submitted to PSAB in October 2018 and approved.
Procurement

1. An OJEU Notice was published in November 2018. Thirteen bidders responded to a Standard Questionnaire (SQ) seeking responses to basic capability, capacity and due diligence questions. Four SQ respondents were invited to submit initial tenders and negotiate. Following submission of initial tenders, two rounds of negotiations were held. The third tender was declared final following full evaluation and moderation in October 2019.
2. Palladium’s tender was evaluated as the most economically advantageous and scored highest under both technical and commercial evaluations. The overall tender score was higher than other bidders’ scores by a margin that provides a high degree of confidence that Palladium are the optimal delivery partner.

Day Rate

The average day rate is £419 per day against an average day rate of £619 for other PF Procurements.

Savings

The competition elicited savings of £1.44m from the procurement ceiling of £10m. The £1.44m will be rolled back into the Programme to increase volume of delivery and impact on the same pricing basis as the rest of the Contract.

Sub-Contractors

Sub-contractors to Palladium are Hivos (a NGO specialising in community led renewable energy projects, gender equality and social inclusion and networking and collaboration) with a sub-contract value of £1.06m; Castlerock (An engineering firm specialising in infrastructure delivery and renewable energy technology), with a sub contract value of £1.86m; and Economic Consulting Associates (specialising in financing infrastructure projects) with a sub-contract value of £0.26m.

This reflects the Programme’s requirements for delivery to be predominantly owned by the prime contractor, avoiding a managed service model and deep and complex supply chains (sub-contractors are not engaging their own sub-contractors). As required, Palladium have not applied margin on margin to sub-contractors’ charges.

Pricing Model

The pricing model is an innovative mix of cost plus with capped charges and rebate provisions which the Procurement Team believe may have potential to be adopted in other procurements i.e. price is based on an actual cost profile for deploying the resources to deliver the service specified. Should it cost the delivery partner more to deliver the service, they will absorb the additional cost. Should it cost less, FCO will not be charged against the profile - effectively receiving a rebate which means resources can be redeployed elsewhere. This applies to staff costs, overheads, T&S etc. The profit margin element is a fixed sum.

Proposed Contract Term

The proposed contract term is four years from November/December 2019.

The proposed term also reflects the nature of the required services i.e. the desired outcomes are not a ‘quick fix’. Influencing and changing the renewable energy policy and regulatory environment, proving technical capability and providing the basis for building credible cases for funding will all take time to achieve. However, it is also anticipated that the programme will achieve early results, for example the delivery of renewable energy demonstration projects.

Contract Value

The initial total contract value over the four year term is £8.56m. This figure is made up of evaluated costs and non-evaluated estimated costs of delivery of the Demonstration Project Strand. Actual Demonstration Project costs will follow the capped and model agreed with Palladium. In line with OJEU Notice and Public Contract Regulations (PCR 2015) rules on increasing to contract value to increase volume of delivery, the value of the contract may be increased to up to £13.5m should scale-up funding be identified.

Tender Evaluation Criteria

The tender evaluation criteria and relative weightings were as follows:

Criteria	Weighting (Total 100%)
Technical	75%
Price	25%

Technical Criteria	Weighting (Total 75%)
Methodology	35 %
Performance Management	10%
Resourcing	30%

Charging Mechanism

The requirement is for a small core team to be established for the duration of the programme.

The competition required the supplier to provide full transparency around all contract costs, including full sight of staff costs, staff utilisation rates, contribution to overheads, treatment of pass through costs and profit margin. All payments for the core team will be made monthly in arrears (i.e. no up-front investment is required by the FCO).

The competition has been based on a full understanding of all costs and the expected profit margin, rather than the starting point being based on bidders own standard pricing models. It has been demonstrated in similar sized procurements that the market is willing to adapt its standard pricing models to adapt to meet requirements such as the above where they have an intent to meet the required outputs (in addition to making a reasonable return).

As the programme develops and specific demonstration projects are considered, FCO will seek fixed prices wherever possible and desirable. Each project will be priced separately (to reflect the differing technologies and circumstances that may be present in specific project), based on actual technology and installation cost as well as resource costs (broken down as per Commercial Pricing Principles).

Key Contract Clauses

FCO Commercial supplied the PF Framework Agreement and Call-Off Contract as a contract template for IREP. This has been adapted only to suit the fact that the contract for IREP is not a call-off contract. All substantive clauses have been retained. However, a number of factors exist which will require specific consideration within the contract clauses. The key issues that have been identified to date are summarised below:

Liability & indemnity: FCO to make clear that suppliers are not expected, unless otherwise stated, to bear the risk for all outcomes, but are required to bear the risk for delivery of the defined inputs and outputs. The supplier’s responsibility should indemnify FCO for costs and risks associated with the delivery of inputs and outputs. FCO will not require the supplier to provide indemnification related to any future RE outcomes.

IPR: FCO will make clear that applicable foreground IPR, including any documentation, designs, deliverables, processes, data and work products produced specifically under this contract will belong to FCO, thereby ensuring that it may “lift and shift” the services quickly and at minimal cost to another provider without the need to re-develop a new bespoke operating framework. FCO should not expect to acquire technical Renewable Energy IPR, but should maintain a contractual right to use technical data in order that the Demonstration Project providers are not given an irreversible advantage in any future competitions to scale up RE delivery.

Price: FCO requires sub-contractor costs to be passed through at cost (i.e. to avoid margin on margin) and full price transparency with reference to appropriate data to provide assurance that market rate is achieved.

Terms & Conditions: Use of the FCO standard Terms and Conditions template, amended to reflect the specific requirements as necessary and agreed by FCO Legal (and if necessary by the specialist commercial team in Government Legal Department). Appropriate flow down of terms through the supply chain.

Licences: FCO to be granted royalty free, perpetual licences to use any background IP or software in the supplier’s solution (the intent being that there is no restriction preventing FCO from quickly, easily and cheaply moving to an alternative supplier if necessary).

Exclusivity: The contracts will not contain any exclusivity provisions. The FCO reserves rights that it may engage other service providers to carry out similar work.

Payment terms: These will be in line with FCO payment policy. Contract price will be established in £ Sterling and all payments made in Sterling. FCO will not be subject to currency fluctuation risk.

Indexation: Prices agreed at the time of contract signature will remain valid for the Contract term. There is no provision for inflation related increases to the Contract price.

Step in rights: FCO should retain the right to step in (in full or part) to deliver the service using alternative resources if the supplier is not able to perform the services (and/or sub-contractors fail). Key to the ability to effectively deliver this right is the extent to which the FCO can “lift and shift” the requirements from a supplier – for example the agreement in respect of IP rights must support the “lift and shift” ambition, otherwise the right of step-in becomes difficult to achieve in practice.

Data provision: FCO must be able to extract relevant data at any point with no additional cost. The supplier shall not be entitled to withhold any information which could prejudice future competitive procurement exercises. FCO are the data controller.

Safeguarding: FCO requires its safeguarding requirements to extend to the Delivery Partner and all Sub-Contractors.

People Implications (including TUPE)

There are no existing TUPE implications that arise as a consequence of the proposed contract, and none are envisaged at the end of the contract.

The Procurement Team (FCO Commercial, DLA Piper and SDT) will disband following award and the contract will be managed by the SDT which will transition to a contract and programme management configuration.

When the programme ends, UKB staff will move on to other roles and locally engaged staff, depending on their contract terms with the embassy, will either be issued with redundancy notices or placed elsewhere in the Embassy.

Contract Management

Once the contracted is awarded, responsibility for the management of the appointed supplier will fall to the SDT, British Embassy Jakarta. He is an experienced civil servant and has previous experience of procuring and managing large scale public contracts and designing and delivering major programmes. . He reports directly to the Programme SRO, Owen Jenkins, HMA Indonesia and Timor-Leste.

Contract Management will be a whole team approach with certain duties delegated within SDT. Overall responsibility lies with the Contract Manager. Ultimate responsibility lies with the SRO.

The main responsibilities of the Contract Manager include:

- Maintaining positive and professional relationships with stakeholders/contractors;
- Overseeing the performance of contractors;
- Ensuring continuous improvement;
- Ensure contractual compliance – that they are delivered as agreed and to the required level of performance, quality and cost;
- Establish, agree and operate contractual governance arrangements;
- Lead on the monitoring and reporting of Key Performance Indicators (KPIs) and Service Level Agreements (SLAs);
- Manage change controls and ensure these are reflected in programme documentation;
- Co-ordinate and agree the sign-off of contract milestones and subsequent payments; and
- Liaise with Posts overseeing delivery locally.

Handover

The Contract Manager will develop a Contract Management Plan, ensuring roles and responsibilities are identified and understood by all parties, appropriate contract documentation is in place and signed, governance procedures and mechanisms for managing change/risks are established, and any risks/factors from the procurement process requiring on-going management (highlighted below) have suitable action plans.

Training

SDT has attended Commercial and Contract Management training and is undertaking/completed the FCO online contract management training course, with a view to completing expert level. SDT is also attending the contract management training to be delivered by FCO Commercial in Singapore in November 2019

Risk Transfer

The general principle is that risks should be passed to ‘the party best able to manage them’, subject to value for money. This section provides an assessment of how the key risks have been apportioned between the FCO and appointed supplier.

Risk Category	Potential risk allocation			Description
	FCO	Supplier	Shared
Design Risk				Supplier designs the detailed approaches, technical solutions, operating tools and processes. / FCO owns foreground IP and all designs of any specially created material/process. / FCO retains right to share supplier owned IP/data to prevent future market lock-in or distortion.
Supplier Availability				Availability of suitable sub-contractors to be managed and assured by the supplier. / Impact of failure will be owned by FCO.
Data Security				FCO to make its expectations clear. / Supplier to meet all data requirements (e.g. GDPR) & retain responsibility for maintaining adherence to FCO and legal requirements.
Supplier Performance				Risk of delivery to expected performance levels owned by supplier and to be reflected in SLAs.
Variability of Volume				Note: Volume refers to the amount of work passed to the supplier. / Demand may come from a number of different sources and is largely unforeseeable. / No volume guarantees to be offered.
Scale				Note: Scale risk refers to the ability to increase scale to respond to increased demand: / FCO own the scale of ambition. / Supplier(s) to own responsibility for scaling to meet expanded demand.
Termination				Break clauses in contract. / Standard termination for cause clauses.
Financing				FCO to consider funding Demonstration Projects/milestone payments to incentivise supplier where appropriate. / Supplier(s) to fund shot term operations.
Legislative				Supplier unable to influence risk and as such it is owned solely by FCO.

Commercial Risks and Mitigations

Risk	Mitigation
Post contract award client-supplier disagreements.	As much as possible agreed pre-award with contractual ability to impose final MREL framework.
Misaligned or unclear pricing and invoicing processes.	Written clarification pre-award and embed in contract.
OJEU limit limits potential to scale up programme.	Push envelope within regulations. Undertake new procurement process if necessary.
Programme activities overlap and/or conflict with other UK ODA and donor work in the renewable energy sector.	Identify and engage UK programmes, donors and other actors to create synergies and add value to one another and avoid duplication.
Insufficient resources to optimally manage programme.	Considering bid for more resources - PFFU have approved d a bid for 1 FTE LE B3; SDT could scale down wider embassy contribution, streamline reporting requirements. Undertake appropriate training, handover and succession where necessary to ensure programme team capacity, knowledge, skills and continuity.
Ineffective governance/contract management arrangements.	Agree refined arrangements contract pre-award. Governance already in place and robust, will meet weekly at CM ops level. Embedding of SDT staff within delivery partner team will help jointly deliver programme strands but also help contract management.
Uncertainty over programme length and/or budget allocation due to ongoing negotiations between JFU and HMT regarding programme fund allocations across Spending Review periods.	Risk is largely owned by JFU/PFDU and mitigations will be led by them. However, SDT is also putting in place mitigations: i) Maintaining close contact with PFDU/JFU to ensure SDT is aware of changes as soon as possible (ongoing). ii) Maintaining momentum on procurement and FBC assurance to ensure prompt programme launch. iii) Keeping PFDU updated on programme progress and delivery to reduce risk of IREP being selected for funding cuts (monthly calls, monthly steering group, monthly financial reporting). iv) Realistic forecasting of spend throughout programme development and delivery (monthly). v) Effective contract management, including working closely with implementers to spot and address any external delivery roadblocks (ongoing). vi) Use adaptive programming approach to channel funding into more advanced strands (once in delivery phase) if programme duration is shortened. Modular approach allows for budget haircuts or re-prioritisation on certain programme strands.
Procurement approval or delivery delays result in drawdown being postponed.	i) Realistic forecasting of spend (ongoing); iii) Effective procurement and contract management, including working closely with implementers to spot and address any external delivery roadblocks (ongoing); iv) Use adaptive programming approach to channel funding into more advanced strands (once in delivery phase).
Currency fluctuations: potential for volatility surrounding Brexit negotiations and beyond (particularly in no-deal scenario); and political changes in Indonesia post-Presidential election/inauguration.	i) Contractual arrangements will specify that implementer(s) bare currency risk, but ultimately this may result in lower levels of service and consequent effect on outputs and impacts. ii) Should this be the case, we will use adaptive programming approach to channel funding into most effective strands/those for which a budget uplift is critical for success.
Loss of political commitment to reform which affects programme delivery. Incumbent Jokowi won April Presidential elections; inauguration in October. Possibility of change of Energy Minister post-election (this could be a positive move depending on who appointed).	i) Secure broad range of support for programme (political and other key stakeholders) (ongoing). ii) Close collaboration with national and local governments in programme design (ongoing). iii) Strong embassy engagement and relationship management (ongoing). iv) May embed staff in ministries for greater influence and monitoring of results (delivery phase). v) Increase level (and seniority) of engagement with GoI as well as improved donor co-ordination to influence GoI to meet international commitments as a bloc (mobilisation/delivery phases). vi) Build in flexibility to phase programme activities and/or redirect resources or stop programme activities that can no longer deliver desired impact (design/delivery phases). vii) Accelerate MoU signing to pre-empt election (signed February 2018); viii) tie-in work to UK COP and UK-supported Indonesia Low Carbon Development Initiative to help increase buy-in.
Unsupportive regulations for renewable energy reduce investor confidence; protectionist policies and continued poor regulatory frameworks reduce investor confidence across sectors.	i) Close collaboration with national and local governments across ministries; ii) May embed staff in ministries for greater influence. iii) High level lobbying and engagement with GoI e.g. by senior visitors; iv) Improved donor co-ordination to influence GoI as a bloc; v) Lobbying and engagement via Indonesian business and sector organisations (e.g. KADIN); vi) Focus on commercial, economic and developmental benefits to Indonesia in engagement with GoI. All ongoing.

Financial Case
This Financial Case updates the Programme budget and profile provided in the OBC and financial management and reporting arrangements. SDT will continue to provide regular finance updates the Prosperity Fund Delivery Unit (PFDU) and the Joint Funds Unit.

Programme Budget

The Programme’s budget allocation is £13.5m from the Prosperity Fund. There are no contingent liabilities associated with this funding. All funds are ODA eligible. This includes all delivery partner costs as well as associated FCO staffing and administrative and delivery costs.

Of the total budget of £13.5m:

SDT will spend approximately £1.8m on programme management and delivery staff and related costs over the lifetime of the Programme design and delivery phases. This reflects business case development, procurement and staff and related costs since 2017. The Cross-Government Prosperity Fund Full Economic Costs (FEC) model for FY17-18 is used to calculate staff costs. SDT will continue to work with FCO finance to increase the accuracy of these forecasts.

- £10m (£8.56m plus the competition savings of £1.44m rolled back in on the same pricing terms as the rest of the contract to increase volume of delivery and impact for the brokerage and policy strands) will be transferred to Palladium to be spent directly on implementing activities for the duration of the programme, including payments to sub-contractors. A portion of this (£0.75m) is margin.
- £1.6m has been clawed back as part of the spending review settlement. The remaining £0.7m pays for aspects of the programme that FCO will pay for directly, including Wilton Park Conferences, events, study trips for GoI policy officials, external audit costs, fixed term input from Subject Matter Specialists e.g. Ofgem, and legal and commercial fees etc.

1. The programme will be delivered over four years from November 2019. In line with HMT approval for an extended delivery window for the PF portfolio, this will require disbursements beyond the current spending round which expires in March 2021.
2. In line with SOBC and OBC provisions, SDT will keep opportunities for programme scale up under review, should additional funding through PF or other sources become available.

Staffing

From November 2019 approx. £1.08m will be for programme management staff posts, travel and subsistence.

This is outside the Treasury percentage cap for programme management costs outlined within Prosperity Fund guidelines. However, PFDU have confirmed this is within tolerance of the overall FCO PF portfolio percentage cap.

The staffing model takes into account DFID’s lessons learned in delivery of their multi-year climate change programmes in Indonesia (through the Embassy-based UK Climate Change Unit). This shows the importance of UK based staff who have a strong understanding and experience of operating within the UK civil service and in commercial and programme management; and who can provide direction and build the knowledge, skills and capabilities of their local staff. Of the 13 DFID programme staff at Post, 6 are UKB; SDT match this profile for Programme staffing.

As the ‘knowledge hub’ for PF strategy, assurance, management, reporting, and so on, the UKB D6 Head of Sustainable Development Team and UKB C4 Deputy Head are expected to provide best practice guidance and advice to policy and programme leads across the Embassy who are providing in-kind support to programmes. In addition, the Head/Deputy have specific oversight responsibilities for the Global Future Cities, Global Infrastructure, and ASEAN Low Carbon programmes (see Management Case for more detail). There are strong synergies between these and the bilateral renewable energy programme; UKB management time is needed to fully exploit these and engagement with DIT led (including programme dedicated non-ODA resource) secondary benefit delivery.

In addition to managing the supplier, IREP will also employ a hybrid delivery model with direct delivery support provided by SDT, including through the UKB D6 Head, UKB C4 Deputy Head and C4L Energy Advisor. SDT will provide delivery support to the delivery partner, leveraging its strengths and contacts to support direct engagement with the Government of Indonesia. This will be reflected in relevant job profiles, where we expect to reclassify roles in the embassy as hybrid admin/implementer, to more accurately reflect their specific responsibilities for both programme and supplier management and frontline delivery of the programme. This is being discussed with the FCO Prosperity Fund Delivery Unit and updated job profiles will need to be approved by the Joint Funds Unit. Resource needs for the Programme will remain under review to support optimal programme delivery and VfM as part of SDT MREL responsibilities. Should this approach be approved this will reduce the proportion of IREP admin spend.

The allocation of funds between different programme strands and activities will be reviewed regularly by SDT and the Programme’s Steering Board and shifted as necessary to maximise impact through an adaptive programming approach, incorporating learning and any changes in circumstances.

Financial Management

Value for Money

The main cost across the programme is human resources to deliver the technical assistance and capacity building activities. The tendered price is fixed and capped (and if actual costs are lower the programme effectively receives a rebate from Palladium). Also see the Commercial Case regarding the contract pricing model and the Award Recommendation Report (Annex 2).

Financial Forecasting

Forecasts will be reviewed and agreed monthly by the UKBC4 Deputy Head with the support of the A2L Programme Officer and Manager, with D6 oversight and sign-off in line with FCO and JFU requirements. Forecasting will use the FCO Hyperion/OBIEE systems, based on the payment schedule agreed with the implementing partner(s). For all activities, accurate forecasting will be managed by ensuring payments follow the agreed schedule defined by clear and time-bounded deliverables and costs.

SDT has and will continue to respond to PFDU and JFU requests to update financial forecasts for IREP, including scenario modelling for programme scale-up, potential reductions and in-year re-profiling. In September 2019 SDT responded to FCO requests to identify PF underspend to return to HM Treasury for financial year 19/20.

SDT will continue to work with PFDU, and post-contract award with the IREP implementing partner, to maintain accuracy of programme forecasts to support the accuracy of overall FCO PF portfolio forecasting. SDT understands the importance of accurate forecasting as the PF seeks to manage forecast overspend for future years and as FCO and JFU build a strong case to HMT for the next Spending Review for the PF. SDT will continue to support these efforts.

Disbursement of Programme Funds

As agreed with the Prosperity Fund Management Office, funds will be allocated by SRO letter on a per annum basis.

Invoicing and payment to suppliers will be monthly, based on inputs and actual expenditure; a full breakdown of spend to component levels will be required, distinguishing pass-through cost from margin, on an open book accounting basis with the option for rolling annual external audits to minimise fiduciary risk. This is standard practice for commercial contracts. Payments schedules will be reviewed bi-annually and can be adjusted if necessary.

Monitoring and Reporting of Programme Expenditure

Financial reporting will be carried out monthly by the A2L Programme Officer, under oversight of the UKBC4 Deputy Head Manager and sign off at D6 level, using FCO Hyperion/OBIEE systems, alongside the MR tool.

In accordance with the contractual provisions, funds to the contractors will be posted to receipt on a monthly basis in arrears on receipt of a valid invoice supported by a breakdown of activity that has been delivered. The Contract Manager (UKB D6) will be responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary. Where appropriate, full details of forecasted future spend by financial year against the annual work-plan will be included in an annual report to HMG leads. The implementing partners(s) will submit annual audited accounts for each of the financial years covered by the project.

Provision has been made for an external audit at either the end of year 1 or year 2 to ensure financial rigour
Financial and Fraud Risk Assessment

Any programme of this size and geographical focus needs to consider the potential fiduciary and fraud risk in the operating environment. Key risks have been identified in the table below, with mitigating actions and contingencies detailed. These are replicated in the full risk register.

Risk	Impact	Mitigation, Contingency & Timelines	RAYG
Procurement delays and delivery delays result in drawdown being postponed; programme strands take / time to reach implementation.	Programme fails to fully deliver expected outcomes due to reduced delivery timeframe - e.g. does not increase energy supplies or does / not generate secondary benefit.	i) Building in sufficient time to complete the procurement processes within; ii) Realistic forecasting of year 1 spend (ongoing); iii) Effective procurement and contract management, including working closely with implementers to spot and address any external delivery roadblocks (ongoing); iv) Use adaptive programming approach to channel funding into more advanced strands (in delivery phase).	Y
Difficulty accessing as much external funding as envisaged; Level of co-financing offered by Programme is unattractive to market to establish / innovative solutions with high potential but associated risk.	Lack of funding leads to reduced / no. of brokered and demonstration projects; reducing no. of technologies for which feasibility is demonstrated; leads to fewer people gaining electricity supplies; fewer commercial opportunities which reduces secondary benefit.	i) Source an implementer with proven capacity and capability to access external funding from a variety of sources to deliver infrastructure projects; ii) Feedback to policy strand (any resulting changes will have a long lead-in time) (once in delivery phase); / iii) Early and sustained engagement with major donors to source additional funding (ongoing); iv) Drawing down expertise from the collaborative network to address specific issues (once in delivery phase); v) Programme anticipates and tolerates a degree of failure in brokerage stream; vi) Use adaptive programming approach to channel funding into more effective strands (once in delivery phase).	Y
Fraud, corruption or mismanagement of funds by delivery partner leads to reputational damage and failure to achieve outcomes.	Reduced funding available for programme delivery, which leads / to fewer activities and failure to / generate primary or secondary benefit; reputational damage to / HMG.	i) Rigorous due diligence checks of implementers/partners; ii) Rigorous financial control, ensure all subcontractors are aware of their obligations and prohibitions (at appointment and throughout delivery); iii) Strong oversight mechanisms including annual audits and open book accounting hardwired into agreements with implementers (at appointment and throughout delivery); iv) Blocks on dispersal if concerns are raised (as needed); v) Consider termination of contract(s)/use of adaptive programming to transfer funding to lower-risk pillars if above actions fail to mitigate risk (as needed).	Y
Currency fluctuations: / potential for volatility surrounding Brexit / negotiations and beyond; / and political changes in Indonesia pre- and post-Presidential election.	Currency fluctuations could lead to increased costs at local level, constraining programme budget / and causing scale-back of some / activities; or conversely potential / for budget under-spends.	i) Contractual arrangements will specify that implementer(s) bear currency risk, but ultimately this may result in lower levels of service and consequent effect on outputs and impacts; ii) Should this be the case, we will use adaptive programming approach to channel funding into most effective strands/those for which a budget uplift is critical for success.	G

Management Case

Governance

The management and governance structure aims to:

Maximise programme impact with implementation managed and delivered by third parties that have the expertise and resources to deliver a programme of the scale envisaged and to achieve VfM through outsourcing and economies of scale.

Ensure that there is clear responsibility for oversight and management to proactively monitor delivery and manage risks effectively.

Ensure there is the necessary capability and expertise in BEJ to manage contracts effectively, lead on complementary activities that cannot be delivered by implementer(s), and deliver on central requirements for reporting, evaluation and communications.

The IREP, as an FCO programme will meet the governance obligations and requirements as set out in the SRO letter and change control process, agreed with the X-Whitehall Joint Funds Unit (JFU) who have overall responsibility for the PF Portfolio. HMA Indonesia and Timor Leste is the Programme’s SRO and holds the budget.

The FCO Prosperity Fund Delivery Unit (PFDU) is responsible for ensuring these requirements are met. PFDU reports to the Economic Diplomacy Director, who is the FCO representative on the PF Portfolio Board.

SDT manages the programme and formally reports to, and seeks direction on key decisions, from the SRO who chairs the Programme’s Steering Group. The SRO and SDT also have regular day to day contact and formal weekly meetings.

The Steering Group was established in January 2018 and meets regularly. The composition of the Steering Group ensures the Steering Group’s membership can best support the SRO. Palladium will be invited to attend a portion of the Steering Group, normally after the core group has met to report on progress against the Programme’s Delivery Plan, spend to date and forecasting and raising key issues for decision and steer.

The purview of the Steering Group also includes related PF programmes that the SDT oversee (Global Future Cities, Global Infrastructure and ASEAN Low Carbon programmes) in order to maximise synergies and ensure delineation between programmes, particularly the IREP and ASEAN Low Carbon programmes.

SDT also reports to the Embassy Programme Board. The Programme Board is chaired by the DHM and meets monthly to monitor progress of all Indonesia programmes and projects including Prosperity Fund, Newton Fund, International Programme, and GREAT Challenge Fund. This helps ensure that synergies and joint working opportunities between different programmes and projects are exploited, and that programme outputs deliver against HMG policy objectives.

Working with Government of Indonesia

The Programme is supported by GoI. The SRO signed an MOU with the Minister for Energy and Mineral Resources in February 2019 and with the Co-ordinating Ministry Bappenas (equivalent to Cabinet Office) in April 2019. These MOUs provide the programme with formal GoI endorsement and a commitment to co-operate, particularly on the Programme’s Policy Strand; subsidiary implementing agreements will be signed with the Ministry of Energy and Mineral Resources, Ministry of Finance, BAPPENAS, the Coordinating Ministry of Economic Affairs, Coordinating Ministry of Maritime Affairs and PLN, the state owned enterprise responsible for power production and supply.

The Programme will not include GoI in formal programme governance arrangements but will engage through bilateral meetings between the SRO and Minister and at working level between SDT and Ministry officials. As required by GoI regulations, the programme will adhere to necessary reporting requirements for ODA activity in Indonesia.

 Staffing and Resources

The SDT IREP programme team consists of a UKBD6, UKBC4, C4L (75%) and A2L funded from the programme budget. The UKBD6 is managed by the SRO; the SRO also countersigns the UKBC4.

The team is dedicated to managing the Indonesia Renewable Energy Programme but supports wider embassy responsibilities within 20% of its overall capacity: improving commercial and programme management capability across the embassy (UKBD6); oversight of the PF Future Cities (UKBD6, A2L), Infrastructure (UKBC4, A2L) ASEAN Low Carbon Programme (0.25FTE C4L, UKBC4); climate change diplomacy (UKBC4, C4L); secretariat support for Post Programme Board (A2L). The remaining capacity is spent on broader embassy corporate contributions such as attendance at management committees, information management, crisis teams, Queen’s Birthday preparations etc.

The team has absorbed the ASEAN LCP offer of 0.25 FTE C4L programme manager within the Energy Attaché and Policy Lead C4L role. The LCP is also supported on an in-kind basis by the SDT’s D6, C4UK, B3L and A2L. Locating the oversight of the LCP within the SDT is helping maximise synergies between the two programmes.

BEJ have additional non-ODA staffing resource to support secondary benefits realisation. This is comprised of 1 x C4L in SDT to lead private sector engagement. Additional staff within the DIT team at Post will support.

Upon award, the team will shift from a design and procurement configuration to a programme and contract management configuration to manage mobilisation and delivery. This does not change the staffing resources set out above but will be reflected in updated role profiles, which will include elements of programme delivery in addition to the management of suppliers.

SDT and the programme SRO will keep staffing resources under review to assess whether additional admin or delivery resource is required.

MREL expertise and advice has been provided by PA Consulting (fund-wide M&R contractor) and WYG (fund-wide E&L contractor), including discussions with SDT during development of the M&R Service Prospero IT system.

1. GESI specialist support is provided by specialists and technical experts provided by the Prosperity Fund. GESI advisors have supported the programme design and procurement, and will further support the programme during mobilisation and further as required.
2. Specialists may continue to be engaged in future:

Renewable energy implementation and financing expertise with regular in-programme touch points to support BEJ as an intelligent buyer and customer.

- Social inclusion expertise with regular in-programme touch points to support community engagement and gender equality.
- Benefits realisation (‘results’) expertise so that impact and spill-over benefits are identified and maximised. Effort will be required to ensure that international business, including UK companies, are aware and engaged in potential opportunities created via programme activities and outcomes.

In-kind support will also be provided by FCO staff and wider HMG on policy, programme management and benefits realisation (e.g. DfID support on RE and DIT support on secondary benefit) which will help drive forward design and delivery in line with HMG policy objectives.

SDT responsibilities are set out in more detail in the OBC (Annex 1) which also illustrates a wider ‘virtual team’ structure including management, frontline and in-kind support configurations. Annex 3 of the OBC sets out where the SDT fits in to wider embassy structures in terms of other PF programmes.
Delivery and Contract Management Plan
See Commercial Case.

Risk

An updated risk register is included as part of the Award Recommendation Report (Annex 2).

The Embassy has engaged closely with key stakeholders to understand potential risks and develop mitigation measures.

Additional measures to reduce risks and increase the likelihood of success include:

A staged, results-based approach to delivery meaning interventions can be halted if they are not on track.

MoUs and robust governance arrangements to secure active buy-in from key stakeholders and to create the right conditions for successful implementation.

A flexible and adaptive approach to programme implementation allowing the SDT and SRO to best respond to the evolving context by addressing under-performance early on and by capitalising on areas making the greatest progress.

Monitoring, Reporting, Evaluation and Learning

Results Framework

An indicative primary purpose ToC and LogFrame is contained in the OBC’s Annex 3. They outline the expected impacts, outcomes and outputs of the programme. It also shows how the programme links to the intermediate outcomes of the PF Theory of Change (ToC) and the UN Sustainable Development Goals (SDGs).

The ToC and LogFrame will be further refined with SDT, Palladium and PF MREL advisors during the Programme’s mobilisation phase post contract award.

The programme MREL will be consistent with the programme ToC and the LogFrame analysis that flows from this. It will report expenditure and impacts (results) in line with central PF reporting rhythms.

1. MREL for this programme will be consistent with the central PF approach to MREL. SDT will work with the MREL contractors, to develop critical indicators for programme level reporting, identifying ‘aggregatable’ indicators for regular reporting and management indicators to allow assessment of progress and impacts.
2. This will include gender disaggregated results (which could include number of women employed; female income; hours saved by women as a result of reduced fuelwood collection etc.).

Monitoring and Reporting

Responsibility for data capture, measuring baselines and reporting primarily sits with implementer(s). Key Performance Indicators (KPIs) as tendered will be included in the Contract and used to measure performance. KPIs will include poverty reduction and gender equality, Porfolio Level primary and secondary benefit KPIs. All KPIs will require collection of gender-disaggregated data where possible.

The Prospero IT platform/dashboards provided by M&R contractor PA Consulting will be used by SDT to input and monitor a range of information such as primary and secondary benefit; gender equality and social inclusion; SDGs; finance; VfM; risk; staffing; synergies with other PF programmes operating in Indonesia, and programme ‘good news’ stories.

During the Annual Review process, SDT will require central support from HMG experts on gender, inclusivity and poverty reduction to ensure a robust evaluation of Palladium’s performance in these areas.

1. The Programmes’ first full Annual Review will take place in 2020. As agreed between the SRO, PFDU and JFU, a light-touch Annual Review will take place in November 2019.
2. The implementer(s) will submit monthly accounting and performance reports to the SDT. This will enable SDT to make key decisions regarding programme adaptation, to ensure efficiency levels are maintained and effective delivery against outcomes and impact are kept on track.

Palladium will be expected to submit reports on a regular basis (at least quarterly), providing summaries of progress against the work plan deliverables and LogFrame outputs (with gender-disaggregated data where possible).

These reports will be scrutinised by SDT and the Programme Steering Group who will provide challenge to ensure it is robust and transparent; reports will be subject to continuous improvement.

Regular meetings to discuss results, VfM and performance will take place throughout the Programme’s duration and particularly at key stages of implementation. Outputs from these discussions will also be issued to inform the Annual Review Reports.

Reporting Frequency and Costs

Consistent with PF requirements, implementer(s) will develop a quarterly results reporting system that takes into account MREL guidance, particularly around data quality and consistency, as well as the Prospero IT platform and PF Annual Review formats.

Evaluation and learning

The programme will conduct Annual Reviews where progress and lessons learned are shared with stakeholders and integrated into the communications strategy. In addition, this programme could be selected by the central PF for an independent evaluation. If so, we will work with the E&L contractors to develop and carry out the work.

The overarching evaluation methodology will be decided by the E&L evaluators and SDT will manage the coordination between stakeholders in-country. If the programme is not selected for a centrally-funded evaluation, SDT may still conduct its own mid-term evaluation and seek support from the E&L evaluators.

Communications
Communications will be a vital part of ensuring the Programme is a success in ensuring the positive spill-over impacts and reputational benefits for the UK.

Given one of the barriers to international and UK companies doing business in Indonesia is a lack of information and inaccurate perception of risk, communications to stakeholders on the reality and availability of opportunities will be vital to achieving the expected PF impacts.

The key objectives for communications will be:

- Influence national and local decision-makers to ensure effective implementation and delivery of the programme.
- Use the programme to raise the profile and reputation of the UK in Indonesia while facilitating access to stakeholders in national and local government and in the private sector.
- Promote the programme across UK HMG audiences.
- Ensure UK companies are aware and able to take advantage of opportunities and access resulting from programme activities.

The main audiences are:

- Indonesian local and national government, in particular decision makers in key sectors targeted by the programme.
- Indonesian media and citizens (including targeting women and the poor when appropriate).
- Indonesian businesses and investors interested in partnerships with UK companies.
- HMG Departments/Agencies.
- Energy Businesses and investors.

Dedicated non-ODA resource embedded in DIT Indonesia Team and in the DIT Energy Team in the UK will directly target UK renewable energy sector to support secondary benefit realisation.

If there are significant successes resulting from programme activity, the team will consult with the FCO SE Asia regional hub, Media office and the PFMO communications team on the potential for informing UK media. Working with PFDU, defensive press lines and FAQs are in place.

Strategic activities will include:

Ongoing engagement with relevant national government departments, governors and local government officials in targeted regions to raise the profile of programme activities; advertise the potential of UK engagement in key sectors; and ensure we are aware of developing opportunities (e.g. major contracts, policy reforms etc.) and corresponding risks.

Timely media moments (blogs, tweets, editorials) in Indonesia to highlight programme activities and successes to a wide audience capitalising on reputational benefits for the UK.

Communications activities including meetings, presentations and trade missions (non-ODA funded) with UK companies that could benefit from the opening up of opportunities in Indonesia’s regions. This will link to work undertaken by DIT to directly facilitate business wins.

In terms of implementation responsibilities, communications activities will be co-led by SDT (with support from DIT and Media and Communications Section in British Embassy Jakarta as appropriate) and the Palladium. The division of key responsibilities is likely to be as follows:

SDT/British Embassy Jakarta

- Develop and continually update strategic communications plan.
- Identify and undertake media publicity for fund activities.
- Identify and communicate with international companies, including in the UK and Indonesia.
- Ensure the Programme is promoted through wider Embassy activity and engagement with stakeholders.
- Coordinate communications activities with implementing partners.

Palladium

- Engage with sponsoring departments and/or local authorities to ensure activities are aligned with, and embedded in, wider implementation plans.
- Support outreach to potential beneficiaries e.g. promote opportunities to private sector including UK companies.
- Provide information to the Embassy to support wider media activity.

During the mobilisation period, working with the communications leads in FCO, BEJ, DIT and Palladium, SDT will develop a detailed communications strategy and delivery plan.