Prosperity Fund Programme Reporting Requirements
Annex A to the SRO letters formally allocating Prosperity Fund finance to departments for individual programmes set out the conditions governing allocation of funds including the reporting requirements related to the use of that money. This note sets out the content of reporting expected by the Joint Funds Unit (JFU). It applies both to programmes in receipt of transitional funding as well as those under full implementation following final business case approval. The change in reporting requirements reflects also the shift from many small-scale projects in the Prosperity Fund’s first year to the larger programmes for years two to five.
Monthly Financial Reporting of expenditure and forecasts – this is critical for the JFU to manage ODA/GNI calendar year cash pressures and overall financial year spending (accruals) across the portfolio. As set out in allocation letters, reporting “should include progress made in spending funds and ensuring that any risks (of both an over- or underspend) are highlighted to the JFU with a clear plan for mitigating those risks.” This is important as increases in subsequent annual budgets resulting from this must be approved by the Prosperity Fund SRO (currently John Mahon, DG Exports, DIT), as similarly, does any in-year overspend.
Quarterly Progress Reports – should include narrative reporting of progress against outputs, including against the agreed work plan; an update on the funding position; and on key programme risks. The risk update should focus on residual risk, ie: after implementation of mitigation measures, and include an assessment of risk trends, ie: increasing, decreasing or stable. Any other significant issues, eg: where a risk has come to pass and is being responded to, or unforeseen challenges, should also be covered. The quarterly report will draw on monitoring by programme teams and on routine implementing partner/supplier reporting. Data (disaggregated by gender, income quintile and age) on output level key performance indicators may be informed by MREL data. Staff numbers and spending should also be specifically addressed. Quarterly reports should be provided to PFMO within six weeks of the end of the quarter to which they refer and be signed off by SROs.
Annual Review Reports – annual reviews represent a key strategic opportunity: to take a step back and assess the prospects for meeting outcome level objectives and key performance indicators; how gender and inclusion issues are addressed; review the validity of the theory of change and whether this needs amendment; review the risk framework and how well risks are being managed; consider how well value for money is being driven across the four dimensions of economy, efficiency, effectiveness and equity; and report on progress against the communications and stakeholder management plan. A reporting template is attached along with a smart guide on how to complete it (an alternative template has been provided for programmes with allocations up to £1 million).
The findings of annual reviews will feed into overall portfolio quality reporting to Ministers. Annual Reviews will also provide a strategic opportunity for Ministers to consider the reallocation of resources away from poorly performing and towards highly performing programmes. As such they should be signed off at the least by SROs.
Programme Governance – each programme is supposed to set out its governance framework and a representative from the JFU is entitled to sit on the programme’s governance board(s). Terms of reference of the governance board should be sent to the JFU.
This reporting will play a key role in identifying those successful programmes and programme components that could benefit from additional funding. It will also identify those where progress is less than expected and remedial action is required, or from where funding should be reallocated. As such this reporting will be critical to the active portfolio management approach called for by the Prosperity Fund’s Ministerial Board. It is strongly recommended that every programme has a delivery plan, which should capture the essential information that will be required for monitoring, as well as facilitating action on review recommendations. There is no set format for delivery plans, which should be developed by teams to meet their own programme management needs.
## Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: MENTARI* UK-Indonesia Low Carbon Energy Partnership (referred to in pre-delivery as Indonesia Renewable Energy Programme (IREP)
Programme Value: £13.5m		Review Date: 4-6th May 2021
Programme Code: GB-GOV-3-PF-INJ-REP-922	Start Date: 6 January 2020 (date of start of programme delivery). (SOBC approval date January 2018, OBC approval date September 2018)	End Date: 11 December 2023

Summary of Programme Performance
Year	December 2019 (Light Touch)	Jan 2020 – April 2021
Programme Score	A	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review
The Review Team (RT) were pleased to observe that in spite of the significant challenges posed by the Covid-19 pandemic since the launch of the programme, the programme has made significant progress towards its objectives, in particular in establishing good working relationships with its key stakeholder the Ministry of Energy and Mineral Resources. RT have noted that the programme has also made significant improvments in its delivery through its commercial partner consortium led by Palladium, who are fully on board with the objectives of the programme.
RT felt that it is too early to evaluate some of the detailed Outputs, due to the early stage of the programme and the obstacles imposed by Covid-19. The programme team, however, feel confident that they will be able to catch up and deliver the main objectives of the programme within the timeframe of the Mentari Programme.
As such the RT are pleased to assign a A rating for the current stage of the Programme.

List of recommendations for the next year
Recommendation 1: Financial Information Monitoring – Whilst the Review Team found the programme had close monitoring of the invoicing for the Palladium expenses, RT found it difficult to assess the achievement of the KPIs by the Delivery Partner against the payment milestones. RT therefore recommend that a more structured budgeting is put in place to enable the detailed forecasting for the remainder of the programme which is tied in with the delivery milestones by Palladium.
Recommendation 2: the Brokerage Strand is the most challenging part of the programme and will require close monitoring of its objectives in order to achieve its successful delivery within the short time scale of remaining 2.5 years. Whilst the RT appreciate that the current programme has been impacted by the Covid-19 pandemic, it is important that the strand is able to achieve its objectives.
Recommendation 3: Demonstration Project strand should be monitored closely so that it is tied in with the Policy and Brokerage strands.
Recommendation 4: The Collaboration Network would require closer ties with the Ministry of Finance who are responsible for the Green Finance policy and can influence the greater Policy strands in the programme, alongside the Ministry of Energy & Mineral Resources.
Recommendation 5: The programme should continue to develop its Secondary Benefits strategy and engage with the delivery partner during programme mobilisation.

SRO Commentary
I am grateful to the Review Team for their report. I am pleased to see the Mentari programme awarded an ‘A’ rating over its first year, and believe this is a fair reflection of the programme’s work. It has been a challenging year to deliver programmes due to the Covid-19 pandemic, and while this has caused some delays and presents some risk as the report acknowledges, the response from the Sustainable Development Team and Mentari consortium partners has kept the programme largely on track to deliver its ambitious goals.
Mentari forms a key part of HMG efforts to support accelerated low carbon energy transition in Indonesia, and it has made a significant contribution to wider HMG work on COP26. A major highlight of the programme to date is the partnership approach with the Government of Indonesia. This has enabled us to take advantage of new opportunities, such as Indonesia’s apparently increased willingness to phase out coal. This furthers our efforts to become a close and trusted partner for Indonesia as it continues its low carbon development pathway.
I agree with the recommendations set out in this review and will ensure the Sustainable Development Team and delivery partners take steps to respond to these, with progress reviewed over the next year. I note in particular, and share, the comments on the Brokerage Strand. I stressed at the last Steering Board the need for increased action in this area. It is is an ambitious undertaking and will require high levels of skill, innovation and focus to deliver effectively.
Mentari is well set up to deliver impact in the coming years at good value for money and I look forward to seeing the results, as, I know, does the new SRO who will take over from me from this point.
List of Acronyms
ASEAN: Association of Southeast Asian Nations
COP 26: UN Climate Change Conference under UN Framework on Climate Change
CPN: Competitive Procedure with Negotiation
DFID: Department for International Development
DIT: Department for International Trade
PFDU: Prosperity Fund Delivery Unit
JFU: Joint Funds Unit
ODA: Official Development Assistance
GESI: Gender Equality and Social Inclusion
FBC: Full Business Case
FCO: Foreign and Commonwealth Office
FCDO: Foreign, Commonwealth and Development Office (from September 2020)
GDP: Gross Domestic Product
GF: Green Finance
IREP: Indonesia Renewable Energy Programme (former name for Mentari programme)
LCEP: ASEAN Low Carbon Energy Programme
MEMR: Indonesia Ministry of Energy and Mineral Resources
MOU: Memorandum of Understanding
MREL: Monitoring, Reporting, Evaluation and Learning
OBC: Outline Business Case
OJEU: Official Journal of the European Union
PF: Prosperity Fund
PLN: Indonesia state-owned national electricity company
RE: Renewable Energy
SDA: Social Development Adviser (Prosperity Fund)
SDGs: United Nations Sustainable Development Goals
SMEs: Small and Medium Enterprises
SOE: State-Owned Enterprise
SRO: Senior Responsible Officer
VFM: Value for Money

## A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-50-PF-13B-INJRE/summary
DevTracker Link to Log frame:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-50-PF-13B-INJRE/summary

Indonesia Renewable Energy Programme
Indonesia is the world’s 4th most populous country (with over 260m people) and is a G20 economy, predicted to be a top ten economy by 2030 accounting for almost 35% of ASEAN GDP. However, over 28 million Indonesians live below the poverty line, inequality is rising and there are major structural issues holding back development, namely lack of infrastructure and a poor business environment (only recently, Indonesia’s Global Competitiveness Index ranking deteriorated 5 places from 45th to 50th).
Access to reliable, affordable energy is a key constraint to economic growth and raising standards of living, with the problem particularly acute in the remote islands of eastern Indonesia. The government has set targets to provide electricity to 100% of the population yet significant numbers of communities lack access to affordable, reliable 24/7 electricity with sufficient capacity to enable productive use, such as supporting business growth of fishing (20% of Indonesia’s poor are fishermen), agricultural and tourism industries.
At the same time, Indonesia is among the world’s top ten greenhouse gas emitters. In 2016 the government set targets to reduce its emissions by 29% against a Business as Usual scenario by 2030. Decarbonising the energy sector will be crucial to meeting this goal. National plans target a 23% share of new and renewable energy by 2025, yet given current trajectories in the sector this target currently seems a long way off.
However Indonesia has huge potential for generating its electricity and providing power from renewable sources: solar, hydro, wind, wave, tidal, geothermal and others. Uptake has so far been slow, with policies and regulations restrictive to renewable energy proliferation, particularly private sector investment. The energy sector is dominated by fossil fuels, which currently account for around 80% of electricity generation (coal production forms a major domestic and export industry). However, there is a huge potential for a substantial increase in generation share from renewables, including community-led solar mini-grids in eastern Indonesia replacing generators powered by costly imported diesel.
Creating favourable policy and regulatory frameworks that support renewable energy, encouraging large scale private sector investment as well as supporting community-led small-scale projects would see renewable energy help to drive inclusive economic growth and poverty reduction, in a sector in which the UK public and private sector has significant experience and expertise to offer. Developed as part of the FCO’s Prosperity Fund portfolio, the Indonesia Renewable Energy Programme (IREP), now known as the MENTARI UK-Indonesia Low Carbon Energy Partnership, aims to increase renewable energy generation share nationally and improve inclusive access to clean energy for poor communities in eastern Indonesia, reducing poverty and supporting economic growth by:
- Improving renewable energy policy, regulation and financial instruments through technical assistance to national and regional government;
- Increasing investment in renewable energy by bridging the gap between available external finance, technology and viable programmes through brokerage;
- Accelerating development and innovation in renewable energy by enabling innovative, replicable demonstration projects; and
- Enabling communication and partnering between domestic and international renewable energy sectors, including donors, industry, SMEs and academia to develop domestic innovation, best practice and knowledge transfer.

The MENTARI (Menuju Transisi Energi Rendah Karbon Indonesia – Mentari means ‘dawn’ in Bahasa Indonesia) programme aims to deliver inclusive economic growth and poverty reduction in Indonesia by supporting low carbon energy uptake. MENTARI is a four-year Programme (2020 - 2023). By working closely with the Government of Indonesia (GOI) and other stakeholders to improve the enabling environment and drive investment, MENTARI aims to demonstrate the possibilities of low carbon energy for Indonesia's economic development, job creation and social inclusion, while helping to mitigate climate and environmental impacts. The programme specifically focuses on how low carbon energy can best support disadvantaged communities in eastern Indonesia.
In addition, the programme forms a key component of HMG’s low carbon development support for Indonesia (with a focus on clean growth akin to the UK’s strategies, rather than a focus on tackling climate change in purist terms), including as the UK prepares to host the COP 26 international climate summit in 2021. The programme will be instrumental in the UK’s efforts to encourage raised ambition for emissions reductions in the energy sector.
Development of the renewable energy sector and tackling barriers to foreign investment will also yield secondary commercial benefits for international, including UK renewable energy businesses (renewable energy goods and services make up approximately 17% of UK exports to Indonesia).
The interventions above will be delivered through four interlinked programme strands:

The Policy Strand will work with national level government and public institutions, including the Ministry of Energy and Mineral Resources (with which British Embassy Jakarta has signed a Memorandum of Understanding covering low carbon work) and other ministries, and the state-owned electricity company PLN, and sub-national authorities to address renewable energy policy, regulatory and fiscal issues.

The Collaborating and Networking Strand will support domestic and international knowledge transfer of renewable energy best practice, including technologies and business models; it will support coordination among low carbon donor activities, promote public messaging on renewable energy and economic development and raise awareness of other programme activities.

The Brokerage Strand aims to leverage £500m+ (Palladium confirmed they would commit to delivering £500m rather than the original £150m target) of new investment in renewable energy projects from public, private and multilateral sources, with a focus on eastern Indonesia. This Strand includes a suite of activities to bring projects and finance together, including technical assistance to support bankable project development and reach financial closure, raising awareness in the domestic, regional and international markets of project opportunities in Indonesia, and active matchmaking between project developers and financiers.

The Demonstration Project Strand will fund the development replicable off-grid business and cost recovery models. This strand will showcase the importance and opportunities of community engagement, mainstreaming GESI, demonstrate replicable business models to attract private sector investment, and showcase renewable energy as a vehicle for supporting productive uses of energy in supporting commercial activities, for example cold storage for fishing communities or solar irrigation.

Mentari received approval for its Outline Business Case in July 2018. In February 2019, the British Embassy Jakarta signed a Memorandum of Understanding with the Indonesian Ministry of Energy and Mineral Resources covering cooperation on low carbon development, announced by the UK Foreign Secretary and his counterpart as part of the Indonesia – UK Partnership Dialogue in July 2019. The procurement of a main implementing partner, via an OJEU Competitive Procedure with Negotiation (CPN), resulted in the identification of a preferred supplier in October 2019. IREP received approval for its Full Business Case on 30 October 2019 and contract signature and programme mobilisation with the delivery partner took place in December 2019 and January-April 2020 respectively. The programme moved into full delivery in May 2020 following a mobilisation phase and held an official launch with the GOI in July 2020 (although many aspects had started delivery within the mobilisation phase and diplomatic engagement, coupled with policy and regulatory assistance through the Embassy team had been in place for considerable time.
The challenges imposed by the Covid-19 Pandemic has meant some delays in implementation of the strands.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
Review Team are satisfied that significant work is being done in the area of inclusive growth where there is active involvement of stakeholders in various strands to promote the G&I issues.

Annual outcome assessment (Secondary Purpose)

In spite of the Covid-19 pandemic difficulties, the programme has managed to make inroads into the Policy strand, specifically with the Ministry of Energy and Mineral Resources (MEMR), whereby impressive work is being carried out in assessing the areas of reform that are necessary to encourage the participation of the private sector in Indonesia’s Green Energy programme.
It is still too early in the programme to assess the progress of some of the strands, and the interdependencies between each imply that any delays or barriers to delivery in one strand may impact the delivery of the others. This is particularly the case with the Policy and Demonstration Project strands which will impact the Brokerage strand in delivery of private sector investment in the targeted projects (although brokerage is designed to operate within the current regulatory environment).

Overall output score and description
The Review Team feel that the programme has made good progress in spite of the challenges with Covid and is on track to delivering the next phase of the programme, including engaging with private sector financiers to start realising wins in the brokerage strand.
The RT are also aware that challenges remain with the implementation of the Green Finance/energy regulatory policies by the GoI, which may impact the attractiveness of investment opportunities to the private sector. RT, however, feel that the credibility which the programme has established with its stakeholders gives it a good opportunity to influence policy and regulatory reform to unblock those barriers.

As such the RT are pleased to assign a A rating for the current stage of the Programme.

Key lessons
The Embassy Programme team and Mentari delivery partners highlight below some key lessons learned from the first year of programme implementation:
Context and Political Economy
- Policy and regulatory strand assistance success in delivering outcomes and impacts is dependent on political and economic factors that are not within Mentari’s control. This was a known risk at the outset of the programme which explains the configuration of the programme to also deliver Brokerage, Demonstration and Collaboration & Networking strands, along with the involvement of the Embassy team in investing diplomatic capital. Building relationships in-country, effectively blending Mentari technical expertise and assistance with HMG diplomatic efforts and understanding local demand and context is therefore key to increasing chances of success and in creating a more valuable and flexible UK-Indonesia partnership.
- Engagement and relationship building with state-owned electricity utility PLN is key for success in some aspects of the programme, given the pivotal role of this organisation in delivering Indonesia’s electricity plans.
- Covid-19 impacts have largely been well managed by the Mentari programme, which has been key to keeping the programme on track. Frequent communication between all Metari stakeholders and the ability to adapt programme activity, including delaying, dropping or ‘doing differently’ existing plans as well as designing alternative or new activity, has ensured the programme has remained relevant in spite of the pandemic.

Programme support for HMG objectives
Mentari has become an essential component of the UK’s low carbon energy and climate change work with Indonesia, including as part of preparations for COP26. These all share the objective of accelerating the development of renewable energy in Indonesia as an alternative to fossil fuels, in order to bring benefits for the economy, people and the environment. The flexible technical assistance, in coordination with the Embassy, Mentari programme has been able to provide valuable work in driving forward dialogue and momentum on these issues. This has been helped by the UK’s leadership in COP26 which has supported the programme. One example of this joint approach has been Mentari’s support for the Friends of Indonesia Renewable Energy dialogues, which in Indonesia deliver the objectives of the COP26 Energy Transition Council. Through these, Mentari has supported the conveing of development partners to engage in dialogue with Indonesia on issues including the phasing out of coal power plants, acceleration of renewable energy development and modelling of long-term energy planning scenarios to achieve faster low carbon transition.

Ways of Working and Structures
- The Embassy programme team has developed a hybrid working arrangements with the delivery partner consortium in order to more effectively blend the technical expertise and capability of delivery partners with the dilomatic and government-to-government relationships with HMG. This has been effective in increasing the impact of the programme, but has taken some time and effort on all sides to reach effective working relationships.
- Some resources within the Mentari delivery partner have needed to be reconfigured since the start of the programme in order to increase the efficiency and capability of the consortium. These changes, including the appointment of a new ‘Team Leader’ role and changes to Gender, Equality and Social Inclusion support, have had positive impacts. Additional resources have also been provided to the Brokerage strand as it was felt that the configuration, capability and capacity of the brokerage strand needed to increase in order to match the high ambition of the strand’s targets.
- RT have observed that the capacity of the FCDO programme team has been stretched, particularly given the pressures of Covid-19 and the additional need to work on COP26 preparations (including the new Friends of Indonesia Renewable Energy dialogues), FCDO merger and other HMG priorities outside of the low carbon energy sector.

Key actions
Please refer to action Recommendations 1-5 as detailed above.

Summary of changes to the logframe since the last annual review
N/A – This is the first full Annual Review.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

1- POLICY STRAND:
Output Title	Policy Strand, Output 1: GoI supported with recommendations on subsidiary regulations & effective implementation of new Perpres
Output number per LF		1	Output Score	33%
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of recommendations on subsidiary regulations developed	Target: 3 / Achieved: 1	On schedule

Key Points
The output is on schedule according to the current logframe. There are no major risks noted. The programme team have identified the complex process of securing Govt buy-in to new regulations and while they appear to have navigated and connected with that very effectively, the ability to secure the remaining work in this output will depend on continued cross-government engagement, as the country presents its 10yr capacity plan and emerges from COVID19 into economic recovery. RT has noted that the picture may be uncertain.

Output Title	Policy Strand, Output 2: On-grid policy and regulatory recommendations developed (that mainstream GESI and business case) and presented
Output number per LF		2	Output Score	100%
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
On-grid policy and regulatory recommendations developed	Target: 1 / Achieved: 1	Achieved

Key points
Output complete. No comments

Output Title	Policy Strand, Output 3: Off-grid business model options defined (incl. GESI aspects), evaluated, and proposed
Output number per LF		3	Output Score	100%
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
At least 3 off-grid business models, including G&I aspects, by year 1 defined	Target: 3 / Achieved: 3	Achieved

Key points
Output complete. No comments

Output Title	Policy Strand, Output 4 Preparation / recommendation of a regulatory framework and associated capacity building to implement the agreed business model(s)
Output number per LF		4	Output Score	0%
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1 detailed off-grid model design document (including regulatory framework and needed capacity building for implementation)	Target: 1 / Achieved: 0	First milestone December 2021

Key points
RT identified in interviews with the policy and demo strand leads how the demonstrator project’s delays (due to COVID) may slow down this output. Although there remains time to deliver it, and the programme team were optimistic, RT feel that there is a moderate risk of missing this milestone.
Recommendations
Continue to monitor the dependency between the demo project and this output and assess whether the logframe requires revision and to push back the expected date of delivery. If so, there may be wider impact on the policy strand.

Output Title	Policy Strand, Output 5: Guidelines and TA on planning, procurement, & contracting provided to PLN
Output number per LF		5	Output Score	0%
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3 guidelines developed for PLN by the end of the Programme	Target: 3 / Achieved: 0	First milestone December 2021

Key points
RT did not have the opportunity to speak to PLN directly during our interviews but it is clear from the governance that they are represented indirectly on the Steering Committee. Continued buy-in from PLN is required for this output. Although the interviews identified some risk to that given the significantly reduced additional capacity requirement, PLN announced (unilaterally) its decision to reach net zero by 2050 during the weeks following the AR interviews. Continued confidence therefore feels realistic.
RT were also informed that due to financial pressures which PLN are currently under, it is making it more difficult to prioritise Green projects which are more expensive.

Recommendations
Link the programme’s output directly to PLN’s political commitment to decarbonise, in order to ensure continued buy-in and visibility for this output.

2- COLLABORATION & NETWORKING STRAND:
Output Title	C&N Strand, Output 1: Matching, coordination and knowledge exchange between key stakeholders in technical low carbon energy skills (including education) sector
Output number per LF		3	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of International and Indonesian academic and/or training institutions receiving programme matchmaking and/or knowledge sharing support	Target: 1 / Achieved: 1
Number of joint activities organised by International and Indonesian academic and/or training institutions	Target: 0 / Achieved: 0	No target in 2020. To be established in Y2 of MENTARI
Number of diagnostic reports and/or products developed on low carbon energy TVET in Indonesia	Target: 1 / Achieved: 1

Key Points
The Collaboration and Networking strand has evolved in the last year and the focus has moved more into enabling, enhancing and facilitating other strands.
The partnerships between UK and Indonesian universities was ambitious, and have proven difficult to realise in practice. Conversations on this work continue. The Friends of Indonesia Renewable Energy Dialogues (FIRE Dialogues) have proven a valueble donor co-ordination tool in a crowded and at times disjoined space, and have allowed for greater collective action particularly in regards to Government of Indonesia’s regulatory and energy planning reforms.
Recommendations
The programme team are already considering reviewing the C&N strands to mainstream into the other programme areas which is sensible. As part of this, the programme team should consider setting new objectives and goals for this area, reflecting the evolving nature of the need and making sure the work is an integrated part of the programme’s Theory of Change, in order to avoid the risk of adhoc activity.

Output Title	C&N Strand, Output 2: Branding & communication products produced to share lessons
Output number per LF		3	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of communication products produced, disseminated, and (potentially) used	Target: 2 / Achieved: 3

Output Title	C&N Strand, Output 3: Facilitate knowledge sharing and develop partnerships
Output number per LF		3	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of stakeholder (inter/national) engagement plan developed	Target: 1 / Achieved: 1
Number of events (consultation, facilitation, FGD, workshop) to facilitate knowledge sharing and partnership development	Target: 0 / Achieved: 19

3- BROKERAGE STRAND:

Output Title	Brokerage Strand, Output 1: Innovative Financing mechanisms/better de-risking schemes supported (includes access to these facilities) or developed
Output number per LF		1a	Output Score	N/A
Risk:		Minor/ Moderate/Major/Severe/	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new and/or existing financial schemes/facilities/mechanisms (i.e. blended finance facility or other de-risking solutions) that are receiving TA support	Target: 2 / Achieved: to be achived by end of the programme	N/A

Key points
The output will be an important contributor to the success of the programme which will support the key Brokerage Strand of £766m investment target. The Ministry of Energy, while in charge of the policy, is dependent on the Ministry of Finance for the provision of financial incentives and it is therefore important that the Mentari programme has a direct engagement line with the MoF as one of the key stakeholders in order to influence the likelihood of their approval for the various schemes.

Output Title	Brokerage Strand, Output 2: Extension of marketing and DD services for existing public and private investors.
Output number per LF		1a	Output Score
Risk:		Minor/ Moderate/Major/Severe/	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of marketing and due diligence proposals submitted to financial institutions.	Target: 5 by the end of the programme (cumulative) / Achieved: 1 for the target year,	1 event achieved.

Output Title	Brokerage Strand, Output 3:Continous engagement with financiers and developers for matchmaking and improving understanding of regulatory environment and opportunities.
Output number per LF		1a	Output Score	100%
Risk:		Minor/ Moderate/Major/Severe/	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of facilitations, meetings, trainings, FGDs, and/or events organised.	Target: 15 / Achieved: events or one-on-one engagements for both financiers and developers by the end of the programme (cumulative.)	2 to date

Output Title	Brokerage Strand, Output 4: Pipeline of quality low carbon energy projects (in “support mandate”)
Output number per LF		1a	Output Score	0%
Risk:		Minor/ Moderate/Major/Severe/	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Size and value of probability weighted pipeline for on-grid and off-grid clean energy projects (cumulative.)	Target: £766m value of probability weighted pipeline for on-grid and off-grid clean energy projects / Achieved: N/A	Not at the stage where it is possible to gauge the probability of success.

Key points
The RT were informed that the programme has already produced a pipeline of £1.0bn in capital value of which a portion of successful projects will score towards Mentari’s £766m investment target. The RT believe, however, that the £766m target maybe challenging as £100m has been secured for the current year, with the remaining years requiring swift catch up with the balance target. This may imply putting considerable pressure on the programme to implement the Policy strand work and the successful completion of the Demonstration Project, in order to attract the private investors.

Recommendation: Closer monitoring of the strand and an update of any Risk issues which need to be addressed, while updating the forecasts for each year.

Output Title	Brokerage Strand, Output 5: Tailored TA to projects delivered )Including projects linked to green bonds).
Output number per LF		1a	Output Score	0%
Risk:		Minor/ Moderate/Major/Severe/	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of low carbon energy projects that are receiving TA and brokering services.	Target: TA service to at least 30 projects provided by the end of the programme (cumulative). / Achieved: 1	1 acheved in the past year, although the numbers ramp up to 10, 20 and 30 cumulatively by end of the programme.

4- DEMONSTRATION PROJECT STRAND:

Output Title	Demo Strand, Output 1: Feasibility studies & business cases (including technical, economic & social potential of low carbon energy) developed
Output number per LF		1	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of feasibility studies and business cases developed	Target: 1 / Achieved: 2	Progress was initially slowed by COVID, but has recovered somewhat in the second half.

Key Points
Delays due to COVID-19: COVID has slowed the implementation of this strand. Of all the programme strands, the demonstration strand has been the most susceptible to the disruption of the pandemic because of the need for an on-the-ground presence to carry out much of the pre-feasibility, feasibility and engagement work. RT heard that this has not been possible for much of the year. Project installation and procurement has been delayed until next year and the original schedule for the feasibility studies was pushed back to the second half of the year. The programme team did, however, adapt its delivery model to work through the local presence, instructing them on how to carry out the feasibility studies themselves when flying-in a team from Java was considered too high risk, which was an innovative adaption. While this has caused some data quality issues, it has also provided early lessons learned on working through local partners and generated additional insights that a team from outside the area would not have identified.
Solid project, but role as part of wider programme is at risk: The project is demonstrating good practice in critical areas for success and generating impact – for example engaging with local government, incorporating opportunities for G&I, thinking widely about use-case (entrepreneurs, healthcare etc) and considering local context. RT consider that the logical link to the wider programme may be at risk, however, because of the delays to this strand and the resulting mis-match in timings between the strand and the policy strand that the lessons learnt were intended to feed into. The demonstration strand was intended to test one of the off-grid business models that the GoI and PLN were considering as part of their policy refresh, but the delay has meant that the policy work is proceeding without the results of the business model test being available.
Strong, established team: This strand is benefiting from the long term presence in the area of delivery partner Hivos. This has clearly been very beneficial in getting the local government on board.
Recommendations
The programme team should review the contribution the strand is making to the wider programme and ensure the demonstration project is still contributing to the wider programme aims rather than becoming in effect a separate, parallel project.

Output Title	Demo Strand, Output 2: Off-grid low carbon energy demonstration project implemented with viable project structure and governance
Output number per LF		2	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of small-scale off-grid low carbon energy facilities established and operational	Target: 0 / Achieved: 0	This piece of work begins in earnest next year

Key Points
This output has been delayed by COVID, but procurement is due to start in May 2021. This output is not due this year.
Rising scope and rising cost: The scope of the project appears to have crept up during the year, with an increase in the kWh to be installed and a connection across 1.5km of forest to another village to be added. Review Team were informed that the reason for the increase in scope was following detailed discussions with Hivos, where serios concerns over community relationships were discovered. The revised scope ensures a more ‘inclusive’ solution for the nearby communities of Mata Woga as well as Mata Redi where both would be electrified. A rigorous quality and ethics standard has been set to avoid common failures in similar systems and issues of Human Rights in the supply chain. This has inevitably resulted in raising the cost of this strand, which may impact the VfM assessment for it.
Recommendations
- The programme team should ensure it is clear what the project is attempting to demonstrate, that it can still achieve that aim and that the target audience is bought into the demonstration, so that the lessons learnt have the best chance of influencing change.
- The programme team need to guard against scope creep and rising costs, particularly given potentially weaker link to the overall programme aims. The team need to ensure costs remain in-line with wider value to the programme.

Output Title	Demo Strand, Output 3: Inclusive off-grid development models (including training on low carbon energy business models, O&M, PuE, and GESI potential) provided to the community, local government, BUMDes, BLU and O&M providers
Output number per LF		3	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of trainings on low carbon energy business models (Technical & non-Technical)	Target: 5 / Achieved: 5

Key points
The output has made good progress, completing the targeted five training sessions despite the challenges of COVID. The training incorporated insights from local consultations and research, including considering the Productive Use of Energy sessions, the high rates of domestic violence and higher rates of crime in the area. This demonstrates good understanding and tailoring to local context. A 40% participation rate for women provides hope that the benefits of the training will be shared broadly within the community, although more data would be needed to see if the training has reached other types of excluded communities such as the socially or economically excluded communities, those with disabilities etc. This may be a stretch goal.
The reporting confirms that the training was delivered in November 2020, but there appears to be a gap in some quantitative data (such as targets for number of people trained) and qualitative data to go alongside the quantitative data. Questions such as quality of the training, attendee feedback and follow on surveys to assess the longevity of the learning and the extend to which the training has driven or amended action would be beneficial to assess the likely sustainability of the knowledge sharing. This is a particular concern in areas such as the operation and maintenance (O&M) of the equipment that risks becoming a white elephant if the training is insufficient to enable local teams to take over the equipment in the longer term and to expand the economic opportunities of the trainees.
Recommendations
The programme team could consider embedding qualitative assessments of the capacity building alongside the qualitative data and setting targets for number of people trained.

Output Title	Demo Strand, Output 4: Knowledge products on demonstration project developed and disseminated
Output number per LF		3	Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of knowledge products produced & disseminated	Target: 0 / Achieved: 0

Key points
The logframe records zero knowledge products produced and disseminated against a target of zero, but the delivery partner’s annual report indicates four products produced in 2020. This may be due to the different reporting windows of the logframe and annual review, or to a tighter definition of what the logframe records considers recordable knowledge products.
As above, qualitative indicators are not included for these reports. There is also does not appear to be a record of how these products have been disseminated, for what purpose, to whom and to what benefit. From the titles, it is assumed these products were preparation for the training courses.
Recommendations
The programme team should consider qualitative indicators for the knowledge products to verify the quality of the outputs and therefore the likelihood of them contributing to the intermediate outcomes.
The programme team should consider a communication and dissemination plan for any products resulting from this programme (not just the desmontration strand) to help ensure knowledge and lesson learning reaches the maximum relevant audience and that the value extends beyond the life of the programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

The Review Team noted that:
- Brokered projects are open to the UK and international companies to promote a diverse and innovative supply chain.
- The main cost across the programme is human resources to deliver the technical assistance and capacity building activities. The tendered price is fixed and capped (and if actual costs are lower the programme effectively receives a rebate)
- In accordance with the contractual provisions, funds to the contractors are posted to receipt on a monthly basis in arrears on receipt of a valid invoice supported by a breakdown of activity that has been delivered. The Contract Manager (UKB D6) is responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary.

RT were informed that the programme had underspent in FY 2020/21. Some of this was due savings on office space and travel restrictions during COVID, but the largest impact came from the delay to the demonstration strand that caused the procurement to move to FY 2021/22.
The programme team need to implement a system for setting and assessing spend by programme strand. It is understood this may be a challenge because of the cost model of the contract, but a key component of the value for money assessment is whether the cost of individual strands is in line with initial expectations, delivery progress and with value earned.

VfM performance
RT do not consider able to provide an overarching assessment of the Value for Money of the programme at the time of the Review, mainly due to the early stage stage assessment of it, and particularly in light of the delays in achieving some milestones due to Covid-19. (A more meaningful VFM assessment should be feasible over the whole life of the programme). RT, however, believe that the programme team has made strong mitigation plans to overcome these delays and are confident in achieving their milestones for the programme.

Economy
The programme team have carried out some benchmarking. To support efforts to achieve value for money over the contract, the FCDO have contractual rights to require the delivery partner to conduct a benchmarking exercise on any or all costs in the contract at any time, to ensure they remain competitieve in the market.
The pricing model is an innovative mix of cost with capped charges and rebate provisions, which the Procurement Team believe may have potential to be adopted in other procurements i.e. price is based on an actual cost profile for deploying the resources to deliver the service specified. If it costs the delivery partner more to deliver the service, they will absorb the additional cost. If it costs less, the FCDO will not be charged against the profile - effectively receiving a rebate allowing for deployment of resources elsewhere. The profit margin is fixed as a percentage and capped at a certain amount.
Efficiency
From DP’s annual report, “The team has identified opportunities to re-allocate budget items initially planned for activities currently restricted by COVID-19. Due to COVID-19, spending on items like travel and office rent is lower than originally forecast. The PT have proposed reallocating these resources to provide increased service input levels, for example, providing additional technical support for government policy and commercial developers. For year two of the project, they will continue working with the FCDO team to identify how to administer this, minimise year one budget variance and deliver value for money.”
Effectiveness
The RT feel that it is too early to assess the effectiveness of the programme at this stage as it is only just starting to deliver outsputs. However, the Theory of Change and logframe has been updated to reflect changes to this year and delays due to Covid-19 response and ODA reprioritisation. Furthermore, the RT was particularly impressed with the work on building a relationship with the Ministry of Energy and Miniral Resources, which sets the programme up well for a positive reception from stakeholders.RT were informed that the prgramme still expects to achieve the benefits set out in the business case in spite of the delays due to Covid pandemic. RT feel, however, that there remain some risks to the effective delivery of the programme. These are stated below in section E.

Equity
The Review Team were shown evidence that the programme is actively supporting the gender and Inclusion goals and are satisfied with the progress achieved.

Assessment of whether the programme continues to represent value for money
As mentioned previously, it is difficult to form an overarching assessment of value for money given the gaps in information.
Quality of financial management
The RT feel comfortable that there is a good audit process for the invoices presented by the delivery partner Palladium, although we found it difficult to reconcile them to the actual cost line items for the programme.

The RT were informed that since carrying out the Annual Review in May 2021, the Mentari programme and the Embassy team have undergone an internal FCDO audit, whose findings correlate with those of the RT’s findings.

Recommendation: See recommendation 1 on pg 4

Date of last narrative financial report	August 2021
Date of last audited annual statement	Mentari DP completed annual self-audit (covering January-December 2020) and submitted statement to FCDO 1 March 2021. / A first Mentari external audit is currently underway as of September 2021. The DP is required to commission this with the FCDO annually. / FCDO internal auditors reviewed Mentari as part of its review of British Embassy Jakarta programme monitoring. This report was submitted to the Embassy on 18 June 2021.

## E: RISK (1 page)

Overall risk rating: Moderate

The Review Team feel that with the ongoing Covid Pandemic there is a moderate risk of delay to the programme. This is mainly due to:
1. Change in priorities for the Government of Indonesia to alieviate the economic situation.
2. Uncertainty of Government of Indonesia’s funding commitments in green financing and other policy incentives to attract private investment.
3. Related to Risk item 2, RT heard about competition from new upcoming cheaper Fossil Fuel plants such as Coal in Indonesia which will make the policy change towards green projects more difficult.
4. Programme delays in the Demonstration project may impact the Policy and Brokerage strands.
5. RT feel that the challenge to procure the £1.5bn private investment within the remaining 2.5 years of the programme may be tight, if there are the existing delays.
6. RT, however, remain confident that the programme team is aware of these challenges and is working closely with both the delivery partner Palladium and the Ministry of Energy and Mineral Resources to resolve any blockers.
7. Spending Review, ODA Allocation and staff funding risk presented by FCDO merger and reduction of ODA global budgets.

Overview of programme risk
The RT observed that the Business Case contains good tables of risk ownership; identification of risk and mitigations; Financial and Fraud Risk Assessment, although they were unable to assess if they are being actively monitored.

Outstanding actions and recommendations from risk assessment
Assess if Risks are actively being monitored and parties responsible for it.

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Several strands of the programme are behind the timeframe set out at the start of implementation. The primary cause of this is COVID which has delayed implementation, this is particularly notable where more on-the-ground work is required in the Brokerage and the Demonstration strands. That said, the Demonstration team in particular has found ways to amend delivery plans to keep delivering despite travel restrictions.
Changes in the Delivery Plan
N/A

Asset monitoring and control
N/A

Recommendations:
The Brokerage Strand will be the key Commercial consideration which requires active monitoring by the programme team so that the delivery partner’s KPIs are achieved.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
There is evidence that the programme is engaging with the business community it is targeting (through the brokerage strand). For example, a November 2020 appearance at Indonesia’s largest RE event, EBTKE Connex. The programme has two targets concerned with private sector engagement and evidence of the identified pipeline of RE projects (£937m risk adjusted pipeline against a target of £30m for this point in the programme) at this stage in the programme suggests there is demand from the business community to engage with the programme’s brokerage work on the project side. There is insufficient evidence at this stage to show how the investor side has responded with no projects securing investment at this early in the programme (as would be expected – the first milestone to secure financial close is December 2022). Our interview with the brokerage strand suggested there could be increased risk of headwinds to investor appetite due to reduction in demand signals from the Government, as a result of COVID19 economic slowdown.
Though there was anecdotal evidence in the paperwork and discussions (see below) that there was some awareness of the programme in the non-stakeholder business community, that is difficult to judge effectively in this review.

(Where relevant) What role has non-ODA spending played in promoting programme objectives?
There is good evidence that the programme is using non-ODA alongside its ODA funding to support UK engagement. For example, the use of non-ODA to fund UK firms to join the EBTKE event in November 2020, and promotional work in July 2020 through the British Chamber to ASEAN. The programme is highly visible in the COP26 communications collateral in the region and continues to be signalled by senior Ministers and interlocutors from the UK Government during their engagements.

## H: MONITORING & EVALUATION

Evidence and evaluation
The programme delivery partner conducted a “Yr1” Annual Report in December 2020, just 5 months after formal launch, but covering a roughly 12 month period, including mobilisation. It describes coherently the progress to date against each workstrand and target. It articulates the headwinds for the programme due to COVID, as 1) reduction in energy demand (all strands), as seen elsewhere in the World, 2)pressure on private/public budgets leading to decreased investor appetite (brokerage strand); 3) financing challenges for investors (brokerage strand); 4) increased liquidity challenges for the State Owned Entity PLN (all strands); and 5) a preference for income support expenditure by the Government (policy strand). These are fundamental challenges to the programme’s context and the programme team conducted a review of the logframe and MREL documentation as a result.
In March 2021 the Prosperity Fund EL provider conducted a light touch programme adaptation review of Mentari, examining the strategic context and continued demand for the programme. It identified that there was a continued case to deliver the interventions, and though the COVID19 context had meant considerable challenges, the programme had adapted well. Recommendations to improve MREL (e.g. By allowing more in-depth analysis of online engagement) and to coordinate with and learn more effectively from other donors appear to being integrated well.
Many of the contextual challenges continue to be seen during the Annual Review, which took place around 6 months later than scheduled due to COVID19. This continues to cause challenges for the brokerage and demo strands most specifically. As noted in the EL review, the programme team are taking an adaptive approach and have discussed with RT areas in which they may adjust interventions further, in order to deal with the changing context e.g. refocussing the collaborating and network strand so it is mainstreamed. RT do not assess that the underlying Theory of Change for the programme requires revision or that the strategic case has changed.

Monitoring progress throughout the review period
RT’s review took feedback from two members of the Government of Indonesia which appeared to show a clear appetite and engagement with the programme at working level. The SRO identified the significant political impact that the programme has in his interactions with the Government Ministers, both to raise ambition and to support wider UK soft power (secondary benefits).
RT interviews were all conducted virtually due to COVID19, and alongside these pieces of reporting also reviewed the relevant project documentation.