Annual Review - Summary Sheet
Indonesia Renewable Energy Programme
Programme Value: £13.5m		Review Date: December 2019
Programme Code:	Start Date: January 2020	End Date: December 2023

Summary of Programme Performance
Year	Nov 2018 – Oct 2019
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learned since last review
This is the first review of the Indonesia Renewable Energy Programme (IREP). It is a light-touch review since the programme has not yet reached the £1m spend threshold for a full review. This review has taken place at the end of the procurement phase, and prior to contract signature. This review therefore is shorter and focusses on the procurement process, consideration of the programme’s operating context and the delivery activities that the Low Carbon Energy Team (LCET) have undertaken alongside procurement. It makes a number of recommendations as the programme moves into full delivery.
Due to the stage of the programme at the time of review it has not sought comments or input from external stakeholders. The review has been conducted primarily by LCET with oversight and comment from the Head of Prosperity Fund, SE Asia. A full standard review will be conducted by March 2021.
List of recommendations for the next year
Recommendation 1: The programme should ensure that a relevant and robust MREL framework is developed during the mobilisation phase, drawing on the support of the Prosperity Fund’s MREL advisers, and that sufficient financial management processes and frameworks are developed to manage supplier activities post-contract signature;
Recommendation 2: The programme should develop a comprehensive Contract Management plan and review LCET capacity to manage supplier contracts, undergoing training where necessary (e.g. training provided by FCO Commercial in November 2019 in Singapore);
Recommendation 3: The programme should retain flexibility in its approach to low carbon energy interventions, including as Jokowi’s second presidential term gets underway;
Recommendation 4: The programme should keep its current staffing levels, which include both administrative and delivery staff, under review and consider recruiting an additional post to lead on MREL and internal and external communications. It should also consider opportunities for in-kind support, e.g. from other embassy teams, where available;
Recommendation 5: The programme should look for opportunities to leverage or join up with other HMG-funded donor activity in the renewable energy sector in Indonesia, including programmes under International Climate Finance support.
Recommendation 6: The programme should continue to develop its Secondary Benefits strategy and engage the delivery partner during programme mobilisation.
JFU Comment
I agree with the report’s findings and recommendations, and with the score of A, noting this mainly reflects to date the meeting of procurement milestones and positive engagement with the Indonesian government. The programme does now have a fairly short time frame within which to deliver results and we will need to revisit should the existing timeframe and budget prove to be unrealistic. In the meantime, it is important the programme finalises its logical framework and quantifiable targets as soon as possible.
List of Acronyms
ASEAN: Association of Southeast Asian Nations
COP 26: UN Climate Change Conference under UN Framework on Climate Change
CPN: Competitive Procedure with Negotiation
DFID: Department for International Development
DIT: Department for International Trade
PFDU: Prosperity Fund Delivery Unit
JFU: Joint Funds Unit
ODA: Official Development Assistance
GESI: Gender Equality and Social Inclusion
FBC: Full Business Case
FCO: Foreign and Commonwealth Office
GDP: Gross Domestic Product
GF: Green Finance
IREP: Indonesia Renewable Energy Programme
LCEP: ASEAN Low Carbon Energy Programme
LCET: Low Carbon Energy Team (British Embassy Jakarta, formerly Sustainable Development Team)
MEMR: Indonesia Ministry of Energy and Mineral Resources
MOU: Memorandum of Understanding
MREL: Monitoring, Reporting, Evaluation and Learning
OBC: Outline Business Case
OJEU: Official Journal of the European Union
PF: Prosperity Fund
PLN: Indonesia state-owned national electricity company
RE: Renewable Energy
SDA: Social Development Adviser (Prosperity Fund)
SDGs: United Nations Sustainable Development Goals
SMEs: Small and Medium Enterprises
SOE: State-Owned Enterprise
SRO: Senior Responsible Officer
VFM: Value for Money

A. Introduction and Context
This is a light touch Annual Review for the Indonesia Renewable Energy Programme and covers the period November 2018 to the end of October 2019. IREP received approval from the FCO IIOC for its Full Business Case on the 30th October 2019.
Prosperity Fund
The cross-Government Prosperity Fund (PF) was created in 2015. The primary purpose of the Prosperity Fund is to support the inclusive economic growth needed to reduce poverty in partner countries. Through this primary purpose, the Fund’s activities will contribute to the UN Sustainable Development Goals (SDGs). The fund also looks to create new economic opportunities for international business, including UK companies, and mutually beneficial economic relationships as secondary benefits, as a result of this economic growth. The Fund has a budget of £1.2 billion over the 7 years (2015/16-22/23) to provide technical assistance to partner countries to promote economic reforms and remove barriers to trade, to strengthen policy capacity and build strong institutions and tackle corruption.
Indonesia Renewable Energy Programme
Indonesia is the world’s 4th most populous country (with over 260m people) and is a G20 economy, predicted to be a top ten economy by 2030 accounting for almost 35% of ASEAN GDP. However, over 28 million Indonesians live below the poverty line, inequality is rising and there are major structural issues holding back development, namely lack of infrastructure and a poor business environment (only recently, Indonesia’s Global Competitiveness Index ranking deteriorated 5 places from 45th to 50th).
Access to reliable, affordable energy is a key constraint to economic growth and raising standards of living, with the problem particularly acute in the remote islands of eastern Indonesia. The government has set targets to provide electricity to 100% of the population yet significant numbers of communities lack access to affordable, reliable 24/7 electricity with sufficient capacity to enable productive use, such as supporting business growth of fishing (20% of Indonesia’s poor are fishermen), agricultural and tourism industries.
At the same time, Indonesia is among the world’s top ten greenhouse gas emitters. In 2016 the government set targets to reduce its emissions by 29% against a Business as Usual scenario by 2030. Decarbonising the energy sector will be crucial to meeting this goal. National plans target a 23% share of new and renewable energy by 2025, yet given current trajectories in the sector this target currently seems a long way off.
However Indonesia has huge potential for generating its electricity and providing power from renewable sources: solar, hydro, wind, wave, tidal, geothermal and others. Uptake has so far been slow, with policies and regulations restrictive to renewable energy proliferation, particularly private sector investment. The energy sector is dominated by fossil fuels, which currently account for around 80% of electricity generation (coal production forms a major domestic and export industry). However, there is a huge potential for a substantial increase in generation share from renewables, including community-led solar mini-grids in eastern Indonesia replacing generators powered by costly imported diesel.
Creating favourable policy and regulatory frameworks that support renewable energy, encouraging large scale private sector investment as well as supporting community-led small-scale projects would see renewable energy help to drive inclusive economic growth and poverty reduction, in a sector in which the UK public and private sector has significant experience and expertise to offer.Part of the FCO’s Prosperity Fund portfolio, the Indonesia Renewable Energy Programme (IREP) aims to increase renewable energy generation share nationally and improve inclusive access to clean energy for poor communities in eastern Indonesia, reducing poverty and supporting economic growth by:
- Improving renewable energy policy, regulation and financial instruments through technical assistance to national and regional government;
- Increasing investment in renewable energy by bridging the gap between available external finance, technology and viable programmes through brokerage;
- Accelerating development and innovation in renewable energy by enabling innovative, replicable demonstration projects; and
- Enabling communication and partnering between domestic and international renewable energy sectors, including donors, industry, SMEs and academia to develop domestic innovation, best practice and knowledge transfer.

In addition, the programme forms a key component of HMG’s low carbon development support for Indonesia (with a focus on clean growth akin to the UK’s strategies, rather than a focus on tackling climate change in purist terms), as the UK prepares to host the COP 26 international climate summit in 2020. The programme will be instrumental in the UK’s efforts to encourage raised ambition for emissions reductions in the energy sector.
Development of the renewable energy sector and tackling barriers to foreign investment will also yield secondary commercial benefits for international, including UK renewable energy businesses (renewable energy goods and services make up approximately 17% of UK exports to Indonesia).
Programme Status and Light-Touch Annual Review
IREP received approval for its Outline Business Case in July 2018. In February 2019, the British Embassy Jakarta signed a Memorandum of Understanding with the Indonesian Ministry of Energy and Mineral Resources covering cooperation on low carbon development, announced by the UK Foreign Secretary and his counterpart as part of the Indonesia – UK Partnership Dialogue in July 2019. The procurement of a main implementing partner, via an OJEU Competitive Procedure with Negotiation (CPN), resulted in the identification of a preferred supplier in October 2019. IREP received approval for its Full Business Case on 30 October 2019 and contract signature and programme mobilisation with the delivery partner is expected to start by early December 2019. A short (c. two month) mobilisation phase will lead into full programme delivery from early 2020.
This review covers the period November 2018 to October 2019 and focusses on:
- Reviewing the procurement approach for the IREP main delivery partner, specifically the value and efficiency of using an OJEU approach over other options;
- Considering the context for IREP, specifically the relevance and value of a renewable energy programme in Indonesia and as part of UK international climate diplomacy, and any changes to this since OBC approval;
- The financial profile of IREP and options, opportunities and risks of budget reductions or scaling up;
- The effectiveness of programme governance arrangements compared to approaches set out in the OBC, and joint delivery approach between the implementing partner and British Embassy Jakarta.

As such this review contains sections on Performance and Conclusions, Value for Money and Financial Performance, Risk, Commercial Considerations, Political Economy and Business Environment. In comparison to the usual Prosperity Fund Annual Review template, it does not contain sections on Detailed Output Scoring or Monitoring and Evaluation: these will be included in IREP’s first full annual review.
## B: Performance and Conclusions

Annual outcome assessment (Primary Purpose – inclusive poverty reduction, economic development, gender equality, women’s economic empowerment)
At the time of review IREP is in the final stages of procurement and is yet to begin full delivery, therefore it is not yet possible to conduct a comprehensive assessment of performance against primary purpose objectives.
Great care has been taken to ensure that the PF Primary Purpose underpins every intervention IREP will undertake. IREP has gone through a detailed procurement process to identify a delivery partner, through an OJEU CPN. From the beginning this process has allowed LCET to ensure that potential delivery partners fully understand the primary purpose the programme is seeking to achieve. Following submission of initial bids, the CPN included two rounds of negotiations with bidders with revised tenders submitted after each negotiation round. LCET pushed for bidders to improve their ambition on primary purpose.
A preferred bidder has been identified, and there is high confidence in their understanding of primary purpose and their ability to deliver impact. Throughout the procurement process, IREP made use of Social Development and MREL advisors and the bid evaluation panel included legal and commercial representatives to ensure that evaluation was robust and informed by specialist expertise (detail on the procurement process is provided later in the Review). Following contract signature, the programme will move into a short mobilisation phase; one of the key outputs from this will be a fully developed Theory of Change, Log Frames and MREL suite (Targets, Baselines, Key Performance Indicators, and Measures for programme inputs, outputs, outcomes and impact) relating to primary purpose of the programme. This will be led by the implementing partner and their MREL and GESI specialists and the PF’s MREL experts, with close oversight from LCET.
The programme has received highly positive feedback from the Prosperity Fund’s Social Development Advisers (SDA) for its approach to hardwiring GESI considerations into IREP’s design and procurement documentation through to interaction with suppliers, and has been identified as a showcase good practice example for other programmes to draw learning. The programme’s senior SDA fed back at a recent G&I learning event that ‘Some of the G&I practice in PF would give DFID a run for its money, particularly Indonesia…Indonesia did something quite incredible on G&I. The scale and vision of what they did was quite beautiful’.
Much of the above lays the foundations for effective delivery of primary purpose with the delivery partner from early 2020. However, alongside the procurement, LCET has also worked to build the profile of the UK’s low carbon energy support to Indonesia; and the Embassy’s relationships with key stakeholders in the government and elsewhere are primed to aid delivery. IREP is a bilateral programme, and a flagship for the Embassy, forming a key part of its wider low carbon development assistance for Indonesia: buy-in from the Indonesian government is critical for its success and so awareness raising and relationship building has been essential for the UK to put forward a credible programme that is welcomed by the government. The steps that have been taken towards this over the review period include:
- Signing a Memorandum of Understanding between the FCO (signed by HMA) and the Ministry of Energy and Mineral Resources (MEMR) in February 2019 on wider Cooperation on Low Carbon Energy Development (covers both IREP and ASEAN Low Carbon Programme, but allows for further / expanded work with MEMR and other ministries should the opportunity arise);
- Showcasing the opportunities that can be brought about through renewable energy development by bringing a delegation of officials from MEMR and PLN, the national electricity SOE, to Orkney island; the visit helped to solidify our relationship with key RE personnel within MEMR and was a key milestone of our co-delivery of the IREP policy strand;
- Multiple high-level meetings to discuss UK-Indonesia collaboration on low carbon energy development and high-profile communications, including HMA meetings with the Minister of Finance and HMA presenting at a high-level panel at the Indonesia EBTKE Conex, Indonesia’s largest renewable energy conference and expo event.
- MOU on low carbon co-operation also signed with Bappenas in April and announced by FS and his Indonesian counterpart in July, following the UK-Indonesia partnership dialogue in London.

Annual outcome assessment (Secondary Benefit)
At the time of review IREP is in the final stages of procurement and is yet to begin full programme delivery, therefore it is not yet possible to conduct a comprehensive assessment of performance against secondary benefit objectives.
However the programme has undertaken activities over the review year to engage UK and international business on opportunities in the renewable energy sector in Indonesia. Increasing these opportunities remains an important secondary target of IREP, and LCET works closely with the Department for International Trade team in the Embassy to realise synergies between IREP’s ODA work and DIT’s work in this sector. LCET has recruited a secondary benefits adviser, funded by non-ODA, embedded within DIT’s Energy Team to lead this work. LCET will work with the delivery partner during mobilisation to finalise MREL and KPIs and an overall approach to achieving secondary benefits. The desire for secondary benefits was made clear throughout the procurement phase.
Due to the nature of IREP, and the relevant expertise of the private sector in the UK, secondary benefit opportunities will be unlocked over the course of the programme. LCET and the DIT Energy Team in Jakarta are working on a secondary benefits strategy for IREP, looking at each strand of the programme. The potential for secondary benefit is baked into much of the programme: the RE sector in Indonesia is currently under-developed, and the UK’s expertise in project planning and development, emerging and established renewable energy technologies and interest in working internationally in the sector means that the UK is ready and well placed to take advantage of opportunities in a more open RE sector in Indonesia. Specifically:
- Improvements to the policy and regulatory environment in the RE sector at the national and sub-national level, the focus of IREP’s policy strand, will enable and encourage greater investment in on and off-grid RE projects, which international and UK business can benefit from;
- IREP’s brokerage strand will leverage public, private and multilateral finance into RE projects across Indonesia, providing matchmaking services and showcasing specific project and investment opportunities, providing a wide range of opportunities for international and UK business;
- The programme’s Communicating and Partnering Stand will raise awareness of the RE sector’s potential in Indonesia to both challenge perceptions of risk and provide guidance for international industry, and to demonstrate the UK’s expertise and offer to Indonesia. The non-ODA funded part of the programme is taking an active approach to engage UK businesses in informing them about the opportunities and market landscape in Indonesia. It is also actively promoting UK capabilities to Indonesian stakeholders.

In September 2019, a non-ODA funded report on the opportunities in the Indonesian renewable energy sector, aimed at investors, was launched in Singapore. UK launches were held in London and Aberdeen. This report was well received, and colleagues in Singapore are exploring replicating this approach in other ASEAN countries. A visit to Orkney Island in the UK bringing Indonesian ministry officials and private companies was also organised under non-ODA funds to showcase UK capabilities and lessons learned. A documentary about the island and how its renewable energy solutions are relevant for Indonesia was produced and aired on one of Indonesia’s national TV channels and further use of this material is planned.
Key actions
See list of Recommendations.

## C: Value for Money and Financial Performance

Key cost drivers and performance
IREP provides monthly financial performance updates to the FCO Prosperity Fund Delivery Unit, responding to questions and requests for clarifications where necessary. This review provides an update to current financial forecasts and spend to date for the financial year 2019/20, in line with PFDU and JFU reporting cycles.
In September 2019, following a request to review programme budget allocations in light of PF funding uncertainty caused by delays to a multi-year spending review and as agreed with the programme SRO IREP revised down its allocation for 19/20 by around £1.6m, based on best available forecasting at the time during the procurement process when budgets were subject to final tenders. However, the total programme allocation of £13.5m, as approved by FCO, remains unchanged, and inflexibility in the in-year ‘use it or lose it’ approach negatively impacts the programme’s adaptability.
An extended procurement phase has resulted in delays to disbursing funds to delivery partners, however activities are expected to begin in mid-December 2019.
The forecast breakdown of spend for this financial year is as follows:
Total FY19/20 allocation: £1.136m
- Staff costs (admin and delivery, including UKB, local, platform charges and admin/T&S)
- Procurement related costs
- Implementing partner costs (all forecast)
According to the latest financial forecast submitted in late November, spend to date for this financial year is £213,249. Programme admin spend remains under review and LCET is working with PFDU and JFU to update programme team job profiles to reflect hybrid admin/implementer responsibilities, which will reduce admin costs. Financial profiles for delivery partner costs are currently a best estimate and will become clearer once the contract is signed with the delivery partner and the programme moves into full delivery. LCET will closely monitor implementing partner spend. Restricted access for the programme team to programme UK-based staff cost spend remains a risk to accurate and responsive forecasting of the programme. The programme team and PFDU finance team have requested access from FCO finance but this has not been granted, LCET will continue to request access to all UK-based costs for the programme.
The procurement delivered an innovative pricing model which transfers risk to the delivery partner (see Commercial Considerations section below). It includes a service credit regime intended to incentivise the implementing partner to deliver on a mix of key programme inputs, outputs, outcomes and impact. It provides the option of reducing delivery partner margin should performance in particular areas be unsatisfactory i.e. not meet the specified KPIs.

VfM performance compared to the original VfM proposition in the business case
At the time of review the programme is in the final stages of procurement and yet to enter full delivery and so it is not possible to assess the value for money performance of the delivery partner. Assumptions around the ‘Economy’ and ‘Efficiency’ of the programme and its interventions remain unchanged since the Outline Business Case although in some areas have been enhanced through the procurement process. The programme remains highly relevant for HMG’s security, prosperity and climate change priorities and the relationship with the Government of Indonesia, and is perhaps even more relevant now given the increasing prioritisation of low carbon development and climate change action by HMG over recent months, given the announcement that the UK will host COP 26 in 2020.
The programme has sought to achieve significant value for money through the procurement. As agreed with the programme SRO and FCO commercial, IREP followed an OJEU CPN rather than using the Prosperity Fund Framework. This delivered supplier commercial outcomes that enables delivery of all programme requirement for significantly less than the stated procurement budget, the savings from which can be rolled back in to scale up activity in IREP’s policy and brokerage strands. The preferred supplier is not part of the Prosperity Fund Framework Energy Lot and so would not have been eligible to bid should the programme have used the framework. More detail on the lessons learned from the procurement and covered in the Commercial Considerations section below.

Assessment of whether the programme continues to represent value for money
The programme has not yet started full delivery with its delivery partner; the value for money proposition remains unchanged from that approved by FCO in the Full Business Case stage. The value for money ‘Economy’ of the programme was a key consideration for the procurement process. This is described in detail in section E: Commercial Considerations, below. LCET will prioritise achieving value for money from this programme and from the contract with the delivery partner. A key part of this will be ensuring delivery partners are delivering to the required level of performance, with embassy delivery support where necessary, and the programme’s innovative cost model referred to above. To ensure continued ‘Efficiency’ throughout the programme, an adaptive programming approach will also be used to ensure the right interventions are undertaken, with activities stopped, delayed, redefined or replaced where required.
This adaptive programme approach includes considering how IREP can be used as vehicle for additional HMG work in Indonesia, for example through the planned scale-up in International Climate Finance support and regionally and centrally managed programmes. Additional HMG support or funds channelled from other HMG interventions could, as an example, be used to increase the volume of IREP’s brokerage activity, helping to leverage additional finance into renewable energy projects in Indonesia.
The programme has been designed to be outcome-focussed – while the thematic focus of the programme is supporting the renewable energy sector in Indonesia, the objective is to use renewable energy as a vehicle for achieving development outcomes of inclusive economic growth, poverty reduction and supporting gender equality and social inclusion. Increasing access to sustainable renewable energy in rural communities that can power productive uses to support economic growth and women’s economic empowerment, and supporting a policy and investment framework to ensure that this approach is embedded across the country will help to support these aims and the programme’s ‘Effectiveness’ will be measured in these terms. As above, the programme will retain an adaptive approach to its inputs and outputs to ensure that these most effectively support the programme’s outcomes.
‘Equity’ considerations were at the heart of this programme’s design and procurement approach from the start. For example, the need to focus on GESI formed an essential part of bidder requirements and evaluations throughout the procurement. this received positive feedback from the Prosperity Fiund’s Social Development Adviser, who commented: “the negotiated approach meant that suppliers were given detailed feedback on the strengths and weaknesses of the GESI approach by the SDA. It allowed the Indonesia PF team to…differentiate the tokenistic responses and approaches from the potentially transformative ones. It incentivised the suppliers in their final bid to up their own game on GESI”.
Programme value for money should be seen in the wider context of HMG’s renewable and low carbon energy interventions in Indonesia. While IREP is a programme in its own right, it also provides a structure and platform for other sources of UK funding to dock in to. IREP’s value for money can also be assessed by considering the sustainability and legacy of the programme’s design and interventions and its relationships with government, suppliers and industry, and how this can be used for any potential future HMG investments in developing the renewable energy and other low carbon sectors in Indonesia. Assessing this potential will form a part of IREP’s Evaluation and Learning activities.
Establishing a robust contract management plan, delivery plan and MREL approach will support value for money, the effectiveness of the programme and ability to make informed decisions on optimal adaptations. Developing an MREL framework and Key Performance Indicators will be a major focus of the programme’s mobilisation phase once the contract is signed. This will be facilitated by the PF’s MREL experts.
Quality of financial management
The programme has not yet begun mobilisation and so a financial management framework with the implementing partner has not yet been developed; this will form a key part of discussions and outputs from the mobilisation phase. However, assurances of bidders’ capability and experience and track record of delivering similar programmes was sought during procurement, and pricing submissions were heavily scrutinised, with clarifications sought to the point where LCET have confidence that financial management would be low-risk.
Financial profiles for delivery partner costs are currently a best estimate and will become clearer once the contract is signed with the delivery partner and the programme moves into full delivery. Forecasts will be updated during the beginning of programme mobilisation, which will enhance the accuracy and predictability of programme spend.
To increase programme value for money LCET is looking to secure exemptions from Indonesian Value Added Tax (at a rate of 10%). This requires multiple approvals from different parts of the Indonesian government but LCET will continue to explore how this can be achieved. The potential to secure the tax exemption is being shared with other programmes operating in Indonesia, potentially saving c£8m across programmes which can be rolled back into programme delivery.

Date of last narrative financial report	25th November 2019
Date of last audited annual statement	N/A

D: Risk

Overall risk rating: Moderate
The overall risk rating is Moderate, and remains largely static.
Overview of programme risk
There are currently no Red-rated risks for the programme. A major risk, delays to the programme as a result of a delayed procurement process, has now been reduced significantly as a delivery partner has been identified and the programme moves into full delivery.
More significant risks include:
- Uncertainty of long-term Prosperity Fund budgets, in part due to delays to the multi-year spending review conducted by HM Treasury and potential for PF to perform poorly against other ODA spending departments when a multi-year SR does conclude, is a significant risk to the programme.
- Loss of political commitment. This risk has been reduced following Indonesian national elections and the inauguration of President Jokowi’s second term, and the appointments of a new energy minister. President Jokowi’s second term is now underway and early indications are that relevant ministerial appointments are favourable to the programme and low carbon development. The programme has signed a Memorandum of Understainding with its main government patner, the Ministry of Energy and Mineral Resources, and is now working on agreeing more detailed implementing arrangements to deliver the programme.

The programme risk register currently contains 23 risks. Risks are reviewed regularly by LCET and are discussed at the programme steering group with actions taken where necessary. Risks are reported to FCO and JFU in line with standard reporting cycles. Risk reporting will move to the Prospero system in November 2019 in line with JFU requirements.
LCET sought to reduce risks through commercial clarifications and negotiation during procurement. Much of the project delivery risk will rest with the delivery partner given the successful transfer of risk though the procurement. An MREL framework, contract, performance and financial management plan will be put in place to managed risks taken on by the supplier, and a risk reporting regime will be established, recognising that ultimate risk always sits with the client.

E: Commercial Considerations (1 page)
Delivery against planned timeframe
Finalised delivery plans will be agreed between LCET and the implementing partner during mobilisation. Due to the length of the procurement and the intended short mobilisation phase, there is a requirement and expectation that the supplier will mobilise quickly. One key output from the first year of the project will be an operational demonstration renewable energy project. The CPN process has taken longer than originally anticipated. But the benefits this yielded, particularly dispensing with a lengthy inception period have paid off.
Performance and lessons from procurement of an implementing partner
As agreed with the programme SRO and FCO commercial, the procurement followed an OJEU CPN rather than using the Prosperity Fund Framework. During 2018 the programme team considered the options for procuring the programme, including using the existing Prosperity Fund framework. This included extensive market testing, including the appetite and capability of suppliers to deliver the full requirements of the programme in the Indonesian context. Following this it was agreed that an open process would be more likely to source more competitive and higher quality bids in comparison to the PF framework. It was also agreed between the programme team, SRO and FCO commercial that a CPN process would be worth the additional time and resource effort, given the benefits to the quality of both the technical aspects and price of supplier proposals.
This resulted in a highly competitive process with multiple good quality and credible bids, and a preferred supplier that gives high confidence to deliver an impactful programme. The preferred supplier was not included in the Prosperity Fund framework energy Lot. This has demonstrated the benefits offered by a OJEU CPN approach to procurement, particularly where it is difficult or undesirable to specify exact input and output requirements against outcome/impact objectives.
The ability to hold successive rounds of negotiation requiring revision of tenders was invaluable in improving supplier understanding of FCO / programme requirements and the evaluation team’s understanding of bidders’ proposals. This has resulted in revised tenders of higher quality and better value.
The pricing model is an innovative mix of cost plus with capped charges and rebate provisions which the Procurement Team believe may have potential to be adopted in other procurements i.e. price is based on an actual cost profile for deploying the resources to deliver the service specified. Should it cost the delivery partner more to deliver the service, they will absorb the additional cost. Should it cost less, FCO will not be charged against the profile - effectively receiving a rebate which means resources can be redeployed elsewhere. This applies to staff costs, overheads, T&S etc. The profit margin element is a fixed sum. The programme team acknowledge the resource requirements for this but believe the additional transparency and higher degree of control over delivery partner costs represents better overall value.
However, the CPN is time and labour intensive and must not be underestimated, but given the advantages a CPN procurement offers, overall delivery confidence is high and in terms of quality and price potential, ahead of expectations. LCET is of the view that the approach paid dividends over prioritising expedience.
LCET are confident this approach will translate into a well-defined and good value programme with improved potential for success, avoiding a lengthy, costly inception period in favour of maintaining competitive tension whilst agreeing specific activities, service levels, resource allocation and costs, that can otherwise give rise to supplier-client conflict post-award.
Changes in the Delivery Plan
The delivery plan will be finalised and agreed with LCET during mobilisation from late November 2019 and reviewed and recalibrated regularly, aligned with adaptive programming approach.
Asset monitoring and control
As part of the call-off contract, the Intellectual Property that the Programme produces will be owned by the UK government. This programme will deliver a renewable energy demonstration project, fully funded by the programme, such as a solar mini-grid with battery storage, in eastern Indonesia with final ownership switching to government of Indonesia or a special purpose vehicle established by them, through an appropriate model designed by the delivery partner in consultation with relevant stakeholders including the local community. It is LCET’s preference that there is strong local community buy-in and ownership of the project. FCO will not retain any stake or long-term involvement in the project. A second demo project is being planned and may involve match-funding from other sources.

F: Business Environment (½ page)

How has the business community and business environment responded to the programme?
LCET regularly engages with the renewable energy business community in both the UK and Indonesia relation to this programme, who have responded positively to the aims its proposed interventions and LCET. The delivery partner will continue to engage business throughout the programme. One of the fours strands of the programme, Communicating and Partnering, will work with renewable energy players including government, donors, investors, contractors, start-ups and academia to facilitate knowledge transfer and encourage innovation in the renewable energy sector in Indonesia, and provide a route for industry and investors to inform the work of the policy and brokerage strands of the programme. Part of the MREL framework will include ensuring that these relationships are being built and utilised for the benefit of the programme.
(Where relevant) What role has non-ODA spending played in promoting programme objectives?
LCET has a small non-ODA budget to undertake secondary benefit activities that complement IREP and help to achieve commercial wins for UK and international business.
Two significant non-ODA funded activities have strongly complemented IREP in this review year:
Funding for the development of a report Indonesia Renewable Energy Business Opportunities, which was launched in September 2019. This report provides detail on the current and projected Indonesian renewable energy market on sectors including solar, wind, biomass, geothermal and hydro including trends, government regulations and policies, growth potential and deployed technologies. It shows to potential investors and contractors the scale of the opportunity in this sector in Indonesia, and provides a comprehensive introduction to the market. The report, launched in Singapore, London and Aberdeen, has been very positively received by both public and private sector stakeholders and will be a useful document and reference tool for IREP and will help to support its objective of raising investment in renewable projects.

Funding a visit by Indonesian companies, journalists and Indonesian energy policy makers (the latter funded under the programme’s policy strand - a good example of a blended approach which maximises impact of both ODA and non-ODA funding) to Orkney Island in Scotland. Indonesian stakeholders saw how Orkney became global leaders in renewable energy – wind, solar, tidal, wave - and produce more electricity than required, which it sells back to the grid or uses to produce hydrogen fuel for ferries and vehicles. The trip resulted in a documentary focusing on the economic benefits that Indonesia can draw from clean energy transition, broadcast on primetime television across Indonesia’s 17,000 islands showing policy makers buying into IREP, with numerous new commercial leads identified. The experience of Orkney, as a small island that has established its own electricity network powered by renewable sources, is a powerful example for IREP’s targeted provinces in eastern Indonesia where thousands of communities across hundreds of islands can learn from their experience. As a result of the visit, officials in MEMR have expressed their interest in reviewing regulations in Indonesia to enable the development of new RE technologies, namely marine floating solar. LCET is agnostic in terms of the type of RE technology deployed and supported through IREP and will consider whether this technology can support coastal and fishing communities.