## Annual Review Template

Title: MENTARI* UK-Indonesia Low Carbon Energy Partnership (referred to in pre-delivery as Indonesia Renewable Energy Programme (IREP)
Programme Value £ (full life): £13.5m		Review date:
Programme Code: [AMP ID#] N/A: As an ex-FCO initiative the programme is not currently on AMP.	AMP start date: / 6 January 2020 (date of start of programme delivery). (SOBC approval date January 2018, OBC approval date September 2018)	AMP end date: / 11 December 2023

Summary of Programme Performance
Year	December 2019 (Light Touch)	Jan 2020 – April 2021	May 2021 – March 2023
Overall Output Score	A	A	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-50-PF-13B-INJRE/summary
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-50-PF-13B-INJRE/summary

List of Acronyms
Acronym	Explanation
ABB	Activity Based Budget
ADB	Asian Development Bank
AR	Annual Review (refers to Mentari Annual Review undertaken in 2022)
CDEL	Capital Departmental Expenditure Limit
COP26	UN Climate Change Conference number 26 under the UN Framework for Climate Change, hosted in the UK in 2021
ConEx	Conference and Expo – EBTKE ConEx is the Indonesian government’s largest annual renewable energy conference and trade show
EBTKE	Indonesia Ministry of Energy and Mineral Resources Directorate General of New and Renewable Energy and Energy Conservation.
FCDO	Foreign, Commonwealth and Development Office
FIRE	Friends of Indonesia Renewable Energy (dialogues)
FY	Financial Year
GESI	Gender Equality and Social Inclusion
GHG	Green House Gas
GoI	Government of Indonesia
IBEC	Indonesian Blue Energy for Blue Economy Centre of Excellence
ITS	Institute Technology of Surabaya
JETP	Just Energy Transition Partnerships
KPI	Key Performance Indicator
MEMR	Indonesian Ministry of Energy and Mineral Resources
NDC	Nationally Determined Contribution (to the UNFCCC Paris Agreement)
PLN	Indonesia state-owned national electricity company
PPA	Power Purchase Agreement
RE	Renewable Energy
RT	Review Team
RUEN	Rencana Umum Energi Nasional (National energy plan)
RUKN	Rencana Umum Ketenagalistrikan Nasional (General Plan of National Electricity)
RUPTL	PLN Business Plan
SMI	Sarana Multi Infrastruktur (Indonesia’s Infrastructure Investment Bank)
Solar PV	Solar Photo Voltaic
TA	Technical Assistance
TVET	Technical and Vocational Education and Training
VfM	Value for Money
VGF	Viability Gap Fund

A. SUMMARY AND OVERVIEW

Please note, this is an independent annual review (AR) carried out by three individuals external to the MENTARI programme: Ulrike Hotopp (AR lead, Director, LIVE Economics ltd), Resha Piya (Energy Advisor, British Embassy Kathmandu) and Giulia Robinson (Monitoring and Evaluation Advisor, FCDO).

Description of programme
The MENTARI (Menuju Transisi Energi Rendah Karbon Indonesia – Mentari means ‘dawn’ in Bahasa Indonesia) programme aims to deliver inclusive economic growth and poverty reduction in Indonesia by supporting low carbon energy uptake. MENTARI is currently a four-year Programme (2020-2023). By working closely with the Government of Indonesia (GoI) and other stakeholders to improve the enabling environment and drive investment, MENTARI aims to demonstrate the possibilities of low carbon energy for Indonesia’s economic development, job creation and social inclusion, while helping to mitigate climate and environmental impacts. The programme specifically focuses on how low carbon energy can best support disadvantaged communities in eastern Indonesia.

In addition, the programme forms a key component of HMG’s low carbon development support for Indonesia. The programme was highlighted at the COP26 international climate summit 2021 for its instrumental role in the UK’s efforts to encourage raised ambition for emissions reductions in the energy sector.

The interventions are delivered through four interlinked programme strands:
1. The policy strand: working with national level government and public institutions to address renewable energy policy issues, such as regulatory and fiscal questions.
2. The collaborating and networking strand: supporting domestic and international knowledge transfer of renewable energy best practise (to note – this strand will be changing in scope this year, with a shift in focus to further technical assistance, while collaboration and networking will be mainstreamed into other strands)
3. The brokerage strand: aiming to leverage £766m of new investment in renewable energy projects from public, private and multilateral sources, with a focus on eastern Indonesia.
4. Demonstration Project Strand: funds the development of replicable off-grid business and cost recovery models.
In January 2022 the Programme team received agreement for the Viability Gap Fund (VGF), additional CDEL to the programme which will enable the brokerage strand to create further opportunities by a) reducing the risks of funding renewable energy projects b) providing further Technical Assistance to the Government of Indonesia and its infrastructure financing company to develop capacity to support more renewable energy infrastructure. The VGF will have links to the policy strand of the programme, through capacity building activities.

The Review Team is aware of the global and national context, during which this AR is conducted, including:
- Russia-Ukraine war and its impact on the rise in energy prices this year, which has affected the Indonesia energy market and impacted Indonesian households and business.
- Indonesia is among the world’s ten largest greenhouse gas emitters, with more than 3% of global emissions. Indonesia has been identified as a likely country for support through a new Just Energy Transition Partnership (JETP).
  [note] For detail on JETP with South Africa see https://www.gov.uk/government/news/joint-statement-international-just-energy-transition-partnership
These and other changes in the global environment impact on the rationale for the MENTARI programme as well as its operating environment.

Summary supporting narrative for the overall score in this review

The overall programme score for this review is A+. The programme has either met or achieved all expectations of planned milestones, and all strands are delivering high-quality outputs. Two years into delivery, MENTARI is also overall on track to contribute to expected outcomes and impact.

- The programme has shown to be adaptive and flexible – introducing the Viability Gap Fund (VGF) this year, and changing scope of the collaboration and networking strand towards further technical assistance, while mainstreaming communications into other strands. At the output level, the programme has responded flexibly to requests from the Government of Indonesia (GoI) and BE Jakarta. The VGF was set up following identification of a gap in the delivery chain; it will provide up to 20% of project funding to reduce project risk and provide additional TA.
- Under the policy strand, MENTARI has closely collaborated with government officials to understand their needs with respect to the energy sector. MENTARI has been successful in supporting the GoI to reform regulations and policy which encourage renewable energy development in Indonesia.
- Under the brokerage strand, MENTARI has actively engaged with investors and project developers through different forums and events, and has successfully enabled partnerships and opportunities. The programme has also established a significant number of projects (52 RE projects) in the pipeline, and this is continuously increasing.
- Due to the COVID-19 pandemic, there have been some delays in the achievements of outcomes, in particular with respect to the demonstration project. But these difficulties have been overcome and the project is now due to be opened / handed over to the village in August 2022. The design of the demonstration project has been GESI sensitive, promoting an inclusive approach to solar PV development to engage the local community and support the local economy. Further GESI success can be seen in the GESI strand’s output score of A+, which has developed a guideline for delivering G&I sensitive events, and a case study on the immediate positive changes that emerged from young women and men who participated in trainings provided by MENTARI.
- The review also finds the programme has delivered strongly on Soft Power, creating a real sense of partnership with the MEMR and other parts of the GoI.
While the review has identified some risks (see risks section), and provided recommendations to improve delivery and impact, the review team is confident that the programme is performing well and will continue to deliver on outputs and outcomes.

Recommendations for the year ahead

No.	Recommendation	Owner / timing
	Risk Management
1	Improve due diligence process by widening and deepening it (e.g. include investors in RE projects)	Palladium and BEJ - urgent
2	Structure risks according to the FCDO’s guidance, upload them to the AMP as soon as this is available and, in the process assess the PT’s risk appetite for each risk.	BEJ – as soon as possible
	Programme management
3	Ensure clear and transparent selection criteria for the VGF	Palladium and BEJ – urgent - by full implementation of VGF
4	Reduce the additional demands on the team (esp Policy Strand) to create a better balance of planned work and adaptive work.	BEJ in collaboration with MEMR and Palladium – beginning of 22/23 FY programming
5	Ensure local and regional (sub-national) levels of Government and delivery are fully addressed in the MENTARI programme	Palladium with BEJ and delivery partners – by next AR
	Monitoring and Evaluation
6	Review the targets / milestones (they may not be high enough)	BEJ via Programme Steering group – by end of 2022/23
7	Update the Theory of Change and Logframe based on revisions of workstrand. In particular, review and test underlying assumptions esp of brokerage strand	Palladium with BEJ – by next AR
8	Identify and use external benchmarks, particularly to enable a VfM assessment over rest of delivery period.	Palladium – by next AR
	Programme delivery
9	Increase visibility and content of the MENTARI programme through its website and social media.	Palladium – by end of 2022

Note: For progress made on the recommendations of last year’s AR, please see Annex.

Based on the review and the progress made over the last year we recommend an extension of the programme to ensure that impacts can be delivered.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The MENTARI Theory of Change (updated Feb 2022) can be summarised as follows:

- Through four strands, the MENTARI programme aims to achieve
  - (1) improved investments for renewable energy projects (with a target of £766m of increased investment in renewable energy)
  - (2) increased access to reliable and affordable renewable energy, with a target of 844,000 additional households with access to low carbon electricity (including for women and/or marginalised groups) leading to economic growth, and
  - (3) more inclusive economic growth contributing to the reduction in poverty and GHG emissions and improvement in gender equality and social inclusion.
- The programme assumes that greater investments lead to improved infrastructure, business and trade growth, and participation in the global economy. It also assumes implementation will support demand and supply of actors mainstreaming GESI, environmental and inclusive growth in the design, financing and implementation of on and off grid RE projects.
- Learnings from individual strands will feed into the rest of programming – for example, learning from the demonstration project feeding into brokerage, and the programme raising awareness of the benefits of RE will support the policy strand, improving capacity and motivation among policymakers and influencers.
- Close collaboration with the GoI in the policy strand but also other strands enables the creation of secondary benefits (soft power).
In the context of the programme being in its second year of implementation, the review finds the Theory of Change logic on steps to achieving outcome and impact to be valid. The recent introduction of the Viability Gap Fund (VGF) however illustrates that the assumptions made in the brokerage strand regarding the risk appetite of investors may have been too optimistic, assuming either a lower risk to small scale renewable energy projects or higher risk appetite. These changes need to be understood in the context of a change in global outlook with respect to expected return on investment in part driven by a rise in input cost. This will need to be revisited later in programme implementation, to see whether outcomes and impacts expected are being materialised by current projected programme end.

To note, as the collaboration and networking strand is changing in scope this year, with a shift in focus to further technical assistance and mainstreaming into the other strands, this revision will need to be reflected in an update Theory of Change, and a subsequent update to the MENTARI logframe. As part of this process, the programme will consider whether and how a change in scope could affect expected and achieved outcomes and impact.

The Delivery Partner has revised the ToC for each strand, considering the current state of implementation and recent changes in the programme’s activities. Through this process, each strand had the opportunity to adjust its priorities and workplan, consequently reviewing the logframe indicators accordingly.

Figure 1: MENTARI Theory of Change (updated Feb 2022)

VfM (effectiveness)
- The Mentari team has 12 VfM indicators covering the 4 Es, including three on Effectiveness. These are useful tools to monitor the programme over time. So far only one observation (March 22) has been recorded and there are no external benchmarks. This means that it is not possible to make any statements as to whether the values of the indicators represent good VfM. (See Recommendation 8).
- Mentari is now in its second year of delivery. Due to Covid there have been some delays in the achievements of outcomes, in particular with respect to the demonstration project. But these difficulties have been overcome and the project is now due to be opened / handed over to the village in August 2022.
- The policy strand has delivered outputs and exceeded targets. However the work has also identified a number of risks to the achievability of the Mentari objectives. These risks include the indirect and direct subsidies for fossil fuels provided by the GoI and local content regulations including for renewable energy installations.
- The brokerage strand has identified over 30 renewable energy projects to be included in the pipeline. However its work has also identified a gap in the delivery chain caused by risks and uncertainties in the delivery of small scale renewables projects. The additional funding sought for the VGF addresses a risk to achieving the objectives of the programme. While this leads to additional spending, it is also an enabler for VfM by ensuring the investment targets are not missed.
Secondary Benefits
The programme has delivered strongly on Soft Power, creating a real sense of partnership with the MEMR and other parts of the GoI.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Two years into delivery, MENTARI is overall on track to contribute to expected outcomes and impact. Although the timelines for the demonstration pilot project were affected by the COVID-19 pandemic, so far results have not been affected.

At the outcome level, only the ‘number of types of jobs created in the demonstration project area’ had a milestone for March 2022 of 1, which was achieved. All other indicators do not have milestones for this annual review period, therefore the 6 ‘on- and off-grid renewable energy projects brokered’ and 1 ‘small business established or supported in the demonstration project intervention area’ have exceeded expectations.

Impact indicators are similar, with no milestones set for March 2022. Two impact indicators relate to households with energy access and renewable energy capacity additions, which are expected to be achieved following the implementation of the pilot demonstration project. Out of the cumulative milestone of £766m ‘investment brokered in Low Carbon Energy in Indonesia’, £487m has been achieved this year, which is a significant result for the programme. As a consequence, the programme could consider revising upwards the £766m milestone for December 2023, given over 50% of the figure has already been achieved this year, with two years left of programming.

MENTARI’s milestones for programme-end are ambitious – including 60 cumulative renewable energy projects brokered (outcome 2a), 15 cumulative businesses established or supported in the demonstration project area (outcome 3b), and 844,000 additional households with access to low carbon energy in Indonesia (Impact 1a).

Given output results, the programme is on track to achieving milestones at this stage of the programme. It will be important to review these next year when a year of implementation will remain to achieve results, following the annual review.

Year ahead:
- To contribute to the expected outcomes and impact, the success of the pilot demonstration project is crucial. This next year will be an important year to track initial progress against expected results in this strand, and ensuring that results associated with this strand will be achieved.
- To support the GoI in its preparation and hosting of the G20 events with respect to RE, and raising awareness of MENTARI programme.
- The introduction of the Viability Gap Fund (VGF) is also an important workstream this year, which will enable the brokerage strand to create further opportunities by a) reducing the risks to funding of renewable energy projects b) providing further Technical Assistance to the Government of Indonesia and its infrastructure financing company to develop capacity to support more renewable energy infrastructure. The VGF will have links to the policy strand of the programme, through capacity building activities.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the analysis of achieved results, independent reviewer’s data collection, VfM assessment, including the programme’s achievement of an ‘A+’ in this annual review, there is a clear and compelling case for MENTARI to continue. The review team has found the programme represents ‘good’ value for money, and is delivering high-quality outputs, and starting to deliver high quality outcomes, as well as secondary benefits such as an enhanced collaborative relationship with the GoI. The programme has additionally supported BE Jakarta through COP26 in supporting the GoI in its preparation and hosting of G20 events with respect to RE.

Mentari has implemented the recommendations from last year’s AR where appropriate – please find actions against the last year’s recommendations in the annex.

Recommendation:
Update the Theory of Change and Logframe based on revisions of workstrand. In particular, review and test underlying assumptions especially of the brokerage strand (Recommendation 7 in the summary table.)

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Outputs have been grouped by work strand. Intermediate outcomes have been included in the Annex to provide a holistic picture of the programme delivery at the end of Year 2. Narrative comments are provided after each set of scores (Outputs) by strand.
No weighting has been applied to outputs. This had been agreed at the beginning of the programme by the programme team. However, it has to be noted that it is likely that outputs are therefore weighted equally despite the fact that they play a different role in the programme delivery (see also the changes in budget and spending by strand in section E.)

POLICY STRAND
Output Title	Policy Strand, Output 1: GoI supported with recommendations on subsidiary regulations & effective implementation of a new Presidential decree
Output number:		1	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 1a: Number of recommendations on subsidiary regulations developed	1	Output moderately exceeded expectations / 2 policy recommendations a) Solar PV PPA study and b) Local Content Requirement Review for the Indonesian Ministry of Energy and Mineral Resources (MEMR)

Output Title	Policy Strand, Output 2: On-grid policy and regulatory recommendations developed (that mainstream GESI and business case) and presented
Output number:		2	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 2a: Number of on-grid policy and regulatory recommendations developed	1	Output met expectations / 1 thematic paper New Paradigm: “Renewable Energy Procurement in Indonesia” developed.

Output Title	Policy Strand, Output 4: Preparation/recommendation s for a regulatory framework and associated capacity building to implement the agreed business models
Output number:		4	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 4a: Detailed off-grid model design developed for agreed models	0	Output met expectations / (delivery: June 22)

Output Title	Policy Strand, Output 5: Guidelines, TA, or capacity building on planning, procurement, & contracting provided to PLN
Output number:		5	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 5a: Number of new and/or improved guidelines TA or capacity building provided on PLN planning, procurement, and contracting	2	Output moderately exceeded expectations / 3 technical guidelines assistance and capacity building to PLN on RE Quota calculation, grid management and blue energy development.

Output Title	Policy Strand, Output 6: Support for UK energy transition policy dialogue provided – output introduced during FY 21/22
Output number:		6	Output Score:	n.a.

Indicator(s)	Milestone(s) for this review	Progress
Policy Strand, Output 6a: Number of studies, activities and/or capacity building on energy transition provided		Training on grid management / Training on blue energy for blue economy – core modules / Training on blue energy for blue economy – elective modules

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the policy strand’s outputs is A+ as the programme has either met or exceeded expectations of the planned milestones for outputs under this strand. Output 6 was included in order to bring together all activities related to the UK energy transition policy dialogue under one output. It therefore has no set Milestones.

In addition to the outputs listed above MENTARI has also completed three activities outside the logframe which contributed to the policy strand:

- High-level review on the draft RUPTL 2021–2030
- Long-term energy planning, including a review of the energy sector’s nationally determined contribution targets
- Local content requirements review

MENTARI’s flexible and adaptable approach to addressing the needs of the GoI and BE Jakarta, as demonstrated by including output 6 and additional activities into the workplan, has been key to the achievements of this strand. The programme has responded flexibly to requests coming from the GoI and BE Jakarta, even if these were not part of the agreed workplan.

The MENTARI team closely collaborated with government officials, mainly from MEMR, as well as PLN and BEJ to understand their needs with respect to the energy sector. MENTARI provided technical assistance by producing several documents and policy recommendations. One example is the Geospatial Least Cost Planning Guideline to support MEMR’s and PLN’s interest in further capacity building to optimise hybrid generation. The secondees working in MEMR and funded by MENTARI are a mutual resource which on the one hand provide the GoI with skills and capacity and the other keep the MENTARI programme in MEMR’s mind.

As a result of technical assistance and capacity building work, MENTARI was successful in supporting MEMR and PLN to reform regulations and policy that encourage renewable energy development in Indonesia. The GoI ownership of the deliverables produced by the MENTARI programme is excellent.

Some examples of policy reforms where GoI incorporated recommendations from MENTARI were:

- The programme suggested using specific software and methodology to optimise the PLN Business Plan (RUPTL). MEMR included this suggestion in the MEMR ministerial decree 11/2021 as "optimisation of power system planning".
- The programme proposed a regular re-assessment of the implementation and projection of the RUPTL for PLN and business holders to increase their renewable energy penetration. MEMR added this suggestion in article 28 in the ministerial decree 8/2021 as an annual evaluation of electricity demand forecasting. In article 22, to increase the proportion of renewable energy in the RUPTL to achieve the target as stated in the General Plan of National Electricity (Rencana Umum Ketenagalistrikan Nasional – RUKN).
  [note] Business holders are project developers and investors who hold a business area license issued by PLN, allowing them to develop and operate energy projects in that area. By default, PLN has the right to develop and operate energy systems everywhere, unless they issue a license to others to do so on their behalf.
- The programme developed the thematic paper on New Paradigm: “Renewable Energy Procurement in Indonesia”. This paper also covers gender and inclusion aspects in RE procurement to ensure equal access to opportunities. This is contributing to implementing the PLN Diesel Replacement Programme.
In addition to the outputs of the policy strand described above MENTARI can at least be partly credited with an acceleration of the deployment of renewable energy and cleaner energy transition to ensure energy security
- The GoI has committed to the clean energy transition via the national energy plan (Rencana Umum Energi Nasional—RUEN) and targets a share of Renewable Energy Sources in the energy mix of 23% by 2025 and 31% by 2050.
- For the first time, Indonesia holds the G20 Presidency in 2022 with “Sustainable and Cleaner Energy Transition” as one of its three priority issues.
- Indonesia had prior to COP26 committed to reaching net zero emissions by 2060 or sooner with international assistance. In signing up to the Coal to Clean Power Transition Statement, Indonesia committed to exploring bringing forward the retirement of coal power to the 2040s (conditional on additional international technical and financial assistance) – retirement in the 2040s, is significantly earlier than current plans for phase out by 2058.
Value for Money, Policy Strand- Output level:
Outputs exceeded expectations while spending in total did not exceed the allocated budget (underspend 23%). This demonstrates that from an efficiency perspective the programme is on track to deliver VfM in this programme strand.
[note] It has to be noted that underspending can indicate a need to redistribute spending allocation or that the type of resources (e.g. staff skills) provided have not been suitable etc. However, this does not appear to be the case here.
In addition, the UK is supporting the US and Japanese International Partners Group leadership in developing a new Just Energy Transition Partnership (JETP) with Indonesia. The UK is already leveraging its strong networks and existing coordination functions, such as the Friends of Indonesia Renewable Energy (FIRE) dialogues established as part of the UK’s COP26 leadership in 2021 and supported via MENTARI to drive the success of the Indonesia JETP in collaboration with the GoI and other development partners.
The ability of the programme to deliver additional outputs and activities also contributes to efficiency, however they are likely to have taken up additional administrative and planning resources.
Recommendation:
Reduce the additional demands on the team to create a better balance of planned work and adaptive work. (Recommendation 4 in the summary table)
Explanation:
Being flexible and adaptable as per the context is considered as a strength of the programme. However, it can sometimes be counterproductive, if the GoI makes several requests or requests that do not align with MENTARI’s objectives. Open and transparent consultation with GoI and BEJ will be necessary to ensure alignment with MENTARI’s objectives and capacity to deliver. This would allow the programme team to focus on the implementation of the workplan activities to achieve agreed milestones.

BROKERAGE STRAND

Output Title	Brokerage Strand, Output 1: Innovative financing mechanisms/ better de-risking schemes supported (includes enabling access to these facilities) or developed
Output number:		1	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 1a: Number of new and/or existing financial schemes/facilities/mechanisms (i.e., blended finance facility or other de-risking solutions) that are receiving TA support	0	Output moderately exceeded expectations / Implementation of feasibility study by setting up VGF with SMI

Output Title	Brokerage Strand, Output 2: Extension of marketing and DD services for existing public and private investors
Output number:		2	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 2a: Number of marketing and due diligence proposals submitted to financial institutions	1	Output moderately exceeded expectations / Engaged 3 financial institutions to finance potential projects.

Output Title	Brokerage Strand, Output 3: Continuous engagement with financiers and developers for matchmaking and improving understanding of regulatory environment and opportunities.
Output number:		3	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 3a: Number of facilitation, meetings, trainings, FGDs, and/or events organised	5	Output moderately exceeded expectations / 7 match-making events

Output Title	Brokerage Strand, Output 4: Pipeline of quality low carbon energy projects (in “support mandate”)
Output number:		4	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 4a: Size and value of probability weighted pipeline for on-grid and off-grid clean energy projects (cumulative)	GBP 100 million (cumulative)	Output moderately exceeded expectations / 52 potential RE projects of risk-adjusted CAPEX value of GBP 944 million.

Output Title	Brokerage Strand, Output 5: Grant or Tailored TA to projects delivered (including projects linked to green bonds)
Output number:		5	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 5a: Number of low carbon energy projects that received TA, Grant, and/or brokering services	7	Output moderately exceeded expectations / Technical assistance and brokering services to 13 Renewable Energy Projects. Support PLN Diesel Replacement Programme and PLN Sustainability Bond

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Brokerage strand’s outputs is A+, as the planned milestones have all moderately exceeded expectations for outputs under this strand.

After delivering the feasibility study (see Output 1a) completed in the previous year, MENTARI and the BEJ programme team prepared an addendum to the Business Case worth £2.7m to support de-risking RE projects identified by PT Sarana Multi Infrastruktur (SMI), the GoI infrastructure investment company. It was signed off by the British Embassy Jakarta Country Board, Development Director and HM Ambassador. MENTARI worked with SMI to develop the internal procedures and due diligence processes to enable the establishment of the VGF with SMI. PT SMI appeared to be the ideal partner because it is a Special Purpose Vehicle of the Ministry of Finance to support national and regional state-owned enterprises in sourcing funding for the green economy, including renewable projects.

Under the VGF scheme, MENTARI will pay up to 20% of the total capital cost of renewable energy projects to the private project developers/investors to make the project economically viable. With VGF support provided to renewable energy projects, the electricity cost generated from RE projects will be similar to the average electricity cost generated from the non-renewable energy plants (e.g. coal fired plants). To the RT’s knowledge the selection criteria for the projects supported by the VGF have not been developed yet. The RT considers this a priority before the VGF actually goes live.
[note] See Business Case Addendum, VGF

MENTARI was actively engaged with investors and project developers for matchmaking purposes for financing RE projects. They have used different types of engagement methods such as one-to-one discussions, workshops, business forums and dialogue events to enable partnership opportunities. In 2021, the programme conducted 7 events to approach and engage directly with potential investors and project developers. As a result of these events, it was successful in matching 4 investors and 6 project developers. MENTARI have also identified 16 potential investors for other projects and are engaging 3 financial institutions to finance potential projects.

The programme has established a good number of projects in its pipeline. 52 RE projects with a total estimated risk-adjusted CAPEX value of GBP 944 million were in the pipeline of the programme by March 2022 and this pipeline is continuously increasing, exceeding the target of £766m. The pipeline consists of RE projects of different sizes including larger projects. This means that the project team had to address another set of challenges compared to the smaller projects supported at the beginning of the programme.
[note] See MENTARI, Annual Report, March 2022

In addition the programme delivered its technical assistance and brokering services to 13 RE projects, with an estimated CAPEX of GBP 392 million and supported the PLN Diesel Replacement Program with a CAPEX value of GBP 366 million and the PLN Sustainability Bond with a CAPEX value of GBP 380 million. Examples include specific technical assistance to developers working on hydro power stations and matchmaking support with a suitable investor. The programme closely monitors the project development status and records it in the Brokerage Investment Tracker.

The annual review process revealed that project developers find the MENTARI support and approach to develop RE projects unique and useful in providing support based on the needs of the company. In comparison, other development partners are more prescriptive. Most of the project developers were satisfied with the technical assistance provided by MENTARI. However, the RT has also seen evidence that communication and information provision by MENTARI about its activities could be optimised to give developers a fuller overview and understanding of MENTARI’s activities.

The project pipelines are encouraging. However, the RT noted that these pipelines are mainly from project developers/investors at a national level as MENTARI’s support was focused on a national level. This focus is likely to have been caused by the close cooperation with the national electricity provider while local, off-grid projects are owned by local governments and communities. (The Demonstration project is an example of this.) This focus is due to change to consider the regional (sub-national) potential as well.
[note] A similar observation can be made at the policy strand which focuses on the national level and is only now starting to consider local and regional policy making.

The annual review process revealed that MENTARI carried out due diligence checks of its immediate partners and oversaw and monitored their financial audits. However, they did not carry out due diligence checks of the project developers/investors who benefit from the project. This might bring a reputational risk to the programme if the project developers/investors are found to have used funds without clear origins. However, the review team has not identified any signs that this risk has actually occurred.

Value for Money
This programme strand is on track to deliver VfM. The inputs have been used efficiently to deliver outputs. The decision to set up the VGF is likely to ensure effectiveness of the Brokerage Strand by providing the necessary enabler to overcome a gap in the risk profile between projects and investors. The Business Case addendum provides a clear rationale for intervention.
[note] The Mentari team has 12 VfM indicators. However, only one observation exists at the moment (March 22) and there are no external benchmarks. It is therefore not possible to make any meaningful VfM statements.

MENTARI decided not to support a project which would have involved close cooperation with PLN, after completing a feasibility study. MENTARI considered it of insufficient quality and a potential risk to MENTARI’s reputation. In the view of the RT, a decision like this supports the effectiveness of the programme even though it means some money has been spent on a project that will not come to fruition.

Recommendations:

Expand the MENTARI support to the sub-national level. Support local government to develop local energy transition plans and support local project developers/investors to develop their renewable energy projects. (Recommendation 5 in the summary table)

Ensure clear and transparent selection criteria for the VGF (Recommendation 3 in the summary table).

Urgently carry out due diligence checks of all partners to ensure the MENTARI support is provided only to genuine project developers/investors and ensure there is no reputational risk to the programme and UK government. (Recommendation 1 in the summary table)

DEMONSTRATION PROJECT STRAND
Output Title	Demonstration Project Strand, Output 1: Feasibility studies (supply + demand) & business cases (including technical, economic & social potential of low carbon energy) developed
Output number:		1	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output 1a: Number of feasibility studies and business cases developed	1	Output met expectations / 1 pre-feasibility study for the Demand Load Incentivisation Programme through Productive Use of Energy for Mata Redi and Mata Woga.

Output Title	Demonstration Project Strand, Output 2: Off-grid demonstration project implemented
Output number:		1	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output indicator 2a: Number of small-scale off-grid low carbon energy facilities established and operational		Output met expectations / After some delay contract for engineering and construction signed in January 2022 (completion expected August 2022)

Output Title	Demonstration Project Strand, Output 3: Inclusive off-grid development models (including training on low carbon energy business models, O&M, PuE, and GESI potential) provided to the community, TVET providers, local FIs, local government, BUMDes, BLU and O&M providers
Output number:		3	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output 3a. Number of trainings on low carbon energy business models (technical and non-technical)	5	Output substantially exceeded expectations / 15 training activities to support and ensure the sustainability of the Demonstration project.

Output Title	Demonstration Project Strand, Output 4: Knowledge about applying small-scale renewable energy for electrifying off-grid produced
Output number:		4	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output 4a. Number of knowledge products about small-scale off-grid produced	1	Output moderately exceeded expectations / 3 knowledge products completed and used during capacity-building activities of the communities.

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall score for the Demonstration strand’s outputs is A+ as the programme has either met or exceeded expectations for the planned milestones for outputs under this strand.

MENTARI designed the solar PV demonstration project to support productive use of energy by local businesses and income-generating activities that could enhance the economic activities of the village as well as increase clean electricity access to households. This model is expected to reduce the cost of power generation due to the increased load factor of the system and lead to increased income for local communities.

The programme finalised the pre-feasibility study for the solar energy project for Mata Redi and Mata Woga in August 2021. The feasibility study complies with the Indonesia National Standard guidelines and other international standards, which include a significant exploration of social, gender, and environmental issues. After completion of the pre-feasibility study, a call for tender was launched to identify an engineering and construction provider for the project. The call was successful but the successful bidder required additional work which led to costs and caused delay. However, the project is now on course to be completed in August.

In addition, MENTARI produced three knowledge products: Guidelines and Toolkit for the Business Model, Gender Action Learning and Sustainability Building Movement and Community Energy Toolkit (Comet) Modules: electricity for households. These knowledge products were used during capacity building activities with the communities in these villages and were aligned with the policy strand’s outputs.

The programme provided around 15 capacity development trainings to community members to support the use of and ensure the sustainability of the demonstration projects. These trainings were aimed to prepare the village-owned enterprise to operationalise the solar mini-grid system, develop technical skills in operating and managing solar PV plants, provide skills and knowledge for productive use of energy and mainstream gender and social inclusion aspects.

The programme identified the potential businesses and income-generating activities in the community that could be the anchor loads for the solar PV system, thereby combining RE with sustainable livelihoods. They supported businesses to follow the market standards related to planting, harvesting and packaging of agricultural produce and to establish business-to-business linkages to ensure access to markets.

Through MENTARI support, the village-owned enterprise focusing on the renewable energy business - BUMDes Hali Dewa was officially launched in Mata Redi in August 2021. The programme carried out several activities to help BUMDes to establish and operate effectively. The programme consulted with different government officials, including Ministry of Villages, Development of Disadvantaged Regions and Transmigration and MEMR to comply with the national and regional regulations. MENTARI also initiated the discussion with PLN to ensure the quality and sustainability of the BUMDes in operating and managing the mini grids.

MENTARI’s support described above combining community engagement, inclusion and sustainable local businesses is considered key for the sustainable operation of the solar system and economic growth of the village. These types of continuous technical assistance activities are expected by stakeholders to allow scaling up of solar mini-grid systems in other remote villages. However, the RT also note concerns raised about the sustainability of the Demonstration Project caused by its own success: once it is handed over to the local government and BUMDes there is a risk that growing electricity demand of the village outstrips supply leading to disappointment in the system. However, the MENTARI team assesses that the design of the scheme allows for sufficient growth over the coming years.

Value for Money
The Demonstration Project Strand has delivered and exceeded expectations with respect to outputs. This indicates that it is on track to deliver efficiency. The hold ups and delays of the completion of the contract for the construction of the demonstration project however led to additional costs, which might cause risks to VfM (economy). However, the RT has not seen evidence that this led to an increase in costs. This is caused by:
[note] The Mentari team has 12 VfM indicators. However, only one observation exists at the moment (March 22) and there are no external benchmarks. It is therefore not possible to make any meaningful VfM statements.
- Over time there have been more training and engagement activities than first envisaged. This additional Community Engagement work which would have come at an extra cost to the FCDO was balanced against earlier savings or had to be cancelled due to COVID.
- The scope of the demonstration project changed as an additional hamlet was included in the project.
- The costs for the design and construction of the demonstration plant have not increased even though there had been delays due to COVID.

COLLABORATION & NETWORKING STRAND
Output Title	Collaboration & Networking Strand, Output 1: Capacity building and knowledge exchange, including focus on opportunities for women and marginalised groups, provided to inter/national academic/TVET stakeholders in low carbon energy sector
Output number:		1	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Collaboration & Networking Output 1a: Number of International and Indonesian academic and/or training institutions receiving programme matchmaking and/or knowledge sharing support	1	Output moderately exceeded expectations / Support BLK Don Bosco and the establishment of the Indonesia Blue Energy for Blue Economy Centre of Excellence (IBEC).
Collaboration & Networking Output 1b: Number of activities organised by MENTARI for supporting inter/national academic and TVET stakeholders focusing on low carbon energy in Indonesia.	1	Output moderately exceeded expectations / 4 activities to support Indonesia's international or national academic and TVET institutions in low carbon energy development.

Output Title	Collaboration & Networking Strand, Output 2: Branding & communication products produced to share knowledge and lessons
Output number:		2	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Collaboration & Networking Output 2a: Number of communication and knowledge products produced and disseminated	1	Output substantially exceeded expectations / 16 communication and knowledge products to its key partners and the general public.

Output Title	Collaboration & Networking Strand, Output 3: Promoted knowledge sharing and facilitated partnerships
Output number:		3	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Collaboration & Networking Output 3b: Number of events (consultation, facilitation, FGD, workshop) to facilitate knowledge sharing and partnership development	10	Output moderately exceeded expectations / 28 events to facilitate knowledge sharing and partnership development.

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Collaboration & Networking strand’s outputs is A+ as the programme has either met or exceeded expectations for outputs.

Several organisations, both international and Indonesian academic and/or training institutions received MENTARI support. BLK Don Bosco, a local TVET institution in Sumba and a key partner of the programme received several trainings. In addition, the programme supported the establishment of the Indonesian Blue Energy for Blue Economy Centre of Excellence (IBEC), a consortium of the Institute of Technology Surabaya (ITS - Indonesia), Heriot-Watt University (UK), Aquatera, and Tekno Sains.

MENTARI organised 4 activities (in person and online events) to support Indonesia's international and national academic and TVET institutions in low carbon energy development. The programme aimed to contribute to human resource development in the renewable energy sector in Indonesia through these activities.

In addition, the programme organised a total of 28 activities to facilitate knowledge sharing and partnership development among several stakeholders, including GoI, PLN, donor programmes on renewable energy, academia and TVET. For example, MENTARI organised and facilitated Indo EBTKE ConEx and side events covering Solar PV Hybrid and marine renewable energy technologies. These events aimed to disseminate recommendations, lessons learned, and knowledge developed by the programme.

The programme produced 16 communication and knowledge products and shared them with partners and the general public through its website, YouTube channel and other communication platforms. The press releases of Indo EBTKE ConEx 2021 were covered in 149 articles by 86 online media and three printed media. This has increased the visibility of the programme and opened the opportunities for collaboration and partnership among the stakeholders.

The RT noted that coordination between some ministries of the GoI could be optimised with respect to the promotion of low carbon development in Indonesia. For instance, Indonesia’s energy related targets in its NDC appear less ambitious than Indonesia’s National Energy Policy (NEP) and medium-term development plan would allow.

Similarly, there are various approaches taken by different development partners such as USAID, GIZ, World Bank, ADB etc. to promote clean energy in Indonesia. This complex landscape may at times create confusion among stakeholders.

MENTARI may be able to play a role to improve coordination. However the RT was not able to collect sufficient detailed evidence in order to come to a conclusion concerning the root causes of the lack of coordination or make informed recommendations.

One project developer mentioned they feel limited data and information is available on MENTARI’s website and social media compared with other development partners. This particular developer stated that they were aware only of the strand they are working with and not what other strands are doing. They suggested improving the content of website and social media which they use to look for information on upcoming events, fund availability, genuine investors and project developers, policy recommendations, programme outputs and outcomes etc.

Value for Money
Networking and coordination has exceeded expectations with respect to outputs demonstrating that the strand is on track to deliver VfM (efficiency). The RT notes that the programme team intends to merge this strand into the other three strands.
[note] The Mentari team has 12 VfM indicators. However, only one observation exists at the moment (March 22) and there are no external benchmarks. It is therefore not possible to make any meaningful VfM statements.

Recommendations:

Increase visibility and content of the MENTARI programme through its website and social media (Recommendation 9 in summary table)

GENDER, SOCIAL INCLUSION AND ENVIRONMENT
Output Title	Gender, Social Inclusion and Environment, Output 1: Programme demonstrates G&I integration across (i) MENTARI programme intervention design (internal), (ii) support to relevant stakeholders (internal/external), and (iii) knowledge sharing (internal/external).
Output number:		1	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Gender, Social Inclusion and Environment Output 1a: Percentage of women and/or marginalised groups involved in facilitated discussions	Minimum 30%	Output moderately exceeded expectations / 41% female participants
Gender, Social Inclusion and Environment Output 1b: Number of most significant stories, focused on livelihood, gender and inclusion, and secondary benefit, developed to illustrate project contribution to socio-economic, education, empowerment, environmental conservation benefits in the area of demonstration project.	1	Output met expectations / 1 Gender and Social Inclusion case study: "Unlocking Young Women's Potentials in Mata Redi".
Gender, Social Inclusion and Environment Output 1c: Number of G&I learning events organised that will focus on programme stakeholders (e.g., policymakers, financiers, private developers, etc.)	2	Output met expectations / 2 learning events to mainstream Gender and Social Inclusion in the low carbon energy sector.
Gender, Social Inclusion and Environment Output 1d: Number of G&I TA support provided to programme stakeholders (internal/external)	8	Output moderately exceeded expectations / 20 different types of Gender and Social Inclusion TA

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Gender, Social Inclusion and Environment strand’s output is A+ as the programme has exceeded planned milestones for outputs under this strand.

MENTARI considered Gender and Social Inclusion as a crucial part of the programme. They prepared a guideline for delivering inclusive online events to ensure G&I sensitivity. The programme organised/facilitated several events, where 41% of the participants attending the events were women.

In addition, the programme developed one Gender and Social Inclusion case study: "Unlocking Young Women's Potential in Mata Redi". The case study highlights the immediate positive changes that emerged from young women and men who participated in the trainings provided by MENTARI. This case study was shared with government and other organisations including the local community in Mata Redi.

MENTARI conducted 2 learning events and 20 different types of interventions to mainstream Gender and Social Inclusion, starting from the design to implementation at the project level in the RE projects. These interventions include developing the practical guidelines, G&I safeguards, handbooks, action plans, monitoring plans, case study and building awareness and capacity of relevant stakeholders on necessity of G&I integration and its applicable instruments in a low carbon energy programme, ensuring that this market is accessible to women, youth, people with disabilities and other marginalised groups through organising workshops, seminars, and training events etc.

Value for Money
Equity is an important factor in delivering VfM. The MENTARI programme is on track to deliver VfM with respect to equity.

Recommendations:

Continue mainstreaming gender equality, social inclusion, and environmental standards in all phases of the programme cycle to ensure vulnerable people benefit from the programme. Track risks to capture safeguarding issues and implement safeguarding procedures effectively. (This recommendation is not listed in the summary table.)

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The Recommendation from last year’s AR and actions taken can be found in the Annex.

D: RISK

Overview of risk management

MENTARI has an overall risk rating as Receptive.

There are 34 risks in the MENTARI risk register. MENTARI is currently using out of date risk categories instead of current FCDO risk categories to register risks to the programme. In addition, the MENTARI risks are currently not uploaded in the AMP.

None of the risks are above the FCDO’s appetite line and rating of risks is either Receptive, Cautious or Minimal after mitigation actions.

The BEJ programme team keeps oversight of risks via steering committee meetings and ensures risk is a standing agenda item for the meeting with partners. Similarly, the delivery partners provide updates on risks in their quarterly progress report.
Type of risk (from risk register)	Mitigation
Strategy and contextual risks include risks related to the COVID-19 pandemic and focus on recovery, unsupportive regulations for renewable energy, political changes, and natural disaster.	During the year, the programme implementation suffered from COVID-19 impacts such as cyclical mobility restrictions, and the GoI’s focus on recovery, limiting prioritisation of low carbon objectives in Indonesia. Local economic downturn reduced GoI support and investor appetite in renewable energy. The programme was flexed to address the need of the context and delivery was continued virtually, taking the necessary safety measures. / The programme made a case for green recovery and pivot options such as supporting PLN’s diesel-to-solar initiative and sustainable bonds. / Events such as natural disasters or terrorist incidents may occur, so the programme has considered the ways to mitigate these risks in the programme design, selection, and implementation.
Policy and programme delivery risks include risks related to FCDO’s ODA cuts, PLN’s focus on promoting least-cost energy, delay in accessing data from PLN, possibility of failure of the demonstration project and COVID-19 and its impact on leveraging external funding and implementing the demonstration and brokerage activities.	The programme has addressed the risks associated with political changes through close collaboration with GoI officials, adapting to meet their requirements, enhancing their capacities, and embedding programme staff in the ministries for greater influence and monitoring of results. FCDO and its delivery partners will remain vigilant in the operating environment, continue identifying and managing risks along with scenario planning to mitigate possible risks. / To mitigate these risks, the BEJ and the MENTARI team continued regular engagement and coordination with high level officials from the Ministry of Foreign Affairs, MEMR, PLN, private developers, investors, and other relevant stakeholders. / BEJ influenced the GoI through the co-chairing of the Friends of Indonesia Renewable Energy Dialogues. The programme carefully selected the feasible technology, location, and community for the demonstration project. They extensively engaged local government and the local community and built their capacity to ensure their buy-in on the project, in order for the project to be operated sustainably.
Financial and fiduciary risks include mismanagement of funds by DPs and selection of RE project developers/investors with a vested interest that could lead to reputational damage and failure to achieve outcomes.	To mitigate these risks, MENTARI carried out due diligence checks of its immediate partners and oversaw and monitored their financial audits. / The programme should set robust selection criteria and risk mitigation measures to mobilise the VGF (see Recommendation 2)
Reputational risks include support to project developers/ investors that use money from money laundering, COVID-19 transmission from the programme team to demonstration project community and support to PLN being perceived as supporting coal use in Indonesia.	The annual review revealed that MENTARI relied fully on the due diligence checks conducted by other partners including private companies. This arms-length due diligence clearly causes risks to UK’s reputation. However, no evidence has come to the RT’s attention indicating this risk materialising.
Safeguarding risks mainly include risk of vulnerable people being exploited in the Mentari’s demonstration projects and renewable energy projects supported by the brokerage strand.	To mitigate these risks, MENTARI have carefully considered gender equality, social inclusion, and environmental standards throughout its project cycle - design, community mobilisation, delivery and monitoring. / MENTARI has a comprehensive risk register to capture safeguarding and other risks and has ensured appropriate safeguarding procedures that are implemented effectively. The BE Jakarta and the MENTARI have prioritized safeguarding agenda and has provided orientation and training to partners.
People risks include disputes within consortium partners, staff leaving the programme and risk of exposure of staff to COVID 19.	To mitigate these risks, the MENTARI developed the ways of working, clear responsibility and expected deliverables from the consortium partners and provisioned to make any replacement sub-contractors and/or staff, including ability to re-contract or adapts program outputs if necessary to ensure a high performing programme. / The programme also organised a wider team building exercise and strategy session to improve team relationships and to better understand the programme objectives and scope. Similarly, BE Jakarta and all partners have put in place standard operating procedure for COVID-19 and adopted remote working modality where possible.

Recommendation
The risk register is currently not following FCDO’s guidance and are not registered on the AMP system. The RT recommends to structure risks according to the FCDO’s guidance, upload them to the AMP as soon as this is available and, in the process assess the PT’s risk appetite for each risk (Recommendation 2 in the summary table).

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The programme has been well managed over the year considered in this report. COVID caused significant challenges.
The delivery partner regularly reports with:
- 12 monthly financial forecasts and actuals
- 4 quarterly reports which run into 40 pages and more
- 4 presentations to the steering group, which include the content of the QRs
- 1 Annual report summarising the quarterly reports and highlighting outstanding results etc.
The RT considers the length of the QRs and the Annual Report as too long and too detailed, in places repeating what has already been reported. It might be advisable to shorten the QRs or reduce the duplication of effort which comes with a QR and a PowerPoint presentation for the Steering group.

The RT has been content with the statements and information by programme team members and delivery team members as to how risks can be reported, including by junior staff in MENTARI.

Economy
Figure 1 Budget and Actuals by Strand - over time and compared to Business Case

Notes:
- The strand in the SOBC are: Policy, Brokerage, Pilots (here Demo) and Enabling Technology (Capacity Building or Networking and Collaboration)
- Figures include all RDEL and CAPEX for demonstration project (GBP 570,404.20. VGF CDEL not included.
- In year 1 RDEL was equally allocated as initial allocation was not per strand

Spending compared to Budget in Year 2
Overall the programme underspent by 39%. This underspending varies between types of activity and strand, as can be expected given the pandemic and the ease with which activities could be continued. In some cases this meant that activities had to be postponed in others that they moved online.
These variations also reflect the flexibility of the programme and the teams willingness to adapt. For example, “Third Party led activities”, about 15% of the total budget, include spending on an activity in included for third party engagement which had not been included in the budget.

Other budget lines which overspent include the work on the website, according to BEJ an area which they would like to see developed in the future and used to more effect as a communication tool, the delivery partners staff and personnel spending on the Policy Strand which overspent by 20% reflecting the changes in personnel in this area as well as prioritisation of the TA in this area.

Quality of monthly financial forecasting could be improved. This may be explained by the pandemic, however, this has been no improvement as could be expected as the team learnt over the course of the pandemic its impact on spending.

Short term TA underspent by more than the programme overall with the exception of the support the Diesel Replacement Programme as part of the Brokerage Investment. Other significant underspends occurred in Overheads for events such as Learning, Workshops and Training, which are most likely to have been moved online.

Figure 2 Spend Compared to Budget in %

Note: The budget was reduced during year 1 from £2.5m to £2.m. This explains the difference between the figures in section D of the last annual review and this AR.

Cost drivers
As noted in AR 2020/21 the costs are driven by the characteristics of the programme which is mainly a TA programme with the added capability of the brokerage work, also TA. Most of the spending is on personnel and short term technical advisors. These also require overheads and to some extend travel expenses as far as that was possible. The programme could therefore be subject to changes in day rates of advisors. However, these are agreed in the contract and the financial reporting provides clear and transparent information.
The CDEL was spent in the last month of the Financial Year 21/22. The budget was transferred to an escrow account managed by Palladium, to be invested into projects alongside PT SMI. No funds were, or will be, transferred to SMI directly.

Financial Reporting and Management
The programme does not use an Activity Based Budget (ABB). This makes an assessment of spending or unit costs more difficult than it otherwise would be. However, at this stage in the programme’s delivery period, while the use of ABB is included in the recommendation this is not deemed as urgent. The programme team will want to balance the resources it will take the delivery partner to change its approach to financial reporting and forecasting with the benefits of more scrutiny.
The programme team has provided some challenge to spending as detailed in the Monthly Forecast March 2022 Final spreadsheet. This demonstrates the scrutiny required for this programme.
The contract contains the obligation for the of benchmarks. Benchmarks and VfM indicators have been provided to the RT team. While these will be useful in the future currently they are not very informative because only one number has been reported. In addition to this internal benchmark we also recommend that the MENTARI team includes some external benchmarks to demonstrate its ongoing VfM.
The detailed financial report supplied by MENTARI to the RT includes profits per consortium partner, the costs of different staff etc. This allows the programme team to keep a close oversight over the spending compared to budget.
While the MENTARI team has provided detailed financial data, it is not possible to establish how much of it was admin spending. However, as stated in the AR for 20/21 the programme is exempt from the strict admin spending limits because of the type of work delivered. The contractual arrangements which cap the spending on the one hand and include refunds to HMG in cases of underspend in combination with the programme teams scrutiny provide sufficient safeguards on spending.

The spending pattern of RDEL was as could be expected throughout this financial year.

Efficiency
MENTARI is on track to deliver VfM with respect to efficiency. As said above, inputs have been turned into outputs and some expectations have been exceeded in all strands.
Cooperation with other donors is a particularly important part of achieving efficiency. This includes the avoidance of duplication of other donors’ work but also improved coordination and mutual support.
Activities such as FIRE or achievements under Intermediate Outcome 2 for the Cooperation and Networking Strand demonstrate the success the programme had. There is more scope to develop cooperation with other donors as observed under section D.

Recommendation
Identify and use external benchmarks, particularly to enable a VfM assessment over rest of delivery period. (Recommendation 7 in the summary table)

Date of last narrative financial report		Date of last audited annual statement	Palladium submitted an annual (external) audit statement to FCDO on 5 June 2022.

Annex
Recommendations 2020/21
Recommendation from Annual Review 2020-21	Assessment on Progress (August 2022)
Recommendation 1: Financial Information Monitoring – Whilst the Review Team found the programme had close monitoring of the invoicing for the Palladium expenses, RT found it difficult to assess the achievement of the KPIs by the Delivery Partner against the payment milestones. RT therefore recommend that a more structured budgeting is put in place to enable the detailed forecasting for the remainder of the programme which is tied in with the delivery milestones by Palladium.	FCDO and Palladium have discussed invoicing and reporting structures in response to this recommendation and as a result some changes to the budget and work plan structure have been put in place. This includes an updated Palladium annual and monthly forecast structure, which sets out estimated costs for each activity line. / The RT agrees that switching to an output-led, milestone based approach across the programme may undermine significantly the ability of the programme to be adaptable and responsive to changing requirements and new opportunities.
Recommendation 2: the Brokerage Strand is the most challenging part of the programme and will require close monitoring of its objectives in order to achieve its successful delivery within the short time scale of remaining 2.5 years.	This is an ongoing action and one that Mentari must continue to prioritise and find ways to continuously improve delivery. The Brokerage Strand remains an important and challenging part of the Mentari programme. Significant progress has been made since the previous Annual Review in 2021, and new structures have been put in place to increase the resources available to the Brokerage Strand team, including additional Strategic Short-Term Technical Advisors and regional leads who are responsible for sourcing additional local projects. These efforts must continue, and FCDO and Mentari are exploring options to scale up Brokerage resources and activity to utilise additional funds allocated to the programme.
Recommendation 3: Demonstration Project strand should be monitored closely so that it is tied in with the Policy and Brokerage strands.	The Demonstration Project has made significant progress since the last Annual Review in 2021, with the procurement of an Engineering, Procurement and Construction (EPC) contractor in late 2021, and ongoing construction throughout 2022. The project is expected to reach its operational stage in August 2022. / There is ongoing learning from the demonstration project going into the policy and brokerage strands.
Recommendation 4: The Collaboration Network would require closer ties with the Ministry of Finance who are responsible for the Green Finance policy and can influence the greater Policy strands in the programme, alongside the Ministry of Energy & Mineral Resources.	Efforts to engage the Ministry of Finance in detailed programme activity remain difficult, for Mentari and other Embassy programmes. Ministry of Finance are part of Mentari Government of Indonesia steering groups, and have been included in the UK-led Friends of Indonesia Renewable Energy (FIRE) dialogues, however it has been difficult to engage them in concrete programme activities. / Mentari should continue its efforts to engage the ministry. This work has started but will need continued focus over the rest of the programme. Other Embassy programmes will also engage the Ministry of Finance on key issues that may support Mentari objectives, for example the new UK Partnering for Accelerated Climate Transitions (UK PACT) programme work on carbon pricing.
Recommendation 5: The programme should continue to develop its Secondary Benefits strategy and engage with the delivery partner during programme mobilisation.	Mentari has made limited progress on supporting commercial benefits for UK business, although Mentari remains in regular contact with a number of UK-based renewable energy project developers and investors regarding the Mentari Brokerage Strand project pipeline, and as this develops this may lead to opportunities for UK business. / Mentari is no longer funded by the now defunct cross-government Prosperity Fund, which had clearer portfolio secondary benefit targets. / On other areas of secondary benefit, Mentari has made significant progress on UK soft power and furthering diplomatic objectives, notably with the development of the FIRE dialogues and UK COP26 presidency, as demonstrated in the AR above.

Intermediate Outcomes
This annex summarises the delivery of the programme on intermediate outcomes. All of these have met the target milestones as set out in the Annual Report by the MENTARI programme team.

Intermediate outcome / indicator	Progress
Brokerage
IO 1: Partnerships established between stakeholders, project developers and financiers
1a: Number of intermediations established between stakeholders, project developers, and financiers	Four intermediations were established between stakeholders, project developers and financiers by MENTARI to develop projects.
IO 2 Improved capacity to identify & appraise projects, with more financing options
2a: Number of potential financiers showing commitment to make low carbon energy investments in Indonesia	Five financiers committed to finance renewable energy projects in Indonesia.
IO 3: Improved access to more appropriate capital for providers and low carbon energy companies (incl. innovative financing schemes)
Brokerage Intermediate Outcome 3a: Percentage change in outreach and/or applications taken by Programme partner investors	Exact percentage changes in outreach and/or applications taken by programme partners investors is not available. However, there are 5 investors have committed to invest in renewable energy projects supported by MENTARI
IO 4:Improved access to more appropriate capital for providers and low carbon energy companies (incl. innovative financing schemes)
4a Number of new and/or existing financial schemes/facilities/mechanisms tailored and presented to key stakeholders that could increase the flow of finance towards the low carbon energy sector in Indonesia	MENTARI presented VGF scheme to PT. SMI and they have agreed on the due diligence process and plans to disburse the VGF to selected project developers in 2022.
IO 5 Improved investment readiness and quality, including G&I & ESG, of low carbon energy projects and sponsors
5a: Number of low carbon energy projects report improved project quality, including G&I	MENTARI technical assistance improved quality and readiness for investment of 5 low carbon energy projects. These are / Three solar projects in Alor, Rote and Sumba developed by HDF Energy. / One solar project in Katingan developed by Watala. / Diesel Replacement programme of PLN
Demonstration Project
Intermediate Outcome 1: Improved capacity (technical & management) of BUMDes and O&M skills of PV operator to manage and maximise lifetime of small-scale off-grid low carbon energy facility
1a BUMDes has established minimum infrastructure to manage and maintain off-grid low carbon energy system	One BUMDes Hali Dewa in Mata Redi was established in August 2021, and it has minimum infrastructure to manage and maintain solar PV project.
1b: Number of guidelines on Village Funds for small-scale low carbon energy that generate local community interest and/or are adopted	MENTARI developed “Guideline and Tool kit for BUMDes Establisment” to establish BUMDes describing the process of developing and managing, inclusive village-owned enterprises focusing on the renewable energy business. BUMDes Hali Dewa has adopted this guideline to operate and manage the mini-grid system.
1c: Number of instances that showcase local government and local community claiming ownership of demonstration project	MENTARI recorded two types of local contributions, which came from the local government and community in developing the demonstration project in Mata Redi. Local government approved decrees and formed Steering Committee while community contributed time and local materials for the project.
Collaboration and Networking Strand
IO 2: Improved knowledge exchange, learning, collaboration & partnerships, that mainstream G&I, in the low carbon energy sector
2a: Number of key stakeholders (including civil society organisations, technology providers, media, local government (local/national), public institutions, etc.) collaborating and forming partnerships	MENTARI collaborated and formed partnership with two stakeholders to support human resources development in Indonesia’s low carbon energy sector. These stakeholders are / Swiss State Secretariat for Economic Affairs (SECO) through their programme "Renewable Energy Skills Development" (RESD) / Balai Latih Kerja (BLK) Don Bosco, a local TVET institution in Sumba