## Annual Review Template

Title: MENTARI* UK-Indonesia Low Carbon Energy Partnership (referred to in pre-delivery as Indonesia Renewable Energy Programme (IREP)
Programme Value £ (full life): £20 million with cost and time extension (initial budget was £13.5 million). The programme value during the period being reviewed was £13.5m		Review date: July 2023
Programme Code:	start date: 6 January 2020	end date: April 2026

Summary of Programme Performance

Year	December 2019 (Light Touch)	Jan 2020 – April 2021	April 2021– March 2022	April 2022 – March 2023
Overall Output Score	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Log frame

## A: SUMMARY AND OVERVIEW
Description of programme
The Mentari (formerly Indonesia Renewable Energy) programme is a £13.5m programme that aims to support inclusive economic growth and poverty reduction through accelerating and expending clean and affordable energy in Indonesia, while mainstreaming Gender and Inclusion in its delivery. The programme started in January 2020 and was originally planned to end in December 2023. The business case addendum for a programme cost and time extension to April 2026 with total budget of £20 million was approved in June 2023.
The Mentari programme is working closely with the Government of Indonesia (GoI), and other stakeholders, to promote a conducive investment environment in the renewable energy sector of Indonesia. The programme has the following four strands, where gender and inclusion are mainstreamed in every workstream of the programme.
1. Policy Strand aims to reform national and regional renewable energy policies, regulations, guidelines, and financial instruments that bring about a more conducive business environment in the low carbon energy sector.
2. Brokerage Strand aims to increase investment in low carbon energy projects by bridging the gap between potential financiers and viable project developers through brokerage, technical assistance and providing small amounts of catalytic Viability Gap Funding (VGF).
3. Demonstration Project Strand aims to demonstrate viable and replicable off-grid low carbon energy systems that will bring socio-economic benefits including for women and marginalized groups.
4. Collaboration, Capacity Building & Networking Strand (CCBN) supports collaboration, networking, and capacity building of relevant stakeholders in the low carbon energy sector including policy makers, investors, project developers, communities, and academia.
The programme was originally a legacy cross-government Prosperity Fund Programme which now has been transferred to the bilateral Indonesia country plan budget, with the oversight of the Indonesia and ASEAN Development Director. A consortium led by Palladium International with Castlerock, ECA, and Hivos are the delivery partners of the Mentari programme.
Mentari has an adopted adaptive programming approach to respond to the dynamic changes resulting from Indonesia’s ambition towards a Net Zero emissions economy and to support the Just Energy Transition.
Summary supporting narrative for the overall score in this review.
The Annual Review was carried out from 24 June to 7 July 2023 covering the programme from April 2022 to March 2023. The Annual Review team comprised three team members: Resha Piya, Energy Advisor, British Embassy Kathmandu, Anintya Hapsari, Portfolio and Finance Manager, British Embassy Jakarta and Rohini Kumar, JETP Finance lead, FCDO. The team conducted meetings with several stakeholders of the programme including British Embassy Jakarta (BEJ) implementing team, delivery partners, government officials relevant to the programme, PT Sarana Multi Infrastruktur (PT SMI) and PT Brantas in accordance with the terms of references provided to the review team. The team also visited the solar mini-grid sites at Sumba and observed the technical aspects of the systems, interviewed the local government representatives, communities, BUMDes members and technicians managing the solar systems. Based on the observations and feedback from the stakeholders the team has prepared this report.
The overall score for the Mentari programme for this year is A+.
Some of the achievements supporting the overall score in this review include:
The programme has either met, moderately exceeded, or substantially exceeded expectations of the planned milestones for all outputs. The Mentari team has been successful in meeting the expectations and gaining the trust of GoI and other stakeholders in the energy sector due to its flexible and adaptable approach. This is as a result of the high-quality technical assistance (policy recommendations, guidelines, studies, training etc.) provided by the Mentari team which GoI is using in developing their policies and regulations.
The programme’s Technical Assistance (TA) to project developers has increased the bankability of the projects and increased the confidence of the investors. As a result, Mentari has brokered a pipeline of 25 Renewable Energy (RE) projects at different stages worth GBP 680 million (cumulative). Mentari has also developed a system to deliver viability gap funding (VGF) to enable PT SMI to invest in less bankable projects that have economic and social impacts, which would otherwise not be commercially viable. Through this VGF, Mentari has signed grant agreements with PT Brantas Energi for developing three hydropower projects. With a relatively small VGF amount (£1.1million) invested in these projects, it has been able to mobilize 6 times the investment from PT SMI and project developers.
The programme has successfully demonstrated that decentralised solar PV mini-grid systems for rural electrification can be extremely effective. The team has closely worked with the local government and communities to develop their capability on operating and managing the system for the long term.
The CCBN strand of the programme has also effectively collaborated with other Mentari’s programme strands and with external stakeholders, including government, academic institutions, project developers, and other development partners. They were successful in strengthening partnerships among key government ministries to work on low carbon energy policies such as Local Content Requirements (LCR) and Women’s empowerment in Renewable Energy Sector.
In addition, the Mentari team has successfully integrated Gender and Inclusion (G&I) considerations into many of their activities under all strands.
Progress on recommendations from the previous AR (if completed)
There were 9 recommendations in last year annual review and 6 of them have been completed. Three recommendations are still to be completed, these are ensuring clear and transparent selection criteria for the VGF, reviewing targets/milestones as they may not be high enough, and identifying and using external benchmarks, particularly to enable a VfM assessment over rest of delivery period. Based on the previous year’s recommendations, the Mentari team worked with PT SMI and the BEJ team to develop the selection criteria and process for the VGF. The team also worked closely with the local and regional levels of government, particularly during the implementation of demonstration projects. To increase the visibility of the programme, the team updated the MENTARI website, YouTube channel and posted key activities through social media. The programme team reviewed and updated the Theory of Change (ToC) and logframe. However, there were no significant changes made nor were the milestones made high enough. The recommendation is to review the ToC and increase the milestones linked to the service credits (incentives linked to the completion of certain deliverables) to reflect the actual workplan activities, such as work related to the Policy strand and Collaborating, Capacity Building and Networking strand.
The Mentari team is working with the grant management team and legal and finance specialists to improve the due diligence process while selecting the renewable energy projects. The team is closely collaborating with the BEJ team to manage pressure from the additional demand on the team like supporting G20 events, Hydrogen Roadmap etc.
Major lessons and recommendations for the year ahead
The major lessons learned, and recommendations are:
- The Indonesian Renewable Energy sector is rapidly evolving. Whilst Mentari has benefitted from its adaptive and flexible programming approach, balancing this with proper project management discipline (including revising ToC and milestones, regular forecasting and budgeting, updating workplans) would support the team to respond to the challenges of changing priorities and requests from the GoI and other stakeholders. This would also help the programme to avoid being stretched too thin across multiple requests. Revising the ToC and better alignment of programme indicators (outcome and output indicators in the logframe) with International Climate Finance (ICF) Key Performance Indicators (KPIs) will also support more effective measurement and reporting of ICF relevant results.​
- In the VGF implementation, the stakeholders’ interpretations of the current VGF proposed funding guideline were found to be not uniform. Therefore, the criteria need to be more clearly defined and the implementation of the VGF should comply with these guidelines.
- The project developers were waiting for the VGF to be disbursed while the annual review process was carried out. This delay could have a detrimental impact on the success of the scheme while BEJ is considering options to scale it. Therefore, expediting both the disbursement for the current qualifying projects as well as the review and evaluation of the scheme overall is recommended.
- For the demonstration project, a detailed feasibility study was carried out including the possible productive use of energy in the villages. However, there was very limited evidence that the communities were pursuing the productive use of electricity. As per the villagers’ feedback, the higher cost of the required tariff was the main constraint for pursuing business endeavours. The recommendation is to evaluate the tariff structure to explore making it more affordable for domestic and productive use of energy.
- For the CCBN strand, there was good communication at workstream level with relevant line ministries. However, broader comms from the programme to all relevant ministries is recommended, as there was some evidence that certain ministries were unaware of activity in workstreams that they were not specifically involved in but where that activity might have been relevant or of interest to them. More effort is needed to coordinate between the programme (all strands) and all relevant ministries and to disseminate information.​
- Mentari has tried to incorporate G&I in all strands. However, G&I integration in the Brokerage strand is still challenging, specifically around finding women-led and disadvantaged groups-led renewable energy projects or initiatives. Therefore, specific interventions targeted at women and disadvantaged groups to bring them into the low carbon energy supply value chain when providing TA via the brokerage strand is recommended.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Mentari programme has recently reviewed their Theory of Change. There has been no change in the impact statements “Increased access to reliable and affordable low carbon energy (including for women and/or marginalised groups) leads to inclusive economic growth” and “Increased investment in quality low carbon energy projects”. These original impact statements remain relevant at this point in the programme and for the coming year.
However, the programme has included three additional intermediate outcomes since last year to measure the practice and lessons learned from the demonstration project, including the local ownership of the off-grid systems, its business models managed by Badan Usaha Milik Desa/Village Owned Enterprise (BUMDes) as well as the replicability of the model. The addition of these intermediate outcomes is relevant. There are also minor refinements in some intermediate outcome statements to make it clearer and to capture the support to broader stakeholders.
Additionally, since the original business case, an intermediate outcome statement 5, “Indonesia’s stronger engagement and political position at international energy transition dialogue” under the Policy Strand had also been added in year 2 to measure the activities carried out by Mentari to support GoI on energy transition.
Some of the outcome indicators, however, are not aligned with the outcome statements. For example, outcome 2 titled “Investments brokered for low carbon energy projects”, whereas the indicator used to measure this “the number of on- and off- grid RE projects brokered”, is not aligned. The indicator 2a should be reported as value of investment brokered supported by Mentari (in GBP) to align with the outcome statement.
Finally, there are also some indicators that are not particularly meaningful, for example intermediate outcome indicator 1a “Number of guidelines accepted by the GoI” does not really demonstrate how Mentari recommendations have been integrated into GoI’s policy. As Mentari’s main objective has evolved into an ICF programme with a focus on the low carbon energy sector and just energy transition, better alignment of Mentari’s programme indicators (outcome and output indicators) with ICF KPIs would support more meaningful results.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Over the past year, activities planned under the programme are on track to contribute to the expected outcomes and impact. Under the policy strand, the Mentari programme has achieved or over-achieved the intermediate outcomes, with the GoI recognising the contribution the programme has made to the development of the local carbon energy sector in Indonesia, including the formulation of various policies, guidelines and recommendations, and supporting the GoI on G20, the Indonesia Just Energy Transition Partnership (JETP) and various high-level dialogues. For instance, the programme team carried out the study on Local Content Requirements as well as RE Quota Pilot Study and submitted it to Perusahaan Listrik Negara (PLN), a state-owned utility company. Based on these study recommendations, PLN has implemented RE Quota by announcing bidding for Java 1 Hydropower. Similarly, the programme team shared the learnings from the demonstration project and built the capability of the Ministry of Energy and Mineral Resources (MEMR) in using KSO model/BUMDes partnership. As a result, MEMR has used the model for special allocation budget concepts. Additionally, the GoI is also seeking to mainstream Gender and Social Inclusion in low carbon energy policies as a result of the programme’s work in this space.
Through the brokerage strand, the programme successfully encouraged local project developers and financiers to invest in low carbon energy projects that have local economic and social benefits. During last year, three partnerships were established, and the projects are currently being implemented on the ground.
Additionally, the demonstration strand was successful in installing two demonstration projects in Mata Redi and Mata Woga, demonstrating viable renewable energy infrastructure models managed by local village enterprise (BUMDes). This model acted as a blueprint for 21 other BUMDes.
Going forward, we recommend that the team re-assess the Theory of change (ToC) and associated milestones given that the programme has been extended both in terms of duration and budget. This is particularly the case given the likely ongoing support the GoI might request from the programme, for example, on the JETP and achieving the GoI’s Net Zero targets. As huge investment will be needed in this sector, Mentari might want to consider scaling up its activities with other investment partners, such as the private sector, bilateral and multilateral development partners and other climate and development finance organisations in order to mobilise more finance for the development of low carbon energy projects in Indonesia.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
The programme should continue as low carbon economic development, renewable energy development and energy transition remains a priority for the UK and is in line with the International Development Strategy. Furthermore, with Indonesia making ambitious commitments on the JETP, Net-zero carbon emissions and coal phase out, this opens more doors for Mentari and BEJ to engage with GoI on these issues. The UK’s support, through the Mentari programme, continues to play a key role in the policy, planning and practice of enhancing low-carbon economic development and reducing greenhouse gas emissions.
The annual review findings show there is a clear and compelling case for Mentari to continue as the Mentari team have been performing outstandingly in delivering its outputs and outcomes. They have developed good and trusted relationships with GoI and other stakeholders. Because of the Mentari programme, BEJ also has a good visibility within the energy sector of Indonesia. Despite a crowded donor environment, GoI considers Mentari as a valuable partner for any support they need related to the energy sector. The Mentari programme has also demonstrated the importance of gender equality and social inclusion in the energy sector of Indonesia.
## C. DETAILED OUTPUT SCORING
POLICY STRAND
Output Title	Policy Strand, Output 1: GoI supported with recommendations/TA on subsidiary regulations & effective implementation of new Perpres
Output number:		1	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 1a: Number of recommendations on subsidiary regulations developed	1	Output substantially exceeded expectations. / 8 policy recommendations developed. / Three RE Quota calculation in NTT for Timor, Flores and Sumba Power systems / Local Content Requirement (LCR) 2.0 / Waste Management Cost / LCOE Hybrid / Hybrid RE Configuration / Hybrid Technology Assessment

Output Title	Policy Strand, Output 2: On-grid policy and regulatory recommendations developed (that mainstream GESI and business case) and presented
Output number:		2	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 2a: Number of on-grid policy and regulatory recommendations developed	1	Output met expectations. / 1 thematic paper New Paradigm: “Renewable Energy New Planning” developed.

Output Title	Policy Strand, Output 4: Preparation / recommendation of a regulatory framework and associated capacity building to implement the agreed business model(s)
Output number:		4	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 4a: Number of detailed off-grid model design developed for agreed model(s) by end of Programme	1	Output met expectations. / In-depth Assessment of Commercial Off-grid Renewable Energy Business Model developed and finalized. This assessment covers 3 off-grid business models: Operational Cooperation (KSO), Micro- Independent Power Producers, and Village-Owned Enterprise partnership.

Output Title	Policy Strand, Output 5: Guidelines, TA, or capacity building on planning, procurement, & contracting provided to PLN
Output number:		5	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Policy Output 5a: Number of new and/or improved guidelines, TA and training identification on PLN planning, procurement, and contracting	0	Output substantially exceeded expectations. / 4 trainings provided for PLN and MEMR staff on DigSILENT Power Factory software, HOMER Pro and Geospatial Least Cost Planning.

Output Title	Policy Strand, Output 6: Support on UK Energy Transition Policy Dialogue provided.
Output number:		6	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Policy Strand, Output 6a: Number of study, activity, and/or capacity building on energy transition provided	0	Output substantially exceeded expectations. / 4 activities carried out to support Indonesia’s energy transition. / Prototype for Indonesia NZE calculator - online excel-based - developed. / study on early retirement of coal power IPPs: International experience and application to Indonesia developed. / Two FGDs with the government and brief policy document on blue energy development produced. / Provided technical advisory to BEJ and supported G20 Energy Transition Working Group.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score of the policy strand’s output is A++. The programme has either met or substantially exceeded expectations of the planned milestones for outputs under this strand. Some of the output milestones in this strand were not challenging last year, so, there is a need to make milestones ambitious for the coming years.
The Mentari team effectively provided technical assistance to the Government of Indonesia (GoI) by conducting various studies, producing several documents and policy recommendations, and building the capacity of MEMR and PLN for reforming policy and regulations that encourage renewable energy development and energy transition in Indonesia.
The Mentari team has been successful in building a strong foundation and presence in Indonesia. They have established good working relationship and trust with GoI, mainly MEMR, PLN, Ministry of Villages, Development of Disadvantaged Regions, and Transmigration (MVDDRT), and other stakeholders at the national and sub-national level as a result of their close work to understand their needs related to the energy sector and collaboration in developing appropriate solutions. The Mentari team also have a deep understanding of the local context in the energy sector resulting in strong and trusted partnerships, and recognition of Mentari and BEJ in the energy sector of the country. One successful example of this is where the Mentari programme was invited to participate in the Policy Working Group of the Indonesia JETP. Other examples include the acceptance of Mentari policy recommendations into relevant guidelines and regulations, such as Renewable Energy Quota Study and the case studies which have provided inputs and a practical methodology in implementing the MEMR Ministerial Regulation no.8/2021 and no.11/2021. As a result of Mentari’s excellent work, other development programmes are seeking to replicate the Mentari model.
Additionally, given that Indonesia has a JETP, with the prospect of larger investments, there will be a huge demand for RE components and systems in the country. Currently, most of the components used in the solar PV energy projects supported by Mentari are imported. There is the potential to develop the domestic manufacturing and supply chain for renewable energy in Indonesia - the programme has worked on a local content requirement study which supports the manufacturing and production of RE components and systems in Indonesia.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The indicator for output 5a has been revised this year from “Number of new and/or improved guidelines, TA or capacity building provided on PLN planning, procurement and contracting” to “Number of new and/or improved guidelines, TA and training identification on PLN planning, procurement and contracting”. The update of this output is to align with the adapted changes in the collaboration, capacity building, and networking (CCBN) strands. The Policy Strand will provide technical context and identify potential capacity building topics which will be delivered through CCBN strand.
In addition, since the original business case, Mentari has added Output 6: “Support on UK Energy Transition Policy Dialogue provided” in the logframe in year 2. This output was added to address the needs of the GoI and BEJ to work on JETP. Last year, the Mentari team did not include any milestones for this indicator. However, they carried out several activities under this output.
Lesson Learned in the past year:
As a result of its good reputation and trusted status, and the programme representing a strong diplomatic tool, Mentari might be exposed to potential scope creep through the team receiving various requests from the GoI and other external stakeholders. The team therefore need to be cautious that these asks are not outside the objectives of the programme. The team might want to consider whether the objectives need to be broadened going forward as part of the extended programme and under a possible Mentari phase 2, including estimates on required resourcing, in order to ensure they can continue to respond to volume of requests for policy support. In the past year we have seen some examples of how staff were stretched in responding to the needs of JETP, G20 and High-Level dialogues.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
More detailed workforce planning for the policy strand, to help anticipate asks and adjust resourcing accordingly	TL, Mentari	PRO	Quarterly reviews
Stronger support from BEJ to deal with ad hoc asks that are not aligned with Mentari objectives	SRO/PRO	TL, Mentari	As required
Explore how Mentari could support the development of domestic manufacturing and supply chain of renewable energy technology	TL, Mentari	PRO	March 2024

BROKERAGE STRAND
Output Title	Brokerage Strand, Output 1: Innovative financing mechanisms/ better de-risking schemes supported (includes enabling access to these facilities) or developed
Output number:		1	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 1a: Number of new and/or existing financial schemes/facilities/mechanisms (i.e., blended finance facility or other de-risking solutions) that are receiving TA support	0	Output moderately exceeded expectations / Supported implementation a Carbon Credit scheme between Climate Partner as the potential buyer for the biomass project in Halmahera by Dewa Agri Coco. In addition, supported in operationalization of the VGF with SMI. The grant agreement signed with three project developers.

Output Title	Brokerage Strand, Output 2: Extension of marketing and DD services for existing public and private investors
Output number:		2	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 2a: Number of marketing and due diligence proposals submitted to financial institutions	2	Output moderately exceeded expectations / Engaged 3 financial institutions a) Climate Capital, b) RMU and c) Climate Partner to finance potential renewable projects.

Output Title	Brokerage Strand, Output 3: Continuous engagement with financiers and developers for matchmaking and improving understanding of regulatory environment and opportunities.
Output number:		3	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 3a: Number of facilitation, meetings, trainings, FGDs, and/or events organised	6	Output met expectations. / 6 events organized for financers, developers and other relevant stakeholders.

Output Title	Brokerage Strand, Output 4: Pipeline of quality low carbon energy projects (in “support mandate”)
Output number:		4	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 4a: Size and value of probability weighted pipeline for on-grid and off-grid clean energy projects (cumulative)	GBP 250m cumulative	Output substantially exceeded expectations. / The pipeline constitutes of 59 potential renewable energy projects with a risk-adjusted CAPEX value of GBP 1,366.69 m.

Output Title	Brokerage Strand, Output 5: Grant or Tailored TA to projects delivered (including projects linked to green bonds)
Output number:		5	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Brokerage Output 5a: Number of low carbon energy projects that received TA, Grant, and/or brokering services	10	Output moderately exceeded expectations / Technical assistance to 11 Renewable Energy Projects including individual projects, GOI/PLN programmes and projects receiving VGF.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the Brokerage strand’s outputs is A+, as the planned milestones have either met, moderately exceeded or substantially exceeded expectations for outputs under this strand.
The Mentari team provided technical assistance to individual project developers, supported the PLN diesel replacement programme and the sustainability bond, supported the Ministry of Village to establish BUMDes (an institution that operates and manages mini-grid systems) and developed the capacity of BUMDes to operate as an inclusive renewable energy business, facilitated matchmaking between project developers and financiers and operationalized VGF scheme to mobilize other funds.
Up to March 2023, Mentari supported 24 projects and 2 national and regional projects initiated by GoI and PLN. Mentari’s technical assistance to renewable energy project developers has increased the bankability of the projects and increased the confidence of the investors. As a result of this, at the impact level, the programme has brokered 25 renewable energy projects in the pipeline at different stages worth GBP 680 million (cumulative). Likewise, the technical support to PLN, MVDDRT, and BUMDes has been quite effective in increasing their confidence in understanding and managing renewable energy projects. Subsequently, PLN is currently designing a programme to replace diesel generators on 129 sites and have established 21 BUMDes which are planning to develop renewable energy businesses.
Mentari was actively engaged with investors and project developers for matchmaking purposes for financing renewable energy projects. They used different types of engagement methods such as investment fora, one-to-one meetings, stakeholder consultations etc. to enable partnership opportunities. Last year, the programme conducted 6 events to bring together investors and project developers. As a result of these events, it was successful in matching 3 project developers and 3 investors.
Early evidence suggests that the VGF has enabled PT SMI to invest in less bankable projects that have economic and social impacts, which would otherwise not be commercially viable. There is a great quantity of RE projects in Indonesia which require this type of funding and PT SMI is very welcoming of the scheme because of the additional confidence in the viability of the project resulting from the VGF, and therefore the return on investment is more attractive and less risky.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Mentari has revised output 5 from “Tailored TA to projects delivered (including projects linked to green bonds” to “Grant or Tailored TA to projects delivered (including projects linked to green bonds”. This was updated to assess the low carbon energy projects that received grants from the programme.
Mentari TA is currently mobilizing both private investment and public investment but there is no disaggregated data showing how much private vs public investment has been mobilised. Disaggregating the data will be helpful in understanding where Mentari efforts are being focussed. In addition, the Mentari team will have to classify whether investment into State Owned Enterprises (SOE) are public or private investments.
Lesson Learned in the past year:
A thorough evaluation of the VGF scheme is required to determine the impact it has had; and what the options might be in order to scale any potential future scheme, including bringing onboard other potential partners. BEJ has begun scoping this evaluation, but we recommend an early action is to update the current VGF guideline to enable funds to be disbursed to publicly owned project developers, which is not currently in the guidelines. The reason for this as currently Mentari is providing VGF to hydropower projects developed by subsidiaries of PT Brantas Abipraya which is 100% owned by the GoI.
Some further consideration on what type of project qualifies in terms of size and value is also recommended. In the investment grant agreement between PT SMI and Palladium, Article 9 Terms of Disbursement states at (1)g that the amount of the percentage of the investment grant can fund (i) up to 20% of the total CAPEX or up to GBP 750,000 of the total project value or (ii) up to 30% or up to GBP 750,000 for special cases such as small projects or projects with innovative elements in accordance with the mutual agreement of the parties and the agreement of the FCDO. However, there appears to be a different understanding on the definition of small projects and the maximum VGF amount that can be provided between the Mentari Team, BEJ programme team and PT SMI. Additionally, the number of renewable energy projects in PT SMI pipeline that has met these criteria is found to be limited.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Update the VGF guidelines to reflect that publicly owned entities can qualify for VGF funding. Also specify clearly what type of project qualifies in terms of size and value to have common understanding.	SRO/PRO	TL, Mentari	By August 2023
Undertake and finalize the VGF evaluation to identify scalable and sustainable models for operating VGF.	SRO/PRO	TL, Brokerage team Mentari	By March 2024

DEMONSTRATION PROJECT STRAND
Output Title	Demonstration Project Strand, Output 2: Off-grid low carbon energy demonstration project implemented with viable project structure and governance
Output number:		2	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output indicator 2a: Number of small-scale off-grid low carbon energy facilities established and operational	2	Output met expectations. / 2 small-scale off-grid solar PV project installed and are in operational in Mata Redi and Mata Woga.
Demonstration Project Output indicator 2b: Number of commissioning report and O&M contracts drawn for demonstration project	1	Output moderately exceeded expectations / 3 commissioning report and O&M contracts developed for demonstration projects.

Output Title	Demonstration Project Strand, Output 3: Inclusive off-grid development models (including training on low carbon energy business models, O&M, PuE, and GESI potential) provided to the community, TVET providers, local FIs, local government, BUMDes, BLU and O&M providers
Output number:		3	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output 3a. Number of trainings on low carbon energy business models (technical and non-technical)	2	Output substantially exceeded expectations. / 26 technical and non-technical training activities to support and ensure the sustainable operation and management of the Demonstration project and economic development of community.

Output Title	Demonstration Project Strand, Output 4: Knowledge about applying small-scale renewable energy for electrifying off-grid produced
Output number:		4	Output Score:	A+

Indicator(s)	Milestone(s) for this review	Progress
Demonstration Project Output 4a. Number of knowledge products about small-scale off-grid produced	2	Output moderately exceeded expectations / 4 knowledge products developed about small-scale off-grid.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the Demonstration strand’s outputs is A+, as the planned milestones have either met, moderately exceeded, or substantially exceeded expectations for outputs under this strand.
From a technical perspective, Mentari appropriately designed the relevant systems and installed quality components to a high specification. This means the sites are of a robust quality and fit for purpose in a rural context. As a result, the Team has succeeded in demonstrating that decentralised solar PV mini-grid systems for rural electrification can be extremely effective.
Additionally, the team worked well with the local community to get their support for the building of the two mini-grid systems and continued to work with them to a) help them understand how electrification would benefit them; b) make the system sustainable in the long term through the setting up of a BUMDes; and c) operating and maintaining the systems through training and developing qualified human resources including a service contract with TML Energy.
The team also consulted widely with local stakeholders and central government on how best to embed such mini-grid systems and the operational model within the rural community. This was evident from their support and buy in.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The programme has added three additional outputs and their respective indicators since last year. These outputs are output 5 “Advocate to GoI and other stakeholders (incl. project developers, PLN) in replicating the good governance and inclusive social economic ecosystem”, output 6 “Setting-up the transitioning process for sustainable mini-grid system in the community and BUMDes and output 7 “Providing technical assistance and capacity building to other potential BUMDes and village government to upscale the knowledge from the Demonstration Project”. These outputs measure interventions made by the Mentari team to replicate and scale up the learning from the demonstration projects. The addition of these outputs is relevant to the programme.
The programme has also added output indicator 2b “Number of commissioning reports and O&M contracts drawn for demonstration projects” under output 2 to measure the agreements made by the programme for demonstration projects. In addition, there are also minor refinements in some output statements to make them clearer and to capture the support provided to broader stakeholders.
Lesson Learned in the past year:
The Team has delivered training on productive use of energy (e.g., candlenut oil production, citronella oil production, ginger and lemon grass cultivation etc). Whilst community members have participated in the training, there was limited evidence that they are getting involved in this productive use of renewable energy and generating income and wider economic benefits for the community. One main reason for this case might be the tariff. The basic electricity tariff of IDR90,000 for household use (450 Wh) was difficult for most households to pay. This meant that those community members who were thinking of investing in equipment (refrigeration; wood working) for business use could not really afford to do so because that would mean upgrading to a higher capacity, which they could not afford.
The team has also supported the establishment of a BUMDes, through capacity building measures and relevant training. However, there are some challenges in relation to:
1. Governance/oversight and accountability: the composition of the BUMDes is made up of a few related members which might lead to potential conflict with other members in the future. Lack of governance means there is no oversight regarding potential misuse or inaccurate recording of the fees.
2. Remuneration: Some functions are underway e.g., collection and recording of the fees, but no members are currently being paid for their work in BUMDes. This is a potential disincentive which might impact members’ motivation to continue working for the BUMDes. There were also instances where BUMDes members were giving their time to support site related activities but were not being compensated or reimbursed for their time doing this, which had caused tension between them and their families.
3. Sustainability of the model: BUMDes members were not presently active in promoting the productive use of energy. They therefore need continued support to help the community make the most of the electricity being provided for economic benefit.
There is a plan to transfer the sites from private ownership and make them village assets. However, the timeframes for doing so were not clear, leaving a potential risk open. The transfer should happen quickly to avoid potential conflicts.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Evaluate and address reasons why community has not pursued the productive use of energy.	Demo Lead	TL, Mentari, PRO	December 2023
Evaluate tariff structure to make it more affordable for domestic and productive use of energy.	Demo Lead	TL, Mentari, PRO	December 2023
BUMDes should hire one paid dedicated Project Manager accountable for the management of the solar PV system and provide governance and audit function and promote productive energy use in the village.	Demo Lead	TL, Mentari, PRO	March 2024
Clarify BUMDes pay structure and terms and conditions and communicate to them	Demo Lead	TL, Mentari, PRO	September 2023
Prioritize facilitation of land transfer from private ownership to village government ownership	Demo Lead	TL, Mentari, PRO	As early as possible

COLLABORATION & NETWORKING STRAND (Now COLLABORATION, CAPACITY BUILDING & NETWORKING STRAND (CCBN))
Output Title	Collaboration & Networking Strand, Output 1: Capacity building and knowledge exchange, including focus on opportunities for women and marginalised groups, provided to inter/national academic/TVET, and relevant stakeholders (incl. MEMR, PPSDM, PLN) in low carbon energy sector
Output number:		1	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Collaboration & Networking Output 1a: Number of International and Indonesian academic or training institutions, and relevant stakeholders (incl. MEMR, PPSDM, PLN) receiving programme matchmaking and/or knowledge sharing support	2	Output substantially exceeded expectations. / Supported 16 international and Indonesian academic institutions, training institutions and relevant stakeholders through matchmaking, capacity building and collaboration activities. These include MEMR, PLN, BPSDM, TVET, NTB, universities etc.
Collaboration & Networking Output 1b: Number of activities organised by MENTARI for supporting Inter/national academic, TVET, and relevant stakeholders (incl. MEMR, PPSDM, PLN) focusing on low carbon energy in Indonesia	1	Output substantially exceeded expectations. / 5 activities organized by Mentari to support international or national academic, TVET and relevant stakeholders in low carbon energy development in Indonesia.

Output Title	Collaboration & Networking Strand, Output 2: Branding & communication products produced to share knowledge and lessons
Output number:		2	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
Collaboration & Networking Output 2a: Number of communication and knowledge products produced and disseminated	1	Output substantially exceeded expectations. / 10 communication products and 20 policy reports and papers produced and disseminated by Mentari to key stakeholders and/or the public.

Output Title	CCBN Strand, Output 3: Promoted knowledge sharing and facilitated partnerships
Output number:		3	Output Score:	A++

Indicator(s)	Milestone(s) for this review	Progress
CCBN Output 3b: Number of events (consultation, facilitation, FGD, workshop) to facilitate knowledge sharing and partnership development	10	Output substantially exceeded expectations. / 29 events organized by Mentari to facilitate knowledge sharing and partnership development.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score of the policy strand’s output is A++. The programme has substantially exceeded expectations of all planned milestones for outputs under this strand. The output milestones in this strand were not challenging last year, so, there is a need to make milestones ambitious for the coming years.
This strand has hugely evolved over the course of the programme and the programme now has mature relationships with the GoI and other relevant stakeholders in the Indonesian energy sector. This has enabled the team to now also focus on capacity building which is reflected in the new name of the programme strand.
The CCBN strand has also effectively collaborated across other programme strands, as well as with external stakeholders, including government, academic institutions, project developers, and other development partners. The programme has managed to deliver 29 events facilitating knowledge sharing and partnership development, which include technical working groups, Focus Group Discussions, training, knowledge sharing workshops and various meetings. In addition to this, the programme has also produced and disseminated 10 communication and knowledge products. This has resulted in the establishment of 2 new partnerships to support human resource development in the Indonesia low carbon energy sector. One partnership, with SMA Solar Technology, delivered capacity building on off-grid operating patterns and end-to-end inverters for PLN Papua and Papua Barat. This training has improved the knowledge of PLN staff. Another partnership was with University College London to collaborate with the Demonstration Project Team to conduct a Feasibility Study Benchmarking and Joint Research Programme enabling knowledge exchange between the team and students.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There is no additional output in this strand since last year. There is only minor refinement in output 1 to capture the capacity building, knowledge exchange support provided by Mentari to relevant stakeholders including MEMR, BPSDM and PLN.
Lesson Learned in the past year:
Whilst the CCBN strand has proactively responded to requests coming from various stakeholders and been effective in gaining trust from GoI, this has also brought risks in managing the programme resources and budget to fulfil demand from different partners.
There was good communication at workstream level with relevant line ministries. However, there was some evidence that certain ministries were unaware of activity in workstreams where they were not specifically involved in, but that might have been relevant or of interest to them.
CCBN strand has managed to secure positive engagement with BPSDM which is critical in strategically leveraging CCBN’s function in delivering Mentari’s capacity-building and knowledge exchange with MEMR. However, the process took almost one and a half years due to bureaucratic communication channels. At the end of March, it was agreed to create a separate Technical Working Group with BPSDM as a new member of the Steering Committee.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Strategically manage capacity building requests from different stakeholders	TL Mentari/PRO	Delivery Partners	When required
Leverage stakeholder relationships to deliver outputs that could free up Mentari resources to focus on other priorities	TL Mentari/PRO	SRO	When required
Evaluate the resource level to support the evolving and increasing work of CCBN strand	SRO	PRO	August 2023
Develop broader comms strategy to inform all relevant ministries about programme activities.	TL Mentari	PRO	September 2023

GENDER AND INCLUSION
Output Title	Gender and Inclusion, Output 1: Programme demonstrates G&I integration across (i) MENTARI programme intervention design (internal), (ii) support to relevant stakeholders (internal/external), and (iii) knowledge sharing (internal/external).
Output number:		1	Output Score:	A

Indicator(s)	Milestone(s) for this review	Progress
Gender and Inclusion Output 1a: Percentage of women and/or marginalised groups involved in facilitated discussions	30%	Output moderately exceeded expectations / 43% women participated in the events organized by the programme.
Gender and Inclusion Output 1b: Number of most significant stories, focused on livelihood, gender and inclusion, and secondary benefit, developed to illustrate project contribution to socio-economic, education, empowerment, environmental conservation benefits in the area of demonstration project and other relevant strands within MENTARI.	1	Output met expectations. / 1 Gender and Inclusion case study: "Mainstreaming Gender and Inclusion for Renewable Energy Projects" was developed.
Gender and Inclusion Output 1c: Number of G&I learning events organised that will focus on programme stakeholders (e.g., policymakers, financiers, private developers, etc.)	2	Output met expectations. / 2 learning events were organized to mainstream Gender and Inclusion in the low carbon energy sector.
Gender and Inclusion Output 1d: Number of G&I TA support provided to programme stakeholders (internal/external)	8	Output substantially exceeded expectations. / 24 different types of Gender and Inclusion TA support was provided to programme stakeholders

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the Gender and Inclusion (G&I) strand’s outputs is A, as the planned milestones have either met, moderately exceeded or substantially exceeded expectations for outputs under this strand.
The Mentari team successfully integrated the G&I considerations into many of their activities under all strands. They organized different types of interventions for building the capacity of the government and project developers to mainstream G&I in planning and implementation of the energy projects. This positively influenced the MEMR to consider developing a Gender and Inclusion policy for the energy sector of Indonesia. Furthermore, the MEMR and the Ministry of Women Empowerment and Child Protection (MWECP) recognise the need to work together with the Mentari programme on these issues.
The G&I strand has also benefitted from the growing interest in G&I in Indonesia’s energy sector which has resulted in positive responses coming from both GoI and private sectors (ie Project developers). The Mentari team should continue to work on G&I mainstreaming in the Indonesian energy sector by adding additional outputs and outcomes in their future work.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Mentari has revised the G&I output statement to “Programme demonstrates G&I integration across (i) MENTARI programme intervention design (internal), (ii) support to relevant stakeholders (internal/external), and (iii) knowledge sharing (internal/external)” from “Programme supports demand and supply actors in mainstreaming GESI, Environmental and inclusive growth in the design, financing and implementation of on and off grid low carbon energy projects” in year 2. In addition, they have added indicator 1d “Number of G&I TA support provided to programme stakeholders (internal/external)” and revised indicator 1a to account for marginalized groups involved in the events organized by the programme. Mentari also removed the environment from the statement and there is no specific indicator that measures the environmental aspects of the programme.
Mentari’s work is primarily focussed in supporting low-carbon economic development in Indonesia and moving forward Mentari will also be increasing their support towards energy transition in Indonesia. However, currently there is no outcome indicators to capture the amount of CO2 emissions reduced by the renewable energy projects supported by Mentari which is highly relevant. Therefore, there is the need to include one indicator to measure this which would suggest the adding “Environment” back to the cross-cutting output name and statement. The programme team will need to consider this when they plan to revise their ToC and logframe.
In addition, output statement of G&I is not included in the ToC and does not show any link of this output to outcome and impact statements. It is recommended that a G&I output statement is included in the ToC.
Lesson Learned in the past year:
There is a lack of proper disaggregated data to understand the potential impact some of G&I initiatives have delivered through the Brokerage strand.
Although, G&I training was also provided to the project developers under the Brokerage strand, there are still challenges around finding women-led and disadvantaged group led renewable energy projects or initiatives. In the future, the team could make more effort on current activities or design some activities to focus on outreaching and matchmaking to women-led and disadvantaged group-led projects/initiatives and to female and disadvantaged group financiers to bring them into the low carbon energy sector.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Better, disaggregated data in brokerage and policy strands, where possible/appropriate	TL, Mentari	PRO	September 2023
Specific intervention targeted at women and disadvantaged groups to bring them into the low carbon energy supply value chain when providing TA via brokerage strand.	TL, Mentari	SRO/PRO	During brokerage events
Add “Environment” back into the output statement and name, and include an indicator to capture CO2 emission reduction by the renewable energy projects supported by Mentari	SRP/PRO	TL, Mentari	During revision of Logframe

## D. VALUE FOR MONEY
VfM assessment compared to the proposition in the business case.
Economy: The programme has been extremely effective, given the relatively modest budget, and has been effective in sourcing additional resources for bespoke pieces of work (e.g. collaborating with Ricardo Energy under the UK PACT skills share Programme to deliver Indonesia’s Hydrogen strategy). However, as the programme is adaptive where it responds to the multiple requests by GoI and other stakeholders, programme staff have been stretched in some instances. Additionally, it takes a disproportionate amount of time for the Delivery Partner to sub-contract for short term assignments, which do not always result in quality deliverables. They therefore consider the Short-Term Technical Assistance (STTA) resource to be better value for money than sub-contracting, and an increase to the daily rate caps for STTAs could be considered, to test whether any legacy Prosperity Fund guidance is still fit for purpose, and to support even better-quality resource.
Efficiency: With the available resources, the programme has been successful in carrying out almost all activities listed in the workplan and has mostly exceeded all output milestones. This was achieved within budget coming in just under 0.03% variance. The programme is also prioritising using local human resources, where applicable, which is more cost effective than using international equivalents. The use of STTAs for short term assignments over using full time employees also enable cost savings. Additionally, with up to 20% of the VGF, the programme was able to mobilise more than four times the value of equity and debt raised by project developers and PT SMI.
Effectiveness: The programme has been effective in influencing the GoI to bring enabling policies in low carbon energy sector both in on and off grid sectors. Through the demonstration project, the programme also successfully demonstrated to local government and communities that decentralised solar PV systems can be suitable options for off grid rural electrification, and that the BUMDes business model can manage and operate such systems. The GoI has already started to replicate this business model. Additionally, the programme effectively encouraged project developers and financiers to invest in renewable energy projects through the provision of TA only – this represents excellent value for money.
As a result of the programme’s trusted reputation, the BEJ has been able to use this as a diplomatic tool, including enabling access to other policy areas. For example, the UK (via Mentari) is one of only two bilateral partners sitting on the JETP policy working group.
Equity: The programme has considered G&I throughout the workstreams and have measured percentage of women and marginalised groups taking part in training, facilitated discussions and programme activities. This has been complemented by showcasing examples of female and people from rural and disadvantaged groups participating in the Renewable Energy sector, as part of Leave No One Behind. They have also worked with and encouraged the GoI to mainstream G&I policies in the sector.
There is, however, limited disaggregated data to measure female participation in some of the workstreams, particularly the Brokerage strand activities, where numbers of female project developers or financiers are not collected. More support could also be provided to enable female participation to have a voice in decision making process in the rural communities' context.
Explain whether it makes sense to continue with the programme from a VfM perspective.
The programme should continue as it is performing outstandingly well across multiple strands, captured through the four workstreams, with a relatively modest budget. Not only is this reflected in the reputation the programme has with GoI and other key stakeholders, but also from feedback from RE developers. However, going forward, the team should re-assess the ToC and associated milestones given that the programme has now been extended both in terms of duration and budget. The programme should continue to seek ways to deliver VfM through working with other development partners, government organisations and relevant agencies including through mobilising their funds, where relevant.
## E: RISK
Overview of risk management
The Mentari programme has 32 active risks in its risk register and all the risks are within the overall risk appetite for BEJ. The residual risk rating of these risks is related to either major (2), moderate (18) or minor (12) risk categories.

Active programme risks in the BEJ’s risk register

Mentari is currently not recorded in the Aid Management Platform (AMP) as BEJ programme team do not have Osprey devices which are required to access AMP. At this stage, the programme team is maintaining an offline document for the programme risk register.
The Strategy and Context related risks include lack of political commitment to reform, poor capacity, and frequent change in key personnel in GOI, lack of conducive policy frameworks, overlap or conflicting UK priorities and programmes, and prioritization on COVID 19 recovery diverting focus on low carbon economic growth. It is also recommended that the Mentari programme team consider a new risk around UK changing domestic energy policy relating to climate change. To mitigate these risks, the Mentari team and BEJ team are closely collaborating with representatives from national and local governments to build trusted relationships through technical assistance that is tailored to their requests. The programme has been flexible and adaptable whenever possible to address the needs of the energy sector of Indonesia. Further, the programme has aligned with political implementation opportunities brought about through the multilateral Indonesia Just Energy Transition Partnership. The programme has also engaged with other UK programmes and other energy programmes supported by bilateral and multilaterals to create synergies and add value as well as to avoid duplication.
The Policy and Programme delivery risks include uncertainty in the ODA budget allocation for the programme and programme extension, weak programme management and MREL systems, the change in the ways of working due to the merger of FCO and DfID, the delay in implementation and disbursement of the VGF and the difficulty accessing and leveraging investment from the private sector in the renewable energy sector. To address these risks, the programme team is closely working with the BEJ team by organizing fortnightly meetings and ad hoc meetings when required to plan the activities, forecast appropriately and implement them effectively.  However, there is a need to further improve the programme management to handle the rapidly changing context.
The Reputational risks to Mentari include mismanagement of funds, safeguarding risks mainly at community level, conflicting UK interests e.g., promoting trade at the expense of climate change. To mitigate these risks, the programme has applied rigorous due diligence checks of implementers and partners, rigorous financial control, and oversight mechanisms.
The Financial and Fiduciary risk to Mentari includes fraud, corruption, and mismanagement of funds by delivery partners, which is mitigated by putting rigorous due diligence checks. Another financial and fiduciary risk is the limited appetite of PT SMI to mobilize VGF, which might not utilize the allocated VGF amount by BEJ. To mitigate this risk, the programme team is closely working with the PT SMI team to develop the suitable project pipelines for the VGF.
The Safeguarding risk for the Mentari programme is related to the risk of vulnerable people, including children and women being exploited in return for Mentari - related activities and projects. Another risk is that programme interventions fail to deliver benefits for women and disadvantaged people. To mitigate this risk, the programme team has ensured a good safeguarding procedure in place, G&I mainstreaming throughout its programme from design, delivery and evaluation.
The People risk to Mentari includes lack of sufficient and qualified staff both at BEJ and delivery partners to effectively implement the programme as well as to address the frequent requests from the GOI and other stakeholders. To mitigate this risk, more detailed workforce planning is required.
Mentari’s risks are discussed in the biweekly meetings between the BEJ team and the programme delivery team. In addition to this, the delivery team submits programme risks in the quarterly progress reports. If there are certain high-level risks arising which requires BEJ’s immediate attention and oversight, the delivery team will put these in writing to the BEJ programme team.
Although there is good understanding of the risks between the delivery partner and BEJ, it was unclear whether both parties understood each other’s risk appetite and shared the same view on the risk assessment process, that is, on impact, likelihood, and rating of risks. While this is fine when things run smoothly, if a risk gets worse, this might impact whether such an instance would be recognised in time by both parties and managed accordingly.

Recommendations for the year ahead:
BEJ programme team maintains a good practice to review and update the risk register on a quarterly basis which should be continued. It is recommended that the team look at and review any risks that are no longer relevant and can be closed. Once the BEJ programme team has access to AMP, they will be required to upload the programme risks into AMP and continue to review and update directly in AMP.
## F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Reporting Performance
Good programme governance is in place whereby Mentari holds workshops with all counterparts (including GoI) to work towards the annual workplan. The final workplan is reviewed by GoI and signed off by the Minister (in Indonesia) and this occurs annually. The programme also holds quarterly working group meetings to discuss any workplan changes with relevant stakeholders. The BEJ programme team also holds biweekly meetings with delivery partners to discuss programme progress, issues and any emerging programme risks. The delivery partner provides monthly forecasts to the BEJ programme team and submits quarterly reports, however there was evidence of where the delivery partner submitted these deliverables beyond the agreed date.
Mentari has adopted an adaptive programming approach which enables the programme to respond and flex swiftly to deliver requests made by GoI and other stakeholders. This has resulted in the excellent reputation Mentari has with its stakeholders. Mentari’s delivery partner, Palladium and its consortium partners, play a key role in the programme’s successful delivery. This adaptability, however, also posed some programme management challenges, and these are:
- The current logframe milestones have not been maintained to reflect the workplan activities as well as the incoming activity requests that Mentari received. As a result, Mentari have exceeded almost all output milestones set out in the logframe that was originally developed based on the initial budget which are not particularly stretching.
- Mentari delivery partner submitted 3 quarterly reports over the past year, however they had difficulty in submitting the annual progress report on time to support the annual review process.
- The quality of programme reports can also be improved. There have been inconsistencies between results reported in the delivery partner’s Quarterly Report and the logframe.
- The adaptability of the Mentari programme also posed complexity to monthly forecasting as the programme had to continuously flex their budget to respond to additional activities requested by stakeholders.
In addition, challenges observed specifically in the programme management are:
- The programme’s annual workplan does not include a complete picture of Palladium’s resource cost and does not maintain an Activity Based Budget. Taken together these two issues make it difficult to assess the spending incurred for each activity and strand and measure VfM.
- Mentari’s delivery partner also struggled to submit monthly invoices on time and submitted several invoices altogether (late) which makes it challenging to reconcile between forecasted expenditure and actual spend.
Financial Management
Budget confirmation only came in well into the financial year, and the Mentari programme received a programme allocation from BEJ ODA portfolio allocation of £4,450,000, broken down to 53% Resource Departmental Expenditure Limit (RDEL) and 47% Capital Departmental Expenditure Limit (CDEL). Within this initial allocation, the Mentari delivery partner submitted an initial budget and forecast for the year of £4,507,452 including a portion of overprogramming. However, as central FCDO guidance enforced an ODA spending pause in summer 2022, followed by an ODA budget reduction in December 2022, the programme allocation was brought down to £3,853,568. Further, towards the end of the FY, looking at their level of activity and forecast, Mentari returned a proportion of their programme allocation to the central finance team which reduced their allocation to £3,553,568 with final RDEL proportion of £2,146,141 and CDEL of £1,407,427.
Out of the revised budget, the programme spent 99.7% of the budget allocated. In addition to that, BEJ programme team also spent some of the budget for legal consultations and programme visits. While this represents good programme spend, there were some challenges understanding the CDEL guidance, which meant Mentari were unable to spend their CDEL allocation last year.
Strand wise spent:
Strand	% of Budget Allocated for Each Strand	% of Actual Spend for Each Strand
Policy	27%	29%
Brokerage	26%	24%
Demonstration	26%	27%
CCBN	21%	21%
Overall	100%	100%

Commercial Performance
Formal agreement with the delivery partner is through a commercial contract with Palladium International Ltd. Since the initial contract signing in December 2019, the contract has gone through 3 contract variations to capture the changes in key personnel as well as scope of the programme. Valued at £8,057,002, this is a silver contract with 3 KPIs for which the PRO is responsible for the reporting the contract’s performance in each quarter as part of cross-HMG contract transparency requirements. In the last KPI reporting, the contract was rated as good or on track.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Better project management discipline, including updating workplans and milestones, and ensuring data consistency recorded across various documents.	TL, Mentari	PRO	Quarterly
Work with MEL adviser to review programmes ToC, logframe as well as milestones towards establishing more ambitious milestones that are reflective of the agreed budget as well as to align with ICF KPIs to establish more meaningful measurements and results. This is in attempt to fit with an ‘adaptive’ programming model as well as the low-carbon energy objective of Mentari programme.	PRO, SRO	TL, Mentari, MEL Adviser	September 2023
Delivery partner to more formally record programme risks and submit to BEJ, at least quarterly.	TL, Mentari	PRO	Quarterly
Engage with Central Finance Team early to get a clear guidance on CDEL spending and work with Delivery Partner towards achieving agreed CDEL budget amount. This will then need to be reflected through their purchase order and forecast.	PRO	SRO, Mentari	ASAP

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The addition of Section G to the Annual Review template took place after this review was commissioned and therefore this section has not been drafted by the Annual Review team responsible for the rest of the report above. Instead, the below (Section G: Monitoring, Evidence and Learning) has been prepared by Mentari programme management staff in the Low Carbon Energy and Infrastructure team, British Embassy Jakarta.

Monitoring and Evaluation

The British Embassy programme team and programme delivery partners have regular meetings related to programme management, monitoring and reporting: (1) bi-weekly meetings between the management team from delivery partners and embassy programme team to discuss programme and contract operations and administrative matters, risk and programme progress; (2) bi-weekly / weekly meeting between strand leads from delivery partners and embassy programme team to talk about strand-specific progress, risks and opportunities; (3) monthly meeting between MREL Manager from delivery partners and MREL officer from embassy programme team to talk about MREL process, progress, and compliance; (4) quarterly steering group meeting between delivery partners and programme team to see the overall programme progress and challenges over the previous quarter as well as looking forward to the upcoming quarters. These quarterly meetings will evolve to focus more on deep dives on more strategic issues in future.

Delivery partners maintained a permanent, full-time MREL manager position during the review period. The delivery partner also has access to an MREL short-term technical advisor (STTA) who is experienced in working with FCDO programmes. The MREL Manager and STTA have given valuable inputs over the programmes implementation. The last in-depth review of the programme logframe was done in February – March 2023.

The embassy programme team also visited brokerage and demonstration pilot project sites several times during the review period to see first-hand the implementation on the ground and cross-reference this with progress reports provided by delivery partners. During the visits, the programme team met with relevant stakeholders and beneficiaries to listen to feedback and comments on the project.

During the annual review process, the reviewer team had the opportunity to interview the programme team, delivery partners, beneficiaries and stakeholders of the programme, as well as a field visit to the demonstration pilot project site. A fuller methodology for the Annual Review is described in Section A of this report.

Evidence
As an adaptive programme, the programme team and delivery partners maintain regular communication to assess any changes in the context for the programme, and risks and opportunities, developing and discussing evidence to inform judgements about the ongoing activities and priorities for the work plan. As per the contract, the delivery partner is also obligated to continue to review ways to improve the delivery of services to better meet the overall objectives of the programme.
Learning
Refer to section “Major lessons and recommendations for the year ahead” on page three of this report.

Date of last narrative financial report	The delivery partner provides monthly financial reports and invoices, including an explanatory note on spending.	Date of last audited annual statement	29 March 2023