## Annual Review Template

Title: MENTARI* UK-Indonesia Low Carbon Energy Partnership (referred to in pre-delivery as Indonesia Renewable Energy Programme (IREP)
Programme Value £ (full life): Up to £20,000,000. Programme was initially £13.5m but a time and cost extension was approved in mid-2023.		Review date: June 2024
Programme Code: AMP ID 400399	AMP start date: [Not on AMP but programme started on 6 January 2020]	AMP end date: 30 April 2026

Summary of Programme Performance
Year	December 2019 (Light Touch)	Jan 2020 – April 2021	April 2021– March 2022	April 2022 – March 2023	April 2023 – May 2024
Overall Output Score	A	A	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	[to be filled once on AMP]
DevTracker Link to results framework:	[to be filled once on AMP]

## A: SUMMARY AND OVERVIEW

Description of programme
The Mentari (formerly Indonesia Renewable Energy) programme is a £20m programme that aims to support inclusive economic growth and poverty reduction through accelerating and expanding low carbon energy in Indonesia, while mainstreaming Gender and Inclusion in its delivery. The programme started in January 2020 and was originally planned to end in December 2023. The business case addendum for a programme cost and time extension to April 2026 with a total budget of £20 million was approved in June 2023.
The Mentari programme is working closely with the Government of Indonesia (GoI), and other stakeholders, to promote a conducive investment environment in the renewable energy sector of Indonesia. The programme has the following four strands, where gender and inclusion are mainstreamed in every workstream of the programme.
1. Policy Strand aims to reform national and regional renewable energy policies, regulations, guidelines, and financial instruments that bring about a more conducive business environment in the low carbon energy sector.
2. Brokerage Strand aims to increase investment in low carbon energy projects by bridging the gap between potential financiers and viable project developers through brokerage, technical assistance and providing small amounts of catalytic Viability Gap Funding (VGF).
3. Demonstration Project Strand aims to demonstrate viable and replicable off-grid low carbon energy systems that will bring socio-economic benefits including for women and marginalized groups.
4. Collaboration, Capacity Building & Networking Strand (CCBN) supports collaboration, networking, and capacity building of relevant stakeholders in the low carbon energy sector including policy makers, investors, project developers, communities, and academia.
The programme was originally a legacy cross-government Prosperity Fund Programme which now has been transferred to the bilateral Indonesia country plan budget, with the oversight of the Indonesia and ASEAN Development Director. The programme is primarily delivered via a commercial contract delivered by a consortium led by Palladium International with Castlerock, ECA, and Hivos.
Mentari has an adaptive programming approach to respond to the dynamic changes resulting from Indonesia’s ambition towards a Net Zero emissions economy and to support the Just Energy Transition Partnership (JETP).
Summary supporting narrative for the overall score in this review
This Annual Review was carried out from 17 June to 5 July 2024 covering the programme from April 2023 to May 2024. The Annual review team of three officers comprised of staff from British High Commission Singapore and British Embassy Jakarta. The team conducted meetings with several stakeholders of the programme including the British Embassy Jakarta (BEJ) implementing team, delivery partners, government officials relevant to the programme, PT Sarana Multi Infrastruktur (PT SMI), PT Brantas, and Dewacoco. Based on the observation and feedback from stakeholders, the team has prepared this report.
The overall score for the Mentari programme for this year is A+.
Some of the achievements supporting the overall score in this review include:
- The programme has either met, moderately exceeded, or substantially exceeded expectations of the planned milestones for all outputs.
- The Government of Indonesia (GoI) welcomes the support the Policy Strand has provided them. GoI notes the programme’s flexibility to support their requests as a particular advantage compared to other international donors. Mentari’s support to the GoI’s development for a national hydrogen strategy was particularly welcomed.
- The programme supported the JETP’s Comprehensive Investment and Policy Plan (CIPP) by conducting studies that developed the section on Local Content Requirement (LCR).
- The projects supported by the £2.7m Viability Gap Fund (VGF) during this period have made substantial progress, with some due to be operational in late 2024. PT SMI feedback indicates no other international donor provides a similar facility that can help make small renewable energy projects become bankable. The fund has helped BEJ develop a strong relationship with PT SMI, a prominent infrastructure financer in Indonesia.
- The Demonstration strand’s rural electrification project in Sumba continues to be a model showcasing just energy transition. Its success has led to the regional government request Mentari’s support to help them plan for similar projects in 20+ other locations and include a gender and inclusion element in their development.
- Visits by a UK minister to VGF-supported projects and His Majesty’s Ambassador’s (HMA) visit to the demonstration project would have contributed to the UK’s domestic visibility as a credible partner on energy transition.
Progress on recommendations from the previous AR
There were 26 recommendations in last year’s annual review and 23 have been completed.
The key recommendations that have been actioned relate to managing requests for support, VGF disbursal timing, workforce planning, and the usage of energy from the demonstration project. Focusing on the first point, as the delivery partner and BEJ programme team have agreed a workplan till the remainder of the programme, this will address this issue.
The outstanding three relate to further clarifying guidelines for the VGF and refreshing programme management documents. The experience of delivering the VGF in 2023 should help refine and codify the selection criteria. An evaluation of the Brokerage strand and its VGF were about to commence during the writing of this review. Given all the Output targets were set based on the programme originally ending in December 2023, a refresh with more ambitious targets and reflecting the new end date would help maintain stretching Outputs for the delivery partner.

Major lessons and recommendations for the year ahead
The major lessons learned, and recommendations are:
- The Impact level outcomes have been achieved, though attribution to the programme’s support is difficult. Since the programme started in 2020, there are now an additional 8,780,779 households in Indonesia with access to low carbon energy (targeted 844,000 by the end of the programme) and an additional 2.93 GW of renewable energy capacity (targeted 1.6 GW by the end of the programme).Very positive progress, but difficult to attribute the programme’s contribution towards this given its focus on policy reform, several international donors operating in the same sector, and Indonesia’s own energy transition efforts. Recommend identifying a methodology to identify how all the strand’s activities contribute to the impact – particularly from the policy strand.
- The programme has performed well against the Outcome level indicators to date. There was positive progress towards the improving regulations and guidelines for the low carbon energy sector through supporting the Ministry of Energy and Mineral Resources (MEMR) develop its National Hydrogen Strategy and update the Local Content Requirement (LCR) regulation for solar projects. The demonstration project in Eastern Indonesia continues to provide socio-economic benefits for women and marginalised groups. Previous targets to support small businesses, particularly women-led businesses have been met, and this year saw the creation of six types of jobs. Various parts of GoI have visited the site, influencing views on how to mainstream the approach on rural electrification and just energy transition. The outcome on brokerage investments for low carbon energy projects was met in the previous year.
- The Indonesian renewable energy sector continues to evolve. GoI requests for technical assistance to develop or refine policies and regulation for the low carbon energy sector are expected to continue. GoI will likely look to this programme for support given their acknowledgement of its flexibility. However, as the remaining programme workplan almost reaches the spending limit of the delivery partner’s contract with the programme, the BEJ programme team will need to find alternative means to meet these requests. It is recommended that the programme team seeks a Business Case Amendment to allow the programme to spend beyond the existing commercial delivery contract (e.g. Accountable Grants to non-profit organisations).
- Feedback on the VGF from various sources are very positive, but guidelines on its implementation could be more detailed. The projects it has selected so far are the right strategic fit for the programme and there is strong evidence of additionality, but the approach/guidance to project selection needs to be codified for consistency. It is recommended that the BEJ project team works with the delivery partner to articulate their approach to project selection to ensure consistency as they look to identify the fourth VGF project this year.
- The process to extend the commercial delivery partner’s contract to reflect the increased programme budget and extended end date were protracted. This caused uncertainty to the delivery partner team with job security, affecting staff morale. This could have been avoided had there been clearer records showing the contract’s original value and an explicit line in the Business Case Amendment for the VGF to show its exclusion from the commercial contract (except for management fees). No immediate recommendation for the existing programme, but something for the BEJ programme team to consider as they design the next iteration of this programme.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Mentari programme reviewed their Theory of Change in 2023. There has been no change in the impact statements “Increased access to reliable and affordable low carbon energy (including for women and/or marginalised groups) leads to inclusive economic growth” and “Increased investment in quality low carbon energy projects”. These original impact statements remain relevant at this point in the programme and for the coming year. But worth reviewing again when a new Indonesian government takes office in late 2024.
There have been some changes to the intermediate outcomes and outputs for the Brokerage, Demonstration, and CCBN strands. Brokerage added an intermediate outcome to measure changes in outreach/applications by investors the strand works with. And it reframed an output to focus on impact of assistance by the strand. The Demonstration strand also changed several outputs to reflect the change of focus from establishing the off-grid solar plant to mainstreaming the model.
Four new Programme Level Outcomes have also been added. These broadly relate to the ‘just’ element of energy transition as they address points like G&I, increased income, and access to low carbon energy. These are useful to track to help put the programme into context, but it would be difficult to attribute the programme’s contribution to these large numbers – particularly when the programme’s strategic outputs can come from the policy interventions.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to continue to deliver against expected outcomes and impact. The work of the four strands have contributed towards GoI’s energy transition policies and the JETP’s interests. But one of the key recommendations is to update the output targets to reflect the extended programme period. An outline where the programme’s activities have delivered against the high-level outcomes:
- Policy strand activities have contributed towards improved policies and regulations in the low carbon energy sector. This includes support to Indonesia’s development of a National Strategy on Hydrogen and an analysis of Local Content Requirement (LCR) regulations to support development of the JETP’s Comprehensive Investment and Policy Plan (CIPP). These contribute towards improved subsidiary policies, regulations and guidelines for a more conductive business environment in the low carbon energy sector).
- Brokerage strand activities contributed towards an increase in low carbon energy projects materialising. It focused on selecting and funding projects for the Viability Gap Fund, technical assistance to a biofuel company, and continued its technical assistance towards the national energy supplier’s Diesel Replacement Programme (DRP). These two outputs contribute towards increasing investments brokered for low carbon energy projects.
- Demonstration strand activities over the review period worked to ensure the delivery of the mini solar grid, continued to deliver socio-economic benefits to the community. This included creation of six new jobs in the area (civil worker, electrician, catering service, technical surveyor, geospatial surveyor, and social surveyor) and the identification of 15 women-led businesses that benefited from the new renewable energy source. These contribute towards improving socio-economic benefits generated, particularly for women and marginalised groups, in demonstration project intervention area).
In the year ahead, the programme will continue to produce studies that seek to improve the implementation of LCR, business models for hydrogen, and power purchase agreements for renewable energy. The Brokerage strand will continue its support for the DRP, identify further projects for VGF support, and support PT SMI’s development of a Trust Fund. The Demonstration strand will focus on several handover activities to support the just energy transition concept delivered in Sumba.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Given Indonesia’s position as a top ten global greenhouse gas emitter and the UK government’s global interest to tackle climate change, a programme like this should exist. The programme should continue till its scheduled end. The programme has met or exceeded its output targets, and some of these outputs have been particularly positively received by the host government.

## C. DETAILED OUTPUT SCORING

1. POLICY STRAND

Output Title	Policy Strand, Output 1: GoI supported with recommendations/TA on subsidiary regulations & effective implementation of new Perpres
Output number:			1	Output Score:	A+
Impact weighting (%):			17	Weighting revised since last AR?	N/A
Indicator(s)		Milestone(s) for this review			Progress
Number of recommendations, on subsidiary regulations developed		0			15 documents produced as below: / 1. Hydrogen in Indonesia / 2. Hydrogen technology, nomenclature and global developments / 3. Hydrogen regulation and supply chain / 4. Indonesia's position in the global hydrogen market / 5. International learning in developing a national hydrogen roadmap / 6. Renewable energy and green hydrogen options for Pantar Island / 7. Matrix regulation clauses PJBL / 8. Naskah Akademik hybrid / 9. Report on Perpres 112 Evaluation - Electricity Generation Cost 2023 / 10-11. 2 reports of LCR and each summary: LCR System and Reformulation for MOI / 12-13. reports of LCR and each summary: Cost Benefit analysis (JETP and RUPTL) / 14. Battery costing report / 15. NZE Sectoral mini papers (draft)

Output Title	Policy Strand, Output 2: On-grid policy and regulatory recommendations developed (that mainstream GESI and business case) and presented
Output number:		2		Output Score:		N/A
Impact weighting (%):		N/A		Weighting revised since last AR?		N/A
Indicator(s)			Milestone(s) for this review		Progress
Number of on-grid policy and regulatory recommendations developed			0		0 (Note: The cumulative target for this output have been achieved in the previous years. But further activity is planned linked to this Output in the year ahead to align with GoI initiatives.)

Output Title	Policy Strand, Output 4: Preparation / recommendation of a regulatory framework and associated capacity building to implement the agreed business model(s)
Output number:		4		Output Score:		N/A
Impact weighting (%):		N/A		Weighting revised since last AR?		N/A
Indicator(s)			Milestone(s) for this review		Progress
Number of detailed off-grid model design developed for agreed model(s) by end of the programme			0		0 (Note: No activity relevant to this output was planned for this year, but the cumulative target for this output have been achieved in the previous years).

Output Title	Policy Strand, Output 5: Guidelines, TA, or capacity building on planning, procurement, & contracting provided to PLN
Output number:		5		Output Score:		A+
Impact weighting (%):		15		Weighting revised since last AR?		Down
Indicator(s)			Milestone(s) for this review		Progress
Number of new and/or improved guidelines, TA and training identification or capacity building for PLN on planning, procurement, and contracting.			1		3 trainings delivered: two Homer Pro Training (batch 4 and 5) complemented by a Scenario Planning session on applying its use on energy planning.

Output Title	Policy Strand, Output 6: Support on UK Energy Transition Policy Dialogue provided.
Output number:		6		Output Score:		A
Impact weighting (%):		10		Weighting revised since last AR?		Down
Indicator(s)			Milestone(s) for this review		Progress
Number of study, activity, and/or capacity building on energy transition provided			1		1 – Support to development and issuance of Comprehensive Investment Plan and Policy (CIPP) document, specifically on Local Content Requirements section.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score of the policy strand’s output is A+. The strand’s activities have either met or exceeded expectations of the planned milestones for outputs – but there is a caveat. One of the key output targets (number of recommendations made) is low as it is reactive to requests from MEMR for technical assistance on policies. Requests for support come throughout the year and the number is difficult to predict. It cannot be guaranteed that MEMR will always seek the programme’s support or adopt its recommendations. But, on this occasion, the hydrogen related products influenced MEMR’s development of their National Hydrogen Strategy and the LCR related products helped develop the JETP’s Comprehensive Investment and Policy Plan’s (CIPP) chapter on LCR. Both are significant wins for the programme in terms of progress against the Theory of Change as the former is a national strategy and the latter tackles the biggest barrier to investment in the renewable energy sector. These are significant wins given the complex political economy of Indonesia’s fossil-fuel heavy energy sector.

The review team’s interview with the Indonesian Ministry of Energy and Mineral Resources showed how the programme’s support to their development of a national hydrogen strategy was particularly useful last year and how the strand’s flexibility to support initiatives is a benefit. Additionally, noting the impact of LCR as a disincentive to investment in the low carbon energy sector in Indonesia and the significant investment the UK is putting into the Indonesia JETP, the strand’s contribution to the LCR sector of the CIPP demonstrates the strand’s value to multilateral efforts.
The strand’s delivery of Homer Pro training is an ongoing effort from the previous year but is relevant as it educates PLN (national energy distributor) staff on the proper sizing and design of hybrid off-grid systems. Homer Pro is a software application used for designing and simulating micro-power systems, integrating various generation types to optimize energy solutions. The objective of this training is to deepen PLN personnel's expertise in utilizing the Homer Pro application, crucial for modelling and optimizing hybrid systems.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes for the strand recorded in the change log. Programme team to consider updating output targets.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Previous AR recommendations for this strand have been actioned by the programme team. A workplan is now prepared by the delivery partner in consultation with the programme team and there is regular catchups between both to monitor progress. The programme team has also responded to the request to explain how the programme supports development of domestic manufacturing and supply chain if the renewable energy sector by referencing its work on LCR and JETP.
Main issue identified by the review team in discussions with the delivery partner is that the programme is now reaching its budget ceiling but the requests for assistance from JETP and MEMR are expected to continue. The contract with the delivery partner can no longer increase in value to accommodate further requests due to procurement rules. A recommendation is made in the Programme Management section as this issue cuts across all the strands.
2. BROKERAGE STRAND
Output Title	Innovative financing mechanisms/ better de-risking schemes supported (includes enabling access to these facilities) or developed
Output number:	2	Output Score:		N/A
Impact weighting (%):	N/A	Weighting revised since last AR?		Down
Indicator(s)		Milestone(s) for this review	Progress
Number of new and/or existing financial schemes/facilities/mechanisms (i.e. blended finance facility or other de-risking solutions) that are receiving TA support		2	0 (Note: Cumulative target achieved last year and MENTARI supported two projects with dedicated TA support. In 2023, Brokerage focused the efforts to support the implementation of two blended finance mechanism established in previous years: Viable Gap Fund and Carbon Credit Scheme.)

Output Title	Brokerage Strand, Output 2: Extension of marketing and due diligence services for existing public and private investors
Output number:		2	Output Score:		A
Impact weighting (%):		N/A	Weighting revised since last AR?		Down
Indicator(s)			Milestone(s) for this review	Progress
Number of marketing and due diligence proposals submitted to financial institutions			1	0 (Note: Cumulative target was achieved last year. Since the strand did not add new project developers, or investors this year, no marketing and due diligence proposals were developed and submitted to financial institutions.)

Output Title	Brokerage Strand, Output 3: Continuous engagement with financiers and developers for matchmaking and improving understanding of regulatory environment and opportunities.
Output number:	3	Output Score:		A+
Impact weighting (%):	5	Weighting revised since last AR?		Up
Indicator(s)		Milestone(s) for this review	Progress
Number of facilitations, meetings, trainings, FGDs, and/or events organised		2	7 facilitated trainings, meetings, FGDs, and/or events carried out: / three series of trainings for Dewa Agri Coco, that were (1) Carbon Credit Training; (2) Gender Action Learning Sustainability (GALS) for the community and Dewa Agri Coco staffs; and (3) GALS training for management. These contributed to developing the business model for a waste-to-energy project using coconut husks. / facilitated intermediaries/meetings between (1) SEP and Blue Orchard Invesment; (2) SEP and Cross Boundary Energy; (3) PT Multitron to Indoventures / and (1) FDG MKI Hybrid

Output Title	Brokerage Strand, Output 4: Pipeline of quality low-carbon energy projects (in “support mandate”)
Output number:	4		Output Score:		A+
Impact weighting (%):	8		Weighting revised since last AR?		N/A
Indicator(s)		Milestone(s) for this review		Progress
Size and value of probability weighted pipeline for on-grid and off-grid clean energy projects (cumulative).		GBP 766m cumulative		As the end of the last FY, the programme supported a pipeline of GBP 2.97 billion (unadjusted CapEx). The probability-weighted value of this pipeline is £1.86bn, which is much lower than the total CapEX because the risk of the identified projects is currently being assessed through feasibility studies.

Output Title	Brokerage Strand, Output 5: Grant or Tailored TA to projects delivered (including projects linked to green bonds)
Output number:	5	Output Score:		N/A
Impact weighting (%):	N/A	Weighting revised since last AR?		Down
Indicator(s)		Milestone(s) for this review	Progress
Number of low carbon energy projects that received TA, Grant, and/or brokering services		10	0 – Achieved. We have achieved cumulative target for this output in previous years. This current year, Brokerage did not add new brokering services. This was due to the focus of the Strand was to complete the existing TA and support the implementation of VGF

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the Brokerage strand’s outputs is A, as the planned milestones have been either met or moderately exceeded expectations for outputs under this strand.
In 2023-24, the Brokerage strand pivoted towards three complex but impactful projects: (1) establishing and disbursing the Viability Gap Fund (VGF) – a £2.7-million innovative blended finance facility established to improve the ‘bankability’ of small-to medium-sized renewable energy projects, (2) supporting PT Dewa Agri Coco – an innovative circular-economy biomass project - in establishing a Carbon Credit scheme as well as providing organic certification and gender equality and social inclusion training, and (3) ongoing technical assistance to the national energy provider’s (PLN) Diesel Replacement Programme (DRP).
Disbursal of £1.1m from the VGF to date has delivered tangible results, including supporting three innovative mini hydropower projects, totalling 7.1 MW in capacity. The VGF is also well targeted, filling a key gap between MDB and DFI finance (typically targeted at larger ticket sizes) and development impact financing (which provides TA only or focuses on smaller community project). The VGF targets small-to- medium-sized renewable projects.
The VGF economic case was well articulated and evidenced. The choice of policy instrument – a construction grant – had the desired effect of de-risking the upfront capital expenditure required to signal the project’s ‘bankability’ to the loan provider – PT SMI (Sarana Multi Infrastructure). Around £893k of UK grant contribution leveraged around £11.45 million of capital investment.
There was sufficient evidence of additionality as the projects selected were ‘marginally bankable’ – e.g. they were seen as technically viable but requiring large upfront investment to attract project finance. There was also evidence of innovation, in terms of:
- The support mechanism: whilst the project developer (PT Brantas) could access MDB and other development partners’ technical assistance, direct project finance for SMEs and smaller RE projects was seen as lacking. The capital grant support provided by Mentari for projects of such size (e.g. mini hydro) was seen as filling a key gap in the local renewable energy investment ecosystem. Such support was also not readily available from MDBs and other development partners.
- The structuring of the financial and development transaction: The blending of a Mentari grant, a PT SMI loan, and project developer equity is an effective approach. However, the review failed to find evidence of the concessionally of PT SMI’s loans, which were considered comparable to commercial loans by the project developer.
- The social and economic impact of the project: the mini hydro projects included other concessional elements from the Ministry of Public Works (e.g. land concession) as well as the commercial case for collaborating with PT SMI – a 100% GoI-owned infrastructure financing company - was well supported during the review, reflecting a pragmatic approach of working with an established local partner as well as with the local investment ecosystem. For example, the programme was able to leverage PT SMI’s existing relationships with the main electricity off-taker – PLN. This is a key demand-side factor in ensuring the viability of RE projects in Indonesia.
The selection of the developer – PT Brantas (a State-Owned Enterprise) was based on the commercial specification of the projects and their innovative nature. The review team was satisfied that the delivery partner had brought in external expertise to conduct due diligence and had engaged with other financial partners, including commercial banks. There is also evidence of impact at scale. The VGF’s design and popularity to developers convinced PT SMI to seek the programme’s support to design a trust fund for investment in similar projects.
However, there was limited evidence of spillover or signalling effects to the rest of the private finance ecosystem in Indonesia: the scheme is tied to PT SMI’s operating model and any future iterations of the VGF should consider co-funding with other partners (including UK DFIs and MDBs). It should also consider other ‘blending’ approaches which leverage other UK-enabled sources of finance such as Private Infrastructure Development Group (PIDG) and British International Investments (BII), whilst remaining embedded in the local finance ecosystem.
From a financial and delivery perspective, compliance with the terms of the construction grant was seen as straightforward by the recipients, although they did note delays in the disbursement of the funds resulting in a period of uncertainty and project delays (i.e. the PT SMI loan followed after the construction grant).
In relation to the strand’s technical assistance to DEWA Agri Coco, by the end of March 2023, MENTARI identified a pipeline of 59 potential renewable energy projects with an unadjusted CAPEX value of £2.97bn. The probability-weighted value of this pipeline is £1.86bn, which is much lower than the total CAPEX because the risk of the identified projects is currently being assessed through feasibility studies.
The programme provided support to Dewa Agri Coco on: (1) Carbon Credit Training; and (2) Gender Action Learning Sustainability (GALS); and facilitated two matchmaking meetings. Dewa Agri Coco welcomed the ongoing support provided by Mentari on carbon credits.
The strand’s matchmaking capability was less active in generating a new pipeline of TA and matchmaking support as cumulative outputs were achieved last year (22/23). However, the strand’s technical assistance to the Diesel Replacement Programme (DRP) significantly increased the number of pipeline projects in Indonesia (Output 4). The CAPEX value of the two DRP phases add up to £860m, which significantly helped the programme exceed the output. The target for this output likely did not anticipate a programme like DRP. Although all the output targets need updating, this needs particular attention given the extent it has been exceeded.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The outputs indicators were not revised in the past year, although the programme team should explore introducing more output indicators around the VGF given it is still at the active delivery stage.
Some of the output indicators in the log frame are no longer relevant as cumulative targets have been achieved and they therefore fail to capture actual performance delivery of the programme in the current year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Previous recommendations have mostly been addressed. The process of selecting the three hydro projects should help the programme team and delivery partner codify guidelines on project selection. At the time of writing this review, terms of reference were being prepared for an evaluation of the strand using the EQUALS framework.
Noting the remaining £1.5m in the VGF, some recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Codify the criteria for VGF project selection based on the experience of selecting the three projects for consistency	Delivery Partner	Brokerage strand lead BEJ and PRO	September 2024
Complete the EQUALS evaluation for the Brokerage Strand and VGF	PRO	BEJ Programme team	Before October 2024

For future iterations of the VGF, the programme team should consider a more rigorous project selection process, guidelines on the size of the grant, partnerships with UK-supported financial institutions, and conditionality.

3. DEMONSTRATION PILOT PROJECT STRAND
Output Title	Demonstration Project Strand, Output 4: Knowledge about applying small-scale renewable energy for electrifying off-grid produced
Output number:		4	Output Score:		A
Impact weighting (%):		10	Weighting revised since last AR?		Down
Indicator(s)			Milestone(s) for this review	Progress
Number of knowledge products about small-scale off grid produced			1	1 - produced a case study with a topic of Gender and Inclusion in the villages where the solar PV is, with a title of "Dreams Under Humma". The study contributes to our wider efforts on demonstrating ‘just energy transition’ to wider audiences.

Output Title	Demonstration Project Strand, Output 5: Advocate to GoI and other stakeholders (incl. project developers, PLN) in replicating the good governance and inclusive social economic ecosystem
Output number:		5		Output Score:		A
Impact weighting (%):		5		Weighting revised since last AR?		N/A
Indicator(s)			Milestone(s) for this review		Progress
Number of recommendations provided to GoI to replicate the good governance and inclusive social economic ecosystem from the Demonstration Project			0		3 recommendation provided as below: / Synthesis Report on the technicality and governance of integrated Solar PV in Mata Redi and Mata Woga. / The application of smart meters and demand side management for centralised solar PV Indonesia. / Rural electrification sustainability through Productive Use of Energy.

Output Title	Demonstration Project Strand, Output 6: Providing technical assistance and capacity building to other potential BUMDes and village government to upscale the knowledge from the Demonstration Project
Output number:		6	Output Score:		A
Impact weighting (%):		10	Weighting revised since last AR?		N/A
Indicator(s)			Milestone(s) for this review	Progress
Number of villages receiving coaching clinic, consignment, assistance from DP Strand.			21	21 - In Year 3 and 4, Demonstration pilot project strand provided coaching clinic, knowledge sharing, consignment to 21 villages receiving Special Allocation Fund (DAK) for Renewable Energy. This was requested by Ministry of Village, Transmigration, and Disadvantaged Regions, as MENTARI managed to establish an affordable business model of RE in village level.
Number of coaching clinic / consignment delivered to other potential BUMDes and PemDes			2	2 sessions were delivered during the period: / In June 2023, a joint-ministerial visit to the Sumba site by the Ministry of Villages, Ministry of Finance, BAPPENAS and MEMR learned best practice from the demonstration project that resulted in 21 BUMDESA (rural development network supported by GoI) receiving funding from a Special Allocation fund (DAK – Dana Alokasi). This outcome builds on a coaching session delivered in Sumba on October 2022 on utilising their DAK effectively. / In September 2023, a second coaching clinic took place in villages receiving DAK to use these effectively using the example set by Sumba that was welcomed by GoI.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the Demonstration strand’s outputs is A+, as the planned milestones have either met, moderately exceeded, or substantially exceeded expectations for outputs under this strand.
This year, the Demonstration strand has focussed on ensuring community ownership and sustainability of the two mini-grid projects. The project team worked with a range of village, provincial and national stakeholders to:
- strengthen the financial and institutional capacity of the village business unit (BUMDes); and setting an affordable, progressive tariff to ensure electricity costs are sustained within the community.
- ensure Productive Uses of Energy are embedded in the community, with a strong focus on gender and female-led businesses.
- scale up the funding models by improving access to the Special Allocation Fund and working with PLN on electricity purchase options with subnational-owned enterprises (e.g. BUMDes).
- disseminate lessons learned to other sub-national governments (e.g. other Sumba districts), provincial level (e.g. Provincial Regulation on Renewable Energy Management) and influence national government, including the National Planning Agency and GoI’s mini-grid programmes.
The review team found evidence of the scalability of the model demonstrated and impact at different levels of Government, especially on community energy management policy and gender-inclusive initiatives.
The community-centred approach to delivery and additional wrap-around support after the initial mini-grid ‘build’ phase (e.g. three years of O&M support) are seen as a distinct feature of this demonstration project, setting it apart from previous projects undertaken by other donors.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
A number of new output indicators were added to reflect the expanded scope of the Demonstration strand since last year, including community engagement, lessons learnt across local, regional and national government as well as:
- Intermediate Outcome Indicator 2a*: Percentage of HHs accessing Productive Uses of Energy (PuE) services, which benefits women and girls.
- Intermediate Outcome Indicator 5a: Number of Inclusive Regulations issued by the local government or cases of integrating gender inclusiveness into policies/systems by other stakeholders.
- Intermediate Outcome Indicator 6a: Number of procedures, guidelines, or implementations adopted and/or disseminated by the government as a result of MENTARI assistance to promote the off-grid business model.
- Output Indicator 5a: Number of recommendations provided to GoI to replicate the good governance and inclusive social economic ecosystem from the Demonstration Project
- Output Indicator 6a: Number of villages receiving coaching clinic, consignment, assistance from DP Strand
- Output Indicator 6b: Number of coaching clinic / consignments delivered to other potential BUMDes and PemDes
The review team recommends closer monitoring of the target around BUMDes revenue which reported a 394% increase. However, this increase reflects several one-off impacts and more frequent monitoring is required to track revenue form electricity payment from the community as a proxy of the model’s long-term sustainability.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Progress has been made against previous year recommendations. An updated progressive tariff structure with a focus on affordability has been proposed. A long process to reduce the electricity tariff have been started in 2023. Additionally, Mentari held discussions with community and village administration regarding the tariff, providing calculation of the possible new tariff, and to gain buy in and consensus from both village administration and community members. Mentari proposed the new tariff reduction. The new tariff has been included in the village regulation draft but has yet to be officially issued and implemented. Delivery partner and programme team expected that it will be officially issued and implemented around the end of the first phase of MENTARI.
In relation to the previous recommendation on the productive uses of energy by the community, Mentari published a detailed feasibility study into productive uses of energy, including a set of technologies and business models tailored to the local context.
For the year ahead, the review team recommends the following:
Recommendations	Responsibilities	Support	Timelines
Focus the remainder of the Demonstration strand towards scaling up the lessons learned from the project and replicating this model across other localities. The team should particularly reflect on the experience of working across various levels of government, funding models and sustainability, and the demand-side support measures beyond the community (including the design of sub-national energy purchasing arrangements with PLN)	TL Delivery Partner/PRO	Demonstration strand leads in BEJ strand lead and delivery partner	By end of programme

4. COLLABORATION & NETWORKING STRAND (Now COLLABORATION, CAPACITY BUILDING & NETWORKING STRAND (CCBN))
Output Title	Collaboration, Capacity Building & Networking Strand, Output 1: Capacity building and knowledge exchange, including focus on opportunities for women and marginalised groups, provided to inter/national academic/TVET, and relevant stakeholders (incl. MEMR, PPSDM, PLN) in low carbon energy sector
Output number:		1		Output Score:		A+
Impact weighting (%):		10		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
Number of International and Indonesian academic or training institutions, and relevant stakeholders (incl. MEMR, PPSDM, PLN) receiving programme matchmaking and/or knowledge sharing support.			0		47. This includes one university engagement with demonstration pilot project strand, 21 institution participating in Geospatial Least-Cost Planning / training, 14 universities attended University Goes to Campus event, and 11 institutions attended scenario planning.
Number of activities organised by MENTARI for supporting Inter/national academic , TVET, and relevant stakeholders (incl. MEMR, PPSDM, PLN) focusing on low carbon energy in Indonesia			0		3 activities organised as below: / 1. MENTARI Goes to Campus / 2. MOOC production / 3. Scenario Planning Training

Output Title	Collaboration, Capacity Building & Networking Strand, Output 2: Branding & communication products produced to share knowledge and lessons
Output number:		2		Output Score:		A+
Impact weighting (%):		N/A		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
Number of communication and knowledge products produced and disseminated			1		32 communication and knowledge products produced and disseminated such as flyers, video, and other event collaterals.

Output Title	Collaboration, Capacity Building & Networking Strand, Output 3: Promoted knowledge sharing and facilitated partnerships
Output number:		3		Output Score:		A+
Impact weighting (%):		N/A		Weighting revised since last AR?		[If Yes, up or down?]
Indicator(s)			Milestone(s) for this review		Progress
Number of events (consultation, facilitation, FGD, workshop) to facilitate knowledge sharing and partnership development			10		28 events were facilitated such as FGDs, governance meeting with GoI, workshops, and trainings.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the CCBN strand is A+. The programme has moderately exceeded expectations of all planned milestones for outputs under this strand – but there is a caveat. Although progress against milestones were exceeded, the strand’s targets were low to begin and many of the activities linked against some milestones are linked to delivering activities by other strands. This reflects the adaptive nature of the programme, which is reactive to GoI requests. The programme team would need to find more qualitative ways to measure this strand’s impact that is not reliant on delivering other strands. The academic engagement appears to be the only distinct activity from this strand, but its support to other strands was still critical towards the programme’s overall success.
This year marked a first full year with the inclusion of the capacity building element, which was incorporated mid last year under this new directive, the CCBN strand conducted three significant capacity building activities targeting a variety of stakeholders including MEMR, PLN and the National Energy Council. One of these was the scenario planning training, which successfully brought together government ministries to enhance long term planning across the energy sector. In addition to new capacity building activities, the strand continued to build on the success of last year with 28 events facilitated include focus groups, workshops and trainings and dissemination of 32 communication products. Consideration should be given to how to measure individual communication products to ensure the target reflects the activity. The CCBN complemented the other strands well, particularly the policy strand with focus groups and training sessions on topics like LCR calculations.
It was interesting for the review team to hear that some of the strand’s activities include collaboration with other European donors. Given donor coordination can be an issue in the Indonesian energy sector, it is worth mapping out how existing activities involve other international donors. This exercise may have secondary benefits to BEJ’s relationships with other local diplomatic missions.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to the outputs since last year.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Recommendations from last year revolved around strategically managing requests from stakeholders and evaluating resource level to support this work. Feedback from the delivery partner suggested that requests have been prioritised well this year and the communication with the programme team has been good. Budget constrains have helped encourage effective prioritisation. A previous recommendation also suggested evaluating the resource level needed to support the increasing work of the CCBN strand. But as the workload is decreasing, reflecting the limited time in the programme, further resource is now not needed.
The final recommendation was to develop a broader comms strategy to inform all relevant ministries about programme activities. Comms have taken place throughout the year. Most notable involved two visits by a DESZ minister to VGF supported projects and the British Ambassador’s visit to the demonstration site in early 2024. Both events generated good visibility of the UK’s contribution towards Indonesia’s energy transition.
Recommendations for the year ahead
Recommendations	Responsibilities	Support	Timelines
Consider refreshing the strand’s outputs to be more distinctive and have its outputs closely aligned to its purpose in the Business Case.	Delivery Partner/PRO	SRO	When log frame reviewed
Map out how the programme collaborates with other international donors to support co-ordination efforts and BEJ’s relations with local diplomatic missions.	Delivery Partner	PRO	October / 2024
Consider amalgamating this strand into others when designing future iterations of MENTARI	PRO	BEJ Strand Lead	When designing future programme

5. GENDER AND INCLUSION
Output Title	Gender and Inclusion strand, Output 1: Programme demonstrates G&I integration across (i) MENTARI programme intervention design (internal), (ii) support to relevant stakeholders (internal/external), and (iii) knowledge sharing (internal/external).
Output number:		1		Output Score:		A+
Impact weighting (%):		10		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
Percentage of women and/or marginalised groups involved in facilitated discussions			30%		41% of women and/or marginalised groups involved in facilitated discussions
Number of most significant stories, focused on livelihood, gender and inclusion, and secondary benefit, developed to illustrate project contribution to socio-economic, education, empowerment, environmental conservation benefits in the area of demonstration project and other relevant strands within MENTARI.			2		1 - the programme produced one last case study on Gender and Inclusion, and the title was "From Margins to Mainstream: Advancing Inclusive Green Jobs in Indonesia’s Energy Sector." (note: cumulative target for whole programme met)
Number of G&I learning events organised that will focus on programme stakeholders (e.g. policymakers, financiers, private developers, etc.)			2		2 - G&I strand collaborated with the Brokerage Strand to support the preparation of a Carbon Credit scheme with Dewa Agri Coco and Climate Partner. G&I not only helped develop a G&I action plan but also facilitated Gender Action Learning for Sustainability (GALS) training, enhancing the project's commitment to equitable practices.
Number of G&I TA support provided to programme stakeholders (internal/external)			8		13 - TA provided such as GALS training and document reviews on G&I aspects.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for the programme’s gender and inclusion indicators is A+. The outputs have moderately exceeded expectation. G&I is mainstreamed in all strands with the sub-contractor, HIVOS, playing a leading role. This is a good approach, though noting HIVOS is also the lead delivery partner for developing the Demonstration strand, it is notable that the main comms linked to G&I for the entire programme so far come from the Demonstration strand.
Publication of documents influencing standards are the highlight G&I outputs over the period. This includes the Gender and Inclusion Handbook, Inclusive Feasibility Study, Guidelines for Sustainable and Integrated Off-Grid Solar PV Governance, and Gender Responsive Guideline of BUMDesa establishment. These guidelines have received significant recognition and are now officially adopted by the Ministry of Energy and Mineral Resources (MEMR) and the Ministry of Village Development (MoVD). While these are positive outcomes, they are mostly linked to the activities from the Demonstration Strand. It would be good to explore ways to generate G&I outcomes explicitly linked from other strands, particularly the policy and brokerage, but the annual review team acknowledges this is not straightforward given the limited time and budget within the remaining programme.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes recorded in the change log for this strand. The programme team is encouraged to update the output targets for this strand to reflect the new end date. The targets could be more ambitious, but any new targets need to be realistic of the limited budget for the remainder of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Some progress has been made towards the previous AR’s recommendations. The programme team constantly checks where G&I data can be better represented in the different strands. Specific interventions to bring disadvantaged groups into the low carbon energy supply chain is also an ongoing effort, but efforts to capture G&I aspects of existing work could be better – particularly in the Brokerage strand. G&I data linked to Demonstration strand outputs are good but less so for VGF supported projects. This is fair for now as neither of the three VGF projects are operational yet, but something for the programme team to consider as soon as the first VGF project is operational. Another previous AR recommendation is the inclusion of an “environment” reference into the relevant output. This doesn’t appear to have been actioned and worth including when the log frame is reviewed.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
If the three VGF projects are completed within the programme’s timeframe, consider capturing G&I benefits from these in a similar manner as done for the Demonstration strand.	Delivery Partner	PRO	Begin review as soon as one VGF project is completed
Add “Environment” back into the output statement and name, and include an indicator to capture CO2 emission reduction by the renewable energy projects supported by Mentari	SRO/PRO	TL, Mentari	When log frame reviewed

Future iterations of Mentari should consider a dedicated budget for G&I mainstreaming. A dedicated G&I Manager is already part of the delivery partner team, but G&I awareness within the delivery partner team has fluctuated over the programme’s lifetime given staff turnover. This would strengthen the G&I awareness of the different strand teams to ensure they factor in G&I with their work.

D: VALUE FOR MONEY
VfM performance compared to the original VfM proposition in the business case
Economy: The programme has been able to achieve more activities than planned with the budget, showing inputs have been maximised. The consortium model has been effective in enabling the programme to benefit from the expertise of local organizations, and flexibility to divert resources to emerging priorities has helped maximise the programmes value. The VGF has been an innovative instrument that has helped investment worth significantly more than its value. Across the three projects, £1.1m was given in support through the VGF, which led to the mobilization of £9.7m from PT SMI and the developer. Designing the VGF so as only the minimum contribution needed to make the project bankable was made helped make this vehicle mor economical. More consideration could be given to assessing the VfM of the selected projects (see below).
Efficiency: The programme has exceeded almost all output milestones, some by a considerable margin. This demonstrates that the available resources have been used efficiently, but the programme team will need to refresh these targets. The flexible nature of the programme has enabled resources to be redirected to support emerging priorities, helping the programme achieve its intended outputs. This has at times led to overstretching the delivery partner, although this has improved notably since last year. Ultimately, the flexible structure remains a net positive. Uncertainty over budget allocations did constrain the delivery partners’ ability to deliver for a short period, but this was resolved and didn’t impact on the overall delivery of outcomes.
On the VGF, more consideration could have been taken to ensure that both the projects themselves and the financing terms represented the best possible VfM. All projects were done through PT SMI and chosen through their existing pipeline. Although some analysis was done to explore alternative financing models, a more exploration of alternative options for partners either on the financing or construction end could have helped confirm that these represent VfM. But it is noted that, due to constraints within the Indonesian system, utilising an alternative partner or financer may not have been possible.
Effectiveness: The programme has been extremely effective at achieving its aims. The nature of the programme has allowed BEJ to quickly respond to various asks from GoI. Although diverting resources to changing asks could risk a divergence from strategic priorities, in this case it has increased the effectiveness of the programme by allowing it to respond to emerging priorities and in helping build credibility with GoI. This has enabled the programme to facilitate meaningful change, for example through the introduction of new regulations on LCRs which occurred as a direct result of studies and engagement done under the policy strand. This strand also contributed to the JETP through the CIPPS document, meaning its contributed to wider UK development priorities. Other strands have also proved effective; the demo strand has fulfilled its objective of showing that small scale off grid PVs can be viable, although too early to assess whether this will lead to replication.
Equity: Gender and inclusion have been considered across all four strands of the programme, and 3 out of the 4 G&I targets were exceeded. Examples include provision of technical assistance on G&I initiatives (brokerage strand), training on G&I (CCBN) and development of gender responsive guidelines from BUMDES (demo). The latter has been adopted by MEMR and has become a reference point for energy programmes run by USAID and UNDP, demonstrating it has reach beyond the activities of the programme. The delivery partner commented that mainstreaming G&I into other strands has created challenges in securing budget for G&I specific activities as they are competing against other priorities within the same allocation. However, the alternative of a separate strand is less preferable from VFM perspective, as it could lead to G&I objectives being sidelined and could increase costs as it would require separate activities. Having separate G&I targets and a dedicated G&I manager to work with other strand leads helped ensure progress was made.
Assessment of whether the programme continues to represent value for money
The programme should continue as it is delivering extremely across all outcomes with a relatively modest budget. It fits well with FCDO strategic aims, particularly as it can support other initiatives like the JETP.

E: RISK
Overview of risk management
The programme has 38 active risks (including eight identified by the delivery partner) in its risk register and all the risks are within the overall risk appetite for BEJ. Mentari is currently not recorded in the Aid Management Platform (AMP) but considerations were being made by the programme team at the writing of this review. At this stage, the programme team is maintaining its programme risk register in its own filing system within FCDO systems.
The Strategy and Context related risks include lack of political commitment to reform, poor capacity, and frequent change in key personnel in GOI, lack of conducive policy frameworks, overlap or conflicting UK priorities and programmes. The residual risk for these ranges from minor to moderate. At the time of writing, it is understood the risk register been updated to include any implications from the UK general election.
The Policy and Programme delivery risks include uncertainty in the ODA budget allocation for the programme and programme extension, weak programme management and MREL systems, and updates to Programme Management standards. Addressing these risks, the delivery partner is closely working with the BEJ team by organizing fortnightly meetings and ad hoc meetings when required to plan the activities, forecast appropriately and implement them effectively. The BEJ team is also working more closely with the BEJ’s Development Management Unit to ensure standards on programme management and compliance are maintained.
The Reputational risk to Mentari include mismanagement of funds, safeguarding risks, and undertaking activities that are seen to extend coal use in Indonesia. The residual risks from these range from minor to moderate. Mitigation involves due diligence, audits, and detailed discussions between BEJ strand leads and their delivery partner counterpart.
The Financial and Fiduciary risk to Mentari relates to the fund mismanagement and the reduced availability of ODA fund. The residual risk is moderate. The risk is mitigated by strong due diligence checks to delivery partners with audits. The funding risk is within the risk appetite.
The Safeguarding risk relates to activities failing to deliver the G&I outcomes and adhering to environmental and social performance standards. The risk is moderate and mitigations in place include careful programme design, utilising G&I experts, and ensuring whistleblowing policies are in place for programme staff.
The People risk for Mentari includes lack of sufficient and qualified staff, for both BEJ and delivery partner, to implement the programme. And for the programme team to balance between programme work and non-programme work. Residual risk here varies from minor to moderate. Mitigations include programme management training and cross-embassy prioritisation exercises to ensure the BEJ team isn’t stretched.
It is recommended that the programme team review the Risk Register in the context of the outcome of the UK general election, after its annual meeting with MEMR in 2024, and once the new Indonesian cabinet forms around October 2024.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Delivery and Performance
The overall performance of the programme is good, but there were some challenges on the programme management side. The main issue raised by the commercial delivery partner was the uncertainty of the contract extension beyond December 2023. The contract was eventually extended till 2025 but the process towards that was protracted and affected staff morale. Months of uncertainty and some departures from the delivery partner team could have been avoided had the documentation surrounding the VGF explicitly stated it was outside the commercial contract and documentation around original contract value been clearer.
The Business Case for the programme is limited to only deliver its objectives via a commercial contract. Given the overall programme still has the budget headroom for additional activities and the commercial contract cannot be increased, the programme team should consider amending the Business Case to deliver activities beyond the commercial delivery contract. This would help maintain the programme’s flexible reputation with GoI.
Although GoI appreciates the flexibility of the programme, particularly on the policy support, they did flag that the programme’s compliance with their administrative requirements could be better. Mandatory documentation (i.e. BAST) required by GoI to formally record outputs from Mentari have not been submitted by the delivery partner or the BEJ programme team since 2022. This will need to be rectified going forward, particularly as the programme closes towards the end of 2025. The programme team will monitor this for GoI compliance.
Financial Management
The BEJ ODA allocation for this programme for April 2023 – March 2024 was originally £2,530,000 but the budget was increased to around £2,700,000 to absorb underspend from other programmes in the BEJ portfolio identified in the latter half of 2023. Although the delivery partner forecasted to spend £2,694,505.04 by the end of the financial year, Invoices received by BEJ for that period totalled to £2,706,078.18 (0.43% variance). Of this figure £1,435,606.19 is categorised as Resource Departmental Expenditure Limit (RDEL) and £1,270,471.99 categorised as Capital Departmental Expenditure Limit (CDEL). Delivery partner invoices between April-May 2024 add up to £109,523.02. This is lower than forecasted, but usually caused by delays receiving subcontractor invoices.
The main driver of spending for the MENTARI delivery partner continues to be personnel, followed by Other Indirect Overheads, Other Direct Overheads and Profit. MENTARI’s spending on subcontractors is decreasing, though still an important option to have given niche expertise required for some activities. Beyond the commercial delivery contract, some spending has also gone towards the programme team (e.g. MEL site visits) but these costs only make up 1.5% of total programme expenditure.
An independent financial audit to the delivery partner was occurring during the AR. No documents were available for review by the AR team due to the early stage that audit was occurring, but the fact of it happening provides some assurance of due diligence on financial management.
Commercial
Formal agreement with the delivery partner is through a commercial contract with Palladium International Ltd. Since the initial contract signing in December 2019, the contract has gone through five contract variations to capture the changes in key personnel, scope of the programme, and a time/cost extension. The updated contract’s value of £15,000,000 puts this as a silver contract with 3 KPIs for which the PRO is responsible for the reporting the contract’s performance in each quarter as part of cross-HMG contract transparency requirements. In the last KPI reporting, the contract was rated as good or on track.
Recommendations for the year ahead:
Recommendations	Responsibilities	Support	Timelines
Seek a Business Case amendment to allow the programme to deliver its objectives beyond the commercial delivery contract.	SRO	PRO	August 2024
Identify a methodology for attributing contributions of the programme to the overall impacts identified in Theory of Change	PRO	Delivery Partner	August 2024
Update all log frame and KPI targets to reflect new programme end-date	PRO	Delivery partner	August 2024

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
The BEJ programme team and programme delivery partners have regular meetings related to programme management, monitoring and reporting: (1) bi-weekly meetings between the management team from delivery partners and embassy programme team to discuss programme and contract operations and administrative matters, risk and programme progress; (2) bi-weekly / weekly meeting between strand leads from delivery partners and embassy programme team to talk about strand-specific progress, risks and opportunities; (3) monthly meeting between MREL Manager from delivery partners and MREL officer from embassy programme team to talk about MREL process, progress, and compliance; (4) quarterly steering group meeting between delivery partners and programme team to see the overall programme progress and challenges over the previous quarter as well as looking forward to the upcoming quarters. These quarterly meetings will evolve to focus more on deep dives on more strategic issues in future.
Delivery partners maintained a permanent, full-time MREL manager position during the review period. The delivery partner also has access to an MREL short-term technical advisor (STTA) who is experienced in working with FCDO programmes.
The embassy programme team also visited brokerage and demonstration pilot project sites during the review period to see first-hand the implementation on the ground and cross-reference this with progress reports provided by delivery partners. During the visits, the programme team met with relevant stakeholders and beneficiaries to listen to feedback and comments on the project.
During the annual review process, the reviewer team had the opportunity to interview the programme team, delivery partners, beneficiaries, and stakeholders of the programme. A fuller methodology for the Annual Review is described in Section A of this report.
Evidence
As a flexible programme, the programme team and delivery partners maintain regular communication to assess any changes in the context for the programme, and risks and opportunities, developing and discussing evidence to inform judgements about the ongoing activities and priorities for the work plan. As per the contract, the delivery partner is also obligated to continue to review ways to improve the delivery of services to better meet the overall objectives of the programme.
Learning
Refer to section “Major lessons and recommendations for the year ahead” on page two of this report.
Date of last narrative financial report	The delivery partner provides monthly financial reports and invoices, including an explanatory note on spending.	Date of last audited annual statement	29 March 2023 (note: an independent financial audit was occurring during this AR process)