## Annual Review Template

Title: MENTARI UK-Indonesia Low Carbon Energy Partnership (referred to in pre-delivery as Indonesia Renewable Energy Programme – IREP)
Programme Value £ (full life): £22,300,000		Review date: June 2025
Programme Code: AMP ID 400399	AMP start date: Legacy Prosperity Fund Programme started on 6 January 2020. Registered on AMP as of 23 August 2024	AMP end date: 30 April 2026

Summary of Programme Performance
Year	December 2019 (Light Touch)	Jan 2020 – April 2021	April 2021 – March 2022	April 2022 – March 2023	April 2023 – May 2024	April 2024 – May 2025
Overall Output Score	A	A	A+	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400399
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400399

A. SUMMARY AND OVERVIEW

Description of programme

MENTARI (formerly Indonesia Renewable Energy) is a £22.3m programme that aims to support inclusive economic growth and poverty reduction through accelerating and expanding low carbon energy in Indonesia, while mainstreaming Gender and Inclusion in its delivery. The programme started in January 2020 and was originally planned to end in December 2023. A Business Case Addendum (BCA) was approved in June 2023 for a cost and time extension to April 2026 and budget increase to £20 million. Another BCA was approved in 2024 to increase the headroom to £22,300,000 and allow the programme to have the flexibility to deliver beyond the commercial contract with Palladium.
The MENTARI programme is working closely with the Government of Indonesia (GoI), and other stakeholders, to promote a conducive investment environment in the renewable energy sector of Indonesia. The programme has the following four strands, where Gender & Inclusion are mainstreamed throughout.
1. Policy Strand aims to reform national and regional renewable energy policies, regulations, guidelines, and financial instruments that bring about a more conducive business environment in the low carbon energy sector.
2. Brokerage Strand aims to increase investment in low carbon energy projects by bridging the gap between potential financiers and viable project developers through brokerage, technical assistance and providing small amounts of catalytic Viability Gap Funding (VGF).
3. Demonstration Project Strand aims to demonstrate viable and replicable off-grid low carbon energy systems that will bring socio-economic benefits including for women and marginalized groups.
4. Collaboration, Capacity Building & Networking Strand (CCBN) supports collaboration, networking, and capacity building of relevant stakeholders in the low carbon energy sector including policy makers, investors, project developers, communities, and academia.

The programme was originally a legacy cross-government Prosperity Fund Programme which has been transferred to the bilateral Indonesia country plan budget, under the oversight of the Indonesia and ASEAN Development Director. The programme is primarily delivered via a commercial contract under a consortium led by Palladium International with Castlerock, ECA, and Hivos.
MENTARI has an adaptive programming approach to respond to the dynamic changes resulting from Indonesia’s ambition towards a Net Zero emissions economy and to support the Just Energy Transition Partnership (JETP). As the UK transitions to becoming a 0.3% development partner with a reduced ODA footprint, MENTARI offers valuable lessons and a compelling narrative. The programme’s integrated approach – combining policy reform, investment brokerage, demonstration projects, and capacity building – is a model for how the UK can create modern development partnerships with hinge economies and tackle climate change.

Summary supporting narrative for the overall score in this review

This Annual Review was carried out from 16 June to 5 July 2025 covering the programme from April 2024 to May 2025. The Annual review team comprised of staff from British Embassy Jakarta (BEJ) and the UK Mission to ASEAN. The team conducted meetings with several stakeholders of the programme including the BEJ programme team and delivery partners. Meetings were also conducted with independent third-party evaluators, NIRAS, who were conducting an evaluation of the Brokerage Strand and, MDF Asia, conducting an end line assessment of the Demonstration Strand. Based on the observation and feedback from stakeholders, the team has prepared this report.

The overall score for the MENTARI programme for this year is A+. The programme’s various strands have either met, moderately exceeded, or substantially exceeded expectations of the planned milestones for all outputs. Its outputs continue to contribute towards the programme’s Theory of Change Impact Targets on increasing Indonesia’s renewable energy generation capacity and value of investments into the sector.

Some of the achievements supporting the overall score in this review include:

The programme set a total target of 3.1 GW of new renewable energy (RE) capacity, building on Indonesia’s 2019 baseline of 10.19 GW, to be achieved by July 2025. Indonesia’s Ministry of Energy and Mineral Resources (MEMR) published data in 2024 indicating Indonesia added 3.45 GW of RE capacity in 2024, meaning the programme has exceeded its overall target.

The programme also raised its impact indicator target for the value of investments brokered to £1.12 billion, building on the £927 million reported in the previous Annual Review (original target: £766 million). According to the latest data from the implementing partner, the programme facilitated a potential investment value of £1.2 billion by July 2025, exceeding the target.

The programme’s various strands have either met, moderately exceeded, or substantially exceeded expectations for their respective planned milestones. Key achievements during the review period include:

  - Policy and Institutional Reform:
    - Supported the Ministry of Energy and Mineral Resources (MEMR) to reform Indonesia’s Local Content Requirements (LCR) in the power sector, removing barriers to renewable energy investment. This collaboration led to the successful issuance of a new Ministerial Regulation on LCR, creating a more enabling environment for clean energy development.
    - Supported MEMR to develop a comprehensive Power Purchase Agreement (PPA) framework for both renewable energy (RE) and variable renewable energy (VRE). This work has fundamentally shifted the approach to renewable power transactions in Indonesia, offering greater clarity and bankability for investors. The process culminated in the issuance of a new ministerial regulation on RE PPA, marking a major milestone in Indonesia’s energy transition.
    - Provided recommendations from an organisational study that were accepted and used by MEMR to inform a partial restructure of its Renewable Energy and Efficiency Directorate.

  - Finance and Investment Facilitation:
    - Signed a Memorandum of Understanding with PT Sarana Multi Infrastruktur (PT SMI), at their request, to co-design a multi-donor Trust Fund for green infrastructure. A requested prompted by the success of MENTARI’s VGF.

  - Sub-national Energy Planning and Inclusion:
    - Supported the East Nusa Tenggara government to develop its Provincial Energy Plan (RUED), embedding Gender Equality, Disability, and Social Inclusion (GEDSI) principles into energy planning.
    - Sustained operations of the 95kWp solar mini-grid in Sumba, now managed by a local BUMDesa, and used as a model for inclusive rural electrification.
    - Building on the success of the pilot initiatives in Mata Redi and Mata Woga, MENTARI has extended its support to 21 additional villages across Sumba Island to replicate the MENTARI model. These replication sites have received targeted assistance in the form of feasibility study development, operator training, and legal entity establishment. These efforts aim to strengthen local enterprises and enhance community capacity to manage clean energy systems effectively.

  - Stakeholder Engagement and Dialogue:
    - Partnered with a local NGO to establish Green Energy Transition Indonesia (GETI), which has created new dialogue platforms between the Indonesian government and development partners on energy transition.

The Government of Indonesia continues to value MENTARI’s support. This is demonstrated by MEMR’s acknowledgment and acceptance of the programme’s technical assistance and policy study recommendations. MEMR officials have also expressed appreciation for the strong working relationships developed over the past year with the programme staff, particularly the collaborative approach and responsiveness to their needs. Senior MEMR officials have even contacted senior BEJ staff directly to praise the programme and express their support for its future continuation.

Progress on recommendations from the previous AR.

There were nine recommendations in previous year’s Annual Review (AR), and eight have been completed.

Key recommendations that have been actioned include the approval of a BCA to extend programme delivery and spending, clarification of the Viability Gap Fund (VGF) project selection process, and updates to the programme’s logframe and KPI targets to reflect the revised end date. The programme team also completed a review of how each strand contributes to overall impact, though it concluded that a formal attribution methodology is not feasible at this stage due to the complex and interconnected nature of MENTARI’s interventions.

The one outstanding recommendation relates to an evaluation of the Brokerage Strand and VGF, which is currently in progress by NIRAS and expected to be completed by August 2025. This evaluation is anticipated to provide valuable insights into the effectiveness of the VGF mechanism and inform future programme design. But interviews took place with those evaluators and initial findings feature in this review.

Overall, the programme has made strong progress in addressing strategic, operational, and monitoring-related recommendations, positioning it well for a successful closeout and for informing the design of a potential MENTARI 2.

Major lessons and recommendations for the year ahead

The year under review marked a transitional phase for the MENTARI programme, shaped by a mix of internal and external factors. Externally, political changes in both the UK and Indonesia caused delays in several areas. Indonesia’s inconsistent support for the JETP led to delays or re-scoping of some activities. Meanwhile, a change in the UK government delayed the approval of a BCA, which had been recommended in the previous Annual Review to allow the programme to continue delivering beyond the commercial contract. This uncertainty affected early-year planning and financial decision-making. Internally, the delivery partner and the BEJ team acknowledged that most of the programme’s core milestones had already been achieved. As a result, the focus shifted to completing ongoing work, initiating evaluations, responding to urgent requests from the Government of Indonesia (GoI), and preparing for programme closure by July 2025. While the commercial contract is ending, the broader Business Case remains active until April 2026, requiring careful coordination during the wind-down period.

As a result of the BCA, the programme increased in value from £20,000,000 to £22,300,000 and added additional delivery partners for the first time: the Institute for Essential Services Reform (IESR) and the United Nations Office for Project Services (UNOPS). Both were engaged to support the JETP, but through distinct approaches. IESR focused on policy research and stakeholder engagement, while UNOPS will provide technical assistance on implementation of a just transition framework.

As both IESR and UNOPS only started their inception and/or activities within the last two quarters of the AR period, and the programme team is currently designing the successor programme, the recommendations of this AR will focus on future programming:

  - Design for flexibility and responsiveness: Consider using a mix of milestone-based and time-and-materials (T&M) contracts to accommodate both clearly defined deliverables and adaptive, demand-driven work. T&M could be applied to the policy reform aspects of the programme, while milestone could be applied to the rest.

  - Prioritise early and plan for closure: Establish clear priorities and budget allocations early in the programme cycle. Build in closure strategies, including handover plans, evaluation timelines, and compliance with GoI mechanisms (e.g. BAST – annual handover report and KAK - annual workplan).

  - Emphasise the co-delivery model and consider capacity: MENTARI is designed to be delivered by programme funded roles within BEJ and the delivery partner. The model functioned well but was not without challenges. Frequent changes in the BEJ team and short-notice requests from BEJ to the delivery partner created pressure on delivery timelines. But these requests were reasonable given they responded to a changing context or emerging opportunity. For instance, although the urgent requests linked to JETP delivery were challenging to manage, they were important to meet to advance a wider multinational effort. While the delivery partner remained responsive, clearer boundaries and escalation protocols would have helped manage expectations more effectively. The model remains valuable but would benefit from more structured roles and responsibilities in future programmes.

  - Seek improvements in the Brokerage strand: While the evaluation is yet to be finalised in the writing of this review, initial findings indicate there is not enough data on the VGF assessment to provide assurance that this model is optimal towards facilitating investment into Indonesian low-carbon energy projects. Working with Indonesia’s unofficial national development bank, PT SMI, has been positive, though linkages with other UK investments instruments (e.g. Mobilist, British International Investments, and UK Export Finance) would deliver more impact.

  - Seek improvements to how the demonstration project is sustainable beyond project closure: A separate assessment on this strand is ongoing but initial findings shows positive feedback on the 95kWp project in Sumba delivered by the programme. However, ensuring its self-sufficiency after the programme concludes has been a challenge. The BUMDes model is a great starting point to help create an economic model that can operate and maintain the infrastructure, but it is not perfect. Despite the challenges, the project is widely seen as impactful towards demonstrating models on sustainable rural electrification.

  - G&I has been adequately integrated across the programme, but there are ways to ensure this is sharper in future programming through governance and project clearance procedures in future MENTARI 2 structures.

Recommendations	Responsibilities	Support	Timelines
Adjust the Theory of Change and logical frameworks from all delivery partners to simplify the future Programme Closure Report.	PRO	Programme team	October 2025
Future programming to factor in evaluation of policy strand.	SRO	Policy Strand lead in BEJ	August 2025
BEJ Programme Team to find a way to sustain support to PT SMI after beyond July 2025 when the main delivery partner contract ends.	SRO/PRO	Brokerage Strand lead in BEJ	August 2025
Future programming to factor in evaluation of brokerage strand	SRO	Brokerage Strand lead in BEJ	August 2025
Programme team to consider alternative models to ensure the sustainability of a rural electrification site beyond programme closure. Factor this into design of future programming. Factor in evaluation findings.	SRO	Demonstration Strand lead in BEJ	August 2025
Future programming should factor in new GEDSI checklist and separate ICF GEDSI.	SRO	GEDSI focal point in BEJ	August 2025
Refresh the risk register to reflect closure of the main delivery partner’s activities in July 2025 and increasing activity from IESR and UNOPS	PRO	Programme MREL and Comms Officer	September 2025
Review UNOPS and IESR safeguarding standards to ensure compliance with FCDO standards.	PRO	Programme MREL and Comms Officer	September 2025
BEJ Programme Team to discuss ways of working with IESR to avoid delays in delivering GETI. Consider a monthly/quarterly SRO level meeting.	PRO	Programme team	August 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The MENTARI programme’s Theory of Change (ToC) for the 2024–2025 extension maintains its core objective of supporting Indonesia’s just and inclusive energy transition. The programme continues to focus on increasing access to reliable and affordable low-carbon energy – particularly for women and marginalised groups – and stimulating investment in high-quality renewable energy projects. These goals are pursued through five strands: Policy, Brokerage, Demonstration Projects, Collaboration, Capacity Building and Networking (CCBN), and Gender and Inclusion (G&I).

The ToC was refined for the extension period to reflect a shift from infrastructure delivery to policy influence, investment facilitation, and sustainability planning. This included a significant revision of the programme’s indicators: 36 were removed, 10 new ones introduced, and 8 revised for clarity and relevance. These changes ensure the monitoring framework better aligns with the programme’s evolving focus and implementation context.

At the impact level, the indicator tracking the number of additional households with access to low-carbon energy was removed due to data limitations. However, the indicator on renewable energy capacity additions was retained, with a target of 0.17 GW during the extension period. The impact indicator on investment value brokered was also retained, but increasing the target to £1.12 billion. PT SMI’s request to help design a Trust Fund, resources were shifted to accommodate that, leaving less resource for technical assistance and matchmaking.

At the outcome level, the indicator on improved policy and regulatory frameworks was revised to broaden its scope beyond “subsidiary” policies. The indicator on brokered renewable energy projects was retained, with a target of 20 new projects. In the demonstration strand, indicators on job creation and business support were removed, having been achieved in Phase 1. However, the indicator on household income increase remains, with a 5% target.

New intermediate outcomes and outputs were introduced to reflect the programme’s evolving priorities. These include mainstreaming the demonstration model, strengthening institutional capacity (e.g., BUMDes readiness), expanding knowledge dissemination (e.g., a Massive Open Online Course (MOOC) on HOMER Pro), and integrating G&I across all strands. The G&I strand now tracks participation of women and marginalised groups, the number of G&I sessions and technical assistance provided, and the production of G&I-focused studies.

Overall, the updated ToC reflects a more strategic and sustainability-focused approach, while maintaining MENTARI’s core objectives. It ensures the programme remains responsive to Indonesia’s energy transition needs and aligned with the UK’s climate and development priorities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains on track to deliver its intended outcomes and impact. Across the four main strands: Policy, Brokerage, Demonstration, and CCBN. MENTARI has contributed to tangible progress in Indonesia’s energy transition. The Policy strand has delivered high-impact reforms, including updates to Local Content Requirements (LCR) and hydrogen infrastructure guidelines. The Brokerage strand has facilitated over £927 million in investment and supported the ongoing development of a national Trust Fund with PT SMI, laying the groundwork for innovative and sustainable financing mechanisms. The Demonstration strand has showcased inclusive rural electrification models, with the Sumba mini-grid project now serving as a replicable blueprint for other regions. Meanwhile, the CCBN strand has strengthened institutional capacity and knowledge dissemination, including the launch of a HOMER (Hybrid Optimisation of Multiple Energy Resources) Pro MOOC and integration of GEDSI principles into regional energy planning. These achievements reflect the programme’s strategic shift from infrastructure delivery to policy influence and sustainability planning, ensuring long-term impact beyond the life of the commercial contract.

The year ahead sees the Palladium-led consortium stop activities by 31 July to prepare for contract conclusion by the end of September. Their remaining activities mainly relate to finalising technical advice, responding to short notice urgent requests from MEMR, finalising internally commissioned independent evaluations on its demonstration project and GEDSI implementation, and finalising a progress report on the PT SMI Trust Fund design. Between August-September, the focus will be on completing mandatory actions and producing documents to support the wider programme’s Programme Closure Report (PCR) in 2026.

This sees MENTARI mainly being delivered by IESR and UNOPS till the Business Case concludes in April 2026. The outputs from IESR’s GETI project and UNOPS’s study will require close monitoring and support. It is too early to tell if they are on track or off track as most of their activities during the scope of the AR period relate to setting-up the dialogues required to deliver the studies/reports expected from them.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Given Indonesia’s position as a top ten global greenhouse gas emitter and the UK government’s global interest to tackle climate change, a programme like this should exist. The programme should continue till its scheduled end. It has met or exceeded the output targets delivered by the Palladium-led consortium.
The IESR and UNOPS outputs are still in their early stages but are expected to conclude by April 2026.
Recommendations	Responsibilities	Support	Timelines
Adjust the Theory of Change and logical frameworks from all delivery partners to simplify the future Programme Closure Report.	PRO	Programme team	October 2025

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Policy Strand
Delivered via Commercial Contract
Output Title	GoI supported with recommendations/ TA on subsidiary regulation & effective implementation of RE policy/ regulation
Output number:		1	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	Down

Indicator(s)	Milestone(s) for this review	Progress
Number of study, proposal, guideline, and/or recommendations developed for MEMR	6	Achieved. There were eight study, proposal, guideline, and/or recommendations developed for MEMR as below. / 2023 Hybrid technologies generation costs / 2024 Single technologies generation costs / 2024 Hybrid technologies generation costs including recalculated generation costs for hybrids of PV+DG+BESS and PV+BESS / DIM for Ministerial Regulation Bills PLT Hibrida / Guildeline for Hydrogen Refueling Station has been finalised and currently under prepress. / Ceiling price hybrid 2025 (laporan tentang harga pembangkit hibrida -atas permintaan Dir. Aneka EBT) / KBLI report / Review of Aneka EBT organisation's study (Review Naskah Kajian Pemekaran Direktorat Aneka EBT)

Output Title	Guidelines, TA, and training identification on planning, procurement, & contracting provided to PLN
Output number:		5		Output Score:		A
Impact weighting (%):		5		Weighting revised since last AR?		Down
Indicator(s)			Milestone(s) for this review		Progress
Number of TA and/or capacity building provided for PLN			1		Achieved. There was a Homer Pro Training of Trainers Module and Facilitation provided to PLN

Output Title	Support on UK Energy Transition Policy Dialogue provided
Output number:		6		Output Score:		A++
Impact weighting (%):		15		Weighting revised since last AR?		N/A
Indicator(s)			Milestone(s) for this review		Progress
Number of study, proposal, guideline, and/or recommendations developed for JETP Secretariat			2		Achieved. There were four study, proposal, guideline, and/or recommendations developed for JETP Secretariat as below. / LCR 3.0c: The Economic Impacts of Solar PV Electricity Development in Indonesia / LCR 3.0d1: Social Accounting Matrix (SAM) / LCR 3.0d2: Computable General Equilibrium (CGE) / Review of JETP CIPP

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Policy strand’s outputs is A++, as the planned milestones have exceeded expectations under this strand. This strand aims to strengthen Indonesia’s low-carbon energy policy environment by supporting the development, improvement, and implementation of national and subnational regulations, planning instruments, and institutional frameworks. It focuses on delivering technical studies, regulatory inputs, and economic modelling tools that inform reforms in areas such as local content requirements, hydrogen infrastructure, renewable energy power purchase agreements, and hybrid energy pricing. Ultimately, the strand contributes to a more enabling environment for clean energy investment by enhancing regulatory clarity, supporting institutional restructuring, and aligning Indonesia’s energy transition with JETP goals.

This year, activities by the strand broadly covered the following:
- Local Content Requirement (LCR) regulatory reform: MENTARI advanced Indonesia’s local content policy by delivering macroeconomic modelling tools (SAM - Social Accounting Matrix and CGE - Computable General Equilibrium) and completing the LCR study series. These informed the update of Chapter 8.1 of the JETP CIPP 2025 and supported MEMR and the Ministry of Industry in aligning LCR policies with investment and industrial development goals, particularly in the solar PV sector. MENTARI’s studies helped revise LCR thresholds, which were previously seen as barriers to renewable energy (RE) project development.
- Hydrogen Sector Regulatory Development: The programme finalised two key regulatory documents: the Standard Business Classification (KBLI) for hydrogen and the Technical and Environmental Guidelines for Hydrogen Refuelling Stations. Developed through field visits, stakeholder consultations, and public dissemination, these documents provide regulatory clarity for early hydrogen infrastructure projects and are now being used by MEMR and BPS.
- EBTKE Organisation Restructure: MENTARI supported the institutional restructuring of MEMR’s Directorate of Various New and Renewable Energy (Aneka EBT) and expanded this to a broader review of the Directorate General of New, Renewable Energy, and Energy Conservation (EBTKE). As a result, EBTKE adopted MENTARI’s recommendation by splitting Aneka EBT Directorate into two: Directorate of Renewable Energy and Directorate of New Energy, enabling more focused and effective governance of Indonesia’s energy transition. The work included reviewing academic justifications, conducting stakeholder interviews, and preparing recommendations to improve organisational effectiveness and responsiveness.
- Renewable Energy Power Purchase Agreement Regulation: MENTARI contributed to the development of a new ministerial regulation on renewable energy PPAs by supporting the drafting of the DIM (Daftar Inventarisasi Masalah/ Problem Inventory List) and academic paper. The regulation aims to standardise contractual terms, enhance legal certainty, and improve the bankability of renewable energy projects, particularly for variable and hybrid systems.
- Hybrid Technology Regulation: The strand provided technical assistance to MEMR in revising ceiling prices for hybrid technologies under Presidential Regulation 112/2022. This included generation cost modelling, HOMER simulations, and the development of SOPs for annual tariff reviews, alongside support for a draft ministerial regulation on hybrid power plants.
Not only were these outputs double the value expected from the strand, but their qualitative impact is also significant – particularly the LCR and hydrogen outcomes. These activities were well-received and considered valuable by Indonesian counterparts, though some timing issues were noted. The programme’s collaborative and responsive approach contributed to its effectiveness.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The Indonesian government transition following the Presidential inauguration in October 2024 introduced significant institutional changes, including the abolishment of the Coordinating Ministry of Maritime Affairs and Investment, formerly responsible for JETP coordination, and the transfer of this mandate to the Coordinating Ministry of Economic Affairs (CMEA), which took some time to formalise until March 2025. This shift, along with internal restructuring within MEMR, was not originally anticipated at the start of the year but was taken on in response to evolving government priorities and requests from MEMR. As a result, the Policy Strand expanded its scope to support these institutional reforms, while also delivering major workstreams on LCR reform, hydrogen sector regulation, hybrid technology pricing, and renewable energy PPA frameworks.

Recommendations	Responsibilities	Support	Timelines
Future programming to factor in evaluation of policy strand.	SRO	Policy Strand lead in BEJ	August 2025

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Considering the budget ceiling issue in the previous year, which limited the ability to expand the delivery partner contract under existing procurement rules, the Policy Strand adopted a more flexible delivery model to meet continued demand from MEMR and JETP stakeholders. This included channelling technical assistance through an Accountable Grant to IESR for work on the JETP CIPP implementation and on the green hydrogen market establishment, as well as to UNOPS for work on the implementation of the “just” element of the JETP. This approach enabled the programme to remain responsive to government priorities while operating within financial constraints. It also offers a potential delivery model for future programming, with lessons around coordination, accountability, and delivery efficiency to be further assessed in the programme completion report. Future programming should maintain good practices highlighted by the main counterpart including technical depth and responsiveness, and to improve alignment with evolving government priorities.

Brokerage Strand
Output Title	Innovative financing mechanism/ better de-risking schemes supported (includes enabling access to these facilities) or developed
Output number:		1	Output Score:		N/A
Impact weighting (%):		N/A	Weighting revised since last AR?		N/A
Indicator(s)				Milestone(s) for this review		Progress
Number of new and/or existing financial schemes/facilities/mechanisms (i.e. blended finance facility or other de-risking solutions) proposed or supported				0		Partially achieved. Trust Fund has yet to be established but buy in from PT SMI was secured on positive discussion was ongoing. MoU to support was signed in October 2024.

Output Title	Extension of marketing and DD service for existing public and private sector
Output number:		2	Output Score:			A+
Impact weighting (%):		10	Weighting revised since last AR?			N/A
Indicator(s)				Milestone(s) for this review	Progress
Number of marketing and due diligence proposal submitted to financial institution				2	Achieved. There were three SEP (PT Sejahtera Energi Persada) project documents submitted to potential investors. / Submitted SEP project documents to potential investor Nol Karbon. / Submitted SEP project documents to potential investor Inecosolar. / Submitted O&M grant proposal of PV Katingan project to GEAPP.

Output Title	Pipeline of quality low carbon energy projects (in “support mandate”)
Output number:		4	Output Score:			N/A
Impact weighting (%):		N/A	Weighting revised since last AR?			Down
Indicator(s)				Milestone(s) for this review	Progress
Size and value of probability weighted pipeline for on-grid and off-grid clean energy projects (cumulative)				0	No specific target was set for this review, but monitoring of the project pipeline remains continue. During the annual review period, resources were reallocated to support PT SMI in the development of a Trust Fund, which limited direct activity under this output. Nevertheless, MENTARI’s technical assistance to PLN’s Diesel Replacement Programme (DRP 2) remains relevant to this indicator, and potential new support for RE projects is under ongoing exploration beyond March 2025, as these contribute to the pipeline of quality low-carbon energy projects. However, the value of DRP 2 and these potential supports has yet to be finalised and remains commercially sensitive at this stage.

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Brokerage strand’s outputs is A+, as the planned milestones have either met or moderately exceeded expectations for outputs under this strand. This strand aims to unlock private sector investment in low-carbon energy projects by bridging the gap between project developers and financiers. It does this by designing innovative financing mechanisms, technical assistance, and facilitating matchmaking to help early-stage renewable energy projects reach bankability. Ultimately, it supports the development of a robust pipeline of clean energy projects and strengthens Indonesia’s climate finance ecosystem.

Activities by the strand this year broadly covered the following:

- Trust Fund Development with PT SMI: MENTARI was requested by PT SMI to co-design a national Trust Fund to pool donor resources for green infrastructure, building on lessons from the VGF. The work is ongoing and includes legal advisory support, stakeholder consultations, and drafting operational frameworks.
- Technical Assistance & Due Diligence: The programme provided tailored support to early-stage renewable energy projects (e.g. solar PV, hydrogen, biomass, RDF - Refuse-Derived Fuel), helping them become investment-ready. This included site visits, feasibility assessments, and project structuring. The sites supported by MENTARI are at various stages, some nearing financial close, some did not go beyond due diligence, while some are already operational but not officially inaugurated yet. Note that the support provided by MENTARI is only limited to the provision of TA to the developer. The programme has no control over the project’s ability to secure investment.
- Support to PLN’s Diesel Replacement Programme (DRP): Contributed technical expertise on tariff formulation, hybrid system design, and bid preparation for DRP Phases 1 and 2, while documenting lessons for future implementation. Although most of the programme is aligned to JETP interests, the DRP assistance directly supports a JETP objective.
- Identifying final VGF projects: MENTARI sought to identify a final project to disburse the remaining £1.6 million of the VGF, but this effort was ultimately unsuccessful. While several potential projects were presented to BEJ for consideration, they were either non-compliant with HMG’s Fossil Fuel Policy or lacked sufficient additionality to justify grant support. Although more projects could have been proposed, many were already bankable without subsidy, or the available grant amount was too small to meaningfully improve their bankability. This outcome reflects both the narrow eligibility criteria set by the BEJ programme team and the broader challenge of finding small-scale renewable energy projects in Indonesia that genuinely require VGF support.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Supporting PT SMI design a multi-donor Trust Fund is the major additional work this strand took on for the AR period. The work is still ongoing and unlikely to be completed by the time MENTARI ends in April 2026.

An independent evaluation of this strand was being conducted by NIRAS at the time of the AR. The full report is expected to be published by August 2025, but initial findings showed the following:

- Feedback from beneficiaries of the quality of TA provided on pre-feasibility and feasibility studies for individual projects was mixed. There were instances where the beneficiary felt that the TA should have been designed with an “investor lens” rather than a developer perspective on proving the technology.
- MEMR want to be more involved in project selection of this strand to ensure projects supported by the programme align with their priorities.
- The VGF was a novel instrument for small-scale RE with strong leverage ratios, but success was concentrated in one transaction that packaged three mini-hydro dams. The design was also a constraint when considering the inability to spend the full fund. There were fair reasons for not spending the full amount, though working beyond PT SMI’s pipeline may have improved the fund’s disbursement chances.
- The matchmaking facility provided by this strand was broadly limited to introductions between investors and developers. There was no follow-up action but there was also no incentive from both parties to involve MENTARI after the introduction.
Despite these initial observations, the evaluators still considered the strand’s overall outputs to be positive and impactful. More in-depth analysis of the design of the brokerage strand and the VGF will be included in the project completion report.

Recommendations	Responsibilities	Support	Timelines
BEJ Programme Team to find a way to sustain support to PT SMI after beyond July 2025 when the main delivery partner contract ends.	SRO/PRO	Brokerage Strand lead in BEJ	August 2025
Future programming to factor in evaluation of brokerage strand	PRO	Brokerage Strand lead in BEJ	August 2025

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

One out of two of the recommendations from the previous AR have been completed. The recommendation to codify the criteria for VGF project selection involved identifying an annex not previously seen addresses most of this requirement. The EQUALS linked evaluation of this strand is ongoing, and NIRAS is due to complete it by August 2025.

Demonstration Pilot Project Strand
Output Title	Feasibility studies (supply + demand) & business cases (including technical, economic & social potential of low carbon energy) developed
Output number:			1	Output Score:		A+
Impact weighting (%):			5	Weighting revised since last AR?		Down
Indicator(s)		Milestone(s) for this review			Progress
Number of feasibility studies and business cases supported		10			Achieved. There were 21 FS supported. / MoV: Acknowledgement letter from Dinas ESDM, East Nusa Tenggara Province. Buy-in from Indonesian officials was greater than anticipated.

Output Title	Inclusive off-grid development models (including training on low carbon energy business models, O&M, PuE, and GESI potential) provided to the community, TVET providers, local FIs, Local Government, BUMDes, BLU and O&M providers
Output number:		3	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of capacity building on low carbon energy business models (Technical & non-Technical)	7	Achieved. There are 13 capacity building provided. / Support Women Champions Advocacy in Mata Redi & Mata Woga Village (28-29 Jun 2024) / Discussion on Governance and Handover of Village Assets from Village Government to BUM Des (Jul 11, 2024) / Socialization of PerDes Iuran and Monitoring & Preparation of BUMDesa Work Plan Development with POKJA and Village Government (23-27 Jul 2024) / BUMDesa mangement and finance mentoring (Q2-Q3) / Mentoring SOP for PV business unit (Q2-Q4) / Monitoring and Coaching Clinic for Villages Receiving PLTS DAK Grant 2023 and 2024 (2-5 Oct 2024) / Monitoring and evaluation of the implementation of Desa Ramah Perempuan dan Peduli Anak (DRPPPA) (5-7 Nov 2024) / Training of Trainers sessions with BLK Don Bosco for instructors MENTARI Annual Report 2024-2025 | 67 Indicator No. Indicator Statement Apr-Mar Target (Y5) Unit Apr-Mar Achievement (Y5) Description from Don Bosco Tech ASEAN at the BLK Don Bosco and Mata Redi (25-29 Nov 2024) / Electricity Course at Don Bosco Vocational Training Center (11 Nov – 11 Dec 2024). / Introductory Training on K2/K3 for the PLTS Operator (13-15 Mar 2025) / Technical O&M SOP Training and Refinement (26-27 Mar 2025) / Pra-Musyawarah Desa with BUMDesa, operator, village government, and women champion, to identify operational problem of the BUMDesa and its business unit (26 Feb 2025) / Progress monitoring based on the Women Champions' latest action plans provided support for their advocacy in Mata Redi and Mata Woga (24-25 Mar 2025)

Output Title	Knowledge about applying small-scale renewable energy for electrifying off-grid produced
Output number:			4	Output Score:		A+
Impact weighting (%):			5	Weighting revised since last AR?		Down
Indicator(s)		Milestone(s) for this review			Progress
Number of knowledge products about small-scale off grid produced		7			Achieved. There were nine knowledge products produced. / Blueprint rural electrification / GALS Video / SOP Management of BUMDesa / Insights on MENTARI’s Support for the Regional Energy Plan Document (RUED) Process in Nusa Tenggara Timur / RUED Chapter by Chapter Summary, / GEDSI Integration Process, / GEDSI Integration on RUED Theory of Change / SOP Technical O&M PLTS for BUMDesa / BUMD Readiness Study: Due Diligence of BUMD PT. Flobamor

Output Title	Provide TA and workshop to strengthen skills on inclusive regional energy planning
Output number:			6	Output Score:		A+
Impact weighting (%):			10	Weighting revised since last AR?		N/A
Indicator(s)		Milestone(s) for this review			Progress
Number of TA and workshops provided to regional government		5			Achieved. There were total 22 combination of TAs and workshops delivered. Buy-in from Indonesian officials was greater than anticipated with request for more workshops than planned.

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Demonstration strand’s outputs is A+ with strand outputs that have moderately exceeded expectations. This strand aims to showcase inclusive, off-grid renewable energy models that support local economic development and poverty reduction. It focuses on building sustainable, community-owned energy systems while strengthening local institutions, promoting productive use of energy, and embedding gender and social inclusion. Ultimately, the strand serves as a replicable model for scaling up clean energy access in underserved regions across Indonesia. The 95kWp solar and battery energy storage system has been active for more than two years.

This year, the Demonstration Project Strand focused on sustaining the Sumba solar project through technical mentoring, productive energy use (PUE), and formal handover to local institutions. The strand also worked to embed gender and inclusion into village governance and regional energy planning. These efforts culminated in the development of East Nusa Tenggara’s (NTT) inclusive Rencana Umum Energi Daerah/ Regional Energy Master Plan (RUED) and the production of replicable knowledge products to scale community-based renewable energy models. Other activities include:

- Sustaining the Mata Redi Mini-Grid: MENTARI formalised the handover of the solar PV mini-grid and productive use assets to BUMDesa Hali Dewa, establishing it as a Centre of Excellence in partnership with BLK Don Bosco. This included the development and validation of O&M SOPs, technical troubleshooting guidance, and K2/K3 safety training to ensure long-term operational sustainability.
- Strengthening Local Business and Energy Use: The programme provided intensive mentoring to BUMDesa on governance, financial management, and productive energy use. This led to improved candlenut processing operations, market engagement, and participation in national certification programmes. Despite challenges like low bill collection and governance risks, efforts were made to improve transparency and diversify income streams.
- GEDSI: MENTARI empowered 26 women champions in Mata Redi and Mata Woga, integrating their advocacy into village planning and governance. GESI principles were embedded into local and provincial energy planning, supported by GALS training, DRPPA monitoring, and public dissemination events, positioning Sumba as a model for inclusive rural electrification.
- Regional Energy Planning and Replication (RUED): The delivery partner supported the development and handover of the East Nusa Tenggara RUED 2025–2034, embedding GEDSI principles and aligning with national energy goals. Complementary efforts included DAK coaching clinics, KSO model development for BUMDesa-led RE projects, and the production of nine knowledge products to support broader replication of inclusive energy models.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The independent evaluation of this strand by MDF will provide further lessons learned. Although it is ongoing, initial findings show positive feedback on the 95kWp project in Sumba delivered by the programme. But ensuring its self-sufficiency after the programme concludes has been a challenge.

The BUMDes model is a great starting point to identify an economic arrangement that can fund operations and maintenance of the infrastructure, but it is not perfect. Socio-economic dynamics in the village make securing funds for O&M challenging. Fortunately, the Indonesian Ministry for Villages will contribute towards O&M funding, but this should gradually be funded by the community over time. Despite the challenges, the project is widely seen as impactful towards demonstrating models on sustainable rural electrification.

Recommendations	Responsibilities	Support	Timelines
Programme team to consider alternative models to ensure the sustainability of a rural electrification site beyond programme closure. Factor this into design of future programming. Factor in evaluation findings.	SRO	Demonstration Strand lead in BEJ	August 2025

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous Annual Review recommended refocusing the remainder of this strand towards scaling up lessons learned and replicating this model across other localities. The achievements of this strand this year shows the recommendation has been completed.

Collaboration, Capacity Building & Networking (CCBN) Strand
Output Title	Capacity building and knowledge exchange, including focus on opportunities for women and marginalised groups, provided to inter/national academic/TVET, and relevant stakeholders (including MEMR, PPSDM, PLN) in low carbon energy sector
Output number:		1	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of international and Indonesian academic or training institutions, civil society organisation, and relevant stakeholders (including MEMR, PPSDM, PLN) receiving programme matchmaking and/or knowledge sharing support	3	Achieved. There were 13 total of programme matchmaking and or knowledge sharing support provided. / Increase access of 13 MENTARI publications through partnership with US Library of Congress / 4 MENTARI knowledge products through partnership with KemenPPPA / Voice for Just Climate Action (VCA) / Indonesia Just Energy Transition (IJET). / PERTAMINA NRE / Pusdiklat of PT PLN (Persero) / PLN Talenta / Undana University Library / University of Indonesia Library / Universitas Muhammadiyah Gorontalo / National Library of Indonesia / Universitas Gadjah Mada Library and Archives / Library of UPN Veteran Jakarta
Number of activities organised by MENTARI for supporting Inter/national academic, TVET, and relevant stakeholders (incl. MEMR, PPSDM, PLN) focusing on low carbon energy in Indonesia	2	Achieved. There were three activities organised. / ToT HOMER Pro conducted / MENTARI Goes To Campus - Nusa Cendana University, Kupang / MENTARI Goes To Campus - Gadjah Mada University, Yogyakarta
% of people reported improved knowledge regarding low carbon energy after participating in MENTARI capacity building events	70%	Achieved. 99.7% of participants reported improved knowledge from MENTARI’s capacity building activities. Regular feedback on satisfaction, relevance, and quality was collected and used to refine programme design. A key example is the HOMER Pro training, which evolved based on participant input, (e.g. adding case studies and restructuring materials) and was eventually launched as a MOOC by 2025, expanding access to hybrid energy modelling skills nationwide.
MOOC and Homer Pro is established	1	Achieved. Workshop on final review of the MOOC Homer Pro has been conducted on September 25th, 2024. The handover of the MOOC final product have been completed formally on November 13th, 2024

Output Title	Promoted knowledge sharing and facilitated partnership
Output number:		3	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of events (capacity building, awareness raising, knowledge sharing, etc.) organised and/or facilitated by CCBN strand.	16	Achieved. There were total 18 events organised and facilitated.
Programme closing (MENTARI Day) event conducted	0	Achieved. The event took place on 3 July 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the CCBN strand is A+. The programme has moderately exceeded expectations of all planned milestones for outputs under this strand. The strand focuses on strengthening knowledge, skills, and institutional partnerships to support the growth of renewable energy. It aims to build technical capacity, promote digital learning, and foster collaboration among government agencies, academia, and civil society.

Key achievements under the Strand include the successful delivery of 18 events such as workshops, public consultations, and university outreach, which enhanced collaboration and knowledge exchange. Notably, the “MENTARI Goes to Campus” series at Universitas Nusa Cendana and Universitas Gadjah Mada engaged over 350 students, raising awareness and interest in renewable energy among youth. Part of the reason why this strand exceeded expectations is that unplanned requests for knowledge sharing were made (e.g. US Library of Congress), which contributed towards exceeding expectations for this output. The request indicates the programmes’ positive reputation.

The programme also supported regional energy planning through RUED consultations and strengthened technical capacity via a MOOC and Training of Trainers on HOMER Pro, while expanding the reach of knowledge products through libraries, online platforms, and media engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe revision for the CCBN strand introduces several key updates. Some indicators were reworded to reflect broader engagement, such as including civil society organisations alongside academic and government institutions. New indicators were added to track outcomes like improved participant knowledge, the establishment of the HOMER Pro MOOC, and the MENTARI Day closing event delivered in July 2025. Meanwhile, several older indicators – such as those related to technical vocation training, diagnostics, communication products, and formal partnerships – were removed. Rationale was either because they were already achieved or no longer relevant for the remainder of the programme.

Despite the logframe changes, the strand itself broadly delivered activities that were like previous years.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Most of the previous AR’s recommendations have been addressed. The logframe has been refreshed and became more aligned with the Business Case. The donor mapping has not been fully completed, but the programme team is aware that some of the programme’s work involved coordination with other donors (e.g. US and New Zealand). The programme team is drafting the Business Case for a future programme and has adopted the previous recommendation to amalgamate this strand to other strands.

Gender and Inclusion Strand
Output Title	Programme demonstrates G&I integration across (i) MENTARI programme intervention design (internal), (ii) support to relevant stakeholders (internal/external), and (iii) knowledge sharing (internal/external).
Output number:		1	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Percentage of women and/or marginalised groups involved in MENTARI activities (facilitated discussions, working group meeting, workshop, training, etc.)	30%	Achieved. Percentage was 42% / A total of 3,118 participants have been recorded in the MENTARI activities since Q1, with 1,309 of them are women.
Number of documents produced (study, mapping, and/or analysis) on gender and inclusion approach implemented within MENTARI program.	2	Achieved. There were two documents produced on G&I approach implemented in MENTARI programme. / G&I plan for integrating GEDSI into the RUED / Report on G&I Reflection
Number of G&I sessions integrated across strands activities and events.	2	Achieved. There were seven G&I sessions across strands activities and events delivered. / G&I Session in RUED Theory of Change development / Gender mainstreaming session in Local Development in Community Based RE during ICW MENTARI seminar. / GALS Session during ICW event. / Co-facilitation of the FGD as a part of DRPPA monitoring in Mata Redi / CSO Event in Kupang / MENTARI Goes To Campus, Nusa Cendana University / MENTARI Goes To Campus, Gadjah Mada University
Number of G&I TA support provided to programme stakeholders (internal/external)	1	Achieved. There were three G&I TA support provided to programme stakeholders. / GEDSI integration on RUED NTT / GEDSI Indicator for ToC of RUED / TA for DRPPA Monitoring Activity

Briefly describe the output’s activities and provide supporting narrative for the score.

The overall score for the Gender and Inclusion (G&I) strand is A+ with the outputs have moderately exceeded expectation. This G&I strand aims to ensure that Indonesia’s energy transition is inclusive, equitable, and responsive to the needs of women and marginalised groups. It focuses on mainstreaming GEDSI principles across policy, demonstration, and capacity-building workstreams, while also supporting women-led advocacy, inclusive planning, and national engagement. Ultimately, the strand contributes to a just energy transition by amplifying community voices, strengthening institutional awareness, and embedding inclusive practices into both local governance and national energy frameworks. The strand, led by HIVOS, continued to play a central role in embedding GEDSI principles into programme design, stakeholder engagement, and knowledge dissemination.

Key achievements include 42% participation of women and/or marginalised groups across 3,118 programme participants, well above the 30% milestone. Seven G&I sessions were integrated into major events, including RUED Theory of Change development, ICW (Indonesia Climate Week) MENTARI seminars, Sumba events and university outreach. Three technical assistance initiatives were delivered: GEDSI integration into the RUED NTT, development of GEDSI indicators, and TA for DRPPA (Women-Friendly and Child-Caring Village monitoring. Two strategic documents were produced: a G&I integration plan for RUED and a G&I reflection report.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While the Demonstration strand continues to be the most visible platform for G&I outcomes, the strand has made efforts to capture G&I outcomes beyond the Demonstration strand, particularly in Brokerage strand through the initiation of a gender lens analysis in low-carbon energy financing, and in CCBN strand through campus outreach. Policy strand also has integrated GEDSI into the PPA and hybrid regulation, hydrogen refuelling station study, and New Paradigm paper to ensure safeguards for marginalised groups, compliance with GEDSI standards, and GEDSI-ready procurement and bankability. These efforts reflect a broader commitment to embedding GEDSI principles across all strands, ensuring inclusive participation and benefit-sharing in both policy and practice.

As a forward look, two key knowledge products are expected to be completed: (1) the G&I Blueprint Document on Low Carbon Energy in Indonesia, and (2) a dedicated analysis on gender and inclusion within innovative financing for low-carbon energy projects. These outputs aim to inform future programming and investment frameworks, ensuring that G&I considerations are embedded from the outset.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Although all three VGF-supported projects have been completed, no G&I outcomes were documented, reflecting a missed opportunity to apply gender-responsive monitoring similar to the Demonstration strand. Likewise, the recommendation to include “Environment” in the output statement and introduce a CO₂ emissions reduction indicator has not yet been actioned. These gaps highlight the need for earlier integration of G&I and environmental considerations into project design and monitoring frameworks, which should be addressed in future programming.

Future iterations of MENTARI should consider a dedicated budget for G&I mainstreaming. A dedicated G&I Manager is already part of the delivery partner team, but G&I awareness within the delivery partner team has fluctuated over the programme’s lifetime given staff turnover. Having G&I focal point function within the existing team in each strand could be beneficial. This would strengthen the G&I awareness of the different strand teams to ensure they factor in G&I with their work.

Recommendations	Responsibilities	Support	Timelines
Future programming should factor in new GEDSI checklist and separate ICF GEDSI.	SRO	GEDSI focal point in BEJ	August 2025

Green Energy Transition Indonesia (GETI)
Briefly describe the output’s activities and provide supporting narrative for the score.

This is an additional delivery partner supported by BEJ through an accountable grant to deliver activities that align with the wider MENTARI programme and its ToC – particularly the policy indicators. Its outputs broadly fall into two strands:

- Implementing the Just Energy Transition Partnership through high-level dialogues and studies
- Establishing a green hydrogen market through technical studies
The outputs have not been scored this year as IESR’s activities during the AR period were still mostly in inception phase. Some activities (e.g. dialogues and initiation of studies) took place but too early to score at this stage.

Main noteworthy activity that occurred during the period is establishing a new dialogue on energy transition to facilitate exchanges between development partners and the Indonesian government. Initial meetings have focused on shaping the group’s objectives. Although formal metrics for this project are yet to finalise, anecdotal feedback from participants have flagged it to be a useful format and demonstrates the UK taking initiative on energy transition coordination with likeminded development partners.

GETI’s outputs will be reviewed more closely in the PCR next year, but a check-in around Q2 FY 2025-26 will be done.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

UNOPS implementation of JETP Standard 9
Briefly describe the output’s activities and provide supporting narrative for the score.

This project was initiated at the request of the Government of Indonesia (GoI) to the JETP Secretariat to support the implementation of the “just” element of the JETP. The primary aim of this intervention is to provide technical and policy support to operationalise Indonesia’s Just Transition commitments, particularly through piloting the application of Standard 9 (S9) – a framework the Indonesian Ministry of National Development and Planning that has not yet been implemented in Indonesia.

The intervention focuses on conducting studies that explore how S9 can be applied. This includes piloting the framework at existing energy sites and assessing how future projects could integrate just transition principles from the outset. The outputs will include detailed research and analysis on the implementation of S9, lessons learned from pilot sites, and recommendations for scaling the framework across other locations. These findings will be shared with stakeholders and used to inform future policy and project design.

The outputs have not been scored this year as UNOPS only commenced work in March 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

## D: VALUE FOR MONEY

Economy: MENTARI has continued to deliver strong economy by leveraging in-house expertise, local partnerships, and cost-sharing mechanisms. The programme reduced reliance on external consultants by collaborating with universities and government institutions, such as PPSDM KEBTKE and BLK Don Bosco, to deliver training and dissemination events. Office and accommodation costs were kept low, representing only 1.88% of total programme spend. Staff fee rates remained competitive, with national long-term staff averaging £98/day and international short-term experts at £480/day, aligning with industry benchmarks. These measures ensured high-quality delivery while maintaining cost discipline.

Efficiency: The programme demonstrated high efficiency through cross-strand collaboration and multi-purpose activities. For example, the HOMER Pro Training of Trainers and MOOC development were jointly delivered by the Policy and CCBN strands, resulting in a scalable, institutionalised training tool now hosted by PPSDM KEBTKE. MENTARI also embedded G&I sessions into broader events, reducing the need for standalone activities. The average cost per participant for training and events was £53.8, and the average cost per event was £5,443.6. The brokerage strand achieved a value of £972.8 brokered per £1 spent, and the average cost per project brokered (excluding DRP and DAK) was £29,777.7, reflecting strong returns on investment. (Note: The brokerage VfM figures are based on a complex methodology that accounts for the diverse nature of support provided to projects at varying stages of maturity and complexity. In some cases, the full value of these projects has yet to be realised or verified.)

Effectiveness: MENTARI delivered effectively across all strands. Key achievements include 12 policy outputs, 22 technical assistance initiatives to East Nusa Tenggara, 9 knowledge products from the demonstration project, and 31 training and knowledge-sharing sessions. The programme also facilitated 3 matchmaking events and supported the development of a renewable energy Trust Fund framework with PT SMI. The HOMER Pro MOOC was successfully handed over to PPSDM KEBTKE, and the RUED for East Nusa Tenggara was finalised and handed over to the Governor. These outcomes demonstrate the programme’s ability to adapt and deliver results aligned with Indonesia’s energy transition priorities.

Equity: Gender and Inclusion (G&I) remained central to MENTARI’s approach. Women represented 42% of participants across all activities, and G&I sessions were embedded in seven major events. Women champions from Mata Redi played a visible role in national forums, and G&I principles were integrated into the RUED and DRPPA pilots. The programme also produced two G&I knowledge products and provided three technical assistance initiatives focused on inclusion. These efforts ensured that MENTARI’s interventions were not only inclusive but also contributed to systemic change in energy governance.

Assessment of whether the programme continues to represent value for money
MENTARI continues to represent strong value for money. It has delivered impactful, inclusive, and sustainable outcomes with a modest budget, while maintaining flexibility and responsiveness to GoI priorities. The programme’s integrated approach, cost-effective delivery, and strategic partnerships have ensured that resources are used efficiently and equitably to support Indonesia’s low-carbon energy transition.

E: RISK

The programme currently has 28 active risks recorded on the Aid Management Platform. All risks remain within the overall risk appetite for BEJ. Risk is monitored on a quarterly basis, both internally by the programme team and a separate session with the delivery partner. Fortnightly catch-ups between the PRO and the delivery partner’s programme manager also occur, which is a forum to raise and discuss risks.

Strategy and Context risks include loss of political commitment to reform, weak government capacity and coordination, decentralisation challenges, unsupportive regulatory frameworks, and tensions within the JETP. This is managed at a portfolio and embassy level, utilising our political access and influence to ensure continued government support. BEJ, have also re-established the FIRE dialogue format (Friends of Indonesia Renewable Energy) for donor coordination in the energy sector, using the IESR component of the Mentari programme to facilitate dialogues and information sharing. This helps broaden donor coordination beyond existing structures (e.g. JETP) to help alignment and avoid duplication of efforts. There are minor risks of duplication with these two formats, but FIRE is still in its early days and was limited to development donors during the review period. Additional risks include corruption, security incidents, and reputational impacts from UK policy shifts or limited visibility of UK support. The residual risk for these ranges from minor to moderate. The risk register has been updated to reflect implications from the UK general election and anticipates further updates following the formation of the new Indonesian cabinet.

Policy and Programme Delivery risks include weak delivery partner performance, limited access to key government stakeholders, uncertainty in ODA budget allocations, challenges in securing external funding for brokerage projects, and finding a final VGF to financially support. Other risks include inappropriate technology or delivery models, weak MREL systems, disputes with delivery partners, and currency fluctuations. These risks are being addressed through regular coordination between the delivery partner and BEJ, including fortnightly meetings, adaptive planning, financial scenario planning, contingency plans for non-disbursal of VGF, and strengthened oversight mechanisms.

Reputational risks to MENTARI include potential mismanagement of funds, safeguarding failures, and perceptions of UK support for coal or insufficient climate ambition. These risks are mitigated through rigorous due diligence, financial audits, inclusive programme design, and proactive communications. Residual risk levels are assessed as minor to moderate.

Financial and Fiduciary risks relate to fraud or misuse of funds by delivery partners. These are mitigated through strong financial controls, open-book accounting, and audit mechanisms. The residual risk is moderate and remains within BEJ’s risk appetite.

Safeguarding risks focus on the programme’s ability to deliver gender and inclusion outcomes and uphold international environmental and social standards. These are mitigated through inclusive design, gender-disaggregated monitoring, and whistleblowing mechanisms. The residual risk is moderate. Relevant delivery partners attended a Safeguarding awareness session hosted by BEJ during the review period.

People risks include limited availability of qualified staff within BEJ and the delivery partner, and the challenge of balancing programme and non-programme responsibilities. These are mitigated through prioritisation exercises, staffing reviews, and cross-embassy coordination. Residual risk levels range from minor to moderate.

It is recommended that the programme team refresh the risk register to reflect closure of the main delivery partner’s activities in July 2025 and increasing activity from IESR and UNOPS till the remainder of the programme. If there were any activities handed over by Palladium to either two, the programme team is recommended to judge the latter’s ability to deliver it.

Recommendations	Responsibilities	Support	Timelines
Refresh the risk register to reflect closure of the main delivery partner’s activities in July 2025 and increasing activity from IESR and UNOPS, including any handed-over activities by Palladium.	PRO	Programme MREL and Comms Officer	September 2025
Review UNOPS and IESR safeguarding standards to ensure compliance with FCDO standards.	PRO	Programme MREL and Comms Officer	September 2025

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery and Performance
The overall performance of the MENTARI programme in 2024-25 was strong, with the main commercial delivery partner delivering to expectations and started winding down activities. The programme maintained momentum across policy, brokerage, demonstration, and capacity-building activities, despite some external challenges (e.g. political changes in Indonesia). Palladium recognised that their delivery was more streamlined this year with budget certainty provided by BEJ earlier than usual in the beginning of the Financial Year. The clear target of concluding activities by July 2025 also helped with planning too. Technical energy experts in BEJ provided quality assurance and challenge to delivery partner outputs before they were submitted to a GoI beneficiary.

Communication between BEJ and delivery partners was also sufficiently regular. Palladium and IESR provided quarterly and annual reports during the period. Meetings were also done bi-weekly and quarterly. Frequency of meetings and reports with UNOPS was lesser but proportionate to the scale and complexity of their project.

Noting the beforementioned risk of early staff departure in the Palladium-led consortium, staffing remained stable, with targeted hires including a GoI Liaison Officer and Communications Specialist to support close-out and stakeholder engagement. The team also demonstrated agility in reallocating resources to priority areas, including the Trust Fund development and technical assistance for hybrid power regulation.

The Accountable Grant with IESR to delivery GETI is in its inception phase in this AR’s timeline. It has been noted that some elements of IESR’s delivery and programme management have been slower than expected. IESR is still familiarising themselves with FCDO reporting processes and quality standards set by BEJ for individual projects. BEJ could be quicker to responding to IESR’s request for feedback on project design. It is recommended that the BEJ programme team speaks to IESR about ways of working to support delivery and refine ways of working.

Not enough info on UNOPS’s performance as they only started work on March 2025. Quality of their output will be reviewed in the next AR.

Financial Management
The programme’s total value increased to £22.3 million following a BCA completed during the reporting period, up from the previous allocation of £20 million. Since its inception in FY 2019–20, the programme has expended £17.9 million as of the end of March 2025. Of this, approximately £14 million was delivered through three delivery partners, £2.7 million via the VGF (will be revised following Brokerage section update), and the remaining through other programme-related activities and operational costs (e.g. programme funded roles in BEJ and travel to projects).

MENTARI’s financial management in FY 2024-25 was sound. The main delivery partner operated on a budget of around £2.7 million early in the year. But this was revised in February 2025 to £2.5 million as the October 2024 Indonesian government change affected delivery of some projects. The main costs from Palladium were personnel and indirect overheads. There is regular weekly contact between the PRO and Palladium on financial management to optimise VfM on project delivery and ensure RDEL and CDEL costs are categorised accordingly. An external audit was commissioned by Palladium to check finances for that FY with no negative findings, which provides assurance of due diligence and financial accountability.

The Accountable Grant with IESR was forecasted to spend £278,075 that FY but only invoiced around 75% of that value. But this was expected given they only started their GETI project with two quarters left in the FY, with limited experience working with BEJ.

Commercial
The delivery partner, Palladium International Ltd., continued to operate under a commercial contract with a total value of just under £15 million. The contract is classified as Silver and includes several Service Credits – which have been satisfied and closed around March 2025.
Recommendations	Responsibilities	Support	Timelines
BEJ Programme Team to discuss ways of working with IESR to avoid delays in delivering GETI. Consider a monthly/quarterly SRO level meeting.	PRO	Programme team	August 2025

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The BEJ programme team and the Palladium-led consortium have regular meetings related to programme management, monitoring and reporting: (1) bi-weekly meetings between the management team from delivery partners and embassy programme team to discuss programme and contract operations and administrative matters, risk and programme progress; (2) bi-weekly / weekly meeting between strand leads from delivery partners and embassy programme team to talk about strand-specific progress, risks and opportunities; (3) monthly meeting between MREL Manager from delivery partners and MREL officer from embassy programme team to talk about MREL process, progress, and compliance; (4) quarterly steering group meeting between delivery partners and programme team to see the overall programme progress and challenges over the previous quarter as well as looking forward to the upcoming quarters. These quarterly meetings will evolve to focus more on deep dives on more strategic issues in future.
Palladium maintained a permanent, full-time MREL manager position during the review period. The delivery partner also has access to an MREL short-term technical advisor (STTA) who is experienced in working with FCDO programmes.
The embassy programme team also visited brokerage and demonstration pilot project sites during the review period to see first-hand the implementation on the ground and cross-reference this with progress reports provided by delivery partners. During the visits, the programme team met with relevant stakeholders and beneficiaries to listen to feedback and comments on the project.
During the annual review process, the reviewer team had the opportunity to interview the programme team, delivery partners, beneficiaries, and stakeholders of the programme. This included interviews with NIRAS and MDF to discuss their initial findings from their evaluations of the Brokerage and Demonstration strand respectively.
With IESR, bi-weekly meetings are set-up towards the same effect. But there should be a higher-level meeting to monitor progress. This has already been recommended in the programme management section.
While the logframe has yet to be updated to include the additional projects from IESR and UNOPS, all of their outputs and outcome indicators are relevant to the existing Policy Strand logframe and its overarching impact indicators.
Evidence
Evidence has been used to inform adaptive management, including revisions to the TOC, updates to the logframe, and changes in delivery models. Regular bi-weekly, monthly, and quarterly meetings, as well as site visits, have enabled real-time learning and course correction. Triangulation of evidence from monitoring data, external evaluations, and stakeholder feedback has strengthened the validity of findings. The financial audit conducted by Palladium provided assurance of sound financial management and accountability
Looking ahead, the programme will continue to strengthen its evidence base through the completion of ongoing evaluations, enhanced data collection, and regular stakeholder engagement, ensuring that learning informs both programme closure and the design of MENTARI 2.
Learning
Refer to section “Major lessons and recommendations for the year ahead” on page two of this report. The programme team should apply these points as they design the successor of this programme.

Date of last narrative financial report	20 June 2025	Date of last audited annual statement	20 June 2025