ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Mentari UK-Indonesia Low Carbon Energy Partnership (formerly known as the Indonesia Renewable Energy Programme)
Country or region targeted	Indonesia
Type of cost extension (if applicable)	Cost and time extension
Original project budget	£13.5m
Original project start and end dates	November 2019 - December 2023
Cost extension value (if applicable)	£6.5m (total amended value £20m)
New reduced budget (if applicable)	N/A
New project end date (if applicable)	April 2026
Business Case Quest Document No.	n/a

INFORMATION
What is the project’s purpose?
The Mentari UK-Indonesia Low Carbon Energy Partnership aims to accelerate Indonesia’s low carbon energy transition to drive inclusive economic growth and access to affordable, clean energy, and emissions reductions in support of net zero goals. It provides technical assistance and international and local expertise for policy reform and knowledge exchange, and to broker increased investment in low carbon energy projects. Mentari has also delivered a renewable energy infrastructure demonstration project showcasing an innovative and leading community-based model for renewable rural electrification, and since February 2022, initiated an innovative Viability Gap Fund to support additional renewable energy projects in partnership with a key Indonesian infrastructure financing institution (utilising £2.7m from the original £13.5m budget); grant support from this VGF is now unlocking additional investment in first-of-a-kind hydropower projects in Indonesia. / In addition to its bilateral technical assistance activities, the programme is also a key vehicle for delivering high-profile HMG diplomatic priorities related to climate change and infrastructure development, including through support for and participation in the Indonesia Just Energy Transition Partnership (IJETP), a major international climate finance initiative to provide financial and technical support to accelerate Indonesia’s low carbon energy transition. / The Mentari programme has been an invaluable tool in establishing the UK and British Embassy as a key partner and trusted advisor for both donors and the Government of Indonesia in the IJETP, with for example Mentari analysis on captive coal power, local content requirements and emissions reductions ambition being welcomed by key stakeholders as highly effective and useful in informing the development of the IJETP in late 2022. This built on previous similar success during the UK’s presidency of COP26, where the flexible and high-quality technical outputs from Mentari, in conjunction with the Embassy and other HMG interventions, played a significant role in supporting Indonesia’s unprecedented participation in a landmark international agreement committing to working towards the phase out of coal power. / The programme underwent a full Annual Review in summer 2022 by a team of independent reviewers led by an externally appointed MREL specialist. This review awarded the programme an overall score of A+. The review found the programme to be on track to contributing towards expected outcomes and impact. It found that the programme had shown to be adaptive and flexible and had established good relationships with key beneficiaries including in the Government of Indonesia. It also found that Mentari had developed a large pipeline of renewable energy infrastructure projects to support and that this had successfully enabled partnerships and opportunities. The review praised the implementation of the Mentari demonstration project, noting in particular its strong community-led and GESI-sensitive approach. Finally, the key findings also noted the abovementioned strengths of Mentari in delivering soft power for the UK.
What is the objective of the cost extension or other changes?
Mentari has been operational since January 2020 and was initially designed to cover a four-year period to December 2023. In February 2022, a programme amendment was approved to establish a Viability Gap Fund, which provides direct, catalytic funding to economically desirable renewable energy projects in partnership with a local infrastructure financing institution. This VGF utilised some headroom in the initial £13.5m budget (including savings resulting from the procurement of the delivery partner). / This amendment proposes a time extension to April 2026 (from December 2023) and a cost extension of £6.5m. The cost extension would cover delivery and operational expenditure during this extended period between December 2023 and April 2026. / Indonesia is a priority country for UK engagement and Green Growth, which the Mentari programme directly supports, is a priority objective under the cross-HMG Indonesia Country Plan 2023-2025. Indonesia is also an important target country for UK engagement under the Indo-Pacific tilt and patient diplomacy approach with ‘middle-ground’ powers. Moreover, Indonesia is a top 10 global emitter of greenhouse gases (with the energy sector the second largest emitting sector) and was a priority country for UK engagement during the UK’s COP26 presidency. It is now also part of the Indonesia Just Energy Transition Partnership (IJETP), a major international climate finance partnership between Indonesia and leading international development partners which seeks to accelerate emissions reductions in Indonesia’s power sector. The UK is a key member of the IJETP and is playing a leading role to facilitate IJETP action on policy reform, building on our work through Mentari since 2020. The Mentari programme delivery partners work closely with the Low Carbon Energy team in the British Embassy Jakarta through an innovative hybrid delivery model designed to maximise the programme’s diplomatic potential alongside its technical work. / 2023-2026 will be a pivotal period for action on Indonesia’s energy transition. It follows two years, 2021-2022, of promising but cautious progress on policy reform and Indonesian government messaging on climate change and renewable energy development, including for the first time a publicly stated intention from the Government of Indonesia to phase out coal power. The IJETP, launched during Indonesia’s G20 presidency on 15 November 2022, adds significant political momentum and potential international support to consolidate and build on this, and drive real-world change. Additionally, the Government of Indonesia published a landmark new Presidential Regulation on the Acceleration of Renewable Energy in September 2022. The next few years are therefore crucial, and it is the right time for a strong and expert UK presence. / The overall objective of the extension period will be to maximise the UK’s influence and contribution to international efforts to accelerate Indonesia’s energy transition and reduce emissions in the power sector, including through active and expert participation in the IJETP and by delivering high-quality and responsive bilateral technical support in renewable energy policy and infrastructure delivery, and to maintain and enhance the UK’s reputation and diplomatic engagement on energy issues with the Government of Indonesia and prepare the ground for a potential longer-term partnership in future years.
What is the additional and total support the UK will provide?
The additional support is worth £6.5m, resulting in a total programme value worth £20m between November 2019 and April 2026. The additional £6.5m would be allocated, indicatively, as £6.3m for direct delivery costs channelled through existing delivery partners, and £200k for associated FCDO and programme team costs such as Monitoring, Reporting, Evaluation and Learning (MREL) activities and legal and commercial costs. FCDO staffing costs, including salaries, are no longer covered by programme budget following the closure of the Prosperity Fund.
What are the expected results?
The key high-level objectives for the proposed extension include the following. More detailed, concrete targets will be discussed between the Embassy and delivery partners to ensure that the extension period has detailed, measurable and ambitious targets across all of its activity. / To provide expert, responsive and trusted support for the delivery of the IJETP and its policy reform objectives, in order to enhance the UK’s reputation and influence, improve the quality and deliverability of relevant IJETP commitments, and align IJETP with UK climate change and sustainability priorities. The Mentari programme will also support the UK’s design and management of its IJETP financial contribution via the World Bank. / To maintain the UK’s close and valued partnership on energy transition with the Government of Indonesia, with associated co-benefits for the UK’s diplomatic engagement. Specifically, this includes maintaining the UK as a strong and effective participant in the Indonesia Just Energy Transition Partnership, supporting the implementation of projects arising from Indonesia’s 2023 ASEAN presidency, and ensuring the UK is able to maintain its close partnership with existing and any new government structures following the 2024 Indonesia Presidential elections. / To assist Indonesia with its energy transition objectives through technical assistance, including to support delivery of high-profile new commitments such as regulations on renewable energy and net zero power sector targets to help achieve accelerated emissions reductions, energy access, gender and social inclusion and sustainable development goals. Specifically, this may include design and implementation of significant reforms to local content regulations and a roadmap for incentivising the development of high-value renewable energy supply chains in Indonesia, plus the design and implementation of further targeted national and/or local policy and regulatory reforms to support the implementation of Indonesia’s 2022 Presidential Regulation on the Acceleration of Renewable Energy and IJETP-initiated reforms. / To provide innovative, flexible and high-quality technical and financial support to project developers and investors to leverage additional public, private and multilateral investment in renewable energy infrastructure. Specifically, the programme will design new targets for the volume of investment leveraged for new renewable energy projects, and/or targets for the number of projects supported (both large and small-scale).
What is the approach to implementation?
Delivery throughout the extended period will largely follow the overall structure put in place during the initial programme design, and which has been delivered since January 2020. This includes delivery of three strands: / Policy – supporting Indonesia to improve the enabling environment for renewable energy, to facilitate and encourage sustained investment in the energy transition, through technical assistance to address key policy, regulatory and capacity issues. / Brokerage – direct support to renewable energy project developers and investors, and matchmaking services, to help high-quality renewable energy infrastructure projects attract investment. This also includes the more recently implemented Viability Gap Fund which can provide grant and technical support to leverage additional investment in innovative renewable energy projects. / Demonstration – construction of an innovative, community-led solar mini-grid project providing power for two remote communities in eastern Indonesia, alongside community engagement and training activities to boost inclusive economic growth, and demonstrating an approach that can be replicated elsewhere. Through the proposed extension period, given project construction was completed in March 2023, the focus of this strand will shift to support for productive uses of energy and sharing lessons learned. / Underpinning all these strands is a specific focus on Gender and Social Inclusion (GESI) and this will continue to be a priority for the extension period. The programme also includes a Collaborating, Networking and Capacity Building component, which promotes international knowledge partnerships in the renewable energy sector, and training activities on key technical, financial, social and environmental aspects of renewable energy development. / The programme has an allocation for the full financial year 23/24 and is expected to be allocated funds in future years under the Indonesia Country Plan. The programme is currently delivered primarily through a consortium led by Palladium International and it is expected that the programme would continue to be delivered via a commercial contract, working closely with British Embassy staff. / The extension period will also be used to consider and develop options for ensuring legacy benefits and activities should the programme close or change in focus in from April 2026. This includes reviewing the structure and options for the continued delivery of the Viability Gap Fund. The Embassy team has reviewed alternative delivery options (including an extension of the current model) for the VGF including partnerships with multilateral institutions and options to allow development partners external to the UK government to provide additional funds in partnership with the UK.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There are no key changes to the overall programme theory of change or purpose. The Low Carbon Energy Team in the British Embassy Jakarta will work with delivery partners to finalise targets and indicators for the extension period and intend to undertake an evaluation exercise in summer 2023 to inform this, including taking into account recommendations from the programme’s 2022 Annual Review. However, the overall high-level outcomes of the programme, to secure policy reform and catalyse renewable energy investment, are unlikely to see substantive changes. The programme underwent a full Annual Review in 2021 and 2022 and will commission a further review in summer 2023. The most recent review scored the programme an A+ rating. / The programme team and delivery partners will review how the extended programme can best support and align with the IJETP and will develop appropriate indicators and targets. / The proposed extension to the programme would mean the delivery falls before, during and after the upcoming 2024 Indonesian Presidential elections, which will deliver a new administration following two consecutive terms under incumbent President Joko Widodo. This risk will be kept under review and should there be any significant contextual changes the relevancy and VfM of programme activity will be re-considered.