 Business Case

Summary Sheet

Country Plan Summary: / UK-Indonesia Strategic Partnership’s Climate, Energy and Nature Pillar: The climate crisis presents our maritime nations with similar challenges. Together we will champion global efforts to deliver a liveable planet for future generations, while delivering clean energy, green jobs and long-term food and energy security for our people. / Country Business Plan: Goal 2, Planet: Work with Indonesia to drive growth that is sustainable, just and resilient, nature positive, decoupled from emissions, and aligned with the aims of the Paris Agreement and Global Biodiversity Framework.

Title: MENTARI 2 UK-Indonesia Low Carbon Energy Partnership
Programme summary (100 words maximum): / MENTARI 2 is the key energy component of the UK–Indonesia strategic partnership, accelerating Indonesia’s energy transition through three strands: / System-level reform: Leveraging UK expertise to strengthen institutions, improve policies, and remove barriers to low-carbon energy investment – both foreign and domestic. / Market development: Enhancing the commercial viability of small-scale renewable projects through technical assistance and targeted interventions. / Modelling reform for inclusive energy access: Piloting scalable rural energy models that empower local communities and inform national strategies for equitable, low-carbon access. / Gender equality and social inclusion (GEDSI) is mainstreamed throughout. The programme reflects the UK’s modern development approach via the Four Shifts and delivers secondary benefits to UK growth.
What is the rationale for UK Aid spending? (200 words maximum): / Indonesia is the world’s fifth-largest emitter of greenhouse gases. Fossil fuels supply over four-fifths of its electricity, locking in carbon and slowing progress towards net zero. Yet the country aims to rank among the world’s five biggest economies by 2045. Without reform, that ambition risks cementing a high-carbon growth path. / MENTARI 2 backs systemic change, not short-term fixes. It strengthens Indonesia’s energy system rather than creating donor-run alternatives, focusing on regulatory reform, investment mobilisation. By changing rules and incentives, the programme helps Indonesia shift from coal to clean energy. / The UK brings expertise, not just money. Technical support will make projects bankable and attract private and multilateral finance, using grants sparingly to unlock structural change. A rural electrification pilot will demonstrate scalable clean energy models, co-designed with local institutions and integrated into Indonesia’s own electrification strategy. A small non-aid component will promote British firms in Indonesia’s energy market, managed by the embassy to keep development and commercial aims separate. / For the UK, MENTARI 2 is development with an investor’s lens – leveraging British expertise to deliver climate impact, unlock growth and strengthen diplomatic ties with a G20 country. It aligns with UK objectives on net zero, inclusive economic development and global influence, while creating pathways for UK firms to access Indonesia’s fast-growing energy market.
Programme Value: / Up to £20,000,000		Country/ Region or Sector: / Indonesia
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		Deputy Head of Low Carbon Energy, British Embassy Jakarta (PRO) / Head of Low Carbon Energy and Infrastructure, British Embassy Jakarta (SRO)
Threshold for final approval of Business Case: / Head of Mission: HM Ambassador to Indonesia
Date of Approval of Concept Note:	07/05/2025	Name and role of Approver / Minister for Indo-Pacific
Date of Approval of Business Case:	dd/mm/2025	Name and role of Approver / Head of Mission Jakarta
Programme Code: 400400	AMP Start Date: 01/04/2026	AMP End Date: 31/03/2031
Overall programme risk rating:	Moderate

## Strategic Case

Global Context and the UK’s Shifting Approach to Development

Global energy transition cuts across several important themes: development, geopolitics, and economic growth. Reliable, affordable, low‑carbon energy systems are essential to inclusive prosperity, decarbonisation of heavy industry and transport, and resilient supply chains across the Global South. Rising electricity demand in emerging economies, such as Indonesia, will be met either by continued fossil fuel dependence or by clean, flexible systems that enable sustainable growth. Choices taken this decade will lock in trajectories for generations and influence a state’s dependencies and global supply chains.

In parallel, the UK is reshaping its development offer through modern development partnerships that emphasise long‑term reform, investment mobilisation and local ownership. This is captured in the Four Shifts outlined by HMG’s Minister for Development:

  1. From donor to investor: use ODA (Official Development Assistance) to catalyse public and private capital, not substitute for it.
  2. From service delivery to system support: change rules, standards and operating models rather than running parallel services.
  3. From grants to expertise: deploy UK technical know‑how; use grants sparingly to unlock structural change.
  4. From international intervention to local provision: co‑design with, and hand over to, national institutions for replication.

These Four Shifts will shape any intervention the UK makes on energy transition, but it would also still align with the following international commitments and strategies:

  1. International Climate Finance (ICF) Strategy prioritises clean energy and system reform to reduce fossil dependence and mobilise sustainable finance.
  2. Sustainable Development Goals: primary alignment to SDG 7 and SDG 13; secondary contributions to SDG 9, SDG 5, SDG 8 and SDG 1.
  3. FCDO’s Partnership Principles by contributing to efforts towards poverty reduction, human rights, financial and domestic accountability.
  4. British Embassy Jakarta (BEJ) Country Plan: contributes to Prosperity and Planet outcomes by pairing UK expertise with competitive financing and investment for sustainable infrastructure.
  5. UK-Indonesia Strategic Partnership: The UK and Indonesia commit to accelerate a just energy transition through policy reform, investment mobilisation, and technology partnerships to deliver affordable, green energy and phase-down coal.

Southeast Asia and Indonesia

Southeast Asia is pivotal to HMG’s objectives on growth, resilient supply chains and geopolitics. Rapid urbanisation and industrialisation are driving strong demand for clean infrastructure, grid modernisation and digital systems. Within this context, Indonesia stands out: it is the region’s largest economy and population centre, home to the Association of Southeast Asian Nations (ASEAN) Secretariat, and a regional normsetter whose policy choices can influence neighbours’ approaches to economic development and the energy transition.

Indonesia is also central to the ASEAN Power Grid (APG) initiative, which seeks to strengthen regional energy security and accelerate the transition to clean power through cross-border electricity trade. Indonesia’s geographic position and substantial renewable energy potential – particularly hydro, solar, and geothermal – make it a critical hub for interconnection. Its active participation is essential to achieving APG’s objectives of integrating diverse energy systems, balancing supply and demand across borders, and reducing reliance on fossil fuels. While initial steps have been taken through the Sumatera–Singapore pilot project, further progress will depend on improvements to Indonesia’s domestic regulatory framework for grid transmission and cross-border power trading, which could significantly accelerate regional connectivity.

Indonesia is a G20 member and a top five global carbon emitter with rising global influence. The country joined BRICS in early 2025 and has an interest to join the Organisation for Economic Co-Operation and Development (OECD) and the Comprehensive and Progressive Agreement for Trans-Pacific Partnership (CPTPP). Bilaterally, the UK and Indonesia intend to elevate ties through a Strategic Partnership expected to be launched at leader level in 2026, which includes a pillar on Climate, Nature and Energy. The direction of Indonesia’s power sector will strongly shape both its own development model and regional climate outcomes; a credible, inclusive energy transition is therefore squarely in UK and regional development, climate and commercial interests.

Our analysis shows that approximately 40% of the Strategic Partnership’s deliverables depend directly or indirectly on the successful implementation of the bilateral energy programme – MENTARI 2. This dependency spans four critical areas of the Strategic Partnership:

Energy Transition (15%): MENTARI 2 underpins Indonesia’s Just Energy Transition Partnership (JETP), supports Perusahaan Listrik Negara’s (PLN, state-owned utility company) governance reform, and accelerates renewable deployment - from solar and wind to geothermal. Without MENTARI 2, these commitments risk stalling.

Climate & Nature (10%): The programme strengthens Indonesia’s ability to meet its Nationally Determined Contributions (NDCs), advance adaptation strategies, and protect biodiversity - key priorities in the Partnership’s climate pillar.

Sustainable Infrastructure (10%): Through technical assistance and policy dialogue, MENTARI 2 complements MELAJU (a separate bilateral UK programme in Indonesia on infrastructure) and other initiatives to deliver green transport, resilient urban systems, and low-carbon infrastructure.

Carbon Markets (5%): MENTARI 2 supports Indonesia’s ambition to become a regional hub for carbon capture and storage and to operationalise high-integrity carbon markets – both critical for mobilising private finance.

Achieving Indonesia’s 2030 energy transition targets will require an estimated US$97 billion in investment for the power sector alone. This substantial finance gap creates opportunities for private capital, including UK firms with expertise in renewable energy, grid services and green finance.

JETP

The Just Energy Transition Partnership (JETP) is a multilateral initiative that supports Indonesia’s energy goals. The UK is a leading member and has committed a $1bn guarantee with the World Bank and $150mn from the multi-donor Private Infrastructure Development Group (PIDG). By aligning efforts with other international partners through the JETP platform, the UK engages an additional set of Indonesian stakeholders – such as the Coordinating Ministry of Economic Affairs (CMEA) – to deliver energy outcomes that would not be achievable through unilateral action alone.

Why the UK/FCDO should be involved in Indonesia’s energy transition

Indonesia’s energy transition is central to its economic modernisation. Decarbonising the power sector will enable electrification of transport and industry, improve public health, and reduce system costs. It will also create domestic value chains in manufacturing and services, supporting inclusive growth and long-term competitiveness. These reforms are essential for Indonesia’s ambition to become a top-five economy by 2045.

The UK has a strong platform through the MENTARI programme, active since 2020 and highly regarded by the Government of Indonesia. MENTARI has delivered across policy reform, system demonstration, and investment facilitation, earning consistent A+ ratings for impact and value. Building on this brand offers a coherent umbrella for UK engagement – linking diplomacy, technical assistance, and commercial demonstration – while reinforcing commitments to UN SDG 7 (Affordable and Clean Energy).

Commercial opportunity follows scale. Indonesia’s energy transition will require an estimated £1.5 trillion in investment by 2040 – including £1.1 trillion for renewables, £45.9 billion for grid and storage, and £4–5 billion for coal repurposing (JETP CIPP 2023). UK firms, recognised globally for expertise in offshore wind, marine energy, transmission, and storage, are well-positioned to deliver scalable solutions aligned with Indonesia’s priorities. Capabilities in market regulation, grid digitalisation, flexibility integration, and climate finance are in demand.

The UK’s distinctive value proposition combines strong bilateral ties built through MENTARI with proven leverage across key financiers and multilateral development banks (World Bank, ADB, PIDG). At a time when some partners are scaling back – such as the closure of the US SINAR programme – the UK can convene stakeholders, de-risk investments, and accelerate deployment of low-carbon energy solutions in Indonesia.

Sector Economics and Constraints

Indonesia’s energy transition depends on deep policy and regulatory reform to shift from a fossil fuel-dominated power sector – currently over 80% coal – to its vast renewable potential of 3,687 GW (of which only 0.3% has been realised). Despite national targets and a new energy policy aiming for 70–72% renewables by 2060, progress remains slow due to fossil fuel subsidies, non-cost-reflective tariffs, restrictive procurement, and LCR that hinder project bankability. Weak investor confidence in Power Purchase Agreements (PPA), outdated grid codes, and uneven institutional capacity further impede progress. Removing these barriers through transparent, predictable frameworks and practical implementation tools is essential to attract private capital and accelerate clean energy deployment. Alongside renewables, Indonesia is exploring civil nuclear energy as part of its long-term low-carbon strategy, aiming to commission its first plant by the early 2030s. While nuclear could provide baseload power, significant challenges remain – including high capital costs, regulatory capacity, and public acceptance.

These structural challenges are compounded by political economy factors. While some reforms, such as adjustments to LCR, have increased confidence in UK engagement in certain sectors, fossil fuel subsidies, non-cost-reflective tariffs, and restrictive procurement practices continue to impede investment and slow the energy transition. MENTARI 2 is designed to tackle these constraints through a dual approach: supporting policy and regulatory reform to establish transparent, predictable frameworks, while demonstrating bankable projects that build investor confidence. This ensures UK engagement moves beyond isolated interventions to deliver systemic change in Indonesia’s power sector.

Electricity in Indonesia is kept affordable because the government sets low prices. However, these low prices make it hard for renewable energy projects to recover their costs and attract investment. For comparison, households in Indonesia pay about 10 cents per kilowatt-hour, Thailand pays slightly higher (10.7 cents), and the UK pays more (25 cents). The cost of producing electricity varies by source: coal is cheapest, while wind and solar are more expensive. Geothermal and biomass can compete with coal, but whether these projects succeed depends on having fair contracts, reliable grid connections, and clear rules for sharing risks.

Indonesia lowered LCRs to about 25% and set specific targets for different technologies (e.g., solar 20%, wind 15%). This change aims to attract investors while supporting local industry. But domestic capacity to meet LCRs is uneven: solar panel production is growing (around 4.7 GW per year, with plans for 19 GW by 2030), but actual solar use is still under 1 GW. There is no major wind turbine manufacturing, battery production focuses on electric vehicles rather than energy storage, and small hydro capability is limited. The grid also faces challenges: Java–Bali has an oversupply of about 4 GW (mostly coal), while remote areas still rely on diesel.

Indonesia’s many islands make it hard to build large power plants everywhere, so smaller renewable projects are key to replacing expensive, polluting diesel. But these projects often struggle to attract investment because electricity prices are kept low, subsidies favour fossil fuels, and costs for setting them up are high. Rules about using local materials and limited domestic manufacturing add more hurdles. Big international banks usually fund large projects, leaving smaller ones overlooked, and local lenders are still learning how to handle renewable energy risks. MENTARI 2 will address these constraints through system demonstration pilots designed as catalysts for systemic change—generating evidence to inform national policy, unlock investment, and create scalable models for inclusive, low-carbon growth.

Why Indonesia cannot do this alone (yet)

Regional disparities further complicate the transition. Over 58% of GDP and approximately 70% of industrial activity are concentrated in Java (Indonesia Statistics, 2024), while eastern provinces and remote islands lag behind in infrastructure and energy access. Electrification rates remain uneven: Java and Bali approach 99% coverage, but some eastern regions still fall below 85%, with frequent outages and reliance on diesel generation. These gaps reinforce inequality and highlight the need for distributed renewable solutions that deliver inclusive growth. Financing patterns exacerbate the problem: multilateral and commercial lenders favour large-scale projects, leaving distributed and small-scale initiatives underfunded.

Legal uncertainty also discourages investment, notably following a 2024 Constitutional Court ruling that affects transmission and poses risks to grid modernisation and renewable integration. This is an ongoing issue that will require legal and technical support to MEMR as it is a barrier to modernising transmission infrastructure.

Political headwinds make reform challenging, but they also underscore the need for credible, trusted partners who can navigate complexity and build consensus. The UK brings a distinctive value proposition: strong bilateral ties, proven delivery through MENTARI, and influence with multilateral financiers. These assets enable the UK to convene stakeholders, de-risk investment, and embed systemic reforms that others may avoid. By combining policy support, technical assistance, and catalytic pilots, UK engagement can accelerate Indonesia’s transition in ways that align with its priorities – ensuring progress even in a difficult political economy. This approach positions the UK as a long-term partner in shaping inclusive, low-carbon growth in Southeast Asia.

What a UK programme in Indonesia would look like and what success means

1. MENTARI 2 will deliver three mutually reinforcing strands that embody the Four Shifts. Each is outcome-focused, timebound, and designed for replication by Indonesian institutions. Results aggregate to policy adoption, finance mobilised, replication, inclusion, and resilience. Each strand will have its own GEDSI objective, and a separate non-ODA component will focus on secondary benefits. The diagram in para 40 provides an outline Theory of Change for the programme. The three strands are:
  1. Policy Reform and Implementation Strand: Creating the regulatory and governance conditions for Indonesia’s energy transition—driving systemic reforms that unlock investment and accelerate clean energy adoption.
  2. Investment Support Strand: Catalyzing private and public finance for renewable energy projects through technical assistance and matchmaking services.
  3. System Demonstrator Strand: Informing National Policy Through Scalable Low-Carbon Electrification Models

Policy Reform and Implementation Strand

The rationale for this strand stems from persistent structural challenges highlighted in Sector Economics and Constraints. While the Government of Indonesia’s (GoI) ambition for systemic reform has slowed since MENTARI 1, there remains strong demand for practical, standardised tools (e.g. model PPAs, tariff calculators, and grid code guidance) that make transactions bankable and replicable. Continued UK engagement is therefore essential to sustain progress, align technical assistance with JETP partners, and mitigate the risk of backsliding on reforms that unlock investment and accelerate clean energy adoption.

This strand aligns with the Four Shifts by prioritising UK expertise over grants to co-design systemic reforms that unlock investment and accelerate clean energy adoption. Rather than delivering services, it strengthens Indonesia’s regulatory frameworks and institutional capacity, ensuring local ownership and replication of reforms for long-term impact.

1. What the strand will deliver:
  1. Make it easier for renewable projects to sell power: We will work with the government and PLN to create clear, transparent processes for buying renewable energy. This includes standard contracts and updated technical rules so projects can be financed and replicated more easily.
  2. Support key energy laws and policies: We will help move forward important reforms, including outcomes from the Renewable Energy Bill and the National Energy Policy, to ensure they are embedded in energy regulations and provide long-term certainty.
  3. Provide practical tools for institutions: We will build capacity by creating easy-to-use tools like standard operating procedures, model contracts, open data systems, and templates to track progress.
  4. Explain reforms to the public: We will improve public understanding of why energy reforms matter – such as reducing fossil fuel subsidies – and show how affordability measures will protect vulnerable households.
  5. Give investors confidence in new sectors: We will strengthen regulations and reduce uncertainty in emerging areas like wind, marine energy, and grid transmission, so investors feel secure about putting money into these markets.
  6. Prepare for future carbon pricing: Where politically feasible, we will help Indonesia get ready for market-based approaches to cutting emissions, such as carbon pricing.

How success will be measured: adoption of priority reforms; integration of tools into national guidance; improved investor feedback on bankability; and evidence of practice change (e.g., procurement specs and planning norms).

Investment Support Strand

This strand targets the urgent need to scale low-carbon energy in Indonesia while broader policy reforms take time to take effect. PT SMI, British International Investments (BII), and International Finance Corporation (IFC) have noted that financing is not the core issue – rather, it is the lack of suitable, bankable projects. Small-to-medium-scale renewable energy projects, which are critical for Indonesia’s archipelagic geography and PLN’s diesel replacement agenda, are often overlooked. These projects face high transaction costs, limited access to tailored financing, and challenges in reaching financial close, despite their strategic importance.

Developers struggle with regulatory complexity, evolving LCRs, and uneven manufacturing capacity – solar is still scaling, wind is nascent, and battery production is focused on electric vehicles (EV). Multilateral Development Banks (MDBs) tend to favour large-scale projects, while domestic lenders are still building familiarity with renewable energy risks. Existing initiatives (e.g., World Bank rural electrification, ADB Energy for All, Green Climate Fund) offer valuable experience but are not always positioned to support small low-carbon energy project developers struggling to attract investment.

This strand aligns with the Four Shifts by positioning the UK as an investor catalyst rather than a donor. It leverages UK expertise to unlock capital for small-to-mid-scale projects, focusing on systemic enablers like standardisation, aggregation, and risk-sharing. The goal is to help Indonesian institutions and lenders build sustainable pipelines to invest in, with lessons feeding into the Policy Reform Strand. Lessons learned from the independent evaluation of the brokerage strand of MENTARI 1 in September 2025 will be applied to this strand of work (see Annex B for details of the evaluation).

1. This strand aims to deliver the following:
  1. Help projects become investment-ready: We will provide expert advice and studies to make renewable energy projects attractive to investors. This could include grouping similar projects together and using standard templates to reduce costs and speed up preparation.
  2. Connect projects with capital through partnerships and matchmaking: We will work with global and local partners – including the World Bank, ADB, IFC, Indonesia’s PT SMI, and UK institutions like BII – to attract funding and set clear standards for what makes a project bankable. At the same time, we will actively connect developers with potential investors through targeted matchmaking services, investor forums, and partnerships. This approach ensures that well-prepared projects find the right financing quickly and builds confidence in Indonesia’s renewable energy market.
  3. Use UK partnerships to unlock investment: We will apply the UK’s Growth and Investment Partnerships approach, working with organisations like BII, PIDG, UKEF, ASEAN’s Green Finance Facility, and MDBs. This will help prepare projects in a consistent way, share risks fairly, and combine smaller projects into packages that investors want.

How success will be measured: number of projects reaching financial close; public and private capital mobilised; uptake of standardised documentation by lenders; and improved bankability metrics. The UK operates as an investor catalyst - using expertise to unlock capital - rather than a donor of last resort.

System Demonstrator Strand

This strand tackles persistent energy access gaps in Indonesia’s remote and coastal areas, where diesel generation remains dominant – driving emissions and reliance on expensive fuel imports. Small-to-medium energy solutions, which fit these contexts, are often excluded from mainstream planning and financing. The Ministry of Energy and Mineral Resources (MEMR) and the National Development Planning Agency (BAPPENAS) have highlighted the need for tested models and robust data to inform national rural electrification strategies.

Building on lessons from MENTARI 1’s Sumba pilot, this strand will co-design a demonstration with local authorities to test governance, tariff, and operational frameworks that can be scaled nationally. The Sumba pilot proved that locally owned models can deliver clean energy, jobs, and productive use of electricity. Its governance approach was later replicated in 42 villages and recognised as best practice by Indonesia’s anti-corruption commission (KPK) – showing how pilots can influence national programmes.

This strand is explicitly aligned with the Four Shifts by focusing on systemic change, not service delivery. The pilot is a strategic tool to generate evidence, build capacity, and inform national policy. It considers approaches to governance, tariffs, and operations and management (O&M) frameworks that Indonesian institutions can adopt and scale - shifting the UK’s role from donor to enabler and catalyst.

Findings from this strand can also inform future commercial engagement by UK marine and offshore energy firms. As Indonesia explores low-carbon electrification across its islands, insights on system design, O&M, and community integration can help UK companies tailor their technologies and business models to local needs – unlocking new market opportunities.

1. The strand aims to deliver the following:
  1. Policy-relevant demonstration project: A pilot in a coastal community designed to test scalable governance and financing models for rural electrification, providing lessons for national programmes.
  2. Operations and Maintenance (O&M) and tariff framework: Co-developed with local authorities to inform national standards and ensure long-term sustainability.
  3. Institutional capacity-building: Training and tools for government, local institutions, and local communities to support productive use of energy and maintain systems beyond handover.
  4. Replication packs and data: Comprehensive documentation and evidence to guide government planning, procurement norms, and budget allocation for scale-up.
  5. Evidence on social and resilience benefits: Including improved health services through electrification of medical facilities (e.g., cold storage for medicines), and gender-inclusive economic opportunities.

How success will be measured: new energy source installed before March 2028 to ensure sufficient time for impact monitoring; replications by GoI and PLN; inclusion of standards into local or national guidance; productive use of energy (PuE) and job creation (including for women and young people); affordability and ability for the community to maintain O&M cost beyond the programme; emissions avoided; and evidence that demonstrators have shifted practice (procurement specifications, planning norms, budget allocations).

Mainstreaming GEDSI across strands

Gender equality, disability inclusion and social equity are mainstreamed in MENTARI 2. Building on MENTARI 1 results, GEDSI will be embedded by design across policy, investment and demonstrator strands, ensuring equitable participation and benefits and institutionalising inclusive practice within Indonesian counterparts.

1. Each strand will incorporate a dedicated GEDSI sub-objective, ensuring that interventions actively promote inclusion and deliver tangible benefits for disadvantaged groups:
  1. Policy Reform: Apply GEDSI analysis to all technical assistance provided to GoI, ensuring recommendations do not inadvertently disadvantage vulnerable groups and, where possible, create pathways for economic and social benefits.
  2. Investment Support: Strengthen ESG (Environmental, Social, and Governance) data for supported projects to improve investment prospects and demonstrate positive impacts on underserved communities. Include mitigation measures for any potential negative impacts.
  3. Systems Demonstration: Design and implement models that generate economic opportunities for disadvantaged groups within beneficiary communities from the new clean energy source. This is to reinforce the principles of a “Just Energy Transition” and enabling replication by GoI at scale.

Further technical details about the context of each of the strands would operate in are available in Annex A. But below is a visual Theory of Change outline showcases the programme’s intended impacts and structure. Note that this may be refined subject to procurement outcomes, innovative ideas from a future delivery partner, and adaptive programming responding to the shifting Indonesian energy context.

## Appraisal Case

Introduction and Criteria

1. The Appraisal Case assesses five intervention options to address the issues identified in the Strategic Case.
  1. Do Nothing
  2. Delivery through a Centrally Managed or Regional Programme
  3. Delivery through another development partners’ programme
  4. Renew MENTARI in its existing structure
  5. Hybrid: Renewing MENTARI with Lessons Learned Applied and Increased Flexibility

Each option is described in detail and assessed against the following objectives set out in the Strategic Case (i.e. policy reform, demonstration and rural electrification, investment support, GEDSI and secondary benefits).

Do Nothing (Option 1)

This scenario involves allowing the MENTARI programme to conclude as scheduled in April 2026, without launching a successor bilateral energy transition programme.

Importantly, this option does not imply a withdrawal of UK support for Indonesia’s energy transition. Since MENTARI 1’s inception in 2020, the landscape has evolved significantly. Multiple international development partners have launched their own bilateral programmes, many of which have drawn on MENTARI’s successes and lessons. The UK remains engaged through Centrally Managed Programmes (CMPs), such as UKPACT, the ASEAN Low Carbon Energy Programme, and the Ayrton Fund’s Energy Catalyst, which continue to deliver targeted support across Indonesia.

By stepping back from direct bilateral programming, the UK could focus on strategic coordination, policy dialogue, and leveraging multilateral platforms such as the JETP. This approach allows for a more cost-efficient posture while still contributing to Indonesia’s energy transition through existing mechanisms.

1. However, there are trade-offs to consider:
  1. Policy/Regulatory Reform: UK influence would be diluted without a dedicated bilateral vehicle. BEJ’s in-house expertise, currently funded through MENTARI, would be reduced, limiting the UK’s ability to respond flexibly to Indonesian requests and shape reforms in real time.
  2. System Demonstration: While other programmes include rural electrification, none have matched the impact or recognition of MENTARI’s Sumba pilot. The opportunity to replicate this model in diverse geographies would be missed.
  3. Investment Support: MENTARI’s role in reforming LCRs was pivotal in unlocking investment. Without continued support, small-scale renewable projects (<10MW) may struggle to attract financing, especially in underserved regions.
  4. GEDSI: MENTARI 1 embedded GEDSI across its strands, particularly in rural electrification. Without a successor programme, momentum on inclusive energy governance could stall, and proven models may not be scaled.
  5. Secondary Benefits to UK Growth: While CMPs and multilateral efforts may reduce barriers to investment, they lack the tailored commercial diplomacy and market-shaping interventions that a bilateral programme like MENTARI offers.

In summary, this option offers a strategic pause that leverages existing UK and international programming, avoids duplication, and reduces resource demands. However, it risks losing the UK’s unique bilateral influence, slowing progress on inclusive and locally grounded energy transition models, and missing opportunities to deepen UK-Indonesia commercial ties in the low-carbon sector. The context outlined in the Strategic Case suggests that while this option is viable, it is suboptimal for achieving the full spectrum of development and diplomatic objective

Full Delivery via Centrally Managed Programmes and/or Regional Programmes (Option 2)

This scenario recognises the strategic importance of supporting Indonesia’s energy transition but proposes doing so primarily through CMPs and regional initiatives funded by HMG. Under this approach, the UK would not renew MENTARI or pursue a new bilateral programme. Instead, bilateral ODA funds managed by BEJ would be redirected to CMPs led from London or regional programming hubs.

This model leverages existing UK investments and delivery mechanisms, offering a cost-efficient and administratively streamlined alternative. It also aligns with HMG’s broader Indo-Pacific strategy and supports regional cooperation through ASEAN platforms. Several CMPs and regional programmes currently active in Indonesia include:
1. Ayrton Fund – Transforming Energy Access (TEA): Supports rural electrification, energy storage, and bioenergy. The programme concludes in 2027 but there are considerations to extend it.
2. ASEAN Low Carbon Energy Programme (LCE): £15m over four years for policy support, capacity building, and technical assistance.
3. ACGF: Managed by the ASEAN Infrastructure Fund and supported by ADB, ACGF mobilises blended finance for green infrastructure projects across ASEAN, including Indonesia. It offers technical assistance and concessional finance to de-risk investments, particularly in renewable energy and climate-resilient infrastructure.
4. ASEAN-UK Green Transition Fund (GTF): £40m programme with pillars on climate policy, energy transition, and green finance.
5. UKPACT: Active in Indonesia since 2021, focusing on energy efficiency and ecosystem development.
6. Energy Transition Partnership (ETP): Funded by the Department for Energy Security and Net Zero (DESNZ), this regional initiative supports coal retirement and wind energy development.
7. Blue Planet Fund – COAST Programme: Supports climate resilience in fisheries and aquaculture, with potential synergies for coastal energy access.

These programmes provide valuable technical expertise, financial support, and policy engagement. However, they face structural limitations that reduce their effectiveness in Indonesia. Regional mandates often dilute country-specific impact, and complex bureaucratic processes constrain adaptive delivery. While UKPACT is the most responsive to GoI requests among these CMPs, its current focus is limited to energy efficiency – a narrow component of the broader energy transition. Many CMPs also lack an in-country presence, which is a critical gap in Indonesia where personal networks and face-to-face engagement are essential for influencing policy and securing buy-in. As a result, these programmes struggle to combine visibility, flexibility, and responsiveness to GoI priorities, limiting their ability to deliver systemic change at scale.

MENTARI 1 addressed these gaps by being locally managed and diplomatically embedded. Its governance structure – anchored in BEJ and co-led with MEMR – enabled agile responses to evolving needs. MEMR’s praise during the 2024 and 2025 Annual Review highlighted the value of this flexibility, which CMPs may struggle to replicate.

1. Assessment Against Strategic Objectives:
  1. Policy/Regulatory Reform: CMPs offer technical assistance but often lack direct engagement with MEMR. Programmes like GTF require multi-country benefit, limiting bespoke support. The call-for-proposals model also reduces responsiveness to GoI requests. However, there could be a role for GCIEP in the future as it slowly develops its energy expertise.
  2. System Demonstration: TEA is relevant but lacks the depth and recognition of MENTARI’s Sumba pilot as they often lack the community capacity building component. COAST presents a promising opportunity for integrated energy-fisheries-health interventions, but no CMP currently combines these elements.
  3. Investment Support: CMPs do not always offer viability gap funding or tailored financial support for small-scale projects. ACGF offers blended finance and technical assistance, but its regional mandate may limit responsiveness to Indonesia-specific needs unless co-financed or coordinated bilaterally.
  4. GEDSI: CMPs incorporate GEDSI broadly but lack the targeted, community-level interventions that MENTARI 1 delivered.
  5. Secondary Benefits to UK Growth: CMPs contribute to lowering investment barriers but lack strategic commercial diplomacy. They do not actively match UK capabilities to Indonesian needs or promote UK firms in the energy sector.

While CMPs and regional programmes offer valuable contributions, they are best viewed as complementary mechanisms rather than primary delivery vehicles. They provide cost-effective support for policy reform and regional collaboration but fall short in delivering locally tailored, inclusive, and commercially strategic interventions. Without a bilateral programme like MENTARI, the UK risks losing its unique influence, visibility, and ability to shape Indonesia’s energy transition in line with both development and diplomatic objectives.

This option is viable for maintaining baseline engagement but is not optimal for achieving the full range of outcomes outlined in the Strategic Case.

Full Delivery via Likeminded Development Partners (Option 3)

This scenario proposes renewing the MENTARI programme with a budget of up to £20 million over five years but delivering it entirely through likeminded development partners and MDBs. Delivery would be operationalised through Delegated Cooperation Agreements (DCAs) or Memoranda of Understanding (MoUs) with partners such as Australia, Denmark, Japan, and New Zealand. And institutions like the ADB and World Bank.

This approach leverages the deep technical expertise, established delivery infrastructure, and strong in-country presence of other donors, while reducing the administrative burden on BEJ. It also aligns with the UK’s commitment to aid effectiveness, donor coordination, and the principles of the Global Partnership for Effective Development Co-operation.

Several bilateral and multilateral programmes already active in Indonesia align with MENTARI’s objectives:
1. Australia’s KINETIK (A$200m): Launched in 2024, it supports policy reform, Small & Medium Enterprise (SME) finance, large-scale green infrastructure, and equitable transition.
2. Denmark’s INDODEPP: Supports energy planning, grid integration of renewables, and energy efficiency.
3. New Zealand’s NZMATES and PINZ: NZMATES delivers rural electrification in Maluku; PINZ supports geothermal capacity development.
4. ADB’s ASETP: A $500m policy-based loan programme supporting Indonesia’s clean energy transition.
5. Asia Zero Emission Community (AZEC): Japan-led platform promoting low-carbon technologies like hydrogen and ammonia.

1. MENTARI 1 has already engaged with several of these initiatives, laying the groundwork for deeper collaboration that can be built on for MENTARI 2. There are also cross-cutting advantages delivering MENTARI 2 this way:
  1. Cost Efficiency: Reduces overheads by using existing delivery platforms.
  2. Donor Alignment: Enhances coherence and avoids duplication.
  3. Scalability: Taps into larger funding envelopes and delivery networks.
  4. Political Leverage: Positions the UK as a strategic co-financer and thought partner.

1. Despite its strengths, this option presents several limitations when assessed against the Strategic Case objectives:
  1. Policy Reform: While partners like Australia and Denmark are well-embedded in GoI systems, the UK’s direct influence would diminish without a visible bilateral mechanism. This could reduce the UK’s ability to shape reforms aligned with its values and commercial interests.
  2. System Demonstration: NZMATES offers a viable delivery partner for coastal electrification pilots. However, the UK has not previously collaborated with New Zealand in this context, and no existing programme integrates energy and health resilience.
  3. Investment Support: KINETIK and ACGF support SME finance and blended finance, but both are relatively new or regionally focused. It is too early to assess their effectiveness in mobilising private capital for small-scale renewables in Indonesia. But ACGF would be a mechanism to maintain engagement with.
  4. GEDSI: While partners incorporate GEDSI principles, few offer the targeted, community-level interventions that MENTARI 1 delivered – particularly in supporting women-led enterprises and inclusive governance models.
  5. Secondary Benefits to UK Growth: This delivery model limits the UK’s ability to shape market access opportunities for UK firms. Without a bilateral platform, it would be difficult to align programme activities with UK commercial diplomacy or promote UK expertise in marine energy, grid services, or project preparation.

This option offers a pragmatic and politically aligned approach to supporting Indonesia’s energy transition. It builds on existing partnerships, reduces delivery risk, and enhances donor coordination. However, it lacks the strategic visibility, flexibility, and bilateral influence required to fully deliver on the UK’s development, diplomatic, and commercial objectives.

While suitable as a complementary mechanism, this option is not optimal as a standalone delivery model. A hybrid approach – where the UK retains a bilateral platform while strategically co-financing partner-led initiatives – would better balance efficiency with influence and impact.

Maintaining the existing MENTARI 1 Structure (Option 4)

This option involves renewing the MENTARI programme in its existing form, with no changes to its structure, delivery model, or funding mechanisms. It would continue operating as a bilateral programme with a commercial contract as the primary delivery mechanism. It would maintain its strands on policy reform, brokerage, demonstration, collaboration capacity building networking (CCBN), and GEDSI. The CCBN strand would be streamlined into the policy strand given the experience from MENTARI 1 delivery saw overlapping and complementary efforts.

The approach ensures continuity and leverages MENTARI 1’s success but lacks the flexibility to coordinate, co-finance with other programmes, and optimise Secondary Benefits. Implications of this option include:

  1. Policy reform: Given the model’s success in delivering technical assistance towards the National Hydrogen Strategy and LCR reforms, continuing this model provides assurance to MEMR. However, the focus on MEMR meant missed opportunities to raise public awareness on energy transition. This was previously delivered by a consultancy firm, but a think-tank may also be in a suitable position to deliver these works.
  2. System Demonstration: The approach of working with an NGO to deliver the Sumba solar array has been positive, particularly from GoI. It could maintain a similar approach, but limits opportunities for diversifying projects across different topographies or collaborating with other programmes such as NZMATES and TEA. This was previously delivered through an NGO with sub-contractors for the construction. A similar approach is likely to be effective. The previous programme did not have a health component.
  3. Investment Support: The Viability Gap Fund of MENTARI 1 proved useful to supporting small-scale projects. But a blended finance facility is too early to commit to for now as the market reacts to regulatory changes in the energy sector and PT SMI’s Trust Fund initiated from MENTARI 1 is still being designed. The technical assistance and feasibility studies support for small developers would be maintained in this option, but the approach has space for improvement by applying lessons learned from the Brokerage Strand evaluation (Annex B)
  4. GEDSI: MENTARI 1 integrated GEDSI into its approach, but in practice, most of the outputs came from the demonstration strand.
  5. Secondary Benefits: This was not explicitly a feature in the first programme. Although the policy reform work helped reduce barriers for all investors, there was no specific effort to support UK firms.

Maintaining the existing structure provides continuity but has missed opportunities. MEMR would appreciate the continued approach to policy technical assistance, but there are efficiencies to realise and test alternative approaches.

Hybrid Approach: Renew MENTARI with Lessons Learned Applied and Flexibility (Option 5)

This option proposes renewing the MENTARI programme with a budget of up to £20 million over five years. It builds on the success of MENTARI 1 while addressing delivery limitations through a hybrid model that combines a core commercial contract with flexible funding mechanisms – covering both ODA and non-ODA components. This approach positions the UK as a catalyst for systemic change, enabling strategic visibility, deeper bilateral influence, and adaptive responses to Indonesia’s evolving energy transition needs.

MENTARI 2 will deliver across three strands: Policy Reform, System Demonstration, and Investment Support – each with embedded GEDSI objectives and a non-ODA component to support UK growth. Enhancements reflect lessons from MENTARI 1 and shift the programme from transactional delivery to systemic influence:

  1. Flexible partnerships to amplify systemic impact: A new collaboration fund will enable co-financing with likeminded partners (e.g., NZMATES, TEA, ACGF) and UK CMPs (e.g., GCIEP, UKPACT). This moves from rigid contracting to adaptive partnerships that shape policy and investment ecosystems.
  2. System Demonstration in a coastal area: Rather than delivering isolated infrastructure, MENTARI 2 will pilot governance and financing models in a coastal community to inform national rural electrification strategies. Lessons from the Sumba pilot (Annex C) will guide design, ensuring replication across diverse geographies.
  3. Embedding health resilience into national electrification standards: Clean energy will be used to strengthen essential services (e.g., vaccine refrigeration, medical devices), generating evidence for integrated planning. Findings will inform tariff frameworks, procurement norms, and GoI standards – shifting from one-off benefits to systemic inclusion of resilience in energy policy.
  4. Formalised collaboration with MDBs and Development Finance Institutions (DFIs) to shape markets: Technical working groups with MDBs will co-develop policy reform packages and investment pipelines, embedding systemic reforms that unlock capital at scale. In-house expertise in BEJ will ensure diplomatic alignment and technical quality.
  5. Enhanced investor matchmaking through UK platforms: By leveraging HMG initiatives (MOBILIST, BII, UKEF), MENTARI 2 will move from ad hoc investor engagement to structured matchmaking that accelerates financial close and builds replicable investment models for domestic lenders.
  6. Non-ODA component to position UK industry in emerging markets: A capped non-ODA allocation (up to £500k) will support UK firms through feasibility studies, visibility at energy conferences, and pilot development for marine energy and grid services. This aligns UK commercial engagement with systemic reforms, creating long-term trade and investment opportunities.
  7. Streamlined delivery structure for coherence and influence: Merging the CCBN strand into Policy Reform reduces duplication and strengthens strategic coherence. Embedding advisers in BEJ ensures sustained policy influence—shifting from transactional delivery to embedded partnership.

1. MENTARI 2 offers strong alignment with UK foreign policy, climate leadership, and development objectives. It enhances Value for Money (VfM) through:
  1. Economy: Competitive procurement for core delivery.
  2. Efficiency: Streamlined strand integration and adaptive management.
  3. Effectiveness: Targeted, high-impact interventions with replication potential.
  4. Equity: Inclusive programming with GEDSI mainstreamed across all strands.
  5. Cost-effectiveness: Strategic co-financing and market shaping for UK industry.

Assessment against Strategic Case objectives:

  1. Policy Reform: The hybrid model retains MENTARI’s proven co-delivery approach with MEMR, while enabling new partnerships with NGOs and think tanks to raise public awareness and support implementation.
  2. System Demonstration: New pilots will showcase integrated energy-health-economic models in coastal areas. A balanced approach – one project via commercial contract, others via CMPs – ensures both innovation and strategic control.
  3. Investment Support: MENTARI 2 will adopt a more targeted approach to feasibility studies, focusing on projects with high bankability. Continued support to PT SMI and engagement with the market will inform future decisions on blended finance facilities.
  4. GEDSI: Each strand will have its specific GEDSI objective as mentioned in the Strategic Case. This ensures that delivery of each has specific benefits to disadvantaged communities and/or ensures analysis does not inadvertently cause harm.
  5. Secondary Benefits: The non-ODA component will enable targeted support for UK firms, particularly in marine energy and grid services. This ensures the programme contributes to HMG’s Growth agenda while maintaining ODA integrity.

Essentially, this is the most comprehensive and strategically aligned option. It preserves the UK’s bilateral influence, enhances flexibility, and enables deeper collaboration with partners. MENTARI 2 will deliver high-impact, inclusive, and scalable interventions while supporting UK commercial interests and maintaining strong VfM. It is the optimal model for addressing the full range of objectives outlined in the Strategic Case.

Appraisal of High-Level Options

Each high-level intervention option has been assessed against five strategic criteria derived from the programme’s theory of change and the objectives outlined in the Strategic Case. These criteria reflect both development impact and alignment with UK interests. Scoring is based on a scale of 1 to 5, where 1 indicates minimal contribution and 5 indicates strong alignment and high impact.

The UK’s development policy is evolving to focus on systemic change and local ownership, as articulated in Baroness Chapman’s Fabian speech. These four shifts provide a framework for modern, effective development programming. Including this criterion ensures that our delivery model reflects these principles, prioritising catalytic finance, institutional reform, technical know-how, and sustainability through local replication. It also strengthens coherence with the UK–Indonesia Strategic Partnership and demonstrates that MENTARI 2 is designed for transformational impact rather than transactional aid.

High-Level Options: Criteria
Criteria	Detail
Policy Reform	The overall impact the option will have on reducing poverty through energy transition. With particular attention to policy reform to reduce barriers to increase low carbon energy use and rural electrification to reduce poverty.
Rural Electrification	The overall impact of the option will have on producing demonstration projects to showcase alternative models to GoI on rural electrification through renewable energy sources that also create economic opportunities for the community in Eastern Indonesia.
Investment Support	The overall impact the option will have on producing an arrangement, that works within current GoI policies, to support the commercial viability of small renewable energy projects (less than 10MW) and increase Indonesia’s clean energy output.
Secondary Benefits	The overall impact the option will have on reducing barriers to investment and create commercial opportunities for UK industry.
Value for Money	The overall costs required to manage and deliver satisfactory intervention is proportionate.
Alignment with four development shifts	Measures how well each option reflects systemic change, local ownership, and catalytic finance.

Appraisal Scoring
Criteria	Option 1: / Do Nothing	Option 2: / Delivery via CMPs	Option 3: / Delivery via other development partners	Option 4: / Renew MENTARI with its existing structure	Option 5: / Hybrid: MENTARI with applied lessons learned and flexibility
Policy Reform	2	3	3	4	5
Demonstration & Rural Electrification	2	4	3	4	5
Investment Support	2	3	3	4	4
Secondary Benefits	1	1	1	2	4
Value for Money	2	4	3	2	4
Alignment with four development shifts	1	3	3	4	5
Total	10	18	16	20	27

1. The appraisal identifies Option 5 – Hybrid: MENTARI with Lessons Learned and Flexibility as the preferred delivery model, scoring highest across all criteria. This option offers the strongest alignment with both development and diplomatic objectives, combining the strategic influence of a bilateral programme with the efficiency and reach of multilateral collaboration. It enables:
  1. Targeted policy reform through co-delivery with MEMR and flexible engagement with NGOs and think tanks.
  2. Scalable demonstration pilot in a new topography that integrates energy, health, and economic outcomes in underserved communities.
  3. Focused investment support for small-scale renewables with higher bankability.
  4. Commercial diplomacy through a non-ODA component that supports UK firms in accessing Indonesia’s energy market.
  5. Strong VfM through competitive procurement, adaptive management, and strategic co-financing.

Alignment with Four Development Shifts:

1. Option 5 scores highest because it operationalises all four shifts:
  1. Donor to Investor: It uses ODA to unlock private and public finance through policy reform and bankability support, rather than substituting with grants.
  2. Service Delivery to System Support: Demonstrators are framed as system pilots with replication pathways, not as permanent service provision.
  3. Grants to Expertise: Technical assistance and regulatory know-how are the core offer; grants are used only where they catalyse structural change.
  4. International Intervention to Local Provision: Delivery is co-designed with MEMR, PLN and Indonesian Village-Owned Enterprises (BUMDES), with formal handover and replication plans embedded from inception.

1. Other options fall short:
  1. Option 4 aligns partially (strong on expertise and system support but lacks flexibility for investor mobilisation and local provision beyond pilots).
  2. Options 2 and 3 show moderate alignment (regional/CMP models embed some expertise but dilute local ownership and investor leverage)
  3. Option 1 does not reflect the shifts, as it removes bilateral influence and offers no mechanism for system change or replication.
  4. Option 5 is therefore the optimal path forward to deliver a high-impact, inclusive, and strategically aligned energy transition programme in Indonesia.

Learning from Other UK Energy Transition Programmes and ICAI Review

MENTARI 2 builds on the UK’s broader portfolio of energy transition programmes, including Transforming Energy Access (TEA), UK PACT, and Productivity for Prosperity (P4P), as well as insights from the Independent Commission for Aid Impact (ICAI) review of UK aid for energy transition (2021–2025). These sources provide valuable lessons that have directly informed the programme’s design.

Key lessons integrated into MENTARI 2 include:

1. Flexible Delivery: Successful programmes combine commercial contracts with accountable grants and MoUs to enable modular engagement. MENTARI 2 adopts a hybrid model to support co-financing and collaboration with likeminded partners.
2. Embedded Expertise: Local ownership and co-delivery with government counterparts have proven essential for sustainability. MENTARI 2 retains embedded advisers within BEJ and strengthens coordination with MEMR and PLN.
3. Investment Mobilisation: Many programmes struggle to move from feasibility to financial close. MENTARI 2 expands support for project preparation, with improved public calls for proposals to enhance pipeline quality and focusing on improving ESG data to improve investor interest.
4. GEDSI Integration: GEDSI outcomes are strongest in community-level interventions. MENTARI 2 mainstreams GEDSI across all strands through each strand having a specific GEDSI objective.
5. Adaptive Learning: Programmes with robust MREL frameworks show better responsiveness. MENTARI 2 will procure an independent MREL supplier early and embed learning cycles into programme governance. But the programme management team within BEJ will also take adaptive learning principles into its daily delivery and engagement with suppliers and beneficiaries.
6. Political Economy Awareness: Programmes that acknowledge elite capture can influence policy decisions that accelerate or slow energy transition efforts. MENTARI 2 incorporates political economy insights into its policy reform and stakeholder engagement strategies.
7. Strategic Coherence: ICAI found a lack of a unified energy transition strategy across UK departments. MENTARI 2 contributes to coherence by aligning with the UK–Indonesia Strategic Partnership, the BEJ Energy Strategy, greater co-ordination with DBT, and adopting a clear Theory of Change.
8. Portfolio Focus: ICAI noted the UK’s portfolio was spread across too many small programmes. MENTARI 2 consolidates delivery into a streamlined hybrid model with targeted interventions and a flexible fund to avoid fragmentation.
9. Monitoring & Evaluation: ICAI praised the UK’s Monitoring, Evaluation and Learning (MEL) system but flagged inconsistent Key Performance Indicator (KPI) reporting. MENTARI 2 will strengthen KPI 15 (transformational change) and ensure robust reporting across relevant ICF indicators.
10. Finance Mobilisation Risks: ICAI highlighted risks of concessional finance crowding out private investment. MENTARI 2 addresses this by focusing on enabling environments, feasibility studies, engagement with relevant expertise, and strategic engagement with PT SMI and MDBs.
11. Country Ownership & JETP Lessons: ICAI found limited uptake of UK guarantees and tensions in JETP design. MENTARI 2 applies these lessons by focusing on locally driven reforms, flexible TA, and realistic delivery models.
12. Coordination & Governance: ICAI identified blurred departmental roles. MENTARI 2 embeds joint accountability through BEJ programme governance and cross-strand advisory support.

These lessons ensure MENTARI 2 is strategically aligned, operationally focused, and responsive to the evolving landscape of UK climate finance and Indonesia’s energy transition needs.

## Commercial Case

This section outlines the commercial strategy for delivering the preferred option identified in the Appraisal Case: a renewed bilateral energy programme – MENTARI 2. Building on lessons from MENTARI 1, the programme adopts a more flexible and inclusive delivery model. It sets out the proposed delivery mechanisms, evaluates alternative funding arrangements, and explains how VfM will be achieved throughout the programme lifecycle.

Flexibility will be particularly important for MENTARI 2, as the 2024 Annual Review identified a key limitation in the contract-only structure of MENTARI 1: it restricted collaboration with NGOs, development partners, and MDBs on aligned initiatives. A Business Case amendment was required in MENTARI 1 to allow this flexibility but should have been present from the start. This insight has directly informed the more adaptive and inclusive delivery model proposed for MENTARI 2. The programme will adopt a hybrid delivery model comprising:

  1. A single core commercial contract covering all delivery strands: policy reform, demonstration projects, investment support, GEDSI, and secondary benefits to UK growth.
  2. A flexible fund to respond to emerging opportunities that align with programme objectives but fall outside the scope of the core contract. This can also be delivered via a separate commercial contract but more likely through Accountable Grants or Memoranda of Understanding (MoUs). This is to enable targeted collaboration with NGOs, multilaterals, and other development partners (subject to budget availability).
  3. A non-ODA funding stream to support UK industry engagement in Indonesia’s renewable energy sector, particularly in emerging areas such as marine energy and grid services.
  4. Programme-funded staff embedded in BEJ to co-deliver outputs, ensure quality assurance, and maintain strategic alignment with UK diplomatic and development priorities.

Requirements

Terms of reference will be detailed once the Business Case has been agreed. The BEJ programme team will work with FCDO Commercial Directorate to develop it. However, initial requirements and market capability for delivering MENTARI 2 will vary per strand and entail the following:

  1. Policy Reform
    1. Requirement: Procurement of Technical Assistance services through a commercial contract with a delivery partner experienced in energy policy reform. Will require regular engagement with GoI and other entities influential in policy development. This will be complemented by programme-funded advisers embedded in BEJ to co-deliver outputs and quality assurance.
    2. Market capability: This can be delivered through either a commercial contract or accountable grant. There are capable Indonesian NGOs that can deliver this but there is more flexibility and technical capability if delivered through a commercial entity (e.g. engineering consultancy firm).

  1. Investment Support
    1. Requirement: Engagement of a private entity with expertise in green finance and low carbon energy technologies to deliver feasibility studies and technical assistance to small renewable energy developers to help progress their projects and make them attractive for investors. Familiarity or willingness to work with financial institutions such as MDBs and BII. Ability to work closely with BEJ embedded advisers for project design and matchmaking activities.
    2. Market capability: Delivery is best suited to a commercial entity with experience in green finance and infrastructure/energy development. While some NGOs have relevant experience, the technical complexity and financial structuring required favour a private sector partner.

  1. System Demonstration
    1. Requirement: Delivery of a pilot off-grid electrification project in an Indonesian coastal community. The delivery partner will be expected to integrate both productive use of energy (PuE) and health resilience outcomes. Familiarity of working with village development enterprises required to help ensure self-sufficiency of the project after programme closure. Ad-hoc advisory support to existing Ayrton-funded projects may be required.
    2. Market capability: Can be delivered through either an NGO or commercial entity. NGOs have demonstrated success in community engagement and PuE integration. However, commercial entities may offer stronger engineering and health systems integration capabilities.

  1. GEDSI
    1. Requirement: Ensure policy analysis for GoI does no harm to underserved communities and creates benefits where possible. Support for small project developers includes detailed analysis/data on the ESG impacts of the project to improve investor interest. And a rural electrification project creating economic opportunities for disadvantaged groups.
    2. Market capability: Best delivered through specialist advisory services or NGOs with proven track record in GEDSI integration in the energy sector. Delivery partners will be expected to demonstrate GEDSI mainstreaming in all activities, with clear assessment criteria.

  1. Secondary Benefits to UK Growth
    1. Requirement: Delivered through a non-ODA funding stream, this component will actively support UK industry engagement in Indonesia’s renewable energy sector. Activities will be determined annually subject to budget allocations, but may include feasibility studies, market access support, and showcasing UK energy technologies. The programme will also promote UK methodologies and tools to influence policy and unlock commercial opportunities. Interventions will be guided by HMG’s commercial priorities and available non-ODA.
    2. Market capability: Dependent on availability of non-ODA funding and commercial priorities of HMG in Indonesia. Likely to be delivered through a commercial entity in collaboration with the BEJ programme team and DBT. The suppliers will be expected to conduct activities similar to mapping Indonesian energy needs to UK capabilities, engage UK firms through structured outreach and sector briefings, support development business cases for non-ODA support, track and report commercial outcomes.

  1. Cross-cutting needs
    1. Capacity to meet GoI’s requirements for financial compliance (i.e. responding to BAST and KAK requests)
    2. Capacity in each strand to organise and facilitate events (e.g. Focus Group Discussions and handover ceremonies)

Contract Model

Although each strand could be delivered separately, MENTARI 1 was primarily delivered through a £15 million commercial contract with a consortium led by Palladium International, complemented by programme-funded advisers embedded in BEJ. This model enabled streamlined programme management, synergies between strands to optimise outputs, strong performance oversight, flexibility, VfM, and alignment with diplomatic objectives. Having BEJ manage a single commercial contract also allowed the embassy to have more capacity to support complementary diplomatic activities that help deliver the objectives of the programme.

A Time and Materials (T&M) contract proved effective in delivering MENTARI 1 but a hybrid approach to contracting could realise VfM. This will be determined during the Terms of Reference development stage for procurement. But the initial view is to have a combination of T&M, milestone payments, and Payment by Results for the programme. The approach reflects the need for flexibility to respond to shifting GoI requests for policy analysis, a degree of certainty of the outputs when supporting project developers with technical assistance and feasibility studies, and familiarity of what was needed to deliver the demonstration project in MENTARI 1.

The core commercial contract for MENTARI 2 is expected to be classified as Silver Tier. The contract value is within this tier’s threshold, and the complexity risks builds on a proven structure from MENTARI 1, where embedded programme-funded staff in BEJ provide strong internal oversight and quality assurance. The programme’s complexity is moderate, with clearly defined strands and a single core delivery partner. Risks are well-identified and mitigated through phased contracting, quarterly reviews, and diversified delivery routes. The Silver Tier classification reflects the programme’s strategic importance while recognising the manageable delivery risks and established market capability.

To mitigate financial risks associated with potential reductions in the UK’s ODA budget – as particularly under the anticipated 0.3% GNI ceiling – a break clause will be included in the core commercial contract. This clause will allow FCDO to review and, if necessary, terminate or scale down the contract at predefined intervals, subject to budget availability and programme performance. The clause will be triggered by significant changes in funding allocations or strategic priorities, ensuring that the UK retains flexibility to adapt delivery in line with fiscal constraints while maintaining value for money and minimising disruption to programme outcomes.

High-Level Assessment Criteria

To ensure the selection of the best supplier for MENTARI 2, the procurement process will apply a robust set of high-level assessment criteria aligned with the programme’s strategic objectives and delivery needs. The criteria will be detailed at procurement stage but expects suppliers to be evaluated on:

  1. Technical Expertise and Track Record: Demonstrated experience in delivering energy policy reform, rural electrification projects, investment support, and GEDSI integration in Indonesia or similar contexts.
  2. Delivery Capability: Proven ability to manage complex, multi-strand programmes with adaptive delivery models. Experience of co-delivery with FCDO staff advantageous.
  3. VfM: Clear articulation of cost-effectiveness across the 5Es (Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness), including competitive pricing and resource allocation.
  4. Strategic Alignment: Understanding of UK foreign policy priorities and ability to deliver outcomes that support both development and UK commercial interests. Knowledge of the UK-Indonesia Strategic Partnership (once published).
  5. Partnership and Collaboration: Capacity to engage with Government of Indonesia, MDBs, NGOs, and UK industry, including co-financing and joint delivery models.
  6. Monitoring and Evaluation: Familiarity with FCDO standards for compliance, monitoring and evaluation through demonstrating strong performance management systems, ability to meet KPIs, production of quarterly and annual reviews, and quality assurance mechanisms. Familiarity with GoI accounting systems would be an advantage.
  7. GEDSI Mainstreaming: Evidence of inclusive approaches and tools when delivering analysis and projects in the energy sector.

Performance Monitoring

Performance monitoring for MENTARI 2 will be managed through a robust framework from a hybrid contract structure. Payments will be issued based on actual time worked and materials used and agreed milestones. Holdback payments linked to KPIs may also be utilised. BEJ embedded programme-funded advisers will provide ongoing oversight and co-delivery support, ensuring that outputs align with strategic and technical expectations. This approach provides the flexibility needed for adaptive programming while maintaining strong value for money controls.

1. KPIs will be refined at procurement stage but would likely entail the following:
  1. Policy Reform
    1. Number of policy recommendations adopted by GoI
    2. Number of technical assistance products delivered and implemented by MEMR
    3. Number of capacity-building sessions conducted for GoI staff
    4. Stakeholder satisfaction score from GoI counterparts
  2. Demonstration & Rural Electrification
    1. Number of households and public facilities connected to renewable energy
    2. Number of new jobs created through productive use of energy (PuE)
    3. Number of health facilities powered, and operational improvements recorded
  3. Investment Support
    1. Number of feasibility studies completed and accepted by developers
    2. Value of private finance leveraged for supported projects
    3. Number of small renewable energy projects reaching financial close
    4. Number of projects supported from PT SMI’s pipeline
  4. Gender & Inclusion (GEDSI)
    1. Number of policy recommendations outlining the impact an initiative could have to disadvantaged groups
    2. Number of technical assistance or feasibility studies produced for developers that include ESG data/analysis
    3. Number of disadvantaged groups benefiting from the new clean energy source
  5. Secondary Benefits to UK Growth
    1. Number of UK firms supported to access Indonesian energy market
    2. Number of UK-Indonesia institutional or commercial partnerships facilitated

To ensure accountability and delivery quality under the contract structure, performance against strand-specific KPIs will be monitored through quarterly reviews and deliverable quality checks. This approach balances flexibility with strong oversight, ensuring value for money while accommodating the adaptive nature of the programme.

In addition to the core contract’s internal performance monitoring mechanisms from BEJ staff, MENTARI 2 will also procure an independent Monitoring, Reporting, Evaluation and Learning (MREL) supplier through the FCDO’s Global Evaluation and Monitoring Framework Agreement (GEMFA) framework. This supplier will provide external validation of programme outcomes, assess delivery partner performance, and support adaptive management through periodic evaluations and learning reviews. The MREL supplier will be sought shortly after a future supplier for the core contract concludes their inception phase. The timing allows the Terms of Reference for a future MREL supplier to be as accurate as possible.

1. Terms of Reference for a future MREL supplier will be determined once the main commercial contract has been awarded. But would likely entail the following:
  1. Delivery of Core MREL Functions:
    1. Timely submission of reports to BEJ to align with Annual Reviews and PCR
    2. ICF KPI tracking validated
    3. Log frame alignment analysed accurately
  2. Quality Assurance and Evaluation
    1. Evaluation completion rate submitted on schedule
    2. Quality of narratives and data in evaluations as reviewed by BEJ
    3. Meeting EQUALS standards for publication
  3. Learning and Adaptive Management
    1. Adaptive Recommendations made and accepted by BEJ or delivery partner
    2. Stakeholder Engagement score from satisfaction ratings from BEJ team
  4. Compliance and Risk Management
    1. Compliance with FCDO standards
    2. Risk monitoring reports

To demonstrate that a commercial contract remains the most effective mechanism for core delivery, the following section compares alternative funding arrangements and outlines how each contributes to VfM, accountability, and delivery effectiveness:

Category	Commercial Contract	Accountable Grant (AG)	Memorandum of Understanding (MoU)
Advantages	Legally enforceable under contract law / Clear accountability and risk allocation / High FCDO control over deliverables and timelines / Strong VfM assurance through competitive tendering / Suitable for both for-profit and not-for-profit suppliers	Encourages innovation from civil society to meet a strategic goal set by the FCDO / Can be more adaptable to local contexts / Lower administrative burden than commercial contracts / Suitable for non-commercial partners	Ideal for partnerships with multilaterals or governments / Simplifies collaboration under pre-agreed framework / Lower administrative burden than commercial contracts / Supports pooled funding and joint programming / Higher flexibility in delivery
Disadvantages	Requires detailed specification upfront / Higher administrative and procurement burden / High effort to design for adaptive or exploratory programming / More difficult to terminate quickly and cost effectively	Not legally enforceable / Cannot be used with for-profit entities / Less FCDO control over delivery / VfM harder to benchmark / Private sector exclusion	Not legally enforceable / Limited FCDO control over delivery / Risk of unclear accountability / Requires strong institutional relationships / Not suitable for direct procurement of goods and services

Value for Money

1. This approach allows the programme to retain the performance and VfM benefits of a commercial contract while enabling strategic partnerships and co-financing opportunities through Accountable Grants and MoUs. The hybrid model enhances VfM by:
  1. Economy: Competitive procurement for the core contract ensures cost-effective delivery.
  2. Efficiency: Consolidating overlapping strands (e.g. merging CCBN into policy) reduces duplication.
  3. Effectiveness: Flexibility to fund high-impact NGO or multilateral-led initiatives increases reach and relevance.
  4. Equity: Rural electrification projects will target underserved coastal and non-agricultural communities.
  5. Cost-effectiveness: Benchmarking of key cost drivers (e.g. personnel, logistics, security) will inform budgeting and contract negotiations.

Early Market Engagement

An Early Market Engagement (EME) session was held on 4 July 2025 to inform the commercial design of MENTARI 2. The event attracted strong interest from both international and local suppliers, and provided valuable insights into market expectations, delivery preferences, and lessons learned from MENTARI 1. During the session, suppliers were asked about their interest in bidding for the programme. While formal expressions of interest were not recorded, the level of engagement was high, with over 60 organisations participating (even more organisations registered to join the call but didn’t attend) and many saying they do not see reasons for being unable to join a future tender.

1. Key findings from the EME also included:
  1. Route to Market Clarity: Suppliers emphasised the importance of early confirmation of the procurement route (open competition vs. framework) to enable fair and timely consortium formation. FCDO committed to ensuring a level playing field and allowing sufficient response time once the route is confirmed.
  2. Contract Structure and Budgeting: The market welcomed the hybrid delivery model but requested clarity on capital allocations for demonstration projects and the proportion of budget allocated to the commercial contract. FCDO confirmed the contract will be commercial (not non-profit) and that budget allocations reflect strategic priorities and ODA constraints.
  3. Subcontractor Participation: FCDO reaffirmed its policy against exclusivity agreements, allowing subcontractors to participate in multiple bids. This was welcomed by suppliers to promote competition and collaboration.
  4. Lessons from MENTARI 1: Suppliers highlighted the need for wider dissemination of policy outputs, more flexible contracting and budgeting, improved GEDSI mainstreaming, and broader project selection processes. These lessons have been integrated into the design of MENTARI 2.

These findings validate the proposed hybrid model and reinforce the importance of flexibility, transparency, and strategic alignment in MENTARI 2’s commercial approach. But they have also helped the BEJ programme team decide on route to market and contract value.

Route to Market

Although EME survey feedback indicated some interest in an open competition, there was strong market confidence in the FCDO’s Global Development Delivery (GDD) Framework. Many suppliers listed under the GDD Framework – particularly those in Lot 4 (Economic Development and Trade) are thematically aligned with MENTARI 2’s strategic focus on supporting Indonesia’s energy transition and JETP implementation. While Lot 1 (Climate Change) had slightly more representation among EME attendees (by one) and has relevance in advancing climate objectives, Lot 4’s thematic relevance and supplier capabilities make it the most appropriate route for the core contract. The economic development lens of Lot 4 aligns closely with the programme’s scope and ambition, reinforcing the recommendation to proceed with Lot 4.

1. Lot 4 is designed for high-value contracts (£7m–£100m) and is thematically aligned with MENTARI 2’s objectives. It provides access to suppliers with expertise in:
  1. Just Energy Transition Partnerships (JETP) and clean energy infrastructure
  2. Climate finance mobilisation, including blended finance and UK guarantees
  3. Technical assistance for policy reform, investment facilitation, and market development
  4. Green and inclusive growth, including rural electrification and energy access
  5. Strategic partnerships with UK institutions, including BII, UKEF, and the Centres of Expertise

Lot 4 supports both ODA and non-ODA activities, enabling delivery of MENTARI 2’s hybrid model and UK commercial benefit strand. It also allows for flexible delivery models, including consortium approaches and fund management functions. Most lead suppliers in Lot 4 have a presence or familiarity with Indonesia’s energy sector, providing assurance of credible proposals. Additionally, the GoI expects MENTARI 2 to be operational in early 2026, especially as the UK–Indonesia Strategic Partnership is due to be signed in early 2026. The GDD Framework offers a shorter procurement timeline, helping HMG deliver on its commitments with minimal delay.

Although GDD Lot 4 is the recommended route to market, further consultation with FCDO Commercial Directorate, particularly its Procurement Steering Board is required.

Contract Value

While MENTARI 1 operated with a £15 million contract over five years, MENTARI 2 will be delivered in the context of the UK’s ODA budget declining toward 0.3% of GNI. Although the full programme will still be up to £20 million, the primary commercial contract for delivering it will be reduced to a value of up to £10 million over five years. This reflects the budgetary constraint while maintaining delivery ambition. The contract should include provisions for cost extension, subject to the availability of additional budget and programme needs, ensuring flexibility to scale delivery in response to strategic opportunities or evolving GoI priorities.

## Financial Case
Affordability

MENTARI 2’s Concept Note has received ministerial approval for a total programme envelope of up to £20 million over five years, with the majority of spend expected to be ICF-eligible ODA, and a minor non-ODA component to support UK Growth. This allocation aligns with the UK’s strategic priorities in Indonesia and supports the upcoming UK–Indonesia Strategic Partnership, expected to launch in late 2025.

MENTARI 2 is affordable within current and projected budgets if BEJ’s requested ODA uplift is approved. Subject to this approval, the programme can be delivered in full over the five-year period. In the event of reduced resources, delivery will be scaled down with priority given to the Policy Reform strand to maintain strategic impact under low-budget scenarios.

The summary of indicative budget plan is outlined below:

Category	2026-27	2027-28	2028-29	2029-30	2030-31	TOTAL
Delivery partner - ODA RDEL	£2,065,000	£1,715,000	£1,365,000	£1,015,000	£665,000	£6,825,000
Delivery partner - ODA CDEL	£885,000	£735,000	£585,000	£435,000	£285,000	£2,925,000
Non-ODA Projects	£50,000	£50,000	£50,000	£50,000	£50,000	£250,000
Flexible Projects (e.g. DCA, Trust Fund)	£2,500,000	£1,991,250	£950,000	£950,000	£950,000	£7,341,250
MREL Supplier	£150,000	£150,000	£150,000	£150,000	£150,000	£750,000
Programme Funded Roles	£265,000	£275,000	£290,000	£302,000	£320,000	£1,658,750
Team T&S	£50,000	£50,000	£50,000	£50,000	£50,000	£250,000

TOTAL ODA RDEL:	£5,065,000	£4,221,250	£2,845,750	£2,513,000	£2,180,000	£16,825,000
TOTAL ODA CDEL:	£885,000	£735,000	£585,000	£435,000	£285,000	£2,925,000
TOTAL Non-ODA:	£50,000	£50,000	£50,000	£50,000	£50,000	£250,000
TOTAL PROGRAMME VALUE	£6,000,000	£5,006,250	£3,480,750	£2,998,000	£2,515,000	£20,000,000

The main commercial delivery partner will be responsible for delivering the core programme activities, with a combined ODA RDEL and CDEL allocation of £9.75 million. Up to £7.34 million is allocated flexibly to either accommodate a contract cost extension with the main delivery partner, buy into proposals from CMPs, MDBs, and likeminded delivery partners. Up to £2 million is allocated for programme-funded roles and operational costs, and £500,000 for an independent MREL contract to be procured via GEMFA.

The main commercial delivery partner will also be responsible for delivering non-ODA eligible activities. However, delivery of relevant activities will only take place when non-ODA budgets are available.

The commercial contract will include provisions for cost extension, subject to the availability of additional budget and evolving programme needs, allowing flexibility to scale delivery in response to strategic opportunities or GoI priorities.
Funding Arrangements

1. MENTARI 2 will be funded through FCDO’s bilateral ODA allocation for Indonesia. The programme will operate a hybrid delivery model, with the core commercial contract funded through ODA, complemented by:
  1. Accountable Grants and MoUs (subject to budget availability) for targeted collaboration with NGOs and development partners.
  2. A non-ODA funding stream to support UK industry engagement in Indonesia’s renewable energy sector, particularly in emerging areas such as marine energy and grid services. This will be sourced through a separate bid to the various non-ODA funds HMG operates.

This structure ensures flexibility to respond to strategic opportunities and evolving GoI priorities, while maintaining clear financial oversight.

This separation reinforces the shift from grants to expertise and from donor to investor, ensuring ODA remains focused on development impact.

Budget Management and Controls

1. The programme will be subject to FCDO’s standard financial controls, including:
  1. Monthly financial reporting and forecasting.
  2. Annual Reviews to assess budget utilisation and reallocation needs.
  3. Compliance with FCDO’s Programme Operating Framework and Managing Public Money principles.

1. All spending will be subject to robust review through:
  1. Annual audits for delivery partners
  2. Spot checks
  3. Regular VfM analysis using the 5Es criteria (Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness)

The spending profile for the main delivery partner is expected to decline year-on-year, reflecting the anticipated glide path of ODA budgets available to BEJ. Spending on other categories is expected to remain relatively stable across the programme period.

0.3% ODA Implications and Risks

At the time of writing, BEJ’s ODA budget to fund this programme is yet to be finalised. In anticipation of reduced resources under the UK’s 0.3% GNI ODA ceiling by FY 2027-28, the programme team has developed a tiered approach to delivery for the outer years of the programme:

	High	Moderate	Low
Policy Reform	Proceed as normal	Proceed as normal	Heightened scrutiny and prioritisation on TA requests from GoI
System Demonstrator	Proceed as normal with additional support on mainstreaming	Infrastructure expected to be built by 2027. Limited additional support to mainstreaming.	Infrastructure expected to be built by 2027. No further additional support to mainstreaming.
Investment Support	Proceed as normal	Fewer projects supported	Dropped.
Secondary Benefits	Subject to non-ODA availability.	Subject to non-ODA availability	Subject to non-ODA availability.

Definitions for High, Moderate, and Low will be determined at FY 2027-28 when 0.3% ODA budgets will be implemented. Risks for delivering high-cost activities can be mitigated by front loading budgets to the first two financial years of the programme. This is primarily aimed at the costs for the System Demonstrator pilot.

1. Financial risks will be managed through:
  1. Structured risk allocation within the commercial contract.
  2. Contingency planning for currency fluctuations, inflation, and delivery delays.
  3. Flexibility to adjust delivery modalities (e.g., shifting from contract to grant) if needed.

## Management Case

High-Level Governance

MENTARI 2 is due to be part of a wider UK-Indonesia Strategic Partnership expected to be launched in early 2026, which includes a Climate, Nature and Energy pillar. The energy part of the pillar will be supported by an existing energy transition MoU between BEJ and MEMR. This MoU previously shaped high-level engagement between BEJ, MEMR and the lead supplier of MENTARI 1. A similar approach would be taken in MENTARI 2, but an Implementation Agreement IA will be needed to ensure GoI buy-in to the programme and set expectations between the three parties. Local provision is embedded through co-delivery with MEMR and PLN, reflecting the fourth development shift.

High-level governance structures and meeting frequencies are broadly expected to follow the MENTARI 1 experience but should be flexible to respond to changes from either GoI or HMG on resourcing and staff availability. This would likely entail the following:

  1. Annual Steering Committee (ASC) – Senior official representation from FCDO/BEJ and GoI/MEMR to agree scope of works.
  2. Technical Working Group (TWG) – The ASC will be preceded by three separate TWG meetings to discuss progress and future works for each main strand (policy, investment support, and rural electrification). GEDSI adviser(s) should be embedded in each TWG.
  3. Ad-hoc meetings – These meetings are expected to take place between BEJ and MEMR on a regular basis (frequency TBD) to ensure the programme’s outputs remain aligned to both HMG and GoI interests and contribute to FCDO performance monitoring of the supplier.

The programme will also be part of a future BEJ Indonesia Energy Strategy. Governance arrangements are still being developed but expected to report to the BEJ Country Board and have regular reporting on KPIs. These will feed into the wider Country Business Plan. The programme will be primarily managed by Low Carbon Energy Team within BEJ but will work closely with other embassy teams such as the political team and DBT.

FCDO/BEJ Programme Team

The MENTARI 2 programme will be managed through a hybrid team structure combining strategic leadership, operational delivery, and embedded delivery advisory support. The SRO provides strategic oversight, while the PRO leads day-to-day programme management supported by project officers handling financial, MREL, and administrative tasks. A team of programme-funded advisers deliver technical expertise across policy reform, rural electrification, investment support, and GEDSI integration, with one adviser dedicated to best practice for MREL compliance. This structure ensures strong alignment with UK diplomatic priorities and responsiveness to GoI needs.

Overall costs for the programme-funded advisers are in the Financial Section. These will be paid from BEJ’s bilateral ODA budget. The SRO, PRO and Programme Support Officers will come out of non-ODA administrative budgets from either the UKB or CBS pay sources. All roles and funding sources will need to be flexible in anticipation of 0.3% ODA implications in future years.

Programme Role	Regular Job Title	Grade	Brief description of responsibilities (percentage of time spent on programme)
SRO	Head of Low Carbon Energy and Infrastructure	G7 UKB	Strategic direction for programme (15%)
PRO & Programme Manager	Deputy Head of Low Carbon Energy	HEO UKB	Day-to-day programme management (50%) and lead on Secondary Benefits.
Project Support Officer	MREL and Comms Officer	EO CBS	Day-to-day programme management support for financial management and MREL (80%)
Project Support Officer	Programme Support Officer	EO CBS	Day-to-day programme management support (40%)
Project Support Officer	Programme Officer	AO CBS	Ad-hoc support to programme management and delivery (30%)
Adviser	Private Sector Development Adviser	G7 UKB	Advising on ways to drive partnerships and finance mobilization to connect the programme with other UK development tools, global investors, and the JETP. (80%)
Adviser	Lead Energy Adviser (programme funded)	G7 CBS	Advising on overall approach of the programme and engagement with Indonesian government (90%)
Adviser	Senior Energy Adviser / (programme funded)	SEO CBS	Advising delivery of the Policy Strand. (90%)
Adviser	Energy Adviser / (programme funded)	HEO CBS	Advising delivery of Demonstration & Rural Electrification Strand (90%)
Adviser	Energy Adviser / (programme funded)	HEO CBS	Advising delivery of the Investment Support Strand and liaising with DBT for Secondary Benefit opportunities (45%)
Adviser	MREL Adviser / (programme funded)	SEO CBS	Role sits in a separate team but partially funded by this programme to provide best practice advise on shaping programme team and delivery partner approach to MREL and compliance with FCDO reporting standards (25%)

A monthly dashboard will be maintained by the programme team to track overall performance and provide assurance to the SRO. Any issues identified through this dashboard will be escalated to broader BEJ oversight mechanisms for its ODA portfolio. As of September 2025, these include the Monthly Programme Review (MPR) and the Quarterly Portfolio Board (QPB). The MPR focuses on financial management and compliance with FCDO standards, while the QPB provides strategic direction across BEJ’s ODA programming. VfM assessments for these programmes funded roles are available in Annex D.

The Secondary Benefits strand will be led by the PRO, with support from delivery advisers and close coordination with DBT, UKEF, and BII. Regular internal meetings will be held to align policy reform outputs with UK commercial interests where possible, coordinate bids for non-ODA funding, and identify opportunities to promote UK expertise in Indonesia’s energy transition.

Note that this structure could change to respond to any changes required to deliver the energy elements of the UK-Indonesia Strategic Partnership. At the time of writing, this is due to be launched in January 2026. Implementing the Partnership indicates a need for closer collaboration between the FCDO and DBT teams in future years.

Delivery Partner Engagement

In terms of activity delivery, the commercial delivery partner will deliver three strands: (1) to enable policies for renewable energy development in Indonesia; (2) demonstrating pilot project(s) to showcase possible sustainable and replicable off grid business model; (3) providing investment supports toward potential renewable energy projects in Indonesia to smoothen the path to achieve financial close. GEDSI objectives are present in each strand and non-ODA will be utilised to pursue Secondary Benefits/UK Growth interests.

Future delivery partners will be encouraged to organise their teams to mirror the BEJ programme team. This means that the BEJ’s SRO, PRO, programme management officers, and advisers will need to have a counterpart in the delivery partner’s structure. Regular meetings will be conducted to monitor progress against KPIs, refine outputs, and coordinate engagement with GoI. Frequency of meetings to be determined at inception phase with any new supplier, but will likely entail the following:

  1. Quarterly meetings between BEJ programme team and delivery partner to review progress and address strategic issues, manage risks, and
  2. Monthly meeting between BEJ SRO and equivalent in delivery partner for high-level discussions on delivery and performance issues
  3. Fortnightly meetings between BEJ PRO and equivalent in delivery partner
  4. Fortnightly/weekly meeting between leads of each strand to
  5. Fortnightly meetings between PSO and equivalent in delivery partner
  6. Quarterly meetings between BEJ programme team, DBT and delivery partner to discuss Secondary Benefit opportunities and non-ODA funding

Coordination with other HMG Initiatives and Flexible Funds

This programme seeks to complement and amplify the impact of other HMG initiatives with energy interests in Indonesia. By leveraging BEJ’s technical and diplomatic expertise, it ensures strategic alignment, avoids duplication, and enhances value for money. This coordination also strengthens UK visibility in the sector, enabling more coherent and effective delivery of energy-related support across government.

This was an ad-hoc part of MENTARI 1 delivery, which involved regular co-ordination meetings between the BEJ programme team and the implementing partners of Ayrton Fund’s Energy Catalyst and Accelerate 2 Demonstrate programmes, and UKPACT’s Energy Efficiency projects in Indonesia. It will also engage with the Growth Gateway programme, which at the time of writing, has projects in Indonesia linked to OECD Accession and JETP.

To complement the success of main activities delivered by commercial delivery partners, programme team will also work with other organisations through Accountable Grants or MoUs. To expand the success of investment support, programme team will collaborate with DBT at BEJ through annual bid of non-ODA funding to deliver UK market access.

MREL & Risk Management

MENTARI 2 will adopt a dual approach to MREL. An independent MREL supplier will be procured through the FCDO’s GEMFA Framework, while each technical delivery partner will be required to allocate sufficient internal MREL resources to collaborate effectively with the GEMFA contractor and ensure MREL is considered in daily programme delivery.

The GEMFA supplier will lead on quality assurance and peer review of the programme’s MEL components. This includes regular reviews of the ToC, log frame indicators, midterm and end of programme evaluations, annual lesson-learned exercises, and reporting against ICF indicators – using data provided by technical delivery partners. Subject to BEJ requirements, this may also include portfolio level analysis.

Technical delivery partners will be responsible for implementing robust MREL processes to ensure interventions are evidence-based and monitored across activity, output, outcome, and impact levels. Further details in Annex F: MREL arrangements.

To be refined together with selected delivery partners during inception period, but programme team envisage MENTARI 2 will deliver against eight ICF

The following ICF KPIs will be tracked throughout the programme’s lifetime, but these could change over time as the programme adapts to the evolving context of energy transition in Indonesia:

No	ICF KPI	Level	Reporting	Note
	ICF KPI 2 Number of people and social institutions with improved access to clean energy as a result of International Climate Finance	Output	Annually from Y2	Y1 will consist of three months inception period and activity delivery for nine months. / Programme team do not foresee feasibility to report any result from Y1 delivery, but KPI 15 may be tracked if there are immediate policy requests from MEMR.
	ICF KPI 7 Installed capacity of clean energy as a / result of International Climate Finance (MW)	Output	Annually from Y2
	ICF KPI 11 Volume of public finance mobilised for climate change purposes as a result of ICF	Outcome	Annually from Y2
	ICF KPI 12 Volume of private finance mobilised / for climate change purposes as a result of ICF	Outcome	Annually from Y2
	ICF KPI 15 Extent to which ICF intervention is likely to lead to Transformational Change	Outcome	Annually from Y1
	ICF KPI TA 2 Number of individuals and organisations informed by International Climate Finance Technical Assistance	Output	Annually from Y1	Possible to report this from Y1 as data will be available from output level of ToC and Log frame
	ICF TA KPI 3 Number of climate policies informed by ICF TA	Outcome	Annually from Y1	Unlikely to happen in Y1 unless there are immediate policy requests from MEMR.
	ICF KPI 6 Tonnes of Greenhouse Gas Emissions / Reduced or Avoided as a result of International Climate Finance	Impact	Twice, mid programme and end of programme	To be able to do meaningful reporting, programme team will report to these KPI twice during the programme lifetime.
	ICF TA KPI 5 Volume of emissions reductions avoided/supported by International Climate Finance technical assistance	Impact	Twice, mid programme and end of programme

The overall programme risk assessment is ‘Moderate’. The Strategic Risks broadly stems from Indonesia’s variable appetite on energy transition and prominent fossil fuel sector – affecting impact of this programme’s interventions. Financial risk is mainly on budget availability. Operational risks are expected to be around supplier performance and limited G&I outcomes. These risks are tempered by the fact of previous successful delivery of MENTARI1, which received A+ ratings in its Annual Reviews.

Exit Strategy

A structured exit strategy will be developed shortly after the inception phase. This will be owned by the BEJ programme team but done in collaboration with the delivery partner, with the aim of ensuring a smooth and sustainable transition at programme closure in 2031. This will include handover plans for the System Demonstrator project, technical assistance outputs, and knowledge products to relevant GoI institutions, local stakeholders, and development partners. The strategy will prioritise sustainability of rural electrification models, replication of successful approaches, and retention of institutional capacity built through the programme.

In the event that the UK’s ODA budget is significantly reduced under the 0.3% GNI ceiling or BEJ does not secure the longer-term ODA beyond the current Spending Review (SR) period, the exit strategy will include contingency planning for early closure, activating the break clause in any contracts, or downscaling. This will involve prioritising high-impact deliverables, front-loading infrastructure and policy reform activities, and identifying alternative delivery routes (e.g. through CMPs, delegated cooperation, or co-financing with likeminded partners). If possible, the demonstration project will be completed by FY 2026–27 to ensure tangible outcomes before potential budget constraints take effect.

On programme closure, the exit strategy will also include:

  1. Final dissemination of lessons learned through policy briefs, stakeholder workshops, and media engagement.
  2. A formal handover of assets and responsibilities to GoI counterparts, including BUMDES and MEMR.
  3. Closure of contracts and grants in line with FCDO financial and procurement procedures.
  4. A final evaluation to assess impact, sustainability, and opportunities for future UK engagement in Indonesia’s energy transition.
  5. Completion of a Programme Closure Report.

This approach ensures that MENTARI 2 delivers lasting value, even in constrained financial scenarios, and maintains UK visibility and credibility in Indonesia’s energy sector. The devolve step ensures sustainability and completes the shift from international intervention to local provision.

## Glossary and Annexes

Abbreviation	Full Form
AMP	Aid Management Platform
ASEAN	Association of Southeast Asian Nations
APG	ASEAN Power Grid
BAST	Berita Acara Serah Terima (Final Handover Document)
BAPPENAS	Ministry of National Development Planning
BEJ	British Embassy Jakarta
CDEL	Capital Departmental Expenditure Limit
CMEA	Coordinating Ministry for Economic Affairs
CMP	Centrally Managed Programme
CCBN	Collaboration Capacity Building & Networking
DBT	Department for Business and Trade
DCA	Delegated Cooperation Agreement
DFI	Development Finance Institution
FCDO	Foreign, Commonwealth & Development Office
GEDSI	Gender, Equalities, Disability and Social Inclusion
GoI	Government of Indonesia
GTF	ASEAN Green Transition Fund
ICF	International Climate Finance
JETP	Just Energy Transition Partnership
KAK	Kerangka Acuan Kerja (Initial Planning Document)
KPIs	Key Performance Indicators
LCR	Local Content Requirement
MDB	Multilateral Development Bank
MEMR	Ministry of Energy and Mineral Resources
MoU	Memorandum of Understanding
ODA	Official Development Assistance
PIDG	Private Infrastructure Development Group
PLN	Perusahaan Listrik Negara (State-owned utility company)
PT SMI	PT Sarana Multi Infrastruktur
PuE	Productive Use of Energy
RDEL	Resource Departmental Expenditure Limit
SDG	Sustainable Development Goal
TEA	Transforming Energy Access
ToR	Terms of Reference
UKPACT	UK Partnerships for Accelerated Climate Transitions
UKEF	UK Export Finance
VfM	Value for Money

ATTACHMENTS
ANNEX A: Additional information for Strategic Case (to be published)
ANNEX B: NIRAS Brokerage Evaluation September 2025 (to be published)
ANNEX C: MDF Evaluation of MENTARI1 project August 2025 (to be published)
ANNEX D: VfM Assessments MENTARI2 PFR (for FCDO use only)
ANNEX E: MREL arrangements (for FCDO use only)