Annual Review
(Template for Smaller Projects Programmes1)

Summary of Programme Performance
Year	23-24	24-25
Overall Output Score	n/a	A+
Risk Rating	Minor	Minor	Choose a risk rating

Programme title: Supporting Namibia's sustainable growth & socio-economic development to alleviate poverty & improve livelihoods.
Programme Value £ (full life):	£84,500		Review Date: / 14/08/2025
Programme AMP Code: 400402	Programme Start Date: 25/07/2024		Programme End Date: 01/04/2026
DevTracker Link to Business Case:		n/a
DevTracker Link to results framework:		n/a

## SUMMARY AND OVERVIEW

Programme description: / Summarise the strategic context from the programme approval document and any key changes in external context or UK priorities during the year. Include the kind of funding (e.g., ODA or non-ODA) / This is an ODA funded programme aimed at supporting Namibia to address areas of key socio-economic challenge to positively impact and improve life in Namibia. To support Post’s goals under the 2023-25 CBP to promote freedom & democracy; build defence & security partnerships to protect UK interests & values; strengthen the bilateral relationship with Namibia; support Namibia to deliver a cleaner, greener planet through climate action, adaption & mitigation activities and environmental conservation (goal 4); and empowering women & girls in key socio-economic areas on gender-based violence, education, & economic empowerment (enterprise development) (goal 5).
Intended policy objective(s) of projects within this programme. / This is taken from the Strategic Case of the programme approval document. / Supporting the empowerment of women and girls leading to more awareness on issues affecting women, building women and girls, and awareness workshops on safeguarding women (GBV awareness in rural Namibia, etc.). / Supporting Namibia’s social-empowerment programmes aimed at creating economic development opportunities for rural communities, in partnership with the World Food Programme. / Support the delivery of a free and fair election accessible to all Namibians through election engagement and youth engagement activities. / Building UK International Development visibility and awareness in Namibia through development initiatives.
Overall Programme Score / Completed by PRO / Provide a programme score between C to A++. AMP will calculate this directly based on the scores and weights assigned to each output (or performance area) in the agreed programme-level results framework. / Overall Programme Score is A+, with a project score of 118.8.
Summary supporting narrative for the overall programme score in this review. / Provide a narrative that supports the programme score, considering the detailed scoring of the outputs (or performance areas) in the agreed programme level results framework. / Where supporting evidence is politically sensitive, consider how you will capture this information in a separate annex that is not published.
Major lessons and recommendations for the year ahead / Capture the key lessons and recommendations for the year ahead, with expected timeframe. You don’t need to include the detail of all lessons and recommendations. Fewer and better specific recommendations are more useful. / Project Partner Implementation: The programme projects all have the timeline of June 2024 to March 2025, especially for financial close and payments. However, our experience has been that many implementing partners miss key deadlines or reporting, despite continuous efforts on our part, thereby requiring us to approve an extension of the project implementation activities, with no added funding as this was already dispersed at the start of the project. Therefore, we need to ensure that all implementers understand the FCDO’s timeline and related administration and are capable of adhering to these. / Delays in receiving project completion reports: Some project completion reports have been delayed due to project activities falling beyond the final agreed date for at least 3 projects, delaying full project closure. / Visits and Oversight: Site visits should be planned for earlier in the project delivery period. / Currency risk: Project partners with international agreements (UN) pose a risk to the budget when payments are made internationally in £. To resolve this potential drain to the already modest allocation – as paying in £ would take more than the agreed amount in fees and transactions costs. There was an agreement at UN HQ level for World Food Programme that we can pay locally into the WFP Namibia local account. / Communications and publicity: We learnt that implementers should be informed that communications and visibility should be part of their implementation plan from the design phase of the project. This year we requested the inclusion of media engagement articles to showcase the UK’s International Development activity in country. All the community development and food security & nutrition projects (WFP, DAPP Namibia) and the GBV activities were shared out to our social media and local newspapers. / Reiterate the importance of a whole of mission approach: This year we aimed to involve policy colleagues at Post in project design and delivery, especially in engaging with implementers from their disciplines. However, it is also important for us to ensure support to policy colleagues on continuous monitoring and evaluation and engaging with implementers during the project activity to ensure full governance and reporting compliance.

## PROGRAMME STRATEGY OR THEORY OF CHANGE

Recap from the programme approval document the intended objectives of the programme, and whether the objectives have been changed since approval.

Summarise from the programme approval documents the criteria by which projects were to be selected for funding and how project selection has operated during the year.

Describe whether the programme-level objectives are likely to be achieved. Summarise what information you have to support this assessment, for example if projects have collected and reported information from stakeholders and beneficiaries.

Conclude whether, and with what adjustments, the programme should continue. You should take into account any changes in UK priorities, changes in the contexts in which the programme operates, as well as information about how well the projects have been delivered and contributed to objectives.

As a light touch Annual Review this information will be brief and succinct.

This programme is aimed at supporting Namibia to address areas of key socio-economic challenge to positively impact and improve life in Namibia, and thereby support our wider bilateral activity as captured by the 2023-25 Country Business Plan. Specifically, projects were identified to support Post’s goals to promote freedom & democracy; build defence & security partnerships to protect UK interests & values; strengthen the bilateral relationship with Namibia; support Namibia to deliver a cleaner, greener planet through climate action, adaption & mitigation activities and environmental conservation (goal 4); and empowering women & girls in key socio-economic areas on gender-based violence, education, & economic empowerment (enterprise development) (goal 5).

The programme for 2024/25 approved to support 11 local projects in the following areas:
1. Empowering Women and Girls in key socio-economic areas on Gender Based Violence. We supported women & girls education and empowerment with K’Negongo Foundation (2 projects), a grass-roots NGO working in the Kunene & Kavango Regions to create awareness on sexual reproductive health to alleviate teenage pregnancies and other societal issues; One Economy Foundation, a large NGO, working with young mothers and women in Windhoek and Walvis Bay; with the Ombetja Yehinga Organisation, mid-sized NGO using arts and culture to bring awareness to GBV for the 16 Days of Activism Against GBV; and with Lifeline/Childline Namibia, a large NGO, training and equipping the Namibian Police Force support to build capacity to address issues of Gender Based Violence, including through Police Force GBV training on ‘gender norms, GBV (working with victims and survivors), and child protection in 4 regions;
2. Youth empowerment and women & girls' education. Sponsorship of literacy and education of youth and adolescents in rural Namibia with The Namibian Free Press’s CSR initiative to share newspapers to rural communities across Namibia;
3. Supporting Namibia to deliver a cleaner, greener planet through climate action, adaptation and mitigation. Our projects focused on food security & nutrition support considering the ongoing drought through a programme of support to affected rural communities with DAPP Namibia. This built on a multi-year project that started as a pilot 2023/24, upscaling for rural communities with very limited access to food sources based in extremely rural areas in northern Namibia. We also supported the World Food Programme to build on previous support provided in 2022/23 and 2023/24 towards a food nutrition project (in southern Namibia); in 2024/25 it was scaled up to include the Oshikoto Region in northern Namibia. This region recorded the highest rate of child malnutrition for children under 5-yrs.
4. Strengthen the bilateral relationship with Namibia. A project focused on youth empowerment, partnering with the with UN through the annual Model United Nations programme – a project we have supported since 2021/22. The scope of this meeting has shown year-on-year growth in engagement, interaction, participation and media engagement each year, reinforcing visibility of the UK brand in Namibia;
5. Conservation and Environment. Funding the collection and distribution of the Into the Wild podcast, telling Namibian stories to the UK public around climate change and the impact it has on Namibia’s conservancies and wildlife, human wildlife conflict, and how Namibian communities manage their environments sustainably.
6. Democracy & governance. A research project with the Namibia Media Trust with the objective to generate comprehensive qualitative research findings on youth political participation in Namibia, and to understand barriers and motivators. The project seeks to empower young Namibians to participate meaningfully in the 2025 Namibia Regional and Local elections, thereby promoting a more inclusive and resilient democracy.

With these projects the objectives have been achieved. The only change to the plan during the project period was to consider options to provide support on drought-related issues that arose due to the drought that was declared by the government of Namibia in June 2024, which we did by being able to continue and scale up the food security & nutrition projects. These projects had the added benefit of creating a sustainable source of income for these households from the skills learnt and community empowerment created with the domestic gardens. The DAPP Namibia-BHC flagship project saw a community garden set-up for each household in a communal plot to engage the wider community and provide a sustainable source of food security.

We have a 100% engagement policy with implementers and beneficiaries for all projects to date. The HOM/SRO and PRO/Prog. SRO and Post Communications have engaged and talked at workshops, conducted site visits to the rural food projects, and participated in locally based projects ensuring access to beneficiaries and seeing the impact of our support. However, we also require implementers to monitor beneficiaries to gauge impact.

The food security & nutrition project were initially set as multi-year projects, with the youth empowerment (MUN) being our annual youth engagement activity with the UN. These projects will no longer be possible to support as Post has not received an allocation for 2025/26. This poses a risk as unlike other missions we do not have large budgets but have been able to make an impact in rural Namibia with a very conservative budget allocation. This support adds value for money even within bilateral engagements and for local British Nationals who are then proud of the work the mission is doing in Namibia at all levels.

Delivery of Projects
All programmes will need to score the Performance Area related to Delivery of Projects. Do not delete this page.

Performance area:	Delivery of projects. [This will need to be entered on AMP as part of loading the Annual Review for approval.]
Number:		11	Score:	A+
Weighting (%):		100%	Weighting revised since last AR?	n/a

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

Summarise the projects that have been delivered this year. How many projects? What was the range of project budgets? What was the range of activities (e.g. events, research, communications), places or themes? If there are only a handful of projects, you may simply mention them all.

All projects are for Namibia, placed across 8 of the 14 regions of the country.

The programme for FY2425 was approved to support 11 local projects in areas:
1. women & girls education and empowerment with K’Negongo Foundation (2 projects with this grass-roots NGO working in the Kunene & Kavango Regions to create awareness on sexual reproductive health to alleviate teenage pregnancies and other societal issues), One Economy Foundation (large NGO, working with young mothers and women in Windhoek and Walvis Bay), with the Ombetja Yehinga Organisation (mid-sized NGO, using arts and culture to bring awareness to GBV for 16 Days of Activism Against GBV), with Lifeline/Childline Namibia (large NGO, training and equipping the Namibian Police force with sensitivity training on dealing with GBV victims and survivors in 4 regions);
2. sponsorship for literacy and education of youth and adolescents in rural Namibia with The Free Press of Namibia’s CSR initiative to share newspapers to rural communities across Namibia;
3. food security & nutrition support in light of the ongoing drought (additional programme budget support to affected rural communities with DAPP Namibia (large NGO, multi-year project as a pilot FY2324 and a flagship upscaling for rural communities with very limited access to food sources based in extreme rural areas in northern Namibia), and World Food Programme (multilateral partner, food nutrition project FY2223, scaled up for FY2324 in southern Namibia, and FY2425 scaled up to include a region in northern Namibia with the highest rate of childhood malnutrition for children under 5-yrs);
4. youth empowerment with the UN (multilateral partner, engaging youth in advancing their minds on world issues through Model United Nations – a project supported FY2122, FY2223, FY2324, FY2425. Growing in engagement, interaction, participation and media engagement each year building visibility of the UK brand in Namibia);
5. conservation & environment with Into the Wild (small UK-based NGO, telling Namibian stories to the UK public in climate change and how it affects Namibia’s conservancies and wildlife, human wildlife conflict, and how Namibian community manage their environments sustainably);
6. Democracy & governance with the Namibia Media Trust (a mid-sized NGO, to facilitate a research project with the Namibia Media Trust with the objective to generate comprehensive qualitative research findings on youth political participation in Namibia, and to understand barriers and motivators).

Women & Girls	Menstrual Hygiene Day: MH Day 2024 (Sponsorship)	K'Negongo Foundation	NAD 10,000.00	£452.55
Food security; climate, environment	Community Nutrition Gardens	DAPP Namibia	NAD 296,070.64	£13,398.56
Youth empowerment; education	Model UN	UNIC	NAD 259,888.98	£11,761.17
Environment & conservation	Journey back to Namibia	Into the Wild	NAD 106,911.40	£4,838.23
GBV safety & awareness	Training Police Officers	Lifeline/Childline Namibia	NAD 190,107.50	£8,603.24
Women & Girls; health education	Creating awareness on menstrual hygiene in schools in rural Namibia	K'Negongo Foundation	NAD 217,000.00	£9,820.25
Women & Girls	Effective parenting seminar / #BeFree Sexual Reproductive Health Intergenerational Dialogue	One Economy Foundation / #BeFree	NAD 180,000.00	£8,145.83
Food security; climate, environment	Oshikoto Region - Ikololo Community	World Food Programme	NAD 250,000.00	£11,313.65
Democracy & governance; elections	2024 Election Survey	Namibia Media Trust	NAD 250,000.00	£11,313.65
Women & girls; GBV	16 Days of Activism against GBV	Ombetja Yehinga Organisation	NAD 98,689.97	£4,466.18
Education & community development (youth empowerment)	Let's Read - Build an informed nation (Youth literacy Programme)	The Free Press of Namibia	NAD 8,500.00	£384.66

You have the option (not requirement) to attach as an annex to this programme-level Annual Review a full tabulation of projects. A suggested format is provided in this draft template.

Summarise whether the projects have been delivered according to the planned timescales, budgets and quality. Provide an assurance that risks and finances have been managed in a proportionate manner and in line with PrOF rules. This will be based on the reporting passed from the project level to the programme level.

Reflect back to the Business Case. How have the criteria and mechanisms that were put in place to select and manage projects operated in practice? Is there anything that this programme (or a future programme) could do better in future?

The rubric to score delivery of projects at programme-level is for the reviewer to weigh up whether, on balance, across all projects:

A++	Projects were delivered substantially better than expected (over delivery substantially outweighs any under-delivery).
A+	Projects were delivered better than expected (over-delivery outweighs any under-delivery).
A	Projects have been delivered as expected (any under- or over-delivery is in balance).
B	Projects were delivered below expectations (under-delivery outweighs any over-delivery).
C	Projects were delivered substantially below expectations (under-delivery substantially outweighs any over-delivery).

During this light touch Annual Review, the projects have all been delivered to the required outcomes. With only 2 projects remaining to be finalised before Programme Closure is initiated for the entire programme. Each project was assessed (DDA) accordingly when it was by a new implementer, with previous implementers’ DDAs still being valid. All agreements where in place before any payments and activities were officially started. Post engaged with all implementers continuously throughout the projects’ delivery period via email, calls, face-to-face meetings, and monthly reports where relevant or one report (projects less than 3 months).

We will see the final outcomes at the final PCR to be delivered in 2026.

Post management of the programme was facilitated with Project Board meetings chaired by the PRO/Prog. SRO with a quarterly meeting during which project proposals were approved by the PB – comprising of the SRO, DHC, CSM, Politics/Comms Officer and PA/Consular. All 11 projects were approved by the PB.

This programme was set with an overall risk appetite of minor. This was maintained for most of the programmes with only to risk profiles being above:
- Public Service Delivery & Operations (likely – major) but the likelihood of occurrence was low, yet at project design it was a risk to be aware of. The mitigation strategy noted is “Limited to low risks is noted for the delivery of programme activities based on intentionally engaging local NGOs as project implementation partners to ensure delivery and goal realisation.”
- Strategy & Context (unlikely – major) but the likelihood of occurrence was low, yet at project design it was a risk to be aware of considering working with new implementers. The mitigation strategy noted is “Tolerate and treat the risk by providing project support to grassroots communities to work through these challenges means offering much needed support.”

The individual project scoring has been entered onto AMP and will be submitted with this document.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
No recommendations from previous as this is the first year we are completing this AR process.
Recommendations for the year ahead.
- PRO/Programme Manager to ensure that all implementers understand the FCDOs timeline and related administration.
- Project completion reports have been delayed due to project activities falling beyond the final agreed date for 2 projects, delaying full project closure. Ensure all implementers understand the terms of their agreements on reporting, and activity timelines.
- Site visits should be planned for earlier in the project delivery period.
- Project partners with international agreements (UN) pose a risk to the budget when payments are made internationally in £. To resolve this Post should notify and ensure partners provide local bank accounts for payments.
- To ensure UK visibility on project activity all proposal should include a communications plan approved by the Post Communications Officer – with social media and real media engagement planned.
- Involve policy colleagues at Post in project design and delivery, especially in engaging with implementers from their disciplines. PRO should support policy colleagues in continuous monitoring and evaluation and engaging with implementers during the project activity to ensure full governance and reporting compliance.

Briefly summarise any planned learning that has taken place, using the table below (if helpful) or a simple narrative supporting the score.

First, recap the questions to which the programme was seeking answers.

Next, describe any deliberate learning activities undertaken at the programme or project level. These will be proportionate to the size and style of the projects, for example wash-up meetings, and follow up conversations with external participants.

Last, assess whether the learning activities have or will lead to concrete changes, such as scaling up, replicating or exiting from activities. You can refer to the learning questions or priorities in your results framework.

Learning Question	Learning Activities	Answers and Actions
n/a
n/a
n/a

The following descriptions can be used to assign the scoring.
A++	The programme has effectively generated reliable learning that has been used both within and outside the programme.
A+	The programme has effectively generated reliable learning in a regular and systematic way and has used this to guide action within the programme.
A	The programme has generated reliable, planned learning to guide action in within the programme.
B	The programme has not generated planned learning to a sufficiently high standard.
C	The programme has not generated any actionable learning or has not followed through on plans to generate learning or has made significant changes without using evidence