## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1 | Impact indicator 2 | Details of additions for clarifications and filling in missing data Baseline data amended from' In 2024 there were 68422 application and 24605 (36%) received a scholarship' to 'In 2024 there were 36,414 girls application and 15,251 girls (41%) received a scholarship'. | Atupele Chilalire | 2025-03-18
2 | Impact indicator 2 | Milestone 1: August 2025 (end of year 1) updated from ' Targets will be set 6 months before AR and after discussing with Ministry.' to 'At least 15,251 girls receive secondary scholarships | Atupele Chilalire | 2025-03-18
3 | Impact indicator 2 | Milestone 2: August 2026 (end of year 2) updated from ' Targets will be set 6 months before AR and after discussing with Ministry.' to 'At least 15,251 girls receive secondary scholarships | Atupele Chilalire | 2025-03-18
5 | Output indicator 3.2 | Milestone 2: August 2026 (end of year 2) updated from 'Number of community meetings TBD' to '28 engagement with communities around each school conducted . Follow up engagement meeting will be conducted based on need.' | Atupele Chilalire | 2025-03-18
6 | Inputs (£) | Inputs of budgets in (£) for FCDO and govenment have been amended from zero to reflect estimate budgets totaling to programme budegt of £400,000. | Atupele Chilalire | 2025-03-18
7 | Outcome 2 | Baseline data, milestone yr1 has been amended from 'TBD after base line data analysis' to reflect 'Locus of Control: 4.0 (5.0 in boarding schools and 3.5 in CDSS) Aspirations: 36% (48% boarding, 30% CDSS)', Baseline data, milestone yr 2 has been amended from 'TBD after base line data analysis' to reflect ' Locus of Control 4.8 (5.7 in boarding schools and 4.4) Aspirations 46% (58% boarding, 40% CDSS) and Loucs of Control ' and ' 5.4 (6.2 in boarding schools and 5.0 in CDSS) Aspirations 54% (65% boarding, 50 %CDSS )' | Atupele Chilalire | 2025-04-11
8 | Output indicator 1.1 | The output indicator amended to include dissagregated by 'initial school attendance' | Atupele Chilalire | 2025-04-24
9 | Output indicator 2.3 | The output indicator has removed 'academic clinic' and inserted 'performance reflective sessions' | Atupele Chilalire | 2025-04-24
10

## Template
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
Bridge for Girls Education
IMPACT (2 indicators) | Impact Indicator 1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: September 2025 (end of year 1) | Milestone 2: Sept 2026 (end of year 2) | Comment: the strength of causality here is very low, and the impact-level indicators are mostly here to track the big-picture trend in indicators that matter Comment: there will be growing demand for scholarships but the number of girls receiving scholarships will not be increasing considering that scholarship donations are likely to diminish due to the USAID and other donors aid freeze. Education sector report shows higher figures for applicants and recepients of scholarships but they are not dissagregated. So we have used 2024 secondary schools bursary data which was not published.
More girls can reach their aspirations in life through more schooling and better results | Gender Parity Index in secondary education, disaggregated by rural status and disability | Planned | 0.99 0.98 for rural and semi-urban 1.04 for urban | 1 1 for rural and semi-urban 1.04 for urbabn | 1.03
|  | Achieved |  | 0.999 in rural schools, 1.056 in semi-urban schools, and 1.057 in urban schools
Source
EMIS data
| Impact Indicator 2 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
| A higher number and percentage of girls are receiving secondary scholarships, disaggregated by rural status and disability | Planned | In 2024 there were 36,414 girls application and 15,251 girls (41%) received a scholarship | At least 15,251 girls receive secondary school scholarships | At least 15, 251 girls receive secondary school scholarships
|  | Achieved |  | 14,479 girls received scholarships
Source
EMIS data and scholarship database
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions for outcomes to convert into impact
Identified Girls attend school more regularly and can concentrate on their studies, with better performance and retention | Proportion of scholarship recipients under this project who pass the year (achieve 50% or more marks in the assessment) | Planned | NA | 60% | 70% | Scholarships and support, including CHATS, as well as sensitisation and safeguarding support, help disadvantaged girls remain in school, therefore contributing to better GPI (GPI is below 1 because of higher girls' dropout); remaining in secondary school has many benefits including being able to reach own aspirations.
|  | Achieved |  | 39% 33% in Phalombe 45% in Ntchisi 77% for boarding (69% Phalombe and 82% Ntchisi) 30% for CDSS (25% in phalombe and 35% in Ntchisi)
Source
AGE Africa database triangulated with school perfomance records
| Outcome Indicator 1.2 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions for outcomes to convert into impact
| Scholarship recipients attend classes regularly | Planned | NA | All scholarship recipients attend 80% of classes | All scholarship recipients attend 80% of classes | Scholarships and support, including CHATS, families sensitisation and safeguarding support, help disadvantaged girls focus on school and therefore attend more frequently.
|  | Achieved |  | 93% of the scholars attended 80% of the classes 96% in Ntchisi and 90% in Phalombe
Source
Age Africa database and triangulated with School class attendance registers
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions for outcomes to convert into impact
Girls in identified schools, including the scholarships recipients, have more agency, support, and higher aspirations for their life | Girls in identified schools, including the scholarship recipients, have more agency and higher aspirations for their life based on a) statistically significant and policy relevant improvement in measurements of locus of control, agency, and aspirations; b) qualitative research findings | Planned | Locus of Control: 4.0 (5.0 in boarding schools and 3.5 in CDSS) Aspirations: 36% (48% boarding, 30% CDSS) | Locus of Control 4.8 (5.7 in boarding schools and 4.4) Aspirations 46% (58% boarding, 40% CDSS) | Locus of Control 5.4 (6.2 in boarding schools and 5.0 in CDSS) Aspirations 54% (65% boarding, 50 %CDSS ) | The tools used for assessing agency, locus of control and aspirations are culturally appropriate and are able to approximate meaningful changes in how the girls approach their future. The qualitative researcher is independent and able to measure meaningful feedback that goes beyond the "what we want to hear" feedback. The survey is carried on according to a robust metodology using precision sampling and in a consistent way. Higher agency and aspiration will help in motivating the girls to study hard and remain in school
|  | Achieved |  | Locus of Control: 4.9 overall (Boarding: 5.8, CDSS: 4.3) Aspirations: 45% overall (Boarding: 59% CDSS: 38%)
Source
Baseline survey with 244 girls who are scholars (selected randomly from the full list) and 244 girls who are non-scholars but CHATS participants (also selected randomly). Agency indicator validated. Qualitative sample should be discussed and agreed with FCDO and include an externally hired qualitative researcher.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
| 0 |  | 0 | 0 | 0 | 0
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 (Weight 40%) | Output Indicator 1.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions for outputs to convert into outcomes
The secondary education of at least 500 disadvantaged girls in Ntchisi and Phalombe are receiving scholarshpis and living expenses support | At least 500 vulnerable but academically well scoring girls in Ntchisi and Phalombe to which Age Africa pays school fees, disaggregated by initial school attendance, district, grade and disability status | Planned | 0 | 504 | 504
|  | Achieved |  | 504 girls (245 in Ntchisi, 259 in Phalombe) 413 in CDSS, 91 in boarding Ntchisi (200 CDSS, 45 Boarding, 168 in form 1, 1 in form 2, 76 in form 3) Phalombe (213 CDSS, 46 Boarding 161 in Form 1, 2 in Form 2, 96 in Form 3) 26 girls with Disability (Ntchisi 15, Phalombe 11 Boarding 21 CDSS 5) Hearing impairment 5 Speech-3 Visual Impairment-12 Physical -4 Medical-2 Ntchisi: Hearing impairment-3, Medical-2,Visual Impairment-9, Physical -1 Phalombe: Hearing impairment-2, Visual Impairment-3, Physical -3,Speech impairment-3
Source
Main source is AGE Africa database. This will then be triangulated with school records and receipts as well as field visits from FCDO
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
| 241690 | 0 | £443,763 (assuming govt supports 54% of the 15,251 scholarships based on Mk120,000 value for every beneficiary.) Mk120,000*54%*15,251/2222) | £347,574 assuming other stakeholders/donors contributes 42.7% of all scholarships. Mk120,000*42.7%*15,251/2222 (since FCDO contribution to 504 scholarships representing 3.3% of scholarships) | 1033027 | These calculations are based on proportion of bursary provision in 2024 which states that 54% of 15,2514 scholarships were mde by government and 46% by other donors and stakeholders
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 (Weight 30%) | Output Indicator 2.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions
Disadvantaged girls- including the ones receiving scholarships- are benefitting from complementary academic and life skills support | Number/percentage of CHATS session delivered satisfactorily conducted in a year in each school, disaggregated by school type (CDSS vs boarding) and location (more than 10km from trading centre or not) | Planned | 0 | CHATS sessions to be conducted 8 times per term per school; 60% of these should have satisfactory quality. | CHATS sessions to be conducted 8 times per term per school; 80% of these should have satisfactory quality. | '- due to society and cultural harmful norms, girls have low self-esteem and agency which is limiting their aspirations and hence motivation to study hard. CHATS helps them with higher aspiration and agency for their life - girls who are struggling have the foundational learning basics that will allow them to catch up if offered remediation classes - lack of knowledge and negotiation in life skills, including SRH, is letting girls behind. CHATS can help the girls negotiate better SRH and hence reduce dropouts - Girls are engaged and find the lessons relevant and actionable; - it is possible to timely identify girls who are struggling; - academic clinics are hig quality and help with remediation, girls manage to find the time to attend it.
|  | Achieved |  | 414 CHATS sessions conducted (214 in Phalombe, 199 in Ntchisi) 83% satisfactory quality 87% in Ntchisi, 80% in phalombe
Source
Programme data, triangulated with monitoring visits. All 28 target schools establish CHATS and conduct at least 8 sessions (times) per term.
| Output Indicator 2.2 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
| Number/Percentage of girls regularly participating in CHATS sessions, disaggregated by school type and location and disability | Planned | NA CHATS have just been introduced in the schools | 60% of girls attend regularly (regularly=75% of the CHATS sessions) | 80% of girls attend regularly (regularly=75% of the CHATS sessions)
Achieved
Source
Programme data backed up by attendance registers, triangulated with monitoring visits Participation is defined as attending at least 75% of CHATS sessions
| Output Indicator 2.3 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
| Scholars who are struggling attend performance reflective sessions with support of teacher and family. | Planned | NA | '- 90% of the struggling scholarship recipients come to the performance reflective sessions '- 30% of those who attend without a family member are visited at home, disaggregated by school type
Achieved
|  | Achieved |  | "100% of the scholars attended performance reviews and academic clinics 94% attended with family/guardian "
Source
1) Struggling scholars are All scholars with an average score of less than 50 in their end of term exams which is based on the school reports provided by the schools) 2)These performance reflective sessions are conducted once in a term specifically in january, april/May and september/October depending on when the term opens. Each girl attends one session a term and a followup is based on action points that were agreed.3) attendance to the session is captured using the a perfomance and academic clinic checklist that the scholar, teacher and AGE africa officer signs.
|  |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
| 99680 |  | £573,650 (considering unit cost of teaching and learning in secondary schools per learner per year is US$298, 2024 EMIS report) then govt contribution estimate is 298*2500*0.77 (2,500 girls is an estimate of learners who attend CHARTS. This includes 90% of girls on scholarship that receives academic clinic) | 0 | 673330
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 (Weight 15%) | Output Indicator 3.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions
Girls’ families are more supportive of their education | All guardians of scholars sign social contract, disaggregated by location and sex of guardian; | Planned | NA | 504 guardians signed social contract at baseline (male/female) | 504 guardians have renewed the social contract | 1) girls are systematically penalised in their education because asked to do chores and help in the family instead of being able to focus on their education; 2) Poverty create vicious incentives for parents to marry off girls instead of keeping them in education; these sensitisation meetings can conuteract this vicious incentive by proivding information on returns to education; 3) the sensitisation meetings are relevant and frequent enough and speak to the parents in a way that can change their behaviour; 4) the conuseling is relevant and high quality enough that can improve the family situation
|  | Achieved |  | "504 guardians signed contracts: 245 in Ntchisi and 259 in Phalombe Ntchisi 82 males and 163 females Phalombe 56 males and 203 females 28 community sessions done. 1 per school"
Source
Signed copies of social contracts backed by school FCDO monitoring reports
| Output Indicator 3.2 communities around the school are sensitised on importance of education |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
|  | Planned |  | 28 engagement meetings (1 per school) . Follow up engagement with communities around the schools to be conducted based on need. | 28 engagement meetings (1 per school) . Follow up engagement to be conducted based on need.
|  | Achieved |  | "26 community engagement sessions (1 per school:11 in Ntchisi, 15 in Phalombe).
Source
AGE Africa sensitisation reports.
|  |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
| 29315 |  | 0 | 0 | 29315
FCDO (FTEs)
OUTPUT 4 (Weight 15%) | Output Indicator 4.1 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2) | Assumptions
The immediate community around the school is trained in preventing, recognising and responding to safeguarding risks | Number of traditional authorities/community leaders, headteachers, facilitators and mentors in secondary schools trained and actively engaged in safeguarding mesaures | Planned | NA | 28 Headteachers 28 Faculty advisors 4 mentors 112 peer leaders/facilitators (NA) community leaders | 28 Headteachers 28 Faculty advisors 4 mentors 112 peer leaders/facilitators (NA) community leaders | Lack of training and sensitisation is constraining the ability and willingness of the school and community to recognise and manage safeguarding constraints.
|  | Achieved |  | 28 Headteachers 28 Faculty Advisors -26 Females 2 Males 112 peer leaders all females 4 mentors all Females 282 community leaders -197 males and 85 Females (PTA,Teachers, PEAs, TAs, Mother group, BoG, VDC,ADC, MACODA, CPW
Source
Programme data backed up by signing sheets
| Output Indicator 4.2 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
| Percentage of schools that have taken verifiable action to improve the safeguarding of the children since the training (follow through their plan) | Planned | NA | 30% | 60%
|  | Achieved |  | 100% (100% installed suggestion boxes 77% elected safeguarding committees,100% have SEAH posters with reporting numbers)
Source
SEAH registers, Staff meeting minutes, presence of safegurading forcal person at a school, evidence of cascaded SEAH Orientation at School level. Document between FCDO and AgeAfrica agreeing on what constitutes "action"- these need to be tangible changes (i.e. "establishing a committee" is not enough, it needs to show what has actually been done)
| Output Indicator 4.3 |  | Baseline: Sept 2024 data or as close as possible | Milestone 1: August 2025 (end of year 1) | Milestone 2: August 2026 (end of year 2)
| Number and percentage of SEAH cases that were resolved within the stipulated timeframe, disaggrgeated by location and type of action taken | Planned | NA Data for SEAH cases in the schools to be collected for documentation | 50% of cases identified are resolved within 6 months | 60% of the cases are resolved within 6 months
|  | Achieved |  | 9 cases reported (Ntchisi 1, Phalombe 8) 0 resolved
Source
AGE Africa SEAH registers, Activity reports. Timefarame is 6 months
|  |  | Baseline | Milestone 1 | Milestone 2
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
| 29315 |  | 0 | 0 | 29315
INPUTS (HR) | FCDO (FTEs)

## Budget inputs
Age Africa budgets on outputs
Budget Summary 2024-2025 and 2025-2026 | Totals | M&E costs shared in ratio of 30:30:40 | Allocations to outputs
Comprehensive Scholarship Packages- | 205390 | 36300 | 241690
Creating Healthy Approaches to Success (CHATS) | 51280.22 | 48400 | 99680.22
Community Engagement , Partnerships and SEAH (split by 50% each to outputs 3&4 | 22330 | 36300 | 58630 | £29,315 split into outputs 3&4
Monitoring and Evaluation, Admini and HR | 121000
GRAND TOTAL BUDGET | 400000.22 | 121000 | 400000.22

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.