## Annual Review Template

Title: Bridge for Girls Education Programme (BGE)
Programme Value £ (full life): £500,000		Review date: 06/11/2025
Programme Code: [400404]	AMP start date: 06/08/2024	AMP end date: 31/08/2026

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	D0006081.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400404 Documents

## A: SUMMARY AND OVERVIEW

Description of programme

The Bridge for Girls’ Education (BGE) Programme is a two-year initiative led by Advancing Girls’ Education in Africa (AGE Africa), with a £500,000 budget. It supports academically capable but economically disadvantaged girls who have completed primary school and gained admission to secondary school but are at risk of dropping out due to poverty.

Implemented in 28 secondary schools across Ntchisi and Phalombe districts, BGE supports 504 girls and aims to: 1) Improve school attendance, retention and progression, 2) Enhance academic performance, 3) Strengthen girls’ agency and aspirations.

These outcomes are pursued through four key components: 1) Scholarships, 2) Academic and life skills support, 3) Community engagement, 4) Safeguarding.

Originally scheduled to end in 2026, BGE was to transition into the bilateral Maziko a Maphunziro (Maziko) programme and expand to 1,500 girls. However, due to ODA funding cuts, the focus will now be on supporting as many of the existing girls to complete their secondary education as possible.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect a programme in transition.

About changes to UK ODA

- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

BGE receives a ‘A’ score in its first year. This is due to good progress against most outputs, although this review does highlight areas of underperformance in terms of programme management, particularly timely and high-quality reporting and slow resolution of safeguarding cases.

The programme met its target under Output 1 of supporting 504 disadvantaged girls, including 26 with disabilities, through scholarships, stipends, and in-kind support such as educational and hygiene supplies. It adapted to inflation and food insecurity by shifting from in-kind support to cash disbursements. Solar lamps were also distributed to girls in Community Day Secondary Schools (CDSS) to address electricity shortages and support evening study. However, the programme underperformed on outputs related to academic and life skills support, and safeguarding:

Output 2: Fell just short of its target for CHATS (Creating Healthy Approaches to Success) session delivery, despite strong participation and session quality.
Output 3: Met its target for community sensitisation sessions.
Output 4: Met awareness and training milestones but has had challenges resolving Sexual Exploitation, Abuse and Harassment (SEAH) cases, indicating a need for more focus on these areas.

Major lessons and recommendations for the year ahead

Academic underperformance remains a key challenge for the supported girls, driven by teacher shortages (particularly in English) and language barriers. Girls in boarding schools outperform their peers in Community Day Secondary Schools (CDSSs) across academic performance, aspirations, and agency.

The CHATS life skills programme has been effective in building girls’ confidence and aspirations. However, its modules and delivery approach could be updated to address emerging issues such as safeguarding and climate to maximise impact.

Community ownership and commitment appear to have contributed to improved attendance and support for education. However, safeguarding systems require further strengthening through capacity-building at school level, ensuring trust in reporting and case management systems, as well as overall improvements in prevention, awareness, reporting, and case management efforts.

Recommendations:
- Academic performance: Advocate with the Ministry of Education (MoE) and school administrations to scale-up targeted academic support and remedial classes by December.
- CHATS: Strengthen the CHATS modules and delivery through refresher training for peer facilitators and focus on emerging issues, such as safeguarding, by December.
- Mentorship: Improve the mentorship programme through recruitment of more role models from within the districts, including disabled teachers and peers, by December.
- Safeguarding: AGE Africa should outline enhanced safeguarding measures at school level and how they plan to strengthen case management by mid-November. This must include prompt reporting of cases to Safeguarding Investigation Team (SIT), escalation of unresolved SEAH cases to the District Child Protection Committee (DCPC) while also involving Ministry of Education.
- Community engagement: Establish a mechanism to ensure community action is taken following social contracts and engagement sessions, and that progress is tracked and community involvement is sustained, by December.
- Equity: AGE Africa should investigate if any targeted support can be provided to girls in CDSSs who are falling behind their boarding school peers in terms of their learning, aspirations and agency, by December and ongoing.
- Programme management (by end November):
- AGE Africa and FCDO to agree KPIs to strengthen quality and timeliness of programme management and reporting. This should include monthly meetings with FCDO.
- All log frame targets should be disaggregated by type of school and should only be considered achieved when achieved for girls in both types of schools.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change in the business case is summarised below.

The programme aims to improve retention and progression of vulnerable girls in secondary school through a sequence of outcomes supported by targeted interventions and key assumptions.

Initially, it provides school fees and living expenses to girls selected for secondary school but unable to afford it, based on the assumption that funding is both adequate and well-targeted. Once enrolled, girls receive mentorship to help them overcome barriers—particularly social and cultural pressures—that contribute to dropout. The programme assumes that with foundational skills and reduced household burdens, girls will remain in school and progress academically.

While the overall logic remains valid, some assumptions require revision. Only 39% of scholarship recipients passed the 2024/25 academic year exams, indicating that many lack the foundational skills needed to succeed. Low pass rates among vulnerable girls are driven by structural and contextual challenges. Most girls attend under-resourced Community Day Secondary Schools (CDSSs), where teacher shortages—especially in English—limit learning quality. Long commutes and poor infrastructure further reduce study time and increase fatigue, while language barriers make it difficult for students to grasp core subjects taught in English. Despite strong attendance and improved self-agency, these girls often lack foundational academic support. However, the assumption that mentorship can counteract social and cultural pressures appears to hold as dropout rates in targeted schools are 2.7%, compared to the national average of 4.9%. Though the current sample is too limited for firm conclusions, checks from schools suggest that scholarship beneficiaries are often above school averages and doing much better compared to those without scholarships.

To better align with the programme’s four outputs—scholarships, academic and life skills support, community engagement, and safeguarding—this Annual Review recommends updating the theory of change. This will clarify the linkages between outputs and how they collectively contribute to the intended outcomes.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track for two of its three outcome indicators. School attendance remains high, and the percentage of girls aspiring to remain in school increased from 36% in 2024 to 45% in 2025, just below the 46% target. The average locus of control score, a proxy for self-agency, rose from 4.0 to 4.8, reflecting improved confidence and motivation.

While these are encouraging signs, academic performance remains a concern, particularly in CDSSs where girls face long commutes and inconsistent teacher availability. As of the third term of the 2024/25 academic year, only an average of 39% of students scored above 50%, with 79% in boarding schools and 30% in CDSSs. Persistent challenges in English continue to hinder overall academic achievement.
[note] There are 90 students in boarding schools and 414 in CDSSs. The average has been weighted as it is otherwise less representative of the situation (average 53.3%)

Outcome indicator	Milestone(s) for this review	Progress
1.1 Proportion of scholarship recipients under this project who pass the year (achieve 50% or more marks in the assessment)	60%	39% / (Boarding: 77%, Phalombe 71%; Ntchisi 82% / CDSS: 30%, Phalombe 25%, / Ntchisi 35%)
1.2 Scholarship recipients attend classes regularly	All scholarship recipients attend 80% of classes	93% of the scholars attended 80% of the classes / 96% in Ntchisi and 90% in Phalombe
2.1 Girls in identified schools, including the scholarship recipients, have more agency and higher aspirations for their life based on a) statistically significant and policy relevant improvement in measurements of locus of control, agency, and aspirations; b) qualitative research findings at endline	Locus of Control 4.8 (Boarding: 5.7, CDSS: 4.4) / Aspirations 46% (Boarding 58%, CDSS 40% CDSS)	Locus of Control: 4.9 (Boarding: 5.8, CDSS: 4.3) / Aspirations: 45% overall (Boarding: 59% CDSS: 38%)
[note] Locus of Control method and interpretation: - Locus of Control (LoC) is the mean score on AGE Africa’s short-form instrument adapted from Nowicki–Strickland (1–7 scale; higher = more internal LoC/greater personal agency). Figures reported are group means. - Aspirations is the percentage of girls classified as “high aspirations” using AGE Africa’s aspirations index; “high” is defined against a pre-specified threshold in the MEL Data Dictionary (see Annex). - “Overall” values are respondent-weighted averages across school types; Boarding and CDSS are shown for disaggregation by school type. Minor differences reflect rounding. - “Statistically significant improvement” refers to change from baseline to latest round evaluated with two-sided tests at α = 0.05, with standard errors clustered at school level. - “Policy-relevant improvement” is interpreted as a shift large enough to influence programme decisions—≥0.3 points on the 1–7 LoC scale and/or ≥5 percentage points on the Aspirations share (rule-of-thumb used by the programme). - Qualitative findings (FGDs/IDIs, mentor notes, and safeguarding reflections) are used to triangulate and explain observed changes and school-type differences.
[note] LoC: t=15.9, p<0.001; Aspirations: z=5.8, p<0.001

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

While academic outcomes in CDSSs are disappointing, the programme’s demonstrated impact on attendance and girls’ agency justify its continuation. Strengthening safeguarding systems remains essential in these vulnerable communities, where increased reporting and whistleblowing indicate growing trust and awareness.

The programme remains aligned with the BHC’s bilateral support and FCDO’s broader priorities. As outlined in FCDO’s development narrative, advancing gender equality remains central to its mission. BHC Lilongwe will seek to engage MoE with international partners on the planned shift to free secondary girls’ education in Malawi from 2026, drawing on lessons from the programme and global evidence, and make recommendations with AGE Africa on implications for the programme. While the policy could free up resources for the programme, it may also have unintended consequences leading to fewer resources at school level, with increased pressure on the programme to support the schools to enable the girls to successfully complete Form 4.

## C. DETAILED OUTPUT SCORING

Output Title	The secondary education of disadvantaged girls in Ntchisi and Phalombe is supported with at least 500 girls receiving scholarships and living expenses support
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR.	no

Indicator(s)	Milestone(s) for this review	Progress
At least 500 vulnerable but academically well scoring girls in Ntchisi and Phalombe to which Age Africa pays school fees, disaggregated by initial school attendance, district, grade and disability status	504	504 girls (Ntchisi 245, Phalombe 259) / 26 girls with disability (Boarding 21, CDSS 5, Ntchisi 15, Phalombe 11)

Briefly describe the output’s activities and provide supporting narrative for the score

AGE Africa supports school fees for 504 girls in Phalombe and Ntchisi districts, exceeding the target of 500. This includes 26 girls with disabilities. In addition to school fees, each girl received a living stipend and a package of school supplies—including notebooks, pens, laundry and bathing soap, and sanitary pads—designed to meet both educational and personal needs.
[note] Initially 70 students were identified having difficulties. After screening together with the Department of Special Needs, only 26 were found to have certifiable special needs. The others were provided support but were advised by the Department to no longer be categorised under special needs.

Two visually impaired girls received tailored materials, including Embossing and Perkins Braille Papers, instead of standard supplies. Although uniforms were initially planned, most girls already had them, so calculators and mathematical sets were provided instead. Solar lamps were also distributed to all girls in Community Day Secondary Schools (CDSSs) to support home study in areas with limited electricity.
In the first year, 14 girls dropped out due to pregnancy (7), early marriage (4) and transfer out of catchment area (3). Faculty Advisors, with support from Mother Support Groups and local officers, followed up to encourage re-enrolment. Pregnant girls were supported in accessing appropriate services, but none have returned to school. Once it was confirmed they would not return, 14 new vulnerable girls were enrolled, maintaining the total number of supported students at 504.

Describe any changes to this output during the past year, and any planned changes

A key change under this output was the shift from in-kind school supplies to cash disbursements. Cash transfers have improved learner choice, reduced delivery overheads, and reportedly increased satisfaction. Stipend logs and mentor debriefs indicate that most funds are spent on learning materials, hygiene products (e.g. sanitary pads and soap), transport, and minor school-approved expenses. Quick pulse checks show that learners prefer cash for its flexibility, timeliness, and dignity. Qualitative interviews with beneficiaries showed improved attendance and punctuality was a key benefit, particularly those walking long distances. Parents and caregivers also find it easier to meet immediate school needs, and signed logs enhance transparency. The main risks, household diversion and price fluctuations, are being addressed through clear guidance on priority spending and orientation sessions for parents and caregivers.

Lessons learned this year and recommendations for the year ahead

Given reduced ODA budgets, the programme should prioritise supporting the current cohort of girls, without replacing new dropouts. Nevertheless, follow-up with girls who have dropped out should continue, with the aim of facilitating their return to school. In parallel, retention efforts should be reinforced through the programme’s other outputs to address the entrenched gender norms that contribute to early marriage and adolescent pregnancy.

Finally, AGE Africa should continue monitoring the use of cash disbursements to assess whether they adequately meet girls’ most pressing needs in the context of inflation.

Output Title	Disadvantaged girls- including the ones receiving scholarships- are benefitting from complementary academic and life skills support
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number/percentage of CHATS session delivered satisfactorily conducted in a year in each school, disaggregated by school type (CDSS vs boarding) and location (more than 10km from trading centre or not)	CHATS sessions to be conducted 8 times per term per school: 448 in total for 28 schools / 60% of these should have satisfactory quality	414 CHATS sessions conducted (224 in Phalombe, 199 in Ntchisi) / 83% satisfactory quality / (87% in Ntchisi, 80% in Phalombe)
Number/Percentage of girls regularly participating in CHATS sessions, disaggregated by school type and location and disability	60% of girls attend regularly (regularly=75% of the CHATS sessions)	70% (Phalombe 72.5%, Ntchisi 67.5%)
Scholars who are struggling attend performance reflective sessions with support of teacher and family.	90% of the struggling scholarship recipients come to the support session / 30% of those who attend without a family member are visited at home disaggregated by school type	100% of the scholars attended performance reviews and academic clinics / All reported with family member

Briefly describe the output’s activities and provide supporting narrative for the score

Creating Healthy Approaches to Success (CHATS) is a research-based life skills curriculum developed by AGE Africa in collaboration with Malawian women. Delivered through informal, peer-led after-school clubs, CHATS covers a range of topics including sexual and reproductive health (SRH); gender and rights, and self-advocacy; study and organisational skills, career exploration and entrepreneurship, tertiary and peer support networks.
[note] Peer facilitators are selected from all classes based on classroom engagement and are trained using a standardised three-day Training Manual. Their role is to lead CHATS sessions and support their peers in developing life skills.

Girls also receive mentorship from school-based mentors, visiting professionals (e.g. nurses, doctors, bankers), AGE Africa officers, and Faculty Advisors. These mentors support school attendance, class participation, and provide a safe space for discussing sensitive issues.
[note] Mentors provide additional support to CHATS facilitators and directly mentor girls to help build confidence, resilience, and essential life skills.
[note] Faculty Advisors are responsible for supporting and guiding scholars at the school level. They monitor academic progress, encourage CHATS participation, and serve as key liaisons between AGE Africa, the school, and the students.

In the reporting period, 414 CHATS sessions were delivered against a target of 448, with 70% of targeted girls attending. On average, every school held 7 instead of 8 CHATS sessions per term, for each of second and third term. Targeting excluded the first term due to training commitments that were scheduled during the first term. Attendance was affected by scheduling conflicts with extra classes and suspension of sessions during national exams. Despite this, session quality was high—83% were rated satisfactory, exceeding the 60% benchmark. This reflects the effectiveness of capacity-building efforts for Faculty Advisors, mentors, and peer facilitators. AGE Africa spot verification was based on around a proportion of 27% of the CHATS sessions.
[note] Measured via a standard CHATS Session Quality Checklist completed by mentors/faculty advisors; spot-verified by field officers. Criteria: facilitation readiness, fidelity to session plan, learner participation, time-on-task.

A total of 307 struggling scholarship recipients (100%) participated in performance review sessions, surpassing the 90% target. Each session concluded with performance goals and a personalised learning plan, including: an English performance target, identification of two learning gaps (e.g. reading comprehension, grammar), a schedule for remedial support. Progress is tracked through continuous assessment, including quizzes, reading fluency checks, and class averages. One-on-one teacher support is arranged for girls who fall behind, with coordination from school staff.

Describe any changes to this output during the past year, and any planned changes as a result of this review. See proposed changes in the recommendations below.

Lessons learned this year and recommendations for the year ahead

Given the programme’s difficulties to meet learning outcome milestones, more targeted academic support is needed to help girls pass end-of-year exams. For example, while all the Ministry mandates remedial learning, all schools do not conduct remedial classes and AGE Africa should seek to ensure these go ahead.

The reliance on peer facilitators is reportedly affecting the quality of CHATS session delivery, due to limitations in confidence and subject mastery. In addition, the CHAT’s curriculum needs to be strengthened to address emerging issues such as safeguarding and climate, and scheduling must be better aligned with the school calendar. Transfers of teachers (Faculty Advisors) and absence of strong role models within the mentorship structure has further constrained the quality of support and created capacity gaps in managing CHATS at the school level.

To improve delivery under this output, AGE Africa should: 1) advocate with school management for academic support, building on promising school-based practices such as remedial classes, tutoring, and study circles; 2) reassess peer facilitators and conduct targeted refresher training, including pairing less experienced facilitators with trained mentors or Faculty Advisors; 3) recruit and train additional mentors and role models from local communities; 4) incorporate regular feedback from girls, facilitators, and mentors to refine session content and delivery; 5) update the CHATS curriculum to address emerging issues such as safeguarding; 6) avoid scheduling conflicts by aligning CHATS sessions with school calendars.

Output Title	Girls’ families are more supportive of their education
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review	Progress
All guardians sign social contract disaggregated by location and sex of guardian	504 guardians signed social contract at baseline (male/female)	504 guardians signed contracts (Ntchisi 245 – 82 male, 163 female, Phalombe 259 – 56 males, 203 female)
Communities around the schools are sensitised to the importance of education	28 engagement meetings (1 per school) with follow up engagement based on need	26 community engagement sessions (11 in Ntchisi, 15 in Phalombe) and 2 PTA engagement sessions.
[note] In two communities surrounding boarding schools no community meetings were held as the students from these schools come from across district rather than the immediate community. Engagement efforts targeted the Parental Teacher Associations.

Briefly describe the output’s activities and provide supporting narrative for the score

The programme met its target of 504 guardians signing social contracts across both districts. These contracts, signed during parent engagement meetings, reinforce shared responsibility between families and schools in supporting girls’ education. The presence of headteachers during the signings strengthened institutional accountability and collaboration. As a result, scholarship recipients have shown more consistent school attendance compared to non-recipients, and increased family involvement – evidenced by participation in termly academic goal-setting sessions. While students on the scholarship attended over 80% of the classes, schools report that needy students who lack school fees and are not on scholarship miss most of the classes, between four to five weeks translating to about attendance of 60% of the classes. Those who are not on scholarship but able to pay school fees also miss classes due to lack of parental support.

Community sensitisation activities were conducted in 26 schools, reaching 635 community members (383 men and 252 women). The community members included parents, mother groups, village headmen and other local leaders. These meetings aimed to review programme progress, address barriers to girls’ education, build community ownership, encourage parental support and promote inclusive education.

In Phalombe, 251 participants (188 men, 63 women) discussed issues such as early marriage, absenteeism, and limited study support at home, and agreed on actions to address them. In Ntchisi, 384 participants (195 men, 189 women) focused on performance gaps, absenteeism, and weak parental support, committing to stronger school–home collaboration to improve outcomes for girls. Some students noted that parental and community support influenced their academic performance. One student’s grades dropped after moving to a self-boarding facility but improved after her parents and community members got involved. With their support, she received a bicycle to commute from home, leading to better attendance and a rebound in her academic results.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Community engagement was strengthened over the past year through collaboration with local actors, increasing the reach and relevance of sensitisation efforts. As a result of this review, planned improvements include developing gender-sensitive strategies to boost male guardian participation and introducing tools to monitor the impact of engagement activities on community attitudes and behaviours.

Lessons learned this year and recommendations for the year ahead

While progress under this output is strong, more needs to be done to ensure action is taken following the social contracts and engagement meetings, and that progress is tracked, e.g. through follow-up meetings based on community needs. AGE Africa should put mechanisms in place for this, such as community action plans to ensure community involvement is sustained and consider including a more qualitative measure in the logframe to monitor this.

Output Title	The immediate community around the schools is trained in preventing, recognising and responding to safeguarding risks
Output number:		4	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of traditional authorities/ community leaders, headteachers, facilitators and mentors in secondary schools trained and actively engaged in safeguarding measures	28 Headteachers / 28 Faculty Advisors / 112 peer leaders / 4 mentors	28 Headteachers / 28 Faculty Advisors (26 females, 2 males) / 112 peer leaders (all females) / 4 mentors (all females) / 282 community leaders (197 males and 85 females)
Percentage of schools that have taken verifiable action to improve the safeguarding of the children since the training (follow through their plan)	30%	100% installed suggestion boxes / 77% elected safeguarding committees, 100% have SEAH posters with phone numbers for reporting
Number and percentage of SEAH cases that were resolved within the stipulated time frame disaggregated by location and type of action taken	All cases resolved within 6 months	9 cases (Ntchisi 1, Phalombe 8). Seven were reported in March and not resolved within 6 months as they were anonymous and thus challenging to fully resolve.

Briefly describe the output’s activities and provide supporting narrative for the score

The programme has made progress in strengthening safeguarding systems in schools and surrounding communities. A total of 28 headteachers, 28 Faculty Advisors, 4 mentors, 112 peer leaders, and 282 community leaders were trained in safeguarding practices. As a result, all schools (100%) have installed suggestion boxes and SEAH reporting posters, while 77% have established safeguarding committees – important milestones in creating safer learning environments for girls.

These efforts have contributed to a more supportive school environment, which is critical for improving attendance, concentration, and retention. The involvement of community leaders and the formation of safeguarding committees are positive steps toward building a culture of protection and accountability. Mother Groups and School Management Committees have also been engaged to support community-led safeguarding responses.

Nine SEAH cases were reported— 8 from Khongoloni and Migowi CDSS and 1 case from Ntchisi. At Khongoloni, anonymous disclosures limited specific follow-up. In response, AGE Africa and the District Social Welfare Office plan to use upcoming CHATS sessions to create safe, survivor-centred opportunities for voluntary disclosure and referral once schools reopen. At Migowi, AGE Africa is currently engaging Shire Highlands Education Division to push for progress. The case in Ntchisi was resolved by disciplining a teacher with warning and transfer, this happened before the programme started.

Across both sites, AGE Africa is coordinating with government stakeholders, including Social Welfare and the Ministry of Education, to advance case management, close outstanding cases, and strengthen reporting mechanisms. Efforts are also focused on building trust with learners to encourage reporting and ensure effective SEAH prevention and response.

Key challenges include limited or anonymous reporting, likely due to fear of retaliation, and a shortage of trained personnel, which constrains the scale and effectiveness of safeguarding efforts.

Describe any changes to this output during the past year, and any planned changes as a result of this review. See proposed changes in recommendations below.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

While reporting and whistleblowing is a positive sign of trust built, cases have only been reported in two out of 28 schools, and more must be done to facilitate reporting of SEAH. Trust must also be maintained through strengthened efforts to resolve open SEAH cases within the six-month timeframe and ensure victims receive appropriate support. Serious cases should be escalated more rapidly and robustly, with FCDO pushing for action at the central level with the Ministry of Basic and Secondary Education as well as the Teachers Council of Malawi. Timely and effective case resolution will enhance accountability and may encourage more disclosures.

If budget permits, expanding safeguarding training to include more teachers, school staff, and community stakeholders would improve coverage and sustainability. Strengthening collaboration with Mother Groups, School Management Committees, and local leaders would also reinforce the link between Output 3 (community engagement) and Output 4 (safeguarding), fostering greater community ownership. AGE Africa should also consider facilitating peer-to-peer learning and cluster-based support systems among schools to share best practices and reinforce a strong safeguarding culture. FCDO should also agree with AGE Africa where sufficient actions have been taken to close anonymous cases that otherwise remain open indefinitely.
## D: VALUE FOR MONEY

Key cost drivers and performance

The primary cost driver is the scholarship package—comprising school fees, living stipends, and supplies (e.g. shoes, stationery, solar lamps)—which accounts for 51% of the total budget. Staff and programme management costs represent 18.6%, while mentorship delivery (training peer facilitators and Faculty Advisors) accounts for 13%.

VfM performance compared to the original VfM proposition in the business case

Economy:
Cost control was achieved through strict procurement and strategic supplier partnerships. Transitioning to stipends and digital monitoring reduced delivery costs. Notable savings include:
- School shoes: 20–40% cost reduction via direct sourcing from BATA Malawi (from MWK 50,000–70,000 to MWK 39,599).
- Solar lamps: 47% cost reduction through TOTAL Malawi (from MWK 15,000 to MWK 7,140).

Efficiency:
Efficiency gains were realised through:
- Increasing the reach of sensitisation efforts in collaboration with local actors.
- Digital tools (e.g. Kobo Toolbox) instead of paper-based systems, saving MWK 453,600
- Reduced cost per girl retained by 4.4% and improved satisfaction through switching to cash
- Cost-sharing with sister programme

Effectiveness:
Academic achievement: 39% of scholarship recipients passed the year (vs. 60% target), indicating a gap in academic impact. However, there were strong outcomes in school attendance and improved self-agency and aspirations among girls.
The CHATS life skills programme has been effective in building girls’ confidence and the presence of headteachers during key moments strengthened institutional accountability. Scholarship recipients shown more consistent attendance compared to non-recipients, and increased family involvement.

Equity:
The programme effectively targets the most vulnerable girls, including those with disabilities and at social risk. Tailored support and safeguarding measures have contributed to a dropout rate below the national average. However, re-enrolment remains a challenge for girls who become pregnant, despite supportive policies. In addition, CDSS girls lag boarding school peers in learning, agency, and aspirations – an area requiring further investigation and support which may be outside the scope of this programme’s budget.

Cost-Effectiveness:
Cost reductions and improved delivery (as noted above) demonstrate that the programme is achieving more with fewer resources, while maintaining quality and a strong pro-poor focus. Academic achievement is significantly higher in boarding schools (77%) rather than in community day secondary schools (30%) but at a much higher cost of MWK180,000 vs MWK35,000. Although cost is not the only consideration regarding this split it should be kept under review to seek the highest outcomes.

Assessment of whether the programme continues to represent value for money

The programme continues to represent good value for money, with good performance in economy, efficiency, and equity. To enhance VfM further, efforts should seek to improve academic outcomes and addressing disparities between CDSS and boarding school learners, recognising this should target incremental gains given the wider contextual reasons behind these issues.

E: RISK

Overview of risk management

Over the past year, the programme has maintained a moderate residual risk rating across seven categories, with a generally cautious appetite across all the categories, except for the Strategy and Context category, which has a receptive appetite.

There is a strategy and context risk that macro-economic instability and inflation could lead to foreign exchange and fuel shortages, as well as potential devaluation of the local currency, all of which may disrupt programme delivery through increased operational costs, procurement delays, and reduced beneficiary reach. Additionally, climate and health-related disasters—such as droughts, cyclones, and disease outbreaks like COVID-19 and cholera—pose a risk to girls’ education, particularly if these events result in school closures or widespread hunger, which can lead to absenteeism and increased dropout rates among girls due to pregnancy and early marriages. To help mitigate against inflation and wider poverty, the programme shifted from in-kind support to stipends, helping girls meet immediate needs. To reduce pregnancy-related dropouts, CHATS content has also been strengthened to build girls’ awareness and agency and linking learners to youth-friendly health services where needed. AGE Africa also holds caregiver dialogues on re-admission rights and stigma reduction, and schools follow national re-admission guidelines when a learner is pregnant.

Policy and Programme Delivery risks are that the CHATS life skills model may not be effective in preventing dropouts and poor academic performance among girls. To mitigate this risk, AGE Africa will continue to advocate with school management for academic support, building on promising school-based practices such as remedial classes, tutoring, and study circles, reassess peer facilitators and conduct targeted refresher training, including pairing less experienced facilitators with trained mentors or Faculty Advisors; recruit and train additional mentors and role models from local communities; incorporate regular feedback from girls, facilitators, and mentors to refine session content and delivery, update the CHATS curriculum to address emerging issues such as safeguarding, and avoid scheduling conflicts by aligning CHATS sessions with school calendars.

Reputational risks stemmed from the reputational risk related to SEAH incidents and the programme’s small scale and the challenge of expanding operations with new approaches. These were mitigated through a strengthened focus on safeguarding reporting/follow up, stakeholder engagement, mentor and teacher feedback, and a process evaluation completed in June 2025 to improve delivery and credibility.  Additionally, budgetary changes and ODA cuts posed a separate reputational risk by potentially reducing programme funding and leaving vulnerable girls unable to complete secondary education.. To mitigate this, the BHC in Lilongwe committed to careful prioritisation of funds and built flexibility into the Accountable Grant agreement to extend the programme duration and ensure scholarship beneficiaries complete four years of secondary education.

Financial and Fiduciary risks included ODA reductions, fraud, and procurement policy gaps. Mitigation measures involved anti-fraud and anti-corruption policies, spot checks, and procurement policy revisions. There is also a risk of fraud due to high-value procurements for girls’ school entitlements and living stipend payments, which could lead to financial mismanagement and undermine programme credibility. Mitigation measures included the use of digital payments instead of cash where feasible, rigorous financial reporting, annual audits, spot checks with beneficiary feedback for data triangulation, and strengthening AGE Africa’s procurement systems through recruitment of a procurement officer.

Safeguarding risks are inevitably high in this context and include underreporting of SEAH incidents, high likelihood of SEAH incidents because of a range of issues including power imbalances between teachers and girls’ vulnerability due to poverty. Mitigation measures include a strong focus on safeguarding with staff trained by BHC in October 2024, installation of suggestion boxes in all schools in July 2025, SEAH posters in all schools, and improved incident tracking. There is also pro-active follow up when cases are reported at both the school, district, and central levels. Nonetheless, the slow resolution of cases is concerning, and mitigation measures need strengthening.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

FCDO approved an Accountable Grant Agreement of £400,000 in August 2024 for the programme. While a £100k climate crisis response component is included in the business case to support vulnerable girls in the event of disasters, the decision not to expand the programme means the grant will now focus solely on supporting the current cohort of scholarship beneficiaries through to completion.

The partnership with AGE Africa remained good in terms of regular communication around forecasting and ODA changes. AGE Africa submitted quarterly and annual reports, the risk register was updated quarterly, and an updated delivery chain map was submitted in August 2025, detailing risk status across all tiers. However, quarterly reports were delayed or did not meet required standards, complicating preparation for this Annual Review. This issue was discussed in the September 2025 quarterly meeting, but further action is required to get programme management back on track. Key Performance Indicators (KPIs) will be introduced by end of November 2025, as well as monthly meetings, to improve reporting quality, timeliness, and forecasting. A field visit will also take place in October, focusing on safeguarding.

An annual spot check conducted during field visits in May and July 2025 confirmed that AGE Africa maintains an up-to-date asset register. FCDO verified that asset conditions align with the register. Key assets include four motorcycles, four laptops, and smartphones.

Programme spending is on track, with £201,000 disbursed to date, representing 50% of the total Accountable Grant Agreement value of £400,000. The remaining balance is allocated for the second-year school calendar. The year one audit is currently in progress.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The programme has used multiple channels to capture and apply learning throughout the year, including a baseline assessment, regular programme monitoring visits, field visits, beneficiary feedback and quarterly reporting and review meetings.

Over the past year, the programme’s evidence base has strengthened through routine data collection, monthly verification visits, and CHATS reflections. AGE Africa uses standardised tools, including the Field Supervisors’ Monitoring Tool and digitised Kobo forms for indicator tracking, which ensures consistent and timely data collection. All tools are now fully digitised and disaggregated by district, school type, and beneficiary characteristics (e.g. disability, age, gender). This has increased confidence in attendance, retention, and progression figures.

Beneficiary feedback is collected through focus group discussions, interviews, and CHATS session observations. Scholars consistently reported increased confidence, aspirations, and school participation as direct outcomes of the mentorship and scholarship support.

The BHC programme team conducted four field visits to Ntchisi and Phalombe to gather beneficiary feedback, verify supply distribution, observe CHATS sessions, and follow up on safeguarding cases. These visits provided independent validation through consultations with Education Division Managers, District Education Offices, and other stakeholders, confirming programme fidelity. One visit, in July 2025, included the Development Director, who engaged directly with beneficiaries. Their life stories affirmed that scholarships were well-targeted, and the investment is yielding meaningful impact (see section below).

Evidence
Evidence collected during the reporting period supports key elements of the programme’s theory of change. Data shows that scholarship recipients maintain more stable attendance than their non-scholar peers, with a 2.8% drop out rate compared to 4.9% nationally. Qualitative feedback highlights ongoing economic pressures—such as transport costs, food insecurity, and lack of study materials—indicating that fee support alone may not fully prevent absenteeism later in the term.

CHATS participation appears to be associated with improved school connectedness and increased help-seeking from mentors and teachers, reinforcing its role in supporting retention and wellbeing. However, academic performance remains a challenge, with only 39% of scholars scoring 50% or higher in term assessments during the first academic term.

Beneficiary statements
I like attending CHATS at our school because it has changed my life. At first, I was involved in unhealthy relationships, performing poorly, and had no vision for my future. But through AGE Africa’s CHATS, I have developed a plan for my life and built healthy friendships. My performance in class has also improved because I now understand myself better, which has increased my self-confidence. I am grateful that apart from AGE Scholars, all girls are given the opportunity to build their agency. Bravo AGE Africa!” Clara, Mambala CDSS

 “At first, I was so shy to even ask a question in class. But after attending several CHATS sessions, I am no longer shy. Since we are encouraged to participate during CHATS, I have taken that to class. The other day I even stood in front of over 40 students and made a presentation on behalf of my group. I am so grateful to CHATS that I now have these levels of confidence.” Trinity Piyo, a student at Phalombe Secondary School

Learning
AGE Africa should continue to understand the barriers that girls in CDSSs face, to effectively be able to help address these. It would also be important to gather further evidence of outcomes from community and parental engagement, to be able to track and report on this. Finally, AGE Africa should seek to better understand how trust can be built that enable reporting of SEAH cases.

For the coming year, the BGE programme aims to deepen its understanding of the challenges faced by girls in Community Day Secondary Schools (CDSSs), particularly around academic performance, and safeguarding. Strengthening evidence on the impact of mentorship, CHATS sessions, and community engagement will be key to refining interventions. There is also a focus on building trust in safeguarding systems to encourage safe and timely reporting of SEAH cases.
To implement these learning aims, AGE Africa will continue using digitized monitoring tools, monthly verification visits, and beneficiary feedback mechanisms. Recommendations from this review—such as remedial classes, mentorship improvements, and safeguarding enhancements—will be tracked through quarterly reporting and monthly meetings with FCDO, with findings shared with stakeholders by December 2025.
The BGE programme has shown that while financial support improves attendance and agency among vulnerable girls, academic performance—especially in Community Day Secondary Schools (CDSSs)—remains a significant challenge. Factors such as poor foundation skills, long commutes, and language barriers continue to hinder learning outcomes. The CHATS life skills programme has been effective in building confidence and aspirations, but its delivery and content need updating to address emerging issues like safeguarding and climate resilience. Safeguarding systems have improved, yet slow case resolution and reporting highlight the need for more effort and robust case management.

Date of last narrative financial report	May - July 2025	Date of last audited annual statement	First audit is in progress due January 2026