Business Case: Building State Effectiveness and Accountability (BSEA)

Business Country Plan Summary: This programme contributes to the Bangladesh Business Country Plan (2025-2026) Goal 6 on Development which includes transforming into a modern development partnership focused on state effectiveness

Title: Building State Effectiveness and Accountability (BSEA) programme
Programme summary: / This programme will support the improvement of state effectiveness in Bangladesh to reduce poverty, improve service delivery and increase growth with the secondary benefit of increased trade with the UK and growth in the UK. The programme will focus on problems and institutions, supporting locally-led partnerships on specific policy problems and supporting institutions to become more independent, effective and accountable, thus promoting system improvement and the delivery of shared objectives.
What is the rationale for UK Aid spending? / The programme will contribute to the Foreign Secretary’s priorities on growth and development. The programme will contribute to the Bangladesh Country Business Plan 2025-2026 Goal 6 on Development on transforming to a modern development partnership for state effectiveness. The programme aligns with BHC Dhaka policy and programming which seeks to prevent the Middle-Income Trap and support state capacity through system reform. It builds on the UK’s comparative advantage of politically savvy support for modern development through a partnerships approach and influencing international financial institutions. An effective state is in the UK’s interest as it tackles poverty and enables growth that allows for trade with the UK and growth in the UK.
Programme Value: £19.7 million over 6 years		Country/ Region or Sector: Bangladesh
Department/Country Office confirmation of review processes		Head of Mission
Contact name		Senior Governance Adviser and Team Leader, Cross-Cutting Team
Threshold for final approval of Business Case: Head of Mission
Date of Approval of Concept Note:	28/02/2025	Name and role of Approver Catherine West MP, Minister for Indo-Pacific
Date of Approval of Business Case:	21 August 2025	Name and role of Approver / Sarah Cooke, High Commissioner to the British High Commission, Dhaka
Programme Code: 400438	AMP Start Date: / 01 October 2025	AMP End Date: / 30 September 2031
Overall programme risk rating:	Major

Strategic Case

Context and need for intervention

The nature of the state in Bangladesh

Following the creation of Bangladesh in 1971 and a famine in 1974, the social contract between elites and the majority in Bangladesh is structured around preventing crises, delivering basic services and stimulating inclusive economic growth.[1] Most recently, despite a decade of sustained growth, these gains were not inclusive and did not translate into significant improvements in public services. Rising inequality, high corruption, the lack of secure quality jobs and the concentration of power resulted in a politicised and extractive public sector which created widespread disillusionment. This culminated in the student-led protest movement in July/August 2024, which led to the fall of the government. A key driver of the protests was the inability of the state to deliver effective, inclusive services, ranging from quality education and healthcare to reliable social protection and decent employment.
[1] Gambling on Development: Chapter ‘The Bengal Tiger’ (Stefan Dercon) 2022

There is renewed hope for improving governance, public services and economic growth following the July/August 2024 protests. The Interim Government led by the Chief Adviser Muhammad Yunus has revitalised reform, opening the space for the next government. Segments of the civil service remain committed to improving public service delivery and the risk of public protests or economic crisis is encouraging political parties to think more deeply about service delivery. Bangladesh is on track to graduate from the United Nations’ Least Developed Country (LDC) status in 2026; sustaining growth will require strong governance and institutional resilience. Continued growth will have a secondary benefit of increasing trade with the UK and growth in the UK.

Why FCDO should intervene

Governance in Bangladesh is highly centralised and dominated by two political parties. The exclusive political settlement impacts on service provision and encourages basic service delivery but not necessarily the next set of challenges around improving the quality of services or encouraging economic diversification.[2] Slowing job creation and unequal growth risk entrenching inequality. This has direct implications for the UK, given the significant size of the Bangladeshi diaspora in the UK and growing potential for increased trade and investment between the two countries which will lead to UK growth.
[2] The Aid Lab: Understanding Bangladesh’s Unexpected Success (Naomi Hossain) 2017 The Aid Lab: Understanding Bangladesh’s Unexpected Success | Oxford Academic

Bangladesh runs the risk of falling into the Middle-Income Trap. This is when countries achieve middle-income status through investments in basic services and shifting labour from agriculture to manufacturing, but can not achieve the next level of wealth which requires more significant state capacity.[3] To avoid this, the country must focus on building an institutional and policy environment for sustained, inclusive development. Institutions must be capable of adapting to change, managing complexity, and responding to the needs of a dynamic economy.
[3] World Development Report 2024: The Middle-Income Trap The World Bank 2024

The weak state and low institutional accountability continue to deter investment, limit the broader impact of economic growth and enables corruption in service delivery.[4] Public service delivery remains poor, particularly in health and education, and large segments of the population, especially women and marginalised groups, struggle to access employment and social protection. Bangladesh’s economic future is threatened by risks to the Ready-Made Garments (RMG) sector as free trade agreements expire. These challenges constrain Bangladesh’s ability to realise its human capital potential and meet its commitments to the SDGs. Supporting state effectiveness is critical not only to improve public service delivery and citizen wellbeing but to create enabling conditions for trade, investment, and shared growth between Bangladesh and the UK.
[4] Forging Strength: Exploring the Dynamic Interplay between Institutions and State Capacity (Patrick A. Imam,João Tovar Jalles) IMF Working Paper No. 2025/117 Forging Strength: Exploring the Dynamic Interplay between Institutions and State Capacity

Building State Effectiveness and Accountability (BSEA) is a 6 year and £19.7 million programme which aims to strengthen state institutional capacity to deliver inclusive public services effectively while promoting transparency and accountability. BSEA recognises that public sector and institutional reforms are critical levers for increasing state capacity, which in turn facilitate better service provision and drive economic performance. This is a cross-cutting programme that can work across sectors but with a significant focus on public sector reform/institutional reform and public financial management/domestic resource mobilisation as cross-sectoral functions.[5]
[5] Is the problem driven iterative adaptation approach (PDIA) a panacea for public financial management reform? Evidence from six African countries (Andrew Lawson, Jamelia Harris) Science Direct 2023 Is the problem driven iterative adaptation approach (PDIA) a panacea for public financial management reform? Evidence from six African countries – ScienceDirect

This programme does not provide large-scale technical assistance or service delivery, nor does it advocate for replicating Western models. Instead, this programme takes a new and different approach based on a modern development partnership. It focuses on addressing system-level problems in public sector delivery and changing power relations to tip the balance of power towards more independent, effective, and accountable state institutions, with a strong emphasis on reforms that are politically viable and technically sound. This will help to improve public policy delivery, growth and trade with the UK which will support UK growth.

Lessons learned, results and evidence

a. FCDO governance interventions in Bangladesh

The UK has a long history of supporting governance in Bangladesh and in many developing countries, with programmes recognised for their politically informed, adaptive and problem-driven approaches. We are widely recognised for our ‘Thinking and Working Politically’ approaches that go beyond traditional technical assistance to address complex political realities, which is a comparative advantage compared to other international actors and donors.

The previous Transparency and Right to Information Programme (TRIP), had a component on Promoting Knowledge for Accountable Systems (PROKAS) that demonstrated the value of issue-based partnerships in Bangladesh by bringing together civil society, the private sector and state actors. It was civil-society led, unlike the BSEA programme which is state-led. PROKAS helped to improve migration governance by exploring innovative new structures, including better ways of regulating and working with the government agencies, civil society, private sector partners, recruitment agencies, local communities and aspiring migrants. BSEA learns the lessons of PROKAS but focuses on state actors i.e. civil servants.

Building on PROKAS, the current ‘Bangladesh - Collaborative, Accountable and Peaceful Politics’ (B-CAPP) programme is helping to protect civic and political space, foster collaboration, reduce corruption and mitigate tensions that lead to violence. The Asia Foundation is implementing the ‘Promoting Effective, Responsive, and Inclusive Governance’ (PERI) component which builds on PROKAS and supports demand-side change through civil-society-led coalitions who engage with state institutions. BSEA builds on this experience to support the supply-side as the focus.

The UK has worked alongside international donors such as the World Bank, IMF, UNDP and USAID on fiscal governance reforms to improve tax administration, public financial management, budget transparency and expenditure tracking in government spending, digital governance and anti-corruption. On public financial management, the UK supported the World Bank’s ‘Strengthening Public Expenditure Management Program’ (SPEMP) to improve audit, budgeting and parliamentary oversight alongside the European Union, Canada, and Denmark. The BSEA programme will build on this experience and focus on specific policy problems to achieve change.

Previous UK support for public administration in Bangladesh has some important lessons. In particular, the Department for International Development (DFID)’s Managing at The Top (MATT) programme had a significant positive impact. There were notable successes from the focus on training individuals who delivered reform projects and then went on to be in positions of senior authority and influence. This has created significant political capital with civil servants that still exists. MATT components that focused on systems reform, however, all underperformed, and the investment did not achieve its outcomes.[6] BSEA builds on this experience and has a specific focus on systems reform through testing and policy engagement to learn lessons from MATT and MATT2.
[6] Energizing the Civil Service: Managing At The Top 2, Bangladesh, 2006 - 2011 (Rushda Majeed) in Innovations for Successful Societies 2011 Civil Service Bangladesh_ToU_1.pdf

b. Other international actor support to governance reform in Bangladesh

International actors have played a significant and sustained role in supporting public administration, public financial management and domestic resource mobilisation. The World Bank (WB) is assisting Bangladesh with various reforms aimed at enhancing transparency and governance, leading major reform programmes such as SPEMP and a new PFM Reform Strategy. The WB has also provided technical assistance and policy advice on fiscal governance and procurement reforms. The new multi-year WB programme covers tax policy and administration, public finance oversight, public procurement and statistical systems. The Asian Development Bank supports structural reforms to improve domestic resource mobilisation, enhancing transparency and accountability. BSEA will engage with these reforms through supporting delivery of conditions and/or identifying new areas where the IFIs might want to invest.

The EU has funded initiatives such as ‘Towards a People-Centric PFM’, focusing on citizen engagement and budget transparency, and supported civil society and parliamentary capacity building. The EU's ‘Government to Employees’ project, among other initiatives, seeks to strengthen the skills of public sector employees to boost organizational performance and enhance the delivery of digitalized public services. UNDP Bangladesh has been working on civil service reform, decentralisation and capacity development, and has promoted gender-responsive budgeting and inclusive governance. UNDP and Switzerland’s ‘Strengthening Institutions, Policies, and Services’ programme offers technical assistance for the development of evidence-based policies, implementation, localisation, financing and monitoring and evaluation. BSEA provides a politics-first approach to public administration reform to unlock policy delivery and will align with others.

JICA is adopting a more holistic approach to public administration reform, local governance initiatives, and support for managing public investments. It has supported administrative efficiency and e-governance, training programmes for civil servants and digital transformation of public services. Canada has supported efficient public expenditure, transparency and accountability, and service delivery improvement. USAID has promoted anti-corruption, transparency, and local governance reforms, supporting digital tools for service delivery and citizen feedback mechanisms. The BSEA programme will align with other donor initiatives and focus on the UK’s niche as a politics-first, flexible and adaptive donor able to unlock policy delivery and further loans/grants from the IFIs. FCDO participates in the Local Consultative Group (LCG) structure and will use this structure to ensure donor alignment.

c. Evidence from other FCDO interventions globally

The Partnership to Engage, Reform and Learn (PERL) programme in Nigeria has had significant success in public sector reform. It focused on service delivery in health and education complemented by core governance reforms including budget transparency, budget participation and monitoring, and tax reforms. It successfully worked on tax reforms including citizen discussion on a tax system and supporting government on the tax administration apparatus. There was an explicit discussion about how extra revenues can be re-deployed for public services which helped to encourage tax collection. Results were seen in education and health spending as well as core governance reforms connected with improved budgeting, revenue management and local governance processes. PERL monitoring indicates that these reforms grew in scale, impact, inclusiveness and sustainability over the course of the programme.[7]
[7] Partnership to Engage, Reform and Learn (PERL) Programme Completion Review 2025 Project completion review (D0006687) 204822 (Published - February 2025)

Issues covered under the Transformative Action for Inclusive and Accountable Governance (TRACTION) programme in Malawi to improve economic development and service delivery are aimed at improving governance and public sector performance through adaptive, issue-based reform strategies. TRACTION includes import system reform, transparency and accountability in public procurement, education transparency and accountability, land reform and local investment planning. The programme aims to improve the accountability and responsiveness of local and national government and build coalitions for reform; the lessons will be applied in BSEA.

National CSOs supported by the Pyoe Pin II programme in Myanmar engaged in collective action around agreed issues on education, health, environment, economy, and rule of law, responding to developments in the country’s changing political and social environment. CSOs developed a stronger shared understanding of issues relevant to them and their constituents, which included policy implications and strategies for inclusive and cooperative engagement toward change, as well as organisational skills, such as skills required to effectively develop a network. The programme was also successful in building horizontal and vertical linkages between groups that would not naturally associate. Although BSEA is state-institution led, it will draw insights from the coalition-building and shared understanding aspects of Pyoe Pin II to support action-driven partnerships.

The Governance in Action (GIA) programme in Kyrgyzstan worked towards addressing political constraints to inclusive growth by targeting issues which respond to citizens’ priority needs while simultaneously strengthening governance mechanisms. It used an iterative and adaptive management approach which allowed for experimentation and flexibility to seize opportunities to work on issues where there was political traction. It brought together government officials and non-state actors to work collaboratively, and in their shared interest, to address pressing market issues. These coalitions focused on fostering the minimum level of government action required. BSEA will adopt a similar iterative and adaptive management approach with political momentum.

The States Accountability and Voice Initiative (SAVI) in Nigeria supported partners from civil society, media and state legislatures to form Advocacy Partnerships on a range of core governance and health and education service delivery problems. SAVI was successful in building inclusive, sustainable and replicable models for constructive citizen engagement in state government policy, planning, service delivery and accountability processes. The Programme for Agile Governance and Climate Engagement (PACE) is a new programme which focuses on core governance reforms, service delivery and climate action.[8] The BSEA programme builds on this experience.
[8] Nine Lessons from Issues-Based Programming (Gareth Williams) in Policy and Practice Brief 18 (2025), Policy Practice Policy and Practice Brief 18 - Nine lessons from Issue-based programming | The Policy Practice

The Accelerating Investment and Infrastructure in Nepal (AIIN) was an adaptive programme that aimed to improve the overall environment in Nepal for infrastructure and investment in order to bring about more equitable and sustainable economic growth and jobs. It contributed to FCDO’s Country Strategy Campaign Goal of Trade and Growth by supporting policy and institutional reforms, addressing key constraints and strengthening capacities in infrastructure investment, economic development, and financial sector security and stability. The project focused on policy reforms that required government buy-in and legislative action, and played an important role in influencing the government to amend the Public Private Partnership and Investment Act. BSEA will also seek opportunities to influence specific policy reforms.

d. Lessons for BSEA

There is sufficient evidence from these cases to demonstrate that problem driven iterative adaptation (PDIA) and issue-based partnerships (IBP) can be effective approaches to development programming that has proven to be successful both to bring about change at the level of issues and as entry point for more systemic change. The ODI paper ‘Working politically to support economic reforms in Kyrgyzstan: lessons from an issue-based programme’ identifies the risk of focusing on small interventions that does not lead to broader institutional reform or structural changes.[9] A key method of delivering broader institutional reform or structural change is by ensuring the programme considers the balance between the breadth of engagement with different sectors, problems and institutions and the depth of this engagement.
[9] Working politically to support economic reforms in Kyrgyzstan: lessons from an issue-based programme (Ed Laws and David Rinnert) ODI Report 2022 Working politically to support economic reforms in Kyrgyzstan: lessons from an issue-based programme

The BSEA programme learns also lessons from FCDO’s global experience on PDIA and IBP programmes by focussing on policy dialogue from the beginning as a way to encourage broader institutional reform or structural change.[10] We will ensure engagement in policy reform through programme-funded policy engagement advisers. The programme will likely engage at the local level to test changes to policy change before scaling at national level. Building on these lessons, the proposed programme will adopt a refined PDIA approach, with a sharper focus on supporting state actor-led processes and political economy analysis.[11] It will work to strengthen the performance of public sector actors and support citizen-state engagement. The programme recognises that systemic weaknesses in public administration are political. It also recognises that tackling specific policy delivery problems may be more effective than large-scale reform.[12] Unlike international partners who are constrained by funding modalities or mandates, the UK’s flexible, adaptive and politically smart approach positions BSEA to address entrenched governance blockages.
[10] Nine Lessons from Issues-Based Programming (Gareth Williams) in Policy and Practice Brief 18 (2025), Policy Practice Policy and Practice Brief 18 - Nine lessons from Issue-based programming | The Policy Practice
[11] Coalitions in the Politics of Development, Developmental Leadership Program 2012 Coalitions in the Politics of Development
[12] Building State Capability programme, Harvard University Kennedy School Building State Capability

With this strategic advantage, BSEA will play a catalytic role in influencing more substantial funding from international financial institutions (IFIs) such as the World Bank, IMF and Asian Development Bank. By aligning with some of the policy reform conditions tied to IFI support, BSEA can help shape more context-relevant reforms, particularly in new areas like civil service reform, where significant IFI funding does not exist. We will work closely with the IFIs to explore how the programme can enhance the effectiveness of their financial support or unlock additional support to make use of enhanced capital. BSEA can also help shift partners away from technical approaches, promoting a more politically informed approach, and towards more gender-responsive approaches.

Problem Driven Iterative Adaptation (PDIA)

BSEA will use the PDIA approach developed at the Harvard Kennedy School’s Center for International Development.[13] The approach is an alternative to externally imposed best-practice solutions and focuses on local partnerships, problem identification and problem solving. The approach starts with analysing a problem and spending time identifying its root causes through local stakeholders. This construction of the problem through local actors helps to ensure that solutions identify the real problems defined by local stakeholders rather than external priorities. The next steps involve identifying and testing solutions through trial and error, with refinement of approaches based on feedback and implementation processes. Instead of using external experts, the approach involves a facilitator and local actors who identify problems, develop solutions and drive change. This approach involves fixing specific problems from the bottom up, rather than the top down.
[13] Ibid.

PDIA is a way to build domestic state capacity where reformist state bureaucrats are in the driving seat of reforms. This approach requires patient engagement, partnership and motivation for reform. This includes development entrepreneurs as part of the partnership.[14] This learns the lessons from previous donor support for technical assistance which often substituted for state capacity rather than built state capacity that can be sustained. If technical assistance is supportive to change processes, this may be provided to support delivery by the partnership or institution that is engaged.[15]
[14] Initial Evidence on the Relevance of ‘Development Entrepreneurship’ Outside of the Philippines (Lisa Denney, Jaime Faustino, and Rene Sanapo), The Asia Foundation 2024 Initial Evidence on the Relevance of 'Development Entrepreneurship' Outside of the Philippines - The Asia Foundation
[15] Can PDIA be used at a strategic level in multi-donor trust funds and across various phases of downstream projects? (Robin Richards) K4D Helpdesk Report 1167 (2022) Can PDIA be Used at a Strategic Level in Multi-Donor Trust Funds and Across Various Phases of Downstream Projects?  | K4DD

Pockets of Effectiveness (POE)

BSEA will use the approach of the ‘Pockets of Effectiveness’ (PoE) research conducted by the University of Manchester’s ‘Effective State and Inclusive Development’ (ESID) research centre and partners including the ‘BRAC Institute for Governance and Development’ (BIGD). This approach investigates the political and bureaucratic conditions that enable these organisations to deliver high-quality public services. The research emphasises that these PoEs are not anomalies but are shaped by specific political settlements, leadership dynamics, and institutional autonomy. It offers suggestions for how international actors can support these institutions to navigate challenging contexts to deliver high-quality public services including revenue mobilisation. Successful examples can be seen in case of the Rwandan Revenue Authority and in Tanzania and Uganda.[16]
[16] Pockets of Effectiveness and the Politics of State-building and Development in Africa (Sam Hickey, ed.) 2023 Pockets of Effectiveness and the Politics of State-building and Development in Africa

BSEA will provide support for the development of new institutions or efforts to increase the independence of existing institutions. Following the end of the previous government in August 2024, there is significant focus and momentum behind improving the independence, effectiveness, accountability and citizen engagement of state institutions. This is likely to continue after elections. BSEA will support this process by providing technical assistance to newly established state institutions and state institutions that are becoming more independent following high levels of politicisation. This technical assistance will include support for institutional strategy, organisational design, operations, transparency policies, accountability mechanisms, organisational performance and recruitment processes. This will support state institutional independence and effectiveness at an important moment and help effective institutions to endure.

Assurances

Counter terrorist financing and anti-money laundering

The programme will comply with domestic law and international sanctions on terrorist financing. We will follow the Prof Guide and will strive to deliver maximum impact and value for taxpayers’ money. We will use FCDO’s formal agreement templates and standard contracts which include text which compels our partners to understand and comply with their legal obligations under relevant legislation. We will conduct due diligence and risk assessment of our partners.

Climate change

The programme supports state capacity and accountability which will have an indirect link to climate change. The programme does not directly engage on climate change and does not contribute to the ICF results, but improving state effectiveness and accountability is likely to improve the ability of the Government of Bangladesh to implement public policy.

Partnership Principles Assessment

The Partnership Principles Assessment identifies some momentum behind reform under the Interim Government following the July/August 2024 protests. It identifies weaknesses in development, for example the lack of inclusive growth, institutional development and domestic resource mobilisation. The Partnership Principles Assessment will be reviewed after the elections and annual reviews.

Safeguarding

Bangladesh is a context where violence against women and girls is normalised, vulnerability to climate shocks is high, and environmental and social safeguarding practices can be weak. We will conduct due diligence of partner environmental and social safeguarding policy prior to signing agreements. We will ensure regular monitoring of practice including through safeguarding spot-checks. Agreement templates include information on safeguarding compliance and reporting.

Risk

The programme is designed to support the supply-side of reform. This means the political risk is relatively high, although the reward is also high particularly with an incoming new government. Both components will require buy-in at senior, mid and junior levels of the civil service. This chain comes with political risk, particularly if staff are transferred from their role but also if political will for reform of the specific policy area reduces. The programme will seek to engage across the chain, between senior-level and junior-level and establish a diverse range of participants in the partnerships to ensure durability. It will seek to establish a wide range of partnerships so that some partnerships might end if there is no traction and others might be expanded if there is significant traction. The programme will also seek to engage on problems that are neither very highly political nor have low interest. It will engage on problems that have a medium level of political interest (and potential long-term benefit) rather than high level of political interest which has higher risk of political interference. The programme will also support institutions as they are established or are given momentum to become more independent. The approach will be adjusted based on the political context and momentum for reform.

The Programme risk is Major, and this aligns with BHC Dhaka’s risk appetite. Other risks include reputational and capacity. We anticipate a change in government in early 2026. To manage this risk, the programme will use political economy analysis to identify partnerships, support multi-stakeholder partnerships that endure beyond a change of government and will re-assess its approach after each election. Adaptive management and proactive risk management by the FCDO programme team and implementing partners will help to ensure effectiveness. Risk out of appetite in the programme will follow the internal escalation and mitigation process.

Gender

Gender inequality and social exclusion are deeply embedded in the governance challenges Bangladesh faces today. The programme recognises that achieving meaningful public sector reform requires confronting these inequalities head-on by reshaping how institutions work, who they serve, and who holds power within them. Despite decades of development gains, women, especially from poor, rural, indigenous, and disability-affected backgrounds, continue to experience limited access to quality public services, decent employment, and participation in decision-making.

To address this, the programme will mainstream gender and social inclusion into the heart of institutional reform. This includes strengthening the ability of public service providers, such as local governments, line ministries, and oversight bodies, to design and deliver services that reflect the lived realities of women and marginalised communities. Drawing on successful models such as PROKAS, the programme will convene multi-stakeholder partnerships, including civil society, public institutions, and private actors, to deliver reform. This includes understanding what works to improve women’s and excluded groups’ access to public services.

Public Sector Equality Duty (PSED)

The programme will meet the Public Sector Equality Duty (PSED) by systematically embedding gender equality and social inclusion across its design and delivery. It recognises that structural inequalities, particularly those affecting women, persons with disabilities, ethnic minorities, and rural populations, are integral to the governance challenges Bangladesh faces. Addressing these is not only a moral imperative but a strategic necessity for advancing institutional effectiveness, accountability, and legitimacy. The programme will work to strengthen the capacity of public institutions to design and deliver services that are responsive to diverse needs, promote fair and inclusive recruitment and career progression, and foster working environments that are safe, respectful, and conducive to meaningful participation.

Conflict

There is no conflict risk associated with the programme. The programme will engage with government leadership and senior civil servants who have opposing or competing interests, but there is unlikely to be a risk of violent inter-personal or inter-group conflict.

Theory of Change (TOC)

The BSEA programme is grounded in the recognition that politics-first approaches are required to achieving improvements in state effectiveness and accountability. BSEA aims to strengthen state capability by building the political momentum behind technically sound reforms and policy delivery problems to improve public sector performance. The approach is centred around (1) Action-driven Partnerships using PDIA, (2) support for institutional reform using POE and (3) policy influencing on specific sectors. The programme also seeks to link to IFIs where possible, including (1) support for delivering IFI conditions where political momentum exists and (2) support for tackling policy implementation challenges that may catalyse additional loans and grants from IFIs.

Theory of Change

Problem statement: In Bangladesh, state institutions and civil servants are constrained by outdated practices, systemic inefficiencies and politicization which undermine the delivery of public policy. A coalition of political, bureaucratic, and business elites have captured national and local government structures, hindering reform efforts and limiting the effectiveness of even the most capable civil servants. These structural weaknesses increasingly undermine poverty reduction, equitable development and transition to middle-income status. / Hypothesis: Strengthening state capacity is possible by facilitating partnerships led by civil servants and non-state actors and providing support to state institutions individually and collectively. Where elite capture is not overwhelming, coordinated and strategic action by action-minded officials and institutions with a deeper understanding of political economy can shift dynamics and enable more effective public policy delivery on specific issues.
IMPACT	Select public institutions and civil servants in Bangladesh are more capable of delivering public policy effectively
	↑	↑	↑
Assumption	The programme has helped to build and sustain political will and legal frameworks to enable collaboration, accountability, and evidence-based policymaking
	Component I: Action-Driven Partnerships	Component II: Institutional Support / and Policy Engagement	Component III: Governance Opportunities Fund
OUTCOMES	Select civil servants are better able to address select policy issues more collaboratively, constructively and productively	Select state institutions are functioning more independently and accountably, and groups of institutions are working together with greater interoperability / Policies are better designed, more responsive to citizen needs, and more likely to be implemented by the bureaucracy	Public policy delivery supported by strengthened evidence base
	↑	↑	↑
Assumptions	Action-minded civil servants are open to engagement and want drive change / There is a willingness from state and non-state actors to collaborate through networks / Multi-level buy-in is achieved and regularly renewed to enable implementation of new strategies and policies / There is appetite from policymakers to engage with the strengthened evidence base and utilise findings in their work
OUTPUTS	1.1 Use of formal and informal platforms for dialogue and strengthened networks across targeted groups and institutions / 1.2 Locally driven initiatives are tested and refined through iterative PDIA cycles and PEA, guided by ongoing learning and evidence from implementation / 1.3 Civil servants have improved capability to lead, design, and deliver policy solutions that are technically sound, politically sensitive and relevant to the local context	2.1 Institutions have improved capacity in key areas of responsibility including their ability to engage across government / 2.2 Institutions have improved capacity for independence and resilience / 2.3 Policy engagement leads to more independent and accountable institutions and effective policy delivery in targeted sectors / 2.4 Delivery of IFI prior actions/conditions and mobilization of further IFI grants/loans	3.1 Strengthened evidence base for policy reform that is contextually appropriate, politically viable and locally owned
	↑	↑	↑
Assumptions	Partners and institutions are interested and see value in their engagement / There is consistent appetite and commitment among key stakeholders for enhancing institutions and policy delivery. If stakeholders move, they can be replaced in the partnerships / State and non-state actors are willing to engage and collaborate not criticise / Institutions are willing to engage at a critical moment in their establishment or new independence / The UK and the implementing partners remain credible actors and agents in strengthening state effectiveness
INPUTS	Systems analysis, political economy analysis and GEDSI analysis to identify issues and entry points for partnerships / Facilitation of collaboration among reform-minded public officials and between public officials and non-state actors for joint problem-solving / Facilitation of PDIA process by civil servants with PEA / Building the practical skills of civil servants including on critical thinking, leadership and policy design, delivery and evaluation	Analysis of select state institutions and their institutional environment / Facilitation of institutional capacity development through targeted support / Facilitation of the development of institutional accountability tools / Policy dialogue and influencing to deliver reform / Support for institutional coordination mechanisms and trust-building across government / Support for engagement with IFIs	Flexible funding to support governance and policy reform objectives, e.g. action research, conferences, exchanges, technical assistance for testing approaches and evidence generation on state effectiveness and accountability

Appraisal Case

Appraisal of options

Introduction to the options

The Appraisal Case sets out three realistic options: (1) do nothing, (2) Action-Driven Partnerships, support for institutional reform and policy engagement and (3) Action-Driven Partnerships only. This helps to identify how FCDO can address the challenges identified in the Strategic Case in a way that optimises Value for Money (VfM).

The option of focussing on a single sector such as public administration and/or public financial management was considered, however this presents a significant risk if there is a change in political appetite. As such, the programme will engage with several sectors with a focus on four sectors including public administration and public financial management. It is likely that governments of the next few years will face demands to improve public administration, but government appetite is unclear. Recent IMF analysis has identified public financial management as a key challenge for state capacity.[17] IMF analysis has also engaged with PDIA in support of PFM.[18] As donor spend reduces, domestic resources will be a challenge.
[17] Bangladesh's recent failure to meet two key IMF PFM conditions led to significant delays in disbursement of the fourth tranche loan (amounting to $645 million).
[18] PFM Reform Through PDIA: What Works and When it Works (Jamelia Harris, Andrew Lawson) IMF PFM Blog 2023 PFM Reform Through PDIA: What Works and When it Works

Options appraisal

Option 1: Do Nothing

Under the ‘Do Nothing’ option, resources would be allocated elsewhere in the FCDO portfolio in Bangladesh and there would be no specific investment in institution-building from the supply-side. We would continue to invest in the demand-side of reform through the Bangladesh Collaborative, Accountable and Peaceful Politics (B-CAPP) programme. With the end of sector-specific programmes such as in the health and education sectors, there would be no FCDO investment in supply-side institution-building to drive forward inclusive governance reforms; we would continue policy dialogue in-house.

FCDO Bangladesh would engage in institution-building by influencing the International Financial Institutions such as the World Bank and the IMF. We would use Centres of Expertise to engage with specific institutions, such as using the Centre of Expertise for Public Financial Management to engage with Bangladesh’s National Board of Revenue on tax and domestic resource mobilisation. This would provide light-touch and short-term partnerships between institutions rather than deep relationships on specific problems over the medium-term. The Centres of Expertise engage in different sectors in different ways. The Centre of Expertise for Politics and Governance would not be able engage directly with the Public Service Commission.

The ‘Do Nothing’ options presents strategic and reputational risks for the FCDO. Following many years of investment in health, education, public administration reform and other sectors, doing nothing on institution-building would miss a significant opportunity for UK influence and engagement as Bangladesh moves towards upper middle-income status. The ‘Do Nothing’ option means that FCDO loses the experience of work on governance from the past 20 years of investment at a critical moment in the country’s trajectory as growth continues and aid flows reduce.

A lack of significant engagement with policy would mean the UK’s voice is weakened in a context of an increasing range of international actors in Bangladesh seeking to influence the government and state development. Lack of strong institution building risks Bangladesh falling into the ‘Middle Income Trap’, where weak governance impedes economic development and the ability to achieve high-income status. The Chief Economist visited Bangladesh in October 2023 and identified the need for an effective state to confront vested interests to improve public service delivery and the country’s long-term economic prospects.

Following the change of government in August 2024, the IFIs have increased their footprint in Bangladesh. Support for Action-Driven Partnerships and institution-building through FCDO’s deep understanding of political economy, power dynamics and elite bargains would help to make investments from the IFIs more effective in delivering reform in Bangladesh. IFI investments are more significant than FCDO bilateral programming and represent a significant opportunity.

Option 2 (preferred option): Action-Driven Partnerships, institutional support and policy engagement

In this option, we would provide (1) support for Action-Driven Partnerships to tackle specific policy problems, (2) support for selected institutions seeking reform or new institutions as they are established and (3) engage in policy discussions to encourage effective policy design, reform, delivery and evaluation. This option is based on systems analysis, institutional analysis, political economy analysis and identifying entry points/nascent partnerships in government to tackle specific policy problems or engage specific institutions.

This option uses the ‘Thinking and Working Politically’ (TWP) approach that requires a strong understanding of power dynamics, analysis of those who favour/do not favour change and ability to mobilise groups to drive change. A recent study on the application of PDIA in Nigeria concluded that there is sufficient quality of evidence “to demonstrate that IBP can be an effective approach to development programming that has proven successful both to bring about change at the level of issues and as entry point for more systemic change.” The study also concluded that a PDIA approach is consistent with the experience of how change often happens in Nigeria and so provides a practical way for development partners to enhance domestically-driven change processes.[19]
[19] Twenty years of UK governance programmes in Nigeria:  Achievements, challenges, lessons and implications for future support (Laure-Hélène Piron, Clare Cummings, Gareth Williams, Helen Derbyshire, and Sierd Hadley), in ODI Global Research Report 2021 Twenty years of UK governance programmes in Nigeria: achievements, challenges, lessons and implications for future support | ODI: Think change;

The Action-Driven Partnership approach requires a deep understanding of the context followed by the facilitation of partnerships. The programme will deploy expert facilitators to engage with two different levels of partnership: (1) between government stakeholders to provide a safe space for discussion and shared objectives and (2) with stakeholders from outside government including civil society, the private sector and trade unions with an interest in change who can provide technical inputs and accountability. The facilitation process will use the PDIA model of problem identification, testing and expanding solutions. We will provide relevant technical assistance based on demand.

The types of problem identified for the partnerships to engage with will vary. Selection of the right problems is critical and depends on certain criteria, including (1) whether addressing the problem is politically feasible, (2) whether material results for the poor can be achieved, (3) whether there is potential to scale up and (4) alignment with UK priorities. Precise analysis then problem identification and selection will be done through research and analysis at the start of the programme and throughout, which includes dropping problems that are not gaining traction and engaging on new problems that may gain traction. We will need to identify problems that are politically important but not politically sensitive, and where we can tip the balance against the status quo. FCDO and the implementing partner(s) will develop and regularly update a matrix of problems and institutions to engage based on a range of criteria developed in the Inception Phase.

The problems selected may link to the IFIs. For example, the problems selected may link to IMF loan conditions where partnerships may be forming to deliver the specific policy reform conditions where the implementation is lacking. Support for delivery of these policy reforms would improve the institutions and service delivery and potentially unlock further IMF loans. For example, there is a recent World Bank investment in public financial management reform but no such investment in civil service reform. Building partnerships on specific policy problems and supporting nascent institutions may help to catalyse lending from the World Bank on civil service reform. It may support the IFIs to take a more gender-sensitive approach.

The programme will provide specific technical assistance to strengthen new or increasingly independent state institutions. This is dependent on appetite from the new government following the next election and future government appetite for institutional reform/independence. The programme will provide support for institutions to identify their strategy, organisational design and operating model, as well as transparency, accountability mechanisms and methods for citizen engagement and feedback. Selection of the institutions will likely depend on: (1) if/how far the institution is reform-minded, (2) the significance of the institution and its potential for resilience against authoritarianism, (3) the longevity of its senior leadership and (4) alignment with UK interests.

The programme will have a specific mandate to engage in policy dialogue to encourage policy reform and delivery. The PDIA process may test solutions at local level and policy dialogue may be used to scale successful pilots. Improvements to institutions may be embedded through policy dialogue and accountability for delivery could be encouraged through a specific focus on policy engagement under the programme including through the programme-funded policy engagement advisers.

The advantages of this option are:
- Scalability and sustainability: building on political opportunities that emerge through Action-Driven Partnerships, this approach can scale up efforts, increasing technical assistance to government where reforms are progressing and therefore maximising impact
- Flexibility combining interventions enables the programme to adapt and surge resources in response to opportunities and political realities
- Systems-level reform through institutional analysis and technical assistance to specific institutions has the potential for high-level impact

Option 3: Action-Driven Partnerships only

This would be a narrow approach focussed only on Action-Driven Partnerships. This approach would maintain the good practice around being politically-informed and adaptive. However, there would be risks for durable institutional change. As identified in a recent FCDO review on issue-based partnerships approaches in Nigeria, there can be challenges linking and scaling smaller scale interventions that are locally specific to high level and structural governance reforms.[20] This would be a particular challenge under this option as Action-Driven Partnership participants are not linked to wider support to improve institutional capacity or policy dialogue.
[20] Lessons learned from operationalising Issues-based programming: The experience of UK programmes in Nigeria. PERL- LEAP (Gareth Williams, Helen Derbyshire, Sunny Kulutuye) in Twenty years of UK governance programmes in Nigeria: achievements, challenges, lessons and implications for future support, ODI Global Research Report 2021 Twenty years of UK governance programmes in Nigeria: achievements, challenges, lessons and implications for future support | ODI: Think change

The advantages of this option are:
- Narrower focus enables engagement on a wider range of problems and placing a wider range of ‘bets’ across government that may gain traction
- FCDO would be able to support Action-Driven Partnerships with policy dialogue directly delivered by political officers and governance advisers

Summary of options against success criteria:

Success Criteria	Option 1: / Do Nothing	Option 2: / Action-Driven Partnerships, institutional support and policy engagement	Option 3: / Action-Driven Partnerships only
Flexible and adaptive support based on demand, budget and opportunities		X	X
Support for systems-level reform	X	X
Catalysing reforms identified by IFIs		X	X
Encouraging further IFI investments		X
Responding to ‘window of opportunity’ for systems reform		X
TOTAL	1	5	2

Programme components

The programme will include the following components:

Component 1: Action-Driven Partnerships

This component will start with system analysis, institutional analysis and the identification of emergent partnerships. It will identify entry points, problems, Action-Driven Partnerships and target institutions. This will take place in the Inception Phase during October 2025 to March 2026. This will factor in the political landscape following the election and likely new government in early 2026.

The programme will use various methods to identify potential stakeholders in partnerships. The stakeholders engaged will change as the programme advances. The focus is on real-life problems that matter to stakeholders who can mobilise and drive change. Selection of the right problems is critical and will depend on whether addressing the problem is politically feasible, whether material results for the poor can be achieved and whether there is potential to scale up.

These partnerships will be supported through the PDIA process of identifying problems, testing solutions, evaluating solutions and either expanding or closing the tests. The partnerships may be provided with other forms of capacity building such as leadership training, critical thinking skills and support for working effectively across government. In the testing of solutions and expansion, the programme will likely provide technical assistance to support delivery and improvements in state effectiveness and accountability. Solutions may be scaled by others.

Component 2: Institutional Support and Policy Engagement

This component will provide support to improve the independence, effectiveness and accountability of specific institutions. It will start with systems analysis and/or institutional analysis, and then identify specific institutions to engage. The potential institutions to engage and methods of engagement will be tested in the Inception Phase. These will be reviewed following the election in early 2026. The support may include both institutions that are increasingly independent or new institutions as they are established under the current or future government.

The component may also support institutions to co-ordinate to improve coherence, service delivery and policy implementation. This may involve supporting cross-government co-ordination mechanisms that can support delivery i.e. interoperability including through better data. The support for institutions and for co-ordination will help to reduce politicisation and encourage more effective institutional delivery. The support will vary depend on the needs of different institutions, but will likely be from a menu of options including support for: establishing a mandate, strategic processes, organisational design, operational plans and accountability mechanisms including transparency processes and citizen engagement, with an emphasis on inclusive participation.

This component will also include policy engagement with specific resource dedicated to influencing at the much broader level. The policy engagement will be based on the results or recommendations of activities under components 1 and 2, and research and evidence on how to improve state effectiveness and accountability. It will also be based on shared UK-Bangladesh priorities for policy reform across different sectors such as public financial management and public administration.

This component will also include up to two programme-funded Policy Engagement Advisers. This will be a Country-Based SEO recruited and managed by the FCDO/BHC Dhaka. The Policy Engagement Advisers will cover two key sectors and be responsible for influencing government policy through learning from the programme and UK policy priorities. The Policy Engagement Adviser will be managed by the SEO Lead Adviser to ensure coherence with the programme.

Component 3: Governance Opportunities Fund (GOF)

This component includes flexible resource to deliver quickly against opportunities for governance and policy reform in support of the programme objective. To Governance Opportunities Fund (GOF) will support catalytic, time-sensitive, and high-impact interventions aligned with the programme’s objectives. The GOF will enable the programme to seize emerging opportunities, respond to shifts in the political economy, and pilot innovative approaches. The fund will prioritise initiatives that demonstrate strong potential for policy influence, partnership strengthening, inclusive governance, or public engagement. The criteria for GOF will be developed in the Inception Phase.

The GOF may fund specific political economy analysis to influence and complement IFI loans and grants, for example influence the World Bank’s Development Policy Loans. This might include supporting political economy analysis to help identify prior actions for DPLs or supporting Government of Bangladesh counterparts in their scoping and procurement of technical assistance for the delivery of prior actions under DPLs. It may support other international initiatives such as the Open Government Partnership and the process of accrediting and delivering on its commitments. The GOF may be used to engage with FCDO’s Centres of Expertise; for example funding or co-funding technical support to explore new programming or to develop policy.

Component 4: Monitoring, Evaluation, Adaptation and Learning (MEAL)

This component will support the collection and use of evidence to enhance learning and programme implementation. It will provide insights to encourage FCDO and implementing partners to reflect on the delivery approach and identify areas for improvement. Specific activities under this component will be scoped during the programme’s inception phase. This could include input into the results framework, support in developing a learning agenda, and the delivery of evaluations and annual assessments to guide adaptation. MEAL will be integrated into all programme components.

Illustrative examples

The BSEA is built on an adaptable framework that can be tailored to the unique needs of different sectors. Below are some illustrative examples:

Theme	Action-Driven Partnership	Institutional Support	Policy Engagement
Public Administration	Facilitate an Action-Driven Partnership across government stakeholders to digitise recruitment of new civil servants to encourage more meritocracy. Provide technical assistance on Artificial Intelligence for recruitment	Support the Public Service Commission with research on similar institutions in different contexts to understand effective institutional design then provide technical assistance for strategy development and operational transformation	Share lessons from the UK’s Government Digital Service on digitisation to encourage reform by the Government of Bangladesh through IFI grants/loans
Anti-corruption	Facilitate an Action-Driven Partnership across government to draft a new National Anti-Corruption Strategy to replace the 2010 National Integrity Strategy. Provide technical assistance for specific areas, such as a digital Register of Beneficial Ownership under Ministry of Commerce using UK expertise and experience	Support efforts to increase the independence of the Anti-Corruption Commission (ACC) following elections in early 2026 through support for drafting new mandate, developing institutional strategy and operational plans, and supporting institutional transformation processes	Encourage Bangladesh to adopt the Common Reporting Standard (CRS) and join the Open Government Partnership (OGP) for financial and governance transparency
Domestic Resource Mobilisation	Facilitate partnerships between government stakeholders and government and non-government stakeholders on the automation of VAT refunds to help reduce corruption and business uncertainty / Support the Public Financial Management Reform strategy (2025-30) developed by the World Bank and delivery of specific areas such as PFM in health using UK expertise	Support the design of new institutions formed out of the National Board of Revenue (NBR) and strategic plans to help newly-created institutions / Support the establishment of a PFM Reform Implementation Unit in the Ministry of Finance	Encourage the division of tax policy and collection to meet IMF loan ‘prior actions’ and unlock future funding from the IMF for domestic resource mobilisation
Climate	Support an Action-Driven Partnership to address weak inter-governmental coordination on climate finance to encourage greater funds from international organisations	Support the design of cross-ministerial coordination mechanisms especially where institutional mandates overlap between ministries (e.g., Planning, Finance, Environment) on climate policy implementation and budget alignment	Encourage a Climate Change Act, establishing a legal framework for climate policy alignment and greater state capacity on climate
Health	Support an Action-Driven Partnership on a smart E-Health record with a unique digital ID for all. Support the partnership to work across ministry of health and family welfare (MoHFW) and provide technical assistance on resilient and sustainable systems for health (RSSH), operational coherence and digitalisation processes	Facilitate institutional engagement between two key health directorates: DGHS and DGFP to help improve effectiveness and efficiency. This could involve joint planning, monitoring and reporting, improving institutional functioning.	Support institutional reforms to improve oversight, reduce corruption, and ensure responsive quality service delivery and fulfilling global commitments.
Education	Facilitate partnerships at the local level to improve localised need-based budget planning/forecasting, and to introduce a budget expenditure tracking system	Support the Ministry of Primary and Mass Education in building planning and budgeting capacity at District-level, including adoption of AI-powered budget forecasting tools for better planning - reducing inefficiencies and ensuring optimal resource allocation.	Encourage the design of a decentralised planning and budgeting framework with specific governance structure and clear definitions of roles and delegated authority
Youth	Facilitate partnerships to design and deliver a youth-focused budget and support these efforts through capacity-building	Support the Ministry of Finance’s efforts to engage the community on youth-inclusive participatory budgeting	Encourage the creation of a ‘Young Policy Leaders’ cadre in the civil service using experience from the UK’s ‘Fast Stream’

Technical assistance to government stakeholders

The programme will provide technical assistance to government stakeholders to enable the testing and scaling of solutions to policy problems. This will be combined with the PDIA approach of building partnerships with a good understanding and ability to navigate the political economy of reform. Evidence from the ODI’s report by Samuel Sharp ‘Working politically in practice’ in Malawi (2024)[21] shows that financial support for partnerships may support the delivery of reform.
[21] Issue-based programming in challenging contexts: Learning from Traction Malawi (Tim Kelsall, Samuel Sharp) ODI Global, 2023 Issue-based programming in challenging contexts: Learning from Traction Malawi | ODI: Think change

Value for money for the Preferred Option

The FCDO’s approach to Value for Money (VfM) aims to make the best possible use of our resources to maximise our impact. For the BSEA programme, VfM will be assessed on the extent to which the causal pathways in the Theory of Change (ToC) are successful, with the right mix of activities and outputs leading to the impact. The ‘Thinking and Working Politically’ (TWP) approach is a cost effectiveness ‘Mega-Buy’ and will be used throughout the programme.

Economy in the BSEA programme will be achieved by reducing input costs through leveraging local expertise and resources. By engaging a local partner, local civil society organisations (CSOs) and experts, the programme will reduce reliance on international consultants, thereby lowering costs and building local capacity. Implementing stringent financial management practices, with establishing benchmarks for key cost drivers such as staff salaries, consultant fees, and management overheads to help monitor and control costs effectively. For instance, the average annual salary, average daily rate for external consultants, and management costs as a percentage of the programme budget will be key indicators for measuring economy.

Efficiency of the BSEA programme will be achieved through managing the delivery of outputs through integrating related activities and fostering collaboration among diverse partners. The programme will streamline efforts by fostering partnerships through PDIA processes to solve governance problems whilst building capacity. Examples of efficiency metrics could include the percentage of outputs delivered on time, and qualitative measures of improved coordination and collaboration between partners.

Effectiveness of the BSEA programme will be measured by its ability to achieve intended outcomes and drive impact. Working with established partners who have a proven track record of success in governance reforms will ensure that the programme leverages their contextual knowledge and relationships with local stakeholders. The sustainability of results will be a key consideration, ensuring that the impact of the programme extends beyond its duration by building local capacity and fostering long-term partnerships that can be sustained.

Equity will be a central focus of the BSEA programme by addressing gender equality and social inclusion. The programme will embed gender and inclusion considerations in all activities to ensure that women and marginalised groups are actively involved as outlined in the Gender section above.

VfM Statement

The BSEA programme will represent VfM by ensuring that every pound spent delivers maximum impact. By focusing on economy, efficiency, effectiveness and equity, the programme will contribute to sustainable development and other UK objectives. The programme will undertake regular reviews and adapt based on success and the changing contexts to ensure continued relevance and impact.

The overall cost-effectiveness of the programme will be significantly enhanced by its ability unlock IFI funding such as IMF loans and World Bank grants. The programme will be uniquely placed for leveraging on-the-ground capacity-building and operating in the political context, adding additionality beyond the technical assistance available from the IFIs.
Commercial Case

Overview

The programme has four key components. Components 1 and 2 will be delivered through an Accountable Grant to The Asia Foundation (TAF) and downstream partners. TAF will be directly managed by FCDO, but TAF will identify downstream partners through an open, competitive process. TAF will lead the establishment of at least one new legal entity registered in Bangladesh that will continue to operate beyond the lifetime of the programme. Component 3 will be directly managed by FCDO and involve small grants/contracts. Component 4 will be delivered by a commercial provider.

Delivery options for Components 1 and 2

The nature of the programme means that we need a delivery route with the following five key attributes: 1) the ability to operate in Bangladesh, 2) the ability to engage government as a facilitating actor, 3) the ability to take a ‘politics first’ approach, 4) the ability to mobilise quickly and 5) the agility of the supply chain to quickly respond to the changing needs.

On the basis of these five criteria, we identified and assessed the following delivery routes:
Route 1: a commercial contract through competition (framework mini-competition, open procedure or competitive flexible procedure)
Route 2: a Memorandum of Understanding (MoU) with a multilateral organisation or a consortium
Route 3: an Accountable Grant (AG) awarded to a CSO/NGO or a consortium

Route 1: a commercial contract through competition (framework mini-competition, open procedure or competitive flexible procedure)

Competition provides the greatest assurance around the quality and value for money of the successful supplier. A well-placed consortium is likely to possess a wider range of technical expertise. The value proposition of commercial suppliers is their ability to rapidly recruit and deploy expert consultants/sub-contractors, and their efficiency in management. Commercial contracts are more prescriptive and give FCDO more power to manage performance (via KPIs, Payment by Results mechanisms, etc). A break clause at the end of the Inception Phase would allow analysis and testing before implementation. The Sourcing Strategy approved by Commercial’s Procurement Steering Board will outline the best procurement route which is most likely to be the Global Development Delivery (GDD) Framework for this programme. This will also be the quickest of commercial procurement routes at a minimum period of 4 months.

A commercial supplier, however, would require a clear specification that may not be possible given the flexible and adaptive nature of the programme and the uncertain political context. The requirement for clear objectives would reduce the ability of the supplier to create their own approach, which may reduce the scope for innovation and miss the opportunity to adapt to emerging needs. It may not be possible to establish a new entity for programme delivery through this delivery route which further reduces sustainability beyond the programme. A commercial provider is unlikely to be able to facilitate government-led partnerships because of the limitations of an ongoing trusting relationship and incentive to deliver technical assistance rather than the politics-first approach. Government stakeholders are less likely to respond to facilitation by a commercial provider and may not see the programme as a government-led effort to build state effectiveness and accountability.

Route 2: a Memorandum of Understanding with a multilateral organisation or a consortium

Multilateral organisations have good relationships and a strong ability to engage with government stakeholders in Bangladesh. Various governments have received support from UN agencies, the IFIs and other multilaterals, and there is a high level of trust with these organisations. Multilateral organisations can mobilise quickly through a Memorandum of Understanding and bring in other development partners for support. However, they are large organisations and often not flexible.

Multilateral organisations often follow technical approaches to reform and may find it difficult to engage with the politics-first approach identified by the FCDO. This approach to ‘Thinking and Working Politically’ is a niche for the FCDO and considered a ‘Mega Buy’ on the Governance ‘Best Buys’.15 Multilateral organisations are limited in their engagement in politics and may not be able to explicitly support this approach. The programme will still need to engage with multilateral organisations, particularly as these provide conditions for loans and grants. These loans and grants may form the basis of Action-Driven Partnerships. We may form Action-Driven Partnerships to catalyse additional loans and grants from the IFIs, for example on public administration.

Route 3: an Accountable Grant (AG) awarded to a CSO/NGO or a consortium

CSOs in Bangladesh generally have more experience and reputation in advocacy and service delivery. They are less able to form trusted relationships with government stakeholders as insider facilitators given their traditional role in advocacy and service delivery. AGs are less prescriptive and allow greater creativity in approach and flexibility to advance work on problems gaining traction and reduce/stop work on problems that are not. The partner has more freedom to pursue the objectives via methodologies of their choosing, but means that there needs to be significant trust in the supplier’s capabilities and vision. A default position to reach an AG is through a competitive Call for Proposal (CFP) process which takes up to 3-4 months to mobilise if not fast-tracked. Competition can provide assurance around the quality and value for money of the successful partner. In the three calls for proposals by FCDO over the last 5 years, the outcome has consistently resulted in the winning bidder being the one less expected or the one less obvious. With a consortium, the lead CSO would need to be open to expanding the supply chain over time as per the need.

Analysis of Delivery Options

A summary analysis of the options above against the key criteria is shown below.

	Route 1: Commercial contract through competition	Route 2: MoU with a multilateral organisation/consortium	Route 3: AG to a CSO/NGO/consortium
Ability to operate in Bangladesh	Medium / A number of commercial providers have a presence in Bangladesh although some may not	Strong / Strong presence given historic relationship between governments and multilaterals	Strong / There is a low probability that bidders are not well-established
Ability to engage government as a facilitative actor	Weak / A commercial organisation may be considered a standalone project not facilitator of government stakeholders	Medium / They can work with government due to years of presence as an international actor and global reputation but may direct rather than facilitate	Medium/Strong / Those who have already built experience will be able to facilitate, others may be seen to do advocacy and service delivery and therefore not trusted to work inside government
Ability to take a ‘politics first’ approach	Weak / Commercial providers are incentivised to deliver technical assistance rather than the ‘politics first’ approach	Weak / The nature/mandate of multilaterals means they are not able to take a ‘politics first’ approach or engage in political economy driven programming	Strong / CSOs/NGOs with prior experience of working in politics and governance should be able to take a strong ‘politics first’ approach, but this varies across the sector
Ability to mobilise quickly	Weak / A contract will take minimum 4 months and maximum 6 months to be signed	Strong / Given their strong presence, they should be able to mobilise quickly but may not be as responsive to FCDO-specific requirements	Strong / Once the AG is signed, if the CSO/NGO is already established in Bangladesh, they should be able to mobilise quickest
Agility of the supply chain to quickly respond to the changing needs	Weak / A contract amendment process is cumbersome, and given the nature of the programme, we will need the components to be adaptive	Weak / Multilateral organisations have their own way of operating and are often less flexible to changing demands	Strong / An AG allows the greatest flexibility to adapt and change as the programme evolves. The programme will need to adapt in the changing political context

The analysis leads towards Route 3: an Accountable Grant (AG) awarded to a CSO/NGO or a consortium. However, not all CSOs will be able to meet all the five attributes. Given the focus of facilitating trusted partnerships in government, only a niche CSO/NGO market will be able to deliver. FCDO has been delivering governance programmes for many years in Bangladesh working with various suppliers. We are working on the demand-side of governance through B-CAPP. FCDO knowledge of delivery partners and the related market is strong.

From an Early Market Engagement event in March 2025 on support to design the programme, there were no suppliers who have the same experience as The Asia Foundation (TAF) in a politics-first, Action-Driven Partnership or institutional reform approach. There are other suppliers who might provide the role of knowledge partners and may form a part of the delivery chain to leverage their expertise but are not able to lead on the delivery. TAF is the strongest in this respect. Any Call for Proposals process is most likely to return TAF as a consortium lead and will therefore not present better value for money for the UK taxpayers.

Evidence in Support of a Direct Grant to TAF

There are two key aspects that set TAF apart from other CSOs/NGOs in Bangladesh. One is their registration status in Bangladesh and the other is their strong experience of working on both PDIA approaches and institutional support.

TAF is a US-based non-profit organisation registered in Bangladesh as a ‘development partner’ since 1974. This was evidenced through an MoU with the Economic Relations Division under the Bangladesh Ministry of Finance and a more recent letter from the Bangladesh National Revenue. This status as a ‘development partner’ means that they are exempt from the requirement to register with the NGO Affairs Bureau. Given this status, TAF can operate inside the government and facilitate relationships between government counterparts. This is not common with most other CSOs/NGOs, who tend to work on advocacy or service delivery.

TAF will need to follow government approval processes for engagement with state institutions and technical assistance (including TAPP processes), but with greater flexibility than other organisations. This is useful for the programme where we want a quick start of activities to gain advantage of the ‘window of opportunity’ of the Interim Government and potential reforms. TAF is also able to bring suppliers into the delivery chain and take them out of the delivery chain at pace, which suits the programme’s focus on adaptation and flexibility in an uncertain political context.

TAF has worked in Bangladesh/East Pakistan for over 65 years. Under B-CAPP, TAF leads a consortium with Democracy International and other CSOs to work with political parties, civil society, media organisations, and local authorities to form change coalitions on core issues. TAF is also led a partnership in the UK-funded X-Border project in partnership with the Malcolm H. Kerr Carnegie Middle East Center and the Rift Valley Institute from 2015 to 2020 and in Indonesia, where TAF was the prime implementing organization for the USAID-funded Effective, Efficient, and Strong Local Governance project.

TAF has supported institutional strengthening that is highly relevant for the institutional support proposed in the programme. Since 2017, TAF has been working in Nepal to strengthen the federal system of governance on the Australian government-funded Subnational Governance Program (SNGP). This involves working with all three tiers of government to clarify roles and responsibilities, enabling the system to function more effectively, reducing overlaps, addressing gaps, and improving coordination in key policy areas. The program focuses on improving the political and managerial dynamics in the implementation of fiscal federalism, recognising that a combination of political dynamics, incentives, bureaucratic structures, and gender roles impede policy formulation and implementation. This experience is highly relevant for Bangladesh.

For both components, TAF will need to identify downstream partners with relevant expertise to support programme delivery. This includes a multi-sector technical assistance partner, a knowledge partner and a partner to establish the process for establishing a new entity and more specific technical assistance partners or other knowledge partners. FCDO will require TAF to develop an open and competitive process for selecting downstream partners, using technical selection criteria that are to be approved by FCDO. FCDO will participate in this process to gain assurance that it is resulting in the selection of quality downstream partners. TAF will bring additional staff to support this programme rather than use staff who are currently delivering the B-CAPP programme.

This combination of reputation, status and experience means TAF is uniquely able to engage with government stakeholders, build trust in government-led issue-based partnerships and deliver politically sensitive support at institutional level. TAF will develop a proposal to be agreed once the Business Case has been approved, this will include a Statement of Outcomes. We expect TAF to develop a process for engaging additional suppliers and/or removing suppliers from the programme with FCDO oversight. TAF will also identify specific resource for policy engagement. This approach will maximise sustainability and encourage system-level reform in Bangladesh.

New entity for delivery under Component 2

The Statement of Outcomes for TAF will include the establishment of one or more new entities to deliver some of the programme by the beginning of the third year. They will be established through the support of downstream partners and will slowly build credibility and ability to engage with government stakeholders. The new entity/entities will recruit high-calibre staff to continue delivery of the programme or specific elements, building both technical knowledge and local expertise. This may lead to lower implementation costs with smaller profit margins. The mission and priorities for the organisation will be established by FCDO and TAF.

The new entity/entities will be structured to have passion and longevity in the field of state effectiveness. This would be similar to the Institute of Water Modelling (IWM) (https://www.iwmbd.org/) which is a self-sustained and not-for-profit independent Trust and the Center for Environmental and Geographic Information Systems (https://www.cegisbd.com/geninfo) which works both independently and in close collaboration with government ministries, departments and organisations as well as NGOs and international donors. We may also consider expanding an existing entity for example, the National Institute for Local Government, the BRAC Institute of Governance and Development (BIGD), the Bangladesh Institute of Governance and Management (BIGM) or the Bangladesh Institute of Development Studies (BIDS).

The new entity will become a knowledge partner on state effectiveness and accountability or have a more specific focus, such as public financial management and/or public administration reform. It will take a politics-first approach to engagement and facilitation of government, helping counterparts to understand political economy, PDIA and institutional reform. Building long-term in-country specialist technical expertise is in line with International Development White Paper.

FCDO/TAF will explore the creation of the entity with downstream partners in phases:
- The first phase will focus on assessment and advice on the legal form and structure of the organisation. The supplier will advise on the scope, availability of skilled staff and the appropriate salary scales and the level of current and future demand from the private sector for specialist expertise in this work area.
- The second phase will involve establishing and registering the organisation with appropriate regulatory authority in Bangladesh. The downstream partner will provide guidance on the governance structure and develop internal policies and procedures for ensuring compliance with relevant laws and regulations. The entity will need to meet all the requirements of FCDO including those outlined in the PrOF Guide on Special Purpose Vehicles.
- The FCDO will conduct a Due Diligence Assessment on the new entity when appropriate. Approval to proceed with the new entity will not be granted unless appropriate policies and processes exist to ensure effective implementation, VfM and safeguarding. There are specific due diligence arrangements for entities that have no track record of previous implementation experience. The programme team will ensure adherence to specific due diligence requirements set out in the FCDO Due Diligence Framework and in the Enhanced Guidance on Safeguarding.

FCDO will put in place a clear governance structure in line with the laws of Bangladesh and the relevant FCDO PrOF Guides. The company will be governed by a Board of Directors. The Board will provide leadership and will be responsible for ensuring high standards in corporate governance. A detailed corporate governance framework as well as internal control policies and mechanisms will be developed. FCDO will exit the Board of Directors and will cease to fund the entity as the programme ends unless extended.

Delivery Option for Component 3: Governance Opportunities Fund (GOF)

This fund will be managed by FCDO and delivered through below threshold contracts. The GOF enables FCDO and TAF to identify short-term opportunities to build state effectiveness and accountability and to deliver the programme impact in-line with the TOC, which are not planned under components 1 and 2. The criteria for the GOF will be developed during the Inception Phase in collaboration with TAF. It includes support for research, specific capacity-building or technical assistance and catalytic support for engagement that helps to deliver the impact of the programme. A realistic pipeline of these smaller assignments will be maintained to assign FCDO procurement officers with sufficient time in planning and running this procurement.

Delivery Option for Component 4: Monitoring, Evaluation, Adaptation and Learning (MEAL)

This component will be directly managed by FCDO and will be an above threshold contract to be procured by FCDO HQ through GEMFA2 framework. The MEAL component will support the collection and use of evidence throughout the programme, with specific activities confirmed in the inception phase. The MEAL workplan will aim to support adaptation by feeding into decision-making at key points within the programme cycle.

Delivery Chain

The below sets out the Delivery Chain for the programme:

Timing of AGs around the Bangladesh General Election 2026

Although the design and inception phases of the programme is aimed at making the most of reform appetite, the programme is not contingent on the results of the election in early 2026. The programme has been designed with flexibility and adaptation throughout. Component 1 on Action-Driven Partnerships works at the mid-level of the civil service and seeks reform-minded bureaucrats who are unlikely to change following an election. The problem selection will be important, but the election is unlikely to have a significant impact. The election will have some impact on Component 2 on support for institutions. However, some support is likely to remain the same, such as support for the Public Service Commission whose mandate is fixed by the constitution and whose members have been selected for the next 5 years. The election will most impact the selection of institutions for institutional reform support, which we will manage with updated analysis and second stage of stakeholder mapping/identifications after the election.

The AG covering components 1 and 2 will feature a robust break clause that can be activated after the elections. This will allow FCDO to scale back the scope of the AG or terminate entirely if necessary. The AG will feature a requirement for TAF to support a rigorous evaluation of programme approach and the context to enable FCDO to decide whether to continue at the end of the Inception Phase. The break clause will stipulate the extent of the scale back and the exit costs TAF would be entitled to as agreed in the AG as part of exit planning in advance. The Commercial team will work with the Programme Team to make the break clause as robust as possible, to minimise the need for a negotiated exit.

Cost Drivers

The main cost drivers for the programme are expected to be staff salaries, consultant fees/travel/accommodation, management overheads, cost of Action-Driven Partnership events (workshops, seminars etc), cost related to establishment/development of a new/existing entity, evaluation etc. FCDO will check and apply cost benchmarks wherever the cost data is available based on experience of working through other FCDO programmes in Bangladesh and beyond.

Value for Money

The Current TAF overhead rate is 18.61%. This is updated every 2 years and was 18.51% last time when overhead rate for FCDO B-CAPP programme was agreed. The way the overhead is calculated means that the overall overhead is much lower when there are other partners involved. TAF rate applies to the component(s) they directly deliver. For each partner they manage, they charge a one-off amount of $75,000 per agreement/contract. This brought down the overall rate for B-CAPP to 6%. Given the level of partnership involvement in Components 1 & 2, the FCDO Commercial Manager will negotiate the overhead rate in a way that there is a cap to the number of grants/contracts they charge the minimum for. The aim will be for the overhead rate to stay at a maximum of 12%.

Local office costs are already borne by the B-CAPP programme and the budget will be carefully reviewed to remove any duplication and find efficiency savings wherever possible. TAF’s pre-existing presence/infrastructure in Bangladesh should mean reduced mobilisation costs compared to a new supplier. TAF has passed FCDO due diligence assessments for B-CAPP. A DDA refresh should only highlight their strengths as a long-standing FCDO partner. TAF’s procurement processes/policies for profit and non-profit organisations will be reviewed thoroughly and will be aligned as closely as possible with terms similar to those of FCDO.

Currently TAF does not have a project-specific account and although FCDO makes quarterly advances, the local offices receive funds from their HQ weekly. FCDO will make a strong recommendation to open a dedicated account for the project. FCDO will also ask TAF HQ to either open a separate account for this project at HQ or transfer funds received from FCDO with immediate effect. This will provide better assurance to FCDO for the intended purpose the funds will be used for and will allow monitoring of any interest earned or exchange rate gains made. This will ensure much greater value for money.

FCDO will closely monitor TAF’s procurement of the downstream partners for Components 1 and 2, and will maintain a close oversight of how the partners are managed. FCDO will procure and directly manage the Component 3 partners. Grant/Contract performance management tools like milestones and KPIs will be introduced within grants/contracts agreed. Expenses will be capped and will remain subject to challenge against our VfM criteria.

Financial Case

Affordability

This Business Case seeks approval for up to £19.7m for six years including inception and implementation phases, from October 2025 to September 2031. Funding for the BSEA programme will come from the FCDO bilateral ODA allocation for Bangladesh and will be classified as Resource Departmental Expenditure Limit (RDEL). The programme will be implemented in two phases: an inception phase of 6 months and an implementation phase of 5 years and 6 months. There will be a break point after the inception phase and a second break point after the completion of the next spending round period (FY 2028/29) with a provision for annual budget review to accommodate an ODA reduction or a possible closure. The programme scope and budget will be reduced or adjusted depending on progress and following an annual adaptation assessment and annual reviews. As an adaptive programme, there will be a MEAL component and a well-defined governance structure. During the inception phase, the SRO and PRO will closely review the budget and forecast to align with the indicative allocations.

Budget Profile, Planning and Forecasting

The breakdown of these costs by year and the approximate component allocation of funds over the programme lifetime is presented below. However, the precise breakdown will be adjusted during the inception phase based on detailed work-plans and budget from implementing partners, as well as country-level ODA allocations across the Spending Review period. FCDO will retain the flexibility to move funding between components. In the inception phase, the SRO, lead adviser and PRO will engage with the implementing partners to review and adjust forecasts based on actual expenditure trends, maximising efficiencies and economy for UK funding. Of the total budget of £19.7m, £500k will be programmed for the inception phase (October 2025 to March 2026) and £19.2m will be programmed for the implementation phase from April 2026 to September 2031).

Table 1: Indicative Breakdown of Financial Commitments – £19.7 million budget

	Inception (Oct 2025-Mar 2026)	Implementation (March 2026 - September 2031)
Components	FY 2025/26	FY 2026/27	FY 2027/28	FY 2028/29	FY 2029/30	FY 2030/31	FY 2031/32	Total	%
Action-Driven Partnerships	£250,000	£850,000	£1,500,00	£1,500,000	£1,500,00	£1,500,00	£650,000	£7,750,000	39
Institutional Support and Policy Engagement (including programme-funded positions)	£200,000	£850,000	£1,650,00	£3,000,000	£1,600,00	£1,700,00	£750,000	£9,750,000	49
Governance Opportunities Funds (GOF)		£250,000	£300,000	£250,000	£300,000	£250,000	£250,000	£1,600,000	8
Monitoring, Evaluation, Adaptation and Learning (MEAL)	£50,000	£50,000	£100,000	£100,000	£100,000	£100,000	£100,000	£600,000	3
Total	£500,000	£2,000,000	£3,550,00	£4,850,000	£3,500,00	£3,550,00	£1,750,000	£19,700,000

The above table provides estimates for each financial year. The level of technical assistance is around 88% of the budget for components 1 and 2 overall. This can be reduced or increased based on demand for technical assistance and the ODA context. This will also depend on registration processes with the Government of Bangladesh for technical assistance (TAPP).

The four BSEA components, high-level delivery chain and budget are summarised below:

Payment Process

For Components 1 and 2, all payments will be denominated in GB Pounds Sterling except the two programme-funded advisers who will be paid in local currency. We will require all partners to monitor and manage exchange rate losses and gains. Payments to TAF will be made quarterly in advance to cover the programme costs for the first three months. Subsequent payments will be based on the actual expenditure of the reporting quarter and based on the forecast for next quarter. Funding will be contingent on satisfactory progress reports, expenditure reports, costed workplans and forecasts. TAF will submit a detailed workplan and budget and technical proposal for the Accountable Grant. FCDO will hold the budget for the programme-funded advisers including salaries and contingent liabilities. The salaries of the programme-funded advisers will be paid monthly.

For Component 3, FCDO will retain and manage the funds and will be procured through low value contracts or framework, depending on the budget threshold and the nature of the assignment. Some activities may be programmed through TAF. Component 4 will be procured through the FCDO GEMFA-2 framework. Supplier payments will be made against agreed milestones with partial reimbursable payments in line with the contract.

Management Fees and Overheads

For the AG with TAF, the overhead costs or Non-Project Attributable Costs will be paid in accordance with FCDO budget policy. These costs include those incurred by an organisation to support the projects that it runs, such as administration and support, equipment, and office costs. The FCDO programme team will review the financial and technical proposals of implementing partners thoroughly to gain efficiency savings. The FCDO programme team will ensure implementing partners charge FCDO proportionately on overhead costs i.e. office rent, utilities, and on a pro rata basis for staffing linked to head office if they have other donor-funded programmes. For the commercial contracts, if an independent provider is used for the MEAL component, profit margins will be agreed through the GEMFA-2 framework, and the contract value will be inclusive of all applicable taxes and overheads.

Financial Risk and Fraud

The overall residual fiduciary risk is assessed to be ‘Major’ considering the nature of the programme. However, stringent mitigating measures will be applied throughout the programme period to minimise each of the risks to the programme delivery. We have assessed that there is a risk that UK funds are misused or not used for the programme’s intended purposes, do not achieve value for money, and/or are not properly accounted for due to a variety of factors including lack of capacity, competency or knowledge, bureaucratic inefficiency, and/or active corruption.

Although TAF is an existing partner of FCDO and a comprehensive due diligence assessment (DDA) was conducted in 2022, a refresher DDA will be conducted prior to signing the AG. This process will validate previous findings and provide reassurance on their financial controls and the capacity. Delivery chain risk mapping exercises will be completed to assess that the delivery partner has the capacity and capability to deliver the programme and manage UK funds, to be reviewed at every Annual Reviews and verified through spot-checks and field visits. The partner will be required to submit annual audited financial statements and quarterly financial forecasts, and will be paid on a milestone, workplan or output basis as appropriate.

The programme team will adhere to the zero-tolerance policy approach on fraud and ensure adherence with the UK Counter Fraud/Bribery and Counter Terrorism legislation. If GEMFA2 is used to procure a MEAL provider, agencies that are part of the GEMFA2 framework have already been assessed by FCDO to ensure due diligence and fiduciary systems are in place to avoid risk. There is also a risk that the programme spends, and financial forecasts delivered by partners do not align with original expectations, causing a variance in projected and actual spend. Partners will be required to present accurate workplans and financial projections for review every quarter. We will engage with partners regularly on expectations for forecasting accuracy and variances.

Monitoring, Reporting and Accounting for Funds

Implementing partners will be required to report on expenditure and results achieved on a quarterly basis and submit quarterly forecasts and costed work-plans. We will conduct monthly meetings with primary implementing partner(s) to review progress against work-plans and financial forecasts, assess any changes in risk, review risk mitigation measures and escalate issues as appropriate. Financial and asset spot checks will be conducted on partners where appropriate. Independent audits will be conducted on all relevant direct partners annually. We will scrutinise all financial reports in line with the ADAMANT principles, prior to making every payment. FCDO will agree the reporting template and all reporting requirements at the outset of the programme implementation and will provide necessary guidance to the selected partners to ensure partners are compliant with all applicable Programme Operating Framework (PrOF) rules, and that the standard requirements and clauses set out in the AG agreement are followed.

Asset Management

All implementing partners will be required to maintain an up-to-date asset register of all assets purchased using UK funds in line with arrangements and submit an updated asset register annually. FCDO programme team will conduct at least one asset spot-check annually and during monitoring visits. We will also ensure that the disposal of any assets at the end of the programme maximises VfM in line with the PrOF rules.

Audit

Funds disbursed under Accountable Grant (AG) Arrangement will be administered in line with FCDO’s standard accountable grants terms and conditions. Spending will be subject to FCDO’s prior agreement through the approval of annual work plans, budgets and procurement plans and will be assessed through quarterly technical progress reports and expenditure reports. Implementing partners will submit annual audit reports audited by an independent and qualified audit firm.
Management Case

Programme Phases

The programme will take place in two distinct phases: inception and implementation. The inception phase will be for 6 months, followed by a 5 year and 6-month implementation phase. The programme will likely end with the end of the next government in 2031. At the end of this period, the programme will aim to conduct a final evaluation which may lead to an additional phase for the duration of the following government. The original Concept Note gained Ministerial approval for a £50 million programme for eight years; this may allow extension of the programme.

Programme Management

BSEA will be managed by the FCDO Bangladesh Cross Cutting Team. The team is resourced with a G6 Senior Governance Adviser/Team Leader who will be the programme SRO. The SRO will be supported by an HEO Deputy Programme Manager as the PRO. The SEO Governance Adviser will be the Lead Adviser. The SRO will have overall responsibility for delivery and accountability of the programme outcomes through a comprehensive Delivery Plan approach as per the PROF Rules. The PRO will be accountable for driving the programme on a day-to-day basis, the delivery of programme outcomes within agreed time, cost, and quality constraints. Other inputs will be provided by G7 Results Adviser, G6 Senior Economist, G7 Social Development Adviser, programme staff, the Commercial Manager and a Second Secretary Political. Other advisers such as the G7 Health and Education Advisers may input if the programme engages in these sectors. The team will ensure the timely delivery of agreed milestones by programme partners.

Programme Governance Structure

Programme Coordination Committee (PCC): FCDO will set up a Programme Coordination Committee. This committee will manage the programme, coordinate all the components and manage all implementing partners. The committee will hold monthly meetings in the initial phases and quarterly afterwards to discuss programme progress, results, risks, improve coordination and communication, identify areas of concerns and plan activities. The committee will consist of the SRO as Chair of the Committee and include the PRO, Lead Adviser and the implementing partners. Other stakeholders may be included or excluded as relevant.

Joint Steering Committee (JSC): The Joint Steering Committee will be the highest decision-making body for the BSEA programme and will provide strategic direction and oversight for the programme, ensuring that BSEA remains relevant and effective, and contributes to the development priorities of participating agencies and officials. The JSC will meet on a quarterly basis, advise on risks and identify problems, institutions and sectors for further engagement or discontinuation. The JSC will review and approve proposals for the GOF. Project proposals submitted for the GOF will require a concept note outlining the rationale, expected outcomes and alignment with programme goals. Final approval will be contingent upon formal sign-off by the SRO.

Independent Strategic Advisory Panel (ISAP): The Independent Strategic Advisory Panel will serve as a ‘critical friend’ and the primary advisory body to the JSC. The ISAP will meet every six month and will provide sound, high-quality strategic input, analysis, and quality assurance to BSEA. The JSC will decide the ISAP’s composition and terms of reference, aiming to ensure a strong familiarity and understanding of the Bangladesh policy landscape and the use of external expertise.

The FCDO core programme team comprising of the SRO, PRO, Lead Adviser and Results Adviser will meet the implementing partners monthly to review progress against the log-frame and to manage risk. These will be the regular meetings intended to track performance. The MEAL component will analyse adaptation requirements at least once a year with an adaptation assessment; these will be used to steer decisions about the focus of the programme based on the context in addition to the annual review. The programme management structures may change once the new entity is established.

What are the risks and how these will be managed?

The overall risk rating of this programme is Major. The main risks identified, and mitigating actions are set out below.
1. Risk due to upcoming elections and change in government: there is a risk that the elections are delayed, or the post-election scenario is a fractious environment. This will be managed by using political economy analysis to identify and support multi-stakeholder partnerships that endure beyond a change in government, and this will be re-assessed after the elections. As this will be a flexible and adaptive programme, any approaches or partnerships that are not delivering will be discontinued. Any risks that are out of appetite for the programme will follow due escalation process within FCDO.
2. Rapid change of civil servants: Given the frequent turnover of civil servants in Bangladesh's public service, there is a risk that continuity in dialogue and partnerships on programme-related issues may be disrupted. To mitigate this, the programme will foster broad-based partnerships of civil servants across senior, mid-level, and junior ranks. Additionally, it will seek to engage at both national and local levels.
3. Safeguarding risk: In Bangladesh, violence against women and girls is highly prevalent. While this programme will not work directly with vulnerable communities, we will conduct due diligence assessment on our implementing partners on all the pillars including safeguarding. FCDO will recommend that safeguarding responsibilities be incorporated in codes of conduct, job descriptions and performance management systems of partner staff and consultants. We will also ensure that partners have environmental and social safeguarding policy throughout the programme cycle. We will require partners meet international best practice on environmental and social standards. The FCDO Programme team will ensure that regular monitoring including through safeguarding spot checks are conducted and include safeguarding as a standing agenda of the programme management meetings.
4. Climate and Environmental risk: This programme presents minimal climate-related risks. However, work on state effectiveness and accountability is anticipated to significantly bolster the Government of Bangladesh’s capacity to formulate and implement public policy.
5. Fiduciary risk: No funding will be channelled through government financial systems. Robust due diligence on fiduciary and financial management of the supplier/partner will be undertaken and they will be required to demonstrate robust fiduciary standards. Audits will be conducted on an annual basis to provide further assurance. All partner agreements have clauses on robust financial management and prompt reporting of cases to FCDO. More details are provided in the financial case.
6. External context risks including security and natural disaster: There is a risk of deterioration of the security situation pre and post elections because of political, civil unrest or a rise in extremism. Bangladesh faces threats from natural disasters such as cyclones, flooding annually and the threat of earthquakes is rising. We expect our programme partners to be resilient and to operate in Bangladesh in the event of a disaster or an escalation of the security situation in discussion with FCDO on being flexible and adaptive to the situation.
7. Delays in formal government approvals: Planned BSEA engagement with government agencies will require a formal Memoranda of Understanding to document working relations and mutual understanding. Finalising MOUs and similar agreements can involve lengthy internal procedures, multiple levels of review and clearances. These processes may cause delays in securing approvals, which could activities. To mitigate this, TAF would draw on a combination of trust relations and its experience in securing requisite approvals swiftly and efficiently to expedite formal requirements. Where necessary, TAF would call on FCDO support to expedite formal approvals where possible.
8. ODA funding: Due to the reduction in ODA to 0.3%, the programme will retain its flexibility and have break clauses set in the arrangements to enable scale up/down or exit early depending on Ministerial decisions.
9. Reputational risk: Supporting state institutions and civil servants may carry reputational risks. To address this, the programme will conduct thorough analysis and adopt a facilitative role rather than a leading one.

A detailed risk register will be maintained on the Aid Management Platform and reviewed quarterly throughout the lifecycle of the programme. Each risk will have the appetite set and if the residual risk goes out of the risk appetite, then the risk will be promptly escalated to the senior management. At the project level, partners will develop and maintain project specific risk register and will update FCDO as part of the quarterly reporting.

How will progress and results be monitored, measured and evaluated?

BHC Dhaka’s Cross Cutting team will manage the implementing partners as per the requirements set out in the agreements signed by them. The logframe will drive the measurement of progress and results.

Theory of Change: The Theory of Change will be used as a framework to structure and adjust programme monitoring and evaluation activities. This will be reviewed throughout the life of the programme and will adapt to the changes according to the need.

Logframe: A logframe will be developed by the programme team jointly with the Results Adviser, MEAL provider and the implementing partner. This will be finalised in the Inception Phase, and will be used for tracking progress against outputs and outcomes. Given focus on adaptation, the logframe will be updated at least annually to reflect changes. The implementing partners will be required to develop their own MEL plans and logframes to measure performance and to feed into the overall programme logframe. Performance against milestones in the logframe will be reviewed annually, through the FCDO’s Annual Review process. The logframe will build on the lessons from similar PDIA programmes.[22]
[22] Delivering institutional reform at scale: Problem-driven approaches supported by adaptive programming (Clare Manuel) DFID Legal Assistance for Economic Reform Programme, 2016 laser-second-synthesis-paper-delivering-institutional-reform-at-scale-final-feb-2016.pdf

Monitoring, Evaluation, Adaptation, and Learning (MEAL): There will be a strong focus on MEAL across the programme. FCDO and TAF will work together during the Inception Phase to develop a joint results framework which facilitates and promotes adaptive programming. This will be reviewed regularly to capture progress and incorporate new learning as the programme evolves.

TAF’s in-house MEAL team will deliver the day-to-day monitoring of the programme to inform adaptation and provide evidence to feed into their strategy testing approach. This will be complemented by BSEA’s MEAL component to support more strategic learning across the whole programme, including ensuring that the programme is being delivered adaptively. Specific activities to be undertaken through the MEAL component will be identified during the inception phase and guided by input from the G7 Results Advisor.

Programme performance against agreed outputs, milestones, and risks will be monitoring through the results framework and assessed through the annual review process. A midline evaluation and an endline performance evaluation are planned to understand the programme’s contribution to intended outcomes and impacts. Findings from these evaluations will be captured in annual reporting and inform decisions on extending into a subsequent phase. As outlined in the Commercial Case, break clauses will be included in supplier agreements to allow for performance reviews against agreed metrics and specific conditions, such as the availability of ODA.

Exit strategy

The programme will adapt regularly, and add/remove problems and partnerships based on traction, success and failure. TAF will procure downstream partners with flexible contracts that enable scale-up and scale-down based on uptake or ODA context. Detailed analysis of the VFM, programme implications, sustainability and responsible exit will be considered before such decisions are taken. A key part of sustainability will be the establishment of a new entity for programme delivery, likely in the second year of the programme. A downstream partner will be responsible for scoping this part of the programme. This will support engagement on state effectiveness and accountability beyond the end of the programme. The programme is reviewed on an annual basis and will continue based on ODA budgets. The aim is to build the effectiveness and accountability of national and local state institutions, exit will be based on achieving this objective where possible.