Annual Review

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate	Choose a risk rating	Choose a risk rating

Programme title: Southeast Asia: Strengthening Research and Innovation for Development (SEA-StRAID)
Programme Value £ (full life): 2,000,000		Review Date: / Sep/Oct 2025
26/09/2026Programme AMP Code: 400459	Programme Start Date: 18 October 2025	Programme End Date: 31 March 2026

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400459
DevTracker Link to results framework:

SUMMARY AND OVERVIEW

Programme description: / Southeast Asia: Strengthening Research and Innovation for Development (SEA-StRAID) helps to build an equitable research ecosystem in Southeast Asia that promotes lower middle-income country (LMIC)-led research agendas for developing and implementing solutions to local, regional and global challenges. The programme deploys technical advice, capacity building support, and funding for regional Research and Development (R&D) partnerships. It aims to improve access to global research, build respectful partnerships, enable countries to recruit and retain quality researchers, and build a stronger, more stable research system that will help the region to achieve sustainable economic growth. / The programme comprises of two elements: (i) a partnership with Wellcome on Developing Research Excellence and Mentorship in Southeast Asia (SEA-DREAM), and (ii) a small diagnostic component to identify potential opportunities for longer term Research and Innovation (R&I) partnerships in the region. / The successful Developing Excellence in Leadership, Training and Science in Africa (DELTAS) Africa programme[1], delivered in partnership with Wellcome in Africa, provides a blueprint for ecosystem-wide impacts of investing in the building blocks of research aligned with national/regional development priorities. Wellcome approached The Foreign, Commonwealth and Development Office (FCDO) to consider a similar partnership in Southeast Asia. A series of discussions with regional stakeholders led by the South & Southeast Asia Research & Innovation Hub (S/SEARIH) established strong interest in a regional science leadership programme that would work at an ecosystem level. The SEA StRAID programme therefore aims to draw from the experience and success of DELTAs Africa, tailored to the specific context in Southeast Asia, and leverage our increasing partnership with The Association of Southeast Asian Nations (ASEAN). / Developing Research Excellence and Mentorship in Southeast Asia (SEA DREAM) / We will invest £1.35 million over 1.5 years to support the development of research systems in SE Asia in partnership with Wellcome. Wellcome is a trusted partner of the FCDO, with multiple long-term programmes, including joint programmes such as the DELTAS-Africa I and II programmes. In the region, Wellcome has longstanding partnerships with national institutions such as Mahidol University (Thailand) and Oxford University - Mahidol Oxford Research Unit (MORU) - which focuses on clinical trials and public health research and Oxford University Clinical Research Unit (OUCRU) in Vietnam. OUCRU, based in Ho Chi Minh city and Hanoi, as well as sister sites in Kathmandu and Jakarta, is at the forefront of the SE Asia clinical and scientific research on infectious diseases of high priority in the region. / SEA DREAM builds on this experience of working regionally in Africa and draw on the relative strengths of both partners to maximise programme impact. It is important that the UK investment leaves a lasting legacy, and that the ‘sum’ of the research spend is greater than the individual grants to SE Asian Universities and institutions. The programme will help to achieve this and complement existing research investment by both FCDO and other research funders. / We will support partnerships in countries where there is existing research capacity and where there is appetite and interest from the local research community to partner with the UK in strengthening research systems. There will be a particular focus on strengthening research capacity and partnerships for development impact in lower resourced settings such as Cambodia, Vietnam, Laos, and Timor Leste. / Since the programme inception, we have facilitated extensive consultations with Wellcome to co-design the programme, identified regional partners for collaborative and co-funding activities as well as to externally communicate the programme pre-launch, and supported capacity building of the regional delivery partner - the Southeast Asian Ministers of Education Organization (SEAMEO). / Regional R&D Diagnostic / The diagnostic was proposed to identify existing gaps i.e. missing or broken links across the system, barriers that hinder regional R&I collaboration, and potential opportunities for change. It also set out potential entry points for the UK that could underpin our longer-term engagement on R&I for development in the region. Specifically, this included a mapping of the landscape i.e. who is doing what, an analysis of external factors such as geopolitics and regional integration, and an in-person consultation with key regional R&I institutions. The consultation included a wide range of researchers, academics, and relevant policy makers from ASEAN Member States with deep knowledge of the region and the R&I ecosystem. / This element, delivered through a competitively procured Supplier, has delivered a report that sets out key recommendations for the UK to deliver our objectives for driving equitable and sustainable development in the region as set out in the ASEAN-UK Plan of Action (PoA) and ASEAN Plan of Action on Science, Technology and Innovation 2020-2025 (APASTI). These recommendations will be used in a longer-term R&I system strengthening business case that will aim to bring positive change to the region by focusing on the ecosystem as a whole, aligned with the wider HMG regional development strategy and approach.
Intended policy objective(s) of projects within this programme. / The programme will drive science and research excellence and leadership in SE Asia by ensuring: / The health and climate research sectors in SE Asia have the foundations necessary to produce and use high quality research / High quality research meets development needs and contributes to economic development, / FCDO and key partners develop stronger, more coherent partnerships that generate long term development and economic benefits for the region. / We will fund regional consortia to produce globally excellent and outcome-focused research that addresses existing national, regional and global health priorities and responds to emerging issues. The approach will be designed to enable the development of research excellence and equitable research ecosystems, where research leaders are nurtured, networks break down barriers to collaboration, and impactful research is translated into real-world solutions, policies and interventions. / The “Scoping Review of the Science, Research and Innovation Landscape in Southeast Asia” component of this programme identified gaps and opportunities in the R&I ecosystems in the region and particularly identify areas where the UK can use its expertise to support the development and sustainability of the R&I ecosystem in the region.
Overall Programme Score / A
Summary supporting narrative for the overall programme score in this review. / The SEA-StRAID programme has already delivered tremendous value and impact, both through the completed R&D diagnostic workstream and the ongoing work on SEA DREAM. / Component 1 (SEA DREAM) (A): / The past year has been focused on preparing the groundwork for the successful downstream delivery of the programme, now to be launched in Quarter 1 of 2026. This has been delivered through extensive consultations with Wellcome and SEAMEO to co-design the programme in anticipation of the full launch in Q1 2026. The foundational groundwork of the programme has focused on the eligibility criteria for potential funders, developed into a final set of applicant guidelines and cost eligibility guidance, embedded within SEAMEO’s policies which FCDO and Wellcome activities have also sought to develop and strengthen. The full application process has also been developed this year including how potential applications will be assessed and scored, including relevant guidance and policies on due diligence and safeguarding. A full communications plan has also been co-developed to communicate and market the programme and its launch across the Southeast Asia region and ensuing that potential applicants absorb the application requirements and timelines. / Timeline shifts have been made due to unanticipated delays in preparatory activities with the key delivery partner. Despite these timeline changes, we are still confident and content in the current delivery of the programme which has also allowed us to expand financial streams outside of FCDO and Wellcome, to include financial support from country Departments of Science and Technology. Technical assistance to strengthen internal systems and processes of the regional delivery partner SEAMEO as set out in the Theory of Change, as required for a large research granting programme, has been delivered successfully. Focus areas were identified via reviewing of operational, governance, and due diligence processes – Leading to seven key areas for capacity strengthening. These were mapped against 16 outputs including: / Procurement policy / Delegated levels of authority policy / Investment and Treasury Policy / Farud and Bribery policy / Conflicts of Interest policy / Safeguarding policy / Risk Management framework / Sub-Award governance policy / Sub-award funding policy / Sub-award Grant management operational framework / Stakeholder engagement and collaboration further demonstrates the local value and reputation of this programme, even before its delivery. Wider funding sources have been identified and actioned through this engagement with Southeast Asian Ministries/Departments of Science and Technology, broadening the integration into regional/local Science and Technology (S&T) ecosystems, strengthening the financial base of the programme, and demonstrating strong regional ownership of the programme. / Component 2 (Scoping Review of the Science, Research and Innovation Landscape in Southeast Asia) (A+): / Delivered successfully and has met expectations from the business case. This piece has helped us identify key priorities for partnership in Southeast Asia particularly in the areas that SEA (ASEAN) countries value the UK’s expertise in. / Strategic expertise and capacity building – UK’s expertise in technology management, policy analysis and R&I policy management / Sustainable and tailored funding models – long-term and multi-country funding for e.g. the ASEAN UK Green transition Fund was much appreciated for the stability they provide for innovation development. The focus on development of locally relevant solutions was also appreciated. / Technological advancements and digital engagement – AI and digital engagement were recognised enhancements to regional R&I strategies. / Localised innovation ecosystems- the UK’s focus on supporting localised innovation ecosystems that are responsive to regional needs was appreciated. / Long-term strategic partnerships- that drive continuous innovation and improvement, enabling sustained research and innovation R&I development moving beyond the limitations of short-term project-based funding.
Major lessons and recommendations for the year ahead / A summary of the key lessons and recommendation are detailed below / Lesson 1: Future/ongoing work must be considerate of the political situations in relevant countries and adopt awareness for planning of any activities. This can impact necessary lead times for deliverables in country. This is both from a cultural and geopolitical context. Culturally, there are numerous traditions and practices across different countries in Southeast Asia that we need to consider as part of our planning for the launch and delivery of the program. Geopolitically, ongoing situations in the region have mostly limited the capacity of colleagues in country to work on programme activities. This may also impact the engagement with a country in more extreme contexts. / Recommendation: / Culturally, we will continue to engage closely with colleague in country and ASEAN, to ensure that planned activities are aligned with local traditions and cultures regarding high-level events and launches. Geopolitically, we will monitor ongoing situations that may impact colleagues’ capacity and that may also impact a country’s ability to engage fully in the programme or for researchers in said country to do so. Timeframe – To end of Financial Year (FY) 25/26, mainly encompassing launch event/s and engagement to launch program / Lesson 2: Continue to explore local funding options and participation by national S&T departments. Ensure that any such agreements do not inequitably advantage participating countries over others. / Recommendation: / Timeframe – A) During ongoing engagement up to programme launch in this FY, where partners are being engaged with and identified, and B) FY 26/27 when SEA DREAM is launched and the bidding window is open, to be conscious of ensuring fairness and openness in the process and that individual countries or groups of consortia do not enjoy inequitable advantages depending on their position or higher exposure compared to other consortia. / Lesson 3: Work more closely with Wellcome to ensure that FCDO inputs and preferences are incorporated into the SEA DREAM programme – ensuring that FCDO values re enshrined in the foundations of the programme including the centrality of equitably partnerships, and that efforts are based upon ensuring Equality, Diversity and Inclusion per the Equality Act 2010. / Recommendation: / Timeframe – Continuous but primarily to end of FY 25/26. / Lesson 4: Ensuring programme impact and effectiveness through risk management and Monitoring, Evaluation and Learning (MEL). The ambitions of the programme are to have a long-lasting impact on the S&T ecosystem across SE Asia and setting key parameters to monitor and measure success will be necessary during the programme development phase. This will also need to be monitored throughout the delivery phase. / Recommendation: / Timeframe – Continual across whole programme delivery
[1] Developing Excellence in Leadership, Training and Science (DELTAS) in Africa - a research capacity strengthening programme that fosters strong intra-African collaboration to impact health science, policy and practice in Africa with an emphasis on strengthening the whole research ecosystem, research excellence and institutional equity.

PROGRAMME STRATEGY OR THEORY OF CHANGE

The Theory of Change (ToC) framework is summarised below:

This initial ToC from the Business Case (BC) remains accurate and valid for the programme of work.

Key programme outcomes remain on track for successful delivery with successful completion of the R&D Diagnostic project under this programme and FCDO-Wellcome-SEAMEO joint workshop in May 2025 to further co-design the funding calls for the program. A soft launch has been planned for October 2025 at both the ASEAN COSTI S&T meeting in Bangkok, Thailand, and in Kuala Lumpur, Malaysia via direct meetings and engagement with prominent Government S&T stakeholders. In parallel, we are successfully planning and preparing for the full SEA DREAM launch in January 2026 at an event which will signal the opening of the programme for applications. In preparation for this we have successfully developed the application criteria and guidance for potential consortia applicants.

We have experienced some slippage in timings for launch of the SEA DREAM project under this program, of approx. 6-9months compared to initial timings set out in the BC. This has been deemed acceptable to ensure successful delivery of programme aims, outputs and impacts. Overall programme impact however remains on track.

Technical assistance to strengthen the internal systems and processes of the regional delivery partner has been delivered successfully. Impact here was greater than anticipated and led to additional work to support implementation of developed policies for the delivery partner.

Key focus on activities for the next year encompass engagement and launch of the programme, which also opens the window for bid submission. Decisions made here were considerate of ongoing political situations in key countries including Thailand, which meant shifting these timelines, as well as ensuring thorough engagement with relevant Government Departments and local stakeholders to ensure maximum engagement and coverage of the programme equitably across the SE Asia region.

We have also successfully delivered the second component of this programme – An R&I scoping piece. This commissioned project sought to identify opportunities to strengthen R&I ecosystems in Southeast Asia, including the ASEAN member countries, with the aim of delivering development impact and foster inclusive economic growth in the region. Specifically, the research project aimed to a) map the R&I landscape, b) identify gaps and barriers that hinder regional R&I collaboration in Southeast Asia, and c) explore opportunities for long-term intra-regional and international engagements. The primary output for this project was a multi-day workshop delivered in March 2025, followed by the final report from the study – Which sets out the key challenges and opportunities for the UK in supporting Southeast Asia’s S&T ambitions and capacity strengthening activities. This has been successfully delivered against the initial outcomes set out in the BC and was delivered in line with the timescales set out in the BC.

The overarching impact set out in the ToC of a “thriving national & regional research ecosystem that contributes to social and economic development” remains highly achievable from the current state of the programme and will likely be strengthened further by the regional engagement and collaboration ongoing between FCDO, Wellcome and local/regional stakeholders. Through our engagement with ASEAN and the ASEAN Secretariat, we are pursuing certification of the programme with the S&T Secretariat who have also engagement positively and extensively during the inception of this programme of work. We have also used this network to engage with national S&T departments to both collaborate on the design of the programme to consider regional/national contexts and needs, but also to identify and agree co-funding opportunities to further strengthen the financial foundations of the programme beyond the initial funding from FCDO and Wellcome. Through these engagements we have further solidified SEA DREAM’s presence across Southeast Asia including through Ministerial links facilitated by FCDO Embassy and STN colleagues. This has culminated in an agreed launch at a launch event– Which will give the programme and broad and large audience to launch the programme across the region.

This programme continues to deliver significant Value for Money (VfM), particularly considering the level of FCDO investment compared to partners and the anticipated impact that remains to be delivered. Against wider departmental business plans and strategies, this programme will continue with its aims to strengthen the research and innovation ecosystem in Southeast Asia by delivering impactful science and a development approach that is poverty-driven, contributing to the 2030 SDG Agenda. This is framed around building equitable partnerships that deliver results, leveraging UK expertise to provide advice, exchange lessons and evidence, and the objectives in the ASEAN-UK PoA.

1. The following schematic, co-developed with Wellcome, sets out our vision, mission and principles. This ensures a focus on:
  1. Bringing through and enabling a new generation of research leaders to address health and climate change priorities particularly in low resource settings
  2. Forging new partnerships and wider research networks across SE Asia, and through a regionally based operational delivery partner, encouraging further research collaborations across FCDO Posts and Wellcome-supported partners in the region
  3. Building long term links to bolster open mode R&I applications from the region
  4. Enabling and promoting equity, diversity and inclusion in research and sharing lessons on positive research culture across the region

DETAILED OUTPUT OR PERFORMANCE AREA SCORING

Delivery of Projects
Performance area:	Delivery of projects
Number:		1	Score:	A
Weighting (%):		100	Weighting revised since last AR?	N/A

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

SEA- DREAM Activities

Activities over this year have been focused on preparation for the launch of the SEA-DREAM programme, internal capacity strengthening of the local delivery partner and the regional diagnostic study.

A core deliverable under the project “SEA DREAM” which sits under the broader SEA-StRAID programme during the FY 25/26 is the capacity strengthening work for the local delivery partner SEAMEO, to provide bespoke support to develop their governance and operational processes, to strengthen their ability to successfully deliver the programme within the region. This included additional implementation work on the partner’s HR processes and systems. We leveraged the supplier under the existing contract of the FCDO programme ‘The Evidence Fund’, to deliver the analysis and provide assistance to help bridge identified gaps in collaboration with the regional deliverer partner - the Southeast Asian Ministers of Education Organization (“SEAMEO”).

Here, 16 outputs were identified and agreed as part of the Terms of Reference, to develop policies and frameworks for a large multi-year regional research funding progamme based on three key design principles: Fit for Purpose, Robustness, and Proportionality. From this activity, the SEAMEO Secretariat has implemented procurement and risk management practices that were not present before the project initiation. The full list of outputs delivered here are listed below. In addition, assessment and recommendations in relation to cyber threat mitigation and personal data as well as internal control were delivered

  1. Procurement policy
  2. Delegated levels of authority policy
  3. Investment and Treasury Policy
  4. Farud and Bribery policy
  5. Conflicts of Interest policy
  6. Safeguarding policy
  7. Risk Management framework
  8. Sub-Award governance policy
  9. Sub-award funding policy
  10. Sub-award Grant management operational framework

A set of HR frameworks have been delivered to support SEAMEO Secretariat in effectively managing and governing their increasing programme-based staff. All of these outputs have enhanced SEAMEO’s operational & governance capacity and established it as a leader in managing global research opportunities for Southeast Asia.

Delivery Against Planned Timescales, Budgets, and Quality - Programme has experienced slippage on some deliverables due to extended time on preparatory activities and capacity strengthening. New timeline will launch the programme in January 2026 which will also open the bidding window, which will remain open until June 2026 (exact date TBC). Following bidding window closing, bids will be assessed, and final successful applications will be informed later that year with projects commencing in early 2027. Decision to extend these timeframes were made to ensure that the foundations of the programme are rigorous and will allow for better monitoring, VfM and impact from the funded projects. This is also imperative given the longer-term plan in this being the landmark programme for S&T capacity strengthening and engagement across SE Asia for the next decade at least, akin to the DELTAS programme in Africa.

Risk and Financial Management - Wellcome have committed to long-term funding of £45 million for DREAM, so the contribution from FCDO continues to deliver high value and impact. Partnering with Wellcome has ensured significant visibility and credibility for DREAM within the global health sphere and research ecosystems. Wellcome already have SE Asia presence and expertise and have been central in ensuring that lessons have been learned from the DELTAS Africa programme to set up DREAM.

A comprehensive risk register has now been developed and approved, which is monitored and updated regularly. The overall risk rating for this programme is moderate and deemed manageable with the agreed mitigations.

Partnership and joint-delivery – The programme has already demonstrated the value of joint delivery with Wellcome and with SEAMEO, using the lessons learned and pre-existing relationship with Wellcome through DELTAS and wider programmes.

Scoping Review of the Science, Research and Innovation Landscape in Southeast Asia

Objective:
This scoping review mapped the R&I landscape in Southeast Asia, identified gaps and barriers that hinder regional collaboration, explored opportunities for long-term intra-regional and international engagements, and proposed potential interventions and collaboration models for the UK to support R&I growth in Southeast Asia. The project involved a comprehensive desk review, an in-person workshop, and individual stakeholder consultations to gather insights and feedback from a wide range of voices across the region. The key research objectives are outlined as follows:

1. Mapping of the overall science, technology and innovation (ST&I) landscape in Southeast Asia: Map the external policy framework, key stakeholders, and major research and innovation networks and platforms—including clusters and special zones—across ASEAN countries.
2. Thematic priorities and partnerships of the major national and regional scientific research and innovation networks and platforms: Identify key research priorities, major scientific collaborations, and how thematic focus areas have evolved in Southeast Asia over the past decade.
Broad direction of travel: Identify key institutions, emerging international partnership priorities, and opportunities for new or enhanced research and innovation collaborations with established, powerhouse, and emerging knowledge economies in the ASEAN region.
Opportunities for the UK: Propose targeted interventions and delivery models to drive equitable R&I collaboration, maximize development impact, and strengthen scientific ecosystems using proven approaches.

Procurement and Delivery
This work, including procurement, coordinating with the supplier on the technical aspects of the project, and administrative, was led by the S/SEARIH team.

The study employed a mix-methods methodology combining secondary desk-based research with key informant interviews, and a regional workshop where findings from the secondary research and interviews was validated.

The study including the delivery of the workshop was delivered by a consultancy Arup, based in Hong Kong, who were procured through in-house procurement in order to expedite timelines and ensure quality delivery. In the selection criteria for the supplier, the ability to design and deliver a workshop with high-ranking government officials and academics was also included. The SSEARIH team coordinated with FCDO’s Science and Technology Network (STN) based in Southeast Asia who supported the planning, logistics and delivery of the workshop, including through collating relevant participants to input and attend the workshop, all of whom were identified as important R&I stakeholders from their respective countries.

This workshop was delivered in March 2025, bringing together over 40 S&T stakeholders from across SE Asian countries with valuable engagement across 1.5 days in Bangkok, Thailand. The workshop design and execution received positive feedback from the participants. Reflections and feedback from the workshop were shared with the participants. The final report collated the findings from all three sources of information; secondary desk-based research, interviews with over 30 representatives of different entities involved in STI in the region and the workshop that included representatives from ASEAN, national governments, international research entities and academics.

The report has been shared internally with STN teams in the region, and findings from the report are feeding into programme development and design, particularly in the new 0.3ODA world we are in currently.

The Regional diagnostic workstream was delivered on time, against all deliverables.
Recommendations from the report:

The report set out the dynamic and rapidly evolving landscape of R&I in Southeast Asia and how this presented both significant opportunities and challenges (discussed more in [14], and the systemic and sectoral challenges that hindered the region's full potential.

1. The report identified key priorities for partnership in Southeast Asia particularly in the areas that these countries value the UK’s expertise in.
      1. Strategic expertise and capacity building – UK’s expertise in technology management, policy analysis and R&I policy management
      2. Sustainable and tailored funding models – long-term and multi-country funding for e.g. the ASEAN UK Green transition Fund was much appreciated for the stability they provide for innovation development. The focus on development of locally relevant solutions was also appreciated.
      3. Technological advancements and digital engagement – AI and digital engagement were recognised enhancements to regional R&I strategies.
      4. Localised innovation ecosystems- the UK’s focus on supporting localised innovation ecosystems that are responsive to regional needs was appreciated.
      5. Long-term strategic partnerships- The UK’s International Development Strategy focused on long-term strategic partnerships which fosters continuous improvement and innovation which supports R&I development better than only focusing on short-term financing for projects.

The intervention opportunities outlined in the report are below and set out how proposed initiatives can support the opportunities identified in the report. This is set out via eight key themes, and for each theme, analysis of the challenges and opportunities for interventions. These initiatives aim to develop a skilled workforce, foster innovation, and create sustainable, long-term partnerships between Southeast Asia and the UK. Summaries of these key themes and relevant UK opportunities are below:

  1. Education and Capacity-Building - Transdisciplinary and STEM programmes, technical and vocational education and training transition, scholarships and twinning programmes.
  2. Business Management and Commercialisation - Enhanced IP education and training, digital skills development, academia-industry collaboration.
  3. Research Consortia and Centres of Excellence - Established collaborative entities, regional innovation support network, inclusive governance.
  4. Funding Strategies - Integrated funding models, multi-phase projects, flexible grant programmes, short-term project investments.
  5. Incentives and Talent Retention - Flexible work policies and career growth, regional initiatives, recognition and awards, mentorship programmes.
  6. Investor Confidence – Investor relation education, a stable investment environment.
  7. Bureaucratic Hurdles - Simplified procedures, grant & proposal writing training.
  8. Monitoring, Evaluation, and Reporting - Data interpolation, a unified framework for metrics, resource allocation optimisation.

-

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).

See: Major lessons and recommendations for the year ahead (pages 4-5).