Business Case Template - Smaller Projects in programmes

Portfolio/ Business/Country Plan Summary / In a world characterised by new geopolitical challenges and rapid technological change, DOSD works to re-invigorate the UK’s leadership on international development. We support delivery of the Foreign Secretary’s priority of a modern approach to development, contribute to international development priorities such as the Sustainable Development Goals, promote global action to ensure ODA safeguards recipients and does no harm, and help to build open societies underpinned by inclusive, democratic institutions
Programme Title: Preparations for the FFD4 conference – a pivotal moment for the SDGs and mobilising finance
Programme summary (100 words maximum): A programme to support engagement for the fourth Financing for Development (FFD4) conference and its outcomes, with a focus on Global South partners. FFD4 will be held in Seville, Spain, 30 June – 3 July 2025, with the aim of agreeing how to finance the UN Sustainable Development Goals (SDGs) out the 2030 and with a focus on reform of the international financial system. This programme will provide flexible and demand-led support for a range of activities that will contribute to achieving successful FFD4 outcomes in line with UK objectives. These activities will include commissioning quick pieces of research on key FFD4 topics, organising events with key stakeholders in the run-up to FFD4 and at the Summit, and support for partners, particularly Civil Society Organisations, to meaningfully participate in key FFD4 preparatory events and processes. The activities will demonstrate UK leadership and commitment to Global South priorities, including accelerating the SDGs, narrowing the SDG financing gap and Global Financial System reform. This will support the reset with the global south partners and demonstrate the UK modern approach to development and partnership.
Programme Value: £550,000		Directorate/Department: Development & Open Societies Directorate, Development Policy & Partnerships Department
Confirmation of review processes		Head of DPPD confirms the process for Business Case review has been followed
Contact names		SRO: / PRO:
Threshold for final approval of Business Case: Director (under £2m for smaller projects programmes and in line with PrOF rules)
Business Case approval:	25/02/2025	Name and role of Approver: Deputy Director, Development Policy & Partnerships Department
Programme Code:	Programme Start Date: 1 February 2025		Programme End Date: 1 Aug 2025
Overall risk rating:	Moderate
Teams link:

Business Case
For a Smaller Projects programme

## Strategic Case

What is the rationale for FCDO spending?

We live in an increasingly contested world, where too many people face economic hardship; the gap between richer and poor countries is widening; and the effects of the climate and nature emergencies, and rising conflict and fragility, are intensifying desperate humanitarian need. With only 17% of the SDGs with targets on track to be delivered by 2030 and an estimated annual SDG financing gap of $4trn, the world must deliver more and better financing.

The UK and many Global South partners see FFD4 next year as a pivotal moment to secure global consensus on a modernised development finance landscape that addresses development, climate and nature challenges in an integrated way and forms the basis of a renewed global partnership for accelerating progress on the SDGs.

FFD4 also presents a strategic opportunity to demonstrate the UK’s modernised approach to development and partnership based on mutual trust and respect. Initiatives such as the Paris Pact for People and Planet, the Bridgetown Initiative and Hamburg Sustainability Conference have demonstrated what can be achieved when we come together to progress the financing for development and GFS reform agendas. FFD4 is an opportunity to build on these partnerships, while going further and faster. This programme will allow the UK to engage strategically to advance this critical agenda, demonstrating UK commitment to accelerating the SDGs, narrowing the SDG financing gap and Global Financial System reform.

A.2. Proposed programme

This is a flexible programme of up to £550,000. It will provide targeted short-term, responsive support for activities (also known as projects) that will complement UK’s overall engagement in the FFD4 conference and its outcomes. The delivery partners will include relevant UN agencies given their oversight and support role in the FFD4 process and ability to mobilise quickly. There is a possibility we may also engage CSOs and/or academic institutions directly.

The programme will likely support the following broad types of activities:

- Supporting meaningful engagement from partners, particularly Civil Society Organisations from developing countries, including by covering costs associated with attending and substantively engaging in key meetings and conferences.
- Structured engagement and policy dialogues to influence key FFD4 policy and reform agendas. This could include organising roundtables, workshops, conferences and cross-stakeholder knowledge exchanges in the UK and overseas similar to the FFD lunch co-hosted by the Minister for Development at the Hamburg Sustainability Conference in October.
- Research and analysis to build or synthesise evidence base on critical financing for development policy issues; improve understanding and awareness of key issues among relevant stakeholders; possible impact evaluations and feasibility studies including support for think tanks to conduct independent studies.

A.3.	How will the programme ensure compliance with FCDO rules/commitments on:

ODA eligibility

This programme will be reportable as ODA in full. All activities will comply with internationally agreed rules that are overseen by the OECD’s Development Assistance Committee (DAC). Given the technical support nature of this programme, there will be activities which will cover costs for events and conferences (which will be consistent with ODA eligibility.

Gender equality, disability inclusion and those with protected characteristics

The SDGs and Agenda 2030 are underpinned by a commitment to ‘Leave no one behind’, and we will ensure this thread is woven through all projects and discussions. For example, in organising events, we will ensure that those with protected characteristics have equal access. We will draw on the lessons learned from our Wilton Park event from earlier this year.

Paris agreement and Environmental Protection
The selection of projects will strictly follow do no harm principles and will promote positive benefits to the environment where feasible, and comply with the Paris agreement.

Public Sector Equality Duty (PSED): the programme will give due regard to protected characteristics to the eliminate prohibited conduct under the Act (unlawful discrimination, harassment and victimisation); · advance equality of opportunity; and foster good relations between people who share a protected characteristic and those who do not share it.

## Appraisal Case

Describe the criteria under which each project in the programme will be selected for funding.

The programme will focus on activities and projects which support international discussions on how to accelerate the SDGs and narrow the financing SDG gap. The programme is designed to be flexible to maximise the different engagement opportunities which are likely to emerge between now and FFD4, with international preparation for, and inter-governmental negotiations on the FFD4 outcome document beginning in earnest in early 2025. It is likely that UN agencies will be our main delivery partners. Given many of the UN agencies are established UK delivery partners, this will enable us to work within existing due diligence and wider processes and parameters, ensuring funds are distributed in a timely fashion and according to value for money principles. This will be important given the short timeframe we have between now and the conference in Seville.

What do you anticipate the maximum project value will be?

The maximum project value will be £250,000. This programme is aimed at providing a responsive and flexible approach to activities that meet the needs outlined in the programme summary above. However, if this ceiling in project value is likely to be breached then agreement will be sought through the same process as agreeing this business case. The rationale for this will be set out clearly and will be documented in the correct team's folder for audit purposes. The overall programme will not exceed £550,000.

## Commercial Case

How will delivery partners be selected? What funding arrangements are likely to be used?

It is likely that the majority of delivery partners for this programme will be UN agencies, as FFD4 is a UN-led conference, UNDESA and other UN agencies are setting up funds to support and enable its delivery. We will also consider other delivery partners, such as civil society organisations and think tanks, where needed and based on coherence with the programme objective.

Delivery partners will be selected on reputation and experience; ideally, we will engage those that are registered in our internal due diligence database due to short timeline with FFD4 in June.

Given we anticipate the delivery partners to largely be UN agencies, we expect agreements would be in the form of Memorandums of Understanding (MoUs). Where there is a need to seek commercial service providers then we will look to engage providers through the FCDO framework arrangements – although this is not anticipated.

The use of funds per activity is limited to £250,000 (maximum limit). The programme will, within the rules set out in the Programme Operating Framework (PrOF), utilise the full range of available options of engaging activities through MoUs and when needed through Accountable Grants or contracts.

How will the programme manage the risk associated with delivery through each partner?

This programme will respond to short term activities. Regular ‘keep in touch’ engagement with delivery partners will happen on a periodic basis where appropriate. Where activities are undertaken in New York, we will look to on colleagues at our Mission to support with monitoring. It is not anticipated that due diligence assessments of potential delivery partners will be needed as key UN agencies have already completed relevant processes.

## Financial Case

The programme value is £550,000. Regular monitoring of funds will be undertaken to ensure effective and efficient allocation and disbursement through the FYs 2024-25 and 2025-26. The programme will utilise established financial processes for the deployment of the RDEL resources. The cost per activity will not exceed the £250k upper limit as noted in PrOF. In exceptional circumstances, where this limit breeches the ceiling, this may be referred to the Director for approval.
We judge that financial risk associated with this project is moderate. The funds will be managed by the delivery partner and there could be a risk of objectives not being met in full. These could be for reasons beyond their control such as non-attendance of participants or conference logistics issues. Mitigations for financial risk should be worked into project level activities.
Appropriate robust systems and measures will be in place to ensure that the expenditure is well-monitored, reported and accounted for across the initiative. The disbursement of funds will be managed via standard FCDO agreements.  Following the programme completion, we will undertake a proportionate lessons learning and evaluation process.

## Management Case

How will the programme be managed?

The SRO will take strategic decisions, informed by their discussions and engagement with colleagues from UK Mission to the UN in New York, policy teams and posts. The SRO will be supported in their strategic decision making by the DPPD Deputy Director where needed. At the operational level, the programme will be managed by the SRO and PRO. The SRO and the PRO will be responsible for all AMP and HERA and other corporate requirements.

Monitoring and reporting:

Individual projects will be managed by the PRO, who will be responsible for financial management, supplier engagement and compliance with PrOF Rules. The PRO will routinely report to the SRO and flag any emerging risks.

Risks

1. Strategy and Context: There is a risk that we fail to identify any projects that are of a short-term nature and within the £250,000 limit which both complement UK FFD4 objectives and provide strong value of money. To mitigate this, we will work closely with colleagues across the network, particularly those in the UK’s Mission to the UN, to ensure we have early sight of opportunities, as well as working evaluating opportunities against the programme’s objectives and whether there a strong value for money case.
2. Policy and Programme Delivery: For a programme that is envisioned for less than one year, the delivery needs to be at a pace to deliver impact while ensuring value for money. To mitigate this, we will work primarily with UN agencies as delivery partners, given the FCDO has worked with many UN agencies before and completed relevant due diligence etc.
3. Financial and Fiduciary: The business case lays down the contours within which the funds will be utilised. However, due to the responsive nature of this programme, there lies a risk that the funds are not fully utilised. Care will be taken that the funds are disbursed under the criteria set out and any remaining funds are flagged to the departmental finance team as quickly as possible.

There will be a light-touch review of the projects, culminating in a proportionate Programme Completion Report. We deem the residual risk to the programme to be moderate, which falls within our risk appetite.