## Annual Review

Title: Maziko a Maphunziro (Foundations of Learning) Programme
Programme Value £ (full life): £39 million		Review date: 29/04/2026
Programme Code : [AMP ID 400473]	AMP start date: 29/01/2025	AMP end date: / 30/06/2030

Summary of Programme Performance
Year	2025/26
Overall Output Score	A
Overall programme risk rating	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400473/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400473/documents

List of Acronyms

BGE – Bridge for Girls Education
BHC – British High Commission
CDF – Constituency Development Fund
CPD – Continuing Professional Development
CMP – Centrally Managed Programme
DBE – Directorate of Basic Education
DQAS – Directorate for Quality Assurance and Standards
DSTI – Directorate of Science, Technology and Innovation
DTED – Directorate of Teacher Education and Development
FCDO – Foreign Commonwealth and Development Office
GPE – Global Partnership for Education
IPTE – Initial Primary Teacher Education
LMICs – Low- and Middle-Income Countries
MFLP – Malawi Foundational Learning Programme
MIE – The Malawi Institute of Education
MoEST – Ministry of Education, Science and Technology
NMCRP – National Mathematics Curriculum Reform Programme
ODA – Overseas Development Assistance
PEAs – Primary Education Advisers
SMES – Strengthening Malawi’s Education System
TTCs – Teacher Training Colleges
TLMs – Teaching and Learning Materials
VfM – Value for Money

## A: SUMMARY AND OVERVIEW

Description of programme

The Maziko a Maphunziro (Foundations of Learning) programme (Maziko) aims to improve the quality of foundational education in Malawi through a joint effort with the Government of Malawi and key development partners. It builds on the Strengthening Malawi’s Education System (SMES, 2018–2025) programme, which introduced an evidence-based maths reform (National Maths Curriculum Reform Programme, NMCRP) with a new national curriculum, teacher training and learner workbooks for all children in Standards (Grades) 1-4. The initiative is one of the most effective foundational learning reforms delivered at-scale in Low- and Middle-Income Countries (LMICs) with the potential to more than double the number of 10-year-olds with basic maths skills in Malawi. Through Maziko, the British High Commission (BHC) in Lilongwe is now focused on institutionalising and sustaining this reform, ensuring it becomes embedded within national systems and continues to benefit learners over the long term.

This Annual Review covers the programme’s first year. Following Business Case approval in November 2024, delivery began in June 2025 through Cambridge Education. In parallel, BHC procured a new supplier, Montrose, which is now in its inception phase. Montrose will assume full delivery responsibilities when Cambridge Education’s contract ends in March 2026 and delivers until programme closure, which likely to be in March 2028 due to ODA reductions.

The reduction in ODA has resulted in key changes to this programme. Interventions related to school feeding and climate resilience have been removed, scholarships for rural disadvantaged girls will be significantly scaled down and the research and impact evaluation has been removed. This Annual Review therefore reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

Maziko scores an A in its first year. Although a new programme, it represents a continuation and institutionalisation of the maths reform, building on the progress highlighted in the SMES Programme Completion Review (PCR). While there is no new data on learning outcomes after the initial pilot, the programme has continued to deliver value for money and there is good reason to expect continued improvements following teacher trainings – evidence shows that teachers are the most significant factor in determining students’ learning outcomes (see section D). Continuity in supplier has been critical: Cambridge Education has remained a trusted Government partner with strong sector relationships. Despite international shipping delays affecting Term 2 learner workbook delivery in Standards 1–4, Cambridge Education met most milestones for this Annual Review and its final contract extension, training over 34,000 teachers and delivering over 7.7 million workbooks.

During the year, BHC secured $7.5 million in co-funding from the Prevail Fund, ensuring continued provision of learner workbooks for the next two years and avoiding premature shifts to non-evidence-based alternatives. BHC also proactively managed several operational challenges, including negotiating a contract extension with Mott MacDonald until March 2026 despite the global closure of its Cambridge Education subsidiary, and rapidly procuring a new supplier. Montrose was onboarded in time to enable a productive handover between suppliers. BHC also secured an agreement with UNICEF to deliver teacher training DSAs (see Output 2), ensuring the final round of teacher training proceeded as planned.

Finally, Maziko remains aligned with the BHC Portfolio Strategy, with human capital improvements underpinning priorities on Growth and Investment.

Major lessons and recommendations for the year ahead

The SMES PCR recommendations remain relevant for the year ahead and should be considered in parallel (see Annex 1). These are not repeated here. In addition, this Annual Review highlights the following priority recommendations, informed by lessons learnt and broader FCDO shifts over the past year:

1. Advocate for and support a sustainable financing strategy for reform delivery. Engage the Ministry of Education, Science and Technology (MoEST) and key stakeholders to determine how the education budget and Constituency Development Fund (CDF) will support reform implementation. Use this analysis to inform BHC advocacy and guide technical assistance under Output 3 by August.
2. Proactively create opportunities to strengthen Government leadership of the maths and foundational learning reforms. Support sustained ownership and visible leadership, including through a Ministerial field visit, technical deep dives and strong Government engagement in the Education World Forum (EWF) in May and the Foundational Learning Exchange (FLEX) in July.
3. Ensure decisions on teaching and learning materials (TLMs) are fully evidence-based. Support MoEST to build a robust evidence-based on cost-effective alternatives to learner workbooks, including working with the Ministry and the Prevail Fund to the design the Prevail-funded research and options to pilot.
4. Support strong collaboration with sector partners. Maintain close coordination with multilateral organisations, such as the Global Partnership for Education (GPE) and the World Bank, to maximise the impact of FCDO bilateral and central investments. With donor funding to education declining, BHC and Maziko should prioritise sector-wide alignment, promoting transparency, joint planning and mutual accountability to strengthen coherence and effectiveness across the system.
5. Strengthen district-level governance and data use. Work with MoEST to provide clear guidance to districts, schools and PEAs on managing book surpluses/deficits and fully utilising dashboard data. This will support stronger governance and accountability for improved impact and sustainability.
6. Integrate the Bridge for Girls Education (BGE) programme into Maziko by September. As BGE concludes in August 2026, ensure its activities are integrated into Maziko to allow supported girls to complete secondary school, in line with the Maziko Business Case.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

Given changes since Business Case (BC) approval, a new Theory of Change (ToC) was developed during the inception phase of Cambridge Education’s Contract Amendment six (September), reflecting the new programme scope. While the desired outcome and impact remain the same, the intermediate outcome and the outputs have changed, focusing on the narrower scope of the maths reform.[1] There are three outputs: 1) Students and teachers have access to the maths teaching and learning materials (TLMs), 2) quality teacher training on the revised maths curriculum is delivered and 3) the maths reform is institutionalised and sustained.
[1] Intermediate outcomes on education system climate resilience and support for rural disadvantaged girls have been removed.

The ToC is supported by strong evidence, including rigorous impact evaluation results under SMES that show statistically significant learning gains for both girls and boys. The evaluation also noted that the most disadvantaged children are not improving, with high absenteeism, hunger and special needs among this group potentially explaining why they are not benefiting enough. Complimentary investments through the SCALE Centrally Managed Programme (CMP) will partly address this by supporting remediation approaches to ensure all learners can catch up.

The ToC assumes that training in-service teachers will lead to sustained improvements in teaching quality and foundational learning. International evidence, though limited, indicates that without follow-up coaching and pedagogical support, the impact of training alone is unlikely to last. The Continuing Professional Development (CPD) component of the Malawi Foundational Learning Programme (MFLP), funded by the FCDO-supported Global Partnership for Education (GPE) global fund and the World Bank, offers an important opportunity to develop Ministry-led approaches at school and zone level that give teachers ongoing support and peer learning.

The main shift in the reform approach is the added focus on improving pre‑service teacher training to ensure that lower primary maths content in the Initial Primary Teacher Education (IPTE) curriculum aligns with the primary maths curriculum. The programme is also expanding its work on identifying alternatives to termly learner workbooks. This includes assessing the costs, efficiency and effectiveness of various options, informed by programme experience, international evidence and pilots of alternatives to individual workbooks.

This AR recommends, including a new output ahead of the next review to ingrate the current support provided under the Bridge for Girls’ Education (BGE) programme when BGE comes to an end in August 2026. This will allow for continuation of support to 500 girls in secondary schools in Ntchisi and Phalombe, ensuring they can complete their education.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to meet the expected outcomes and impact. Focus for the coming year will be the institutionalisation and sustainability of the reform. Complimentary support through the SCALE CMP (FCDO-funded) on remediation and the MFLP on CPD, will help maximise the learning outcomes and the impact. Support to develop a national learning assessment through the Data for Foundational Learning (Data4FL) CMP will also help ensure that progress can be tracked. Together, these initiatives position Maziko as part of a coherent, Government-endorsed package of foundational learning reforms.

However, overall success of the programme will depend on continued Government leadership and budget commitments to teaching and learning materials. While the maths reform remains a MoEST priority, the reduced education budget for 2026/27 highlights persistent fiscal constraints that threaten full institutionalisation and long-term sustainability.

In the year ahead, Maziko will prioritise strengthening sustainability across outputs, securing continued Government commitment, and aligning with broader BHC efforts on macro‑economic reform. Progress in these areas could contribute to improved fiscal space and generate positive spill‑over benefits across the education sector.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

Based on achievement to date, and overall opportunities of the reform, the programme is recommended to continue. Recognised as one of the most effective foundational learning reforms in LMICs, the reform has not yet reached its full potential. In a context where change can be slow and difficult, Maziko presents a rare opportunity to deliver real and meaningful impact for Malawi’s children, building the human capital required for the future.

## C. DETAILED OUTPUT SCORING

Output Title	All students and teachers in S1-4 have access to the maths teaching and learning materials (learner workbook and teacher guide)
Output number:		1	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review (February 2026)	Progress
1.1 Learner workbooks and revised teacher guides for S1-4 mathematics procured and distributed to all schools	All children have received books for S1 - 4 for terms 1 and 2 of the 25/26 academic year	Achieved: Term 1 and 2 books for the 25/26 academic year were delivered and distributed in schools prior to term start.
	Books for all S1-S4 children for term 3 of the 25/26 academic year have been delivered and stored in a warehouse	Achieved: Term 3 books were delivered on 24 February and stored in the warehouse in Lilongwe.
	Books for all S1-S4 children for term 1 and 2 of the 26/27 academic year have been delivered and stored in a warehouse	Not achieved: Due to shipping delays, Term 1 and 2 books are expected to be in country in April.

Briefly describe the output’s activities and provide supporting narrative for the score

This output moderately did not meet expectations due to international shipping delays of student workbooks. While this was beyond the control Cambridge Education, the impact on teaching and learning was significant.

Through SMES and Maziko, Cambridge Education has refined printing and distribution processes to achieve strong Value for Money (VfM).[2] This year, the programme successfully delivered 7.7 million books to Standard 1–4 learners in Malawi (terms 1 and 2 2025/26 academic year). Building on recommendations from the SMES PCR, BHC also secured co-funding through Prevail for continuation of learner workbooks over two years, avoiding the need to transition to alternative or potentially cheaper options not backed by evidence of effectiveness (see Output 3).
[2] Learner workbooks are a core element of the maths curriculum reform. Every child receives their own workbook each term and complete maths problems directly in the workbook, with lessons designed to complete one page per day. Because the books are written in and only need to last a single term, they can be produced at low cost without needing to be highly durable.

Unfortunately, Term 2 books were significantly delayed due to severe congestion in shipping lanes and ports in East Africa. Learners received their books halfway through the term, which impacted on teaching and learning. Cambridge Education worked with the Ministry to develop and share guidance on remediation during this time. Feedback from schools highlighted that some teachers used teacher guides from last year to progress teaching and learning, while others (Standard 3-4 teachers) who had not yet received guides for all terms, struggled. Whilst the costs of shipping internationally have to date proven to be the most economically competitive, this has raises questions about cost-effectiveness when delays impact on teaching and learning.

Books for the next academic year have also been delayed, originally expected in February, they are expected to arrive in Malawi in April.

Ongoing challenges remain in ensuring accurate allocations of books to schools and districts. While Cambridge Education has made significant progress in refining estimations using Government data for, small variances are unavoidable. Field visits highlight good practices emerging where schools, supported by Districts and Primary Education Advisers (PEAs), are proactively adjusting surpluses and deficits amongst themselves.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no changes to this output. Proposed changes are outlined in the section below.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

According to the procurement ToR, Montrose must identify the best value‑for‑money approach for procuring books for the 2027/28 academic year. This assessment should weigh the trade‑offs between cost, the goal of strengthening national printing capacity, and the risks associated with regional or international procurement. Key factors to consider include the new proposed Government surcharge on imported textbooks and exercise books, the escalating conflict in the Middle East, end-year port congestions, and shipping routes that require vessels to berth on the east coast of Africa before offloading at Beira, as this has contributed to significant delays in the past.

The programme should continue working with the Ministry to promote and support district‑level redistribution of books to manage local surpluses and deficits.

Output Title	Quality teacher training in revised mathematics curriculum is delivered
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review (by February 2026)	Progress
2.1 Every S3 and S4 teacher is trained and feels prepared to deliver the new curriculum	At least 34,000 S3 and S4 teachers, head teachers and PEAs in public schools, including specialist teachers, have been trained in the S3 and S4 revised mathematics curriculum.	Achieved: 34,071 teachers, head teachers, ACCOs and PEAs trained in term 1, and 36,372 trained in term 2 and 3 content, for the S3 and S4 revised maths curriculum.
	90% of teachers trained report being confident or quite confident in teaching the new materials.	Achieved: An average of 96% of participants in Term 1 and 2 training reported feeling confident or quite confident in teaching the new materials
2.2 The mathematics curriculum for early grade teachers in Teacher Training Colleges is updated to align with the approaches of the Standards 1 - 4 primary mathematics curriculum	The IPTE syllabus and module(s) for lower primary maths has been updated	Achieved: The IPTE syllabus and 4 modules on primary mathematics have been updated to align with the revised primary mathematics curriculum, and approved by DQAS for use in TTCs
	Revised IPTE materials have been distributed to TTCs (syllabus, teacher educator and student teacher handbook)	Partially achieved: / 480 copies of syllabuses and 23,920 IPTE materials were printed and delivered to all 10 public TTCs in April 2026.

Briefly describe the output’s activities and provide supporting narrative for the score

This output met expectations. Over 34,000 Standard 3–4 teachers were trained on Term 1 and 2 content, with 96% reporting confidence in teaching the new materials. Prevail Fund support enabled an additional training day in Term 1, improving training quality. The pre‑service syllabus (Initial Primary Teacher Education, IPTE) and training modules for IPTE were completed and distributed to Teacher Training Colleges (TTCs).

The face-to-face teacher training has continued to adapt as reforms expanded. Training materials were developed collaboratively by Malawi Institute of Education (MIE) and national/ international experts, overseen by a joint MoEST–MIE committee. Master trainers, mainly practising teachers or TTC lecturers, facilitated all training.

Delivering five days of training to more than 34,000 teachers in five weeks was a major logistical achievement. In Term 1, timely DSA payments were made across remote areas despite limited cash liquidity, using Standard Bank’s UNAYO system. Following UNAYO’s closure in September 2025, Term 2 payments were subcontracted to UNICEF at short notice. The new and untested approach using a mobile platform caused delays, but strong MoEST coordination helped manage expectations, and training quality remained high, reflected in positive feedback.

A central achievement was extending the reform to pre‑service education. Through close collaboration between Cambridge Education, Directorate for Quality Assurance and Standards (DQAS), the Directorate for Teacher Education (DTED) and MIE, the mathematics syllabus and TTC modules were updated, ensuring the 6,000 teachers graduating annually understand foundational maths aligned with the revised Standards 1–4 curriculum.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This output changed to include a focus on pre-service teacher training, ensuring the reform is nationalised across the system. Going forward, this output will only include training of student teachers on the new syllabus and modules. All BHC-funded in-service teacher training has now concluded.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

This output faced several challenges. The shorter-than-expected contract extension with Cambridge Education, ending in March 2026 due to the organisation’s planned closure, required Terms 1 and 2 teacher trainings to be merged and delivered in December, with special MoEST approval. The sudden closure of UNAYO also put the training schedule at risk. Cambridge Education and BHC worked closely to identify workable solutions, using established networks to ensure delivery could continue.

Despite these efforts, training payments were delayed across many centres and districts, creating potential reputational risks. The experience highlights persistent difficulties with largescale mobile-money disbursement in Malawi, including the need to validate mobile numbers for over 34,000 participants and verify attendance in real time to trigger payments. Given the previous success, after multiple rounds of iteration, of using national bank agents to distribute cash, future largescale trainings should consider piloting alternative banking platforms where feasible.

With BHC funding for termly teacher training now concluded, the programme should identify ways to support nationalisation of the training reforms through Output 3. Priorities include advocating for clearly defined career pathways that recognise the roles of Master Trainer and National Trainer, and sustaining CPD feedback loops across teachers, trainers, PEAs and monitors at district, zonal and national levels. A key entry point for this is the planned CPD reform under the MFLP and ensuring the programme draws on learnings from Maziko.

Output Title	The maths reforms are institutionalised and sustained
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
There is an evidence-based way forward to sustain the mathematics reforms	Sustainability study is completed and presented to MoEST and FCDO	Achieved: The sustainability study was presented to MoEST and FCDO on 13th February.
	MoEST handover workshop conducted on PEA dashboard	Achieved: A two-week handover workshop attended by Ministry officers from the Education Management Information System (EMIS) department and Directorate of ICT was completed in December 2026.

Briefly describe the output’s activities and provide supporting narrative for the score

This output met expectations and focused on the development of a TLM sustainability study and transfer of the real-time data dashboard to the Government.

The study was developed through a consultative process with Ministry counterparts and key experts. Its purpose was to help Government and donors assess evidence and options for the future of learner workbooks. The report examined:
1. The cost-effectiveness of NMCRP’s current printing and distribution model.
2. Costed options for primary mathematics teaching and learning materials (TLMs).
3. Alternative printing and distribution approaches and their relative efficiency.
4. Potential pathways to securing public funding for TLMs, alongside priorities for strengthening MoEST budgeting, procurement, and distribution systems.
5. Evidence gaps, including missing cost-effectiveness data for alternatives to termly workbooks and gaps in data underpinning the Ministry’s TLM strategy.

As noted in the SMES PCR, the programme also developed a national Primary School and Primary Education Adviser (PEA) Dashboard for real-time data capture. PEAs collect data on attendance, materials availability, teaching quality and learner progress, and District Education Officers review the data termly. Initiated at the Ministry’s request to improve accountability, the dashboard was codesigned and scaled nationally in March 2025. Recent work has focused on promoting data use and transferring ownership to MoEST.

In November, a handover workshop prepared MoEST staff to lead production, maintenance and publication of the Power BI dashboard and to migrate data systems to government-managed platforms. Key ICT and Planning officers attended, gaining practical skills and establishing core ICT infrastructure. However, the Ministry still lacks an active website to host the dashboard. Follow-up meetings have documented roles and processes for publishing monthly dashboards, though concerns remain about the limited number of technical staff capable of sustaining these reforms if key personnel change.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no changes to this output and there are no planned changes.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

The sustainability study has strengthened the evidence base for transitioning to a more affordable model for learner workbooks, addressing a key recommendation from the SMES PCR. With FCDO and the Prevail Fund committed to financing individual workbooks through the 2028/29 academic year, MoEST now has more time to plan for long-term sustainability using domestic resources. Supporting this evidence-based transition will remain a core focus for Montrose in the coming year, alongside strengthening national capacity in planning, book procurement, storage and supply chain management.

Depending on MoEST’s progress in institutionalising the dashboard, the programme should consider additional support to embed the capacity for routine dashboard production. This includes strengthening awareness of the dashboard’s value, improving data analysis skills, and ensuring PEAs and district officials use the information to develop SMART, actionable steps that support schools and drive improved performance. It will be important to align with planned dashboard support under the MFLP and engage regularly with the World Bank and DQAS.

D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers for activities were workbooks, teacher training and workshop costs, as well as programme management costs in the form of fees.

VfM performance compared to the original VfM proposition in the business case

Compared to the original VfM proposition in the business case, VfM performance has been positive in the past year as outlined below.

Economy has remained strong over the reporting period, with major cost drivers performing within or better than Business Case expectations. Teacher training costs averaged £19.83 per teacher-day, well below the £25/day planning assumption—even after the 2024 allowance increase—showing that inflation and cost pressures were effectively absorbed without compromising quality. Printing costs for learner materials rose from the SMES benchmark of £0.16 to £0.21 per book, but this remains in line with Business Case forecasts given global increases in paper prices and logistics volatility. Staff day rates have also remained broadly consistent with Business Case assumptions. Management costs stand at 18% of total expenditure, within the anticipated 15–20% range for a national-scale reform. The £3.68 cost per child modelled in the BC has remained realistic and the programme has to date continued to procure competitively and maintain strong cost discipline despite a challenging macroeconomic environment. Upcoming procurement and distribution will likely be impacted by the oil crisis and price increases – the programme team must look at all viable options, including e.g. regional printing, to determine the best value for money.

Efficiency remains strong, with inputs converted to outputs in line with Business Case expectations. Output quality reinforces this efficiency: the quality of the books is high and has so far been evidenced as the cheapest and most impactful option. An average of 96% of teachers trained reported confidence in teaching the new curriculum, showing that training investments are translating effectively into teacher readiness.

Effectiveness is high and closely aligned with the programme’s ToC. Classroom implementation quality remains strong, with 80% of observed lessons rated effective or partially effective, demonstrating fidelity to the structured pedagogy approach. High teacher turnout at trainings despite DSA challenges shows signs of institutionalisation and increased teacher confidence suggests these gains can be sustained. These findings align with the BC’s causal evidence, including the RCT showing ~0.2 Standard Deviation gains in mathematics after one year, placing the reform among the most impactful large‑scale foundational learning programmes in LMICs. Due to ODA reductions, the impact evaluation component has been removed, which means no comparable data will be available to measure learning improvements. FCDO support to develop a national learning assessment means a new baseline will be available in July 2026, with the next assessment point two years later, funded by the MLFP.

Equity performance is positive. Women made up 51% of master trainers in Term 1, meeting the BC’s gender parity ambition. Commitments to disability inclusion, accessible materials, and reaching the poorest learners continue to guide programme design and adaptation. This year, 71,836 large-print workbooks for Standards 1–4 were printed and distributed to 534 schools (35,918 each term). Over 700 specialist teachers were trained, with specialists from the Directorate of Inclusive Education and Montfort College actively involved in training monitoring delivery as well as pre-service module development.

Cost-effectiveness remains strong based on evidence from SMES and Maziko. While SMES pilot evidence is outdated, we can expect continued improvements following teacher trainings – evidence shows that teachers are the most significant factor in determining students’ learning outcomes. However, book delivery delays for Term 2 will have had an impact on cost-effectiveness and continued cost-effectiveness will depend on: how the programme manages unit costs through future procurements, timely book delivery and continued strong instructional quality e.g. through well-functioning CPD, as BHC-funded teacher training is phased out. The focus on sustainability and institutionalisation in the coming few years will help ensure that cost-effectiveness is maintained.

Assessment of whether the programme continues to represent value for money

On the balance of evidence from the above details, the programme continues to represent good value for money and should continue.

E: RISK

Over the past year, the programme operated within a Moderate overall risk rating. The risk environment was shaped by national food insecurity, inflation, macroeconomic instability, fuel shortages and political transitions linked to national elections. These factors affected school attendance and programme stability, resulting in a Major residual Strategy & Context risk, driven mainly by humanitarian needs. BHC mitigated this through an £8m humanitarian allocation targeting poor communities, including children, as well as regular partner engagement, forecasting reviews and forward planning to manage inflation impacts.

Across Policy and Programme Delivery, residual risks remained Moderate despite significant operational pressures, including the closure of UNAYO, potential delays in procuring a new supplier, and shipping disruptions for TLMs. Mitigation included weekly procurement monitoring to support supplier transition, proactive arrangements with UNICEF to manage teacher training payments, and timely communication to teachers on how to continue instruction in the absence of materials. Key lessons include the need for earlier contingency planning, investment in digital and cash-delivery systems, and continued partner coordination.

Safeguarding and SEAH residual risk were Major but were managed to a Moderate residual level, consistent with the Cautious risk appetite. Key risks stemmed from limited partner safeguarding capacity and reluctance to report incidents during teacher training. Mitigation included comprehensive safeguarding training for FCDO and implementing partner staff, and clear reporting information displayed at all training venues.

Financial and Fiduciary risks were well-managed, with strong compliance maintained. Fraud risks—ghost participants, inflated invoices, and diversion of free workbooks—remained at Moderate residual levels, mitigated through spot checks, verification processes, cross-partner monitoring and strengthened financial controls. Transition-related risks were addressed through asset verification and development of a disposal plan. Public radio broadcasts also increased awareness of the reform and limits on TLM sales to private schools.

Reputational risks were Moderate, primarily due to delayed training payments and uncertainty linked to ODA reductions. Regular Ministry engagement, transparent communication and careful prioritisation of funds helped contain these risks.

Public Service Delivery & Operations risks improved with payment issues reduced to a Minor residual risk. While technical with FCDO’s HERA and AMP systems persist, improved forward planning and stronger escalation procedures has mitigated against this.

People risks stayed Low, aligned with the Minimal appetite. Risks related to staff morale and wellbeing, linked to FCDO strategic shifts and ODA reductions, were mitigated through a change management team, regular staff check-ins, line management oversight, access to Mental Health First Aiders and Fairness Champions, and an open-door policy to senior leadership.

Overall, the programme demonstrated strong and adaptive risk management. Despite contextual and delivery pressures, controls remained robust, mitigation was consistently applied, and all risks stayed within appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Reporting and risk management
Cambridge Education consistently delivered timely, high-quality monthly, quarterly and annual reports covering progress against workplans and log frame milestones. They submitted an updated delivery chain map and value for money matrix in November 2025 as required by contract amendment six. Key risks were escalated promptly to BHC, enabling quick action, for example, managing the UNAYO payment system closure and issues around the final contract extension. Fraud and safeguarding incidents were reported immediately to BHC and Reporting Concerns.

Financial management
By January 2026, the programme had spent £9.5m out of the £12.m ODA allocation (79%) with about 16% to be spent in Feb and March, resulting in an under‑spend of 5.0%. Monthly and quarterly financial forecasts were timely and mostly within tolerance, except for two of seven invoices. Supporting documentation was provided within three days. A 14.2% variance in February 2026 resulted from Cambridge Education’s delays in processing invoices.

Spot checks in July 2025 and February 2026 confirmed an up-to-date asset register and annual asset verification. Asset disposal plans are being finalised, with transfers to Government, Montrose, MIE and other BHC programmes. A financial audit scheduled for September 2026 will be undertaken immediately after contract closeout in March.

Delivery against contract
UNICEF performed strongly, demonstrating professionalism and efficiency in delivering training payments despite district-level data errors. As of writing, UNICEF has reported that 96% of teachers have been fully paid and are in the process of paying the remaining 1,473 teachers’ claims. Cambridge Education’s quarterly SRM scores consistently rated “Approaching Target” against three KPIs (Delivery and Support, Quality, and Financial Management) with strong financial management and milestone submissions. Communication issues on learner material quantities for teacher trainings flagged by MoEST in Q3 were addressed through improved engagement.

Late-stage shipping delays, outside Cambridge Education’s control, resulted in missed milestones and a required no-cost extension to April 2026 to complete book delivery. Mott MacDonald remained compliant with the Supply Partner Code and will submit its Annual Declaration at contract end.

Compliance with the Gender Equality Duty
Maziko ensured gender-balanced and inclusive maths materials, equitable learner access, and strong safeguarding measures during teacher training, particularly related to gender-based violence.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Throughout the review period, the programme implemented a thorough monitoring system, including routine field visits, training observations, post-training classroom monitoring, and engagement with national, district and zonal stakeholders. Regular beneficiary feedback from teachers, trainers, PEAs and learners enabled early identification of challenges and informed real-time adjustments to training delivery, logistics and support. The most recent BHC field visit took place in February 2026, covering three northern region schools and including feedback discussions with teachers, headteachers and district officials.

Teacher training monitoring was led by a multidisciplinary MoEST team comprising officers from DQAS, MIE, Directorate of Basic Education (DBE), DTED, Directorate of Science, Technology and Innovation (DSTI), Directorates of Planning, Inclusive Education and district/division offices. Their findings helped refine training strategies, adjust trainer deployment, and assess classroom fidelity and quality, while strengthening Ministry reform ownership.

PEA dashboard monitoring expanded in coverage and continued to generate monthly, disaggregated data on school and PEA performance, improving visibility and decision-making across zonal, district and national levels.

This Annual Review was prepared by the BHC programme team with support from Cambridge Education. It draws on desk-based analysis and evidence from MoEST and BHC field visits and was strengthened through peer review.

Evidence

New evidence has emerged from programme implementation during the year, with implications for future programme delivery. For example, the impact of shipping delays on teaching and learning has provided new evidence for the programme to consider when determining the most cost-effective approach to book procurement and delivery. Field visits provided anecdotal evidence showing that some PEAs and districts are not fully utilising dashboard data. Many focus on meeting required numbers of monthly school visits rather than analysing qualitative data from visits and lesson observations to guide planning and follow-up actions. Visits also revealed positive practices, such as schools and districts redistributing surplus books to manage local shortages.

Learning

Key lessons from the past year highlight the importance of agility in programme delivery and maintaining strong relationships with Government and partners to manage unforeseen challenges, including for example compressed training timelines and payment challenges.

Although the maths reform remains a MoEST priority, reduced education funding in the 2026/27 budget underscores the ongoing fiscal constraints facing the sector. These pressures pose a significant risk to full institutionalisation and long-term sustainability of the reform. In the coming year, BHC will seek to understand if and how the education budget and the Constituency Development Fund will support education and reform delivery. This learning will feed into BHC and programme advocacy and technical assistance under Output 3.

Highlights from the sustainability study into teaching and learning materials are summarised in Annex 2.

Study visits and conferences
In November 2025, MoEST officials from DQAS, MIE and DBE conducted a pre-inspection and study visit to the printing supplier in New Delhi, India. The visit provided valuable learning on managing largescale printing logistics, and the insights gathered will support MoEST’s decision-making as it considers sustainable options for future learner workbook provision.

The programme also supported the Deputy Director of DQAS to present and participate in two international conferences – one in South Africa and one in the UK. These engagements enabled Malawi to share its experiences internationally while strengthening exposure to global evidence and best practices in education.

Date of last narrative financial report	10/03/2026	Date of last audited annual statement	First audit statement report will be ready by 30/08/2026.

ANNEX 1: SMES PCR Recommendations

1. Support an evidence-based transition to a more affordable approach. This includes supporting the transition from single-use workbooks to standard textbooks that can be sustained by the Government. Continued engagement, informed by political economy analysis, will be essential to ensure the continued institutionalisation of the mathematics reform.
2. Promote sustainability through co-financing models. The Ministry of Education should be supported to blend domestic, multilateral, and philanthropic resources to maintain momentum and reduce reliance on external funding in the future.
3. Continue catalytic support for results-based systems. Strengthening governance and accountability at the district level remains critical but requires long-term commitment and engagement to embed these approaches effectively.
4. Maintain UK technical engagement in foundational learning. Even with reductions to 0.3 of ODA, the UK can continue to play a strategic role through targeted technical assistance and UK expertise. This should include remedial approaches that help students who fall behind as well as supporting a consistent approach to student assessments.
5. Explore opportunities to leverage climate finance. Malawi should seek catalytic support to access Global Climate Fund (GCF) resources to build climate resilience within the education system.
6. Strengthen national capacity for planning and delivery. Given the challenges around EMIS data accuracy and the untested capacity of national systems to lead large-scale printing and distribution, targeted technical assistance in planning, budgeting, and logistics could help ensure long-term sustainability of reforms.
7. Strengthen MoEST leadership in driving the next phase of reforms: The Ministry of Education’s leadership and day-to-day management of the primary mathematics curriculum reforms has been recognised as a key driver for its success. After a period of transition in the key implementing partners, there is a need to re-establish the accountability and management practices that ensure the reforms continue to be owned and driven by the Government of Malawi.

Annex 2: Highlights from the sustainability study

Key policy debates on TLM provision continue without evidence to validate core assumptions behind alternative delivery models. MoEST needs support to generate evidence on critical factors such as the technical specifications and costs of printing textbooks every three years, the durability of workbooks and textbooks, and the current availability of notebooks, which parents are required to supply. Because budgeting, procurement and logistics directorates have not been central to the reforms, targeted advocacy will be essential to demonstrate how TLM design influences learning outcomes and to prevent a return to less effective models.

The tables below provide an overview of the alternative options of printing regionally or locally, to avoid the risks of international shipping. It presents a mixed picture, each option with its own strengths and weaknesses:

Regional Printing (South Africa)
Advantages	Disadvantages
Cost – Large volume orders with lower unit costs than Malawi. / Unit costs inclusive of transfer of TLMs to Malawi by truck.	Cost - Higher costs than international printers (where price includes shipping) due to high margin applied by printers and higher costs of paper.
Capacity – large printing companies with industrial machines for paper cutting, printing and binding.	Distribution - Exposure to regional political insecurity and extreme weather may impact transfer of books by land and contribute to delays
Technical capacity – engineering staff with expertise to adapt machines to deliver to unique specifications to test printing innovations.	Forex – International trading requires Forex which can be difficult to raise in Malawi.
Logistical capacity – Logistics staff to manage supply chain to Malawi.	Printing sector capacity in Malawi – Printing regionally displaces large education printing orders from Malawi, with opportunity cost for development of Malawi sector capacity.
Sector capacity - Orders placed with regional printers contribute to development of regional book printing sector development
Distribution - Closer to Malawi with no risk of shipping delays impacting delivery timelines

National Printing (Malawi)
Advantages	Disadvantages
Developing Malawi printing sector - Creates demand for book printing in Malawi. Investment in printing TLMs contributes to building printing capacity in Malawi	Cost - Higher unit cost compared to international and national printers. / Printers in Malawi have periods without work, and the costs of downtime are built into the unit costs for printing orders.
Forex - Reduced Forex pressures, although still required to import paper	Capacity - Printers in Malawi do not have capacity for high volume production, or the machines required to meet the TLM specifications which drive low cost.
Supply chain management – shorter and less complex supply chain is easier to manage.	Sector capacity and competition - Very few printers in Malawi with capacity to tender for large volume print runs, which tends to drive prices up.
Logistical capacity – Logistics staff to manage supply chain to Malawi.	Technical capacity - Malawian printers do not yet have the technical expertise to produce the learner workbook with the current technical specifications. Training would be required.
Distribution – Reduced risk of transport delays impacting delivery timelines