## Annual Review Template

Title: Rights Inclusion Voice and Agency (RIVA) in Nepal
Programme Value £ (full life): £4.98m		Review date: November 2025
Programme Code: 400485	AMP start date: 19/11/2024	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400485 Documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW
Description of programme

The Rights, Inclusion, Voice and Agency (RIVA) programme (£4.98 million, 2024 – 2028) is the British Embassy Kathmandu’s (BEK) flagship investment to advance gender equality, disability and social inclusion (GEDSI) in Nepal. RIVA seeks to empower women, girls and excluded groups to understand and claim their rights individually and collectively, to participate meaningfully in inclusive policy-making and to exercise stronger voice and agency at national, provincial and local levels. The programme strengthens a diverse and intersectional ecosystem of Women’s Rights Organisations (WROs) and Civil Society Organisations (CSOs) through flexible, multi-year funding and catalytic enabling grants, while providing strategic, demand-led technical assistance (TA) to mainstream GEDSI across FCDO’s Nepal portfolio and government systems.

At its core, RIVA aims to build a more vibrant, resilient and sustainable civil-society landscape that reflects the lived realities of the most marginalised and contributes to a stronger social contract, stability and democratic resilience. Through locally-led partnerships, the programme supports collectivisation, peer-to-peer learning, and feminist movement-building across BEK’s three priority provinces - Madhesh, Lumbini and Karnali. RIVA will provide strategic demand-led TA to mainstream GEDSI effectively across BEK’s portfolio and implementing partners. In addition, targeted TA will strengthen the enabling environment for inclusive governance and accountability by equipping local governments and civil-society actors with the tools, evidence and alliances needed to address discriminatory norms and implement GEDSI-transformative policies and laws.

RIVA will deliver on the UK’s Indo-Pacific and Women and Girls Strategies, the Disability Inclusion and Rights Strategy (2022-2030) and BEK’s GEDSI Strategy and Action Plan (2024-2027). It directly contributes to Sustainable Development Goals 1 (No Poverty), 5 (Gender Equality) and 10 (Reduced Inequalities) by shifting power and resources to local actors and amplifying the voices of women and excluded groups. The programme embodies FCDO’s local localisation and “leave no one behind” principles - placing local leadership, equitable partnerships and inclusive governance at the heart of the UK’s full spectrum development cooperation in Nepal.

Summary supporting narrative for the overall score in this review

RIVA has performed strongly during its first year, meeting expectations and laying the foundations for transformative impact on GEDSI and local leadership in Nepal. Despite operating in a complex political and fiscal context - marked by the 0.3% FCDO ODA announcement, delays in signing the SDDirect/Plan International contract, and civic unrest following the “Gen Z” protests - the programme has demonstrated exceptional adaptability and resilience.
Across both delivery partners, RIVA has achieved significant progress. UN Women’s Hamro Sahas ‘Our Courage’ programme successfully transitioned from inception to implementation in March 2025, disbursing grants to 26 diverse WROs and establishing a feminist Community of Practice (COP) across Karnali, Lumbini and Madhesh. In parallel, through a competitive procurement process SDDirect/Plan were successfully contracted in June 25 and are on track to complete inception deliverables by end of Dec - including finalising the RIVA Theory of Change, developing the Grant and Technical Assistance Facility designs, and establishing the Programme and GEDSI Advisory Boards. The decision to bring RIVA under the Samartha MoU enabled government engagement to continue, ensuring delivery momentum and compliance with national frameworks. These achievements reflect strong partnership management, local leadership and alignment with BEK’s GEDSI Strategy and Action Plan (2024–27) and updated portfolio approach under Lens A.
RIVA remains firmly on track to achieve its intended outcomes. It is already catalysing more inclusive local governance, strengthening feminist movement-building and strengthening GEDSI across BEKs portfolio. The programme continues to represent strong value for money, delivering credible early results, demonstrating adaptive management and reinforcing the UK’s commitment to local leadership, inclusion and resilient full spectrum development partnerships in Nepal.
Major lessons and recommendations for the year ahead

The first year of UNW Hamro Sahas has provided valuable lessons on effective approaches to feminist movement-building and partnership strengthening in Nepal’s complex governance environment. These include:
- Flexible, multi-year funding is critical for WROs. It enables smaller, grassroots and intersectional organisations to plan strategically, retain staff and sustain their activism beyond short-term project cycles. This predictability has supported WROs to move from ad hoc activism toward more structured engagement with local governments and national frameworks.
- Investment in collective feminist identity and care has been central to programme cohesion. Activities such as the national induction workshop and the CoP have fostered solidarity, shared learning and mutual accountability among WROs, helping mitigate burnout and strengthen collective resilience.
- Targeted outreach and simplified access to funding proved highly effective in reaching new and diverse WROs. Pre-bid orientations, simplified proposal formats and inclusive communication, leveraging multiple communication channels helped ensure strong participation from first-time applicants, including Dalit, Indigenous, LGBT+, Muslim and young feminist groups.
- Risk-based capacity assessments have been a useful diagnostic tool, allowing UN Women to tailor technical and compliance support to partner capacity levels and build financial literacy, safeguarding and reporting skills while ensuring proportional accountability measures.
- Adaptive delivery and safeguarding emerged as critical lessons amid civic unrest and misinformation. HS demonstrated agility by shifting to virtual engagement, strengthening “do-no-harm” approaches, and embedding care and security planning across partner support mechanisms.
- Local government engagement showed strong potential during the inception phase but highlighted the need for structured collaboration and clear pathways for policy uptake at municipal level.

Under the SDDirect/Plan TA/ Grants Facility component the inception phase underscored the importance of flexibility and partnership coherence in complex political and fiscal environments. For example:
- Adaptive management and close coordination with BEK were critical in maintaining delivery momentum amid delays to contract signing, uncertainty around the Government of Nepal MoU and political unrest following the Gen Z protests. The consortium’s proactive engagement and alignment under the Samartha MoU enabled progress while ensuring compliance and robust risk management.
- Joint governance and collaboration through the newly established RIVA Programme Board strengthened accountability and coherence between FCDO, SDDirect/Plan International, supporting timely decision-making and enabling a shared understanding of priorities in a shifting ODA landscape.
- Contextual sensitivity and safeguarding considerations proved vital in ensuring that research and engagement activities (such as the Gender Inclusion Power and Politics GIPP analysis) could proceed safely and ethically during periods of instability.

Building on these lessons, the following recommendations aim to enhance programme effectiveness, deepen partnerships and sustain adaptive delivery through the next year:

Hamro Sahas
1. Ensure the HS COP remains dynamic and responsive, focusing on emerging issues such as online safety, self-care and resilience-building, while continuing to strengthen solidarity and collaboration among WROs. [Responsible: UNW HS team | Timeframe: Ongoing]
2. Under Component 3, prioritise sustained local government engagement and adaptive planning amid civic unrest. Strengthening WRO - LGU linkages will be vital for advancing accountability and embedding gender-responsive local governance. Ensure strong linkages with Provincial and Local Governance Support Programme (PLGSP), BEKs other Governance initiatives and identify ways for RIVA SDD/Plan TA Facility to support HS identified LG [Responsible: UNW HS team, BEK RIVA team | Timeframe: Q3 2025 / Q4 2026 - Ongoing]
3. Establish robust MEL systems and ensure timely baseline data collection to enable impact tracking, disaggregated data analysis (age, sex, disability, geography) to support credible impact tracking and evidence-based adaptation. [Responsible: UNW HS team | Timeframe: Q3 2025 - ongoing]
4. Continue to identify and foster synergies with wider BEK programming - notably the Security and Justice Programme (SJP), Gender Based Violence (GBV) components, Samartha, EDIT, RAIN and previous UK support under PLGSP – to ensure complementarity and maximise returns on FCDO’s investments. [Responsible: UNW HS team and BEK RIVA team | Timeframe: Ongoing]
5. Continue to monitor Nepal’s evolving political context and undertake regular scenario planning to ensure activities are sequenced safely. The hosting of public events should be timed to avoid potential risks to WROs and mitigate reputational risks to BEK. [Responsible: UNW HS and BEK RIVA team and | Timeframe: Ongoing]
6. Prioritise meaningful engagement of diverse youth (including from the Gen Z movement) across social, ethnic and geographic backgrounds. Create inclusive, youth-led spaces and platforms that amplify their voices and perspectives and integrate intergenerational learning within HS activities. This should include the use of digital tools and social media to connect with emerging youth movements and enhance outreach and visibility. [Responsible: UN Women Hamro Sahas team and BEK RIVA team | Timeframe: Q3 2025–Q2 2026]

SDDirect / Plan International
Operationalise the TA Facility and pilot initial TA requests within the inception phase and early in 2026, while finalising the ToC, logframe, and associated performance indicators to guide results delivery. Early piloting will help test systems, refine processes and demonstrate tangible support to BEK and implementing partners. [Responsible: SDDirect/Plan and BEK RIVA Team | Timeframe: Q3 2025 - Q4 2026]
Leverage learning from UNW HS and other BEK existing and previous programmes (e.g. SJP, Samartha, EDIT, RAIN and PLGSP) to strengthen grant management systems, enhance local partnerships and promote coherence across BEK’s wider GEDSI portfolio. This includes harmonising approaches to safeguarding, social norm change and inclusive local governance. [Responsible: SDDirect/Plan and BEK RIVA Team | Timeframe: Ongoing]
Continue to monitor Nepal’s evolving political and civic context and undertake regular scenario planning to anticipate risks associated with elections, civic movements or changes in government policy. Launch the RIVA Grant Facility only when conditions are conducive to safe and effective delivery, ensuring that timing avoids risks of doing harm to CSOs or potential reputational risks to BEK. Scenario planning should include consultation with CSOs, provincial partners and the RIVA Programme Board to inform adaptive decision-making. [Responsible: SDDirect/Plan and BEK RIVA team | Timeframe: Ongoing]
Define and strengthen RIVA’s role in supporting GEDSI-related TA at local government level, particularly in provinces and municipalities where HS and other BEK programmes are operating. This should include coordination with the Provincial Engagement Facility (PEF), Provincial Training Academy (PTA) identification of high-potential local governments for TA support, and integration of inclusion-focused TA into local planning and governance systems. This will ensure RIVA contributes directly to more inclusive, accountable and gender-responsive governance outcomes across the portfolio. [Responsible: SDDirect/Plan, BEK and PEF | Timeframe: Q3 2025 – Q4 2026]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

At the impact level RIVA will contribute to: A diverse, vibrant, and sustainable civil society that promotes the needs and lived realities of the most excluded and strengthens the social contract, resilience, and stability in Nepal.

At the outcome level RIVA will contribute to: Women, girls, and excluded groups in Nepal are empowered to understand and claim their Rights individually and collectively, participate in Inclusive policy-making and implementation, and have a stronger Voice and Agency at both national and local levels to advance GEDSI.

The intended immediate outcomes of this programme are:
1. The WRO/CSO ecosystem becomes more vibrant and sustainable with increased funding opportunities and enhanced organisational capacity.
2. WROs / CSOs become more inclusive, responsive and better able to advocate for women's and marginalised people's rights through improved collaboration and networking between movements.
3. Resources and decision-making power are shifted to local communities, allowing them to set priorities and deliver effective solutions to advance GEDSI in their local context.
4. GEDSI transformative policies, laws, and legislation that protect and advance the rights of women, girls, and excluded groups are implemented, maintained, and enforced, with better-targeted spending at local, provincial, and national levels.
5. Discriminatory attitudes, behaviours, and social norms are transformed in communities where WROs/CSOs operate, valuing women, girls, and vulnerable groups as equal members and recognising them as decision-makers and leaders.
6. GEDSI is effectively integrated across BEK's portfolio, identifying opportunities to expand UK work on GEDSI by amplifying diverse voices in Nepal and incorporating these realities into programming and diplomatic efforts.

Evidence on how the RIVA components have delivered against the ToC

The UNW HS contribution to the ToC is premised on the belief that if diverse feminist movements in Nepal are adequately resourced, networked and recognised by government institutions, they can challenge discriminatory social norms and influence policy and governance. Initial implementation progress demonstrates that the pathways to impact remain valid. Key assumptions - such as the willingness of local governments to engage with WROs - have held true in early phases. The establishment of the COP and risk-based capacity assessments for all partners have been major milestones.

During inception, under the GEDSI TA and Grants Facility components delivered by SDDirect/Plan, progress has been made on several enabling conditions including: building internal structures, co-designing with BEK on TA delivery, and creating mechanisms to mainstream GEDSI across BEK’s portfolio. The programme’s participatory approach has fostered ownership and early alignment between partners. The establishment of a RIVA Programme Board, GEDSI Advisory Board concept, and draft MERL framework mark key steps. While no outcomes were expected at this stage, the programme is on track to deliver its first technical outputs by the end of the inception period in Dec 2025.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The RIVA ToC continues to hold true and remains a sound framework for guiding delivery and measuring progress. The central logic that strengthening a diverse, vibrant, and sustainable civil society enables women, girls, and excluded groups to claim their rights, participate in inclusive governance, and drive transformative social change, has been validated through both inception and implementation period to date.

The programme is already contributing to its intended outcomes: the WRO/CSO ecosystem has become more vibrant through flexible funding and capacity-building under UN Women’s Hamro Sahas component and collaboration and networking between feminist movements are deepening through the emerging COP. These achievements demonstrate early progress towards transforming discriminatory social norms.

Furthermore, RIVA’s integrated approach - linking movement-building, technical assistance, and portfolio-wide mainstreaming - has already started to strengthened coherence across BEK’s programmes and ensured that GEDSI is effectively incorporated into broader UK engagement in Nepal. As such, the programme continues to deliver against its ToC, contributing meaningfully to a more inclusive, equitable, and resilient Nepal.

As part of inception phase the SDD/Plan MERL Lead had designed a participatory workshop with a number of external stakeholders and the UNW Hamro Sahas team to review and finalise the RIVA programme’s ToC. The workshop was originally scheduled for 12th September but was postponed due to the Gen Z protests. The workshop will now take place in late November. Following this the MERL Lead with the BEK RIVA team will draft a revised ToC, logframe, incorporating UNW Hamro Sahas components, and commence work on the MERL Strategy.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The RIVA programme should continue on its own merit and as a central pillar of BEK’s inclusion and governance portfolio. Evidence from both components demonstrates clear delivery against the ToC and continued relevance to the UK’s strategic priorities in Nepal. UN Women’s Hamro Sahas has validated the programme’s core assumption that adequately resourced and networked feminist movements can influence policy, challenge discriminatory norms, and drive inclusive local governance. Early results, including the establishment of 26 diverse WRO partnerships, the creation of a feminist COP, and constructive engagement with 46 municipalities, show that pathways to impact are working as intended.

Under the TA and Grants Facility, SDDirect and Plan have built strong foundations through the Programme Board, GEDSI Advisory Board, and participatory MERL framework, while embedding GEDSI across BEK’s portfolio. The integrated design ensures coherence between local movement-building and upstream policy influence, amplifying the UK’s diplomatic and programmatic impact.

Crucially, RIVA continues to demonstrate strong value for money through efficient delivery, adaptive management, and a locally led model that maximises returns on investment. By leveraging existing delivery mechanisms (such as the Samartha MoU), streamlining management costs, and embedding GEDSI expertise across multiple programmes, RIVA delivers high impact relative to cost. The programme’s combination of targeted catalytic grants, shared technical assistance, and feminist partnerships represents an efficient and equitable model for achieving transformational outcomes. Given its strategic relevance, proven delivery capacity, and cost-effectiveness, RIVA merits continuation as a flagship inclusion and governance investment within FCDO’s Nepal portfolio.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	UNW HS – Strengthening WROs’ financial and organisational capacity, driving social norms change, fostering feminist networks and movement-building, and enhancing engagement with local governments.
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 WROs selected and funded, capacity strengthened and communities reporting improved awareness.	WROs selected and onboarded. Risk-based capacity assessments completed. WROs implementing social-norm-change initiatives.	Met. 26 WROs (Dalit, Indigenous, Muslim, LGBT+, youth and disability-led) received multi-year flexible grants. All completed capacity assessments and tailored institutional strengthening plans. Over 4,000 people reached through community dialogues, contributing to visible shifts in gender norms. 15 WROs established new governance and safeguarding policies, strengthening accountability and sustainability.
1.2 Networks of WROs are strengthened through CoP and collaborative efforts that foster intersectional movement-building.	CoP co-designed and launched. Sessions convened with WROs. CoP priorities and vision identified and endorsed.	Met. The CoP launched with two further inclusive sessions involving 22 WROs. Members agreed shared priorities on feminist leadership, tackling harmful norms and resilience. Sessions adapted to address online safety and civic activism risks, helping build solidarity and collective learning among diverse WROs.
1.3 Local governments in BEK priority provinces have strengthened their capacity to engage with WROs and promote gender-responsive governance.	Municipalities identified and engaged. Baseline and needs assessments initiated. Three municipalities piloting inclusive mechanisms.	Partially Met. 46 municipalities engaged through coordination meetings with UNW. Baseline assessment underway to inform collaboration plans. Three municipalities (Lekbeshi, Barahatal, Birendranagar) initiated inclusive data and protection systems. Early engagement has created entry points for future GEDSI TA and policy influence at local level.

Briefly describe the output’s activities and provide supporting narrative for the score.

The HS programme, co-created by UNW and BEK under RIVA, has successfully moved from inception into implementation and remains on track to deliver against its objectives. Despite the volatile political environment following the Gen Z protests and delays in local government engagement, the programme has continued to demonstrate strong delivery, effective partnership management and tangible early results. Progress to date substantiates an A rating, meeting or exceeding milestones across the first two result areas and being partially meet under indictor 3.
1.1 – Strengthening Financial and Organisational Capacity of WROs and Social Norms Change
Under this output, 26 WROs - including Dalit, Indigenous, Madhesi, Muslim, LGBT+, and disability-led partners - were selected and onboarded through an inclusive, competitive feminist process. UNW worked with all partners to carry out risk-based capacity assessments and developed tailored strengthening plans. Over 4,000 people participated in dialogues, awareness campaigns and community sessions that contributed to measurable shifts in harmful practices such as Chhaupadi. Fifteen WROs have adopted new internal policies on safeguarding, human resources and financial governance, while others enhanced referral systems for survivors of GBV through the Hamro Sahas Ghar safe-space model. The combination of flexible funding and capacity support has created a strong foundation for sustainable, intersectional feminist leadership. The output is fully on track.
1.2 – Feminist Networks and Movement-Building
The CoP has been established as a flagship achievement of the programme, operationalising a safe and inter-generational platform for collaboration amongst the 26 WROs. Through co-design, members agreed on three thematic priorities: tackling discriminatory norms, strengthening feminist leadership, and building resilience and collective care. CoP sessions were adapted to address misinformation, online safety and trauma in the wake of civic unrest - demonstrating agile programming and responsiveness to the Nepal context. The CoP has begun to generate a cohesive feminist identity and stronger peer learning across provinces, enhancing the sustainability and influence of Nepal’s feminist movement. This output is on track, showing innovation, strong ownership and high relevance.
1.3 – Engagement with Local Governments
UNW has advanced groundwork for sustained collaboration with 46 municipalities across, Lumbini, Madhesh and Karnali. While some activities were delayed due to political instability and the ongoing needs assessment, tangible progress is evident. Three municipalities (Lekbeshi, Barahatal, and Birendranagar) initiated inclusive mechanisms such as Protection Information Management Systems and a Single Women Protection Fund, while others pledged to embed disability-inclusive measures within GBV responses. These achievements demonstrate growing local ownership and practical entry points for future GEDSI TA. The output is assessed as partially met but on course, with adaptive planning mitigating contextual risks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, the HS remained substantively unchanged, but delivery modalities were adapted to respond to Nepal’s evolving political and civic context. The nationwide protests and periods of unrest in Sept 2025 temporarily limited access to some municipalities and partners. UNW responded swiftly by shifting engagement to virtual platforms, sequencing activities to prioritise partner safety, and integrating enhanced do-no-harm, security and collective-care measures across all activities. These adaptations ensured programme continuity while safeguarding WROs and maintaining momentum on movement-building and capacity-strengthening activities.
Implementation timelines under Output 1.3 - local government engagement, were extended to allow for completion of baseline assessments and more meaningful collaboration with municipalities once conditions stabilised. Adjustments were also made to the CoP under Output 1.2, incorporating new focus areas on online safety, resilience and misinformation in response to emerging risks for women activists and human rights defenders.
Looking ahead, no structural changes to the outputs are proposed, but the programme will continue to apply adaptive management and scenario planning to navigate Nepal’s dynamic political landscape. Planned actions include completing the local governance baseline by the end of 2025, launching capacity-building support for select municipalities in early 2026, and further consolidating the CoP as a long-term learning and care platform. These refinements will ensure the programme remains relevant, safe and responsive while continuing to deliver against the ToC.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The first year of UNW Hamro Sahas has provided valuable lessons on effective approaches to feminist movement-building and partnership strengthening in Nepal’s complex governance environment. These include:
- Flexible, multi-year funding is critical for WROs. It enables smaller, grassroots and intersectional organisations to plan strategically, retain staff and sustain their activism beyond short-term project cycles. This predictability has supported WROs to move from ad hoc activism toward more structured engagement with local governments and national frameworks.
- Investment in collective feminist identity and care has been central to programme cohesion. Activities such as the national induction workshop and the CoP have fostered solidarity, shared learning and mutual accountability among WROs, helping mitigate burnout and strengthen collective resilience.
- Targeted outreach and simplified access to funding proved highly effective in reaching new and diverse WROs. Pre-bid orientations, simplified proposal formats and inclusive communication, leveraging multiple communication channels helped ensure strong participation from first-time applicants, including Dalit, Indigenous, LGBT+, Muslim and young feminist groups.
- Risk-based capacity assessments have been a useful diagnostic tool, allowing UN Women to tailor technical and compliance support to partner capacity levels and build financial literacy, safeguarding and reporting skills while ensuring proportional accountability measures.
- Adaptive delivery and safeguarding emerged as critical lessons amid civic unrest and misinformation. HS demonstrated agility by shifting to virtual engagement, strengthening “do-no-harm” approaches, and embedding care and security planning across partner support mechanisms.
- Local government engagement showed strong potential during the inception phase but highlighted the need for structured collaboration and clear pathways for policy uptake at municipal level.

Recommendations

1. Ensure the HS COP remains dynamic and responsive, focusing on emerging issues such as online safety, self-care and resilience-building, while continuing to strengthen solidarity and collaboration among WROs. [Responsible: UNW HS team | Timeframe: Ongoing]
2. Under Component 3, prioritise sustained local government engagement and adaptive planning amid civic unrest. Strengthening WRO - LGU linkages will be vital for advancing accountability and embedding gender-responsive local governance. Ensure strong linkages with Provincial and Local Governance Support Programme (PLGSP), BEKs other Governance initiatives and identify ways for RIVA SDD/Plan TA Facility to support HS identified LG [Responsible: UNW HS team, BEK RIVA team | Timeframe: Q3 2025 / Q4 2026 - Ongoing]
3. Establish robust MEL systems and ensure timely baseline data collection to enable impact tracking, disaggregated data analysis (age, sex, disability, geography) to support credible impact tracking and evidence-based adaptation. [Responsible: UNW HS team | Timeframe: Q3 2025 - ongoing]
4. Continue to identify and foster synergies with wider BEK programming - notably the Security and Justice Programme (SJP), Gender Based Violence (GBV) components, Samartha, EDIT, RAIN and previous UK support under PLGSP – to ensure complementarity and maximise returns on FCDO’s investments. [Responsible: UNW HS team and BEK RIVA team | Timeframe: Ongoing]
5. Continue to monitor Nepal’s evolving political context and undertake regular scenario planning to ensure activities are sequenced safely. The hosting of public events should be timed to avoid potential risks to WROs and mitigate reputational risks to BEK. [Responsible: UNW HS and BEK RIVA team and | Timeframe: Ongoing]
6. Prioritise meaningful engagement of diverse youth (including from the Gen Z movement) across social, ethnic and geographic backgrounds. Create inclusive, youth-led spaces and platforms that amplify their voices and perspectives and integrate intergenerational learning within HS activities. This should include the use of digital tools and social media to connect with emerging youth movements and enhance outreach and visibility. [Responsible: UN Women Hamro Sahas team and BEK RIVA team | Timeframe: Q3 2025–Q2 2026]

Output Title	Procurement phase completed, with service provider contract signed and delivering against the first four months of the inception phase
Output number:		2	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Tender documents developed and signed off at appropriate levels	Early market engagement (EME) event held, and tender operationalised.	Met. EME was held mid-October 2024 and tender was commissioned in December 2024.
Preferred bidder identified through competitive process	Bids from interested potential contractors received and evaluated, leading to selection of implementation contractor SDD/ Plan International.	Met. Five bids were received from interested contractors and evaluated in January 2023 which led to the selection of SDD/Plan International.
Preferred bidder contracted and mobilised	Implementation contractor approved, contract signed with contractor mobilised and commence of inception phase.	Met. Implementation contractor was approved and contract signed in June 2025 following the 0.3% FCDO announcement and a pause in signing new contracts.
Inception phase milestone delivery	Successful bidder SDD/Plan International delivers against key milestones under first four months of the inception period.	Met. SDDirect/Plan International successfully onboarded the core team, established the RIVA programme board, regularly met with FCDO RIVA team, drafted the concept note for BEK GEDSI Advisory Board, TA Menu, delivered the first TA work for BEK.

Briefly describe the output’s activities and provide supporting narrative for the score.

During the reporting period, the RIVA TA and Grant Facility, implemented by SDDirect and Plan International Nepal, successfully transitioned from procurement to inception. The procurement process was completed with full competitive oversight - an EME was held in October 2024, five high-quality bids were evaluated in January 2025, and the consortium was approved and contracted in June 2025 following the temporary pause on new agreements under the 0.3% ODA announcement.
Mobilisation was swift and effective. Within weeks of contract signing, the consortium onboarded the core team, established the RIVA Programme Board, and initiated inception activities. Key milestones included:
- GEDSI Advisory Board: Concept note developed and approved by BEK, establishing a platform to guide inclusive policy and programme delivery.
- GIPP Analysis Toolkit: Comprehensive toolkit designed to inform context-sensitive and iterative analysis across the portfolio.
- Safeguarding and Equitable Partnership Frameworks: Draft frameworks produced to ensure TA and grant activities uphold FCDO’s values of inclusion, safety and respect.
- TA Facility and Grants Facility: A simplified TA menu was shared with BEK, with the first TA request commissioned to support BEK’s inclusion narrative. The Grant Facility manual was also drafted and adapted to the 0.3% ODA context, focusing on shorter-term, smaller-scale grants for grassroots organisations while maintaining emphasis on locally led, inclusive delivery.
Strong coordination with BEK was maintained through regular meetings and joint governance via the Programme Board, ensuring strategic alignment and timely issue resolution. Despite the disruption of the Gen Z protests, the team demonstrated agility and effective risk management. Preparatory work for the ToC and stakeholder consultations were completed, with the workshop now scheduled for late 2025.
Delivered in a complex context marked by shifting budgets and political unrest, the inception phase achieved all planned milestones - procurement, contracting, mobilisation, and early deliverables - while maintaining high-quality coordination and responsiveness. This output fully met expectations for the inception period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A key change during the reporting period was the decision to review and adjust the timeframe for launching the RIVA Grant Facility. This followed a rapidly evolving political context, including civic unrest linked to the Gen Z protests and the announcement of national and local elections for March 2026. To safeguard neutrality and manage reputational and operational risks, BEK, SDDirect / Plan jointly agreed to defer the formal launch of the grants facility until early 2026, once the political environment stabilises.

In the interim, the consortium has focused on completing the Grants Manual, refining the design of the facility and mapping potential grassroots partners, particularly women’s rights, youth and disability-led organisations. The adjusted timeframe allows the programme to preserve its integrity and ensure that grants are launched in a safe, transparent and politically neutral manner, while maintaining progress through preparatory design and targeted technical assistance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons Learned
Under the SDDirect/Plan International TA and Grants Facility component, the inception phase underscored the importance of flexibility, communication and partnership coherence in navigating complex political and fiscal environments. For example:
- Adaptive management and close coordination with BEK were critical in maintaining delivery momentum amid delays to contract signing and political unrest following the Gen Z protests. The consortium’s proactive engagement and alignment under the Samartha MoU enabled progress while ensuring compliance and robust risk management.
- Joint governance and collaboration through the newly established RIVA Programme Board strengthened accountability and coherence between FCDO, SDDirect/Plan International, supporting timely decision-making and enabling a shared understanding of priorities in a shifting ODA landscape.
- Contextual sensitivity and safeguarding considerations proved vital in ensuring that research and engagement activities (such as the GIPP analysis) could proceed safely and ethically during periods of instability.

Recommendations

Operationalise the TA Facility and pilot initial TA requests within the inception phase and early in 2026, while finalising the ToC, logframe, and associated performance indicators to guide results delivery. Early piloting will help test systems, refine processes and demonstrate tangible support to BEK and implementing partners. [Responsible: SDDirect/Plan and BEK RIVA Team| Timeframe: Q3 2025 - Q4 2026]
Leverage learning from UNW Hamro Sahas and other BEK existing and previous programmes (e.g. SJP, Samartha, RAIN and PLGSP) to strengthen grant management systems, enhance local partnerships and promote coherence across BEK’s wider GEDSI portfolio. This includes harmonising approaches to safeguarding, social norm change and inclusive local governance. [Responsible: SDDirect/Plan and BEK RIVA Team | Timeframe: Ongoing]
Continue to monitor Nepal’s evolving political and civic context and undertake regular scenario planning to anticipate risks associated with elections, civic movements or changes in government policy. Launch the RIVA Grant Facility only when conditions are conducive to safe and effective delivery, ensuring that timing avoids risks of doing harm to CSOs or potential reputational risks to BEK. Scenario planning should include consultation with CSOs, provincial partners and the RIVA Programme Board to inform adaptive decision-making. [Responsible: SDDirect/Plan and BEK RIVA team | Timeframe: Ongoing]
Define and strengthen RIVA’s role in supporting GEDSI-related TA at local government level, particularly in provinces and municipalities where Hamro Sahas and other BEK programmes are operating. This should include coordination with the Provincial Engagement Facility (PEF), identification of high-potential local governments for TA support, and integration of inclusion-focused TA into local planning and governance systems. This will ensure RIVA contributes directly to more inclusive, accountable and gender-responsive governance outcomes across the portfolio [Responsible: SDDirect/Plan, BEK and PEF | Timeframe: Q3 2025 – Q4 2026]
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

The main cost drivers for RIVA as a whole remain staffing, downstream partner management and capacity building, grant disbursements to WROs and delivery of TA. During the inception period, partners managed these inputs efficiently, maintaining delivery momentum despite contextual and fiscal challenges. The 0.3% ODA adjustment and delayed SDDirect/Plan contracting required careful re-profiling of budgets. However, strong financial management by partners and BEK RIVA team ensured inception deliverables remained on track and within budget. Travel, consultancy costs were kept within planned limits and remote engagement and joint field visits, reflecting good VFM and adaptive management. The emphasis to locally led TA reduces overall administrative burden while maintaining delivery reach and equity outcomes.
VfM performance compared to the original VfM proposition in the business case

RIVA continues to perform strongly against the VfM proposition outlined in the Business Case. Collectively, these efficiencies and cost-management measures have safeguarded programme performance while maintaining inclusivity and quality.
Under the FCDO’s 4E framework:
- Economy: Procurement and contracting processes achieved good value through competitive tendering (for the SDDirect/Plan consortium) and efficient use of UNW structures.
- Efficiency: UNW existing partnerships with LGs and local stakeholders in the three provinces has helped enhance efficiency and synergies under the programme. For example, UNW previous work in the selected provinces, lessons learned, and best practices has been utilised to ensure efficiency of results.
- Effectiveness: Both partners have achieved key milestones - including partner selection, TA and progress on grant facility design, and early implementation under Hamro Sahas - demonstrating a strong trajectory towards outcomes. The UNW Hamro Sahas the organisational capacity of the WRO’s is being measured (at the beginning and end of programme) and monitored and a plan is being developed to strengthen the capacities ON internal management and control for effective and efficient delivery.
- Equity: The programme continues to prioritise women, girls, and excluded groups, ensuring resources and decision-making power are shifted to local actors. 70% of direct grants under Hamro Sahas support organisations led by Dalit, Indigenous, LGBTIQ+ or youth feminists.

Assessment of whether the programme continues to represent value for money

RIVA continues to represent strong value for money within BEK’s portfolio. Evidence from the inception and early implementation phases confirms that the programme’s ToC remains valid, with clear results emerging on feminist movement-building, inclusive governance and GEDSI mainstreaming across BEK’s wider portfolio.

Given its strong alignment with the UK’s Women and Girls Strategy, Disability Inclusion and Rights Strategy, and FCDO’s whole of society and local leadership priorities, RIVA continues to deliver high strategic and developmental returns for its investment. The programme remains financially sound, operationally efficient, and contextually relevant. It therefore continues to represent good value for money and should be maintained as a flagship inclusion investment within BEKs Nepal portfolio.

E: RISK [½ to 1 page]

Overview of risk management

Risk management under RIVA has remained active, proportionate and responsive to Nepal’s evolving political and civic context. The programme operates within a medium risk appetite, recognising the complexity of working through local civil society partners in a rapidly changing environment. Risk registers are separately maintained by delivery partners (UNW, SDDirect/Plan) and the BEK RIVA team and are reviewed and updated on a monthly basis, alongside quarterly reporting and Programme Board meetings. This routine review process ensures that contextual, fiduciary, safeguarding, and programmatic risks are continually monitored, re-rated and mitigated through early action.

Over the past year, risk exposure has been shaped primarily by three drivers: (i) the fluid political environment following civic protests and government reshuffles in Sept 2025; (ii) the 0.3% FCDO ODA adjustment; and (iii) heightened sensitivity around civic space and digital activism following the “Gen Z” protests and the post-revolution environment. In response, the programme has placed greater emphasis on security and “do no harm” measures for WROs supported under Hamro Sahas, including contextual risk assessments prior to field activities, strengthened incident-reporting mechanisms, and explicit inclusion of partner safeguarding and security provisions. If these risks increase partners will also adopt an adaptive field engagement model, using remote consultation and local intermediaries where direct engagement might increase exposure to harm.

Assurance against safeguarding risks - including Sexual Exploitation, Abuse and Harassment (SEAH) and child safeguarding remains high. Both implementing partners have comprehensive safeguarding policies and have refreshed training for staff and grantees. Gender Equality Duty and Public Sector Equality Duty commitments continue to be upheld. The programme also maintains a low climate and environmental risk profile, consistent with Paris Agreement alignment; all activities have minimal emissions footprints and integrate environmental awareness into TA and grants guidance where relevant.

Due diligence assessments for UNW, SDDirect/Plan remain valid, with no significant red-flag risks identified. Follow-up on previous mitigation actions - particularly around sub-grantee management, financial compliance and safeguarding - has been completed and verified. Based on partner performance and responsive mitigation, RIVA continues to operate within FCDO’s corporate risk appetite, with strengthened oversight and learning mechanisms in place. Looking ahead, the RIVA team will maintain monthly risk review cycles, continue enhanced monitoring of WRO safety and civic-space dynamics.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Both delivery partners - UNW and the SDDirect/Plan consortium - have performed strongly against agreed financial and commercial expectations during the reporting period. UNW has maintained sound fiduciary controls and transparent financial management systems, ensuring timely grant disbursement to 26 WROs under Hamro Sahas and effective oversight of partner expenditures. Financial reporting and compliance as met FCDO requirements.

Moreover, UNW organised workshops for their 26 downstream partners to strengthen their knowledge in results-based management (RBM), financial management, gender-sensitive communication, safeguarding against Physical Sexual Exploitation and Abuse. The six-monthly report noted that pre- and post-training assessments revealed a 78% improvement in RBM understanding and an 84% increase in financial management knowledge.

SDDirect/Plan have likewise delivered effectively against their inception-phase Key Performance Indicators (KPIs), achieving contractual milestones on time and within budget, including establishment of core programme structures, development of key deliverables, and submission of financial and risk management documentation. The consortium has demonstrated prudent budget management, adapting swiftly to the political context if Nepal and realigning workplans and resources without compromising delivery quality.

BEK conducts regular monthly meetings with UNW and SDDirect/Plan, who consistently demonstrate responsiveness to our queries and requests. Out of the total programme value of £4.98m for RIVA £790,136 has been spent to date. The table below shows the cumulative spend under the RIVA components.

Component	Implementing Partner	Budget	Spent to date	Balance
Hamro Sahas (Component 1)	UN Women	£2.6m	£635,542	£1.97m
Programme funded Post (Component 2)	N/A	£0.38m	£87,026	£0.29m
TA support for RIVA (Component 3)	SD Direct/Plan	£1.99m	£67,568	£1.93m
Total		£4.98m	£790,136	£4.18m

BEKs oversight and programme management have remained strong, with active commercial engagement, regular financial reviews, and collaborative problem-solving to maintain delivery momentum. No major fiduciary or compliance issues were identified during the period, and all partners continue to meet FCDO standards of financial integrity, VFM and contractual performance.

Programme funded asset list have been updated bi-annually and are being maintained appropriately. UNW HS programme has acquired 15 IT equipment items through FCDO’s Portfolio Monitoring, Evaluation and Learning (PMEL) programme. These assets have been duly recorded in the Hamro Sahas asset register.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

M&E under RIVA has been systematic and participatory, ensuring that programme learning and accountability remain central to delivery. During the reporting period UN Women undertook regular monitoring activities, including quarterly progress reviews, virtual coordination meetings, and joint reflection sessions with the RIVA BEK team. Monthly risk and performance reviews have been institutionalised across partners, allowing early identification of delivery issues and responsive adaptation. Field visits were conducted by UN Women to all three target provinces, and by the RIVA BEK team to Karnali and Lumbini Provinces to meet WROs and the communities they serve, observe inception activities, and gather beneficiary feedback on funding access, COP, engagement with Nepal’s Local Government and safety situation following the recent protests.

Under SDDirect/Plan monitoring information has directly informed programming decisions, including the sequencing of the Catalytic Grant Facility. The SDDirect/Plan MERL lead has worked closely with BEK and UNW to co-design the RIVA ToC and results framework, which will be finalised after the forthcoming participatory ToC workshop (rescheduled from September to November 2025). The workshop will bring together delivery partners, BEK technical advisers, and external stakeholders to align indicators, integrate the UNW HS components, and define baseline data collection. There is no external M&E supplier; monitoring is embedded within partner systems and coordinated by BEK. The Annual Review process itself has been informed by joint partner reporting, quarterly progress documents, and consultation with colleagues across BEK, ensuring independent scrutiny and quality assurance.

Evidence

Evidence from the inception and early implementation period continues to affirm the programme’s underlying logic and relevance. Monitoring data and partner reports demonstrate tangible progress across key intermediate outcomes - particularly the strengthening of a more vibrant and intersectional WRO/CSO ecosystem and the early institutionalisation of GEDSI principles across BEK’s portfolio. The programme’s evidence base is broadening through risk-based capacity assessments, provincial-level mapping, and beneficiary feedback collected during UNW’s field visits. These data confirm that flexible, multi-year funding and collective care approaches are enabling smaller, marginalised organisations - including those led by Dalit, Indigenous, Muslim, LGBTIQ+ and youth activists - to participate meaningfully in the civic space.

All evidence continues to be reviewed through a Leave No One Behind lens, with emerging monitoring systems designed to disaggregate and analyse data by age, sex, disability and geography in line with the Inclusive Data Charter. While baseline data collection has been delayed by the national context and civic protests, preparatory work for a unified MERL framework and inclusive data plan is underway and will be operationalised early in 2026.

Learning

RIVA’s learning approach emphasises co-creation, reflection and sharing across partners and BEK’s wider portfolio. Over the past year, regular joint learning sessions have been held through the BEK GEDSI COP, the RIVA Programme Board, and the Hamro Sahas Community of Practice. These spaces have generated shared insights GEDSI mainstreaming and on feminist partnership principles, collective care and safe civic engagement. Key lessons include the importance of flexible, predictable funding for smaller WROs/CSOs; the value of early capacity and risk assessments to tailor partner support; and the need for adaptive planning amid political volatility.
For BEK, the RIVA experience offers broader learning on managing inclusion programmes during fiscal transition, highlighting how adaptive contracting, integrated risk management, and equitable partnership models can safeguard delivery quality in constrained environments. These insights are informing BEK’s wider portfolio and FCDOs approach to GEDSI effective mainstreaming and targeted support.
Looking ahead, the programme’s learning aims for the coming year are to (i) strengthen documentation of feminist and inclusive partnership practices; (ii) refine the joint MERL framework to better capture qualitative social norm change; and (iii) establish a routine learning exchange between RIVA partners and other BEK funded programmes to maximise coherence, efficiency, and evidence uptake across the mission and further afield.

Date of last narrative financial report	UNW: 7/11/2025 / SDDirect/Plan: 31/10/2025	Date of last audited annual statement	UNW: June 2026