Programme Completion Review

Title: Somaliland Elections, Democratisation and Governance Programme (SLEDG)
Final Programme Spend £ (full life): £2.71M	Review Date:	July 2025
Programme Code: 400492	Start Date: 14/10/2024	End Date: / 31/03/2025

Summary of Programme Performance

Year	FY 24/25
Programme Score	A+
Residual Risk Exposure Rating	Moderate

DevTracker Link to Business Case (and any addendum):
DevTracker Links to all logframes used during programme lifetime:

A. Summary and Overview

Summary: The Somaliland Elections, Democratisation and Governance (SLEDG) programme (£2.71 million, October 2024-March 2025) was implemented by the Netherland’s Institute for Multiparty Democracy (NIMD) to support the delivery of the 13 November 2024 Presidential and Party Elections as well as preparation for the new administration and subsequent elections. The programme also included a short-term deployment of an FCDO senior strategic policy adviser to support the new administration to develop post-election governance priorities (£39k). SLEDG delivered technical support to the electoral process and institutions including trainings for polling staff and agents, procurement of sensitive election materials, data management, voter education and media and communication support. Following the elections, SLEDG supported a rapid review to capture lessons learned as well as the development of a plan to prepare for 2026 legislative and local elections. The programme therefore strengthened the key electoral processes, improved the capacity of the national electoral body and political parties, and laid the foundations for the next cycle of elections. The programme also enhanced election inclusivity by increasing the participation of women, minorities, youth and persons with disability. The FCDO adviser delivered a well-received comprehensive design for a Delivery Unit and way forward for a technical facility.

The implementing partner, NIMD, worked well with a wide range of stakeholders, including the National Electoral Commission (NEC), political parties, political associations, government, civil society organisations (CSOs), women activists, politicians and platforms, international and domestic observers, and media outlets. … Overall, the SLEDG programme, despite starting just a month before the November 2024 elections, provided rapid, targeted and effective support that helped to deliver on-time, free, fair, and inclusive enough elections and a peaceful transfer of power, both of which are rare in an unstable region. This contributed significantly to maintaining Somaliland’s political stability, a key UK objective. …

The programme scored an A+ from five different outputs scoring from A++ to A. The log frame and the target has been amended with an additional specific indicator including 3.2, 3.3, all indicators of output 4, and 5.4 which is focusing on the post-election to assist the prioritization of the newly elected government. Outputs of the programme and their impact weighting are summarized in the below table.

Output	Score	Weighting
Output 1: A detailed election procedures manual created, and comprehensive training provided to NEC staff and party agents to ensure a transparent and efficient election process.	A+	30%
Output 2: Citizens are well-informed about the election process, legal systems, and procedures through various media channels, and there is provision for disabled access.	A++	20%
Output 3: NEC's institutional capacity has been strengthened by embedding international election experts, leading to improved efficiency and inclusion within the departments (pre- and post-election).	A+	25%
Output 4: Build Capacity Development Structures with the Women's Political Platform (Post-election), bringing together various initiatives and organisations	A	10%
Output 5: Support/influence existing or new administration on articulating and taking forward post-election governance priorities	A	15%

Major lessons:

SLEDG was agreed and implemented (too) late in the day: the SLEDG business case was drafted, approved and implemented at pace. … This required a lot of heavy lifting by BOH / FCDO colleagues. The lateness of approvals also impacted the implementing partner (NIMD) who had to flex and find creative ways to frontload some activities. Other stakeholders that were impacted include the NEC as we were unable to confirm UK support until very close to the elections thus creating further uncertainty. While the programme more than exceeded its targets, earlier agreement could have allowed for even greater impact of activities.

Targets need to be the right balance of ambitious and achievable: The SLEDG targets were ambitious, especially in the very short timeframe. However, they were achievable because of high-quality technical work by the implementing partner NIMD (and the FCDO strategic policy adviser); the willingness of key stakeholders, including NEC, to work closely with the UK due to longstanding working relationships; and BOH’s continuous engagement across the political spectrum and with civil society at large.

The combination of both support to the elections and to post-election planning by the new administration was of particular benefit: the latter was a small amount of funding to second a strategic policy adviser but resulted in outsized impact in shaping the new government’s approach to domestic policy in terms of inclusive development, economic growth and political reform. … UK engaging early and offering this targeted support was critical to shaping their approach. A portfolio programme would have created the flexibility to respond to such a critical and fits with current thinking for future programming in the Somalia Network.

1. FCDO’s political engagement with the GoSL was as important as the technical support: the programme benefited from BOH’s strong relationships with national stakeholders including the NEC. … FCDO / NIMD shared the lessons learnt exercise with NEC who have committed to implement the main recommendations. …
2. Working with international partners is critical, including to ensure sustainability and greater value for money, but coordination needs to improve: … While most other donors were not able to provide direct funding for these elections, the coordinated advocacy and engagement helped keep elections on track. NEC and other domestic stakeholders are clear that they see international funding – in addition to substantial domestic funding - as a key way to safeguard NEC’s independence. But coordination could be improved by obtaining early agreement on prioritisation and roadmaps which would allow donors to support more strategically.

Evidence

As part of the programme, the FCDO funded NIMD to commission an independent, in-depth evaluation conducted by the Centre for Analytical Research in Development (CARD). This assessed the extent to which the project contributed to strengthening the National Electoral Commission (NEC) and fostering overall political stability recognizing that free and fair elections are key to building a strong democracy. It concluded that despite the challenging political climate and a short implementation period, the project contributed meaningfully to ensuring credible elections which were recognised internationally and culminated in a peaceful transfer of power as well as increasing voter registration and supporting electoral institutions.

The CARD report set out their full recommendations against the project outcomes in their report, and these are reflected below in the output sections. Overall, their key recommendations focused on strengthening the NEC’s institutional capacity including through a post-election audit and making their staff permanent. They recommended that the GoSL should allocate reasonable funding to the NEC for operations and capacity development. They also recommended the UK / donors should continue to provide targeted support for specific technical needs, support development of a strategic plan for NEC and to expand targeted voter engagement programs for women, youth, and PWDs, by ensuring voter education materials and methods are adapted for diverse needs.

There were domestic and several international election observation missions and teams. The UK funded the International Election Observation Mission (IEOM), implemented by University College London, and co-funded the domestic election observation mission, deployed by the Somaliland Non-State Actors Forum (SONSAF). The Brenthurst Foundation, the Inter-Religious Council of Kenya, a Diplomatic Presence Mission (including HMA) from European countries, and an independent US team observed the elections as well. All missions reported that elections were peaceful and credible. The IEOM made recommendations for improvement of the process.

Recommendations for future programming

Specific recommendations are set out below under each output. This PCR makes the following overall recommendations:

1. Programme plans for future election support should be developed as early as possible to allow for the greatest possible impact. Political challenges and funding constraints are likely to remain a constant, however as demonstrated by the SLEDG programme – HMG democratisation objectives can be achieved as long as programme / political teams are available to do the heavy lifting.
2. Targets should be developed in close collaboration between post, monitoring/expert teams (x-Network), the beneficiaries, and the implementing partner. To achieve the relevant results in the programme lifetime, it was key to build targets based on the contextual understanding held by BOH.
3. The flexibility to allow for an amendment to include post-election support was key to the programme’s ability to have impact on, and support, the newly elected administration in the crucial phase following the election and transition and should be considered in future business cases.
4. Political engagement: Local – BOH should maintain close continuous engagement with Somaliland stakeholders in any future programming.
5. Political engagement: International – UK should continue to show leadership in driving international community engagement/coordination as key to facilitating future programming on elections.
6. The UK should help to maintain (and diversify) donor funding, including to help guarantee NEC’s independence and the transparency of the election process, while continuing to encourage GoSL to provide substantial funding and maintain national ownership of elections. (GoSL funded approx. 80% of the 2024 elections).
7. Voter registration reforms should be considered as part of future programming. These reforms are important because of the issues identified with data inaccuracies which in turn impacted the efficiency of the voting process. Voter registration for upcoming elections has already been raised to FCDO / donors as a key priority for the GoSL.

How this report was conducted

This report was led by the BOH team with the support from the Economic Development MEL advisor and informed by an independent evaluation (CARD), NIMD’s reports, and regular engagement between BOH and NIMD. It was also informed by BOH’s experience in both the run-up to the election and BOH’s activity on election day when they acted as independent monitors at some key polling stations in Hargeisa.

Actions following approval of this report
- Report narrative submitted on system by 30th June 2025.
- The report will be published in the Deathrocker with sensitive information redacted by end of the July 2025.
- Dissemination of the key findings of the PCR internally and to partners by the end of July 2025.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£2.5 million	£2.7 million (the AGA with NIMD was amended in December 2024 to reflect the requested increase in value to cover post-election activity).
Timeframe	17 September 2024 – 31 March 2025	17 September 2024 – 31 March 2025
Outcomes	The outcome statement is free, fair and inclusive as possible elections with space to re-engage on critical reform priorities.	The outcome statement was not changed, and the programme was able to support the delivery of elections that were deemed to be largely free and fair by external observers.

Overall assessment

This programme was set up at pace and delivered during a short time frame. Despite this the outcome level results were ambitious and there was a risk these would not be met, especially with the high risk of further election delays. The support from the UK through the SLEDG programme was continually lauded by the GoSL and in addition to the results set out below there was a clear benefit to our wider advocacy work that we were able to provide technical support to the elections.

The sustainability of the impact was set out in the business case as dependent on the willingness of the administration emerging after the elections to confront the challenge of a renewed developmental and political settlement. The technical support in the second component of the programme prioritised working with the post-election administration to prioritise its approach to domestic policy in terms of inclusive development, economic growth and political reform. Early signs from the newly appointed administration shows that these priorities match their own, they are engaging international partners on priorities demonstrating partnership intentions but also pushing forward their own growth agenda and a focus on internal stability within Somaliland. The desire to set up a delivery unit further underpins their ambition for sustainable progress following the election success.

To ensure Value for Money we selected those areas of activity where the evidence indicated that effort would have the most impact. The effectiveness of this programme is evidenced by NEC being ready to hold elections on time, the assessments of the observer missions and our own evaluation. The Technical Advisers provided continuous feedback on preparations, intervening where necessary and supporting higher quality outputs. To some extent, a free, fair and inclusive as possible election is by definition equitable. Activities were developed to ensure geographic reach and designed to include the most marginalised, which in this context is mainly women and minority clans. By including component 2 (senior technical advisor) we were able to capitalise on the successfully run election and link the political opportunity towards a more effective long-term strategy.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The Somaliland Theory of Change provides a framework for HMG interventions in Somaliland. The pathway in terms of the SLEDG programme is that state legitimacy is foundational to Somaliland’s stability. For the purposes of this programme, state legitimacy would be derived primarily through the delivery of free, fair and inclusive as possible elections – i.e. elections that are seen as ‘good enough’ to confer legitimacy on the incoming government. This would take place in conjunction with a focus on improving state responsiveness to the needs of citizenry, strengthening the citizen-state contract. The steps to achieving outcome and impact proved to be valid and demonstrated through the achievement of the outcome level indicators set out below. There were no changes to the ToC during the implementation of the programme.

The outcome level indicators from the Results Framework are listed below:
1. Elections are deemed free and fair by independent observers
2. Lessons Learnt and planning for next Electoral Cycle with a focus on inclusion
3. Renewed attempts to improve governance structures and engagement with the international community

Results:

1. Ensuring that the NEC was able to deliver the elections was the first programme target, which was achieved when the elections were held on 13 November 2024. This date was set out in the proposed election timeline by the GoSL however there was concern that there would be further delays. The elections had already been delayed form the original delivery which was supposed to be in 2022 and the international community lobbied for the elections to be held on time. Deeming the elections free and fair was the additional programme target, and with domestic and International Observers assessing the elections free and fair this was also achieved. Although the reports did also identify several shortcomings both in the run-up and the processes on the day.
2. A lessons learnt exercise was delivered in January 2025. The report shared with the NEC who in turn committed to take forward the recommendations within. A future assessment of elections in 2026 will see what changes/improvements have been made to the process and operations. This result will support planning for the next electoral cycle.
3. The High-Level Donor Co-ordination Forum held in February 2025, with an outcome document agreed. The new administration clearly articulated its policy priorities. Notable efforts made towards peace efforts with the East. Public commitments to adhere to the electoral cycle. Ongoing army reform to professionalise and reduce "ghost soldiers". Revenue mobilisation efforts (GST reforms on mobile money transfers). Still underperforming on female representation at all levels of government.

The programme scored A+ is a good reflection on the outcome and impact level results of this programme. There were no major changes to the results framework outcome targets over the programme lifetime. There were additions to the results framework to include outputs delivered in the post-election phase as part of the addendum to the programme.

## C: Detailed Output Assessment

Output Number and Title	1: A detailed election procedures manual created, and comprehensive training provided to NEC staff and party agents to ensure a transparent and efficient election process.
Output Score	A+
Impact weighting (%)	30%			Impact weighting revised since last AR?				No

Output Indicator		Final Logframe Target					Final Result Achieved
Output Indicator 1.1 / # of NEC ToTs trained on election procedures		160 (October 2024)					182 (Female: 16, Male: 166) (114% A+)
Output Indicator 1.2 / # of NEC polling officials trained on election day procedures		8205 (October 2024)					8224 polling officials trained (100% A)
Output Indicator 1.3 / # of training manuals printed		5500 (October 2024)					8000 training manuals printed (145% A++)
Output Indicator 1.4 / # of NEC staff trained on result management		134 (October 2024)					134 (Female:26, Male:108) (100% A)
Output Indicator 1.5 / # of Political Parties Associations ToTs trained		175 (October 2024)					167 (Female:32, Male:135) (95% A)
Output Indicator 1.6 / # of Political Parties/Associations agents trained		25000 (October 2024)					16846 (F: 4521, M:12325) (67% C)
Output Indicator 1.7 / # of journalist trained		300 (October 2024)					408 (F:104, M: 304) (136% A++)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The seven members of NEC were relatively new and were holding their first election. NEC also does not have a strong secretariat as majority of the staff are temporarily hired during elections, leading to institutional challenges. Polling stations staff are recruited from local universities and there are very low chances that they worked on elections before. Training them on election day procedures and on result management was, therefore, vital. Developed and printed training manuals also made the training more efficient and can be reused in the future so contributing to sustainability of the programme’s activities. Party agents at polling stations, who are critical for the election transparency, did not previously receive formal training, except briefing from their respective parties. Training them formally improved the electoral process, made the collaboration between the electoral body and political stakeholders easier, and enhanced the transparency of the vote casting. Training journalists also informed the transparency of the process and informing the public about it.

Lessons learned through this output, and recommendations for future programming

Lessons Learned
1. Capacity and skills of NEC staff are necessary for free and fair elections, training for the NEC and the polling staff can be a successful means in supporting this.
2. Training party agents in polling stations is equally important as they are important for election transparency and increase the confidence of political parties in the process.
3. Involving the media in the process is helpful. The programme trained journalists on how to report on elections, which helped the transparency of the process and enabled them to effectively inform the public about it. The programme also involved the media in voter education, which complimented their role in the process.

Recommendations
1. Given time constraints in the last election, ensure polling staff are identified and trained early on. Because the programme only started two months before the election, the activities it supported had to take place closer to the election date. Therefore, activities that should have taken place months earlier had to be implemented shortly before the election. While this was because of the programme starting late, NEC could have allocated funds for activities that could not wait.
2. Instead of deploying new polling staff with no prior experience in every election cycle the NEC should find a way to record the data of the polling staff, so they could be deployed in the future elections, provided they are available and remain politically neutral.
3. Since substantial amounts were spent in drafting and printing out these training materials, NEC should explore ways to record and repurpose the materials in the future.
4. Ensure party agents in polling stations have formal training on election procedures and their responsibilities vis-à-vis polling station staff since they are important for the election transparency.

Output Number and Title	2: Citizens are well-informed about the election process, legal systems, and procedures through various media channels, and there is provision for disabled access.
Output Score	A++
Impact weighting (%)	20%			Impact weighting revised since last AR?		No

Output Indicator		Final Logframe Target			Final Result Achieved
Output Indicator 2.1 / # of voter education campaigns conducted by CSOs.		48 (13 November 2024)			48 (13 November 2024) (100% A)
Output Indicator 2.2 / # of voters reached with communication materials/media		1 million (October 2024)			2.6 million+ for the NEC VE messages disseminated through contracted TV's social media channels. (260% A++)
Output Indicator 2.3 / # of CSOs participated in voter education		26 (October 2024)			43 (165% A++)
Output Indicator 2.4 / # of Media contracted to Aire voter education and awareness programs		13 TV and 1 Radio (October 2024)			103 (735% A++)
Output Indicator 2.5 / Vehicle access provided to disabled voters on election day		17 Buses			17 Buses (100% A)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Effective voter education and voter information help to better inform voters about the electoral process and voting procedures. Carrying out 129 voter education campaigns across the regions and reaching 2.6 million voters in a short period was significant. CSOs also adopted different forms for conveying messages, to ensure inclusive access to voter education. This component also ensured broad participation as it involved 43 CSOs and 107 media outlets. The roles and responsibilities of CSOs and media outlets have been expanded as well. This will help them to continue playing this crucial role in the future, even with the absence of external funding. Persons with disability not only received tailored voter education (including adding sign language to video materials), but they also received support to access polling stations and cast their votes in the election day. Overall, equal and broader access to election and voting information, and inclusivity in voting was achieved.

Lessons learned through this output, and recommendations for future programming

 Lessons learned
1. Despite conducting a comprehensive voter education campaign, which reached over 2 million voters, voter turnout was low (approximately 53%). This demonstrates that voter education does not solely influence voter turnout. By comparison, voter turnout was 80% in the 2017 Presidential Election and 65% in the 2021 Parliamentary and Local Council Election. …
2. Involving civil society organisations (CSOs) and media organisations was helpful to the wider process as it ensured that efforts were coordinated to some degree with the efforts of the NEC and ultimately made the voter education campaigns easier.
3. Providing tailored voter education and transportation to the people with disability significantly boosted their participation.

Recommendations
1. Electoral stakeholders should develop context-specific voter education and mobilization strategies addressing barriers like insecurity, displacement, climate shocks, and potential voter apathy.
2. NEC should increase public awareness and stakeholder understanding of the electoral dispute resolution process by making the information readily accessible.
3. Expand targeted voter engagement programmes for women, youth, and persons with disability, by ensuring voter education materials and methods are adapted for diverse needs. Training should be provided to election officials on how to assist PWDs, ensuring an inclusive and respectful environment at all polling stations.
4. Voter education should target the various phases of the electoral process, including the importance of voter registration and the need to assess the candidates and parties based on their platforms. Voter information should focus a few weeks before the registration of voters and election day on the practicalities of how to register and to vote.
5. In addition to the traditional media, social media and its influencers should be used more in the future to reach more people, mainly the young, with less cost.
6. NEC must increase the number of mobility aids (wheelchairs, ramps, braille) and transportation services in future elections to cover a wider area and ensure that PWDs can access polling stations.

Output Number and Title	3: NEC's institutional capacity has been strengthened by embedding international election experts, leading to improved efficiency and inclusion within the departments (pre and post-election)
Output Score	A+
Impact weighting (%)	25%		Impact weighting revised since last AR?		No

Output Indicator		Final Logframe Target		Final Result Achieved
Output Indicator 3.1 / # of strategies reviewed/developed - pre-election		8 policies (finance, procurement, voter education, communications, training, warehouse management, media, NEC' strategic plan)		7 policies and procedures developed (100% A)
Output Indicator 3.2 / # of strategies reviewed/developed - post-election		Strategic plan developed for NEC		Comprehensive five-year strategic plan was developed for NEC (100% A)
Output Indicator 3.3 / pre-election assessment for 2026 elections completed (underspend activity)		Pre-election assessment for 2026 elections completed (underspend activity)		Pre-election report for 2026 election produced (100% A)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

An independent, professional, and capable NEC with robust policies is crucial for free and fair elections. … Enhancing the capacity of NEC was a significant intervention that prepared and enabled the institution for undertaking the huge task of holding elections as well as administering post-election activities. Developing a 5-year strategic plan and 7 core policies not only significantly improved the capacity of the institution but also built the confidence of the political stakeholders in the election body and electoral process. The strategic plan gives NEC a clear roadmap and helps them with prioritisation and improvement plans. A comprehensive assessment and audit of the biometric voter registration system was conducted as well, and the proposed options will inform wider and longer-term electoral reform. Unlike other interventions that were confined to the last election, this improves the overall process and will also help the future elections. Post-election evaluation sessions held shortly after the election also documented the lessons learned and will be instrumental for improving the electoral process as well as the future elections.

Lessons learned through this output, and recommendations for future programming

Lessons learned
1. Developing core policies and strategies should neither wait for donor funding nor happen shortly before the election. There must be an ongoing NEC capacity building and preparations outside election cycles.
2. SLEDG’s investment in strengthening NEC yielded positive results, enhancing the coordination of electoral processes and improving NEC officials' capacity. This enabled the effective administration and management of voting activities, leading to accountable electoral processes, as independently documented by political parties, CSOs, and observers

Recommendations
1. NEC remains reliant on donor funding. The government should allocate reasonable funding to NEC for operations and capacity development, while continuing targeted donor support for specific technical needs.
2. More consideration should be given to NEC to strengthen its operational capacity and coordination mechanisms with NEC should be improved.
3. Institutional capacity development, including developing key policies and strategies, should not only take place in the run up to elections but should be done outside election times to avoid time constraints.
4. Plan for permanent staffing in all NEC departments to preserve institutional memory, including on gender and voter education, and establish a permanent presence throughout the country at district level to bring the institution closer to voters and CSOs supporting the electoral process at all stages.
5. NEC should make the media centre operations as core institutional function, ensuring dedicated budget and staffing as this centre significantly boosted transparency and trust.

Output Number and Title	4: Build Capacity Development Structures with the Women's Political Platform (Post-election), bringing together various initiatives and organisations
Output Score	A+
Impact weighting (%)	10%			Impact weighting revised since last AR?		No

Output Indicator		Final Logframe Target				Final Result Achieved
Output Indicator 4.1 / Bridge training course for ToT's for women political leaders		20 ToT's by 31 March 2025				30 women political leaders trained on electoral processes, legal frameworks, affirmative action and strategies to overcome barriers. (100% A)
Output Indicator 4.2 / #of female participants graduating through Democracy Academy (from a range of political parties, the Women's platform and other CSOs)		25 by 31 March 2025				25 completed Democracy Academy. (100% A)
Output Indicator 4.3 / # local and cross-regional exchanges		Bring colleagues from neighbouring countries e.g. Kenya and Ethiopia 31/03/2025				Not achieved (C)
Output Indicator 4.4 / Strategic plan for CIAG developed and technical expert support provided (underspend activity)		Develop a strategic plan				Strategic Plan developed for CIAG. (100% A)
Output Indicator 4.5 / # of consultations and regional meetings to capture broad geographical engagement		5 by 31/03/2025				14 consultation meetings were held which brough together 560 participants. (280% A++)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The programme not only ensured all pre-election support was gender sensitive including the trainings for election staff and voter education campaigns but also addressed key issues around women’s political participation, including supporting women political leaders to build their knowledge and understanding on the electoral process, legal frameworks and develop strategies to overcome barriers to effective political participation. The programme also supported 25 young women to actively participate in decision-making processes by providing them with key trainings, including leadership and communication. This support resulted in a tangible impact, encouraged several participants to express their intention to run in the 2026 elections, and contributed to the advocacy efforts that led to the announcement of women’s Political Participation Fund by the President on March 8, 2025.

One of the key lessons learned from previous elections was the lack of coordination and synergy on the efforts promoting women’s political participation due fragmented civil society sector competes the limited funding available rather than working together to achieve their common goal. To address this, the programme supported consultation meetings in various cities across Somaliland which brought together women from diverse backgrounds, including potential candidates for the 2026 election and those who run the 2021 elections to share lessons learned and to jointly work together to identify strategies for overcoming barriers. The role of grass-root women on improving women’s political participation is one that should not be taken lightly. The programme brought together grass-roots women’s self-help groups that is made up of over 30,000 women across the country with the aim to foster their understanding on the importance of women’s participation in governance and decision making. So while women’s political representation remained low in the 2024 election (just 1 female MP was appointed from the lists after an elected male MP died), , this intervention built the capacity and awareness of the women political aspirants, women voters and paves the way for better coordinated efforts for women’s participation in 2026 elections.

Lessons learned through this output, and recommendations for future programming

Lessons learned
1. …
2. The women empowerment initiative was a best practice for encouraging women's participation. Most graduates appreciated the program, stating that they had learned a lot and that the workshop motivated them to vie in the next elections. So far, four participants publicly announced their candidacy for the next elections.
3. Bringing former female candidates to share their experience with young female political aspirants was helpful by unpacking the real challenges these women faced as candidates, and this has provided clear understanding for the female political aspirant on actual challenges and perceived once. This provides them with clear vision of what is ahead of the as candidates in the future. ,

Recommendations
1. Provide flexible institutional and networking support to the Women’s Political Platform to bolster its peer-training, advocacy, and support functions for aspiring and current women leaders.
2. Internal political party structures were identified as barriers, particularly for women candidates. There is need for political parties in strengthening internal democracy aimed at removing structural and cultural barriers to women’s leadership.
3. Secure funding to continue and expand women’s leadership training and incorporating mentorship ahead of the 2026 elections. To achieve this the donor community together with the Somaliland civil society and other women’s political participation stakeholders need to coordinate

Output Number and Title	5: Support/influence existing or new administration on articulating and taking forward post-election governance priorities
Output Score	A
Impact weighting (%)	15%		Impact weighting revised since last AR?		No

Output Indicator		Final Logframe Target		Final Result Achieved
Output Indicator 5.1 / Political or Development Co-ordination forum held between SL authorities and International Partners		Development Coordination Forum held		Development Coordination Forum held (100% A)
Output Indicator 5.2 / Government clearly articulates priority of needs		Somaliland Government set its priorities		Somaliland Government set its priorities (100% A)
Output Indicator 5.3 / Proposal for SDF Technical Assistance Facility		SDF Technical Assistance Facility developed		Detailed SDF Technical Assistance Facility structure and recommendations developed (100% A)
Output Indicator 5.4 / Needs assessment of the new Peace Building Committee (underspend activity)		Technical assistance provided to the Somaliland Peace Committee		Communications strategy, bylaws, and financial and procurement manuals developed for the Somaliland Peace Committee. (100% A)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

In the post-election period, British Office Hargeisa went to work with the resulting administration and their policy priorities in line with UK objectives. This work identified a practical, strategic approach to make the state more responsive to citizens’ needs through institutional, legislative and regulatory reform, examining both supply and demand side perspectives. It will match these opportunities to the existing pipeline of UK programming to embed systemic change. Through a programme called Somaliland Development Fund phase 3 which is planned to start in this financial year 2025 had a component focusing on supporting the current government for technical support/advisory. Technical advisory support, drawn from existing FCDO framework agreements, will work with key institution including – but not limited to – the Presidency, Ministry of Finance and Ministry of Planning.

With the support of the programme funds, the first high-level development forum between Somaliland government and the development partners including UK, Denmark, US, EU, Sweden, France, Turkey, Norway, Finland, Germany, Canada, was held in Hargeisa in February 2025. This supported a frank donor-GoSL discussion of contextual updates including political and economic updates, government priorities, and what future programmes will look like in consideration with reducing donor funds. The government shared a presentation of the partnership framework to the development partners.

British Office Hargeisa contracted an FCDO Strategic Policy Advisor from London for three months to support the team with the establishment of a technical delivery unit for the new government. The advisor delivered a comprehensive design structure with detailed recommendations on the way forwards for the technical facility with the intention to consider for SDF3 programme delivery. The delivery unit would represent a transformative element of the administration that could develop plans aligned with the administration’s priorities. The unit will help transform the bureaucratic capability of the administration and will target the implementation of specific priorities and reforms. This intervention helped the government with their policy prioritisation and designing a Delivery Unit and assisted us with designing SDF3. It also gave us the space to align SL policy priorities with UK objectives.

The Peace Committee is a new institution, set up by President Irro to lead the government’s peacebuilding and conflict resolution initiatives. The programme provided critical support to build institutional capacity. The support specifically helped to develop a communications strategy, their internal bylaws / regulations, and financial and procurement manuals.

Lessons learned through this output, and recommendations for future programming

Lessons learned
1. Delivering a high-level forum in a politically sensitive context is always going to be challenging. The additional challenge in Somaliland was as this was an initiative of the Government it was important for the UK to only take on a supporting role. …
2. While the target of Somaliland setting its priorities was achieved, the process to get there took up a lot of time from the dedicated Strategic Policy Advisor. …
Recommendations
1. Consider in more detail the financing available within the SDF3 envelope so that more relevant project activities can be included in the redesign of the programme.
2. Engage with Somaliland to understand timing and their own internal plans as they develop. As the new government is fully onboard, revised their priorities, and set clear timelines for what they plan to achieve, it will support SDF3 programme projects designs which will be in line with UK priorities and the country business plan.
3. Engage with the UK’s delivery unit expertise to explore opportunities for support
4. Consider options for a facilitated design intervention, with the Somaliland administration and delivery experts. This collaboration ensures the design of a programme that reflects the local needs while in line with BOH Theory of change and FCDO CBP. It will also enhance sense of ownership for the current government.
5. Consider other funding sources including, including the Public Finance Resource Centre (PFRC) and potentially other FCDO Centres of expertise and draw down facilities with REACH (particularly suppliers with delivery expertise). This considers examples of the sources of funding for the programme once the delivery unit is set up whose main role will be looking for funding for identified programmes/priorities of the government.
6. Explore opportunities for UK expertise to provide the cross-cutting support to the transformation or delivery unit. Considering the delivery unit being new to the context in Somaliland, it will be an opportunity to connect to the UK expertise which enhances knowledge transfer and a learning opportunity for the technical team of the delivery unit

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The business case of the SLEDG programme stated the programme driving the Value for Money (VfM) through Economy by using standard existed rates especially the cost of consultants, trainings, operations cost during the election day, Efficiency by using existed structures to achieve the desired programme output with its limited time, Effectiveness which is measured through the achievement of the programme outcome with the allocated cost, Equity is measured the free, fair, and inclusive as possible election across all accessible districts in Somaliland, and Cost-Effectiveness which drives to achieve a credible, inclusive, durable, and accountable election process. Despite the existence of critical challenges such as the conflict in the east, fragmentation of the clan relationships in Somaliland, yet the programme ensured to achieve the best output it intended to achieve where the International Observers Mission accepted its credible and fair election it was.

Overall, the Value for Money the programme rated as A+.

Economy

Regarding the economy criteria, the overall programme is rated good, it used an existing supplier who was already working with NEC as the number of available suppliers with relevant election expertise in Somaliland are limited. The stipends and other peripheral costs used in the programme were based on NEC’s own budget. The programme percentage contribution to the overall election budget, while roughly the same in absolute terms compared to the 2021 election, is significantly smaller (15% in 2021 to 11% now). The second component of the programme used an in-house framework to second a Strategic Policy Advisor from FCDO (temporarily based in BOH) to work with key ministries (Finance, Planning, and Presidency) which reduced the transaction cost of going to the open market.

Efficiency

The overall efficiency is rated excellent. The programme allocation was based on needs from the NEC and the government ministries where it complemented the gaps needed the international community to fill in. Due to the short time frame, the programme ensured to use an existing supplier using both international and local consultants, specializing in operations, communications, training, and IT who significantly enhanced the NEC’s pre-election capacity, efficiency, transparency, and inclusivity within the departments. This set up the fundamentals for a resilient electoral system that promised fair and reliable elections, boosting public confidence in the democratic process at every level. All the processes were bottom-up inclusive processes where key stakeholders were involved in project design and execution. The programme team and the fund manager managed day-to-day activities to ensure all contractual activities were executed on budget and on time.

Effectiveness
The effectiveness is rated excellent overall. Between February and March 2025, through a competitive process, NIMD engaged the Horn of Africa Strategic Initiatives (HASI) and the Zimbabwe Election Support Network (ZESN), which are joint local and international consultant firms, to significantly enhance CRPAANP’s (Committee for the Registration of Political Parties and Approval of National Parties) operational effectiveness and ensure its long-term sustainability by focusing on the development of five years strategic plan with a clear monitoring and evaluation framework which is fully aligned with Somaliland NDP III, through consultation document organizational restructure focusing on an optimized organigram with clear reporting lines and detailed job descriptions for all positions to enhance inter-departmental coordination mechanisms, policy and manuals development such as a Financial Management Manual clearly outlining controls for budgeting, auditing, and accountability, a HR Policy Manual to standardize recruitment, performance evaluation, and gender-sensitive practices, and a Procurement Manual to implement transparent bidding and contract management processes, and lastly a capacity building training for committee members (on strategic leadership) and secretariat staff (on policy implementation). All those manuals and policies are intended NEC being ready to hold future elections in a timely, transparent, and credible election.

Equity
In Somaliland’s electoral processes, persons with disabilities (PWDs) continue to encounter a range of challenges, including inaccessible polling stations and limited support mechanisms during elections. In response, a dedicated intervention was implemented to enhance inclusivity and provide tailored assistance to PWDs, particularly during the 2024 Presidential and political party elections. This initiative marked a significant milestone in advancing a more accessible and equitable voting environment for all citizens in Somaliland, including women, rural communities and minorities. For the first time, the NEC and NIMD introduced dedicated support measures to assist people with disabilities throughout the electoral process.

In collaboration with the Somaliland National Disability Federation (SNDF), the program has successfully registered around 603 disabled voters across the six leading cities. Key achievements of the intervention included the provision of disability-friendly portable ramps, the establishment of a dedicated call center, the distribution of mobility aids, and the arrangement of transportation services across all six regions of Somaliland. SNDF played a central role in executing these activities. To begin with, SNDF set up a call center to facilitate the registration of PWDs across all six regions of Somaliland. The call center was staffed by nine trained SNDF personnel who worked directly with PWDs to ensure they were registered for the election and had the appropriate voting cards. Next, to address the lack of accessible infrastructure at polling stations, SNDF purchased 81 wheelchairs and 18 portable ramps. The assistance was strategically distributed to various polling stations to assist PWDs in reaching and entering voting booths. Recognizing the challenges many PWDs face in traveling to polling stations, SNDF organized 17 vehicles for transportation of individuals from their homes to the nearest voting stations. This service was intended to ensure that PWDs had a smooth and safe journey to vote. Finally, SNDF conducted outreach efforts in collaboration with local organizations and media to raise awareness among PWDs about the voting process and the availability of accessibility support.

While women are excluded from Somaliland's decision-making tables, considerable number of polling station staff were women this provides safeguarding mechanism to prevent intimidation and harassment at the polling stations. In additional, deployment of security personnel offered protection mechanism for both women voters and female staff at the polling stations.

In rural geographies, voters who were unable to identify their preferred candidate in the ballot paper were assisted by the polling station staff together with the political party representatives. In addition, political parties provide transport support to voters in the rural areas to reach polling stations. Although this programme didn't support was give the political parties’ efforts to provide transportation, the programme supported training for political parties' election staff who are the parties' preventatives on the ground and assuring voters are reaching and casting polling stations.

To ensure Voter education is accessible to all, 129 voter education campaigns across the regions and reaching 2.6 million voters were conducted. These covert education campaigns were not exclusive to main cities but reached communities in the rural areas and IDPs. People with hearing impairments were taken into consideration voter education campaigns included sign language interpretations. CSOs working with the minority communities were part of the CSO that delivered the voter education campaign.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating of the Somaliland Election, Democratization, and Governance programme was moderate. The major risks that were expected to have influence for the programme implementation were NEC commissioner to resign or NEC is disbanded by the president, …, elections are delayed for political, security or technical reasons, Somaliland counteroffensive or clan conflict in the east, …, AS attack in Somaliland during the election days, UK support is perceived as a recognition or partial or evidence of interfering in the election process. Should the NEC have been disbanded during the pre-election period the electoral timelines would have changed significantly and risked public discontent and possible violent demonstrations.

The implementing partner and the programme team in Hargeisa had a weekly meeting to ensure monitoring the contextual developments including risks and potential mitigation measures. Further to that, through the Somaliland Democratization Streeting Committee (DSC), the programme team had bimonthly meetings with the international community to exchange updates such as the status of the election environment and any risks that may influence/impact the execution of the election. The programme team had a regular meeting with NEC to ensure strong collaboration and understand any challenges they are expecting to cause disturbance of the programme/election execution.

 The close collaboration between the programme team, the IP and the NEC ensured that any changes in the approach to the delivery were handled in a timely manner. Timelines were rarely adjusted as they were already so tight, but the team were able to ensure that the priorities stayed on top of everyone’s mind to avoid disruption to the delivery.

The programme team ensured to log the contextual risks and updated the risk register in the Aid Management platform (AMP) which ensured the transparency and accountability of the programme.

Risk category	Description and Risk Mitigation Measures
Strategy and context	Overall rating: Moderate / The election programme faced number of strategic and contextual challenges during the programme implementation period. / … / Clashes between Somaliland and SSC-Khatumo, Las Anod counteroffensive, or clan conflict: / Worked with partners to map co-ordinated response for any clashes. It was agreed to stop any relevant direct support upon evidence of violations on the part of the authorities. British Office Hargeisa (BOH) ensured implementing partners to have plans in place for managing this risk. BOH worked with NEC to assess feasibility of allowing registered voters to vote in conflict areas or alternative. / … / Elections are delayed for political, security or technical reasons: / BOH used this programme to support technical ready-ness. The programme team used diplomatic levers/engagement to hold former president to account and escalated via DSC and HMA as appropriate for any issue that raised. / …
Policy & Programme Delivery	Overall rating: Minor / The UK support is perceived as a recognition in Somaliland: / UK policy on Somaliland independence is well known and with the elections completed we have managed the UK position on recognition and therefore closing this risk. / … / UK support is seen as partial or evidence of interfering in election process: / Support is delivered via NEC as an independent institution, but all parties are aware of and have agreed to UK support. There was also a comms agreed with NEC on what extent FCDO should specify the types of support that the UK provides.
Public Service Delivery and Operations	Overall rating: Minor / NEC commissioners resign or NEC is disbanded: / During the programme execution, NIMD assessed under what circumstances and whether support could continue if a commissioner resigned or NEC is disbanded. Incomplete or absence of NEC affects the timeline and delays the election. While nominating NEC is straightforward, it is susceptible to politicisation and can easily undermine the entire election process. As a contingency plan, we regularly encouraged political parties to close work with and respect the independence of NEC. We also constantly reminded NEC that delivering the election in a transparent, professional, and neutral manner earns them the confidence of all stakeholders. / The NEC remained in place for the 2024 elections and still have their mandate in place under the new government.
Safeguarding	Overall rating: Minor / AS attack(s) in Somaliland during the election: / Normal security protocols are in place for BOH, and partner organisations have their own duty of care responsibilities. The management of BOH assessed the overall contextual situation to determine whether feasible for UK staff to remain in Hargeisa and the safety of BOH imbed under Component 2. / There was no AS violence during the election and so this risk was low with no effect for the election process. / Sexual Exploitation Abuse and Sexual Harassment: The IP submitted their policy on SEAH as part of the due diligence process. This policy met the requirements of the FCDO and during the programme delivery no concerns were reported.

During the programme implementation no fiduciary cases was identified as the fund manager set in place all the mechanisms and procedures to prevent fiduciary activities of the programme.

Update on Partnership Principles
The programme was designed to partner with Somaliland government by contributing technical assistance through election experienced partner. No funds are channelled to the government accounts but through the supplier. The programme team monitor the context and ensuring the government to uphold human right and transparency.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The implementing partner demonstrated varying degrees of effectiveness in programme management across key performance areas. This section of the PCR will assess their performance based on the implementing partners ability on planning, coordination delivery, achievement of results, financial management, compliance with reporting obligations, and overall partnership engagement with FCDO and other stakeholders.
The Programme team had regular engagements with the implementing partner (NIMD) where they evaluated both project and financial performance of the programme regularly. On a quarterly basis the implementing partner provided a performance report of the project which covered project activity progress, risks and mitigations, and spend update, this close engagement provided an insight to closely monitor budget utilization against planned activities and showed the partners ability to accurately forecast which minimized under/over-spend variance. The project team conducted financial management and procurement for IT, vehicles, venues, and services spot checks to ensure the implementer was adhering to the terms and conditions of the accountable grant agreement where necessary. To measure supplier performance, detailed KPIs were designed and used to measure supplier performance. The supplier also delivered programme completion report which was reviewed and approved by the programme team before final payment was made to the implementing partner.

NIMD in close collaboration with British Office Hargeisa developed and maintained a work plan aligned with the agreed results framework and timelines. Coordination with key stakeholders mainly the National Electoral Commission NEC, and other relevant election stakeholders was effective and had positive contribution to the achieved results of the programme and UK’s overall engagement on the election period.
Progress towards the intended output and outcomes was on track throughout the programme delivery period (see output assessment section). The implementing partner showed strong commitment to results-based management and adoptive programming which contributed the agility of this programme to respond to changes in priorities and election needs.
To mitigate fiduciary risks, due diligence assessment was carried out prior to the awarding of the accountable grant agreement. No major risks were identified and agreed actions were followed with the implementing partner. During the implementation period, the implementing partner provided regular financial reports to report on expenditure and results achieved on a quarterly basis. The programme team closely monitored the overall programme spend.
Audit - the programme was audited by an external auditor and the key findings and recommendations of the audit report were addresses immediately. The findings are listed below:
1. Gaps in procurement: the review of the external auditors noted that the evaluation of vehicle hire and food & refreshments costs primarily focused on cost, overlooking the technical evaluation. The auditor recommended that the implementing partner to ensure that future procurement requests specify detailed requirements for items such as vehicle rentals and catering services to facilitate fair and accurate evaluation based on both cost and quality. NIMD responded to the finding and justified the specification used for vehicle hire are the standard vehicles used, and specifications are widely understood. NIMD committed to include details in future procurement documentations to avoid any ambiguity. On refreshments, NIMD confirmed that they used the standard commonly used and applied menus for workshop-related catering services.
2. Gaps in Statutory deductions: the auditor recommended that income tax be filed and paid on or before the due dates to avoid penalties. NIMD confirmed that payroll taxes have been duly filed and paid to the appropriate government authority in accordance with regulation.
3. Non-compliance on reporting requirements: The Auditor recommended that management to ensure that reporting is done promptly as per the agreement to avoid delays in activities implementation due to delays on funds disbursement. NIMD assured that they have completed IATI reporting and successfully uploaded data. On delayed progress reporting NIMD justified the delay on reporting on the need to send consolidated payment requests given that they have pre-financed activities, and a single consolidated payment was more appropriate rather than having multiple reimbursement requests.

The final audit report and the NIMD response to the audit report findings have been shared with the FCDO. While we agree with the NIMD response to those findings which are exclusive to the operating context, on financial management and reporting we would recommend that the Implementing partner improve their financial reporting particularly ensuring that the reporting is based on FCDO financial reporting templates and requirements.

Lessons learned and Recommendations
Despite the short period of programme implementation both FCDO programme team and the Implementing partners showed effectiveness in the delivery of the programme, and this could be reflected from the overall achievements and the results delivered. Positive lessons learned from this programme include the importance of effective coordination and collaboration between BOH and NIMD team which had significant contribution to the design, commercial and implementation stage of this programme. However, such limited short-term programming poses risks to overlock certain programme management aspects including the timeline and quality of reporting both narrative and financial. Although, the implementing partner met with the required reporting timelines, yet there were occasions when reporting was delayed. For example, one of the key recommendations from the due diligence assessment was to provide updated risk register which the implementing partner didn't submit on time thus impacting on the actual tracking of programme risks.
The programme delivery timeline compared to the magnitude of the expected outcomes varied significantly. While this programme achieved or exceeded its expected outcomes, it is recommended that the FCDO to take into consideration required timelines for internal FCDO procurement processes and provide sufficient time for programme initiation stage to provide implementing partner sufficient time for programme delivery planning.
On programme management, the BOH didn't have a dedicated programme manager to oversee the day-to-day programme management tasks, thus creating extra burden for staff to take on additional responsibilities. Recommendation for similar future programming would be to scope team capacity and capabilities to ensure that there is resource available for programme management.
Programme-level approach to monitoring and evaluation

At the programme level there was a “whole of office” approach to the monitoring and evaluation of the SLEDG programme as the elections were a top priority for BOH. This meant that the whole BOH team, plus colleagues across the Somalia Network and BE Mogadishu were involved at various stages. This close oversight proved an effective way to ensure that everyone was sighted on progress throughout the programme cycle and we were able to effectively assess risks and developments to programming. This approach included:
- BOH – NIMD regular partner weekly meetings between October 2024 and March 2025. These meetings provided crucial election and programme updates which played critical role in ensuring BOH priorities alignment with those of other election stakeholders, addressing emerging risks/challenges and maintaining momentum across all election programme delivery
- Close engagement with TAs who supported domestic observation mission and frequent catch ups with the international in the run-up to the election provided insight on election preparations and informed UK engagement with election stakeholders.
- BOH conducted monitoring field visit to monitor pre- election trainings, on election day BOH (+ HMA) attended polling stations to observe performance of trained polling station staff. Further monitoring visits were conducted to monitor post-election activities implementation including Democracy Academy training in Berbera.
- Frequent engagement with the NEC before, during and after the election period (political & programmatic) informed the scoping, design and implementation of the SLEDG programme and the overall UK election engagement.
- Strategic Policy Advisor embedded in BOH for three months of post-election strategic support to GoSL

In addition to the internal monitoring and evaluation activities conducted by the British Office Hargeisa team, the SLEDG programme had external in-depth evaluation with the aim to assess achieved objectives and results linked to the overall programme objectives. The findings of this evaluation report provided crucial insight to the overall election conduct and provided important lessons learned and recommendation which should be taken into consideration for future similar intervention. This is an internal report, if interested contact BOH team.

Date of last narrative financial report	NIMD End of Project report was submitted on 18 April 2025.	Date of last audited annual statement	Audit report submitted by M.N Cliff & Associates LLP on 21 May 2025.