Business Case: Countering Illicit Finance Summit 2026

Summary Sheet

Business Plan Summary / The Development and Open Societies Directorate (DOSD) plays a critical role in building the open international order of the future, reflecting our values, and protecting our interests. A specific goal of the Development and Open Societies Directorate (DOSD) is that ‘accountable, effective, and inclusive institutions, and resilient civil society and civic space, are protected and supported, that citizens are helped to participate in democratic processes and that the threats and harms posed by corruption and illicit finance are reduced.’ / The Foreign Secretary has made tackling illicit finance one of his two personal priorities (alongside children in care). He launched his Illicit Finance Campaign in November 2024 with a high-profile package of sanctions designations targeting kleptocrats and their enablers. He announced in June 2025 his intention to host a Countering Illicit Finance Summit. The Illicit Finance and Anti-Corruption (IFAC) Department is working across FCDO and HMG to deliver the Foreign Secretary’s Campaign and Summit ambitions.

Title: Countering Illicit Finance Summit 2026
Programme summary / The purpose of this programme is to build common insights and agreements amongst high-level political participants about the scale and nature of the illicit finance threat and the domestic and international action needed to tackle these threats. This programme will prepare and deliver an Illicit Finance Summit bringing together a diverse coalition of countries, the private sector and civil society to demonstrate shared commitment to tackling illicit finance and its myriad harms, many of which land hardest in the Global South. Programming interventions will include policy development and engagement activities in the run up to and beyond the Summit, as well as funding the logistical costs of hosting a Summit for approximately 150 participants.
What is the rationale for UK Aid spending? / Illicit finance is a transnational threat and effective action is a global public good benefiting UK partners in the Global South. Approximately US$90 billion is lost every year in Africa, dwarfing total aid flows. Action to tackle the threat can substantially support accelerated development.
Programme Value: £5.6 million (of which £2.6 million is ODA)		Country/ Region or Sector: / Anti- Corruption
Department confirmation of review processes		Key processes for BC review have been followed prior to submission (Ashufta Alam, SCS1 SRO)
Contact name		Shirley Cameron
Threshold for final approval of Business Case: Director-level
Date of Approval of Concept Note:	01/05/2025	Name and role of Approver / Minister Doughty
Date of Approval of Business Case:	16/07/2025	Name and role of Approver / Will Hines, Director (DOSD)
Programme Code: 400538	AMP Start Date: 29/7/25	AMP End Date: 31/3/27
Overall programme risk rating:	Major

Strategic Case
Illicit finance and corruption present a vast, global problem. The United Nations Office on Drugs and Crime estimates that annual laundering volumes range from 2% to 5% of global GDP. For 2024, this translates to between $2.22 trillion and $5.54 trillion. In Africa, it is estimated that approximately $90 billion annually is lost to illicit finance – a sum greater than all annual development aid. The National Crime Agency estimates that over £100 billion may be laundered through and within the UK or UK-registered corporate structures alone each year.

The role that countries that function as global or regional financial centres (i.e. concentrations of commerce, trading, real estate and banking) can play in enabling resources to be drained from developing countries are a fault line in relations the UK and other countries have with the Global South. Corrupt and illicit networks undermine efforts to increase growth, tackle the climate emergency and accelerate progress towards the Sustainable Development Goals. Laundered proceeds from corruption and serious and organised crime are used to fuel conflict and entrench kleptocratic rule, threatening UK and global security. By tackling illicit finance, we can strengthen the resilience and integrity of financial markets and global growth, whilst also supporting the conditions for more accountable forms of governance and public services delivery. These are critical for accelerating nationally led ambitions on growth, trade, democratic stability and accountability in the developing world.

Established and emerging financial centres play a critical role in addressing this transnational threat. The UK is uniquely placed to use its position as a global financial centre to encourage and incentivise action from others as the international financial system as a whole is only as strong as its weakest link. Evidence and programmatic experience also highlight that the most effective approach to address illicit finance is to target the whole ‘value chain’ in a holistic way. This includes source countries e.g. those drained of resources and that experience high levels of harm e.g. violence, reduced investor confidence; financial centres where funds can be laundered and redirected; and offshore havens. Adopting a piecemeal approach which only focuses on one or two aspects of the chain might produce local results, however it is much less effective, efficient and sustainable compared to a joined-up approach. Illicit finance is a networked, transnational problem that requires a networked, transnational response across a broad grouping of countries.

The Foreign Secretary has launched a ‘Campaign’ to lead FCDO engagement with a wide range of UK and global actors to build common understanding and opportunity with others in tackling illicit finance and its harms. A UK-led Summit, in the first half of 2026, on tackling international illicit finance will form the centrepiece of the Campaign. It will be hosted by the Foreign Secretary and subject to further steers, convene a diverse coalition of countries, multilateral bodies, private sector and civil society. The Summit will seek to build consensus about the role illicit finance plays in addressing shared geopolitical challenges and build enhanced commitment to action at the national and global level.

This programme will deliver the activity needed to shape Summit ambition; engage with stakeholders who can help deliver Summit aims, including through targeted Summit pre-events; prepare the logistics to physically host a professional and polished Summit; and conduct targeted post-Summit engagement activity to help ensure the momentum generated by the Summit is channelled into generating new dialogue, partnerships or accelerated implementation of solutions to the challenge.

Programme activity that generates policy ideas will centre around the following five thematic priorities of the Foreign Secretary’s Campaign, and subject to the expressed priorities of the UK and others and potential for high ambition pledges and commitments:

1. Reduce financial secrecy by raising the bar on corporate transparency globally, including in the Overseas Territories.
2. Restrict professionals who enable or conceal money laundering through stronger legal, regulatory and restrictive measures, including sanctions.
3. Hold kleptocrats to account through enhanced law enforcement action including asset recovery, alongside stronger efforts to exclude them from the UK economy through sanctions and other measures.
4. Drive reforms in global financial centres through bilateral partnerships and relevant multilateral structures, including the OECD and Financial Action Task Force (FATF), and in high-risk areas including gold and crypto assets; and
5. Reduce harms to development from illicit finance and grand corruption by supporting long-term reforms that promote stronger institutions and growth and by pushing others, including international financial institutions, to increase their focus on this.

Campaign priorities draw from a sizeable evidence base showing that a portfolio or systems-wide approach is the most effective way to respond to illicit finance risks and the harms they produce. In practice, this means a combination of efforts to expose (e.g. transparency efforts, civil society, investigative journalism), prevent (e.g. legal and regulatory defences) and respond (e.g. law enforcement, sanctions). Evidence points to the important role for both 'supply' and 'demand' side responses in this effort. Supply refers to building capacity so countries individually and collectively can more easily detect, tackle and return illicit finance, and enhancing standards and their enforcement to make it harder for criminals, kleptocrats and professional enablers to move illicit finance through the various layers of the value chain. Demand refers to building awareness of the threat, establishing political will and empowering civil society and journalists to address issues in source, financial centres and the destinations of illicit finance. Critically, strong, coordinated action between countries, the private sector and civil society is needed to respond to this networked challenge.

The Summit and the work leading up to it will be a significant opportunity to translate the technical and networked elements of tackling illicit finance into an engaging narrative for the UK public and other audiences. This will also help explain why and how FCDO’s partnerships in tackling illicit finance is important for supporting the following HMG Missions:

- Kickstarting Economic Growth: By demonstrating how strong defences against illicit finance and corruption are a vital foundation for economic growth domestically and globally. For example, beneficial ownership registers are an important tool for domestic revenue mobilisation, enabling public services funding. Tackling illicit finance and corruption underpins investor confidence and is the bedrock of ensuring a level playing field for business, fostering healthy competition.
- Strong Foundations, Encompassing Economic Stability, Secure Borders and National Security: By limiting the crime, and malign activity, facilitated by illicit finance and corruption. For example, forging modern security partnerships will increase our ability to track cross border illicit finance, and help reduce organised crime.
- Safer Streets: By limiting the illicit funds fuelling criminal activities and violence at street level.

Development Act

This programme will comply with the International Development Act 2002, and will contribute to fairer, more inclusive, and accountable political processes, power structures, and decision-making in FCDO priority countries.

Gender Equality and Public Sector Equality Duty

We will develop a set of inclusion principles to aid the delivery of inclusive and accessible events. These principles will cover inclusive participation across formal and informal roles; accessibility of the venue; and civil society consultation.

Tackling illicit financial flows helps reduce inequality because illicit financial flows lock power within certain groups and elites.

 Counter-Terrorism

The risks associated with terrorism and criminal financing in this programme are considered low. Programme funds will be deployed to other HMG teams to cover the payments of goods and services via Framework Agreements with pre-agreed suppliers and where such agreements benefit from standard due diligence assessments.

Safeguarding

Safeguarding will follow the FCDO do no harm policy and ensure that safeguarding plays a role in promoting sustainability and good value for money. The principle safeguarding risk, if it plays out, is likely to be the exposure of FCDO staff, particularly in junior grades, to very senior leaders at the Summit whose behaviour might breach acceptable standards. An account of safeguarding risks and sources of real-time support will be briefed by the SRO to the FCDO Summit Team (including volunteers as appropriate) in the days before the Summit.
Climate and Environment

No climate or environmental risks have been identified at this stage.  The programme does not invest in fossil fuels or undermines relevant country Nationally Determined Contributions. Programme activity is unlikely to qualify as International Climate Finance-funded.

Risk

The main risks to programme delivery are:

1. Geopolitical: Action or ambition on illicit finance is undermined by wider or unrelated geopolitical dynamics.
2. Political: Lack of political will or resource constraints (financial, technical) act as barriers to national action by government attendees.
3. UK reputation and credibility: UK’s ability to engage credibly with attending countries in the run up to, and at, the Summit is undermined by a perception that UK domestic commitments are weak.
4. UK impact globally on illicit finance: UK impact in addressing the global threats, including those affecting developing countries, is undermined by HMG pressures to prioritise action on other significant or domestic threats and opportunities.

Theory of Change
A detailed Theory of Change will be finalised within three months of the programme commencing, alongside a judgement of the proportionality of developing a logical framework. A high-level ToC is presented below:

Impact and Outcome
At the impact level, the Summit will shine a global spotlight on illicit finance threats and opportunities in support of building momentum for global and accelerated political action. It will be an opportunity to showcase FCDO and wider UK leadership and contribute to protecting existing progress and lines of effort. Specifically, it will address the harms – such as organised crime, fraud, modern slavery and child sexual abuse, inflated asset prices - caused by illicit finance to ordinary citizens in developing countries and wider by advancing collective action on international security (kleptocracy, hostile state activity, investor confidence), global development (grand corruption, financial losses), democratic governance (democracy, rule of law, media freedom) and border security (organised immigration crime).

At the outcome level, the Summit will generate a moment that shines a spotlight on the role of illicit finance in fuelling threats to global security and prosperity, and fosters dialogue at the highest levels amongst partner countries and others. The commitment to, and the quality of, the dialogue will help secure:

1. Increased political prioritisation of actions to curb illicit finance through a series of pledges to address systemic challenges
2. Practical commitments and actions to accelerate the implementation of international standards, and enhance long-term cooperation between governments, law enforcement and the private sector.
3. Strengthened foundations for long-term collaboration between governments, law enforcement and the private sector on specific threats.

To help ensure the Summit drives international action that can make a difference, the Summit will develop a framework for action which the UK and attending countries can consider and make national level commitments. This framework will take existing international standards e.g. those of the Financial Actions Task Force (FATF) into account. A country’s ability to develop and implement clear commitments in line with this framework is likely to shape their inclusion or profile at the Summit. Likely indicators for success will include, but not be limited to, new pledges or actions plans by those attending.
## Appraisal Case

What are the feasible options that address the need set out in the Strategic Case?

FCDO Ministers have confirmed their intention to host a Countering Illicit Finance Summit, and this was announced by the Foreign Secretary in his June 2025 Mansion House speech. Nevertheless, and to help assess the trade-offs, this appraisal assesses all credible alternatives to the FCDO hosting a Summit to generate a view on the effectiveness element of HMG value for money considerations.

Three options might credibly deliver the outcomes described in the Strategic Case:

1. Option A, Do nothing (Campaign only): Continue with delivering an Illicit Finance Campaign using existing staff resource.
2. Option B, Non-Summit UK Moment: For example, a UK-hosted side-event in the margins of an international meeting such as at the global Fraud Summit or UNGA in 2026.
3. Option C, UK-hosted Summit: A Foreign Secretary-convened high profile and dedicated moment to build dialogue and to cement the legacy of the Illicit Finance Campaign as directed by Ministers.

Assessment of options

The appraisal uses a multi-criteria qualitative and quantitative analysis approach to assess the options. The assessment asks the extent to which each option can:

  1. Raise the public profile of the need for action and engage key stakeholders on illicit finance.
  2. Secure political commitments from countries critical to tackling the global threat.
  3. Create platforms for dialogue and relationship-building.
  4. Profile UK leadership in convening a diverse range of stakeholders across public, private, multilaterals and civil society.
  5. Deliver affordability.
Scores against each criterion are: 0 = not fit for purpose; 2 = inadequate for purpose; 4 = slightly fit for purpose; 6 = moderately fit for purpose; 8 = mostly fit for purpose; 10 = fully fit for purpose.
The tables below summarise the analysis. Option C for a UK-hosted Summit is the highest scoring Option and therefore the recommended option.
Option A: Do Nothing (Campaign-only)

Criteria	Advantages	Disadvantages	Score
Raise the public profile and engage key stakeholders on illicit finance	A limited degree of profile and engagement will be possible via a Campaign-only approach.	A Campaign-only approach will struggle to engage with a high volume of stakeholders by mid-2026.	4
Secure political commitment from priority countries	UK bilateral dialogues could deliver a degree of political commitment from a small selection of countries.	Bilateral dialogues led by the FS are likely to be piece-meal. They are also likely to lack the impetus for broader collective statements of intent or ambition that a stand-alone and high-profile moment is likely to provide.	4
Create platforms for dialogue and relationship building	Limited to bilateral fora only.	No opportunity for multi-stakeholder dialogue and alliance-building.	2
UK leadership role in convening stakeholders across public, private, multilaterals and civil society		No opportunity to showcase FCDO leadership on illicit finance, outside Home Office co-hosting the Fraud Summit in 2026.	4
Affordability	Utilises existing resources albeit for reduced policy ambition		10
TOTAL			24

Option B: Non-Summit UK Moment (side-event on the margins of an unrelated international event)

Criteria	Advantages	Disadvantages	Score
Raise the public profile and engage key stakeholders on illicit finance	Some degree of profile and engagement would be possible.	Profile and engagement would be constrained by the limited extent to which the UK could tailor attendance, given any main event plans. A side event would be competing for profile with other side events planned on the same day or week and narrative of wider main event.	4
Secure political commitments from priority countries	UK bilateral dialogues plus a mid-level event could secure a good range of political commitments.	Would be limited to selection of attendees invited to the main meeting (out of the UK’s control) and without the ability to do significant pre-event lobbying by the UK in advance.	4
Create platforms for dialogue and relationship building	Space created for dialogue (alongside a limited set of dialogues via the Campaign)	Constraints on who the UK could invite, particularly in relation to civil society and the private sector.	6
UK leadership in convening stakeholders across public, private, multilaterals and civil society	A degree of UK leadership and convening activity could be demonstrated.	A UK side event is likely to be one of many side events hosted by different country governments. Relative UK leadership on the global stage will be challenging to demonstrate.	6
Affordability	Likely to be affordable.	Additional modest resource would be required to deliver an event. Delivery is made complex for a UK side event hosted outside the UK.	8
TOTAL			28

Option C (preferred option): UK-hosted Summit

Criteria	Advantages	Disadvantages	Score
Raise the public profile and engage key stakeholders on illicit finance	Significant opportunity to raise profile and meaningfully engage with a targeted set of stakeholders, in the run up to and during the Summit.	Increased public profile raises expectation of the pace of UK and global action. Particular challenges in profiling the pace of action in the Overseas Territories.	8
Secure political commitments from invited countries	UK lobbying well in advance is possible. The UK host can decide who to invite, significantly strengthening the prospects for securing new political commitments.	An unintended consequence of a ‘pay to play’ approach is the risk of poor attendance by important, if not like-minded, countries.	8
Create platforms for dialogue and relationship building	Space created for dialogue and potential new collaboration. UK as host can structure the dialogue to maximise prospects for delivering UK and partner priorities, especially for the long-term.	The choreography of a Summit might risk set-piece speeches, rather than genuine dialogue. This can be mitigated by the leadership and tone set on the day.	8
UK leadership in convening stakeholders across public, private, multilaterals and civil society	A stand-alone Summit hosted in the UK gives maximum prospect to profile UK leadership in convening others.		10
Affordability	This is a high ambition albeit high-cost option. No other option delivers this degree of ambition.	While the proposed £5.6 million budget is substantially below a £10 million option involving a very large venue in London, it is the costliest of the three options.	4
TOTAL			38

## Commercial Case

Based on current Ministerial steers, the Summit will be held over two days at FCDO’s Lancaster House in London. The most significant cost drivers for a programme of this type are the venue choice; special protection security services for eligible Heads of Delegation; the numbers of delegates invited; and FCDO’s approach to Summit delivery capability. These are considered in turn below.

This cost driver trend on the venue choice has been reduced to nil given the decision to host the Summit on the FCDO estate. The counterfactual of hosting in a conference centre elsewhere in London would cost in the £500k - £1.5 million range. Lancaster House can accommodate approximately 150 delegates in plenary. Other costs associated with delivering a professional event at Lancaster House, notably event production (table/seating/banners; lighting and audiovisual; branding; and possibly translation services) and catering services, will be funded by the programme budget. Events production and catering services fall within the Framework Agreements held by FCDO’s Protocol Directorate with commercial suppliers that have been selected following a competitively run process. Unit costs cannot be re-negotiated so the main commercial consideration in driving value for money will be agreeing the quantum of inputs. The Summit Team will set clear specifications to help agree a schedule of works, including by scrutinising proposed inputs and recommending decisions to the programme SRO (SCS1).

For special protection security, diplomatic convention and the assessment of threats by the relevant Metropolitan Police Service (MPS) team will determine which Heads of Delegation require special or close protection for the duration of their stay in the UK. If Heads of State/Government (HOSG) or Ministers of Foreign Affairs (MoFA) confirm attendance, they will likely be eligible for special protection. Costs will likely go up depending on the numbers of principals who are HOSG or MoFA. Heads of Delegation that are Ministers of Home Affairs or Finance are less likely to be provided with special protection. The decision on which principals to invite will be guided by policy rather than commercial considerations and the budget has been costed for a high case scenario (£1.6m). The additional costs, relative to core operations, that the MPS will face in providing general security e.g. around Lancaster House, and special protection security for principals, including the likelihood of drawing on Mutual Aid agreements with other UK police services, will be funded by FCDO. These costs will be determined by the operational decisions made by the MPS, so there are no commercial elements for FCDO to consider.

The number of delegates invited will drive costs associated with events production and catering services. Space constraints at Lancaster House will set hard limits to approximately 150 external delegates. This limit is considered affordable within the proposed programme budget. The approach to securing value for money for events production and catering services is described above.

The Summit will be designed and delivered by an in-house FCDO Summit Team in the Illicit Finance and Anti-Corruption Department. The principal cost drivers for programme funded staff are staff salaries and travel costs (£900k). By contrast, the principal cost driver for external consultants are higher fee rates and travel/subsistence costs. The preferred route for Summit delivery capability is to deliver as much as possible through a full-time FCDO Summit Team including for economy, efficiency and effectiveness reasons:

1. FCDO’s Summit Team can hold itself better accountable to Ministers by having direct control of selecting and performance managing individuals critical to Summit success. This means building a team with the right skills including on diplomatic engagement and using real-time team insights to deliver the programme’s objectives. A Summit Team is more likely to hit the ground running, saving scarce FCDO bandwidth and associated costs for other priorities.
2. As internal FCDO staff, a Summit Team will have direct access to FCDO relationships, networks, IT systems and other organisational resources including sensitive information. A successful Summit will require close collaboration of the Summit Team with FCDO colleagues in HQ (e.g. Protocol and Communications Directorates) and across FCDO’s global network of Missions. A Summit Team, compared to consultants, can quickly build good ways of working and support effective and pacy collaboration with other FCDO and HMG stakeholders.
3. In-house programme funded roles also confer authority and trust by dint of the FCDO brand. This will help staff quickly build positive relationships with HMG and external partners.
4. A Summit Team comprising FCDO staff will build new personal experiences and insights. This is a net capability gain for FCDO on an agenda of considerable importance to FCDO Ministers.

Finally, additional events will be organised within this programme to deliver structured engagement and dialogue opportunities with selected groups of stakeholders, and as part of the critical engagement needed to deliver the Summit outcomes. A very limited set of events might be delivered following the Summit and within the life of this programme to help maintain momentum in delivering Summit commitments. A series of three two-day events, co-designed and delivered by Wilton Park for approximately £100k, will conclude by November 2025. Wilton Park has a Framework Agreement with FCDO’s Strategy Directorate and the Summit Team will set a regular rhythm of partner calls with Wilton Park to track progress, risks and value for money. Other single-day events are unlikely to cost more than £20k each, and costs will depend on numbers of participants invited, choice of venue and duration (e.g. half-day or overnight stays). Decisions about the design and delivery of other events will be on an ad hoc basis with the presumption that as much as possible, including decisions on venues and catering, is delivered by the FCDO Summit Team. All decisions on spending will be within the delegated authorities set by FCDO for the Summit Team, including for its SCS1 Head of Summit Team.

## Financial Case

This business case proposes £5.6 million of RDEL, comprising £1.9 million in ODA and £3.7 million in non-ODA. Costs associated with events production, catering and security for delivering a two-day Summit will be funded by non-ODA. Staffing costs for a dedicated team to shape and deliver Summit policy outcomes and pre-Summit engagement activity will be funded by ODA. The Summit Team will explore sponsorship options to bring down costs incurred by FCDO. Sponsorship trade-offs like reputational risks and sponsor demands e.g. for prominent speaker slots or profile will shape final decisions, including seeking Ministerial steers for any high-risk options.

A detailed budget breakdown will be drawn up as programme plans flowing from Ministerial steers evolve. A summary is provided below:

Summit Staffing / Up to 11 roles for approximately 12 months, pay and travel costs. ODA. £900k
Policy development and delivery £1m / Wilton Park series of events. Further events to be determined. ODA
Summit Event Delivery. Non-ODA £3m
Contingency £0.7m / Default is non-ODA, subject to Directorate budget settlements for 26/27 / E.g. Should a major and unforeseen policing incident occur.

Value for Money (VfM)

The Summit Team will seek to drive VfM across economy, efficiency, effectiveness and equity measures. The approach to effectiveness is set out in the Strategic and Appraisal Cases. The box of UK examples below illustrate how a Summit that accelerates domestic-level policy commitments and operational capability in tackling criminal wealth alone can seed the prospects of high impact over time:

Examples of UK Impacts in Tackling Criminal Wealth / Since July 2017, the FCDO-funded International Anti-Corruption Coordination Centre (IACCC) at the National Crime Agency (NCA) has identified over £2.1bn of assets suspected to be proceeds of corruption, helped freeze £641m of stolen assets and supported the arrest of 49 suspects in grand corruption cases across multiple jurisdictions. / Since 2020, the FCDO-funded International Corruption Unit at the NCA has restrained over £441m of assets related to international corruption. Twenty-five individuals or entities have been successfully prosecuted in the UK. / In February 2024, the former Chief of Staff to the President of Madagascar, Romy Andrianarisoa, and a French associate were found guilty of seeking a bribe from Gemfields, a UK mining company, to secure licenses to operate in Madagascar. This was at the conclusion of a fast-paced covert ICU investigation. As part of the early removal scheme to ease prison overcrowding, Andrianarisoa was released and deported in July 2024. / In March 2021, £4.2million stolen by James Ibori, former Governor of Delta State, was returned to Nigeria following lengthy proceedings led by UK law enforcement agencies. These funds have been used towards four large infrastructure projects across the country, overseen by a Nigerian NGO. In July 2023, Ibori and his co-defendant, solicitor Bhradresh Gohil, were ordered to collectively pay over £128m or face additional years in prison. They are currently appealing this order.

Summit plans on shaping high impact deliverables will seek to describe these in ‘potential £m impact’ terms where appropriate. This will include profiling live UK asset recovery cases that will be concluded by the time of the Summit.

To drive economy and efficiency the Summit Team will ensure inputs are designed in a way that maximise the input/benefit interest (e.g. setting clear design specifications within FCDO to help limit the number of iterations on Summit branding options), and subsequently purchased at the appropriate quantity and price, for example:

1. Using suppliers from pre-approved frameworks where appropriate.
2. Thinking creatively about venue options for pre-events, to minimise costs whilst ensuring the location serves the Summit objectives.
3. Negotiating firmly with all suppliers about quantities and where possible (given the limited opportunity through Framework Agreements) on prices.
4. Using FCDO staff, rather than contractors, where feasible.

The approach to costings followed by this programme is comparable to other similar recent events. See also the Commercial Case.

Equity will be considered in the spread of countries invited, an assessment of the extent to which UK nations and English regions might feature, and the selection of speakers or other prominent roles at the Summit.

 Financial management, forecasting and controls

The Summit Team will ensure there is a working lead who can oversee budgets, payments and invoicing to monitor and control all expenditure and has a line of accountability to the SRO. The working lead will engage closely with IFAC’s existing financial management leads including so that expenditure is monitored and reported through FCDO’s financial reporting cycle.

This programme has been prioritised within the Directorate portfolio, including as part of the multi-year Spending Review (SR) process, and was factored into the Directorate budget plans for FY 25/26. These budget plans have been recently confirmed. The budget profile sits predominantly in FY26/27, with a proportion of the £2.6 million ODA budget likely to be spent in FY 25/26. The programme represents an increase in non-ODA spend for the Directorate.

While there is a greater likelihood of an underspend rather than an overspend, costs are expected to remain close to the forecasted budget. Any unspent funds will be redeployed for wider programmatic activity in the remainder of the financial year. The likely timing of the Summit i.e. at the start of the 26/27 financial year means that redeploying funds will be more rather than less straightforward.

There is a minor risk that programme funds are not used for the intended purpose. FCDO financial controls will apply and led by a joint effort by the Summit Team and IFAC corporate finance leads.

## Management Case

Political leadership in delivering a successful Summit will be critical. This leadership ultimately sits with the Foreign Secretary and will benefit from the active role of Minister Doughty as the FCDO Ministerial lead on this agenda. Baroness Hodge as the UK Anti-Corruption Champion will also provide important bandwidth to engage with political stakeholders. Programme accountability sits with FCDO’s Deputy Director Head of Illicit Finance and Anti-Corruption (IFAC) Department, and the full-time Deputy Director Head/SRO of the Summit Team. The Summit Team of no more than 11 officials and funded by this programme, will provide dedicated capability to shape and deliver the Summit, working closely across IFAC existing leads on the Illicit Finance Campaign, illicit finance policy and its global network of specialist advisers.

A temporary cross-HMG Board will meet regularly to advise on Summit delivery, monitor and mitigate risks (not least given the extent to which significant risks map onto HMG equities) and provide practical delivery support. This will complement the existing FCDO Board that meets quarterly to advise on the delivery of the Illicit Finance Campaign.

Information sharing processes and products will build on the existing fortnightly updates provided to Ministers. Engagement opportunities and communication products will evolve to reach general and targeted FCDO and HMG audiences, including at UK Missions overseas and at the Boards and beyond. This will help strengthen engagement and interests across a wide set of internal stakeholders and will complement a Summit Communications Plan, led by FCDO Communications Directorate, that reaches external stakeholders.

While many teams across FCDO and HMG will be critical to delivering Summit success, FCDO’s Protocol and Communications Directorates will remain priority partners for the Summit Team given their role in supporting delivery of all Foreign Secretary-hosted events. The Summit Team has built existing mechanisms to work closely with Communications Directorate. Protocol Directorate engagement will be reviewed at least 3 months preceding the Summit when events delivery activity for the Summit is expected to intensify.

Tactical or day-to-day decisions on Summit delivery will be taken by those in the Summit team closest to delivery, or else lead SCS officials. Strategic, novel or contentious/high-risk decisions will be put to Ministers. Rapid decision-making will be a critical part of delivering success: SCS leads will work closely with private offices and special advisers to help ensure delays in time-critical decisions are minimised. Scrutiny, challenge and support will be provided by Ministers, at the dedicated HMG and FCDO SCS Boards, the IFAC SLT and peers across IFAC.

Risk Management

The risk profile of this programme is Major. This is due to the significant policy ambition set for the Summit, much of which will be determined by partner country governments and of HMG Departments (i.e. out of the full control of FCDO). The principal risks relate to how far invited country governments can commitment to new and ambitious actions and the extent to which the UK can credibly project a leadership position on a global stage given its domestic track record, especially on financial secrecy in its Crown Dependencies and Overseas Territories. A further risk relates to possible poor attendance by high-level invitees. Mitigating actions include the personal engagement of FCDO Ministers, fostering effective partnerships across HMG, and the deployment of FCDO’s technical and diplomatic capability in HQ and across its global network. The Summit Team will develop and maintain a risk register to be regularly reviewed, including as part of the SCS Board governance process.

Monitoring

The Summit Team will develop a framework for action (see paragraph 18 above) to engage senior government partners. This framework will serve as the principal monitoring tool for tracking progress against the Summit’s policy ambition. This framework will sit within a Summit delivery plan covering the three main tracks of Summit delivery (Policy Deliverables; Engagement and Communications; and Operations/Logistics). These will be reviewed against an updated theory of change agreed by the SRO in September 2025. An evaluation of the programme’s success will be conducted as part of its programme closure review.