Business Case

Jordan Humanitarian and Systems Strengthening Programme (JHASS)
Jordan
March 2026

Acronyms
AAI	Accelerating Access Initiative
AG	Accountable Grant
AGA	Accountable Grant Agreement
AMP	Aid Management Platform
BE	British Embassy
BRIDGE	Building Resilience, Inclusion and Diversity through Girls’ Education
CBO	Community Based Organisation
CBSA	Country Based Staff Association
CCF	Common Cash Facility
CEDAW	Convention on the Elimination of All Forms of Discrimination against Women
CfP	Cash for Protection
CMPs	Centrally Managed Programmes
CSO	Civil Society Organisation
DAC	Development Assistance Committee
DCF	Development Cooperation Framework
DCRM	Delivery Chain Risk Maps
DDA	Due Diligence Assessment
DFID	Department for International Development
DRC	Danish Refugee Council
ECHO	Directorate-General for European Civil Protection and Civil Aid Operations
EDPG	Education Development Partner Group
EMIS	Education Management Information System
EMV	Economic Modernisation Vision
ERICC	Education Research in Conflict and Protracted Crisis
ESP	Education Strategic Plan
ESPJ	Emergency Social Protection in Jordan
EU	European Union
EWS	Early Warning System
FCDO	Foreign, Commonwealth and Development Office
FLO	Fraud Liaison Officer
FRA	Fiduciary Risk Assessment
FSP	Financial Service Provider
GBV	Gender Based Violence
GCFF	Global Concessional Financing Facility
GDP	Gross Domestic Product
GEC	Girls Education Challenge
GEMFA	Global Evaluation and Monitoring Framework Agreement
GFMIS	Government Financial Management Information System
GoJ	Government of Jordan
HCs	Host Communities
HDG	Humanitarian Donor Group
HEART	Humanitarian, Education, and Resilience Team
HMA	His Majesty's Ambassador
HMG	His Majesty's Government
IC	International Community
ICF	International Climate Finance
ICT	Information and Communication Technology
ID	Identification Document
IDF	Israeli Defence Force
IMC	International Medical Corps
INGO	International Non-Governmental Organisation
IRF	Internal Risk Facility
ISF	Integrated Security Fund
JCEP	Jordan Compact Education Programme
JDPG	Jordan Development Partners Group
JHASS	Jordan Humanitarian and Systems Strengthening Programme
JHCO	Jordan Hashemite Charity Organization
JOD	Jordanian Dinar
JOSH	Jordan Strategic Humanitarian Committee
JPP	Jordan Protection Programme
JRP	Jordan Response Plan
KPI	Key Performance Indicators
M&E	Monitoring and Evaluation
MEL	Monitoring, Evaluation and Learning
MENA	Middle East and North Africa
MHPSS	Mental Health and Psychosocial Support
MIS	Management Information System
MoE	Ministry of Education (Jordan)
MoF	Ministry of Finance (Jordan)
MoL	Ministry of Labour (Jordan)
MoPIC	Ministry of Planning and International Cooperation (Jordan)
MoSD	Ministry of Social Development (Jordan)
MoU	Memorandum of Understanding
NAF	National Aid Fund
NFE	Non‑Formal Education
NGO	Non-Governmental Organisation
NSPS	National Social Protection Strategy
OCHA	United Nations Office for the Coordination of Humanitarian Affairs
ODA	Official Development Assistance
OECD	Organisation for Economic Co-operation and Development
PER	Public Expenditure Review
PFP	Programme Funded Posts
PPA	Partnership Principles Assessment
PRO	Programme Responsible Officer
PrOF	Programme Operating Framework
PWD	Persons with Disabilities
RAB	Resource Allocation Budget
RCO	Resident Coordinator’s Office
RDEL	Resource Departmental Expenditure Limit
RSSP	Resilient and Sustainable Social Protection
SATs	Syrian Assistant Teachers
SDGs	Sustainable Development Goals
SDU	Strategy and Delivery Unit
SEAH	Safeguarding Against Sexual Exploitation and Abuse and Sexual Harassment
SEB	Severe Expenditure Basket
SR	Spending Review
SRO	Senior Responsible Officer
SRSP	Shock Responsive Social Protection
SSC	Social Security Corporation (Jordan)
SSERJ	Strengthening Societal and Economic Resilience in Jordan
TA	Technical Assistance
UK	United Kingdom
UN	United Nations
UNFPA	United Nations Population Fund
UNHCR	United Nations High Commissioner for Refugees
UNICEF	United Nations Children’s Fund
UNRWA	United Nations Relief and Works Agency for Palestine Refugees in the Near East
US	United States
USAID	United States Agency for International Development
USD	United States Dollar
VAF	Vulnerability Assessment Framework
VAWG	Violence Against Women and Girls
VFM	Value for Money
WASH	Water, Sanitation and Hygiene
WB	World Bank
WFP	World Food Programme

Glossary
Accountability to Affected Populations (AAP)	A commitment to involve crisis-affected communities in decision-making, ensure transparency, and provide mechanisms for feedback and complaints.
Assistive devices	These are technologies or equipment that enable people with disabilities to perform daily tasks, including attending school. They include hearing aids, screen readers, wheelchairs, etc
Cash Assistance	Humanitarian aid provided in the form of cash or digital transfers (primarily through mobile money and e-wallets in Jordan) to enable the most vulnerable individuals and households to meet their essential needs with dignity, choice, and flexibility.
Durable Solutions	Long-term strategies that enable displaced persons to rebuild their lives through return, local integration, or resettlement.
Gender-Based Violence (GBV)	Any harmful act directed at an individual based on their gender, including physical, sexual, and psychological abuse, often exacerbated in humanitarian settings.
Humanitarian Access	The ability of humanitarian actors to reach affected populations and deliver assistance safely and without obstruction.
Internal Risk Facility (IRF)	A flexible funding mechanism within FCDO that allows rapid allocation of resources to respond to unforeseen humanitarian needs, emerging crises, or operational risks without lengthy approval processes.
Localisation	The process of empowering and supporting local actors to lead humanitarian response and decision-making.
Non-formal Education (NFE)	Education which follows a recognised curriculum but is delivered outside of the formal system and typically targets vulnerable children who have missed out on schooling or are overage. It includes remedial education/catch-up classes and drop-out programmes.
Parallel system	A system that operates separately to a national system.
Prevention of Sexual Exploitation and Abuse (PSEA)	Measures to prevent and respond to sexual exploitation and abuse by humanitarian workers, ensuring accountability and safeguarding affected populations.
Protection	Actions aimed at ensuring the safety, dignity, and rights of individuals affected by crisis, including preventing and responding to violence, exploitation, and abuse.
Resilience	The capacity of individuals, households, and communities to withstand, adapt to, and recover from shocks and stresses.
Shock responsive social protection	A social protection system that can expand and contract the number of recipient persons or households depending on predefined triggers. It is at its core is about ensuring the early warning systems, funding, planning and targeting mechanisms exist in order to rapidly scale up the response of social protection mechanisms in times of shock. The aim is to reduce the burden on the humanitarian systems, build ownership within governments, and to offset or reduce what would otherwise have been long-term detrimental effects on the recipients through the transfers of funds during a shock or crisis. (Source: Cornealius et al, 2018, Is my social protection programme ‘shock-responsive’ or ‘adaptive’?)
Social protection	Social protection is the set of public actions that address the deprivation and vulnerabilities of the poorest, and the need of the currently non-poor for security in the face of shocks and the particular demands of different stages of the life cycle. The objectives of social protection can include reducing poverty and vulnerability, building human development and human capital, empowering women and girls, improving livelihoods, and responding to economic and other shocks. Social protection covers instruments that can fall into four categories: 1. Social assistance – non-contributory transfers in cash, vouchers, or in-kind support to individuals or households in need; public works programmes; fee waivers (such as for basic health); and subsidies (e.g. for food, fuel). 2. Social insurance – contributory schemes providing compensatory support in the event of contingencies such as illness, injury, disability, maternity/paternity, unemployment, and old age. 3. Social care services for those facing social risks such as violence, abuse, exploitation, discrimination and social exclusion. 4. Labour market programmes – includes active (promoting labour market participation) or passive (ensuring minimum employment standards) measures. Source: Carter et al (2019) Social Protection Topic Guide and O’Brien (2018) Shock-Responsive Social Protection Systems Research.
Social protection system	A social protection system can be considered at three levels: (i) the sector (mandates, policies, regulations etc.); (ii) individual programmes; (iii) delivery systems underpinning the programmes (databases, payment mechanisms, etc.). The maturity of a country's social protection system has considerable consequences for its ability to be shock-responsive. Source: O’Brien (2018) Shock-Responsive Social Protection Systems Research.
Social registries	Social registries are instruments that collect and process information on families, with the objectives of identification and socioeconomic characterisation to inform the targeting and implementation of social protection programmes. They have traditionally focused on low-income families, but many have evolved to also have broader coverage of vulnerable households who may eventually need social programmes, for example during a shock.
Unified social registry	The unified social registry refers to Jordan’s national social registry. This holds data and information on Jordanian families to inform national social protection programmes. It is located in and supervised by Jordan’s National Aid Fund.

Business Case

Summary Sheet

Portfolio/ Business/Country Plan Summary: / The British Embassy (BE) Amman’s Country and Business Plan aims to achieve: “A strategic partnership for security, growth and sustainability, supporting United Kingdom (UK) interest in a more stable less threatening region.” / Underpinning this statement are four goals: (1) Shared Security and Defence; (2) Resilience; (3) Partnership and Growth; and (4) Platform, Consular and Crisis. / This programme intends to deliver on goal 2 (Resilience) by combining lifesaving and life-changing humanitarian and education services with systems strengthening activities. These will enhance socio-economic resilience and social cohesion among refugees and vulnerable Jordanians and stability in Jordan and the region. / Through a strategic and integrated approach, it will meet immediate needs while creating sustainable improvements in national and international systems and local organisations supporting refugees and vulnerable Jordanians. This makes it the most effective and efficient pathway for supporting refugees and vulnerable Jordanians and enhancing UK impact in Jordan.

Title: Jordan Humanitarian and Systems Strengthening Programme (JHASS)
Programme summary: Jordan hosts the world’s second highest refugee population per capita. According to the Government of Jordan (GoJ), the non-Jordanian population including refugees of all nationalities, asylum seekers, and migrants is estimated to be approximately 3.7 million people, 31.5% of the total population in Jordan. This includes 458,246 refugees registered[1] with the United Nations High Commissioner for Refugees (UNHCR), most of which are Syrian; those not registered; and approximately 2.4 million Palestinian refugees. / JHASS is a strategic and integrated programme designed to: (1) assist refugees living in Jordan and vulnerable Jordanians to meet their basic needs, while (2) pursuing strategic and sustainable improvements to Jordan’s national systems, international humanitarian systems and local organisations supporting refugees and vulnerable Jordanians[2]. / The programme has three pillars: / 1) Core humanitarian assistance - including cash assistance, protection services, support for refugees who wish to return to Syria, and an Internal Risk Facility (IRF). / 2) Education support - including contributions towards the costs of including refugees in the national education system and contingency support for refugee camp schools; and / 3) Systems strengthening support for the humanitarian, education and social protection sectors. / The intended impact is enhanced socio-economic resilience and social cohesion among refugees and vulnerable Jordanians, supported by inclusive systems and contributing to long-term stability in Jordan and the region. / In the longer term, the programme includes a strategy to reduce the financial burden of refugees on Jordan and sets out a responsible partial exit from UK humanitarian support in Jordan. / The programme will be overseen by a clear and robust governance structure and managed by an appropriately resourced FCDO team which includes advisory expertise in each of the sectors. / Delivery will be through only six core implementing partners, which represents a streamlining in BE Amman’s humanitarian partnerships, to reduce programme administration. We will regularly review delivery and remain prepared to reprioritise or stop funding partners where results are not achieved, ensuring accountability and value for money.
What is the rationale for UK Aid spending? / Jordan remains a reliable regional ally and strategic partner in counterterrorism, diplomacy, and global security, with its stability essential to UK national and broader security interests. Continued support for refugee hosting will meet critical humanitarian needs and support stability. Through this, the programme will deliver against the FCDO’s priorities of development and security. / The programme will also deliver the secondary benefit of contributing to the UK Foreign Secretary’s commitment to tackling Violence Against Women and Girls (VAWG) and also has the potential to support FCDO’s migration priority. / This programme responds to the United Nations (UN) Sustainable Development Goals 1, 2, 3, 4, 5, 10 and 13, the Jordan Response Plan, the Regional Refugees and Resilience Plan, and the Jordan Compact[3]. / The programme offers strong value for money by building on demonstrated progress in strengthening systems in Jordan and productive collaboration with the GoJ to achieve positive outcomes for refugees and vulnerable Jordanians. For example, partnerships between the UK, Jordan and other donors have enabled an entire generation of Syrian refugees to access the public education system, avoiding the need for a costly parallel education system. Partnerships have also driven improvements in the education system such as ensuring the inclusion of refugees and other vulnerable groups in key policies and strategies. UK support on social protection has also driven sustainable improvements in national systems and helped catalyse further reform plans. A recent Fiduciary Risk Assessment (FRA) assessed the GoJ’s public financial management and provided assurance that (off budget) financial aid remains a viable option in this country.
Programme Value:	Up to £73 million
Department/Country Office confirmation of review processes	Approved by His Majesty’s Ambassador (HMA) and Deputy Head of Mission and Development Director BE Amman
Contact name	Deputy Development Director BE Amman
Threshold for final approval of Business Case:
Date of Approval of Concept Note:	20/06/2025	Name and role of Approver: / Minister for Middle East, North Africa, Afghanistan and Pakistan / Minister for International Development, Latin America and Caribbean
Date of Approval of Business Case:	12/03/2026	Name and role of Approver / Minister for Middle East, North Africa, Afghanistan and Pakistan / Minister for International Development and Africa
Programme Code: 400552	AMP Start Date: / 1 April 2026	AMP End Date: / 31 March 2030
Overall programme risk rating:	Moderate
[1] https://data.unhcr.org/en/country/jor
[2] This programme does not specifically target Palestinian refugees, most of whom hold Jordanian citizenship. Support for Palestinian refugees is provided through the United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA), which receives funding under FCDO’s Palestine programme managed by British Consulate General in Jerusalem. This includes UNRWA’s operations in Jordan.
[3] The Jordan Compact (2016) is a landmark agreement that linked international support to Jordan’s commitment to provide Syrian refugees with access to jobs, education, and services, while strengthening the country’s economic resilience. For more information see here: https://www.refugee-economies.org/our-work-16-21/innovative-practices/jordan-compact

Strategic Case

STRATEGIC FIT
The Jordan Humanitarian and Systems Strengthening programme (JHASS)[4] will deliver on goal 2 (Resilience) of Jordan’s Country and Business Plan. It will contribute to this goal by enhancing the societal and economic resilience of refugees and vulnerable Jordanians and increasing social cohesion, as well as supporting stability in Jordan and the region. It will do this through a strategic and integrated approach which includes:
[4] JHASS sounds like the Arabic word جهاز (Jihaz) which means ‘systems’.
1. Core humanitarian assistance - providing inclusive lifesaving and life-changing support to meet the basic needs of refugees and vulnerable Jordanians, maintaining wellbeing, improving sense of safety and contributing to stronger community relations. This will be delivered through cash assistance, protection, supporting voluntary returns to Syria and an IRF.
2. Education support – supporting the GoJ to maintain inclusion of refugees in the national education system and complete the transition of education services in refugee camps from the UN to the Ministry of Education (MoE).
3. Systems strengthening support - providing technical assistance (TA) for the social protection and education sectors, and deployments in the humanitarian, education and social protection sectors. This combined with policy leadership from BE Amman’s technical experts will create sustainable improvements in systems supporting refugees and vulnerable Jordanians, promoting human development, social cohesion, and resilience against future crises.

Support to humanitarian assistance strengthens the UK’s partnership with Jordan by fostering sustainability[5], security[6] and regional influence, and closely aligns with our regional humanitarian response. JHASS will support the delivery of the UN Sustainable Development Goals (SDG) 1, 2, 3, 4, 5, 10 and 13, the Regional Refugees and Resilience Plan, National Social Protection Strategy (NSPS) 2025-2033, Education Strategic Plan 2026-2030, and is consistent with the approach set out by the UK and others in the Jordan Compact and with the Jordan Response Plan.
[5] Lakner et al (2020) How much does reducing inequality matter for global poverty? WB Global Poverty Monitoring Technical Note No. 13; June 2020; p. 18.
[6] Rodrik, D., (1999), ‘Where Did All the Growth Go? External Shocks, Social Conflict, and Growth Collapses.’ ‖Journal of Economic Growth, Vol. 4, No. 4, pp. 385–412.

The identified needs go beyond service delivery; they require a strategic and integrated programme that combines core humanitarian assistance (to meet both basic and protection needs), education support, and systems strengthening. JHASS takes a coordinated, holistic approach with built in flexibility - through an IRF to adapt to shocks - and strong focus on localisation to ensure principled and context specific delivery. Without an integrated, multisectoral approach combined with policy-level engagement, results risk being short-term and resource-intensive; with them, the UK will achieve immediate impact alongside long-term sustainability.

HOW THE PROGRAMME CONTRIBUTES TO FCDO AND UK GOVERNMENT PRIORITIES
This programme will deliver against the FCDO’s ‘development’ priority. FCDO has prioritised under “development”: humanitarian, global health and climate and nature with a push into the multilateral space, including the international financial institutions and leveraging finance. This programme makes an important contribution in the ‘humanitarian’ area by meeting pressing humanitarian needs in Jordan. It will do so in a manner aligned with FCDO’s overarching humanitarian priorities[7] which seek to:
[7] Humanitarian Guidance for the Resource Allocation Round, Delivering on the humanitarian reset at Post, in regions and in HFRD. Internal document.
Prioritise people in greatest need and provide them with what they need the most.
Protect those most at risk, including from gender-based violence (GBV); and
Prevent and anticipate future shocks and build resilience in long-running crises.
It will align with these overarching humanitarian priorities through its strategic and integrated approach by: focusing our support to those most in need using established needs assessments; protection activities; and pursuing systems strengthening activities to enhance the shock responsiveness of national social protection systems and Jordan’s humanitarian sector’s crisis preparedness, going beyond service delivery and promoting sustainability.

This programme aligns with the four essential shifts FCDO is making to its development portfolio as follows:
- From donor to investor –we will strengthen private sector investment in the public/national education system by offering UK technical expertise and mechanisms to enable effective collaboration. We will contribute to Jordan’s economic reform vision by leveraging multilateral financing to support the implementation of Jordan’s new NSPS.
- From service delivery to system support – the programme combines lifesaving and life-changing service delivery with strategic systems strengthening support to the humanitarian, education and social protection sectors to embed sustainable improvements in national and international systems supporting refugees and vulnerable Jordanians. Systems strengthening activities will increase as a proportion of the budget throughout the programme.
- From grants to expertise – through targeted TA and deployments, complementing BE Amman’s policy leadership from technical experts, the programme will provide high-quality expertise to the GoJ. We are stopping direct financial aid for the social protection sector pursued under previous programmes, focusing support in this sector on systems strengthening via TA and deployments. We will seek to further leverage our connection to UK expertise, including working with universities and the edtech sector to support Jordan in modernising the education sector.
- From international intervention to local provision – we will engage with local Non-Governmental Organisations (NGOs) to deliver protection services and enhance local capacities and leadership so that local actors are at the heart of our response. We will strengthen the capacities of the GoJ to deliver education and social protection services.

It aligns with FCDO’s principles for delivering development. The programme puts country-led partnership at its heart. GoJ priorities have played a key role in shaping the design of activities, for example priorities under the GoJ’s NSPS 2025-2033 and the National Education Strategic Plan 2026-2030 (ESP) have directly informed social protection and education systems strengthening activities. Similarly, it supports FCDO’s strengthened approach to enhancing multilateral impact, supporting multilateral reform in Jordan, focusing on UN humanitarian actors. Local insights will be fed back to central FCDO multilateral teams to support their engagement.

It will deliver against FCDO’s ‘security’ priority, through supporting Jordan’s domestic stability and regional stability. It will promote social cohesion between all nationalities, with a focus on Syrians given their significant presence and Jordanians, reduce poverty and inequality and strengthen the social contract. Jordan is a key UK partner in the Middle East, offering a stable and credible platform for advancing UK foreign policy objectives in a volatile region. Its strategic location - bordering Israel, Palestine, Syria, Iraq, and Saudi Arabia - places it at the heart of dynamics that directly affect UK national interests. Jordan’s domestic stability remains critical for regional security and upstream migration management, and UK security, defence and diplomatic engagement.
Secondary Benefits
The programme will support the UK Foreign Secretary’s commitment to tackling VAWG through pursuing GBV prevention and response as part of protection activities. It will be informed by best buys research and evidence from what works in prevention and response to VAWG including from Jordan’s previous programming.

It has the potential to support “migration” as a strategic priority. Jordan hosts approximately 3.7 million refugees (of which 2.8 million are registered)[8]. Jordan’s geographic and political positioning makes it a frontline state in managing the impacts of regional crises and in responding to any further displacements e.g. from the West Bank or Syria. Syrians were among the top five nationalities arriving on small boats to the UK in the year ending June 2025. The provision of humanitarian support to refugees in Jordan – particularly Syrians - will address drivers of onward migration and aligns with UK efforts to manage irregular migration at source and deter migration. The programme will also facilitate voluntary returns of Syrian refugees, including by supporting informed decision-making, ensuring returns are safe, dignified, and sustainable where conditions permit. Current evidence[9] suggests that targeted interventions, as described in this programme, have the potential to have a positive impact on reducing irregular migration over certain timeframes. The programme will adapt according to emerging evidence including locally focused data[10] to maximise benefits and will also look to further build the evidence base.
[8] Refer to page no.1/ programme summary for details around total number of refugees in Jordan.
[9] FCDO Internal Paper, *Irregular Migration – Killer Facts, Evidence and Myth Busters*; Axel Dreher et al., “The Effects of Foreign Aid on Refugee Flows,” accessed December 15, 2025, https://www.sciencedirect.com/science/article/pii/S0014292118301958; Khalid Koser and Katie Kuschminder, “Understanding Irregular Migrants’ Decision-Making Factors in Transit,” 2016.
[10] BE Amman is conducting a migration intentions survey and analysis starting January 2026 to identify key drivers and deterrents of migration among Strengthening Societal and Economic Resilience in Jordan (SSERJ) programme beneficiaries and to assess the influence of programme interventions through an independent commissioned research supplier.
CONTEXT
Jordan hosts the second-highest number of refugees per capita globally, placing significant pressure on water, health, education[11], and natural resources[12]. According to the GoJ, the non-Jordanian population including all refugees, asylum seekers, and migrants is approximately 3.7 million. This includes approximately 2.4[13] million Palestine refugees registered with the United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA). The GoJ also reports around 1.3 million Syrian refugees[14] although this figure is difficult to verify and is likely to be considerably inflated. There are 458,246[15] refugees registered with UNHCR, 93% of whom are Syrian, alongside Iraqis, Yemenis, Somalis, Sudanese, and others. Most refugees live in Host Communities (HCs) (82%), with the remaining refugees (18%) living in camps. This complex demographic underscores the need for differentiated approaches: while UNRWA mitigates strain for Palestinians, the Syrian caseload continues to drive humanitarian needs and fiscal pressure on Jordan’s national services. UNRWA’s operations in Jordan are supported by the British Consulate General in Jerusalem while BE Amman focuses on supporting Syrian refugees in Jordan.
[11] Rauschenberger E & T Sabella (2023) Taking Stock in Jordan: The evidence landscape and gaps in Jordan’s educational response to the Syrian refugee crisis. Queen Rania Foundation
[12] Vulnerability Assessment Framework: Socio-Economic Survey on Refugees in HC-UNHCR June 2024
[13] https://www.unrwa.org/where-we-work/jordan, UNRWA registered refugees
[14] Jordan Response Plan 2023
[15] UNHCR Jordan Data Portal as of 30th November 2025 (For the most up-to-date refugee statistics, please refer to the latest figures available here. Country - Jordan)

The GoJ has taken considerable measures to respond to the needs of Syrian refugees, delivering a significant global public good. Jordan has dedicated resources to supporting refugees and has, to date, bore the largest burden[16]. However, it has also had to balance support with domestic stability while managing constrained public resources. Consequently, this has led to Jordan allowing refugees to continue to live in Jordan but with only partial inclusion in national life. Refugees can access the public education system (supported in part by donors). They can also access parts of the national social protection system (they can access social care services and participate in social insurance if working formally but not tax-financed social assistance for the poorest through the National Aid Fund). Access to the labour market remains tightly controlled, with Syrian refugees only allowed to work in occupations traditionally dominated by migrant labour such as construction and agriculture with some access to manufacturing and services). This limited access and a recent increase in work permit fees has pushed a large number of refugees into the informal labour market where there is a reasonably high demand often facing lower pay, lack of legal protection, and heightened vulnerability.
[16] Hoogeveen, Johannes, and Chinedu Obi, eds. 2024. A Triple Win: Fiscal and Welfare Benefits of Economic Participation by Syrian Refugees in Jordan. International Development in Focus. Washington, DC: World Bank. doi:10.1596/978-1-4648-2107-3. License: Creative Commons Attribution CC BY 3.0 IGO

Jordan has been supported by the international community (IC) in hosting refugees through cash assistance, support to refugee camp operations, and enhancing and expanding services that both refugees and HCs can receive, e.g. education.

The Jordan Compact, agreed in 2016, determined how refugees would be hosted in Jordan. It was an agreement between the GoJ and the IC to combine humanitarian aid with long-term development support to Jordan in response to the Syrian refugee crisis[17]. The UK played a leading role in its establishment. The humanitarian assistance component was designed to be predictable, flexible, and aligned with Jordan’s national priorities outlined in the Jordan Response Plan (JRP)[18]. It recognised that the majority of refugees settled in impoverished communities. As such the Compact sought to mobilise support for both refugees and HCs to ensure all benefitted equitably. This became a condition for international assistance. In return for hosting refugees the GoJ committed to expand access to the national education system and to allow some formal employment for Syrian refugees to promote self-reliance.
[17] Barbelet, V., Hagen-Zanker, J., & Mansour-Ille, D. (2018). The Jordan Compact: Lessons learnt and implications for future refugee compacts. Overseas Development Institute. https://media.odi.org/documents/12058.pdf
[18] Jordan Response Plan, https://www.jrp.gov.jo/

The Compact has had important successes. In education, it mitigated the need for a parallel education system for refugees and ensured that an entire generation of Syrian children were not excluded from learning opportunities and recognised certification. Continued support has led to the near complete transfer of education services from the UN to the MoE, as well as clear indicators around refugee inclusion in the ESP. It also enabled refugees to participate in certain – all be it limited - parts of the labour market and benefit from a waiver from work permit fees for some years.

Despite some inclusion in national systems since 2016, there has been a shift in the political economy. Declining levels of aid, a shift towards the GoJ in terms of the burden-share, coupled with slow levels of growth, high public debt (90% of Gross Domestic Product (GDP))[19], high levels of unemployment (and perceptions that refugees are causing this)24 and increasing volatility in the region, has pushed the GoJ to take several actions which have disadvantaged Syrian refugees. These have included a reversal in previously waived fees for work permits and a U-turn on a commitment to take over camp school operational costs, although recent dialogue with the MoE has indicated there is some room for discussion on the latter.
[19] IMF Country Report No. 24/34, https://www.imf.org/en/Countries/JOR

Jordan’s stability is vital for the region. As noted above, Jordan’s domestic stability underpins regional security, supports upstream migration management, and enables UK security, defence and diplomatic engagement in the Middle East. Jordan’s stability has become under increased strain in recent years: the Israel-Hamas war since 7 October 2023, along with related wider conflicts, has had direct repercussions on the region including Jordan. Conflict continues to pose risks to Jordan’s stability and security from both being caught in the crossfire and/or being undermined by the aftereffects - including risk of further migration into a country where, according to GoJ, already approximately 1 in 3 people is a refugee.

1. Jordan is a small resource-scarce country, with high exposure to exogeneous shocks, and dependency on external actors. Unemployment remains high at 21.4% among Jordanians, (disproportionately represented by youth (46.1%) and women (30.9%)[20]) with 44% of employment in the informal sector[21].
  [20] Jordan Overview: Development news, research, data | WB
  [21] Data source: Department of Statistics
2. Strains in social cohesion have emerged due to economic pressures and perceptions around resource access and employment. Tensions have grown in the last two years following policy changes that raised work permit and social security costs for refugees amid high unemployment. Misconceptions about job competition also persist despite evidence to the contrary. The GoJ continues to work with international partners to ensure HCs benefit from humanitarian aid and to maintain stability.

Changes of the US administration have had impact. Jordan has done well to retain it’s $1.45 billion US annual contribution: approximately 3% of Jordan’s GDP, and provided mostly as budget support and military assistance. However, US humanitarian and development funding has been reduced, particularly in the health and protection sectors with particular impact on smaller NGOs that were already struggling with short term funding. This has been further magnified by US aid cuts at the global level, which have affected UN agencies and contributed to programmatic and sectoral UN cuts in Jordan—especially in food, protection and health services. The resulting gaps risk reversing development gains, weakening community resilience, and undermining efforts to maintain stability in HCs.

UNHCR’s June 2025 survey tells us that 80% of registered Syrian refugees in Jordan intend to return to Syria one day, but only 22%[22] within the next year. The fall of the Assad regime in Syria offers hope for refugees returning to Syria, but the reality of ongoing instability, lack of basic services[23] and livelihood challenges in Syria, mean that returns from Jordan are a minority of the registered refugee population. Currently, 72% of registered Syrian refugees, as well as a smaller number of registered non-Syrian refugees, remain in Jordan[24]. Almost half of Syrian refugees in Jordan are from Southern Syria, mainly Daraa and Suwayda, where intercommunity conflict and Israeli Defence Force (IDF) activities continue to foster an unstable security environment. Ongoing volatility may force further displacements. In a favourable scenario, safe, dignified and rights-based return and reintegration of Syrian refugees would be possible, and the programme is designed to support conditions for their voluntary, safe, and dignified return, while continuing to prioritise urgent needs within Jordan[25].
[22] This percentage (22%) is lower than the 40% reported in UNHCR’s January 2025 survey. This could be due to people having already returned or people reconsidering because of the security situation in Syria.
[23] 40% or 8000 schools of education infrastructure (FCDO Syria reporting).
[24] Number of registered Syrian refugees – UNHCR Voluntary Returns Dashboard, Number of registered refugees in Jordan, before the fall of Assad External Statistical Report on UNHCR Registered Refugees and Asylum-Seekers Jordan as of 30 Nov 2024 (619,559 Syrian refugees)
[25] FCDO’s approach to voluntary returns to Syria, reflects this volatility. It seeks to ensure refugee decisions to return are informed and voluntary and FCDO will work with FCDO Syria Office and regional UNHCR office to ensure returnees are monitored.

Despite expectations of Syrian refugees returning to their home country, there is growing concern that those who remain in Jordan may face increased neglect. This is due to the IC shifting its focus toward Gaza and other global emergencies, coupled with a decline in international humanitarian aid.

Wider regional instability: Syria is not the only concern. A worst-case scenario could see Jordan receive refugees from neighbouring countries – including from Palestine. This could be a significant threat to Jordan and risks undermining its economy, infrastructure and social stability.

The UK has been one of Jordan’s most consistent partners, irrespective of fluctuating funding. This programme reaffirms the UK’s commitment to supporting refugees and vulnerable Jordanians, with a focus on inclusivity. Despite reduced UK humanitarian financing[26], the combination of elements (including cash, expertise, system strengthening) will make a real impact against both GoJ and UK priorities. Although the size of our financing is small when compared against GoJ’s expenditure and financing from other donors such as the US and the EU, the UK is prioritising its finance on humanitarian support and on Syrian refugees, something which the GoJ’s budget doesn’t do, although as noted above it does make a significant contribution, and US support has reduced particularly for protection activities.
[26] [Our financing will be lower than previous years. For example, education spend is approximately 18% lower in year 1 than the previous year. This is partly reflective of reducing refugee numbers.]

SCALE OF NEEDS IN JORDAN

Poverty and food insecurity

Vulnerability analysis indicates growing levels of poverty and food insecurity amongst refugees, driven by reduced cash assistance and lower access to the labour market. Poverty rates among refugees in communities and camps have spiked from 57% to 67% over the past two years[27]. In Jordan, food insecurity among refugees remains high. As of the fourth quarter of 2024, 83% of refugees in HCs and 81% of camp beneficiaries were classified as severely or moderately food insecure, despite a slight improvement compared to the fourth quarter of 2023. This deterioration follows WFP and UNHCR funding cuts and transfer value reductions since mid-2023. Compared to pre-cut levels in the second quarter of 2023, the proportion of moderately food insecure households has surged, from 35% to 65% in HCs and from 26% to 56% in camps. Refugees have coped by reducing food intake and relying on less preferred or cheaper foods. Debt remains a critical concern: although new borrowing stabilised in the fourth quarter of 2025, average accumulated household debt still stands at around 1,200 Jordanian Dinar (JOD) (approximately 1,700 United States Dollars (USD)[28]), with rent and food being the primary reasons for borrowing. These trends underscore the urgent need for sustained humanitarian assistance to prevent further deterioration in refugees’ food security and economic resilience[29].
[27] Socio-economic Survey of Refugees in Host Communities 2024
[28] Based on exchange rate on 14 December 2025.
[29] UNHCR Socio-economic Update on Refugees in Jordan – Q4 2024 and Food Security Outcome Monitoring (FSOM), Special Edition Quarter 3 | 2025

Figure 1: Food insecurity is alarmingly high among refugee population, source WFP 2025
`

Protection threats

Refugees in Jordan are exposed to constant protection threats. With limited livelihood opportunities and difficult access to healthcare, higher education and housing[30], they face issues including eviction, child labour, or detention due to problems with their registration status, documentation gaps, and financial stress. These threats lead to negative coping strategies for the most vulnerable including child labour and early marriage and can increase risk of violence against women and children. Issues such as documentation gaps, debts, legal complications or custody issues can pose challenges and barriers to returning to Syria.
[30] ISWG Jordan Refugee Response 2024-25 Strategy.pdf

Gender-based violence remains a significant issue in Jordan. According to the 2023 Jordan Population and Family Health Survey[31], 13% of ever-married[32] women reported experiencing physical violence since the age of 15, and 18% of ever-married women aged 15–49 have experienced physical or sexual violence. Alarmingly, more than half of these women did not seek any form of help, highlighting a significant gap in reporting and access to support services. This low reporting rate underscores the urgent need to strengthen survivor-centred protection mechanisms and improve awareness and trust in available services.
[31] https://dosweb.dos.gov.jo/DataBank/Population/Health/DHS2023_Survey.pdf, page 342
[32] The term “ever married women” refers to women who have ever been married at any point in their lives, regardless of their current marital status.

VAWG remains normalised and in some cases justified as in many countries worldwide. It’s deeply rooted in socio-cultural norms that perpetuate gender inequality and harmful social norms including beliefs that about men’s entitlement and privilege over women. According to the Jordan Population and Family Health Survey, 69% of men aged 15-49 agree that wife beating is justified under certain circumstances[33][34]. Addressing these challenges requires targeted interventions to shift harmful social norms through working with grassroot organisations[35].
[33] See, CEDAW General recommendation No. 19 on violence against women (1992). para. 6. See also, General recommendation No. 35 on gender-based violence against women, updating general recommendation No. 19. CEDAW/C/GC/35 (2017). para. 1. See, General recommendation No. 19 on violence against women (1992). Para 19.
[34] Concluding observations on the sixth periodic report of Jordan. CEDAW/C/JOR/CO/6 (2017), para. 29.
[35] Concluding observations on the sixth periodic report of Jordan. CEDAW/C/JOR/CO/6 (2017).

Children are also exposed to violence. Based on United Nations Children’s Fund (UNICEF)’s study on violence reports 74% of children (79% boys) have experienced at least one form of physical violence in their lifetime[36]. Child marriage persists, especially among refugees[37]. At the national level, 8.5% of marriages (2023), and in Zaatari and Azraq refugee camps, between 50-60% of all registered marriages are child marriages[38].
[36] UNICEF, National Study on Violence against children in Jordan, 2019-2020
[37] UNFPA Jordan | UNFPA 10th Country Programme (2023-2027)
[38] Sharia court in Azraq and Za’atari camps (2020)

Jordan’s national social care systems provide protection services (e.g. support for GBV victims, vulnerable children) for people in need, including refugees. However, there are pressures on national social care services and limited capacity to meet needs, as such the GoJ has indicated that given current pressures this is a sector where support from civil society, including through donor financed programmes, is necessary and welcome. Unregistered refugees can also sometimes experience difficulties in accessing public services pointing to the need for additional services at present.

Jordan has one of the youngest populations globally, with an alarmingly high youth unemployment rate of 46.1% and a decrease in access to education, training, and employment opportunities. These barriers are exacerbated for refugees, who also face economic constraints and cultural stigma. Moreover, adolescents and youth seem particularly affected by mental health and psychosocial issues, as highlighted by a multi sectoral needs assessment published by the International NGO (INGO) International Medical Corps (IMC) in 2024[39]. This highlighted that mental health disorders, including depression and anxiety, significantly affect Jordanian youth aged 10-19, with 16.3% of adolescents experiencing these conditions. A recent school-based survey[40] reported higher rates, with 24.5% having anxiety symptoms, and 16.6% major depressive disorder symptoms. According to the IMC the main barriers to accessing Mental Health and Psychosocial Support (MHPSS) include lack of knowledge about service location, high costs, transportation issues, fear of stigma, and perceived unavailability of services.
[39] MSNA IMC Jordan: IMC 2024
[40] Frontiers | Psychosocial, emotional and behavioural problems, quality of life, and mental health care seeking behaviours among children and adolescents in Jordan: a national school-based survey

The figures and information above highlights that a coherent humanitarian response needs to prioritise support for the most vulnerable refugees through life-saving cash assistance, complemented by targeted protection interventions. Cash assistance is essential for meeting urgent needs and it needs to be combined with protection measures to ensure dignity, safety, and long-term wellbeing while national service provision can’t sufficiently meet these needs.

Limited employment opportunities

Refugees face limited access to formal employment limiting self-reliance, increasing risk of informal migration to third countries and the ability of the UK to exit humanitarian aid in Jordan. Since July 2024, Syrians do not have a waiver on work permit fees[41], making formal employment very difficult for many (employers find it too costly and refugees can’t afford to pay themselves), leading to reducing rates of employment[42] and exposure to the protection concerns of informal work, e.g. work hazards, low pay, and abuse[43]. Syrians were one of the top five most common nationalities arriving on small boats in the UK in the year ending June 2025, accounting for 9% of arrival via small boats, and were the fourth highest nationality of irregular migration to the UK[44]. This data doesn’t outline the route they took, and there is limited information on onward migration trends from Jordan, largely due to the irregular nature of these movements. Lack of opportunities for self-reliance, combined with the closure of the NAF to refugees, which provides tax-financed social assistance for the poorest, limits options for the IC to exit humanitarian aid.
[41] As of July 2024, following the closure of the WB project in January 2204, fees for foreign workers now apply to Syrian refugees with a cost set at 425 JOD plus 85 JOD for required medical tests (previously waived), with an issuance fee of JOD 50 for flexible work permits. Only 14% of Syrian refugees in HC, and 13% of Syrians in camps who are earning income reported having a work permit (Source: UNHCR Socio-Economic Update on Refugees in Jordan – Q4 2024). Non-Syrians cannot get a work permit without giving up their refugee status)
[42] UNHCR Socio-Economic Update on Refugees in Jordan – Q4 2024
[43] Socio-economic Survey of Refugees in Host Communities 2024, Rates of hazardous work and workplace abuses were already high including exposure to workplace hazards and abuse. for Syrian refugees in communities, 82% of those working experience at least one workplace hazard such as exposure to dust fumes or extreme temperatures and 66% experience at least one workplace abuse such as getting paid less than the minimum wage or salary delays.
[44] UK Government, “How Many People Come to the UK Irregularly,” Immigration System Statistics: Year Ending June 2025, accessed December 15, 2025, https://www.gov.uk/government/statistics/immigration-system-statistics-year-ending-june-2025/how-many-people-come-to-the-uk-irregularly.
Vulnerability to climate change
Jordan’s vulnerability to climate change is a significant driver of humanitarian need. Climate shocks and environmental degradation intersect with fragility impacts and disproportionately impact the most vulnerable communities. Refugees and vulnerable Jordanians[45] face heightened exposure to climate-related shocks, including flash flooding, extreme heat, and water scarcity. These risks compound existing vulnerabilities and undermine coping capacities, particularly in informal settlements and camp settings. Nearly 40% of refugees in camps experience severe climate vulnerability. 78% of refugees in Zaatari camp have been affected by leakages and flooding[46] mainly due to the poor condition of in-camp shelters. For refugees and vulnerable Jordanians, increased recurrences of flash flooding will make living conditions even more difficult especially in informal settlements[47]. In rural areas, over 70% of smallholder farmers are vulnerable to climate shocks such as drought and erratic rainfall[48].
[45] National Climate Change Policy of the Hashemite Kingdom of Jordan 2022-2050
[46] UNHCR (2024), Vulnerability Assessment Framework: Socio-Economic Survey of Refugees in Camps
[47] Updated submission of Jordan’s 1st nationally determined contribution (ndc) October 2021
[48] The National Climate Change Adaptation Plan of Jordan 2021
Inequity in, and limited access to, the provision of services including education
The large influx of refugees since 2011 has strained Jordan’s education system and there is significant inequity in provision of services. Nearly half of refugees in Jordan are under 18 (47.1%)[49], with many refugee children born in Jordan, placing pressure on Jordan’s education system. Approximately 10% of the school-aged population are Syrian refugees[50]. To accommodate this number, the MoE has expanded double shift schooling and employed temporary teachers for camp schools and in second shifts for Syrians. While this has been effective in meeting the demand, contact hours and access to experienced teachers are more restricted in these settings creating inequity.
[49] UNHCR, External Statistical Report on UNHCR Registered Refugees and Asylum-Seekers Jordan as of 30 June 2025
[50] UNHCR. (2025b). Regional Flash Updates 16 Syria Situation Crisis. https://reporting.unhcr.org/syria-situation-crisis-regional-flash-update-16

It currently costs the GoJ approximately £200m per annum to educate 160,000 refugees through the national education system. Although this remains a burden-sharing relationship, only 27% of the cost was covered by donors during the 2024/25 academic year, and despite rigorous prioritisation and interventions targeting efficiency and effectiveness, the MoE has been unable to increase resources for equitable quality improvements due to the continued high demand for access. This has led to declining learning outcomes across the board in public education. And while education quality in Jordan, remains broadly in line with quality found in middle income countries, combined with the limited number of skilled job opportunities, these two variables are pushing vulnerable groups to drop out of school and seek low skill work and are increasing child begging and early child marriage.

Limited social protection coverage due to challenges with the labour market and the continuously changing nature of jobs in the economy creates vulnerabilities to shocks, contributes to poverty and inequality, and undermines stability. In 2022, only 45.2% of the population were covered by any form of social protection, which is closely linked to challenges in the labour market (e.g. high levels of unemployment and informality). To build resilience and reduce poverty, Jordan needs a more comprehensive, inclusive, and shock-responsive social protection system. Strengthening this system would support the Economic Modernisation Vision (EMV) 2022–2033 and NSPS[51] by building human capital/human development, increasing productivity, and helping families manage economic fluctuations and maintain consumer spending thus contributing to economic stability[52]. It will further contribute to stability since enhanced social protection, alongside quality education, will equip individuals with the resilience and skills to adapt to changing labour markets, thus supporting social cohesion. Jordan’s NSPS (2025–2033) is based on four pillars: ‘dignity’ through social assistance, ‘empowerment’ via access to essential social services (including social care and protection services), ‘opportunity’ through decent work and social security, and ‘resilience’ to shocks and crises and has strong political buy-in by the GoJ. Enhanced social protection systems can also promote stability by reducing poverty and inequality, strengthening cohesion between different groups which interact through it including refugees and Jordanians, and strengthening the social contract between the state and its citizens[53].
[51] Jordan's National Social Protection Strategy (2025 - 2033) | UNICEF Jordan
[52] 2 The dates of the new NSPS (2025-2033) have been set to align with the dates of Jordan’s EMV (2022-2033) to better highlight the linkages and contribution of social protection to the achievement of the EMV. The contribution of social protection to the EMV and economic stability is highlighted in a key draft Government strategic document FCDO has seen. The strategy has Royal Patronage by His Majesty King Abdullah highlighting the political importance of the strategy to the Government
[53] Loewe, Markus, and Tina Zintl. 2021. State Fragility, Social Contracts, and the Role of Social Protection: Perspectives from the Middle East and North Africa (MENA) Region. Social Sciences 10: 447. https://doi.org/10.3390/socsci10120447 Loewe and Zintil note: ‘Social protection is always a key element of government provision and hence a cornerstone of all social contracts’ and ‘social protection can be a powerful instrument to reduce state fragility and mend social contracts’.

Supporting vulnerable Jordanians also supports stability through building social cohesion. Many refugees live in HCs, that themselves face poverty and vulnerability. Analysis[54] shows that poverty amongst Jordanians was likely to have increased by 21.5% during 2020, implying an overall increase in poverty from 15.7% up to 37.2%[55]. Although poverty levels have fallen since the peak of the pandemic, they are thought to still be higher than pre-COVID levels and to have been exacerbated by rising living costs. Jordan’s population is also highly exposed to economic and climatic shocks; with estimations that one-third could be affected by adverse events[56]. These shocks, though appearing transitory, can potentially have lasting impacts due to harmful coping strategies and affect their ability to respond to risks. Helping vulnerable Jordanians, including through social protection and humanitarian protection services, enabling refugees to continue to access the national education system in HCs, and community participatory events would help foster social cohesion between refugees and HCs.
[54] WB and UNHCR. 2020. Compounding Misfortunes - Changes in Poverty since the Onset of COVID-19 on Syrian Refugees and Host Communities in Jordan, the Kurdistan Region of Iraq and Lebanon. Joint Data Centre on Forced Migration. Link here
[55] The WB and UNHCR Joint Data Centre of Forced Displacement collaborated to produce a dynamic-microsimulation based estimate of the impact of COVID-19 restrictions on poverty among refugees and host communities in Lebanon, Jordan, and Iraq. The simulation exercise used macroeconomic projections on changes in the economy and translates these into shocks to household consumption and therefore poverty.
[56] WB (2025) Project Appraisal Document Jordan: Resilient and Sustainable Social Protection Programme for Results.
HOW THE PROGRAMME WILL ADDRESS THE NEEDS AND CHALLENGES
The JHASS programme plans to invest up to £73m over four years, to respond to humanitarian needs. The focus of the programme will be:
  1. Core humanitarian assistance - including cash assistance, protection services, support for refugees who wish to return to Syria, and an IRF.
  2. Education support - including contributions towards the costs of including refugees in the national education system and contingency support for refugee camp schools; and
  3. Systems strengthening support for the humanitarian, education and social protection sectors.

JHASS is a strategic and integrated programme designed to: (1) assist refugees living in Jordan and vulnerable Jordanians to meet their basic needs, while (2) pursuing strategic and sustainable improvements to Jordan’s national humanitarian systems and local organisations supporting refugees and vulnerable Jordanians. Together this will meet critical humanitarian needs and support stability in Jordan and the region.

The intended impact for beneficiaries is enhanced socio-economic resilience and social cohesion among refugees and vulnerable Jordanians, supported by inclusive systems and contributing to long-term stability in Jordan and the region.

1. The intended outcomes for beneficiaries are:
  1. Refugees and vulnerable Jordanians maintain wellbeing and improved sense of safety while also benefiting from inclusive education and community participatory interventions.
  2. National, international, and local systems and organisations demonstrate measurable improvements in capacity and systems functionality, enabling the delivery of higher-quality, and shock-responsive services for refugees and vulnerable Jordanians.

The programme will consist of the following components:

1. Core humanitarian assistance:
  1. Cash assistance transfers to the most vulnerable refugees.
  2. Protection services to refugees and HCs.
  3. Support to help refugees voluntarily return to Syria; and
  4. An IRF.

1. Education support:
  1. Contributions towards the costs of including refugees in the national education system, including Non-Formal Education (NFE), through financial aid (off budget).
  2. Contingency support for refugee camp school operations as remaining education services transition to the MoE.

1. Systems strengthening support
  1. TA for the social protection and education sectors and deployments in the humanitarian, education and social protection sectors.
DETAIL ON PROGRAMME ACTIVITIES
CORE HUMANITARIAN ASSISTANCE
1. Humanitarian cash transfers will be disbursed to the most vulnerable refugees. There will be two complementary modalities: life-saving cash for food via the WFP, and unrestricted multipurpose cash transfers through UNHCR to cover other essential needs such as shelter, clothing, and healthcare. This dual approach ensures that refugees can meet their basic needs with dignity and flexibility, while also supporting local markets and reducing reliance on negative coping strategies like child labour[57]. Over the next five years, we aim to work with UN partners toward greater coherence in cash assistance delivery, with a view to exploring a single, harmonised approach. We recognise this will take time and require careful sequencing.
  [57] Jessica Hagen-Zanker, Martina Ulrichs, Rebecca Holmes and Zina Nimeh (2017) Cash transfers for refugees the economic and social effects of a programme in Jordan
2. Protection services will be provided for refugees and vulnerable Jordanians, aiming to effectively support priority humanitarian protection needs. The focus will be on those living outside camps since UNHCR and UNICEF provide protection services in camps and are supported by other donors. We will focus on aspects of protection which address the most severe risks of harm. We will prioritise work to prevent and respond to violence against women and children, with dedicated programming focusing on GBV and child protection. This will include psychosocial support services. We will also pursue community participatory activities to promote social cohesion and mutual understanding between refugees and Jordanians such as adolescent-focused gender and GBV awareness modules delivered in schools and community centres. Such activities not only build trust but also create safe spaces for dialogue and engagement.

As part of protection activities, the programme will empower local actors through the provision of small core funding grants to national Civil Society Organisations (CSOs) working on protection in an NGO consortium led by an INGO partner, in addition to project financing. This is reflective of feedback we’ve received on what form of support is most useful to them. It will build their capacities to deliver and amplify local leadership in the refugee response.

The programme will support voluntary returns to Syria. It will continue existing work begun in August 2025, under BE Amman’s previous protection programme the Jordan Protection Programme (JPP)[58], with UNHCR[59] assuming this continues to provide positive results. This will provide Syrian refugees living in Jordan who wish to return with cash assistance to meet the costs of transport and other associated returns cost. Refugees will also continue to be provided with counselling and legal support to ensure returns are voluntary, safe and dignified and to address the practical barriers refugees are requesting assistance with. Regular coordination with FCDO UK Office for Syria and UNHCR regional team will allow us to ensure returnees are monitored over time so we can develop an evidence-based understanding of the situation. This will particularly draw on UNHCR reporting to understand trends and wellbeing outcomes. Further activities to support voluntary returnees may be pursued during the course of the programme.
[58] The Jordan Protection Programme is a former humanitarian programme of BE Amman running from 2022-2026.
[59] Work is aligned with UNHCR’s regional operation approach to voluntary returns to Syria: https://www.unhcr.org/media/2025-operational-framework-voluntary-return-syrian-refugees-and-idps

The programme will have an IRF, which will ringfence 10% of the humanitarian cash assistance programme budget each financial year to rapidly disburse funds in response to an emergency if required. This will enable funding to be available for any new emergencies arising over the course of the project. Jordan’s strategic location and the volatile regional context including ongoing instability in Syria, Gaza, and the West Bank pose a persistent risk of mass displacement and sudden humanitarian crises. Additionally, donor funding volatility and sector-specific shocks (e.g. health outbreaks, Water, Sanitation and Hygiene (WASH) infrastructure failures) may rapidly escalate needs beyond current projections. The IRF will enable early response and ensure our funding continues to be deployed to the highest needs. It will build upon the effective emergency facility under a previous humanitarian business case – the JPP.

The IRF will serve as a flexible, unallocated contingency fund to enable timely, targeted interventions across humanitarian sectors, a mechanism that many donors in Jordan don’t have. Some operate within rigid annual funding cycles and many often lack the technical capacity to respond swiftly to emergencies, compounded by limited allocations for Jordan. To ensure efficiency and readiness, IRF activities will be delivered where feasible through existing partners leveraging their operational capacity and established systems, while streamlining administrative processes, and ensuring rapid mobilisation of resources. In terms of financial management, if the IRF is not activated within a financial year, the full cash envelope remains as originally planned. If activated, funds are reallocated from the cash budget to meet IRF needs, which may affect the following year’s cash allocation depending on timing and scale.

The IRF will be governed under the JHASS programme’s management and oversight structure, with activation guided by predefined criteria, including:
- New refugee influxes or displacement exceeding threshold levels
- Sudden funding gaps in life-saving sectors should other donors not be able to meet them
- Climate-related shocks (e.g. flash floods, heatwaves)

EDUCATION SUPPORT

Financial aid (off budget) to the MoE will continue to enable refugees to continue to access the national education system in HCs through contributing towards the costs of this for GoJ. Since the onset of the Jordan Compact in 2016, around 160,000 refugee children annually have been able to access the national education system through the multi-donor programme managed by the GoJ’s, Accelerating Access Initiative (AAI). In recent years AAI has been funded from the FCDO’s Building Resilience, Inclusion and Diversity through Girls’ Education (BRIDGE) programme, and these activities would be continued under JHASS[60]. Donor support through off-budget financial aid contributes towards key costs of including refugees, including tuition fees, textbooks, contract teachers, NFE and assistive devices and transportation costs for children with disabilities. A recent Fiduciary Risk Assessment (FRA) (August 2025) concluded that off-budget financial aid remains viable and aligns with the preferences of GoJ.
[60] Under both options UK financing for education will be around 18% less than under BRIDGE, however this broadly equates to decreased refugee numbers due to returns.

Contingency support will also be provided to UNICEF to maintain camp school operations as remaining services transition to the MoE. This support also enables Syrian Assistant Teachers (SATs) to work in camp schools, strengthening the connections between the school and community and reducing and addressing drop out.

If stability in Syria is realised, and more refugees are able to return, education support will also be utilised to ensure that students have the required documentation to re-enter the Syrian education system. It will also be used to support the MoE to rationalise numbers of schools and teachers which were expanded to accommodate the increased school population and shift the focus to improving quality and learning outcomes for the most vulnerable.

SYSTEMS STRENGHTENING SUPPORT

The programme will undertake systems strengthening activities for the social protection, humanitarian, and education sectors to create sustainable improvements in systems supporting refugees and vulnerable Jordanians. This will promote human development, social cohesion, and resilience against future crises. BE Amman has used TA and deployments across these three sectors in recent years and seen positive achievements. Lessons have also been learnt, including to provide TA in a demand led way according to the preferred approach of the GoJ. TA for the social protection and education sectors and deployments to each sector will be pursued during the programme, with social protection TA receiving the greatest budget to support our strategy for a responsible partial exit and since education TA can be pursued via Centrally Managed Programmes (CMPs).

TA and deployments will complement, work alongside and be guided by BE Amman’s in-house technical expertise in pursuing systems strengthening objectives. Through sustained and trusted technical relationships, in-house expertise from technical advisers has been used effectively in recent years to provide policy/thought leadership. In-house expertise has also driven system improvements through leading and contributing to international coordination efforts across the humanitarian, education and social protection sectors. For example, in the education sector the UK now sits on the MoE Policy, Planning and Coordination Committee. This provides privileged and direct access to influence and engage senior decision-makers in the MoE. On the humanitarian side, the BE Amman team has been playing a leading role in the humanitarian sector by for example providing strategic leadership and technical expertise as co-Chair of the Humanitarian Donor Group (HDG). Our systems strengthening priorities across each sector will thus guide TA, deployments and policy leadership activities from in-house experts.

Humanitarian systems strengthening will be focused the priorities of building the agility of humanitarian systems to respond swiftly and effectively to emerging and unforeseen crises. It will also help the UN to maximise its impact and relevance and prioritise in line with the UN80 agenda and the Humanitarian Reset. It involves refining its strategic focus, streamlining programming, and strengthening cross-agency collaboration to ensure that interventions are high-impact, scalable, and aligned with national priorities. In this context, marked by declining funding, fragmented coordination, and this transformative agenda, it is increasingly vital for donors like the FCDO to play a proactive role in shaping country-level engagement to improve aid efficiency and effectiveness. Jordan hosts one of the most complex humanitarian portfolios in the region, with protracted refugee situations, emerging climate-related vulnerabilities, and shifting migration dynamics. Yet, coordination mechanisms remain weak, and the reset initiatives risk being disconnected from local realities.

To support UN senior leadership who engage in advocacy and bilateral lobbying efforts with the GoJ, BE Amman humanitarian team will use its influence and political voice to strengthen coherence in responses. We will engage closely with UNHCR – as the lead agency for the refugee response, WFP and UNICEF as major implementing agencies, as well as with the Resident Coordinator’s Office (RCO) in its role is to provide strategic leadership on emergency preparedness and response. It can ensure all UN agencies commit resources and staff for anticipatory action, and that our support to UN agencies and NGOs complement the government-led response efforts. As a major donor in the response and given our influencing role, we would support the RCO to ensure inter-agency readiness and coordination. One of the priorities of the UN80 initiative is to support more integrated planning between humanitarian and development actors. Strengthening collaboration on anticipatory actions and contingency planning for Jordan could be an opportunity to connect humanitarian imperatives with development sustainability. This could be formalised in a joint donor advocacy paper on how to support the RCO and UN reform for our internal and external engagement.

FCDOs active engagement and recognised expertise offer a unique opportunity to ensure that humanitarian reform efforts are grounded in field-level evidence, responsive to emerging risks, and aligned with integrated programming approaches such as the JHASS framework. By convening partners, supporting inclusive coordination platforms, and advocating for coherence between humanitarian, development, and peacebuilding efforts, FCDO can help drive a more accountable and effective humanitarian response. Throughout the life of this programme, FCDO will need to retain the flexibility to adapt around any developments emanating from the Humanitarian Reset and UN80 Reform. We will continue to work closely with policy leads in the Humanitarian Policy and Partnership Department and the Humanitarian Food Security and Resilience Directorate, to ensure our support in Jordan is aligned with global policy development.

Priorities for system strengthening in education are as follows:

- Strengthening government leadership, evidence-based decision making and accountability for refugee education outcomes. We will utilise FCDO’s influential role as chair of the Education Development Partner Group, lead donor of the Refugee Education group, and member of the MoE Policy, Planning and Coordination Committee, to ensure the MoE has the required expertise and knowledge to increase evidence-based decision-making, leadership and accountability for refugee outcomes.
- Unblocking systemic challenges which currently limit equity in provision and ensure benefits from system reforms reach refugees. This potentially includes technical support to reduce double shifting, bolstering equitable use of Edtech/Artificial Intelligence, and strengthening terms and conditions for remaining temporary contract teachers.
- Improving data transparency and availability, as well as use of evidence, to improve systemic efficiency and effectiveness. While data on refugees will remain sensitive, the programme team will work with the MoE to improve reporting.
- Strengthening donor coordination and leadership of AAI. We will continue to support a deployment to the MoE Development Coordination Unit to ensure effective management and utilisation of donor resources, including management of the US Government to Government grant, for which they no longer have in-house capacity to manage.
- Strengthening the relationship between the private and public sector in education through a UK offer. Leveraging our diplomatic, trade, and royal relationships, we will look to identify ways to further connect UK expertise with Jordanian private sector, to support complementary activities which may enhance public sector outcomes.

Priorities for system strengthening in the social protection sector will focus on helping the GoJ achieve its NSPS vision, particularly in the areas of building resilience to shocks and strengthening social care services supporting both refugees and vulnerable Jordanians:
  1. Building the shock responsiveness of Jordan’s social protection system. This work will help implement the new ‘shock responsive’ pillar of the NSPS. It will help strengthen stability and reduce the need for additional donor funding to future crises (e.g. the UK provided £34m emergency social protection support to Jordan during COVID-19). Support will build on work begun through a previous programme[61] to develop a National Early Warning System (EWS) to detect and respond to climate-related and other shocks in a timely manner. The system will be embedded within Jordan’s broader Shock-Responsive Social Protection (SRSP) framework and aligned with humanitarian efforts. Activities under JHASS will include testing protocols that activate temporary social protection support to vulnerable households based on the EWS and conducting simulation exercises and training for MOSD, NAF and National Centre for Security and Crisis Management (NCSCM) to strengthen preparedness. It will also strengthen national financing and budgeting for emergency responses. It will also help expand and enhance Jordan’s unified social registry and link it to the EWS to support more effective response to shocks.
    [61] Strengthening Societal and Economic Resilience in Jordan programme (2022-2026)
  2. Strengthening national social care support for refugees and vulnerable Jordanians[62]. This is a priority intervention for the GoJ and will help implement the ’empowerment’ (social care) pillar of the NSPS. The aim will be to help the GoJ achieve the development of a regulated, inclusive, and sustainable social care system improving the quality of services provided to vulnerable populations, including refugees, as well as generating jobs especially for women. Activities will build on engagement through Strengthening Societal and Economic Resilience in Jordan (SSERJ) programme to help expand the professionalisation of social work for example through helping operationalise the Social Work Licensing Unit, developing a digital accreditation system and launching a woman in social work fellowship to attract and train young women in social care roles. Strengthening the national social care system will support an eventual transition from donor-financed protection services to needs for refugees being met through the national system, with support from civil society.
    [62] Currently refugees are able to benefit from social insurance and social care systems, whereas the National Aid Fund which provides social assistance for the poorest is for Jordanian nationals only
  3. Supporting the implementation of the NSPS – TA and implementation support will be provided to help the MoSD implement this strategy. This will underpin the activities above and help us provide high impact support to enable Jordan to pursue its social protection reform agenda and best spend its social protection budget and World Bank (WB) financing ($400m).
Social protection priorities continue work recently initiated under SSERJ but reflect several changes in direction on work in recent years. Under SSERJ, financial aid and TA were provided to support the inclusion of vulnerable workers, including refugees, in the SSC (which provides contributory social insurance) through the Estidama++ programme. While having achieved positive results to date, the removal of the work permit waiver for refugees will limit the potential for refugees to participate at scale in contributory social insurance via the SSC moving forwards since it will make it more expensive to work formally- a prerequisite to participation. Supporting refugees and vulnerable Jordanians via strengthening the social care system instead is thus seen as the higher priority for programme finance as there is no financial barrier to refugee participation and it will also focus support on assisting vulnerable care users (rather than working refugees who can be comparatively more affluent due to having a formal job). The shift from financial aid to systems strengthening support is in line with FCDO’s four essential shifts.

Previously BE Amman also provided social protection TA across a diverse range of topics and institutions under SSERJ. In this programme, support will be targeted on the NSPS implementation and key commitments in it, aligning work more closely with GoJ priorities. It will also be targeted on the parts of the NSPS considered to deliver most towards our strategy for a responsible partial exit from humanitarian aid and stability objectives. Strengthening shock responsive social protection will build Jordan’s long-term resilience to crises and reduce pressures for emergency donor funding in future, such as happened during COVID-19. Strengthening national social care services not only supports refugees and vulnerable Jordanians now but helps pave the way towards a future exit from humanitarian protection activities. Both will address poverty, build resilience and help strengthen the social contract and cohesion supporting stability. We will closely review progress with social protection systems strengthening activities after two years, given certain activities such as social care support are relatively new areas of engagement for BE Amman. We will reprioritise funding to other components should it not be generating robust results.
Governance and oversight
The programme will be overseen by a clear and robust governance structure, with oversight from BE Amman’s Country Board and Delivery Board. It will also be managed by an appropriately resourced programme team. This team includes humanitarian, education and social development (social protection) advisers, ensuring that there is sectoral expertise guiding work in each of the sectors which the programme works on. Further information is provided in the Management Case.

Key characteristics of the programme
1. In line with FCDO’s humanitarian reset priorities which seek to prioritise, protect and prevent[63], the programme will prioritise the people in greatest need by targeting the most urgent needs faced by refugees (including non-registered refugees) and vulnerable Jordanians. Aid will be guided by the JRP, data from UNHCR’s Vulnerability Assessment Framework (VAF), other needs assessments (WFP’s food security outcome monitoring, UNICEF and MoE reports), monitoring reports (post cash distribution monitoring) and contextual socio-economic analysis (e.g. Jordan Demographic and Health survey, Jordan Labor Market Panel Survey)[64]. The exception is voluntary returns which will focus on those who wish to return. For specific activities the following approach will be taken:
  [63] Humanitarian Guidance for Resource Allocation Round: Internal document.
  [64] This includes data on multiple deprivation in Jordan. Income poverty data is currently not published by the Government of Jordan.
  1. For cash assistance, rather than focusing on a geographical area (e.g. refugees living in camps vs those living in HCs), interventions will target the most vulnerable refugees. FCDO support will utilise the proxy means testing formula for humanitarian assistance used by the humanitarian sector in Jordan which give higher weights to the most vulnerable households (e.g. disabled persons, female headed households) so that they have a greater probability of inclusion.
  2. For protection services, refugees in HCs will be targeted since other actors/donors provide protection services for those in camps and vulnerable Jordanians will also be eligible for support in line with the Jordan Compact and JRP.
  3. We will explore integrating social protection systems and cash programming by actively encouraging our humanitarian cash partners to continue to collaborate with national social protection mechanisms—especially through coordination with the Cash Working Group—to share experiences and operational learnings. We will ensure our partners align with Development and Cash Facility (DCF) best practices – which emphasis that humanitarian cash interventions should complement national social protection systems. It will do so by promoting responsible data-sharing protocols, enabling interoperability and informed decision-making among humanitarian actors and national authorities.
  4. The NAF also uses an established proxy means testing formula meaning that social protection systems strengthening support will also benefit the most vulnerable Jordanians.
  5. On education, AAI and ESP reporting and data from the MoE Education Management Information System (EMIS) will be used to identify and support school aged refugee children. Remedial education will be provided to those that have dropped out of school, enabling them to re-enter formal education, ensuring the programme targets the most vulnerable children.

The programme will also protect the most at-risk groups. For instance, protection activities will focus on the most vulnerable including women, children, youth, children with disabilities, and other marginalised communities. In education, we will prioritise maintaining policy commitments which enable refugees to access the national education system and keep camp schools open.

It will also seek to prevent and anticipate future shocks and build resilience in long-running crises through several means. First preparedness for response and early action, helps mitigate future crises and build long-term resilience. The IRF, and support to strengthen the humanitarian systems’ emergency preparedness will enable timely interventions by key UN institutions and NGOs. Timely intervention can prevent the deterioration of conditions and avoid otherwise avoidable humanitarian losses. Delays can lead to escalation of impacts by twofold or more[65]. Early response is less costly in terms of both direct financial costs and the impact on people’s livelihoods and national longer-term development and growth[66]. A study of FCDO investment in six high risk countries concluded that on average, for every $1 invested in emergency preparedness, $2.60 is saved in the next crisis with a median savings ratio of $1: $1.5.[67] The NAF was an integral part of Jordan’s COVID-19 response. Close monitoring of the conditions for safe return to Syria, escalation of violence in the West Bank and evolution of Israel-Iran hostilities that could trigger cross-border displacements, will be able to be responded to by the IRF, ensuring our ability to respond to worst case scenarios.
[65] Note that there is evidence that a reliance on ex-post disaster financing (including humanitarian assistance) can create incentives for countries to underinvest in government-led systems for response as well as reduce incentives to prevent and reduce risks ahead of time: Clarke, Daniel J.; Wren-Lewis, Liam. (2016). Solving Commitment Problems in Disaster Risk Finance. Policy Research Working Paper; No. 7720. WB, Washington, DC. And Clarke, Daniel; Dercon, Stefan. 2016. Dull Disasters? How Planning Ahead Will Make a Difference. New York: OUP.
[66] Cabot Venton, C. (2013). 'The Economics of Early Response and Resilience: Summary of Findings'. DFID, London; Poole, L. (2015), 'Future Humanitarian Finance: Looking Beyond the Crisis', CAFOD, FAO and World Vision International.
[67] PWC IASC 2017

Early responses will be supported through efforts to build more national resilience to shocks. The scale and complexity of the humanitarian crisis and instability in the region creates risks of further mass displacement (e.g. from the West Bank or Syria) and economic shocks. Alongside these there are climate change risks and together these require a solid system to better prepare and respond[68]. The programme will support Jordan to build more shock responsive social protection systems building on previous UK programming, which will include support the integration of climate data into national planning. This component will deliver targeted, high-impact assistance to support the implementation of Jordan’s NSPS under the Patronage of His Majesty King Abdullah and contribute to the advancement of the National Disaster Risk Reduction Strategy (2023-2030), both of which are political priorities for the GoJ and contain elements of refugee inclusion, as well as the National Adaption Plan.
[68] National Disaster Risk Reduction Strategy 2023-2030 | United Nations Development Programme

1. It also aligns with the humanitarian reset priorities and shifts expected in posts’ humanitarian work[69]. It will do so through providing project and core funding to local actors to deliver protection activities. It will pursue cost-effective mechanisms, such as cash assistance which is a core component of the programme. It will support the reform of the humanitarian system in Jordan in line with UK priorities through systems strengthening activities. We will advocate for stronger inter-agency resource sharing and coordination among UN agencies, reducing duplication and maximising impact. It will build preparedness and resilience to crises and shocks through humanitarian systems strengthening activities and through strengthening the shock-responsiveness of the national social protection system. It will also better link multipurpose cash assistance to social protection systems, ensuring a more sustainable and inclusive approach.
  [69] Internal document: Humanitarian Guidance for the Resource Allocation Round: Delivering on the humanitarian reset at Post, in regions and in HFRD
2. This programme builds on 14 years of experience of operating in Jordan which has generated significant learnings. A list of our programme portfolio in recent years is provided is annex A. To best deliver impact, we are applying the following high-level lessons from these programmes:
  1. Ensure flexibility in the programme to ensure it can adapt to changing needs; the risk facility under the JPP provided flexibility to respond to critical needs.
  2. Multisectoral programmes can promote coherence and flexibility. This was a lesson from the SSERJ programme which saw humanitarian assistance brought into the social protection business case via an addendum.
  3. Cash has been a consistently effective tool for supporting refugees to meet their basic needs. However, the Multi-Purpose Cash Assistance to Refugees in Jordan programme highlighted that low transfer levels of cash assistance only were not sufficient to lift refugees out of poverty or enable them to achieve a dignified standard of living. It showed that a comprehensive and holistic approach addressing the underlying vulnerabilities of refugees during the process of supporting them with cash assistance was necessary – that includes access to education and protection services.
  4. Successful collaboration among implementing partners, stakeholders, and humanitarian donor groups in Jordan effectively addressed challenges and overcome barriers, advancing both UN cash programmes. The interagency relationship between UNHCR and WFP Jordan exemplified a commendable approach to partnership- collaboratively devising plans to ensure the complementarity of cash assistance for food and cash transfers to address other emerging needs of the refugees, and jointly engaging donors on essential refugee trends and needs. This is a lesson from SSERJ and the Multi-Purpose Cash Assistance to Refugees in Jordan programme. However, there is potential to align or converge further, and although a fully consolidated single cash programme is not currently in place and not realistic in the short term given each agency’s distinct mandates and structures, we will continue to aim for one programme in the longer term.
  5. Working with local communities to raise awareness of services and refer beneficiaries as needed is essential to build trust and reach vulnerable families (lesson from our previous protection programme, JPP).
  6. TA can successfully strengthen systems and lead to sustainable improvements. For example, UK support previously has helped strengthen the NAF and SSC. However, to maximise effectiveness it needs to be in line with the GoJ’s highest social protection priorities and preferred approaches (lesson from SSERJ).
  7. Using partners already established in Jordan and trusted by the GoJ can maximise impact. e.g. WB, UNICEF, WFP, UNHCR (lesson from SSERJ).
  8. The political economy around refugee integration needs to be carefully managed. Annual Reviews have highlighted that deployed staff (i.e. education advisers) can ensure strong government relationships, who have effectively enabled open and transparent conversations around sensitive issues, such as data and dialogue on ‘integration’ and long-term planning (lesson from SSERJ).
  9. Consortiums can help programme coherence, reduce administrative burden and helpfully bring in local actors. However, the JPP highlighted that resources need to be invested in the management of the consortium by the lead partner and clear governance arrangements need to be established at the outset.
  10. In the education section, playing the role of coordinating funding from seven donors has enabled the UK to have an influential role in the sector and should be continued. This is a lesson from the BRIDGE programme.
  11. TA has strengthened off-budget aid management in the education sector. Off-budget support (under BRIDGE) has been successful in securing donor support for certain activities which otherwise may not have been funded, as well as enabling a wider pool of donors to contribute[70]. But off-budget aid lacks the rigour of on-budget support; the 2025 FRA recommends a gradual shift which will be explored under JHASS.
    [70] Not all development partners are able to typically provide financial aid for humanitarian interventions. The off-budget mechanism ensures that resources are allocated to specific activities, which is more acceptable for a wider range of donors.
  12. Off-budget aid under BRIDGE has enabled the transition of NFE to the MoE, replacing third-party delivery like UNICEF. This shift reduced administrative costs, improved efficiency, and increased re-enrolment into formal education, allowing for greater scale.
  13. While education access has improved, evidence linking aid to learning remains limited. Double-shift schools reduce instructional time and resources, and reliance on temporary teachers affects quality. This Is a lesson from BRIDGE and future programming must shift from inputs to outcomes if funding allows, with robust quality-focused indicators embedded in the next ESP (2026–2030)[71].
    [71] Selenica, E. (2025). Syrian Refugee Education in Jordan: Aid Effectiveness and Efficiency 2019–24 and New Pathways for 2025 and Beyond. ERICC Background Report.

1. The programme focuses on the UK in Jordan’s comparative advantages. The UK’s comparative advantage lies in its convening power, technical leadership (e.g. in the humanitarian sector, refugee education and social protection), flexible deployment of expertise to key institutions, and deep sectoral experience since 2012. This programme builds on previous programming and the expertise the UK has gathered through this. It reflects the UK’s ability in Jordan to bridge humanitarian and development issues with multi-year funding, giving us a comparative advantage to establish and drive programming which both responds to current needs and builds resilience to future shocks. It reflects our comparative advantages compared to others as follows:
  1. Humanitarian sector - cash will be a principal focus. The UK has extensive experience and comparative advantage as a leading cash donor in Jordan. Protection and returns are also areas where the UK has recent experience from the previous protection programme; JPP and its predecessor. At the time of writing, the UK is the only donor supporting cash for voluntary returns from Jordan. Gender-focused programs were also particularly hit by US funding cuts. US-funded GBV/protection programs have been cancelled in Jordan, disrupting thousands of active cases in which NGOs were supporting high-risk individuals. This has created important gaps which the UK is well-placed from its experience to help towards. The FCDO does not plan to prioritise sectors where other donors play a more prominent role (e.g. WASH- the US, Switzerland and the EU are key donors, or health- the US and Directorate-General for European Civil Protection and Civil Aid Operations (ECHO) prioritise this).
  2. Education sector - we play a key role in donor coordination and technical leadership – both as lead donor on refugee education and co-chair of the Education Development Partner group - which this programme will allow us to continue. The UK has extensive technical expertise on education in protracted crises and conflict settings, and has generated country, regional and global evidence to inform practice and influence government and the development community through Education Research in Conflict and Protracted Crisis (ERICC). Under the AAI programme, Norway, Australia, and the US rely on FCDO technical and coordination leadership to trigger disbursements and guide prioritisation.
  3. Social protection sector - also a sector where the UK is well-positioned to lead efforts, drawing on the global expertise of the FCDO, its local convening power, extensive sector experience in Jordan since 2018, including around successful initiatives like Emergency Social Protection in Jordan (ESPJ), and the Estidama++ pilot programme. We will build on successful previous work, e.g., shock responsive social protection systems and are the only donor providing critical support to the unit in the MoSD responsible for implementing the NSPS 2025-2033 and WB loan. We will also avoid duplicating others work e.g. funding direct social assistance cash transfers to vulnerable Jordanian’s through the NAF which is funded through a $400m WB concessional loan, or prioritise social protection specifically for people with disabilities given this is a priority area of the EU and Germany- two other large Social Protection donors- following the Global Disability Summit which Germany co-chaired with Jordan in 2025.

Multi-year humanitarian programming will be a core feature of the JHASS programme. Evidence shows that predictable multi-year funding and the longer-term presence of agencies results in some greater economy (e.g. better planned procurement of goods etc.) and speed of response to additional in-crises covariate shocks (e.g. climatic, conflict)[72]. Multi-year commitments have also enabled the GoJ to increasingly integrate the refugee response in key sectoral strategic plans, such as the ESP. This ensures greater accountability for outcomes and more predictable pathways for refugee children and provides confidence to the government that support will continue as services are transitioned. We will seek to retain in year flexibility on when our payments are made, to help GoJ and UN partners to manage risks from irregular disbursements from other donors.
[72] DFID, “HIEP Meta Resilience Evaluation”; Simon Levine, Lucy Sida, Tim Gray, and Debby Cabot-Venton, *Multi-Year Humanitarian Funding: A Thematic Evaluation*, 2019.

This programme will align with broader UN reform efforts and the Humanitarian Reset, particularly in light of declining Official Development Assistance (ODA). Through this programme, the UK will reinforce its Grand Bargain commitments to enhance aid efficiency, responsiveness, and accountability. As the UN80 reform initiative progresses, the programme will have the flexibility to adapt its priorities and define concrete actions to support a more agile humanitarian system and pushing the UN to prioritise and identify the most severe needs in Jordan. It is fully aligned with FCDO’s humanitarian framework and Humanitarian Reset, prioritising locally led responses, protection for the most vulnerable and cash assistance.

Through this programme the UK will maintain its leadership roles as co-chair of the HDG permanently represented in the UN led Jordan Strategic Humanitarian Committee (JOSH) and the Education Development Partner Group (EDPG); chair of the refugee education donor group; a steering committee member of the Jordan Development Partners Group (JDPG), and active participant in the Social Protection Donors Group which is was a recent co-chair of. This enables UK influence over policy and the ability to promote integrated, sustainable approaches. Engagement will include aligning humanitarian and social protection systems, especially in social assistance, to reduce duplication and improve long-term outcomes, as well as influencing humanitarian coordination structures that better align with the planning and delivery within national coordination systems. In education, the UK will use these platforms to continue to advocate for integrated service delivery models that strengthen national systems over parallel structures. The UK has led the refugee education donor group since the inception of AAI and provides key technical support in prioritisation, coordination, and decision-making. UK leadership has leveraged approximately £50m annually in support of refugee access to the national education system, and donors, including Norway and Australia, rely on FCDO’s technical expertise to approve disbursements.
Evidence base
This programme has been designed based on robust evidence of what works from international research and our experiences of operating in Jordan for the past 14 years. The evidence base is outlined in detail in the appraisal case.
PROGRAMME ASSURANCES
Counter-terrorist financing and anti-money laundering. FCDO has a zero-tolerance approach towards aid diversion (fraud, bribery, terrorist finance and money laundering) and we will do everything we can to prevent, detect and, if found, respond robustly. We will take necessary steps to investigate all suspicions, allegations or instances of aid diversion and will pursue penalties available in each case, including dismissal, prosecution, suspension, and cancelation of funding. During the design phase a risk assessment was conducted, which is cognisant of all aid diversion risks. A Due Diligence Assessment (DDA) has already or will be undertaken to assess the capacity and capability of delivery partners to deliver our programme[73]. The programme itself aims to target vulnerable groups who may be exploited for illicit financial activities.
[73] A new DDA will only be conducted for the INGO consortium lead. For UN agencies with central framework agreements, we will confirm that the central assurance remains current and review any context-specific risks through updating the country-focused DDA. For the World Bank Jordan a DDA was completed in 2025. For the GoJ, assurance is provided via the Financial Risk Assessment (FRA), not a DDA. Existing DDAs can be relied upon if they are less than three years old, for the same partner, in a comparable programme and context, and where no material changes have occurred.

1. Public Sector Equality Duty. JHASS is compliant with the International Development (Gender Equality) Act 2014. Gender inclusion will be mainstreamed across the work of all partners to ensure women and girls can fully access and participate in humanitarian aid. For example, the needs of these groups are already prioritised within the proxy means testing formula used for cash assistance and this support is considered gender sensitive. Further activities to target their specific needs will be included, where opportunities are identified. Several of our interventions proposed through this programme, including GBV services are targeted to meet the specific needs of women and girls by providing access to services for gender-based violence. The NSPS has a specific focus on gender transformative policies e.g. Women’s Economic Empowerment (e.g. working conditions, remote work, childcare) and disability transformative policies (e.g. social care). Strengthening the social care system in line with this strategy will be supported and is expected to particularly benefit women through providing employment opportunities in a sector with many female workers. Within the population in need, partners will be asked to prioritise those facing multiple exclusions (based on disability, age, ethnicity, religion or belief, sexuality, location, or other overlapping protected characteristics).
2. All partners will be expected to demonstrate how they will be gender responsive in their project proposals. Implementing partners are required to conduct a gender disability and social inclusion analysis, to inform the implementation of the project to ensure they are taking the specific needs of groups with protected characteristics. We will look to include specific requirements to eliminate discrimination, harassment, and victimisation, to advance equality of opportunity and foster good relations between people who share a protected characteristic and those who do not. Partner agreements will specifically consider women and girls, persons with disabilities, refugees, and other vulnerable communities. All planned and achieved results reported to the FCDO will be disaggregated by sex, disability status, nationality, and other relevant factors. The targeting criteria for WFP and UNHCR cash assistance focuses on families that cannot meet their most basic survival needs and have multiple vulnerabilities e.g. members who suffer from severe disabilities, debilitating medical conditions and other vulnerabilities.

Former BE Amman humanitarian programmes have demonstrated successes in inclusion. For example, of the 33,868 people supported through protection services under the previous Protection Programme JPP, nearly 74% were female and 13% had a disability. Last year 54% of refugees receiving cash assistance from UNHCR under SSERJ were women and 11% had a disability. Our education programme facilitated access to public schools for 155,000 refugee children, supported 138 inclusive schools, and provided education services to 4,029 children with disabilities. That said previous programmes have also generated relevant lessons including that disability inclusion/mainstreaming needs to be strengthened across protection interventions (lesson from JPP), disability disaggregated data can be challenging to receive from GoJ reporting (lesson from SSERJ), and refugee inclusion at the target levels can be challenging and required concerted efforts (lessons from SSERJ and JPP). This programme will proactively discuss these challenges with partners and design activities accordingly.

Safeguarding: FCDO has a zero tolerance to sexual exploitation, abuse and harassment, and all forms of physical or emotional violence or abuse and financial exploitation. There is a strong body of evidence around the causal link from provision of cash assistance VAWG. The programme will mitigate these risks by delivering cash assistance through digital wallets, reducing the need for women to travel or queue in public spaces to collect cash, which lowers their exposure to harassment or violence. Additionally, UNICEF and the MoE are implementing the Safe to Learn initiative, which focuses on creating violence-free schools through policy reform, teacher training, and student engagement. All partners will be required to undergo due diligence, providing details of their safeguarding controls and assurance processes and are encouraged to include protection and safeguarding costs in their budgets. UN partners have strong policies on safeguarding and mechanism for accountability for affected populations. We will regularly review the implementation of, and adherence to, safeguarding policies including through at least quarterly meetings with partners, field monitoring and at annual reviews using specific logframe indicators and the risk matrix. Accountability to affected populations, including safeguarding, will continue to be a policy priority. The FCDO will continue to leverage its position as a major humanitarian donor in Jordan to lobby other donors, humanitarian actors, and GoJ to raise the bar on safeguarding.

Conflict Sensitivity and Do No Harm. Jordan has long been one of the most stable and peaceful countries in the Middle East. It is in the interest of the UK to ensure Jordan remains stable despite regional tensions and Jordan’s narrow fiscal space. Wide and growing income inequality is a major risk factor for instability and unrest in middle income countries.[74] Combined with the high unemployment rate, especially for young people; the trauma of displacement among the refugee population and frustrations about the situation in Gaza and other parts of the region, presents a potent mix for pressures building up.
[74] Youth unemployment, education, and political instability: evidence from selected developing countries 1991-2009 – GSDRC. Full article:  Youth unemployment and political instability: evidence from IGAD member countries (tandfonline.com).

1. The programme will take a robust approach to conflict sensitivity, reinforcing the principle of ‘do no harm.’ The JHASS programme will monitor and reduce conflict sensitivity risks throughout the programme cycle. JHASS partners will be asked to provide evidence of a proportionate conflict sensitivity plan. All partners’ plans should demonstrate that they have the expertise and processes to undertake conflict sensitivity analysis at the outset, then build this into project design, implementation, risk monitoring and evaluation. As a condition of funding, partners will need to dedicate resources and activities to practical application of conflict sensitivity analysis. To ensure we minimise any harm in our aid interventions we will ensure there will be disaggregated analysis of how different groups are impacted. Where risks arise around conflict dynamics, including possible unintended consequences of programming, partners will be required to elevate them rapidly through the JHASS governance mechanisms and bring them to the attention of the BE for a decision.
2. Climate and Environment. Jordan contributes a tiny fraction to global emissions and energy use, accounting for 0.04% and 0.02% respectively of the global total, and with per capital emissions of 2.01 t/per person below the global average (4.73 t/per person) (Annex B). While Jordan has made some improvements in its green policies, this low contribution to global emissions is considered to be a consequence of its income level and population size rather than its green policy. Aggressive climate change mitigation within Jordan will thus have limited impact on the global climate trajectory. As Jordan is highly vulnerable to some climate change impacts (e.g., water shortages, extreme heat)[75], adaptation rather than mitigation is a more strategic focus for climate investments.
  [75] While Jordan ranks in the top quarter globally for overall vulnerability on the ND-Gain index, its unique water stress and fragility context make resilience and adaptation priorities.

We will integrate climate resilience into humanitarian programming to safeguard lives, protect development gains, and support Jordan’s stability. Refugees and HCs are positioned as contributors to Jordan’s climate transition. The provision of cash assistance is recognized as ICF eligible. A review conducted in July 2024[76], attributed a minimum of 15% of the total cash assistance to ICF, reflecting its targeted contribution to strengthening adaptive capacities. It supports climate adaptation particularly by enhancing the resilience of vulnerable communities to climate-related stocks such as extreme weather events, prolonged droughts, and food insecurity. We will collaborate with partners to enhance these climate resilience benefits of cash assistance. We will also ensure protection services are informed by analysis of how climate stressors exacerbate risks such as GBV, ensuring interventions are responsive to emerging threats. We will also collaborate with partners to support shock-responsive social protection to address climate shock impacts, supporting Jordan’s climate-smart humanitarian goals and aligning with national level climate strategies, such as the National Adaption Plan.
[76] ICF Review of Jordan Humanitarian Programmes - Authored by: Manisha Gulati, Nancy Zaarour, and Nadim Farajalla- July 2024

We will collaborate closely with other FCDO-supported programmes and initiatives—such as Jahez[77] and other initiatives - to identify complementarities and share learning on effective approaches to reducing climate vulnerability in Jordan. This collaboration will focus on aligning efforts across humanitarian, development, and climate objectives to maximise impact and avoid duplication.
[77] Jahez is an FCDO-supported project which aims to build climate resilience in refugee-hosting communities.

Partnership Principles. BE Amman updated its Partnership Principles Assessment (PPA) in August 2023 after reviewing the GoJ’s level of commitment against four principles: poverty reduction and SDGs; respecting human rights and other international obligations; strengthening management of public finances and fighting corruption; and strengthening domestic accountability. The review concluded that there remains a strong level of commitments with a positive upward or stable trajectory. Activities will be delivered through GoJ, UN agencies, , the World Bank, and NGOs. Also, where working with the GoJ, we will ensure country agency and promote both their ownership and capacity.

Exit strategy. This four-year humanitarian programme is built around a flexible, context responsive exit strategy. It aims to reduce the pressures on Jordan from hosting refugees through supporting voluntary returns to Syria, and to create sustainable improvements in the national, international and local capacities and systems which support refugees and vulnerable Jordanians including to better respond to shocks and thus reduce future humanitarian needs. Given a significant proportion of Syrian refugees are expected to remain in Jordan by the end of the programme, it does not assume a full exit from humanitarian assistance. Instead, it seeks a responsible transition from specific activities and scale down of others where feasible. The aim is to reduce the funding needed from the UK at the end of the programme, while recognising the expected need to continue to provide support at some level to meet ongoing needs.

The strategy is guided by the ‘durable solutions’ approach used by UNHCR, which includes three elements: voluntary repatriation, integration, and resettlement. On ‘voluntary repatriation’, supporting voluntary returns to Syria remains a priority where conditions allow, helping returns be conducted in a safe and dignified manner and also easing humanitarian pressure on Jordan. In terms of ‘integration’, full integration of refugees into Jordan’s economy and social systems is unlikely in the near term due to political sensitivities. However, the programme along with BE Amman’s advisory expertise will help strengthen national services such as education and social care which already support refugees and vulnerable Jordanians, build the capacities of local NGO delivering services, advocate for pro-refugee policy changes (such as opportunities for refugees in specific sectors such as agriculture) using robust political economy analysis and other evidence from Monitoring, Evaluation and Learning (MEL) activities and advocate against any further policy reversals (key audiences will be MoL, Ministry of Planning and International Cooperation (MoPIC), MoE, MoSD and Ministry of Finance (MoF)). It will also build greater resilience in national and international systems to respond to future crises/shocks thereby reducing future humanitarian needs. Resettlement to third countries will not be prioritised given its political complexity and limited scalability.

1. The programme will pursue sustainable enhancements to services for refugees and vulnerable Jordanians through an approach which pursues strengthening international and national systems and empowering civil society. Opportunities for further scaling down support will be monitored throughout the programme. Particular attention to the budget profile will be given in FY27/28 to check whether it aligns with trends in needs. Where exits are feasible, they will follow global best practices, including smooth transitions and comprehensive handover packages to ensure continuity and resilience. FCDO’s 2025 decision to end off-budget social protection financial aid demonstrates readiness to prioritise and exit support where appropriate.
2. By the end of the programme, a favourable scenario would see significant refugee returns to Syria, slightly expanded employment opportunities for those remaining in Jordan and no further roll back of current areas of refugee inclusion, and strengthened national and international systems and local organisations that support refugees and vulnerable Jordanians- including around any new conflict, climate or economic-related shocks. Together this is expected to better meet and reduce future humanitarian needs. However, it is likely that there will still be a refugee caseload in the hundreds of thousands at the end of the programme, so continued UK support—albeit at reduced levels—will likely be needed, especially as international funding declines. A full exit as such is unrealistic; instead, a ‘partial responsible exit’ or scale-down is anticipated, including continued but reduced support for at least cash and education as numbers of refugees in Jordan decrease, and withdrawal from camp school operations and systems-strengthening activities once objectives are met. The programme will also help strengthen the national social care system (which is inclusive of refugees) and NGOs supporting this, which lays the foundations for a future transition away from donor financed protection services. Opportunities to scale down/exit protection activities, with needs to be met instead through the strengthened national social care system, will be closely monitored.

Even in a worst-case scenario where UK humanitarian funding for Jordan becomes no longer available, the programme will leave a lasting impact by having supported voluntary returns and enhancing resilience to shocks thus reducing future humanitarian needs in Jordan, improving refugee and vulnerable Jordanian national and international support systems and strengthening local civil society capacity.

Appraisal Case
APPRAISAL OF FEASIBLE OPTIONS
Four stages are used to appraise the programme
Stage 1 – Identification and appraisal of feasible sectoral options – Rationale, Activities and Indicative Results
Stage 2 - Appraisal of delivery options
Stage 3 - Economic appraisal and Value for Money (VfM) assessment
Stage 4 - Theory of change and assumptions

STAGE 1: IDENTIFICATION OF APPRAISAL OPTIONS - RATIONALE, ACTIVITIES AND INDICATIVE RESULTS
In this section we will evaluate three options – two feasible options for UK support to the humanitarian sector in Jordan, as well as a ‘do nothing’ counterfactual option. A robust analysis of programme options has been undertaken using evidence from internal consultations, external evaluations, and lessons from existing FCDO investments operating in Jordan and across the Middle East and North Africa (MENA) region.

The three programme options considered are:
Option 1. Focus support on lifesaving and life-changing service delivery, prioritising humanitarian cash assistance, protection, and education.
- Option 2. Strategic and integrated approach combining lifesaving and life-changing service delivery (cash, protection, education) with support for voluntary returns, an IRF, and systems strengthening activities to deliver sustainable improvements in systems supporting refugees and vulnerable Jordanians.
- Option 3. Do nothing – no further support to meet the acute needs of refugees in Jordan or their HCs.

The same overall budget of up to £73 million will be used for 1 and 2 over four years. This will maximise the resources allocated to BE Amman and ensure they are fully utilised to address the challenges outlined in the strategic case, given the scale of needs. No budget is required for option 3. Table 1 provides a summary of the budget under each option. A more detailed budget for option 2 is provided in annex F.

Table 1: Summary of budget by component for each option
COMPONENT		OPTION 1	OPTION 2	OPTION 3
Core Humanitarian Assistance		46900000	34420000	0
of which	1. Cash	37900000	24920000	0
	2. Protection	9000000	7000000	0
	2.1 Protection - GBV and Child Protection	5200000	4200000	0
	2.2 Social Cohesion and Resilience	2200000	1750000	0
	2.3 Institutional Capacity Strengthening	1600000	1050000	0
	3. Returns	0	2500000	0
Education Support		25400000	24450000	0
of which	Financial aid to MoE (off budget)	23900000	22950000	0
	UNICEF	1500000	1500000	0
Systems Strengthening		0	13130000	0
	Humanitarian	0	680000	0
	Education	0	950000	0
	Social protection	0	11500000	0
Monitoring, Evaluation and Learning		700,000	1,000,000	0
Total		73,000,000	73,000,000	0

Option 1. Focus support on lifesaving and life-changing service delivery, prioritising humanitarian cash assistance, protection, and education
Description and rationale
This option would prioritise resources on humanitarian cash assistance, protection services and education. The rationale for this option is to direct the maximum resources towards addressing critical needs of refugees and vulnerable Jordanians. It reflects GoJ and UK priorities which have determined that an exit from these areas of humanitarian assistance will have the most significant impact on humanitarian suffering.

This option would have the following components:
Core humanitarian assistance:
    1. Cash assistance transfers to the most vulnerable refugees.
    2. Protection services to refugees and HCs.

1. Education support:
  1. Contributions towards the costs of including refugees in the national education system (including NFE) through financial aid (off budget).
  2. Contingency support for refugee camp school operations as services transition to the MoE.
Indicative results, which have been attributed the UK direct investments, under this option are set out in table 3.
 Supporting evidence
There are critical and ongoing needs for cash assistance among refugees in Jordan, as outlined in the strategic case. Evidence from Jordan and other contexts consistently shows that cash assistance is one of the FCDO’s most cost-effective humanitarian tools strengthening resilience, promoting value for money, and enabling sustainable impact. Cash is considered a “Great Buy” with an extensive evidence base on value for money and effectiveness[78]. Regular cash transfers have been shown to significantly improve food security, allowing families to access diverse and nutritious food from local vendors, which in turn fosters social cohesion and economic stability in HCs[79]. In recognition of this, FCDO’s humanitarian approach/ key shifts identify cash as a priority modality, and the UK’s previous investments in Jordan have demonstrated strong results in improving refugee well-being and reducing vulnerability.
[78] The 2016 UK “Cash based approaches in humanitarian emergencies, a systematic review”[3] found 4,094 studies and 113 published articles.
[79] https://plan-international.org/uploads/2023/01/20230117_GFSC-Research-Final-Report-v2-final.pdf

Evidence highlights the value in complementary food-restricted and multipurpose cash transfers, including in Jordan. WFP is the lead agency on food security and thus delivers food-restricted transfers to guarantee sufficient access to nutritious food, meeting minimum dietary standards. UNHCR’s multipurpose cash supports broader household needs. Global and Jordan-specific evaluations[80] indicate that food-restricted transfers tend to provide stronger protection against food insecurity and help reduce negative coping strategies compared to unrestricted cash alone. In this context, UNHCR’s multipurpose cash transfers may not fully address food security needs on their own, which is why complementary approaches remain important. Similarly, food-restricted transfers are unable to meet other essential needs such as, clothing, bills, and transport.
[80] [https://www.wfp.org/publications]

There is evidence of the cost-effectiveness of the UN-led cash assistance system in Jordan, and our partners have a strong track record of delivery. BE Amman has worked closely with the key agencies with mandate to deliver humanitarian assistance in Jordan (UNHCR and WFP[81]) and donors over time to strengthen the system. Donors now all support two main partners to deliver assistance, streamlining efforts and avoiding a fragmentation of modalities seen in other contexts. UNHCR and WFP have worked together closely to align efforts with each other and promote cost effectiveness[82]. Evidence of this includes a unified needs assessment, data sharing to target beneficiaries and use the same proxy means testing targeting mechanism to reach the most vulnerable households and joint field visits. The Common Cash Facility (CCF) is used for delivering cash assistance that provides organisations direct and equal access to a common Financial Service Provider (FSP) and payment facility. This has reduced costs by removing the need for each agency to establish their own procurement arrangements and negotiate lower bank fees[83]. Over the next five years, however, we aim to work with UN partners toward greater coherence in cash assistance delivery, with a view to exploring a single, harmonised approach.
[81] WFP holds the global mandate for food security under the UN system, specializing in ensuring access to adequate nutrition through food assistance and targeted transfers, while UNHCR’s mandate focuses on protection and overall household needs.
[82] Joint Strategy Enhancing Self-Reliance in Food Security and Nutrition in Protracted Refugee Situations have a joint strategy which includes joint research, data sharing, joint targeting https://www.unhcr.org/sites/default/files/legacy-pdf/5c3c6d584.pdf
[83] Review of the Common Cash Facility Approach in Jordan, UNHCR and CALP, October 2017 59fc36b87.pdf

There is robust evidence for intervention in protection activities. FCDO’s Best Buys in Preventing research highlights that the emerging evidence base shows that, with the right approach VAWG is preventable, with potential for significant effect sizes over 50% within programme timeframes. FCDO’s Best Buys in Preventing VAWG identifies community activism as one of the most effective approaches, which uses facilitated dialogues, participatory and group learning methods, informal discussions, and workshops led by community volunteers to shift harmful social norms over 18 months to three years; school-based interventions, ranked as promising evidence, employ participatory, longer-term approaches that encourage critical reflection and skill-building among students, leveraging curricula and peer norms to influence attitudes toward gender and violence. VAWG prevention interventions can also have multiple secondary impacts on outcomes such as household economic and food security, mental health, and violence against children.

FCDO Jordan has also generated compelling evidence of the benefits of protection activities since UK-funded initiatives began in 2014, continuing via the JPP. These programmes have demonstrated the value of protection interventions in addressing vulnerabilities and strengthening national systems, reinforcing the case for continued investment in this area. JHASS will build on this, recognising protection as both a humanitarian priority and a vital complement to cash assistance. While cash meets immediate survival needs, it does not completely address risks like exploitation, GBV, child labour, or exclusion from services. Protection interventions are essential to ensure that humanitarian assistance is safe, inclusive, and responsive to the complex realities of displacement.

The JPP provided integrated child protection and GBV prevention and response services to refugees and vulnerable Jordanians, reaching 34,000 individuals. The programme demonstrated the value of holistic, person-centred approaches that address both psychosocial and structural protection needs and the value in delivering via NGOs using flexible, locally grounded delivery models that can adapt to shifting contexts and reach underserved populations. It also highlighted the value in combining service delivery with systems strengthening activities for key Government Ministries and Community Based Organisations (CBOs) to create sustainable enhancements in services. Among the most impactful interventions were Cash for Protection (CfP) and helpline activities. These activities not only achieved strong quantitative outcomes but also demonstrated meaningful qualitative improvements in participants’ lives.

These results affirm that protection services are not ancillary they are foundational to a dignified humanitarian response. Under JHASS, protection will be integrated with cash and education support, ensuring that vulnerable groups especially women, youth, persons with disabilities, and unregistered refugees receive holistic assistance that promotes safety, inclusion, and long-term resilience.

Providing core funding to national NGOs to localise protection services and build local leadership aligns with FCDO’s Best Buys guidance, which identifies community activism as a highly cost-effective approach to preventing VAWG. The Jordan Integrated Security Fund (ISF)’s Tamasok Programme (2023-2025) demonstrated that flexible, sustained funding helped enable local NGOs to expand outreach, deliver inclusive services, and strengthen institutional resilience. This aligns with findings from the Ending VAWG Helpdesk Report on Localisation and GBV Services in Jordan (2024), which emphasises that engaging local organisations leads to more effective, timely, and contextually relevant GBV prevention and response. The report recommends that donors prioritise long-term, equitable funding to empower local organisations to lead and co-design protection services. By investing in local actors, JHASS will support the locally led delivery of inclusive protection services, in line with GoJ vision of a greater role for NGOs in service delivery in recognition of the current pressures on national social care services.

The GoJ has provided a significant global public good by allowing annually around 160,000 refugee children to access the national education system. This has prevented a lost generation and been identified as a model for other countries experiencing a significant influx of refugees. This is a burden-sharing arrangement, with the GoJ currently contributing approximately 73% of the cost and donors 27% of the cost[84].
[84] These are the figures for 2024/25 and approximated based on WB unit costs and MoE/AAI data. This has varied since the signing of the Jordan Compact, with the burden share shifting to the GoJ. There is no fixed agreement or understanding about what the burden share should be.

The programme will continue to financially support the MoE to maintain this provision. This avoids the need for a parallel education system. Parallel education systems for refugees offer limited advantages, especially where the language of instruction is the same in the host and home countries and there are no significant cultural differences that may impact integration. These systems are predominantly funded through short term humanitarian financing, which is more unreliable than predictable finance[85] and does not cover long-term contracting of teachers or permanent infrastructure ensuring equity and durability. Parallel systems are more likely to be limited to basic education due to the complexity of providing subject specific teachers for upper grades. This limits the continuity of education[86].
[85] Hopper, R. (2024). Refugee Education Financing: Key Facts and Findings. Policy Research Working Paper 10752. Washington, DC: WB. https://openknowledge.worldbank.org/bitstreams/e45a030e-b2a6-45af-964f-5231136b9ff7/download
[86] WB. (2025). INSPIRE Guide to Refugee Inclusion in National Education Systems. Washington, DC: WB. https://openknowledge.worldbank.org/bitstreams/f1a2af28-4ebf-4029-bdc5-f8da28321d8e/download

Evidence has shown that integration into national systems delivers better economies of scale; has the potential to improve services for all children in the HCs due to the influx of resources allocated to the crisis; provides access to a developed curriculum and formally recognised certification; access to trained teachers; enhances social cohesion and wellbeing; and provides more resilience to crises (as evidenced by COVID-19 disruptions)[87]. Cost-effectiveness data comparing parallel and integrated systems is limited[88] due to the challenge of quantifying the long-term benefits to refugee students as well as the specific interventions needed to support the integration of refugees in host country education systems where the language and culture is significantly different. However, longitudinal data comparing the experiences of refugees in Lebanon (emergency education –no integration), Turkey (transitional-gradual integration) and Australia (long-term integration) highlighted significant student level advantages of inclusion in national education systems including: improved learning outcomes; lower levels of drop-out; reduced disruptions to schooling and educational continuity (between education levels); and reduced discrimination[89].
[87] Shuayb, M., Hammoud, M., & Alsamhoury, O. (2023). Schooling Experiences and Outcomes of Refugee Children in Lebanon, Turkey, and Australia: A Comparative Longitudinal Study. Centre for Lebanese Studies. https://lebanesestudies.com/wp-content/uploads/2023/11/Refugee_report_june_14.pdf
[88] Education Research in Conflict and Protracted Crisis (ERICC). (2024). Expanding Refugee Access to National Education Systems: The State of the Evidence on Enabling Factors, Constraints, and Interventions. ERICC Policy Brief. https://doi.org/10.6084/m9.figshare.27047962
[89] Shuayb, M., Hammoud, M., & Alsamhoury, O. (2023). Schooling Experiences and Outcomes of Refugee Children in Lebanon, Turkey, and Australia: A Comparative Longitudinal Study. Centre for Lebanese Studies. https://lebanesestudies.com/wp-content/uploads/2023/11/Refugee_report_june_14.pdf

Evidence from Jordan has demonstrated that inclusion in the national system has strengthened social cohesion in community settings. Teachers have received training in inclusive education, psychosocial support, and conflict-sensitive pedagogy[90]. These efforts have improved classroom dynamics and reduced discrimination against refugee students. Moreover, the deployment of Syrian volunteers in schools has strengthened communication between refugee families and school staff, enhancing trust and cooperation[91]. Shared learning environments where Jordanian and Syrian students engage in extracurricular activities, arts, and sports have been shown to reduce violence in schools and foster positive relationships between students of different backgrounds[92]. Programmes such as UNICEF Makani centres, which provide a safe space for children and young people to access learning opportunities, child protection and other critical services, and the GoJ NFE initiative, have targeted out-of-school children, many of whom are Syrian refugees. These programs have provided catch-up and dropout support, enabling reintegration into formal education and reducing social exclusion[93].
[90] Rauschenberger, E., & Sarabi, H. (2024). Temporary Contract Teachers in Jordan. ERICC Technical Brief.
[91] Selenica, E. (2025). Syrian Refugee Education in Jordan: Aid Effectiveness and Efficiency 2019–24 and New Pathways for 2025 and Beyond. ERICC Background Report.
[92] Salem, H., & Morrice, L. (2019). Social Cohesion in HC. UNICEF; Delprato, M., Morrice, L., & Al-Nahi, S. (2020). A Summary of Key Patterns in the Jordanian Education System. University of Sussex.
[93] UNICEF (2020). Jordan Country Report on Out-of-School Children.

Integration of services in the national system is not yet complete. As services continue to transition to the MoE, support will remain critical for those services remaining under UNICEF, including the camp school operations. Without this support, schools in camp settings would cease to operate, therefore excluding all camp-based refugee children from access to formal education. Slow transition, while challenging for UN agencies who have seen significant decreases in funding, has demonstrated some benefits. It has allowed operational and technical experience to be handed over, and UNICEF’s continued involvement in the camp schools has ensured additional services, including GBV and psychosocial support are provided to the most vulnerable students[94].
[94] Morrice, L. & Salem, H. (2023). ‘Quality and social justice in refugee education: Syrian refugee students’ experiences of integration into national education systems in Jordan’, Journal of Ethnic and Migration Studies, 49(15): 3856–3876.

This option maximises the finance directed towards essential humanitarian and education service delivery. As such it will make the most immediate and impactful contribution to meeting current critical needs. However, it will not include an IRF, limiting the UK’s ability to respond to emerging issues or new emergencies. It does not include support for system strengthening and therefore does not prioritise making strategic longer-term changes to the humanitarian, education and social protection systems, or support voluntary returns to Syria. This limits the sustainability of support, misses opportunities to enhance efficiency and effectiveness, crisis preparedness, reintegration in Syria, and means there is little preparation for a responsible partial exit from aid.
Option 2. Strategic and integrated approach combining lifesaving and life-changing service delivery (cash, protection, education) with support for voluntary returns, an IRF, and systems strengthening activities to deliver sustainable improvements in systems supporting refugees and vulnerable Jordanians.
Description and rationale
This builds on option 1. It would pursue all the activities listed under option 1, though scaled down, while complementing and expanding on them with additional activities to ensure FCDO can react quickly both meet changing immediate needs and building long-term resilience in line with our strategy for a responsible partial exit from aid. Additional components will include an IRF enabling FCDO to respond to emerging needs. Voluntary returns to Syria will also be supported to enable refugees to pursue their desired future in a dignified and informed way. Finally, activities will be complemented by system strengthening activities.

While the activities under option 1 would be pursued, they would receive moderately less finance to ensure resources for the additional components – with most financing to be reallocated from cash assistance. That said, humanitarian cash assistance and education support would still be prioritised overall in terms of programme resources.

This option would have the following components:
1. Core humanitarian assistance:
  1. Cash assistance transfers to the most vulnerable refugees.
  2. Protection services to refugees and HCs.
  3. Support to help refugees voluntarily return to Syria; and
  4. An IRF.

1. Education support:
  1. Contributions towards the costs of including of refugees in the national education system (including NFE) through financial aid (off budget).
  2. Contingency support for refugee camp school operations as services transition to the MoE.

1. Systems strengthening support:
  1. TA for the social protection and education sectors and deployments in the humanitarian, education and social protection sectors.

A detailed overview of the activities, for example priorities for systems strengthening support for each sector, is provided in the strategic case. Indicative results, which have been attributed the UK direct investments, under this option are set out in table 3.
Supporting evidence
The supporting evidence for Option 1 is also applicable for Option 2. As such evidence set out below focuses on the additional components added under option 2 to avoid duplication.

FCDO’s work on voluntary returns to Syria from Jordan will continue if initial work with UNHCR piloted under the JPP emergency facility continues to generate positive results. It will also be shaped through lessons learnt from it and similar initiatives in the region. As of 2 December, 2,201 refugees have received return cash assistance and confirmed departure from Jordan. Initial feedback from post-distribution monitoring has shown that + 90% were satisfied or very satisfied with support. Furthermore 94% indicated that the assistance did not significantly influence their return decision. But assistance made it financially possible to return or enabled them to do so sooner. This thus shows positive results and aligns with our approach for returns; helping those that already want to leave to do so. Initial evidence from this and UNHCR Jordan’s field engagement also suggests refugees prefer cash for returns rather than transportation (e.g. by organised buses) to support them with a wide range of costs associated with returning[95]. Cash assistance for return costs is thus anticipated to be continued and accompanied by counselling and legal support to address the practical barriers refugees are requesting assistance with, while adapting based on lessons learned.
[95] Current amount is $100 per refugee in line with the regional standard

Evidence from other FCDO humanitarian programmes highlights that IRFs have been pivotal in enabling rapid and flexible responses. For example, following the Taliban takeover, FCDO Afghanistan used its IRF to quickly disburse additional funds to United Nations Office for the Coordination of Humanitarian Affairs (OCHA)’s Country Based Pooled Fund– demonstrating to Parliament and Afghans the UK remains a donor which is well-prepared to respond to a sudden deterioration in need. The IRF has also saved considerable time in programme administration. BE Amman has also had positive experiences with the emergency facility under the JPP. This allowed BE Amman to meet pressing gaps in WASH in refugee camps in 2025 following the closure of the Emirati camp. Notably, the UK was the only donor to step in during this critical moment. It also allowed the UK to be the first donor to support voluntary returns to Syria following the change in Syria’s political landscape in December 2024.

BE Amman has used TA across the humanitarian, education and social protection sectors in recent years and seen positive achievements. For example, social protection TA to the SSC has supported the organisation to develop a long-term strategic reform vision, enabled the delivery of an innovative pilot for extending social insurance coverage to refugees and vulnerable Jordanians, while at the same time helping the SSC strengthen their systems and procedures. Current expectations based on ongoing discussions are that GoJ financing will partly replace donor financing in the next phase of the pilot. In education, TA has ensured inclusion of refugees in key policies and strategies. It has also strengthened the MoE’s capacity to manage off-budget financial aid and coordinate partners, allowing donors with humanitarian funding and no dedicated technical capacity to contribute to government delivery of education.

1. TA in the social protection sector will leverage significant resources. Through partnering with the WB, the financing will complement the Bank’s US$400m Resilient and Sustainable Social Protection (RSSP) Programme. RSSP supports the GoJ to implement the NSPS 2025-2033 through providing finance via a loan for social protection service delivery. Our finance will complement this by providing grant finance for TA and implementation support to help the GoJ implement their reform vision. Through this it will help the GoJ to maximise the potential from the loan and best use their existing social protection budget (US$700m per annum). Challenges for the GoJ in creating new budget lines for TA, using the WB finance for TA and the advantages of having the WB to support with TA procurements, means this finance will play a highly impactful role despite the relatively modest size of funding compared to GoJ’s budget.
2. TA and deployments to the social protection sector will enhance the national services supporting refugees and vulnerable Jordanians, helping reduce poverty, build resilience through enhancing the shock responsiveness of systems and promoting social cohesion and stability. Evidence increasingly shows the role of social protection in enhancing the resilience of poor households. Findings from the COVID-19 response in Jordan points to several relevant and positive impacts including mitigating income loss, reducing food insecurity, and maintain access to basic services[96]. An evaluation of the NAF found that economic activity increased among households and that children of household who are beneficiaries of its Unified Cash Transfer programme are consistently more likely to be enrolled in school and less likely to have a child drop out of school[97]. Rt Hon Baroness Chapman, the UK’s Minister of State for International Development, and H.E. Salah Ahmed Jama, Deputy Prime Minister of Somalia’s Federal Government, highlighted in November 2025 “growing evidence that social protection – local support delivered primarily through a country’s own systems – is among the most effective investments in stability and peace” [98].
  [96] Jordan’s National Social Protection Response During Covid-19, UNICEF August 2020
  [97] Harnessing Administrative Data for Impact: The Case of Jordan’s Unified Cash Transfer Programme
  [98] https://www.gov.uk/government/news/joint-statement-on-social-protection-in-fragile-and-conflict-affected-settings

The COVID-19 pandemic highlighted the importance of social protection globally in responding to shocks, with emerging and developing economies expanding their social protection spend by an average of 28%[99]. Lessons from the pandemic are that those with stronger pre-existing social protection systems, including digital infrastructure, could respond better. Additional research from low-income countries has also pointed to the importance of enhancing social registries and early warning systems to support shock-responsive social protection[100] which will be elements of our TA support to Jordan.
[99] Tesliuc and Fontenez (2025) Adaptive Social Protection Agenda: Lessons from Responses to COVID-19 Shock
[100] Pearson, R., Goodman, R. and Juillard H. (2025). Comparative analysis of shock-responsive social protection systems, Social Protection TA, Advice, and Resources Facility (STAAR), DAI Global UK Ltd, United Kingdom

FCDO successfully supported Jordan to respond to the pandemic via FCDO’s ESPJ programme. This successful £34m programme, scoring an A+ at closure, provided financial support to Jordan’s emergency cash transfer programme ‘Takaful’[101] and combined this with TA, including to build on previous UK support to digitalise assistance. The programme channelled most of the funding via the WB and the close collaboration with the WB, GoJ and other donors is credited to its success. External research has reinforced that Jordan responded well to the crisis and praised its digital support, which this collaboration contributed to[102]. Jordan wishes now to build on the pandemic response and has included a shock responsive pillar in its new NSPS 2025-2033. In line with international research, this looks to strengthen links with an EWS, enhance coordination structures, link the response to the national budget and prepare protocols and staff to respond. The NSPS also seeks to expand Jordan’s unified social registry and link it to the EWS which will support efforts. JHASS will build on this successful project to help Jordan achieve this vision and be better prepared to respond -and finance- future crisis responses.
[101] Through the emergency cash transfer programmes Takaful 2 and Takaful 3, UK support helped reach a total of 241,332 households and 154,690 households respectively. In addition, UK funding contributed to supporting the NAF annual winterisation programme that targeted 105,537 households, and the quarterly cash increase provided to 9,817 households that were part of the original NAF monthly cash transfer programme
[102] UNICEF (2020) Jordan’s National Social Protection Response During Covid-19

Enhancing national social care services is important for individual and family well-being, economic growth and women’s economic empowerment. Globally, research has shown investments in the care economy remain insufficient, leaving gaps in services and them often being unaffordable and low-quality where they do exist[103]. As such unpaid carers have to fill the gaps and these are largely women both globally and in the Arab region[104]. Inadequate public care provision can leave care users facing catastrophic out of pocket costs and affect family caregivers’ income, education and mental health. Enhancing public social care thus has the potential to support individual and family wellbeing. It also can support women’s economic empowerment and economic growth through enabling unpaid caregivers - often women -to participate more fully in the workforce, boosting productivity. The creation of formal and decent care jobs would also create jobs for women who make up much of the care workforce[105], including in Jordan[106]. In Morocco investing in pre-school services - a sector with many similarities to the care sector - generated 9500 jobs, supported women’s economic empowerment and built human capital[107].
[103] ILO (2025) Care Economy Brief: Employment-intensive investments for advancing decent work in the care economy.
[104] 80-90% of unpaid care work is performed by women in the Arab region. Source: ESCWA: Advancing Care Economy in the Arab Region.
[105] Cylus et al 2005, The Care Dividend: Why and How Countries Should Invest in Long-term. ESCWA: Advancing Care Economy in the Arab Region
[106] A study suggested 61% of social service workers were female in Jordan. Source: UNICEF (2023) Multi-Country Review of the State of the Social Service Workforce in the Middle East and North Africa Region
[107] https://www.worldbank.org/en/news/feature/2025/09/24/from-vision-to-impact-preschool-enrollment-soars-in-morocco

Investing in social care is also important for societal well-being and cohesion. It has been argued that a major injustice in society is the vicious cycle of care inequities, where those in lower socioeconomic positions receive less adequate care which in turn puts them and their families in an economically disadvantaged position. Systems that meet care needs can help stop this vicious cycle and promote social justice[108]. Evidence suggests that reducing horizontal inequality in a society can also contribute to stability[109]. A strong care system is also thought able to boost social solidarity/cohesion by building empathy, trust and responsibility between society members. In Jordan, the inclusion of refugees in the public care systems makes this an important benefit.
[108] Tronto, J. (2013). Caring democracy: market, equality, and justice. New York, NY: New York University Press
[109] Walton (2025): Social welfare, conflict and conflict prevention: a literature review

1. Professionalising the care workforce through licensing, accreditation, and competency standards improves service quality for vulnerable groups. Evidence shows that quality of care is influenced by the skills and expertise of staff and as such for many countries, professionalising the workforce is a key strategy for improving the quality of long-term care[110]. Middle-income countries such as South Africa are also advancing in this area[111], and similar efforts have been called for and are emerging in the Arab region. Lebanon, for example, is working to enforce better social care service standards[112]. The professionalisation of social work is also a key priority in Jordan as set out in the NSPS 2025-2033. Helping strengthen Jordan’s care system would create a broad range of benefits for Jordan citizens and refugees in terms of the well-being and financial security of vulnerable people, women’s economic empowerment and social cohesion.
  [110] Cylus et al 2005, The Care Dividend: Why and How Countries Should Invest in Long-term
  [111] South African Council for Social Service Professions: Strategic Plan for 2023/24 to 2027/28
  [112] National Social Protection Strategy for Lebanon, 2023
2. Deployments have also been used in recent years across all three sectors and have enabled us to strengthen the use of evidence in the humanitarian system and build coordination between the MoE and education sectors. The FCDO Economist and Statistician deployed to UNHCR have significantly advanced evidence-based policymaking in Jordan’s refugee response, aligning with the Grand Bargain’s goals of inclusivity, transparency, and collaboration. Key achievements include the Refugee Skills Mapping project and economic contribution analysis, which informed national labour policies, and strategic improvements to UNHCR’s socio-economic data, enhancing its utility for advocacy and resource allocation. Their combined efforts have strengthened humanitarian-development linkages and enhance collaboration between UN agencies. The economist deployed to UNICEF has strengthened GoJ systems by refining Public Expenditure Review (PER) analysis and translating fiscal findings into recommendations for implementing the NSPS and supporting its Monitoring and evaluation capabilities. Providing a secondee to the MoE has delivered improved reporting coordination, strengthened the relationship with the Ministry by improving trust and transparent engagement, and enabled access to a wider set of technical committees and discussions, that we previously would have not had access to. Given the reduction in US technical capacity, the GoJ is now heavily reliant on the FCDO secondee for implementing and oversight of their Government-to-Government agreement which supports the MoE on refugee education.
Option 3. Do nothing – no further support to meet the acute needs of refugees in Jordan or their HCs.
Description and rationale
This option would stop humanitarian funding to the refugee response in Jordan and see us exit the humanitarian, education and social protection sectors. The rationale would be to reserve UK ODA for other contexts. No outputs would be pursued, and no results would be achieved.
Supporting evidence
A decision to stop humanitarian funding to the refugee response in Jordan would have an immediate and detrimental impact on a significant proportion of the 458,246 registered refugees in Jordan, and on Jordan’s own stability (compared to option 2 approximately 58,200 direct beneficiaries per annum would not receive support and over 2,000,000 with an associated link). See table 3 below. As a major and influential donor particularly in the Livelihood (cash), Education and Protection sectors, it will deteriorate the conditions of the most vulnerable groups and impact the country’s stability. As humanitarian needs continue to rise and overall funding declines, the withdrawal of UK humanitarian support is likely to have a significant negative impact. It may also contribute to a broader trend, as many donors have already reduced their humanitarian and ODA funding this year. Food insecurity and negative coping strategies will increase as well as protection risks rising, as well as threats to social cohesion and regional stability. As a leading humanitarian donor in Jordan and the region, a decision to stop supporting humanitarian programmes in Jordan would also carry significant reputational risks.

Under this option (as for the others) the FCDO as a major shareholder to the WB will continue to influence the Global Concessional Financing Facility (GCFF) funding in Jordan and other Bank projects. There is a pipeline of projects developed by the WB and the GoJ, including under the GCFF. Influencing these projects has been limited and the GoJ has signalled that it is no longer willing to borrow to support projects which primarily benefit refugees living in Jordan. Therefore, there is unlikely to be direct funding for humanitarian interventions which primarily target refugees through the GCFF and while GCFF projects could make some enhancements to national education and social protection systems this is not a credible option since it would not provide core humanitarian assistance which is a central component of the programme. Other WB core-funded programmes (e.g. social protection) will have positive impacts for refugees but only via the parts of national social protection systems inclusive of refugees. As such without complementary humanitarian aid, important gaps are left (e.g. humanitarian assistance is needed since refugees can’t access national social assistance). WB social protection financing in Jordan also requires complementary donor grant financing (e.g. for TA).

Exiting the sector at pace will have significant negative implications on the most vulnerable refugees who are already resorting to irreversible negative coping strategies e.g. reducing food intake, child labour, early marriage. Donors which rely on UK technical expertise may cease to support certain sectors, such as education, which in turn could trigger a reversal of the policy allowing refugee access to the national education system on current terms. During 2025 the GoJ initially proposed charging refugees’ fees, and although this was quickly withdrawn, discussions are ongoing. Given current levels of vulnerability amongst refugees, it is highly likely that if such a policy is implemented it would trigger a high level of drop out of school aged refugee children. The UK is a key donor to social protection in Jordan. Without UK support, the implementation of the new NSPS and the ability of GoJ to continue to utilise a $400m WB loan would be negatively impacted. This would be a missed opportunity to strengthen the national social protection system in line with stability aims and our strategy for a partial exit from humanitarian aid in terms of pursuing a transition from protection services to national social care and building resilience to future crises. There will be missed opportunities to generate wider economic spillovers such as local multiplier effects from cash transfers and increased productivity through better education outcomes[113].
[113] Sala-i-Martin (1997) A labor income-based measure of the value of human capital. Japan and the World Economy 9.2: 159-191.

FCDO is currently playing a leading role in both policy influencing and donor coordination forums which could not be fully sustained without UK funding in these areas. The UK is represented in the JOSH and the Education Development Partner Group (EDPG); chair of the refugee education donor group; a steering committee member of the JDPG and co-chair of the DPG, and active participant in the Social Protection Donors Group which is was a recent co-chair of, all of which give us leverage over the overall humanitarian response in Jordan. We would no longer be seen as a credible partner in Jordan, including in key UN donor fora, such as the JOSH where decisions on the response are made and the UK is a permanent member. This could also affect our broader UK-Jordan defence and security partnership.

Table 2 outlines the anticipated sectors, geographic coverage, and target beneficiaries. These projections are subject to change due to the rapidly evolving context.

Table 2: Summary of sectors, geographical coverage for each option
CRITERIA	OPTION 1	OPTION 2	DO NOTHING
Summary	Focus on life-saving humanitarian assistance	Strategic and integrated approach: lifesaving and life-changing services and system strengthening	No further support for the refugee humanitarian response, education and social protection sector in Jordan
Geographic coverage	Targeting the areas with the most humanitarian needs, and high levels of vulnerability. Recognising 82% of registered refugees live outside of camp settings in HCs.	Targeting the areas with the most humanitarian needs, and high levels of vulnerability. Recognising 82% of registered refugees live outside of camp settings in HCs. / National systems strengthening activities will benefit whole country	Exit the refugee response in Jordan. The impact will be felt most strongly in the poorest communities and among the most vulnerable refugees.
Sectoral coverage	Humanitarian cash assistance / Protection services / Education Support	Humanitarian cash assistance / Protection services, including community activities / Education support / Support for voluntary returns / Systems strengthening for humanitarian, education and social protection sectors	No further support for the refugee humanitarian response, education and social protection sector in Jordan.

Table 3 summarises the indicative output level results for each three options. This draws on our understanding of unit costs from previous programming. Further information on unit costs is provided in table 6.

Table 3: Summary of indicative output level results for each option[114]
[114] Estimated results have been calculated for each year according to the detailed budget in Annex F and then the average calculated over the period of the programme to produce the per annum figure presented. For cash, protection and returns, the figures assume the UK is meeting 100% of the costs. For the education figures, donors pay a co-financing cost, which shares the full cost of educating a child with the GoJ. The co-financing cost covers 27% of the full cost of a pupil. As such the results presented show the number of pupils which this programme funds at 27% of the costs of a pupil.
Component	Subcomponent	OPTION 1	OPTION 2	OPTION 3
Core Humanitarian Assistance	Cash	41,000 beneficiaries (refugees) to be supported per annum with cash assistance for basic needs	27,000 beneficiaries (refugees) to be supported per annum with cash assistance for basic needs	0 beneficiaries
	Protection	10,100 beneficiaries (refugees and vulnerable Jordanians) for GBV prevention and response and child protection per annum.	8,100 beneficiaries (refugees and vulnerable Jordanians) for GBV prevention and response and child protection activities per annum.	0 beneficiaries
	Returns	N/A	6,600 beneficiaries (refugees) supported per annum with counselling and cash assistance to voluntarily return to Syria	0 beneficiaries
Education support	No. of children FCDO is paying co-financing cost	17,000 beneficiaries (refugee children) supported per annum to attend a national school	16,500 beneficiaries (refugee children) supported per annum to attend a national school	0 beneficiaries
Systems Strengthening	Social protection TA & deployment	N/A	Shock responsiveness of social protection system enhanced: through testing protocols to activate social protection support based on the EWS, conducting simulation exercises and training to strengthen preparedness and coordination among MoSD, NAF, and NCSCM. An associated link to the 250,000 NAF beneficiaries[115]. / Expansion of Jordan’s Unified Social Registry: through support to GoJ to expand and enhance Jordan’s Unified Social Registry. Will support the GoJ to expand from current 50-60% population coverage to their target of 80% coverage by 2029 supporting their integration into shock responsive social protection systems. An associated link with at least a 20% population coverage increase which is over 2m people. / Strengthen social care: through expanding the professionalisation of social work including by helping operationalise the Social Work Licensing Unit and developing a digital accreditation system for social workers. Will launch a Women in Social Work Fellowship to benefit at least 200 women.	0 beneficiaries
[115] The systems strengthening support will have some impact on the current 250,000 NAF caseload but the causal chain is too far to claim direct attribution

Note: Beneficiary numbers are neither cumulative nor mutually exclusive, as individuals may receive multiple types of assistance. For example, a beneficiary could receive both humanitarian cash assistance and protection services, or a family might have a child benefiting from education support while also receiving cash assistance.
Assessment of options
Step one of the Appraisal Case will qualitatively assess the options against the critical success criteria.
Table 4: Critical success criteria
Critical success factor	Relevance of the programme
Strategic Fit	How the programme fits with FCDO priorities – Development, Security, including the four essential shifts / How the programme fits with FCDO humanitarian approach/key shifts / Support Jordan’s stability and regional stability. / Prevent future crises and building resilience as well as maintaining the UK’s role as a leading humanitarian actor
Value for money	Rigorous value for money processes in place, considers rates of return and cost effectiveness in decision-making. / Focus on equity and how the programme targets the most marginalised and protects against shocks to maintain stability. / Level of overhead costs and ability to control administrative costs / Ability to start quickly delivering programme activities and results. / Low administration burden for FCDO
Scope and ability to adapt and respond to contextual change	Flexible to adapt to future risks and allocate resources to critical needs. / Ability to respond to any new humanitarian emergencies. / Agility to seize critical opportunities as they emerge. / Convening power and credibility towards decision makers
Technical and programme management capacity to deliver	Maximises the reach of UK financial support within the constraints of UK staffing. / Resources, competency, and experience in complex programme management / Good financial accountability and transparency; effective leadership and governance; strong risk management, fiduciary oversight, and results monitoring
Sustainability and exit strategy	Seek to strengthen national systems, to support resilience and prevent further increase in vulnerabilities. / Ability to build the capacity of others, particularly, local NGOs to continue driving the agenda forward after the programme ends. / Ability to help reduce pressures on Jordan from hosting refugees

Below analyses the strengths and weaknesses using evidence of each option have also been assessed against the challenges outlined in the strategic case.

Option 1. Focus support on lifesaving and life-changing service delivery, prioritising humanitarian cash assistance, protection, and education.
Strengths
- The programme will partially support the FCDO’s humanitarian priorities – it will align with the ‘prioritise’ and ‘protect’ approach.
- Interventions will focus on areas where the evidence outlines the highest impact e.g. humanitarian cash assistance, and where the needs are greatest. Cash assistance empowers poor and vulnerable people to make their own decisions and supports the local economy by enabling people to spend in their own communities[116]. This option enables higher spend on cash assistance.
  [116] Evidence from the International Rescue Committee (IRC (2014), Emergency Economies: The impact of cash assistance in Lebanon) and the Lebanon Cash Consortium (Battistin, F. (2016), Impact Evaluation of the Multipurpose Cash Assistance Programme) found that each dollar that beneficiaries spend generates $2.13 of GDP for the Lebanese economy compared to $1.51 for vouchers.
- Protection services have also been found to be effective in supporting vulnerable refugees and Jordanians; this option allows protection services to reach more beneficiaries.
- Given increased number of beneficiaries would be reached by cash assistance, protection services and education this option is likely to make the greatest impact in terms of meeting immediate humanitarian needs and slowing the decline in well-being outlined in the strategic case.
- We will work through well-established UN delivery partners in country, including UNHCR, WFP and UNICEF. This option will provide good VfM through better cost-effectiveness[117] by working through existing humanitarian systems developed by UN agencies.
  [117] In a humanitarian response, speed of response is considered to be a critical humanitarian metric Value for Money of Cash Transfers in Emergencies
- There will be a strong focus on VfM by targeting greatest needs building on the evidence of cost-effective interventions based on the best buys. Supporting access to national systems – such as education – is more cost effective than running a parallel system that would not benefit from economies of scale achieved through a national system or provide children with accreditation or certification.
- This option is less complex and would encounter less administration than option 2 as it would involve working with five rather than six core partners.
- There will be technical capacity to deliver the programme based on existing FCDO capacity.

Weaknesses
- There will be limited sustainability and exit strategy. This option will have no focus on refugee returns, UN reform, systems strengthening including enhancing national responses to shocks meaning that more humanitarian support will be required in future years.
- Opportunities to promote stability in Jordan through enhancing resilience, the social contract and social cohesion through improved social protection would be missed.
- The programme would not align as well with FCDO priorities and shifts particularly in terms of FCDO’s increased focus on systems strengthening, localisation, expertise and misses the ‘prevent’ element of FCDO’s humanitarian approach- a key shift which relates to crisis prevention.
- The absence of an IRF means that FCDO’s capacity to respond quickly to emerging risks – important in this uncertain regional context – would be significantly limited. Responding to emerging issues would require a new programme which would slow FCDO’s response and require more administrative time.
- Evidence shows that when the humanitarian sector can respond quickly to new crises it can prevent worsening conditions and avoidable humanitarian losses. Delays can double the impact, while early intervention is more cost-effective and minimises harm. This options misses’ opportunities to enhance the humanitarian sectors crisis preparedness and contribute quickly via the IRF.
Option 2. Strategic and integrated approach combining lifesaving and life-changing service delivery (cash, protection, education) with support for voluntary returns, an IRF, and systems strengthening activities to deliver sustainable improvements in systems supporting refugees and vulnerable Jordanians.
Strengths
- This option will make an impactful contribution to humanitarian needs through still supporting humanitarian cash assistance and protection services. Although funding for these will be at a lower level than option 1, funding will be sufficient to enable us to retain the UK’s as a leading humanitarian actor committed to proactive and effective response and our convening position in humanitarian coordination groups. The cash support in particular is a highly cost-effective intervention. Monitoring from WFP shows that even modest transfers significantly improve food security and help maintain basic dietary diversity even in crisis. Refugees overwhelmingly report that cash improves their lives, mainly by reducing financial stress and enabling choice[118]. As with option 1 this option will provide good VfM through better cost-effectiveness for the UK by working through existing humanitarian systems developed by UN agencies.
  [118] Cost of Inaction: The Impact of WFP Assistance Cuts on Refugees in Jordan
- This option will include an IRF, enabling us to react quickly and efficiently to emerging humanitarian needs and will also enable us to strengthen the humanitarian sectors crisis preparedness.
- This option aligns well with all FCDO’s humanitarian priorities (protect, prioritise and prevent) and key shifts as well as FCDO’s broader development direction through its focus on localisation, systems strengthening and expertise.
- Sustainability and supports our strategy from a responsible partial exit. This option will strengthen national systems (e.g. education and social protection), international systems (humanitarian) and build local capacities to deliver protection services, thus creating sustainable improvements to services for refugees and vulnerable Jordanians. It will also support voluntary returns to Syria helping reduce humanitarian needs in Jordan. Together this will reduce the need for future UK humanitarian aid.
The FCDO has high technical and sectoral capacity to deliver the programme which has been built by over 14 years of investments in Jordan and is relied upon for our expertise by several donors, including key partners such as Norway, Australia, Canada, the US and Germany.
This option will help do more to promote stability in Jordan by enhancing resilience and fostering social cohesion. It will adopt a holistic humanitarian approach that goes beyond cash and services to safeguard dignity and well-being, with protection as a core pillar. This includes preventing and responding to gender-based violence, child protection risks, and other vulnerabilities, ensuring that assistance is safe, inclusive, and rights-based.
Weaknesses
- This option will reach less direct beneficiaries with cost-effective humanitarian cash assistance, protection services (focused on GBV and child protection) and education support and as such make a less strong impact on maintaining education access. However, the programme will make a strong and lasting contribution through strengthening systems which will have an associated impact on those receiving services in the social protection, education and humanitarian sectors. This is expected to include significant numbers of vulnerable Jordanians receiving social assistance and refugees and vulnerable Jordanians receiving social care services (for example 250,000 NAF beneficiaries with more shock responsive social protection and approximately 2,000,000 added to the unified social registry).
- This multisectoral programme will still require slightly higher administration costs, since it will involve working with six rather than five core partners under option 1. It also involves a higher degree of complexity due to additional components.
Option 3: Do nothing – no further support in Jordan to meet the acute humanitarian needs of refugees
Strengths
- Cost-savings, no immediate financial outlay is required. FCDO would be able to prioritise resources elsewhere.
- Some limited technical expertise needed to close down programmes and therefore less resource intensive. BE Amman staff could focus instead on advocacy and development diplomacy.
Weaknesses
- A sudden UK exit from humanitarian aid would signal disengagement, potentially weakening Jordan’s political will to support shared regional objectives including on Syria and/or migration, at a time of increasing regional polarisation. It would also significantly reduce our ability to influence the design and implementation of the international response in Jordan, including through national coordination frameworks such as the JRP. Exiting humanitarian aid in Jordan would limit our role in shaping donor harmonisation efforts, and policy dialogue on key issues such as refugee inclusion, linkages with social protection, linkages, and localisation. This will also impact on our objectives to provide humanitarian support to Gaza via the Jordan Hashemite Charity Organization (JHCO). The UK would suffer a serious reputational hit. In this vacuum, other actors may step in with approaches less aligned to UK priorities on resilience, migration, and principled humanitarian action, potentially reshaping the operating environment in ways that are harder to reverse. UK aid supports our broader security, defence and diplomatic partnership in Jordan and assuming the funding is returned to centre exiting the humanitarian sector will undermine our ability to deliver other UK objectives in Jordan including security and supporting regional stability. Through this option FCDO priorities (development, security) will not be met.
- Exiting the refugee response completely will lead to refugees facing increasing poverty, malnutrition, protection risks and poor education outcomes. Withdrawal of UK aid from education may trigger other donor countries to follow suit and result in the GoJ reversing the policy allowing access to the national education system. Social tensions may rise due to perceived competition over resources between refugees and HCs. All of these impacts will be harmful towards achieving FCDO’s priorities.
- This option is low VfM. Existing programmes such as education for refugee children and crucial life-saving infrastructure in camps could collapse without ongoing FCDO support. Previous gains from years of investment in refugee inclusion, resilience and infrastructure could be undone.
- Exiting the sector will disrupt the capacity of the refugee response in Jordan. There will be limited ability to adapt or support changing contexts. This will leave Jordan more exposed to shocks which can have a destabilising impact and would miss an opportunity to strengthen the ability of social protection to help respond to shocks as well as cushion necessary economic reforms.
- This option will not support sustainability or a responsible exit from the refugee response in Jordan. There will be missed opportunities to continue to influence and enhance the impact of spend of other development actors including a $400m WB social protection loan as well as broader humanitarian and multilateral reform. Opportunities to enhance resilience and strengthen the social contract and social cohesion which would support stability in Jordan through strengthened social protection would also be missed.

Preferred programme option: Option 2. Delivers the best fit with priorities by combining lifesaving and life-changing service delivery with support for voluntary returns, an IRF, and systems strengthening activities to create sustainable improvements in systems supporting refugees and vulnerable Jordanians and to prepare for a responsible partial exit from humanitarian aid in Jordan. Our previous programmes have amply demonstrated a positive impact in providing essential services to those in need. A new strategic, integrated multi-sectoral programme in Jordan represents good VfM and will lead to better outcomes than siloed interventions. It will best allow FCDO and partners to deliver against the challenges and opportunities outlined in the strategic case and the ability to be flexible to respond to the changing regional context. It will be the most effective way to leverage humanitarian reform in country by engaging a wide set of actors. The programme will therefore address the missing pieces – it will deliver flexible and adaptable services to meet basic needs, support life-changing services, such as education, and will create sustainable improvements in systems supporting refugees and vulnerable Jordanians to promote human development, cohesion and build resilience against future crises.
STAGE 2: APPRAISAL OF DELIVERY OPTIONS
The second appraisal assesses the different delivery options we could choose to achieve the programme’s priorities through the recommended sectoral option (option 2). The same success criteria in table 4 were used. The chosen delivery channel will have implications for the ability of the programme to deliver the benefits identified in table 4.

Three delivery channel options are considered:
- Option 1: Deliver the programme through a small number of UN agencies (UNHCR, WFP and UNICEF) and financial aid to the MoE only
- Option 2: Deliver the programme through a limited number of core partners including certain UN agencies, a consortium of NGOs, the WB and financial aid to the MoE
- Option 3 Multi-pronged and diverse delivery approach working with a range of partners (UN, INGOs, National NGOs, different GoJ institutions, private sector)

Option 1: Deliver the programme through a small number of UN agencies (UNHCR, WFP and UNICEF) and financial aid to the MoE only
Delivery through UN agencies will permit strong sectoral and geographic coverage due to the unique mandates of the UN agencies (UNHCR refugees[119], WFP food security[120] and UNICEF on children) as has been the current experience with UN delivered programmes. UN agencies operate in the camps and are present in governorates where the majority of refugees reside e.g. Amman, Mafraq, Irbid, Zarqa. Delivery through multiple UN agencies would allow for bringing together the different skill sets, experience, capacity, and mandates of the organisations. This will allow for strong analysis to inform our policy priorities. At the same time, UN agencies provide strong technical inputs, they can scale up quickly and potentially they are less time consuming to manage than NGO partners, we have seen strong performance from WFP, UNHCR and UNICEF under our current programmes, with the agencies providing complementary life-saving humanitarian support to refugees in Jordan. UNHCR and WFP's comparative advantages in providing cash assistance, in terms of collective impact and burden-sharing[121], have been proven through their successful track records in various humanitarian crises globally and UNICEF has successfully provided camp school operations in Jordan[122]. UN agencies have adopted responsive management approaches to maximise impact in a protracted crisis and are trusted partners to GoJ. Support to the UN allows us a seat at the table, potentially giving us influence greater than our contribution.
[119] Asylum seekers in Jordan are required to register with UNHCR on a yearly basis to issue legal documents that allows them to access services in Jordan and this enables UNHCR to collect data on the vulnerabilities of refugees. UNHCR, Jordan Factsheet https://data.unhcr.org/en/documents/details/114827
[120] Jordan country strategic plan (2023–2027) | World Food Programme
[121] Programme completion report, Multi-purpose Cash Assistance to Refugees in Jordan
[122] BRIDGE, Annual review

UN actors (UNHCR and UNICEF primarily) could deliver certain protection services, however their geographical reach or level of trust by communities is not always as high as NGOs and it would miss opportunities to build local capacities through working with local NGOs. UN agencies (WFP and UNICEF) could also provide TA to the GoJ on social protection. However, this option would miss opportunities to align efforts closely with the WB who are leading international support currently for the implementation of the NSPS 2025-2033.

Maintaining off-budget financial aid to the GoJ for access to education for refugees is the only option currently to feasibly ensure refugee children can receive quality, equitable education, and benefit from the full breadth of government education services (including Kindergarten, education up to grade 12, and NFE). If the GoJ decides to completely reverse the policy allowing access, then support through the UN (UNICEF) may become necessary to ensure children have access to informal education - although we have not had any indications that this policy change is likely.

Option 2: Deliver the programme through a slightly broader but still limited number of core partners including certain UN agencies, a consortium of NGOs, the WB and financial aid to the MoE
This delivery option involves accompanying the UN agencies (UNHCR, WFP UNICEF) and financial aid to the MoE with delivering protection services via a consortium of NGOs (three to four NGOs including at least two local NGOs, led by an INGO) and TA for social protection via the WB. It seeks to work with the delivery partners best placed to deliver activities and as such envisions a slightly higher number of partners than option 1 (six rather than four) but still aims to limit the number of partners to a core of six.

This blended approach will bring the advantage of working with partners according to their added value in delivering programme components. NGOs are often the delivery partners deployed in the community driven development approach and have expertise in protection activities in Jordan. Delivering through them also would support the localisation of protection services and building of local capacities in line with FCDO’s humanitarian approach which prioritises localisation[123]. That said, NGOs particularly local NGOs may not have the same level of influence with the GoJ if needed during implementation to address challenges.
[123] Noting also that previously reliant on INGOs and direct implementation, UNHCR Jordan is now shifting toward localization, having most downstream partners being national NGOs.

As with option 1, maintaining off-budget financial aid to the GoJ for access to education for refugees is the only option currently to feasibly ensure refugee children can receive quality, equitable education.
Option 3 Multi-pronged and diverse delivery approach working with a range of partners (UN, INGOs, National NGOs, WB, GOJ, private sector)
This option is a multi-pronged and diverse delivery approach, engaging a diverse range of partners (UN, INGOs, National NGOS, different GoJ institutions, WB, private sector) according to their specific areas of expertise. This option would continue to deliver humanitarian cash assistance via UNHCR and WFP and education services via UNICEF and off-budget financial aid to the MoE. Instead of delivering protection services via an NGO consortium it would involve entering into agreements directly with a range of INGOs and NGOs to deliver services. TA would also be delivered via a range of partners (UN agencies, WB, private sector, NGOs).

This delivery model focuses on a diverse approach and would ensure collaboration with the most effective institutions in each specific area of intervention. Direct engagement with NGOs instead of via a consortium model would increase FCDO oversight and direct communication with all NGO partners. A multi-pronged approach- with a broader range and large number of partners- would also promote competition and diversity in the aid sector in Jordan. However, this option would be much more complex and administratively complex to manage for FCDO.
Table 5: Assessment of delivery options
Criteria	Option 1: Deliver the programme through a small number of UN agencies (UNHCR, WFP and UNHCR) and financial aid to the MoE only	Option 2: Deliver the programme through a slightly broader but still limited number of core partners including certain UN agencies, a consortium of NGOs, the World Bank and financial aid to the MoE	Option 3 Multi-pronged and diverse delivery approach working with a range of partners (UN, INGOs, NNGOs, World Bank, GOJ, private sector)
How the programme fits with FCDO priorities	Medium / Able to operate at scale, though with limited opportunities for donor influence over programme design and implementation. This option does little to build local capacities in line with FCDO’s humanitarian approach.	High / Having a slightly broader portfolio of core partners would increase opportunities to work with the most effective and well-placed partners (e.g. WB on social protection).	High / This option would enable FCDO to work with a broader range of partners and those best placed to deliver priorities around TA/evidence. Delivering directly with NGOs rather than via a consortium unlikely to provide significant benefits to meeting priorities.
Value for Money (cost-effectiveness and equity)	High / Strong UN collaboration in providing multi-sectoral support, but higher administration/overhead costs due to costly parallel systems. / Delivering through a one UN approach has been challenging in past programmes. / Inclusion of refugees through national systems in education prevents the need for costly parallel systems.	Very High / Humanitarian crises are rarely one-dimensional. This approach allows for context-specific interventions. / Enables working with best placed partners (NGOs on protection and WB on social protection TA) making support cost-effective. / Inclusion of refugees through national systems in education prevents the need for costly parallel systems.	Medium / Greater management oversight required for larger number of agreements and partners and higher transaction costs. / Inclusion of refugees through national systems in education prevents the need for costly parallel systems.
Scope and ability to adapt and respond to contextual change.	High / UN agencies use early warning and try to anticipate emergencies but currently a lot more work is required, and UN expertise is more limited in some sectors.	Very High / Good room to flex through existing UN agency partners and NGO consortium who collectively have diverse expertise to respond to needs.	High / Direct agreements with partners limits opportunity to provide a coordinated response to new challenges compared to NGO consortium.
Technical and programme management capacity to deliver.	High / UN require little management capacity, reducing requirements on technical advisors and programme management. However, these partners offer less oversight and engagement, including on UK compliance priorities.	Medium / Slightly more partners but still limited to a manageable core number. NGOs often require higher management inputs and technical oversights to reduce risks – in this option FCDO engagement limited to lead consortium INGO. They can offer better-quality engagement and accountability.	Low / NGOs often require higher management inputs and technical oversights to reduce risks- agreements with different NGOs would increase programme oversight time. This diverse and multi-pronged approach would require most FCDO capacity.
Sustainability and exit strategy.	Medium / There will be some systems strengthening that improves humanitarian, social protection and education sectors to promote human development and build resilience – but misses opportunity to strengthen Social Protection via best placed partner. No opportunity to build local capacities in this option with NGO partners.	High / Ability to strengthen systems via best placed partners and build capacities of local organisations via the NGO consortium.	High / Ability to strengthen systems via best placed partners and build capacities of local organisations via working with NGOs.
TOTAL	Medium/High	High	Medium

Preferred delivery option: Option 2 would be the best option for delivering this programme in Jordan based on current partner capacity, expertise, trends in the context and risk management. It would allow for a combination of humanitarian and development partners that would have the capacity and capability to deliver and scale up when needed in areas where there are the greatest humanitarian needs and be adaptable to changing contexts. It enables FCDO to work with the best placed partners (WB on social protection TA and NGOs on protection) and to build local capacities through supporting NGOs in line with our strategy for a responsible partial exit. At the same time, it would limit delivery routes to through only six core partners – streamlining our deliver and creating a simpler programme and more efficient programme administration than under option 3.

STAGE 3: ECONOMIC APPRAISAL AND VfM STATEMENT
Cost and benefits of JHASS
Table 6 below provides an estimate of the costs and potential benefits of the programme, in terms of the number of beneficiaries. It is a guide to what each component may cost, what it will “buy” in terms of support to the affected people, and how many people will benefit. This will be updated in line with negotiations with partners, needs assessments and when details of the programme implementation are worked out. The costings per beneficiary are based on what was delivered in previous humanitarian programmes in Jordan.

Table 6: Costs per beneficiary of key interventions
Programme delivery elements	Indicative budget (£m)	Activities	Number of beneficiaries	Estimated cost per beneficiary (£)[124]
Humanitarian: cash assistance via WFP and UNHCR	25	Cash Assistance	27,000 per annum	233 per annum[125].
Humanitarian: Protection via NGO consortium- GBV and Child Protection activities (based on estimations from JPP)	4.2	Psychosocial support and case management	1,200 per annum	586 (psychosocial support) / 402 (case management)
		Family and child helpline	3,500 calls answered per annum	8 per call answered
		Parenting and GBV programmes	3,400, participants per annum	92 - 233 per participant, depending on type of programme
Humanitarian: Returns via UNHCR	2.5	Cash for returns and counselling	6,600 participants per annum	94 per participant (including cash for transport and counselling)
Education via MoE	23	Donor co-financing of cost per pupil	16,500 per annum	349 per annum. (co-financing cost[126])
[124] Includes management fees where these figures are available.
[125] Our contribution is part of a broader, multi-donor effort supporting UNHCR and WFP cash assistance programmes. In Jordan, WFP applies the Severe Expenditure Basket (SEB), which focuses on lifesaving needs rather than the full Minimum Expenditure Basket. By complementing other donors, our funding helps ensure that the most vulnerable refugees particularly those who are unemployable and meet essential needs such as food and rent. Value for money is achieved through pooled resources, shared delivery systems like the Common Cash Facility, and joint targeting, which reduce duplication and transaction costs. WFP has reduced assistance to 15 JOD/person/month, but monitoring shows there is an impact. Households receiving 15 JOD were significantly more resilient than those receiving only 10 JOD or nothing.
[126] Donors cofinance the cost of students’ school with the GoJ. The unit cost is the donors cost, not the full cost of educating a child.

Note: Beneficiary numbers are neither cumulative nor mutually exclusive, as individuals may receive multiple types of assistance. For example, a beneficiary could receive both humanitarian cash assistance and protection services, or a family might have a child benefiting from education support while also receiving cash assistance.
Regarding choice of interventions under this programme, we will prioritise humanitarian cash assistance, refugee education, and TA for social protection in terms of the budget based on strong rigorous evidence on the cost-effectiveness of these interventions and alignment line with the FCDO best buys. Cash assistance will receive the greatest budget allocation (34%), closely followed by financial aid to MoE (31%), followed by social protection TA (16%) a lower amount and then all other activities (19%). There will be key points of monitoring within the programme, which will assess whether the funding allocation components are right, based on where the humanitarian needs are greatest. This approach aims to safeguard the progress achieved over more than a decade of humanitarian investments in the country, support Jordan’s stability, and facilitate a responsible partial exit if the situation permits.
VfM OF AN INTEGRETED APPROACH
Investing in measures to reduce humanitarian needs in an effective, timely manner represents strong value for money and is considered a humanitarian FCDO ‘best-buy’[127]. Failing to address humanitarian needs and its associated negative outcomes (chronic food insecurity, harmful negative coping strategies) risks instability, exacerbated vulnerability, and high levels of continued humanitarian need in Jordan. An integrated humanitarian approach seeks to combine different sectors of aid (such as livelihoods, and humanitarian protection) into a coordinated response that addresses the multiple, interconnected needs of forcibly displaced populations. This approach is contrasted to siloed, fragmented and sector-specific interventions, which often lack coordination. There is a growing body of evidence showing that integrated approaches can lead to better outcomes at lower cost, particularly in protracted crises[128].
[127] FCDO Humanitarian ‘Best Buys’ Analysis
[128] ALNAP (2018), The State of the Humanitarian System, https://alnap.org/help-library/resources/sohs-2018-full-report/

JHASS is an integrated programme because:
  1. Use of core partners across the sectors and activities – The programme uses a core set of partners which cut across the different sectors and activities of the programme (humanitarian, education and social protection). The NGO consortium will be used to deliver protection activities and activities under the IRF as needed. UNHCR will be used to deliver both cash assistance and returns support. Existing partners will also be used to house deployees (e.g. UNHCR, MoE, WFP, UNICEF).
  2. Single governance – The programme will benefit from a single governance structure encompassing all sectors.
  3. Supports GoJ strategy through different sectoral activities – Working across multiple sectors allow us to meet GoJ priorities. For example, combining humanitarian cash with social protection activities allows us to demonstrate our support is benefiting refugees and vulnerable Jordanians.
  4. Operates across the humanitarian - social protection nexus – By combining humanitarian and social protection activities, we can continue to harmonise approaches across these sectors. JHASS will continue to work to align humanitarian cash with national social protection systems, including the NAF through harmonised targeting, interoperability of registries, and joint assessments to ensure complementarity and avoid duplication. Working across this nexus will promote efficiency. By working on both humanitarian protection and national social care we can consider opportunities to work towards an exit of protection support.

There are potential benefits resulting from integrated approaches in crises, which are:
- Improved efficiency and reduced duplication, integrated programming reduces overheads and coordination costs, as agencies share logistics, assessments, and staff.
- Better Outcomes per pound spent: Multipurpose cash transfers, an example of integrated programming, provided greater improvements in food security, shelter, and health than sectoral aid at a lower administrative cost.
- Increased resilience and long-term cost savings: A study which assessed the fiscal cost of refugee subsistence needs in middle-income host countries, including Jordan found that investing in preparedness and early development-oriented support reduces long-term dependency and fiscal pressure on host governments. Integrated approaches to health, education, and livelihoods were found to be more cost-effective than fragmented humanitarian aid.
- Community-level cost savings: Integrated programmes reduced the burden on local populations, who would otherwise navigate multiple aid providers. This decreased hidden costs like time lost and duplication of travel.

VfM OF OUR PREFERRED OPTION
For ODA spend, the main objective is to maximise each pound's impact on those living in poverty. It is hard to quantify the benefits and costs of an adaptable programme, and this is even more the case in crisis situations. However, we can base the cost and benefit analysis on a number of benefit streams expected from the programme against the 5E’s VfM measures.
Economy: inputs of the appropriate quality at the right price
The programme will keep cost drivers of inputs low by:
Leveraging National Systems: JHASS continue to support inclusion of refugee children into Jordan’s national education system, avoiding the high costs of parallel structures and maintaining the burden-sharing arrangement. This approach has proven more economical, with per-child costs significantly lower than parallel education systems, which require separate infrastructure, staffing, and materials and are consistently found to be 30–50% more expensive than integrated models[129].
[129] WB & UNHCR, 2021 – The Global Cost of Inclusive Refugee Education
Reduce start-up costs: we will continue funding experienced partners (e.g. UNHCR, UNICEF and WFP) with a track record of delivering on this programme’s objectives and providing strong VfM. This will allow for a quick start to the programme and minimal transaction costs due to delivery systems being in place. Overheads costs will be capped between 6.5-8% depending on intervention type and partner size.
Cash assistance is cheaper than in-kind aid: it avoids the storage, transport, and distribution costs associated with in-kind aid making it a more efficient modality in many humanitarian contexts, data suggests that cash is 25-30%[130] cheaper to deliver than in-kind aid[131]. Evidence from previous programmes, shows that 88% of the UK’s contribution to WFP and 91% of contributions to UNHCR effectively reached beneficiaries, demonstrating continued VfM[132].
[130] The total cost of transferring $1 (i.e. the Total Transfer to Cost Ratio (TCTR)) of food was estimated at $1.9 and cash $1.2-1.3.
[131] 424-summary-vfm-cash-in-emergencies-report-final.pdf (calpnetwork.org)
[132] UNHCR Jordan: 2023 Basic Needs Cash Assistance Post Distribution Monitoring Report
Drivers of costs for education will be benchmarked including learning materials, teachers’ salaries, assistive devices for children with disabilities, and operational support for camp-based schools. We aim to minimise costs by leveraging existing government procurement systems and supporting implementing partners in identifying and negotiating cost-saving opportunities with suppliers.
As a multi-year programme JHASS partners will be able to procure early pre-position which can reduce input costs[133], such as time to negotiate better rates with financial partners or pre-position any commodities needed.
[133] Cabot Venton and Sida, 2017, The Value for Money of Multi-Year Humanitarian Funding: Emerging Findings accessible here
Efficiency: convert inputs into outputs
Humanitarian cash assistance produces better efficiency, with much better targeting of beneficiaries’ real needs. Technological advances have driven the cost efficiency of humanitarian cash assistance. Digital payment technology increases the potential to reach people quickly and minimise the risks of fraud and loss of resources, making the process more cost efficient[134]. In Jordan, efficiency gains have been made through reducing delivery costs such as banking fees, UNHCR's CCF in Jordan has significantly reduced bank transfer fees from 2.5-5% to 1.67% [135]. Cash is not only proven to improve VfM in humanitarian contexts but is also widely accepted as the preference of many refugees[136].
[134] UNHCR, Multi-Purpose Cash and Sectoral Outcomes: A Review of Evidence and Learning
[135] The average daily cost per beneficiary for cash-based transfers (CBTs) in 2021 was USD 0.50. UNHCR's Common Cash Facility (CCF).
[136] Refugee financial inclusion and financial health in Jordan 2024, UNHCR

Protection activities combine higher impact but smaller scale activities, such as psychosocial assistance and case management, and bigger scale activities with lower cost and impact at an individual level, such as community activities. The streamlining of the delivery of protection services into a consortium will promote efficiency in delivery.

The AAI mechanism to support refugee inclusion in the national education system pools donor funding to enable greater scale and a reduction in the duplication of functions such as programme design, management and donor reporting. Similarly support to camp schools’ operations has been shared with the EU and Switzerland reducing administrative burden and programme management costs of UNICEF demonstrating efficiency.

Shock responsive social protection systems can deliver aid faster and more quickly during climate related/socio-economic crises.

Effectiveness: best outcomes from our inputs and outputs
Focus on impact for all components: Humanitarian cash assistance has a strong evidence base in delivering proven outcomes. UNHCR cash assistance in Jordan had positive impacts on the lives of recipient refugees by improving their living conditions, as reported by 97% respondents in HCs and 76% in camps[137]. It was also considered essential to reducing household financial stress and overall stress levels in the recipient families (98% in HCs and 80% in camps) [138]. A study including Jordan, found that WFP refugee beneficiaries in receipt of cash transfers had higher dietary diversity scores relative to refugee non-beneficiaries.[139] Relevant protection interventions under JPP were found to be very effective.
[137] 2024 Annual assessment report Jordan basic needs cash assistance programme
[138] 2024 Annual assessment report Jordan basic needs cash assistance programme
[139] World Food Programme. (2018). Evaluation of the WFP Regional Response to the Syrian Crisis (2015-2018) (https://www.wfp.org/publications/evaluation-wfps-regional-response-syrian-crisis-2015-2017)
In education, partnerships with influential donors will be maintained through technical leadership to maximise education outcomes for refugees and improve alignment.
TA can have a disproportionately large impact by enhancing the effectiveness of a much larger funding stream. For example, TA in social protection[140] will influence the outcomes of the WB’s $400 million loan to Jordan[141] and GoJ’s $300m investment towards the NAF/$700m Social Protection spend. Since the WB cannot use loan financing for TA, the UK as the sole donor providing technical support holds a unique position to influence how these funds are used[142]. This includes strengthening systems, improving targeting mechanisms, and ensuring that investments reach the most vulnerable efficiently and equitably. Building upon the FCDO’s previous investments in providing TA to the NAF in the ESPJ programme.
[140] FCDO’s financial support to the WB Trust Fund alongside other donors has proven there is an association between a small amount of catalytic funding for TA from the UK-supported RSR (Rapid Social Response programme) and International Development Association (IDA). TA provided through the RSR improves the effectiveness of IDA projects before they start or existing projects; and it can be instrumental to influence additional resources. The evidence shows that once systems are strengthened, national funds and donor grants or loans will be spent more efficiently in an improved system so there is a long term, sustainable gain. By the end of 2016, 80 RSR projects were associated with IDA operations, totalling $47.6 million. RSR funding, which was associated with IDA financing of approximately $6.4 billion, including additional financing, which is a ratio of 61.
[141] Resilient and Sustainable Social Protection Programme (US$400 million)
[142] FCDO has been able to successfully use grant financing in TA to influence WB loans
TA to integrate climate into national social protection systems improves institutional effectiveness demonstrating measurable improvements in systems.

Cost-effectiveness: ultimate impact on poverty reduction, supporting social-economic resilience and social cohesion
Humanitarian cash assistance is an FCDO best buy and can be more effective at addressing people’s needs than in-kind transfers and vouchers. WFP funded research for Jordan found that the cost-effectiveness gains of switching from vouchers to cash are significant; beneficiaries’ purchasing power can be increased by up to 19%[143].Cash assistance has significant multiplier effects on the local economy. Robust evidence from the International Rescue Committee and the Lebanon Cash Consortium on the impact of cash on Syrian refugee households found that each dollar that beneficiaries spend generates $2.13 of GDP for the Lebanese economy compared to vouchers at $1.51, which benefits refugees and HCs.
[143] In Lebanon and Jordan, the cost-effectiveness gains of switching from vouchers to cash are significant; beneficiaries’ purchasing power can be increased by up to 19 per cent (BCG Perspectives‘Is cash better than food vouchers for Syrian refugees?)

Protection activities are more resource intensive for partners to deliver but they are life changing for individuals. Activities such as case management for survivors of GBV or community activities for youth can meet multiple needs and have a long-term impact on the individual’s and the household wellbeing, as well as on social cohesion. Moreover, local service providers will receive capacity strengthening from consortium partners that will bring long term benefits and potential for replicability of good practices.

There is a strong evidence base on the cost-effectiveness of including refugee students in Jordan's National Education System[144]. Inclusion in the national system is currently based on a burden-sharing relationship, requiring less dependency on donors than an alternative parallel system that would require 100% of donor financing. It is also critical for social cohesion, recognising that the majority of Syrian refugees live in community settings.
[144] WB and UNHCR. (2021). The Global Cost of Inclusive Refugee Education. Washington, DC: WB. UNHCR Jordan. (n.d.). Jordan - UNHCR. Available at: https://www.unhcr.org/jo/ ODI. (2023). Including refugee learners in national education systems. Available at: https://odi.org/en/publications/including-refugee-learners-in-national-education-systems/

Under the ESP, the MoE has committed to increase access for refugees and vulnerable Jordanians to Kindergarten. Pre-primary education is considered a ‘good buy’. There is substantial evidence that millions of poor children show lower levels of language and cognitive development than their better-off peers over the first five years of life. The deficit becomes quite large by the time these children enter primary school. This is likely to affect these children’s ability to benefit from standard schooling. Pre-primary interventions can have important long-term economic benefits in high- and middle-income countries, provided that children attend regularly, and that the classroom experience offered is better than what children already experience in the home in terms of early stimulation and social-emotional support[145].
[145] WB & FCDO (2020) Cost effective approaches to improve global learning: What does recent evidence tell us are “Smart Buys” for improving learning in low- and middle-income countries? Recommendations of the Global Education Evidence Advisory Panel

Social protection is an FCDO ‘great buy,’ with benefit cost ratios ranging from 1.5 to 2.5 from programmes based in Jordan[146]. It has proven to be highly successful at reducing poverty and halting a decline into destitution and building the resilience of populations to idiosyncratic shocks[147]. Using social protection approaches, like safety-nets (which we’ll be strengthening through TA), is cheaper than traditional humanitarian response in recurrent and predictable crises[148].
[146] World Bank (2021–2022), Jordan Programmatic Poverty ASA and Takaful Cash Transfer Programme Review; Mindset Research (2020), Evaluation of UNICEF’s Hajati Programme; World Bank and UNICEF (2021), COVID-19 Response in Jordan: Lessons from Emergency Cash Transfers.
[147] Bastagli, F., Hagen-Zanker, J., Harman, L., Barca, V., Sturge, G. and Schmidt, T. (2016) ‘Cash transfers: what does the evidence say? A rigorous review of programme impact and of the role of design and implementation features,’ London: ODI; Independent Commission for Aid Impact (ICAI) (2017) ‘The effects of DFID’s cash transfer programmes on poverty and vulnerability: an impact review’, London: Independent Commission for Aid Impact.
[148] Slater, R. and Bhuvanendra, D. (2013), “Scaling up existing social safety nets to provide humanitarian response: a case study of Ethiopia’s Productive Safety Net Programme and Kenya’s Hunger Safety Net Programme. Fit for Future Social Protection Thematic Study,” CaLP, UK; del Ninno et al. (2016); Maunder et al. (2015); Cabot Venton, C. (2013), “The Economics of Early Response and Resilience: Summary of Findings,” DFID, London (avoided losses defined as response assumed to occur before negative coping strategies have been employed, and before prices have destabilized).
Equity: reaching marginalised groups
In Jordan, needs of refugees are outstripping the capacity of the humanitarian system to address them. The intended activities are specifically designed to target vulnerable and under-represented groups. We will ensure disaggregated data, including gender, age, disability, geography and where possible climate vulnerability. Women, children, and people with disabilities will be key targets of the programme.
Targeting of cash assistance integrates gender and equity issues (e.g. persons with disabilities, serious medical conditions). A study found that transfers appear to be well-targeted to some vulnerable households in both urban and camp settings including those with disabled members, those with a higher ratio of children among their members, and those with no workers[149]. A recent evaluation of WFP and UNHCR Multi-Purpose Cash programming found that it was gender sensitive, however, there is more to be done to embed this in design to make it transformative[150]. Deployments will support UN agencies on improving their target methodologies.
[149] Cash Transfers and Food Vouchers for Syrian Refugees in Jordan: Do They Reach the Multi-Dimensionally Poor, Ragui Assaad, Alma Boustati and Vishal Jamkar, Working Paper No. 1561 August 2022
[150] Evaluation of the UNHCR/WFP Joint Action for Multipurpose Cash Assistance in Lebanon (2019–2021), (UNHCR and WFP, February 2023).
The proposed protection intervention will be delivered equitably, including to the most vulnerable and people with disabilities. While the focus will be on delivering protection services such as child protection and support to survivors and people at risk of GBV, wide community engagement will ensure that those needing services can access them. Moreover, strengthening national capacities through working with National NGOs to deliver these services will ultimately contribute to more equitable delivery as both refugees and Jordanians will benefit from increased quality and capacity of these systems to respond to their protection needs.
Social protection is directed to the poorest and most vulnerable. Social assistance via the NAF is prioritised for the poorest and most vulnerable households. Our TA will help strengthen the support the NAF provides during shocks. Our TA will also enhance services for the most vulnerable including orphans, elderly, disabled through enhancing social care and at the same create employment opportunities expected to particularly benefit women.
Inclusion of vulnerable children in education: The primary focus of education services will be to ensure the most vulnerable and neglected children have access to education, enhancing their productive potential, reducing welfare dependency, improving social cohesion[151] and reducing their risk of exploitation, criminal behaviour, early child marriage and child labour[152] leading to greater cost-effectiveness.  The Girls Education Challenge (GEC) found that inclusive interventions, though sometimes more costly at the outset, offer strong VfM by significantly reducing dropout rates and improving learning outcomes. The most cost-effective strategy was a twin-track approach: combining broad, inclusive education policies with targeted support for the most marginalised girls[153]. Working through the MoE enables the programme to influence broader strategic planning that improves equity for the most vulnerable, including refugees.
[151] UNICEF Office of Research. (2015). The Investment Case for Education and Equity. Florence: UNICEF Innocenti Research Centre.
[152] UK Home Office. (2020). Literature Review: The Impact of Education on Child Exploitation. London: Home Office Research and Analysis.
[153] DFID. (2019). Girls’ Education Challenge: Value for Money Report. London: Department for International Development.
JHASS’s dedicated focus on systems strengthening and localisation will ensure that decision-making power and resources can be transferred to national actors where possible, and we will ensure that humanitarian agencies are accountable to the populations they support. Localisation is recognised a ‘high potential’ best buy in humanitarian responses[154] and we will gather evidence to support and inform its implementation.
[154] FCDO Humanitarian ‘Best Buys’ Analysis.

VfM STATEMENT
This programme represents VfM. The programme will be designed to adapt to different forms of support for refugees, utilising the most cost effective and sustainable modalities, with a particular focus on cash assistance, refugee education and systems strengthening – particularly TA for social protection. The appraisal has provided robust reasoning and evidence to support the case that the potential benefits from the interventions under the workstreams would be substantial, and more than justify the cost. Cost-effectiveness might vary under different funding or geopolitical conditions.

OVERVIEW OF VfM INDICATORS FOR MONITORING
JHASS will develop a VfM strategy at the inception phase to determine key VfM considerations, indicators, and benchmarks. Indicators will be finalised at the design stage. All concept notes, grants, and agreements with delivery partners will include VfM considerations from the outset, explaining how costs and cost drivers will be captured and monitored over time, based on evidence and experience from earlier programmes (e.g. SSERJ, JPP). Individual indicators for different programme components will be tracked along with those set out in the overall JHASS logframe and regularly reported against. Possible VfM indicators are outlined in Annex D.

STAGE 4: THEORY OF CHANGE AND ASSUMPTIONS
THEORY OF CHANGE
JHASS’s theory of change runs throughout the business case and links the strategic case and problem statement to what FCDO recommends as the best options for delivery of the programme in the appraisal case. To address the identified problems and evidence outlined in the Strategic Case, FCDO proposes an integrated programme to address the needs in an approach aligned with the International Development Strategy, FCDO’s priorities and four shifts to its development approach, and BE Amman’s Country and Business Plan. The Theory of Change for JHASS is set out in figure 2 below.

Figure 2: JHASS Theory of Change

Contextual assumptions
Political & policy
- GoJ maintains its commitment to hosting refugees and refrains from forced returns or major restrictions on rights.
- Refugee inclusion in national systems (education, social protection) remains politically feasible.
- GoJ continues constructive engagement with international partners on humanitarian, education, and social protection sectors.
Economics
- Macro-economic reforms proceed without undermining social protection or triggering severe shocks.
- Jordan’s fiscal space remains sufficient to sustain refugee-inclusive services.
Regional and donor environment
- No large-scale new displacement overwhelms response capacity.
- Conditions in Syria allow voluntary, safe, and dignified returns for those who choose.
- Other donors maintain funding for humanitarian and development activities at adequate levels.
Service delivery and change sssumptions
- Access to integrated services reduces negative coping strategies, maintains or improves wellbeing and enhances safety and dignity.
- Communities accept and engage with services delivered through formal institutions and NGO partners.
- Inclusive service delivery strengthens social cohesion and public tolerance of economic reforms.
Institutional capacity assumptions
- GoJ institutions have capacity and willingness to absorb TA and engage in policy dialogue.
- Institutional data systems support inclusive service delivery and civil society engagement.
- NGO consortia and CSOs maintain capacity and coordination for protection interventions.
- Programme-funded roles are effectively absorbed within key institutions.
- Grievance redress and inclusion mechanisms strengthen the social contract.
Programme delivery assumptions
Outputs to outcomes
- Implementing partners maintain operational capacity and access.
- Vulnerability-based mechanisms effectively identify and reach the most vulnerable.
- Beneficiaries can access services without major barriers (distance, documentation, stigma).
- IRF can be activated and disbursed rapidly.
- MoE continues to permit refugee enrollment in national schools.
- Services (cash, protection) are of sufficient quality and scale to maintain or improve wellbeing.
- Cash transfer values meet basic needs despite inflation.
- Protection services effectively reduce key risks.
- Educational access translates into learning and value for families.
- TA and deployments are absorbed and applied to improve service delivery.
- Advice and evidence provided is timely, relevant, and used for policy and programming.
Outcomes to impact assumptions
- Sustained improvements in wellbeing across sectors build household resilience.
- Inclusive delivery service supports peaceful coexistence and avoids tensions.
- Strengthened systems sustained beyond programme support.
- Reduced vulnerability and improved cohesion contribute to broader stability in Jordan.
Commercial Case
COMMERCIAL APPROACH
1. The commercial approach of this programme prioritises working with the best placed partners with the mandates and relationships to deliver, draws on our extensive experience of operating in Jordan and knowledge of partner effectiveness and seeks to reduce administrative burdens by limiting the number of delivery partners. This will help us deliver this programme with the greatest effectiveness while minimising transaction costs.
2. As a humanitarian programme, the commercial approach will necessitate working with the international organisations with the mandate to provide support to refugees which will in turn strengthen the humanitarian architecture. In line with this it will work with UNHCR to provide multipurpose cash assistance and WFP to provide cash assistance for food security to Syrian refugees- given these are the organisation with mandate on these respective topics. It will mean supporting MoE with education support, with mandate for public education, and UNICEF on camp schools given UNICEF has the mandate to manage these. It will also prioritise supporting organisations, most of which are international organisations, which the GoJ already has partnerships with (e.g. WB) to complement existing work and ensure partners are trusted by GoJ.

We will pursue delivery through deliberately limiting the number of core delivery partners to six to reduce transaction costs. We will rationalise partnerships, and delivery will be pursued through direct agreements with six main core partners – UNHCR, WFP, NGO consortium, MoE, UNICEF and the WB. The aim is to streamline programme administration and reduce transaction costs. These partners will be used to deliver across multiple components of the programme to minimise administration, for example reducing the number of funding agreements and enabling partner meetings to focus on several components. For example, UNHCR is expected to deliver cash assistance and returns support. The NGO consortium will be used to deliver protection activities both via direct service delivery and grants to protection focused NGOs. Existing partners will also be used to house deployees (e.g. UNHCR, MoE, WFP, UNICEF), and to deliver IRF activities (e.g. UNHCR, UNICEF or the NGO consortium) and for evidence generation (e.g. UNHCR, WFP and WB) under MEL activities. The NGO consortium model will enable FCDO to focus our interactions only with the lead consortium partner creating administrative efficiencies. BE Amman’s Humanitarian, Education, and Resilience Team (HEART) team had nine partners in 25-26; thus, focusing on a core six partners represents streamlining. Any additional partnerships will try to be avoided and only pursued where these core partners are unable to deliver essential activities, e.g. for IRF activities if additional expertise to respond to a new crisis is necessary.

The programme will build upon and strengthen existing partnerships and routes, leveraging their proven effectiveness to ensure impactful delivery. This is reflective of the programme following BE Amman’s history of already providing humanitarian assistance in Jordan for over 14 years. We will apply lessons learnt from our previous programmes in Jordan, including lessons in delivering effectively via UNHCR, WFP and the WB. We will also learn lessons from partnerships which encountered difficulties, such as a consortium model under the JPP, and apply these to future models and focus on delivery partners found to be most aligned to our current objectives (e.g. social protection TA under SSERJ pivoted to delivery via the WB). We will continue to strive to strengthen delivery through our ongoing monitoring and evaluation of activities and through our systems strengthening activities (e.g. to improve financial management of the MoE).

We will also ensure that when working with delivery partners, overlapping costs are evaluated and we identify where delivery partners receive funds from multiple sources. We will continue to work with partners and donors to encourage financial transparency and to understand their funding sources and how UK finance can be deployed for maximum impact. Our position within key sectoral groups – such as the HDG and Social Protection Partners Group- supports us to do this. We will also use FCDO’s network to understand and maximise UK funding to partners coming from other sources. For example, the UK’s position as a WB shareholder enabled us to have early sight of the WB’s social protection programming in Jordan and align our bilateral funding to it to maximise its impact.

Pure commercial contracts will not be pursued except for MEL activities or audits since the best placed delivery partners operating in Jordan, due to levels of coverage, capacity, experience, expertise and influence are often organisations (e.g. Multilateral Banks and UN agencies) which do not participate in competitive commercial process and so a commercial process would exclude the actors who are expected to be best placed to deliver the activities. As such the focus will be on the best delivery partners outlined above and ensuring that they continue to implement robust commercial and procurement procedures.
DELIVERY ROUTES AND INSTRUMENTS
Table 7 outlines the delivery partners and instruments we would currently use to mobilise FCDO funding, and provides the rationale for this, along with information on our expected level of influence and alternative partners considered.

With changes to the aid sector in Jordan associated with changed ODA funding and the UN80 reform process it is possible that by the time FCDO is ready to enter into agreements the organisations operating in Jordan and those best placed to deliver will have evolved. Changes in the context, and particularly any further crises, may also necessitate changes should the scale be too significant to meet under the IRF. We will work with all partners to establish how best to mobilise FCDO funding to deliver the objectives of the business case in line with the Programme Operating Framework (PrOF).

BE Amman has had dialogues with key stakeholders to inform this business case. As part of this it has led INGOs and NGOs consultations at the beginning of the Concept Note stage and will continue to do so to understand delivery options, informed by humanitarian needs analysis. This will be followed by a formal call for proposals for the NGO consortium based on a detailed terms of reference with clear evaluation criteria to measure the proposals against. Given the recent funding reduction in Jordan, we anticipate receiving numerous proposals from potential NGOs so we will assess the proposals based on the best possible VfM.

Table 7: Delivery Partners and Instruments: Rationale, Influence Level and Alternatives Considered
Pillar	Partners and Instruments	Rationale for the partner selected and why they are the most cost-effective options	Expected level of influence	Alternatives considered
Core humanitarian assistance
Cash assistance transfers	UNHCR and WFP Memorandum of Understanding (MoU)	Mandate - UNHCR has the mandate in Jordan to provide multipurpose cash assistance to refugees and WFP to provide cash for food security. / Established systems – Both agencies have established systems in place to be able to deliver assistance fast and effectively to refugees. / Expertise – WFP has expertise in cash assistance for food security and UNHCR in providing cash for basic needs given their organisational focus and experience in Jordan and other contexts / Avoids proliferation/fragmentation - UNHCR and WFP are the key institutions used by the donor community for these interventions thus supporting them reduces fragmentation and proliferation of cash assistance in Jordan providing clarity for beneficiaries and efficiency. / Proven – UHNCR and WFP are proven delivery partners of BE Amman, able to deliver efficiently and cost-effectively on these topics. / Aligned with national systems – UNHCR and WFP have aligned their approaches with national social protection systems promoting efficiency and harmonisation. / Robust procedures – UNHCR and WFP have strong procedures including relating to procurement and safeguarding as shown via BE Amman’s due diligence reports.	Moderate. We are influential as a leading humanitarian donor and chair of the HDG. But influence is moderate as we are one of several donors supporting their cash assistance activities.	NGO) - but this would create parallel systems and be less cost-effective. / Jordan’s NAF provides cash assistance from Jordan’s budget to vulnerable community members but is closed to refugees. / The Zakat Fund provides cash assistance from charitable sources but is also focused on Jordanians. / Private sector first tier supplier is not an option in Jordan since the UN has legal protection over refugee data as such, they would have insufficient information to target refugees. Similarly pooled funding is not a realistic option (see below).
Protection	NGO consortium – comprised of international and national NGOs with a lead consortium partner (Accountable Grant (AG))	NGO consortium / Expertise – INGOs and NGOs in Jordan have developed expertise in working on protection issues and are regularly deliver protection programming. / Trusted by communities – NGOs and especially national NGOs, such as the Jordan River Foundation which FCDO partnered with through the JPP, have been successful in engaging communities in sensitive protection topics e.g. GBV and child protection. Their role as separate from the Government can be an asset on engaging in sensitive topics. / Reach – NGOs operate across Jordan and can reach wider areas of the country compared to actors such as UN agencies. / Builds local capacities – partnering with national NGOs provides them with the opportunity to build experience, expertise and capacities. / Aligns with the NSPS – the GoJ wish to increasingly deliver social services via CSOs. / Streamlines administration- assigning one consortium lead will enable FCDO to focus its engagement on one partner and ensure they meet FCDO’s robust procedures and standards. This lead partner would both coordinate protection service delivery activities and administer grants to NGOs working on protection. The programme will learn lessons from the JPP consortium model and ensure the appropriate consortium design and financing. / Larger consortium budget – Consolidating activities under the consortium will increase the budget which is anticipated to drive more interest from delivery partners.	High. Influence will be high over the consortium due to the expected high significance of funding for the organisations in a context of scarce resources and the ability to clearly define the activities as the sole donor.	UN agencies (e.g. UNHCR) but reach across Jordan is not as great, NGOs are uniquely placed to support communities on these issues and would not be as effective in building local capacities/local leadership. / Private sector partner could coordinate the consortium – but less likely to be embedded in communities, NGO coordination mechanisms or to be able to work flexibly with consortium members.
Voluntary returns	UNHCR for return focused protection services (MoU)	UNHCR (returns) / Mandate – UNHCR’s mandate enables it to be present in refugee camps and provide outreach and counselling, as well as to support refugees at the border during the return process. / Information access- UNHCR’s position as an international actor with operations in Syria enable it to remain up to date with changes in the context in Syria. / Coordinated regional approach – UNHCR are active in supporting Syrian refugees return from across the region, meaning via UNHCR we can provide support as part of a wider regional approach. Working with UNHCR also avoids creating proliferation in cash delivery partners.	High/moderate. We will be influential as the currently only donor for returns support. But UN has own governance and decision-making systems and will need to align with regional approach to returns.	NGOs could provide support focused on returns but are less well-placed to support on this topic due to UNHCR’s mandate, presence in Syria and regional approach.
Internal Risk Facility	Existing partners prioritised e.g., UNHCR, UNICEF and NGO consortium (MoU and AG)	Expertise – existing partners have expertise and mandate across key sectors in which emergencies could arise. UNHCR-basic needs, shelter, primary health and camp coordination, WFP in food security, UNICEF for WASH and education, and NGO consortium for protection. / Speed of response –these actors already have established work in these sectors enabling quick scale up. Existing agreements with these partners will also enable FCDO to respond more quickly to new crises (e.g. via avoiding new commercial processes or due diligence). / Streamline programme administration – using existing partners will minimise programme administration for BE Amman.	As in relation to these partners outlined above and below.	Additional UN (e.g. United Nations Population Fund (UNFPA), UN Women, WHO, NGO or private sector organisations but would delay speed of response and increase transaction costs.
Education support
Contributions towards the costs of including of refugees in the national education system through financial aid (off budget)	MoE (UK-GoJ bilateral MoU)	Burden-sharing relationship – Currently the MoE cover around 73% of the annual cost. Operating a parallel system would require the donors to cover 100% of the cost. / Strengthen national systems – providing funding directly to the GoJ helps strengthen national systems. / Use of a special account – A special account has been utilised by donors since the start of the Jordan Compact. It allows donors to ensure that off-budget financial aid is utilised to meet specific indicators as well as to pool their funding enhancing efficiency. / Aligns humanitarian with national service delivery – it will support refugee education through national systems creating coherence in the education refugees and Jordanians receive and enabling a sense of belonging in HCs. / Cost-effective – it is a more cost-effective delivery model than providing education through third parties.	High/moderate. FCDO is a leading education donor (Chair of Education donors’ group and depended on by other key donors for expertise). Influence has been strengthened by current FCDO secondee and would be strengthened if this is continued. But decisions affecting MoE sometimes made at higher level (e.g. Royal Court) harder to influence and requiring cross-embassy approach.	N/A – no credible alternative / As set out above, not working with GoJ would mean implementing a parallel system through the UN/NGOs and would likely limit refugees to informal education that is not certified or accredited.
Contingency support for refugee camp school operations as services transition to the MoE	UNICEF (MoU)	Mandate and expertise – UNICEF has been responsible for education in refugee camps. They are as such well-placed to work on infrastructure in refugee camps and supporting camp school operations, and undertaking research into key issues, such as the causes of refugee children being out of school.	High/moderate. We are influential as a leading education donor. But influence is limited as we would be one of a number of donors supporting this organisation on camp school operations and UNICEF’s capacity to influence the GoJ has been reduced by staffing reductions.	No viable alternative. UNICEF have the mandate to manage camp school operations. The best alternative will be to transition operations fully to the MoE, but this is currently on-hold due to reductions in funding. If numbers of refugees decrease significantly then there may be future opportunities to fully transitions services.
Systems strengthening
Education – TA	FCDO Centres of Expertise support[155]	Timely expertise – BE Amman can access expertise swiftly due to established Centres of Expertise and dedicated in-house expertise. / Cost-effective for BE Amman – using existing facilities enables BE Amman to access support without requiring additional budget. / Reduces programme administration – using Centres of Expertise for research and TA reduces the need to create new agreements and work with new partners	We will be able to influence the exact activities of the Centres of Expertise support, but they will likely need to utilise FCDO relationships to ensure they are impactful with the MoE.	Private sector organisations/think tanks, universities, NGOs – but would increase programme administration and cost requirements and delay delivery.
Social Protection TA	WB (MoU)	Trusted and influential partner – The WB is closely aligned to the GoJ’s approach for social protection and is trusted by them, helping FCDO deliver support in line with the GoJ’s vision and preference. / Experienced and proved – FCDO successfully collaborated with the WB to provide emergency social protection during COVID and to strengthen the NAF prior to this. / Maximise and complement WB loan – The WB is providing a $400m loan to the GoJ to support the implementation of the new NSPS. FCDO is complementing this via TA via a WB trust fund. This partnership – currently £1.4m for 25/26 will be extended. / Robust systems, including for procurement – BE Amman’s due diligence report found the WB to have robust systems in place to manage funds responsibly, including to support the GoJ to make procurements as part of funding. / Opportunity to pool funding – should other donors wish to support the implementation of the NSPS 2025-2033 via the WB Jordan they could provide funding through this WB fund trust fund, improving efficiency and coordination.	High/moderate. As the only donor to the WB on social protection in Jordan we can clearly specify our project activities. The WB is perhaps the most influential organisation with the GoJ on social protection due to the scale of their funding. Together this provides us with a good avenue to indirectly influence the GoJ.	Other international actors active in social protection space, e.g. UNICEF, WFP, UN Women. / Private sector TA – but experience under SSERJ suggests can be difficult to establish new relationships in this sector. / Direct delivery to Government e.g. MoSD, NAF – but may not be utilised to maximum benefit without technical support from international expertise and others active in this space.
[155] FCDO Centres of Expertise will be pursued in the first instance for education TA for cost-effectiveness, however other partners will be explored if this route no longer becomes possible – with existing partners to be used delivery partners if they can fulfil the objectives of research.

Explanation for two cash assistance delivery partners and direct agreements
As noted earlier in the business case, national social assistance provided via the NAF is only open to Jordanian citizens and excludes refugees. As such it is necessary currently to provide cash assistance to refugees via external organisations. Two UN agencies in Jordan currently have the mandate to provide it and are used by most donors – UNHCR which provides cash assistance for basic needs and WFP which provides cash for food security. Providing support through these organisations, rather than third parties such as NGOs, avoids creating new cash systems which can create confusion for beneficiaries, duplication of support, and increase transaction costs. We will also provide cash to support those returning to Syria through UNHCR to avoid a proliferation of different cash partners.

While a single unified cash system with all donor contributions channelled through one UN organisation would reduce transaction costs and ultimately be preferable, the aid architecture in Jordan and UN mandates does not currently reflect this model. The UN80 reform process is currently underway, and it is possible this will lead to changes which enable FCDO to streamline its delivery of cash assistance in Jordan via either UNHCR or WFP in the future. We will continue to engage constructively in this process at post. Over the next five years, we aim to work with UN partners toward greater coherence in cash assistance delivery, with a view to exploring a single, harmonised approach. We recognise this will take time and require careful sequencing.

However, at present these two organisations are used by the donor community to channel assistance according to their mandate and FCDO believes it necessary to deliver assistance via both partners to be able to support both basic needs and food security and to continue to align with the approach of the GoJ and other donors. UNHCR and WFP do however work together very closely on how they deliver cash assistance to reduce transaction costs. For example, they both use the same proxy means testing formula and do joint monitoring and site visits. The CCF is used for delivering cash assistance that provides organisations direct and equal access to a common FSP and payment facility. This has reduced costs by removing the need for each agency to establish their own procurement arrangements and negotiate lower bank fees. Efforts have also been made to align their approach with the national social assistance system. FCDO has played an active role in encouraging these agencies to harmonise their approaches and will continue to press for efficiencies through our partnerships and convening work.

BE Amman has previously explored the option of pooling cash assistance funding. However, there is not donor buy in for this in Jordan due to different donor funding cycles which make pooled arrangements difficult to sustain and several donors could not guarantee long-term contributions, which is important for a pooled mechanism. The two main cash assistance programmes (UNHCR and WFP) are already funded by multiple donors through coordinated systems, which achieve efficiency without formal pooling. Given these factors, maintaining separate contributions allows flexibility, accountability, and alignment with UK priorities while still leveraging shared systems like the CCF and joint targeting for cost-effectiveness.

Monitoring, Evaluation, and Learning (MEL)
The three workstreams will be supported by monitoring and evaluation activities to track the impact of work, provide assurances on how FCDO funding is being used and learn from the activities. This will be guided by a comprehensive MEL framework to be developed during the inception phase, linked to the theory of change. It will have a focus on monitoring to ensure accountability in our programmes, with evaluations to be completed on a few targeted topics to generate learnings to contribute to the evidence base where more limited. Core delivery partners will be expected to undertake MEL activities in line with the framework and will be provided with budget for these as part of their funding agreements.

FCDO will work with an independent MEL supplier. Their responsibilities will include supporting FCDO to develop the MEL framework, working with delivery partners to agree and align their MEL work with the framework, to monitor and evaluate programme activities and create to learning documents. They will provide monitoring information which the FCDO programme team will draw on in assessing the programme and reviewing the Theory of Change. Using a supplier ensures adequate MEL capacity for a programme of this size, reduces programme administrative for the programme team and ensures a coordinated and robust MEL process. The GEMFA 2 (Global Evaluation and Monitoring Framework Agreement 2) framework will be used to identify a supplier which will then be formalised with an AG or commercial contract. The GEMFA 2 framework will support quicker procurement reducing transaction costs for BE Amman and better access to specialised expertise.

Commercial principles applied
We will apply rigorous approaches to drive commercial management principles for all our partners, regardless of whether we will be funding through memorandums or grants as above. While many of our partnerships will build on existing relationships, we will not be complacent and will continue to pursue robust commercial approaches.

We will deliver in a way which sets an example in good donorship and supports humanitarian actors to manage the challenges facing the sector. This will involve designing agreements which enable flexibility in when our funding is provided to help the UN manage funding shortfalls. It will also involve multi-year agreements where feasible to enable UN partners to better plan responses.

We will collaborate with other donors to align our delivery approaches, leverage other funding sources, and provide partners with unified messages. This will enable our partners to deliver more effectively.

We will proactively engage with the UN80 reform process to help build strong delivery institutions in Jordan. UN agencies, such as UNHCR, UNICEF and WFP, are expected to play an important role in the delivery of this programme. As such FCDO in Amman will engage proactively and constructively with the UN80 reform process, including through utilising our convening role across the sector and deployees, to help successful structures most able to deliver UK priorities to emerge from current reforms.

We will collaborate with central FCDO teams to inform multilateral and INGO engagement in country. In engaging with local UN institutions, the WB and INGOs we will ensure we are aware of central reform priorities through engaging with FCDO Headquarters and reinforcing these messages locally. Similarly, we will share our experiences in Jordan to help inform FCDO Head Quarters positions and negotiations. Through this we will support FCDO’s strengthened approach to enhancing multilateral impact using a whole of FCDO approach, with coherent use of UK multilateral investments, that drive reform. We will continue to track internal reforms to multi-bilateral programming and align our work with evolving approaches.

We will deploy robust due diligence procedures to identify suitable partners. We will complete/update these before entering into agreements and follow up with partners to address any areas needing improvement, supporting them in this where needed. Due diligence will be complemented by delivery chain mapping and delivery chain risk mapping to ensure that risks down the delivery chain are understood and mitigated. Clear communication that FCDO standards must be met by all in the chain will be made.

We will work with national partners through the NGO consortium. This will help build local knowledge and capacities and contribute to stronger institutions within Jordan in line with the localisation agenda.

FCDO template agreements or centrally negotiated MoUs will be used. We will use standard FCDO AG and MoU templates to ensure that FCDO’s standards are applied. Where a specific agreement between FCDO and an international partner has been agreed we will use these to align with central priorities and ensure the efficient and rapid mobilisation of funding.

VfM and cost drivers
A robust VfM framework will be developed which will inform and be implemented through the commercial management of the programme. As part of this the benchmarking of partner costs will be used to ensure cost control. Across all partners, management fees will form an important component of costs. We will ensure these are in line with central FCDO UN agreements on fees and we will benchmark NGO costs against comparative organisations. Other main cost drivers will be the provision of direct support to beneficiaries and the provision of technical expertise. We will review this regularly including to assess the proportion of funds being deployed directly to beneficiary’s vs management costs, and to ensure that technical expertise is in line with expected costs for international and national expertise. Tracking VfM elements will form part of our commercial management.

Performance Management
In addition to ensuring clear and robust agreements with partners, clear Key Performance Indicators (KPIs) through logframes with clear indicators, will be agreed with each partner. This will ensure that expectations are clear and enable performance to be robustly assessed. Regular dialogue and reporting from partners, on at least a quarterly basis, will be pursued so any risks and issues to performance are addressed early on. Payments will be made in tranches where feasible to enable progress to be reviewed and tranches only to be released where progress is adequate. Partnerships with the WFP, UNHCR and the NGO consortium will be led by the Humanitarian Adviser, the MoE and UNICEF by the Education Adviser and the WB by a Social Development Adviser. Advisers will be supported by the team’s programme managers. This will ensure there is accountability within FCDO for the robust management of the agreement.

We will regularly review delivery and remain prepared to reprioritise or stop funding partners where results are not achieved, ensuring accountability and value for money. In particularly we will review the performance of social protection systems strengthening activities after two years of the programme to assess whether to continue or reallocate funding to other components.

Financial Case

ODA ELIGIBILITY AND AFFORDABILITY

The projected total budget for the JHASS is up to £73m covering a four-year period from April 2026 to March 2030. This is deemed affordable given expectations of current ODA trajectory and affordability within the planning assumptions in BE Amman’s Country Business Plans and budget envelopes and the next Spending Review (SR) currently underway. All spend within this programme will meet the criteria for ODA, as defined by the Organisation for Economic Co-operation and Development's (OECD) Development Assistance Committee (DAC). Agreements with partners will be made for an initial three-year period, where activities are anticipated across this period[156], in line with SR and BE Amman’s budget for this period. Following this, where activities are due to continue to the end of the programme, agreements will be extended by a further year following the next SR. This approach reflects the strategic importance of predictable, multi-year funding in protracted humanitarian contexts.
[156] Some activities may require shorter term agreements e.g. IRF activities responding to urgent needs and returns work giving this is a fast-changing area.

Under the JHASS programme, we expect that at least approximately 15% of the overall budget may be considered eligible for ICF, depending on the final design and implementation of activities. This will primarily include climate-tagged cash assistance. While the specific outcomes are yet to be determined, the programme aims to explore how these components can contribute to strengthening the resilience of vulnerable communities and supporting Jordan’s broader climate objectives.
### SOURCES OF FUNDING
All costs on JHASS will count against the Resource Departmental Expenditure Limit (RDEL) and will be covered under the FCDO BE Amman’s bilateral budget. Annual budget for the programme as outlined in the cost profile below, will be determined through BE Amman’s ODA allocation processes. Projected spend is covered within the current Country Business Plan (currently being under review) for BE Amman. The budget proposed is subject to the next SR allocations and part of the new Country Business Plan.

OVERVIEW OF COSTS

Based on intended delivery plans and the capacity of partners to absorb funding due to humanitarian needs table 8 below sets out an indicative expenditure profile for the programme across all components based on the assumption that all approvals are received by April 2026 and the programme commences in April 2026 and will end in March 2030. The indicative cost profile will be adjusted during the inception phase and throughout the programme, as necessary and overseen by the programme governance set out in the Management Case. The specific allocation of costs between activities under each component may vary during the mobilisation phase. A detailed budget breakdown is provided in Annex F.

The total proposed budget for the programme is up to £73 million over four financial years, with flexibility to respond to significant spikes in need and assuming a reduced but flatline budget for Jordan over the multi-year SR2 allocations. In line with the programme’s strategy for a responsible partial exit, the programme reflects a reduction in spend over the course of the programme. It envisions a scale down in line with the expectation that many refugees will wish to return to Syria (noting 80% have expressed a wish to return one day), and an end to specific TA activities once objectives have been met enabling a scale down in costs for systems strengthening as well (although this will become a larger proportion of spend in final years). These justify a reduced final-year’s budget. At the same time, it permits the continuation of lifesaving and life-changing services in cash, protection, education and systems strengthening at lower levels in the final years given some refugees wish to stay in Jordan long-term. BE Amman will keep under review the risk that needs remain higher than anticipated in later years and consider a range of options to address this (e.g. addendum, additional programme, utilising centrally managed programmes) in line with BE Amman’s ODA budget, giving this issue particular attention in early FY 27/28.
Table 8: Estimated annual spend profile
Year/Delivery Route	2026/2027	2027/2028	2028/2029	2029/2030 / (Final year)	Total
Up to planned expenditure	£23,000,000	£20,000,000	£16,000,000	£14,000,000	£73,000,000

The funds for this proposed programme for this financial year are part of the UK’s ODA programme budget for Jordan and is in keeping with the allocation for this spending review. The final year budget is subject to the outcome of a future spending review.

Spending will be profiled at the start of each UK financial year and can be calibrated downwards or even stopped, considering the broader portfolio and alignment with available ODA, while adapting to assessed priorities. However, as a general rule changes from the funding amounts set out in partner agreements with try to be avoided or kept to an absolute minimum due to the importance of predictable multi-year financing and as early notification of partners annual budget will be provided as possible. The budget will be disclosed upon agreement on the selected partner, as we await to review proposals which will include a detailed budget covering different categories including programme input costs, staffing costs, and support costs. These will be broken down by financial year and reviewed before selecting a partner.

The JHASS programme team will forecast monthly to ensure spend accuracy is well monitored. The proposed management approach enables JHASS to increase or decrease spend according to context and need. Annual spend projections have been calculated using cost estimates from previous and ongoing humanitarian, education, and social protection programmes implemented by BE Amman as benchmarks. Based on learnings from good practices and gaps in previous FCDO-funded programmes in Jordan, a dedicated monitoring and evaluation component has been proposed to drive accountability and effective tracking of results.
ACCOUNTING, MONITORING AND REPORTING FOR FUNDS
The JHASS Senior Responsible Officer (SRO) will have overall responsibility for financial management and performance of the programme including adherence to PrOF rules (rules 22-27), alignment between financial investments and programme results. Please refer to the management case for further details on roles and responsibilities.

Partners would be expected to submit a detailed multi-year project proposal (where required) and provide satisfactory financial reports before subsequent disbursements are made. Partners will be expected to provide an annual costed work plan to ensure accurate budget profiling and forecasting which would be monitored quarterly against planned activities and expenditure. FCDO will provide support to improve reporting and forecasting where necessary and will receive quarterly financial reports from all partners detailing actual spend, forecast for the following quarter and updates on estimated total spend for the reporting year with explanation on any variances beyond the +/-10% threshold[157]. Annual financial reports will also be submitted at the end of each year for partners holding multi-year agreements with BE Amman. The reporting cycle and frequency would be agreed with partners during programme mobilisation to factor in payment controls.
[157] This approach was taken under the JPP and proved helpful in understanding the causes of variances exceeding this threshold which occurred several times. In other BE Amman programmes, the magnitude of forecasting variances has varied by partner with some never exceeding this amount and others more regularly.

The Programme Responsible Officer (PRO) will quality assure all request for payments submitted by partners then advise the SRO on whether to approve them. All payments, irrespective of size or type of agreement, will be based on request submitted by the partners that provide proof of expenditure and a narrative justification for the request. The narrative report would be reviewed by the advisers and programme managers who will make an initial recommendation to the SRO. The JHASS team would periodically review the use of all BE Amman funding as part of an agreed reporting and monitoring cycle. All partners will be required to provide an annual audited financial statement to provide assurance on the effective and efficient use of BE Amman funds and assess financial risk and controls.

Implementing partners would be responsible for grant arrangements with and fiduciary risks of, their downstream partners (if any) and will disburse funds to partners in line with FCDO’s principles on narrative and financial reporting. The JHASS team will use monitoring missions to undertake spot checks, asset verification where applicable and, when required, expenditure verifications during the programme.

We do not expect significant asset purchases. The SRO will ensure there is a complete, accurate inventory of all assets purchased and that regular physical checks take place as part of the annual audit. At the end of the programme, all assets will be disposed of in a manner that represent the best VfM for FCDO with clear records of decisions made and in line with PrOF Rule 28[158].
[158] Rule 28: The write-off of losses or fruitless payments, including assets lost, stolen or damaged, must be approved at the appropriate level.

The IRF aligns with FCDO’s risk-based financial management principles, including over-programming flexibility and in-year budget responsiveness. It will be profiled in Hera under the Resource Allocation Budget (RAB) scenario and monitored monthly, with clear reporting on spend, impact, and VfM. Further information on the IRF is provided in the annexes.

FINANCIAL RISKS MANAGEMENT

The operating environment in Jordan is relatively stable. However, exposure to corruption, fraud and aid diversion remains moderate. There is also a financial risk around illegible expenditure. To mitigate these and other financial risks, some controls to be applied include:
- Conducting and maintaining valid DDAs for direct partners and following up on any recommendations made as part of the progress.
- Conducting spot checks and field visits on at least an annual basis.
- Ensuring FCDO’s requirements of annual financial audits of partners are met and external audits of specific partners undertaken where required.
- Engaging proactively with contracted Multilaterals/and partners on their internal and external audits.
- Including a fraud risk assessment in the Terms of Reference for any FCDO-commissioned audits.
- Developing, monitoring, updating, and applying Delivery Chain Risk Maps (DCRMs) to show the flow of funds from FCDO through suppliers down to the last downstream partner and map associated risks.
- Conducting periodic review meetings to discuss context and fiduciary risk issues, assess spending rates and engage on future spend profiles.
- Agreeing VfM indicators at the proposal review stage and reporting on and assessing VfM throughout the programme.
- Partners will be encouraged through the contracts and AGs to maintain variances on forecasts and expenditure within acceptable thresholds of +/-10%.
- Monitoring exchange rate fluctuations, ensuring that all commitments are in pound sterling, and ensuring implementing partners will bear the risk of exchange rate fluctuations.
- Inclusion of comprehensive financial and fiduciary risks in the programme risk register and appropriate mitigation strategies proposed to effectively manage and monitor these risks.
- Risks will be formally reviewed regularly as part of quarterly progress reporting.

JHASS Programme Team will continue to brief partners on FCDO Fraud Policy, reporting channels and requirements for managing corruption and fraud risk. In accordance with FCDO’s zero tolerance approach, we will follow up with agencies if we have reason to believe that UK funds or assets have been lost, damaged or unaccounted for or otherwise diverted. BE Amman programme team will collect beneficiary feedback (at least annually), undertake spot checks (at least annually), and assess risks during partners’ review meetings (at least quarterly).

Assessment of financial risk and fraud as reflected in the risk matrix in the Management Case, the likelihood of fiduciary risk in Jordan is moderate. This is based on the last updated Fiduciary Risk Assessment in 2025 and updated Annual Statements of Progress that have been completed.

We intend to visit programme sites at least once every year but can do that more often if needed. Any specific risks identified through the DDA process will be monitored closely by the programme team. Moreover, the partner will be informed of its responsibility for reporting any suspected or confirmed cases of fraud or aid diversion using the central FCDO reporting concerns mailbox.

In case of fraud being detected, BE Amman programme team will work with partners to attempt recovery of UK assets/funds. Internal Audit Department’s Investigation Section will be notified of any incidents of fraud and BE Amman will assist in the assessment of any necessary investigations. BE Amman will have full access to financial information about programme funds as part of delivery chain risk mapping and will actively seek to improve the financial management procedures further. Funding will be made conditional on meeting minimum financial management conditions.

A further area of financial risk associated with BE Amman’s previous programming is budget instability. Under the JPP, the annual budget of the programme needed to be amended from initial plans due to pressures on UK ODA such as responses to crises in Ukraine and Afghanistan and at times early confirmation of the new budget couldn’t be given. While targets were revised according to the new budget, these changes still negatively impacted on performance contributing to the ‘B’ score in 24/25. To mitigate this risk under JHASS, budget changes for partners will be kept to a minimum as far as possible, and confirmation of annual budgets/notification of budgetary changes will be provided as early as possible. Learning from the JPP, partners will also be encouraged to take a responsive framework with regular scenario planning and resource reviews. For JPP stronger coordination among consortium partners was needed to manage budget changes. For the NGO consortium under JHASS, a dedicated Consortium Management Unit will be established by the INGO consortium lead during the inception phase to drive coordination and leadership across all partners. This will be able to lead work to adjust annual targets and activities where needed, as well as more broadly ensuring efficient coordination, financial discipline, and accountability across partners. A clear governance structure for the consortium will also be established at the outset.
AUDIT
Partners and their downstream suppliers will be required to provide independent assurance that FCDO funds have been used for the intended purposes annually. Annual audit reports received from partners will be reviewed by the Programme Manager and in case of any observations, these will be followed up on.

FUNDS DISBURSEMENT
Funds will be disbursed to the selected partner quarterly in arrears where possible, following thorough scrutiny of the financial report. Disbursement amounts will be based on the partner’s financial report, which will clearly identify the UK’s contribution, and will be accompanied by quarterly narrative reporting. In cases where the partner requests advance payments, we will require a robust VfM rationale and evidence of need, supported by accurate financial forecasts. Such requests must be justified in writing and will be assessed on a case-by-case basis. The MoUs or Accountable Grant Agreements (AGAs) signed with the partner will outline the reporting schedule, which will be directly linked to the receipt of financial reports and subsequent payments.

For off-budget financial aid, the transfer of funds will follow a disbursement schedule that will be agreed with the MoE and set out in a new MoU with the GoJ. The MoE will provide quarterly financial reports and annual reports of the programme to BE Amman, providing evidence and assurances that the amount provided by us has been spent on agreed budget lines. The Office of the Auditor General will provide an annual audited statement of the whole education sector within 9 months of the end of the financial year. Any additional auditing deemed necessary by BE Amman will be financed out of the TA fund. This could include a light external financial audit for the joint donor account. We will continue to track audit recommendations on UK funding (to the MoE) through the internal Annual Statement of Progress, which includes a section specific to the education sector.

FINANCIAL MANAGEMENT
All potential partners must have established financial management systems and the capacity to absorb and monitor the budget of this programme. Prior to any funds disbursement, we will conduct a due diligence assessment of any new partner, which will assess the agency’s financial capability and systems. This will include looking at the agency’s policies, standard operating procedures, and accountability systems in place to manage funds. Where there are consortium partners or downstream partners, the assessment will also look at the procedures in place for managing partners and what levels of due diligence are undertaken throughout the delivery chain. Regular monitoring of the programme by BE Amman will also provide further assurance through, for example, meetings with downstream partners and performing spot checks.

This programme has a significant financial aid component, and we have put in place strong monitoring mechanisms and mitigation measures, which have been reinforced since the start of AAI.

The AAI Annual Statement of Progress in 2024 concluded that there is a moderate level of fiduciary risk within the government but that it is stable and that there is credible Public Financial Management reform.

A full FRA was completed by BE Amman in August 2025. The FRA delivered a clear assessment on the overall level of fiduciary risk within the education sector including the risk of corruption and the credibility of financial management systems. The overall risk remained at moderate, consistent with the previous FRA (conducted in 2022). It recommended a gradual shift to on-budget support to make use of rigour of the Government Financial Management Information System. Recommendations will need to be considered collectively with other donors contributing to AAI as a shift from off budget may prohibit them from contributing to the programme.

Management Case

PROGRAMME MANAGEMENT AND GOVERNANCE STRUCTURE
The JHASS Programme will be managed by the HEART team at BE Amman, which has advisory capacity for each of the sectors – humanitarian, education and social protection - the programme works in.

It will be is governed through a robust structure that draws on existing and well-functioning BE Amman oversight mechanisms. It enables functional leadership to be exercised by subject matter experts across humanitarian, education, and social protection sectors. Strategic oversight is maintained by the Country Board, while operational assurance is led by the Delivery Board. This model ensures governance utilises existing structures promoting administrative efficiency and avoiding duplicative structures, has senior oversight, promotes cross-sectoral and embassy collaboration, ensures agility and allows resources (staff time, expertise, influence) to be deployed where most needed. A governance diagram is included below (figure 3) to illustrate reporting lines and escalation pathways. There are three main layers of governance:
1. Strategic Oversight is provided by the Country Board, the senior decision-making body for all HMG activity in the BE Amman. This Board, chaired by the HMA, has responsibility for the strategic direction for all activity and resources at Post to ensure these align with the embassy’s Country and Business Plan, and resource decisions to deliver the Plan. As such it will provide strategic oversight of the JHASS programme, ensuring continued alignment with the UK’s cross-government objectives in Jordan and decisions related to resource reallocation. It will also oversee any risks from this programme escalated to the Country Level Risk Register. The Board meets quarterly, and membership of this board is provided in Annex E.
2. Operational Assurance is led by the Delivery Board, chaired by the Development Director and Deputy Head of Mission, which oversees the implementation of programmes that deliver against the Country and Business Plan. It ensures operational excellence by reviewing delivery progress, risk and financial management, and compliance with legal and fiduciary obligations. A Delivery Board quorum can approve changes in spend of up to £2m within and between programmes including JHASS.  These will be taken within BE Amman’s ODA country allocation, and any high risk or novel project issues will be referred to the Country Board (including by Out of Board decision). SROs make delivery and spend decisions up to £0.5m, referring novel or contentious issues to the Delivery Board. This Board meets monthly/six weekly and is timed to report into the quarterly Country Board meetings. Membership of this board is provided in Annex E.
3. Programme Leadership, which occurs at different levels, but which is led overall by the SRO, who holds ultimate accountability for the programme’s success. Programme leadership will be provided by the SRO, PRO and technical experts as follows supported by programme managers, programme funded roles/deployees and cross-cutting resources:
- Deputy Development Director (Grade 6) – SRO: Provides overall strategic direction, decision-making, and high-level engagement with donors and government stakeholders. Accountable for programme delivery, financial management allocation decisions, and team management.
- Humanitarian Adviser (Grade 7) – PRO: Supports the SRO in day-to-day delivery, ensuring implementation remains on track. Oversees financial performance, partner engagement, risk mitigation, and quarterly reviews. Ensures delivery partners meet FCDO standards on safeguarding, compliance, and value for money.
- Technical Expertise: Dedicated advisers provide sectoral leadership across core components:
  - 1x Humanitarian Adviser – County Based Staff (SEO): Leads on humanitarian response, humanitarian partner engagement, risk mitigation, and coordination with donors, civil society, and government counterparts.
  - 1x Education Adviser (Grade 7): Leads on refugee education, chairs the refugee education coordination group and education development partner group, advises AAI donors on strategic direction and future planning, and works with the MoE to influence policy reforms for vulnerable Jordanians and refugee children.
  - 1x Social Development Adviser (Grade 7): Leads on social protection activities, safeguarding, and monitoring of poverty and vulnerability. Promotes gender equality and inclusion across programme components.
- Programme Delivery Team: Programme management capacity is delivered through a flexible team of 1 x senior programme manager, 3 x programme managers and 1 x programme officer, each assigned functional leadership over one of the three core components: Humanitarian Assistance, Education Support, Social Protection / Systems Strengthening or of monitoring and risk management[159].
  [159] Some of team may not be at 100% FTE on this programme.
- Programme Funded Posts (PFPs) will be used to deploy technical experts into partner agencies, aligned with Embassy governance and systems strengthening priorities.
- Cross-cutting responsibilities such as MEL, safeguarding, and risk management are coordinated jointly and reviewed quarterly. The team is supported by resources in economics, statistics, governance and procurement, and by the Strategy and Delivery Unit enabling robust performance tracking and learning. The team will also engage with the Political and Governance team around influencing and engagement.

Decisions around allocation of resources would follow the following process in line with this governance structure. The SRO has the authority to approve decisions (e.g. to enter into a partner agreement) relating to JHASS funding where these directly mobilise the programme in line with the approved business case, updating the Delivery Board for information. For decisions relating to the reallocation of resources within JHASS or across programmes the programme team, primarily technical experts and led by the PRO, would discuss and prepare advice. The PRO would present this to the SRO to decide on whether to proceed. Where the reallocation is below £0.5m the SRO makes the final decision. Where it exceeds £0.5m and is under £2m (or under £0.5m where novel or high-risk), it would then be presented to the Delivery Board for decision/ratification. Where it is over £2m or novel/high risk it would be presented to the Country Board. Should the programme team seek a business case cost addendum it would require Ministerial approval in line with FCDO’s internal processes given the size of JHASS as a £73m programme.

For escalation of risks, similarly the programme team would flag risks falling out of appetite to the SRO. Where risks fall out of appetite and can’t be managed by the team alone the risk would be escalated in BE Amman’s Portfolio Risk Register for discussion at the Delivery Board. The Delivery Board may then decide to escalate it to the Country Board via the Country Level Risk Register. The Country Board would then consider whether it needs to be escalated further such as to the FCDO MENA risk register or to Ministers, or whether it can be managed at post.

Additional BE Amman and cross-FCDO resources will be available to draw on proportionally throughout the lifetime of the programme including the Ambassador for targeted diplomacy with senior stakeholders in government, UN system, Ambassadors, and heads of agencies. The development director for targeted diplomacy with senior stakeholders in government, UN system and responsible for oversight of all ODA spend, compliance with FCDO rules and escalating risk to Headquarters when outside of risk appetite.

These arrangements are not fixed. They will be reviewed and adapted as necessary to reflect staffing realities, any changes to FCDO’s operating model and to ensure the governance framework remains fit for purpose. Where appropriate, structures will be reconfigured to maintain effective oversight, mitigate risks, and support agile delivery. A governance diagram outlining roles, reporting lines and oversight bodies are outlined below in figure 3.

Internally, the core JHASS team will meet weekly to monitor delivery and to go through overall outcomes results, risks, and logframe. We will also meet with HMA each month to provide updates on progress and discuss strategic issues relevant to JHASS. Externally, at least quarterly progress meetings will be held with partners to review implementation, risks (including fraud and safeguarding), and course correction. These meetings will be refined during the inception phase.

The JHASS governance model will include inputs from local stakeholders and marginalised groups. FCDO will ensure meaningful participation of representatives organisations such as Persons with Disabilities (PWDs), especially during partner selection, quarterly reviews, and through feedback mechanisms built into the MEL framework. This supports FCDO’s commitment to localisation and inclusive programming.

Figure 3: Governance diagram outlining roles, reporting lines and oversight bodies

PROGRAMME DELIVERY CYCLE
Mobilisation: Following Business Case approval , off-budget financial aid and MEL contract will be mobilised through existing FCDO frameworks.
- Inception Phase: The inception phase will finalise implementation plans, governance protocols, the MEL framework, and risk management processes. It will also define the scope of partner progress meetings and establish reporting templates and benchmarks.
- Implementation Phase: Delivery will be coordinated through the HEART, who will provide technical oversight, manage contracts, and engage strategically with partners. At least quarterly partner meetings will serve to assess delivery against the Theory of Change, track KPIs, and adapt programming where needed. Regular engagement with government counterparts and other donors will ensure policy alignment and complementarity.
- The programme will apply responsive management, using quarterly data and partner reports to trigger changes in delivery. Changes to programme approach, scope, or resource allocation will be proposed by the HEART, discussed with the SRO, and approved by the Delivery Board/Country Board before following the relevant approval guidelines. These decisions will be informed by field data, risk trends, and external evidence.
- VfM will be tracked through quarterly reviews using economy, efficiency, effectiveness, and equity criteria. VfM indicators will be embedded in the MEL framework and monitored through partner reports, financial analysis, and field validation visits by FCDO staff.
- Closure and Exit Strategy: The programme’s exit strategy as outlined in the Strategic Case will be further developed during implementation. A Project Completion Review will inform final learning and reporting.
RESPONSIVE PROGRAMME MANAGEMENT AND GOVERNANCE
JHASS will be a flexible and responsive programme, underpinned by strong data and analytical feedback loops. It will adjust to emerging opportunities and risks and respond dynamically to programme performance. A robust, overarching MEL function will support MEL activities.

The programme will be subject to ongoing review, assessing the effectiveness of implementation arrangements, the validity of programme assumptions, and evolving conditions on the ground. Where evidence indicates the need to scale components up or down, or to revise the delivery model, changes will be made - subject to approval in line with the governance structure outlined above.

PARTNERSHIP MANAGEMENT
The JHASS programme will adopt a rigorous and transparent approach to partnership management, ensuring that all implementing partners are selected, supported, and held accountable in line with FCDO standards and the principles of effective development cooperation.

PARTNER SELECTION AND DUE DILIGENCE
Partner selection will be conducted through open call for proposals or via existing FCDO frameworks, ensuring fairness, transparency, and VfM. Due diligence assessments for all partners will be in place which will evaluate:
- Financial capacity and controls
- Organisational governance and leadership
- Safeguarding policies and track record
- Delivery capacity and technical expertise
- Alignment with FCDO’s values, including localisation, inclusion, and transparency.

DOWNSTREAM PARTNER OVERSIGHT
All lead partners will be required to submit detailed downstream partner management plans during the inception phase. These plans must include:
- Clear roles and responsibilities of sub-grantees.
- Monitoring and reporting tools.
- Risk mitigation strategies.
- Safeguarding compliance mechanisms.
- Referral pathways and complaints handling procedures.

FCDO will review downstream partner risks quarterly and conduct spot checks on any high-risk sub-grants to ensure compliance and accountability throughout the delivery chain.

ONGOING PARTNER ENGAGEMENT AND PERFORMANCE MONITORING
During implementation, FCDO will convene structured at least quarterly review meetings with all partners. These meetings will assess:
- Progress against the logframe and delivery milestones.
- Financial performance and budget utilisation.
- Risk management, including fraud and safeguarding.
- Operational challenges and opportunities for adaptation.

These reviews will be informed by partner reports, field visits, and technical input from FCDO sectoral advisors (e.g., education, humanitarian, social protection, MEL). FCDO will provide ongoing support and challenge to partners to ensure high-quality delivery and continuous improvement.

INCLUSIVE AND DATA-DRIVEN MONITORING
Partners will be expected to report disaggregated data by sex, age, disability, nationality/refugee status and other relevant protected characteristics, to enable inclusive monitoring and ensure that the programme is reaching the most marginalised groups. This aligns with FCDO’s commitment to equity, gender equality, and disability inclusion.

MONITORING, EVALUATION AND LEARNING
The MEL approach and programme monitoring oversight for the JHASS programme will be led by the BE Amman team. They will be responsible for ensuring that the programme is implemented effectively, delivers VfM, and adheres to FCDO’s PrOF guidance. The FCDO team, supported by an independent MEL supplier, will work closely with implementing partners to ensure that monitoring systems are robust, inclusive, and aligned with FCDO quality standards. To support the generation of evidence and enduring accountability, the programme will commission at least one independent review – mid-term, final, or both, alongside targeted research, and analysis. These reviews and research activities will collectively inform programme implementation, enhance strategic learning, and guide future planning. Monitoring will primarily be conducted through regular partner reporting, complemented by independent monitoring supplier and FCDO field visits. During the inception phase, a comprehensive MEL framework will be developed, which will include:
- A detailed results framework/logframe with milestones and end targets aligned with the programme’s Theory of Change.
- A review of implementing partners’ data collection, MEL, and analysis plans, as well as their reporting mechanisms. Partner MEL systems will form the backbone of programme reporting and analytical delivery. FCDO will work with partners to ensure these systems generate meaningful insights into outcomes and VfM.
- Annual Reviews to systematically assess progress against the logframe, ensuring that outputs and outcomes are being delivered as planned. These reviews will assess VfM across economy, efficiency, effectiveness, cost-effectiveness and equity, and test the continued relevance of the Theory of Change in light of new evidence and contextual shifts. They will draw on partner reports, disaggregated data, field visits, and beneficiary feedback to inform adaptive management, highlight areas for course correction, and guide strategic planning.
- A mid-term reviews if completed will assess whether the programme remains on track to achieve its intended outcomes and whether the Theory of Change remains valid. It would also evaluate the strategic value of the programme and its contribution to FCDO objectives.
- A Final Review would assess overall impact, sustainability, and lessons learned, informing future programming and contributing to institutional learning.
- To support this MEL approach, programme funds will be allocated to implementing organisations for data collection and analysis. This will strengthen the evidence base for decision-making and improve the efficiency and effectiveness of influencing objectives. This will primarily come from the systems strengthening budgets for each sector.
- FCDO will have a supplementary MEL budget for research, evidence generation, and learning activities and will also conduct a Project Completion Review at the end of the programme, drawing on all available evidence, including beneficiary feedback, field observations, and external reviews, to assess the programme’s legacy and inform future design.
- Across activities, the programme will track climate-related outcomes and ICF-tagged activities through indicators in the logframe and VfM framework, aligned with FCDO’s ICF reporting requirements.

FCDO will commission as part of MEL activities, targeted research, evidence generation, and learning activities aligned with programme priorities. These efforts will inform implementation and continuous learning, improve accountability, and generate evidence to support FCDO’s advocacy on Jordan’s refugee response. Evidence will be pursued to help us advocate for pro-refugee policy, such as further access of refugees to employment in specific sectors, and to advocate against any further reversals in refugee inclusion. Key institutions we will target are likely to include the MoL, MoPIC, MoE, MoSD and MoF. It will include products such as socio-economic assessments, political economy analysis, education studies, migration trends and aspirations, and policy briefs to guide decisions, improve accountability, and support advocacy. Activities will be pursued in line with BE Amman’s influencing strategy in coordination with teams across the embassy including the Political and Governance team. Existing partners will be used as a preference in the generation of evidence to streamline programme administration.

FCDO Jordan has experience of pursuing evidence generation to complement our advocacy agenda under the SSERJ programme which will be drawn upon. It funded a valuable political economy analysis around refugee employment in Jordan. It also funded WFP and UNHCR skills mapping work which showed the economic contribution of refugees to Jordan’s economy[160] and was used to advocate for refugee employment in niche sectors open for work for refugees including the garment sector and Information and Communication Technology (ICT) sector[161] . The data also has been used to highlight the skills of refugee returnees to support reconstruction efforts in Syria such as to the WB and Syrian investors. The evidence has influenced GCFF funding on UK priorities on refugee economic inclusion including a digitalisation project and refugees working in agriculture.
[160] Jordan Refugees’ Economic Participation, Boston Consulting. WFP, UNHCR PowerPoint Presentation (wfp.org)
[161] Garment sector, ICT sector, Agriculture sector, Construction sector
STRATEGIC ALIGNMENT AND COORDINATION
FCDO will ensure that partner activities are aligned with national systems and donor coordination mechanisms. Where appropriate, partners will participate in government-led steering committees and technical working groups to promote harmonisation, policy alignment, and sustainability.

RISK ASSESSMENT AND MANAGEMENT
What are the risks and how will these be managed?
Overall, we assess the JHASS programme risk to be MODERATE taking into consideration the scale and complexity of the programme. There is potential for escalation depending on regional developments, funding volatility, and operational challenges. Risk management will be embedded throughout the programme lifecycle, aligned with the FCDO’s PrOF and risk management policy.

A full analysis of the risks associated with providing funding to UN multilateral agencies (UNHCR, UNICEF, WFP), key delivery partners for the JHASS programme, along with strategies to mitigate these risks has been/will be recorded in the programme’s risk register. The JHASS programme have adopted a risk register (see annex G). The JHASS programme team will report against these risks and mitigating actions in each strategic review; and will be required to flag any major changes and risks through ongoing engagement.

The JHASS programme will operate in a complex and dynamic environment, requiring a robust and adaptive risk management framework. Risks will be managed in line with FCDO’s PrOF and risk policy. A risk register will be maintained online (on Aid Management Platform (AMP)) and updated at least quarterly. Escalations will be documented, with the SRO accountable for risk management and the PRO leading quarterly reviews.

Partners will be expected to report risks, fraud, and safeguarding concerns through standard channels. Risk will be a standing agenda item in at least quarterly partner meetings. The Embassy risk champion will support alignment with wider BE Amman risk governance. All allegations of fraud or safeguarding will be reported per FCDO protocol. A zero-tolerance approach will be upheld across all agreements.

The JHASS risk register is provided in Annex G. Some of the key risks and mitigation strategies are described below:

- Funding volatility, potential further UK aid cuts affect programme performance and humanitarian needs.
- Significant risk to JHASS is the geopolitical instability. Jordan is located within an instable region and has limited natural resources.
- Uncertainties around other donors’ funding: Further reduction in funding by other donors could occur creating additional pressures on humanitarian agencies and the GoJ in a context of already reduced funding.
- Government policy shifts: Changes in refugee policy or restrictions on access to services could undermine programme delivery.
- Complex management due to a multi-sectorial approach and multi partner delivery mechanism which could lead to coordination and oversight challenges if not appropriately managed.
- Social tensions and protection risks: Perceived inequities in aid distribution may fuel host-refugee tensions.
Risk Monitoring
Throughout the life of the JHASS programme, risk will be overseen in the first instance by the PRO and SRO. When necessary, risks will be escalated up the chain of command to the Delivery and Country Board and beyond as set out above. In circumstances regarding suspicions of fraud, terrorism financing, and money laundering/corruption, the incident (if any) would be reported to the BE Amman Fraud Liaison Officer (FLO), they will escalate the issue as appropriate. In certain circumstances concerns will be raised to Head of Mission/HMA level as appropriate, particularly any risks around safeguarding, which will be a key focus of BE Amman’s monitoring of this programme. Reviewing the risk register and appropriate mitigating actions will form an integral part of regular reviews.

There will be quarterly reviews of risks to ensure they are within the overall BE Amman’s risk appetite. The risk matrix will contain clear triggers and channels for any escalation through BE Amman structures as outlined above as required. Risks will be discussed at team programme management meetings and the at least quarterly stakeholder progress reviews, ensuring a good flow of risk information. Risks will be jointly owned by BE Amman and delivery partners/donors.

Risk Appetites
The JHASS operates in a complex and evolving regional environment and humanitarian landscape, where achieving meaningful and delivering tangible output and outcomes requires balancing ambition with risk management. The programme adopts a calibrated risk appetite, recognising that certain risks are necessary to achieve the programmes desired outcomes.
- Strategy and Context: risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact. BE Amman appetite is receptive for this risk.
- Policy & Programme Delivery risk: risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing, and/or operational support. These risks undermine our impact and influence. BE Amman appetite is receptive for this risk.
- People: risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance. BE Amman appetite is cautious for this risk. JHASS recognises that leadership, workforce capacity, and engagement dynamics are fundamental to programme success. While some degree of uncertainty is inherent in staffing and partner engagement, the programme prioritises investment in leadership development, fostering a collaborative culture, and ensuring staff resilience through training and professional support.
- Financial risk: BE Amman has a cautious appetite for financial and fiduciary risk. JHASS is committed to strict financial accountability, compliance, and value-for-money principles. In the 2023 Transparency International Corruption Perception Index[162], Jordan was ranked 59 out of 180 countries assessed so the risk of aid diversion is relatively low. While some flexibility is required to respond to evolving political and economic conditions, the programme will maintain rigorous financial controls, conduct regular risk-based assessments, and ensure robust oversight mechanisms to prevent misuse of funds and financial mismanagement.
  [162] 2021 Corruption Perceptions Index
- Reputational: risk arising from political or adverse events, including delivery failures and ethical violations, damaging the FCDO’s reputation. BE Amman appetite is cautious for this risk.
- Safeguarding: BE Amman has a cautious appetite for safeguarding risk. The programme upholds a zero-tolerance policy for safeguarding violations, particularly in relation to women in governance, young activists, refugees, and ethnic/religious minorities engaging in reform. JHASS will implement robust reporting mechanisms, offer legal and support where needed, applying digital security protocols, and protective engagement strategies to prevent harm and uphold ethical governance standards. These include Safeguarding Against Sexual Exploitation and Abuse and Sexual Harassment (SEAH).

SAFEGUARDING
Safeguarding is central to JHASS programme design and delivery. All partner agreements will include safeguarding clauses and reporting requirements. The FCDO team will engage on safeguarding during partner reviews and ensure alignment with the UK’s safeguarding due diligence standards. Complaints mechanisms will be established for beneficiaries. Partners must have clear safeguarding policies in place, including referral pathways and staff training. Serious concerns will be escalated to reportingconcerns@fcdo.gov.uk. Environmental risks are expected to be low but will be assessed during inception. Where applicable, partners will be required to meet FCDO environmental due diligence standards.

Exit Strategy. Jordan’s four-year humanitarian programme is designed to be context-sensitive, acknowledging that a successful transition hinges on the evolving operational environment and regional geopolitics. Central to this strategy is easing Jordan’s burden of hosting refugees by supporting voluntary returns to Syria, strengthening national and international systems and local capacities to better support refugees and vulnerable Jordanians which remain, and building resilience to future shocks and crises thereby reducing future humanitarian needs. While a full exit from humanitarian assistance is unrealistic given many refugees will still remain the programme seeks to scale down support and exit some activities by the end of the programme.

Annex A: BE Amman’s Humanitarian Programming in Recent Years
In recent years our programme portfolio has consisted of the following programmes in the humanitarian, education and social protection sectors:
- Strengthening societal and economic resilience in Jordan programme – provides social protection TA, along with financial aid to the SSC to extend social security coverage to vulnerable workers, along with cash assistance.
- Multi-Purpose Cash Assistance to Refugees in Jordan programme (2019-2024) – provided cash assistance to the most vulnerable refugees living in Jordan.
- Jordan Compact Education Programme (JCEP) – supported the education of refugees through national systems through AAI (2016-2025).
- BRIDGE - supported the education of refugees through national systems through AAI (2022-2026).
- Jordan Protection Programme (2022-2026) (JPP) - provided protection services to refugees and vulnerable Jordanians including GBV prevention and response, child protection, psychosocial support and disability rehabilitation services, systems strengthening and an emergency facility supporting WASH and voluntary returns to Syria. This followed on from the success of protection services delivered in the Humanitarian Protection for Vulnerable refugees and HCs in Jordan (2018-2021).
- Emergency Social Protection in Jordan (2020-2023) (ESPJ) – provided financial aid, combined with TA for institutional strengthening, capacity and systems building (e.g. MIS systems, grievance mechanisms, targeting) enabling the efficient and rapid scale-up of social assistance in response to the COVID-19 pandemic.

Annex B: International comparisons on Jordan emissions

Country	Emissions Total / (Mt CO₂e/yr)	% Global	Emissions per capita (tCO₂/person)	Energy Use Total / (TWh)	% Global
UK	427	0.8%	4.53	2,031	1.2%
China	15,685	29.1%	8.66	44,279	26.4%
US	6,017	11.2%	14.20	26,644	15.9%
India	3,943	7.3%	2.20	10,123	6.0%
Jordan	21	0.04%	2.01	28	0.02%
Egypt	329	0.6%	2.22	180	0.1%
Saudi Arabia	623	1.2%	20.38	355	0.2%
UAE	218	0.4%	20.13	130	0.08%
Global Total	53,800 (Global total)	—	4.73 (Global average)	167,791 (Global total)	—

sources:
https://ourworldindata.org/co2/country/jordan;
https://www.iea.org/countries/jordan/emissions

Annex C: Internal Risk Facility
This Annex describes the operation of the Internal Risk Facility (IRF), which could ringfence 10% of the humanitarian cash assistance programme budget each financial year to rapidly disburse funds in response to an emergency. The IRF delivers on the Core Humanitarian Assistance JHASS component.
Background and justification
There are shocks and associated spikes in needs that can be predicted, and others that will remain unforeseen. Responses can be slow, offer poor value for money and have a negative impact on people’s wellbeing. Even with good early warning and rapid donor decision making, it can take weeks to finalise donor (including the FCDO) administrative programme processes.

IRFs have been widely developed by the Department for International Development (DFID) and FCDO in recent years as an effective mechanism to prepare and act quickly in the face of a sudden and/or predictable shock. An IRF provides flexibility to a specific FCDO programme so that it can scale up quickly and effectively. It is part of the JHASS business case to this effect. It will provide swift response mechanisms that can save considerable time in programme administration and ensure we are well prepared in advance. We also expect additional benefits of promoting better planning and preparedness by partners, robust decision making, more time and focus on risk and controls etc, linked to the system strengthening component of our programme.

There is a highly unstable political context in the Middle East which could potentially involve further mass displacements into Jordan over the period of the business case, particularly the ongoing instability in Syria, Gaza and the West Bank. Humanitarian needs in Jordan are also rapidly evolving and subject to change over coming years, and donor funding volatility and sector-specific shocks (health outbreaks, WASH infrastructure failures, or protection gaps) may rapidly escalate needs beyond current projections. As such, 10% of the funding of the humanitarian cash assistance budget could be used to respond to any new emergency or critical gaps if needed, so the UK can deliver timely and effective assistance. It builds on the successful contingency fund model under the JPP, which allowed FCDO to respond swiftly to emerging WASH needs and support voluntary returns to Syria.

There are sectors in Jordan that have been more hit by reduced funding, and even if FCDO doesn't currently support those sectors, we will maintain a close monitoring in order to quickly respond if needs and gaps are high and putting the life of vulnerable groups – including the beneficiaries of the JHASS programme – at risk. For instance, in the WASH sector, it is increasingly difficult to maintain the minimum provision of water, sanitation, and hygiene services in camps due to the continuous decline in humanitarian funding for the refugee response. This has led to the prioritization of life-saving activities, instead of sustainable centralized systems. The closure of the Emirati Jordan Camp last May and relocation of around 2000 of its residents to Azraq camp had put additional pressure on the water network. Moreover, the refugee community is increasingly vulnerable to waterborne diseases, with diarrhoeal diseases re-emerging and placing the health of children and older people, including outside camps at significant risk. Recent studies show that while hygiene promotion efforts in camps appear to contribute positively to reducing contamination levels, there remains a risk of backsliding if preventive measures are not consistently reinforced. The recent international funding cuts have also put critical health services for refugees at risk; 72 supported healthcare facilities or projects have been suspended or have reduced their services provision. Primary health services in refugee camps remains the sole responsibility of external aid actors, with acute gaps in primary healthcare and in sexual and reproductive health. In urban areas, refugees can access healthcare services at subsidised rates. However, these costs still represent a significant financial burden, leading many refugees to deprioritise healthcare. Around 43,000 refugees may lose access to primary health care and cash assistance for medical needs.
Triggers
The 10% for the IRF will be taken from the humanitarian budget of the programme, specifically the cash assistance component. We judge this to be reasonable to respond to changes in context and emerging needs that wouldn't be covered by other donors.

The JHASS team will continuously monitor agreed indicators that can trigger IRF activation. The IRF triggers will be based on partners needs assessment, and FCDO qualitative and quantitative assessments. Triggers will be used to release funds for both preparedness measures (e.g. stockpiling), and rapid response (with relief item distribution and/or service delivery), and short programmes to respond to documented emerging multi sector needs and gaps.

The IRF could be mobilised as a response to:
- new and immediate acute needs, such as large-scale acute needs arising from a new conflict in the region and consequent new refugee influxes or displacements; a new climate-related crisis (flash floods, heatwaves), or a health outbreak.
- large scale acute needs related to a slow onset crisis, such as sudden funding gaps in life-saving sectors particularly in camps, or an acute deterioration of the food security situation.
- Preventative Early Action, to prevent vulnerable populations sliding into destitution and adopting damaging coping mechanisms

Responses under these headings may include life-saving assistance, i.e. food, cash, water, nutrition, health and additional protection services.

The IRF will be activated:
When other mechanisms in Jordan have failed, or the scale of needs exceeds existing mechanisms, and calls for additional funds have been made by humanitarian partners through ad hoc communication, lobbying and advocacy, flash appeals or updates to existing Humanitarian Response Plans.
When the Government and UN-led response system have developed contingency and readiness plans.
Once suitable justification from our current partners under the JHASS (UN and NGOs’ needs assessments) provided to FCDO has enabled us to determine the UK added value to respond. The IRF funds would provide relatively short-term emergency provision of supplies or services (no time limit is placed).

The IRF is intended to be used based on the specific triggers and criteria identified for the IRF. As with activating the IRF, the decision to reallocate funds from the cash assistance component to this mechanism would be made by the SRO where under £0.5m. Where over £0.5m and under £2m, or novel or high-risk, the decision would then be presented for ratification by the Delivery Board. Where over £2m it would be presented for ratification to the Country Board. The JHASS PRO will review likely need at the end of each financial year and make a recommendation to the SRO. Urgent needs and use of the IRF will also be considered during the course of the year on a need’s basis.
Governance and management
Eligibility
Funding will be disbursed through existing JHASS partners (UN and NGO. FCDO will assess whether existing partners are well positioned (capacity, geography, access) to scale up to meet priority needs. Only if their capacity and expertise is absolutely unable to fulfil the needs, additional partners would be identified.
Activation
Where the team believes the trigger(s) have been met, the PRO will seek SRO approval to activate the IRF, specifying the evidence for a trigger having been met, the partner selection process to be followed, the size and duration of the funding to be provided. The SRO will then present the case for the allocation of this contingency funding for approval to the Delivery Board and/or Country Board if needed (likely for Out of Board decision) depending on size of funding/sensitivity in line with the programme governance processes outlined in the Management Case. The request will include a justification of need, proposed delivery modality, and risk assessment.
Mobilisation
This IRF proposes the option of either direct award or a call for concept notes/proposals among JHASS partners. The PRO should recommend one option to the SRO during activation, based on urgency, the capability of partners to meet identified needs and the capacity of the team to review multiple concept notes.

The IRF can be mobilised in two ways:
1. Direct award: In the likely event of the need to respond rapidly to a specific emergency situation, the team will assess needs and use existing information on partner access and capacity to approach partners directly and request a concept note/proposal. Partners will submit documents via email within 48 hours of the request. The HEART will review and submit the chosen project to the SRO for approval. Approval should ideally be granted 48 hours after receipt of concept notes. Partners will be informed of the decision ideally within 96 hours of the request being made.
2. Call for proposals: the HEART team will issue a call for proposals when funding is needed to respond to a slow onset crisis or for preventative early action. At activation, the SRO will specify the timeline for each stage of the process.

To ensure flexibility, this amount can be supplemented by headroom (for example, from Crisis Reserve bids), depending on the scale of need. The IRF budget will be reviewed at the end of each financial year.
Duration
The duration of projects funded by the IRF will be specified when seeking SRO authorisation to activate the IRF and may be extended with their approval. If an existing partner is involved the project would be administered through a cost-extension to the selected partners agreement.

Implications for partners’ preparedness
Procedures for emergency response funding alone cannot ensure timely and effective interventions by FCDO partners. Emergency preparedness investments are required to ensure the feasibility of response. A minimum set of investments in emergency preparedness can therefore be incorporated into all projects within the programme, and the capacity of partners (and their track record) for developing and updating readiness.

Annex D: Potential VFM indicators
Based on previous programmes, the table below outlines potential VFM metrics. VFM indicators on WASH and health will be developed in line with the WASH[163] and Health VFM sector guides[164].
[163] https://washdata.org/sites/default/files/documents/reports/2018-04/JMP-2017-update-methodology.pdf
[164] Better value, better health Strategy and implementation plan for value for money in WHO
IMPACT: Enhanced socio-economic resilience and social cohesion among refugees and vulnerable Jordanians, supported by inclusive systems and contributing to long-term stability in Jordan and the region.
Core humanitarian funding	Economy / Efficiency / Effectiveness / Cost-effectiveness / Equity	Admin fees, digital banking transaction fees / Costs per beneficiary, Total cost transfer ratio, admin as a % of total spending / Cost per household support with climate resilient interventions / No. of direct transfer recipients / Effectiveness of targeting mechanism (% of beneficiaries in the bottom income deciles) / % poverty rates, % improved food security, / Local economy multiplier effects (improving local markets for refugees and HCs in Jordan) / Cost per household lifted above the national poverty line (supporting social cohesion) / % beneficiaries by gender, age, disability and specific vulnerabilities e.g. climate vulnerability
Education support	Economy / Efficiency / Effectiveness / Cost-effectiveness / Equity	Cost per child per school year / Unit costs for tuition fees and textbooks / Multiple donors pooling funds / Primary completion rate / Primary school survival rate / % of refugee of pupils (boys and girls) completing school. / Improved learning outcomes / Reduction in number of children out of school / Cost of educating a refugee per annum in a) camp schools; b) double shift schools and c) single shift schools / Total number of children enrolled with disabilities. / Total number of children enrolled in drop-out and catch-up programme. / % of out of school children
Systems strengthening	Economy / Efficiency / Effectiveness / Cost-effectiveness / Equity	Proportion of administrative costs versus programme costs consistent with that of other similar research programmes. / Timeliness and quality of TA support / Evidence of adjustments in government (recipient and donor) policy and / or programmes / Evidence of improvements in assistance to people affected by crises / Cost of TA support for strengthening national systems e.g., leading to improved outcomes in social protection. / Coverage of beneficiaries reached who are severely vulnerable to crises/shocks including climatic

Annex E: Membership of BE Amman’s Delivery Board and Country Board
Delivery Board membership	Country Board membership
Description: Responsible for delivery oversight of the programmes that deliver against the HMG Jordan Country and Business Plan. It ensures operational excellence by ensuring appropriate controls, assurance, consistency, and capability.	Description: Responsible for the strategic direction for all activity and resources at Post to ensure these align with the embassy’s Country and Business Plan, and resource decisions to deliver the Plan.
Chair: The Delivery Board will be chaired by the Deputy Head of Mission/ Development Director; the Deputy Head of Mission / Development Director who may delegate their role to an alternate (at least Grade 6/7). / In addition to the Deputy Head of Mission / Development Director, permanent members include: / Deputy Development Director / Campaign Goal Team Leaders or Deputies / Team Leader and Deputies of the Strategy and Delivery Unit (SDU) / Programme SROs / Representative of the Country Based Staff Association (CBSA) (optional) / Representatives from under-represented groups in the Embassy / An SDU secretariat / If a regular Board member is unable to attend, a designated replacement can deputise. / The Chair may invite others to attend boards regularly or extraordinarily, as full members or observers, as they see fit. Observers will be welcomed.	Chair: The BE Amman Country Board is chaired by the HoM. In HMA’s absence, the Deputy Head of Mission will act as Chair. / In addition to the HoM, permanent members include: / Deputy Head of Mission / Development Director / Deputy Development Director / Campaign Goal Team Leaders / Head of Strategy and Delivery Unit / Heads of all non-FCDO Sections, if different from categories above / Designated representative(s) of the CBSA / British Council / SDU Secretariat (see below) / Observers (see below) / If a permanent Board member is unable to attend, a designated replacement can deputise. / Representatives from other HMG departments or partners will be invited to specific meetings if the agenda covers topics that impact their direct interests. / Regional leads (such as Regional Trade Commissioners, or their representatives) and policy leads in London will be invited to attend meetings when relevant.

Annex F: Detailed budget for JHASS programme by sector[165]
[165] No budget for the IRF is provided since this would only be allocated should an emergency arise. Up to 10% of the humanitarian cash assistance budget could be used for it.

ANNEX G: JHASS Risk Register
Risk Description (cause, event, consequence)	Risk Category	Gross Likelihood	Gross Impact	Gross Risk Rating	Mitigation Strategy (including timescales)	Residual Likelihood	Residual Risk Rating	Residual Impact
Geopolitical Instability: Escalation of conflict in Syria, Gaza, and the West Bank could increase refugee flows to Jordan and strain resources.	Strategy and Context	Likely	Major	Major	Maintain flexible funding and programming/IRF; strengthen contingency planning and early warning systems.	Possible	Major	Major
Uncertainties around other donors’ funding: Further reduction in funding driven by US funding/ODA cuts leads to erosion in core humanitarian, education and social protection support. This leads to additional pressure on humanitarian agencies and the GoJ in a context of already reduced funding.	Strategy and Context	Likely	Major	Major	Strengthen stakeholder engagement and donor coordination platforms to improve visibility of donor intentions; advocate for transparency in funding commitments; map donor contributions; scenario planning; promote strategic dialogue and collaboration among donors in Jordan; advocate for and support increased domestic financing where politically feasible (e.g. aspects of social protection).	Likely	Moderate	Moderate
Funding Volatility: Further reduction in the FCDO’s budget for this programme; this affects the finance for the programme in the outer years, creates budget instability for partners, produces a drop in performance and leads to unmet needs among vulnerable populations and reputational risk for FCDO and partners.	Policy and Programme Delivery	Highly Likely	Major	Severe	Programme design enables positive impact and VfM at varying levels of funding; flexible programme designs able to scale up or down; ongoing and close communication with Headquarters/MENA to understand ODA picture; achieve quick results and use evidence and impact stories to demonstrate impact and VfM; scenario planning; sectoral coordination and transparency on changes; regular review of exit strategy.	Likely	Major	Major
Complex management: multi-sector, multi-partner delivery creates coordination and oversight challenges.	Policy and Programme Delivery	Likely	Moderate	Moderate	Restraining delivery to six core partners and a high bar for any additional partnerships (e.g. for IRF); clear governance structures; shared delivery framework; joint Theory of Change, logframe, and MEL approach managed by independent supplier; regular joint team coordination meetings to review progress, address bottlenecks, and adapt to emerging needs or contextual changes; PRO acts as single main project focal point.	Possible	Minor	Minor
Aid Diversion and Fraud: Risk of misappropriation of funds or resources in a high-need, high-volume aid environment. Fraud and / or aid diversion occurs due to weak systems of governance and accountability. This detracts from the effectiveness of the programme and potentially causes reputational damage.	Financial and Fiduciary	Possible	Moderate	Moderate	Conduct due diligence and delivery chain risk mapping; enforce zero-tolerance policy; audits and spot checks. The programme will have robust monitoring systems and oversight processes. These will be detailed in the FCDO due diligence review which will understand the processes to mitigate and manage fraud risks and provide clear actions where there are weaknesses. FCDO will map delivery chain risks and use independent monitoring to assess delivery chain risks through field observation, beneficiary feedback and expenditure monitoring.	Unlikely	Minor	Minor
Social Tensions and Protection Risks: Perceived inequities in aid distribution may fuel host-refugee tensions; increased GBV, child labour.	Policy and Programme Delivery	Likely	Major	Major	Apply conflict sensitivity and equity-based targeting; protection services include community engagement promotive of cohesion; social care interventions promotive of cohesion.	Possible	Moderate	Moderate
Government Policy Shifts: Changes in refugee policy or restrictions on access to services could undermine programme delivery.	Strategy and Context	Likely	Major	Major	Maintain strong diplomatic engagement; align with national strategies; support inclusive policy dialogue; advocacy drawing on evidence generated under MEL approach.	Possible	Moderate	Moderate
Climate and Environmental Shocks: Water scarcity, heatwaves, and flash floods may disrupt service delivery and increase vulnerability.	Strategy and Context	Likely	Moderate	Moderate	Integrate climate resilience into social protection components; support shock-responsive systems.	Possible	Moderate	Moderate
Safeguarding and SEAH: Risk of sexual exploitation, abuse, or harassment by implementing partners or within communities. Implementing partner and their downstream partners do not apply a safeguarding policy, leading to an increased risk of harm and abuse through programme funded activity.	Safeguarding	Unlikely	Major	Moderate	Enforce safeguarding standards; require partner SEAH policies; establish complaints and referral mechanisms. Ensure FCDO safeguarding policies are reflected by the implementing partner and other downstream partners and are understood and implemented all the way down the delivery chain. FCDO to ensure that effective reporting mechanisms are available for staff and programme recipients through established and functioning grievance mechanisms and due diligence process assessments. Regular discussions on safeguarding will be held with partners.	Unlikely	Minor	Minor
Capacity and Capability: Due to ongoing FCDO restructuring, FCDO does not have management or advisory capacity to engage effectively with the programme beyond the first phase.	People	Possible	Moderate	Moderate	The FCDO will review internal capacity at each programme annual review.	Unlikely	Minor	Minor
Partnerships: Lack of availability of technically capable implementing partners and co-ordination with like-minded donor partners becomes no longer possible.	Policy and Programme Delivery	Possible	Moderate		BE Amman has had dialogues with key stakeholders to inform this business case, including INGOs and NGOs consultations. Given the recent funding reduction in Jordan, we anticipate receiving numerous proposals from potential NGOs. Continued dialogue investment in relationships with like-minded partners and coordination forums to sustain partnerships e.g. such as around education support.	Unlikely	Minor	Minor