## R&R programme
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach | [6 empty] | Business Case:
PROJECT TITLE | R&R (Resilience and Response) Programme - Mozambique | [5 empty] | 13. Impact: Mozambicans are more resilient to climate and conflict shocks, with reduced humanitarian impacts and stronger national and local systems able to anticipate, respond to and finance resilience over time.
IMPACT | Impact Indicator 1 |  | Baseline | 2027-03-01 | Target (Mar-28)
Mozambicans are more resilient to climate and conflict shocks, with reduced humanitarian impacts and stronger national and local systems able to anticipate, respond to and finance resilience over time. | Percentage of population in target areas covered by multi-hazard early warning systems | Planned | TBD (INGD data) | Baseline established | Increase from baseline |  | 14. Outcomes:
|  | Achieved |  |  |  |  | a. Strengthened institutional capacity within Government and key partners to plan for, finance and manage climate and conflict resilience, preparedness and response.
|  |  | Source |  |  |  | b. Improved mobilisation and effective use of climate finance for adaptation, resilience and nature‑based solutions.
|  |  | INGD (National Institute for Disaster Management); UNDRR Sendai Framework monitoring |  |  |  | c. Strengthened resilience of poor and vulnerable households and communities to withstand current and future climate and conflict‑related shocks, reducing reliance on repeated emergency assistance.
| Impact Indicator 2 |  | Baseline | 2027-03-01 | Target (Mar-28) |  | d. Improved ability of Government, private sector, and international partners to tackle underlying drivers of conflict.
| Progress against a resilience outcomes basket covering climate resilience, conflict resilience, climate finance and shock-responsive systems | Planned | TBC | TBC | TBC
|  | Achieved |  |  |  |  | 15. Outputs:
|  |  | Source |  |  |  | a. Enhanced institutional capacity across government, partner institutions and the private sector to manage conflict risks and to plan, finance and deliver climate preparedness and resilience, underpinned by timely and effective technical assistance.
|  |  | TBC |  |  |  | b. A pipeline of innovative, catalytic conflict, climate‑resilient and nature‑based projects developed and supported, with improved readiness for climate finance.
c. Humanitarian preparedness, anticipatory action and rapid response mechanisms strengthened at national and sub‑national levels.
d. Evidence, learning and performance data generated to inform scale‑up, adaptation and transition from humanitarian response to more sustainable resilience approaches.
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions | e. UK engagement, partnerships and influencing aligned across the portfolio to support a coherent UK offer on resilience, climate finance and preparedness.
Institutions and key partners effectively plan, finance and manage resilience, preparedness and response, including action on conflict drivers. | Number of institutions demonstrating improved capacity to plan, finance or manage resilience, preparedness or response | Planned | 0 | 3 (Climate Finance Unit, FIPAS, 3 district administrations (conflict)) | 7 | - Political and institutional space exists for reform-minded actors to engage on climate, humanitarian and conflict prevention agendas - GoM continues to prioritise and resource key institutional functions, including the Climate Finance Directorate and disaster management structures - Staff trained and supported through TA remain in post long enough to apply learning and embed changes - Security situation permits continued engagement with government and partners in conflict-affected areas - Private sector remains willing to engage in conflict-sensitive approaches and dialogue | f. Citizen-state social contract through security sector and local community resilience activity re-built and improved, and increased support for peacebuilding initiatives that leverage the private sector.
Achieved
|  |  | Source |  |  |  | 16. As a result of its design, the programme will make a “significant” contribution to climate change, as defined by the OECD DAC Rio Markers for Climate. At least 40% of the programme budget is estimated to be International Climate Finance (ICF) eligible. The following ICF Key Performance Indicators are likely to be monitored at the impact and outcome level:
|  |  | Partner monitoring data (use an institutional capacity assessment scorecard at baseline, midline and endline; define “improved” as progress against agreed dimensions (for example planning, coordination, fiduciary systems, use of evidence, preparedness systems) |  |  |  | a. ICF KPI 1: Number of people supported to better adapt to the effects of climate change
| Outcome Indicator 1.2 |  | Baseline | 2027-03-01 | Target (Mar-28) |  | b. ICF KPI 4: Number of people with improved (climate) resilience
| Number of UK-supported systems, protocols, policies or coordination mechanisms adopted and operationalised by government or key partners | Planned | 0 | 1 | 3 |  | c. ICF KPI 8: Ecosystem loss avoided (Ha)
|  | Achieved |  |  |  |  | d. ICF KPI 11: Public climate finance mobilised (GBP)
|  |  | Source |  |  |  | e. ICF KPI 12: Private climate finance mobilised (GBP)
Monitoring data showing documentary verification plus evidence of operational use (not just drafting or approval)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%) |  | Expected results
17. The programme is expected to deliver the following indicative results, aligned with the programme’s three pillars:
INPUTS (HR) | FCDO (FTEs) | [5 empty] | a. At least 4 new climate finance proposals approved and mobilised totalling £50m+ in public and private finance, catalysed by UK support. Projects will generate climate-resilient assets and benefit climate vulnerable communities, in line with national priorities.
b. At least 200,000 people receiving improved rural access to water through climate‑resilient investments, and through reforms and strengthening of the national rural water investment fund which enables leveraging of new financing (indicative projection, subject to co‑financing from climate finance and private sources).
c. At least 240,000 people reached through UK‑supported humanitarian assistance and shock‑responsive support. Those benefiting will include communities affected by both conflict and climate-related extreme weather events.
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions | d. More effective, locally led humanitarian and crisis response and preparedness. Reforms to be supported will include anticipatory and shock‑responsive approaches.
Improved mobilisation and effective use of climate finance for adaptation, resilience and nature-based solution | Volume of climate finance mobilised (GBP) catalysed by UK support | Planned | 0 | Climate finance pipeline developed | £50m mobilised | - International climate finance facilities (GCF, Adaptation Fund, CIFs, carbon markets) remain accessible and operationa - Political commitment to climate finance reforms remains stable and the Climate Finance Directorate continues to function with reduced political interference - GoM maintains a credible and transparent institutional framework for climate finance - Public and private investors remain willing to engage in Mozambique despite political and security risks - Carbon market regulatory frameworks develop sufficiently to enable blue/green carbon projects | e. At least 4 Community Conservation Areas (CCAs) supported, at least 2,000 jobs and income opportunities, and investment mobilised. Demonstrating this innovative rural development approach attracts further funding to scale Mozambique’s nature and wildlife economy – which has an estimated potential to increase by 10 - 20 times.
|  | Achieved |  |  |  |  | f. Private Sector funded peace mechanism established to deliver conflict sensitive CSR activity, support livelihoods and bridge service delivery gaps.
|  |  | Source |  |  |  | g. Improved social contract between local administrations and security actors and communities through the delivery of peacebuilding workshops and activities that support more human rights compliant security sector.
|  |  | Government/Partner reports |  |  |  | h. Improved conflict and political economy analysis to inform HMG and international community on obstacles and pathways to peace.
| Outcome Indicator 2.2 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Change in community-level revenue from supported value chains/livelihoods | Planned | 0 | Baseline established | 20% over baseline
Achieved
Source
Government/Partner reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions
Poor and vulnerable households and communities are more resilient to climate and conflict shocks and less reliant on repeated emergency assistance | Number of people supported to better adapt to the effects of climate change | Planned | 0 | TBC | TBC | - Security conditions permit humanitarian access to crisis-affected populations - Climate shocks do not exceed the capacity of strengthened systems to respond (i.e. no unprecedented catastrophic event overwhelms all systems simultaneously) - Humanitarian partners retain capacity to scale up and deliver in conflict and climate-affected areas - Government coordination and disaster management mechanisms remain functional - Anticipatory action triggers can be accurately monitored and verified - Markets function sufficiently for cash/voucher-based assistance to be effective - Early evidence and learning from Phase 1 demonstrates results and builds confidence for scale-up
Achieved
Source
Government/Partner reports
| Outcome Indicator 3.2 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Number of people protected through Anticipatory Action / Forecast-based Financing and disaster risk finance mechanisms | Planned | 0 | TBC | TBC
Achieved
Source
Government/Partner reports
| Outcome Indicator 3.3 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Number of people benefitting from peacebuilding value-chain activity OR Number of people in target districts who adopt peaceful mechanisms for resolving conflict | Planned | 0 | Baseline established | Increase of 50% on baseline
Achieved
Source
Government/Partner reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions
Enhanced institutional capacity across government, partner institutions and the private sector to manage conflict risks and to plan, finance and deliver climate preparedness and resilience, underpinned by timely and effective technical assistance | Number of institutions receiving UK-supported technical assistance aligned to agreed programme priorities, disaggregated by sector (climate finance, WASH, social protection, conflict/peacebuilding, preparedness) | Planned | 0 | 4 | 6: Climate finance - Ministry of Public Works (Directorate of Water) Water - Ministry of Planning and Development (Climate Finance Directorate) ANAC (Conservation) Private Sector ADIN Target Area Security Actors Target Area District Administrators | -Qualified technical advisers and experts are available and deployable within required timeframes -Government and partner counterparts are willing and available to engage with UK-supported TA across climate, WASH, social protection, preparedness and conflict sectors -Staff trained and supported through TA remain in post long enough to apply learning -Security conditions permit TA deployment in conflict-affected areas, including northern Mozambique -Institutional reform processes are not blocked by political or administrative changes during the programme period
Achieved
Source
Government/Partner records; Climate finance facility submission records
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | 2027-03-27 | Target (Mar-28)
| Number of conflict and political economy analyses produced and shared with HMG and international partners to inform policy and programming | Planned | 0 | 1 | 2
Achieved
Source
Partner reports; Carbon market project records
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions
A pipeline of innovative, catalytic climate-resilient and nature-based projects developed and supported, with improved readiness for climate finance | Number of climate finance proposals submitted to relevant financing mechanisms with UK support, disaggregated by sector (WASH, social protection, nature/conservation, other) | Planned | 0 | TBC | 4 | - Security conditions in conflict-affected areas permit access for peacebuilding activities - Local communities willing to engage in dialogue and reconciliation processes - Extractive sector companies willing to engage on Voluntary Principles implementation - Private sector actors receptive to conflict-sensitive business practices - Political space for civil society peacebuilding work maintained - Partners selected through Call for Proposals have capacity to deliver
Achieved
Source
VPSHR Secretariat reports; Government of Mozambique records
| Output Indicator 2.2 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Number of community based value chains supported | Planned | 0 | 2 | 4
Achieved
Source
VPSHR Secretariat reports; Government of Mozambique records
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Number of Community Conservation Areas (CCAs) supported through UK-backed partnerships | Planned | 0 | Partnership established; target areas identified | Up to 30 LMMAs and 4 CCAs supported
Achieved
Source
BIOFUND annual reports; Conservation area management records
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions
Humanitarian preparedness, anticipatory action and rapid response mechanisms strengthened at national and sub-national levels, informed by evidence and learning | % of After Action Review action points implemented by INGD within agreed timeframes | Planned | 0 | TBC | TBC | -Security conditions permit engagement with government, partners and communities in target areas, including northern Mozambique -Government maintains functional disaster management coordination structures (INGD and sub-national) -Early warning data systems provide sufficiently timely and reliable information for trigger design and activation -Humanitarian partners willing to invest in preparedness and anticipatory approaches, not only reactive response -No single catastrophic event overwhelms all programme-supported mechanisms simultaneously
Achieved
Source
Verification of SOPs, triggers, contingency plans, financing arrangements, coordination platforms and evidence of operational use or activation; partner and government (INGD) records. Quarterly reporting.
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Average time from agreed trigger / shock onset to assistance delivery through UK-supported mechanisms (days) | Planned | TBD — baseline established from first qualifying response event | Measurable reduction from baseline | Reduced from baseline
Achieved
Source
Event-based operational tracking using humanitarian partner records for selected responses. Per-event reporting.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2027-03-01 | Target (Mar-28) | Assumptions
Citizen-state social contract rebuilt and improved through security sector and local community resilience activity, with increased support for peacebuilding initiatives that leverage the private sector | Number of operational peacebuilding, dialogue or community-security initiatives supported by the programme (including civil-military engagement) | Planned | 0 | 3 | 6 | -Security conditions in conflict-affected areas permit access for peacebuilding and community-security activities -Local communities willing to engage in dialogue and reconciliation processes -Extractive sector companies and other private sector actors willing to engage on VPSHR implementation and conflict-sensitive business practices -Political space for civil society and community-level peacebuilding work maintained -Security actors remain engaged in civil-military dialogue and accountability initiatives -No significant escalation in conflict that entirely closes operational space for peacebuilding activity
Achieved
Source
Initiative tracker; signed partnership/support arrangements; partner activity and progress reports; evidence of continuity and functioning
| Output Indicator 4.2 |  | Baseline | 2027-03-01 | Target (Mar-28)
| Private sector funded peacebuilding or conflict-sensitive mechanism established and operational | Planned | 0 | Process indicator TBC | Mechanism established and operational
Achieved
Source
Signed agreements; governance documents; funding commitments; implementation evidence; partner reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | 2026-03-27 | Target (Mar-28)
| Progress towards Mozambique achieving full membership of the Voluntary Principles on Security and Human Rights (VPSHR) initiative | Planned | Observer status | Action Plan developed | Action Plan approved; progress towards full membership
Achieved
Source
VPSHR Secretariat reports; Government of Mozambique records
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on E94: Leone Tarabusi: I think we can leave 4 CCAs supported also first year. What since the number will be stable across the 2 year
Note on F94: Leone Tarabusi: the 30 LMMAs are form BPF so out of R&R. So this need to be cancelled leaving only the 4 CCAs

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.