Programme Completion Review

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

Programme title: UK Participation in Jordanian Helicopter Airbridge
Programme Value £ (full life): £500,000	Review Date: 30/07/2025
Programme AMP Code: 400574	Programme Start Date: 10/02/2025		Programme End Date: 30/04/2025
DevTracker Link to Business Case:		DevTracker Programme GB-GOV-1-400574 Documents
DevTracker Link to results framework:		DevTracker Programme GB-GOV-1-400574 Documents

## SUMMARY AND OVERVIEW

Progamme Summary: / The “UK Participation in Jordanian Helicopter Airbridge” programme, valued at £500,000 was initiated as a UK response to the King of Jordan’s request in September 2024. The objective was to continue to support the “International Gaza Humanitarian Gateway”, that includes the land corridor, helicopter airbridge and possible renewed airdrops to deliver urgent aid from Jordan into Gaza. / This programme was approved by Ministers based on a submission to support the helicopter airbridge initiative. / Background: / Since October 2023, the British Embassy Amman (BEA) has worked to support the Jordanian and UK’s humanitarian response in Gaza, through several components including: / Funding provision under the British Consulate General Jerusalem (BCGJ) oPt Humanitarian programme budget to the Jordan Hashemite Charity Organisation (JHCO) who have been officially assigned, under Jordanian Royal Directives, to lead the humanitarian response to Gaza. / Co-chairing (with Netherlands) the Amman-based donor group to coordinate the donor response from Amman and liaise with Government and UN / Support to the Government of Jordan and the UN to establish a functioning overland route for the delivery of humanitarian assistance from Jordan to Gaza. / Working with the Jordanian Armed Forces (JAF) on airdrops to Gaza / On the 20th of November 2024, the Jordanian Armed Forces (JAF) delivered critical medical and humanitarian supplies via a convoy of military helicopters into Southern Gaza and received by the World Food Programme. This operation was a proof of concept for King Abdullah’s ‘Humanitarian Airbridge’ initiative, aimed at delivering modest amounts of aid, demonstrating ‘international solidarity’ and putting pressure on Israel to allow more aid to enter Gaza by land. / On the 28th of January 2024, after the start of the ceasefire, King Abdullah launched another “Helicopter Airbridge” initiative aiming to fly 16 helicopters on a constant rotation over seven days to deliver 34 metric tonnes of high-value aid to Gaza per day. This initiative was supported by the UK through a ministerial approval which was complementary to the scaling up of the Jordan Land Corridor, as part of the humanitarian surge of supplies into Gaza.
Intended policy objective(s) of projects within this programme. / The objective of this programme’s activity was to provide emergency aid to Gaza following the ceasefire in January 2024. Providing this assistance to Gaza was an important way for Jordan and the UK to provide and show support for Palestinian civilians which indirectly impacted the stability of Jordan by highlighting Jordan’s support to the population of Gaza.
Overall Programme Score / The programme consists of one component based on a single activity that scored an A so the overall score for the programme is A.
Summary supporting narrative for the overall programme score in this review. / The A score reflects the programme’s achieved objective of supporting Jordan in delivering rapid aid into Gaza by providing £500k to the JHCO to procure, on behalf of the UK, high value aid material that went to hospitals in the South of Gaza following the ceasefire that was approved in January 2024. / The helicopter option expedited the delivery of supplies that were mainly critical medical supplies and vaccines, some of which had not been possible to deliver by other routes. The initiative was seen as part of a holistic effort to get aid into Gaza by whatever means possible
Major lessons and recommendations / This programme was designed as a humanitarian response based on ministerial approval in a challenging context ahead of drafting a full Business Case and signing an MoU. / Recommendations: / Proceed with designing a standalone flexible and risk aware humanitarian programme that can provide support to Gaza and eventually the West Bank, through both the Jordan and Egypt corridors. This programme should be grounded in humanitarian principles and responsive to the needs and change in context, specially related to access. / Continue to co-chair the Amman-based donor group for Gaza alongside the Netherlands and continue engaging with technical partners including the JHCO that acts as Jordan’s Coordination body, to get access to the latest updates regarding the humanitarian crisis in Gaza / Continue supporting the collective efforts from the Government of Jordan (GoJ) and humanitarian agencies to bring critical supplies into Gaza and ensure joint Governmental/donor messaging to Israel to loosen and simplify restrictions. To respond to acute humanitarian needs in Gaza, Convoys via the Jordan corridor remain vital noting that the pipeline of food/shelter/relief items in Jordan is strong, led by UNRWA, WFP and UNICEF - together with INGOs.
Actions following the approval of this PCR. / There are no outstanding actions for this programme before we formally close it as this single activity/ component has been fully implemented: 1.Aid has been delivered to Gaza on the 27th of January; 2. payment was approved as a special payment by HMT on the 22nd of April; 3. Payment was disbursed to the JHCO on the 14th of May and receipt was confirmed by the JHCO. The partner provided the packing list for the items that were funded by the UK and delivered via the airbridge into Gaza and recently shared the final report for this activity that was reviewed by the BEA programme team. Feedback is expected from JHCO shortly.

## PROGRAMME STRATEGY OR THEORY OF CHANGE

This programme was designed for a one-off activity that was approved by the Foreign Secretary with an objective set to respond to Jordan’s request to support the King of Jordan’s Airbridge initiative that was launched at the start of the ceasefire. The initiative was complementary to the scaling up of the Jordan Land Corridor, as part of the humanitarian surge of supplies into Gaza.

A Theory of Change was not developed for this programme as a one-off activity, however a logframe was developed with an Impact statement: “Vital services delivered to the most vulnerable in Gaza” and its indicator measuring the “Number of Jordanian field hospitals in Gaza supported with essential medical supplies funded by FCDO”. The Outcome statement: “Increasing volume of aid into Gaza via the corridor” was set with one indicator measuring the “Volume of medical supplies delivered to Jordanian field hospitals in Gaza via air corridor”. The logframe included one output that is related directly to the activity that was funded by the UK: “Provision of essential medical supplies to JHCO funded by FCDO” with one indicator measuring the “Value of medical supplies procured through FCDO funds”

## DETAILED OUTPUT

Delivery of Projects
Output	Provision of essential medical supplies to JHCO funded by FCDO
Number		1	Score	A
Weighting (%)		100	Weighting revised since last AR?	N/A

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

This programme was designed as a one-off activity/component programme with an output and an indicator related to the value of medical supplies procured through FCDO funds with a target set as £500k. The funding of £500k that was provided to Jordan to support the delivery of high value aid into Gaza was successfully delivered through this programme. The aid arrived at the targeted destination landing in South Gaza/ Kissufim, then received by WFP and delivered by WHO to hospitals based in the south of Gaza.
Despite the delay in the implementation from December to January and the uncertainty around the helicopter option after the ceasefire was announced mid-January, this output was delivered successfully at short notice on the 28th of January. This was after the Jordan Armed Forces (JAF) went ahead with the initiative and the UK managed to get a ministerial approval to move ahead with agreeing with the JHCO and secure the funds to provide the medicines on the UK’s behalf and we would pay for these in due course.

The UK-funded high-value medical supplies for the Airbridge initiative was procured through the Jordan Hashemite Charity Organisation, with whom we’ve had worked previously through the BCGJ’s programme, providing a total of £2m funding for the procurement of medicines and prosthetics. These supplies were sent to the JAF-Royal Medical Services field hospitals inside Gaza. This funding also covered the running cost of trucks delivering humanitarian aid via the land corridor.

As the BCGJ’s humanitarian programme Business Case could not be used for this activity because it had reached its maximum financial headroom after being extended several times, the UK participation in the initiative was based on a ministerial approval to a submission made by Jordan. The activity was mobilised ahead of drafting a BC and signing an MoU with the delivery partner.

## ANNEX: PROJECTS

Name of project	Description	Country of delivery	Delivered according to agreed budget, timescale and quality?
Supporting Jordan's Humanitarian Airbridge Initiative	Contributing to Jordan's initiative to deliver medical and humanitarian aid to Gaza that took place after the start of the ceasefire and was complementary to the scaling up of the Jordan Land Corridor, as part of the humanitarian surge of supplies into Gaza. The UK approved funding £500k emergency medical aid to Gaza to go on the Jordanian helicopters.	Programme based in Jordan and activity delivered by Jordan benefiting Gaza	Yes