Business Case

Summary Sheet

Portfolio/ Business/Country Plan Summary: will [insert a summary of the relevant Portfolio/Business/Country Plan from your department here]

Title: / Indo-Pacific Regional Governance Programme
Programme summary (100 words maximum): / The Indo-Pacific Governance Programme will support the foundations on which we can deliver the UK objectives in the Indo-Pacific by establishing partnerships for ‘progressive governance’ that enable broader UK priorities in the region. Support will be based on a combination of a) strategic programming b) deep context analysis and learning, and c) increased capacity to deliver advice and support to governance actors in the region. The programme will build on a base of successful projects in Sri Lanka, Philippines, Maldives, Myanmar and Thailand and will test a long-term approach for strategic engagement on governance in the region.
What is the rationale for UK Aid spending? (200 words maximum): / A free and open Indo-Pacific region is a key priority for the UK. We want a prosperous, safer, healthier Indo-Pacific, underpinned by the rules-based international system, which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and is more resilient to shocks and stresses. / How states are governed is fundamental to achieving these objectives. This requires that we can be agile and responsive to harness opportunities for cooperation and develop modern partnerships that support long term stability and sustainable development. The programme will enable the UK to take ‘strategic bets’ at the country level that is informed by a regional perspective to understanding how to support the Foreign Secretary’s vision of ‘progressive realism’ with a focus on enabling UK partnership and priorities, adapting to new challenges, and defending rights and rule-based systems.
Programme Value: £15m		Country/ Region or Sector: / Indo-Pacific
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		Ben Powis – Senior Governance Adviser, Indo Pacific Regional Department
Threshold for final approval of Business Case: / E.g. Minister, Foreign Secretary; HMT. See the PrOF Rules for the most recent information on approval thresholds.
Date of Approval of Concept Note:	17/12/2024	Name and role of Approver / Minister for the Indo-Pacific
Date of Approval of Business Case:	dd/mm/yyyy	Name and role of Approver
Programme Code:	AMP Start Date:	AMP End Date:
Overall programme risk rating:	Major

# Strategic Case

1. A Free and Open Indo-Pacific region is a key priority for the UK. We want a prosperous, safer, healthier Indo-Pacific, underpinned by the rules-based international system, which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and is more resilient to shocks and stresses. Developments in the Indo-Pacific have disproportionate influence on the global economy, supply chains, climate change, strategic stability and norms of state behaviour. The region’s growing geostrategic significance renders it a flashpoint for great power politics and consequent instability.
2. How states are governed in the Indo-Pacific is critical to achieving UK objectives and our partner with governments in the region. While we cannot assume shared values with many governments in the IP, there are a wide range of shared interests in stimulating growth, responding to new threats (such as climate change) and maintaining stability and sovereignty. The UK Foreign Secretary has set out a ‘progressive realism’ approach, one that see the world as it is, and seeks to forge partnerships based on respect and progressive thinking. Understanding the political context, and designing appropriate interventions, is essential to building these partnerships and supporting the UK’s priorities in the region.
3. The UK has been supporting a range of innovative interventions across the IP to promote rights, strengthen democratic process and institutions and respond to emerging threats. The Integrated Security Fund (ISF) has until now been the main channel for this work, which include a range of innovative and impactful programmes offering developmental and diplomatic benefits. There is strategic value in supporting the continuation of some of these programmes and transitioning to FCDO baseline, and to use this based to develop a longer-term approach to governance in the region. This will both consolidate impact and maintain our political engagement as well as providing a strong basis to develop a more coherent and coordinated regional approach that is aligned to the UK’s priorities in the region.
Governance and engagement in the Indo-Pacific
1. The Indo-Pacific has some of the most vibrant growth potential in the world, but also lies at the cutting edge of the climate challenge and security risks. Growth in the Indo-Pacific remains robust. Average growth in 2025 is forecast to be close to five percent. Strong growth has lowered debt concerns across the region; yet some countries remain highly vulnerable. The potential impact of new US tariffs on China imports is not yet known, along with the security risks of debt dependency. The region accounts for 51% of CO2 global emissions. China and India are together responsible for 39%, but the rest of the region still accounts for 12% of global emissions (with many IP countries on an increasing trajectory), which is only slightly less than Europe. The region is a global biodiversity hot-spot and the epicentre of enormous recent nature loss of nature. The IP is also a focal point for geopolitical competition, which could disrupt the delicate web of trade, economic and security relationships across the region and globally.
  [note] Total 51% of global emissions - China and India are together responsible for 39%, but the rest of the region still accounts for 12% of global emissions (with many IP countries on an increasing trajectory) which is only slightly less than Europe.
  [note] Eight countries accounted for 60% of the loss of mammal and bird biodiversity between 1996 and 2008; seven of them are in the IP region.
2. Most states in the Indo-Pacific are notionally democratic but many tend towards authoritarianism. Just as there are concerns about democratic recession globally, trends in the Indo-Pacific vary widely. The region includes examples of competitive politics, elites-led contests (or 'toxic alliances’) and electoral autocracies. Within this varied picture many of the global trends towards shrinking media freedoms and civic space, reduced independence of key institutions (i.e. judiciary and electoral commissions) and lack of space for opposition or dissent are increasingly common. Data shows that the IP is tracking these global trends, though there is a varied picture on democratic regression. According to globally accepted measures, 78% of the population are denied all or some democratic rights and freedoms. China and other countries provide alternative models of governance that are attractive to many politicians and populations, implying that the pathway towards democracy and human rights cannot be assumed.
  [note] Southeast Asia's Toxic Alliances Duncan McCargo, Rendy Wadipalapa Journal of Democracy, Volume 35, Number 3, July 2024, pp. 115-130
  [note] Designing Resistance: Democratic Institutions and the Threat of Backsliding | International IDEA
  [note] v-dem_dr2024_lowres.pdf
3. Autocratic governance is a threat to sustainable development and cooperation in the Indo-Pacific. The relationship between growth and democracy is contested. Autocracies can achieve economic growth, and growth does not ensure a pathway towards democracy. However, there is strong evidence that democracies provide stability and predictability in growth and other development outcomes relative to autocracies5. Autocracies have much higher variation in growth than democracies and are more likely to experience economic crises. Low-capacity autocracies tend to rely on unequal or exploitive partnerships; more open and transparent governments are able to forge partnerships that deliver on long-term interests.
4. Even where elections are held, there are concerns that the outlook for human rights and broader freedoms ‘remain bleak’ across much of the Indo-Pacific region. There is broad intolerance of dissent evident throughout much of the region as restrictions on the rights to freedom of expression, assembly and association tightened in multiple countries and territories. Critics of government policies and actions, including human rights defenders, political activists and journalists, were arbitrarily arrested and detained; protests against injustice were often met with unlawful, sometimes lethal, force. Perceived Western ‘hectoring’ on rights has limited traction and can undermine engagement in a region where most countries are keen not to be forced to ‘take sides’ in the context of increasingly polarised geopolitics.
  [note] Human rights in Asia and the Pacific Regional Overview Amnesty International
Testing a new approach to partnering on governance
Box 1: Thinking and Working Politically – A Governance ‘Mega Buy’ (Best Buys Governance Review 2019)

‘Given that political context is considered the factor most commonly determining success/failure across all (governance) interventions, thinking and working politically is best considered a ‘mega buy’.

Policy is never made in a political vacuum. Even apparently benign policy reforms create losers as well as winners. A failure to adopt political approaches to development, approaches which take into account power dynamics, is likely to jeopardize entire programmes.

The core constituent components of projects that claim to ‘think and work politically’ are (i) strong political analysis, insight and understanding; (ii) a detailed appreciation of, and response to, the local context; and (iii) flexibility and adaptability in programme design and delivery, notably with respect to the selection of stakeholders and programme implementers.

1. Cooperation and partnership will require understanding the context and being agile to opportunities. A values-based approach – centred on democracy and rights – can feed polarisation in a fast-changing geo-political context. This does not preclude the immense scope for ‘modern partnerships’ on issues that the UK has prioritised, namely growth, climate and security. Working politically to understand the context and being agile to opportunities for engagement is recognised as a ‘mega buy’ (Box 1) and is especially relevant in a region where the UK has a strong interest in establishing political access and influence.
2. This programme will test new approaches to partnership and engagement on governance in the Indo-Pacific to support the UK’s objectives. There are multiple opportunities to forge partnerships, based around common interests, that lead to more strategic goals. Emerging challenges of climate change, economic vulnerability and social pressure offer avenues to engage with states that do not openly share UK values but nonetheless share our interests in economic development, managing resources, climate threats and ensuring security in the region. Managing domestic pressures or tensions that undermine stability can also offer points where support may be welcome and that may open discussions linked to the value of the rules-based international system or the protection of rights. Taking this approach, the programme aims to test an approach to governance partnerships with three entry points:

- Enabling progressive governance – supporting political processes and institutions that support open economies and domestic stability, including tackling corruption and kleptocracy, as well as effective policy making and implementation, and constructive engagement between states, society and competing elites. This will be led by political economy analysis to identify issues and opportunities around which partnerships can be developed.
- Adapting to new challenges – harnessing shared interests and opportunities to collaborate to tackle emerging risks, including climate change, illicit finance / kleptocracy, mis/dis information, and social polarisation as shared concerns and areas for cooperation on innovations in politics and institutions to meet these challenges.
- Defending rights and the rule of law – working to secure rights and freedoms and support for the rule of law and the international mechanisms that support domestic interests. This includes forging partnerships between human rights defenders and democratic actors in the region to drive positive change. This pillar will include a strong emphasis on countering the roll back on gender rights.

Strategic fit to UK priorities

1. The UK’s engagements in the Indo-Pacific region are guided by four key principles: to promote peace and security; to support growth and create economic opportunities for all; to seize opportunities for clean energy transition; and to achieve the Sustainable Development Goals, while building more resilient economies. How states are governed is central to UK priorities in the IP as growth, climate and nature and security fundamentally depend on the capacity of states to plan, implement and manage contestation. Therefore, it is the UK’s interests – as well as the populations of Indo-Pacific countries – to improve the effectiveness and accountability of governance where it is possible to do so.
2. Democratic resilience has been a core component of the FCDO Indo-Pacific Strategy. This reflects the evidence that democracy is under threat globally, as well as the centrality of open and inclusive governance to delivering across the UK’s objectives. This strategy is currently under review to align with the Foreign Secretary’s vision for foreign policy based on ‘progressive realism’, that sees the world as it is and not as we would like it to be. In this context, this implies a greater understanding of the types of political contest in the region, the norms that underpin these, and the challenges these imply. In line with the FS’s priority on forging ‘modern partnerships’, the UK will adapt our approach to focus on areas of mutual interest and strategic opportunities through principled partnerships. The approach proposed in the IP will be closely aligned to emerging strategy for the region, including the revised China strategy and the Foreign Secretary priorities on the rule of law and illicit finance.
3. As this approach is being developed, it is important to maintain successful programming both to consolidate results and to maintain political engagements in the region. Under the Integrated Security Fund (ISF) the UK has been supporting innovative programming in the Indo-Pacific focused on Sri Lanka, Myanmar, the Philippines, the Maldives and ASEAN countries that include peace building and counter extremism, rule of law, parliamentary support, documentation of human rights violations and election support. There is an opportunity to transition these programmes to FCDO baseline to consolidate impacts while developing a future portfolio of projects, including the expansion to new countries, building in the lessons learned. This short-term extension of the existing portfolio will also enable development of this longer-term strategy and approach, with emphasis on enhanced agility, testing and learning and complementarity to central and bilateral investments.
4. The success of this programme is not contingent on extension and there are options to scale. There is a strong case for the continuation of the selected ISF programmes as a stand along project, as well as the value for more in-depth testing, analysis and learning within the current phase of this two-year programme. There is a also significant scope to scale (up or down) within the approved budget ceiling, enabling this programme to adapt to demand and budget availability while ensuring results and value for money. The risks of not continuing after the current proposed end date are reflected in the programme risk register, with sufficient mitigation to ensure these can be managed within risk appetite.

Expected outcome and impact
1. The goal of the programme is to support the delivery of UK objectives in the Indo-Pacific by developing modern partnerships that promote open, accountable and inclusive governance and stability.
2. This will be achieved through a regional governance programme that is designed to consolidate successful governance programmes and to test a longer-term approach for governance support in the Indo-Pacific. The specific objectives of this initial phase are to:
  1. Consolidate critical and successful projects to ensure responsible closure and the sustainability of the achievements attained;
  2. Maintain and expand the UK’s political engagement and partnerships on governance in the region;
  3. Develop and test a longer-term strategic approach to support broader UK objectives in the region and enhance country level programming and strategies;
  4. Develop more agile and effective technical and programmatic support to governance in the region; and
  5. Enhance contextually-driven learning to scale-up programme results with partner governments.
## Assurances
1. Legislation: The intended programme will be fully compliant with the International Development Act. It will contribute to poverty reduction in the countries and communities affected by disasters and other shocks. It is judged that terrorist financing is not a significant risk. FCDO expertise will be drawn on to ensure best practice is adhered to, including thorough rigorous due diligence of all partners that receive programme funding.
2. Gender Equality:  This is an important programmatic vehicle for gender and social inclusion for the Indo-Pacific region, providing an opportunity for a “beyond values” approach and enable posts to adapt to both political will and entry points (notably on the importance of tackling low labour-force participation to drive growth) as well as risks (including in response to rollback of Sexual Reproductive Health and Rights (SRHR). ISF has been one of the main delivering the commitments set out in the UK Women, Peace and Security (WPS) National Action Plan. Therefore, this programme will enable posts to retain and build on key legacy WPS projects, as well as support the design of new “inclusive and gender responsive” governance portfolio. We will seek to make proportionate contributions to Strategic Objective 1 by increasing women’s participation in peace and stabilisation processes in the region, as well as Strategic Objective 4 by taking into account any gender-related differences in needs and contribute to reducing inequality between genders within key security and justice institutions in the region.
3. A new approach to gender and social inclusion (GESI): the adaptive nature of the programme will be designed to respond to both emerging opportunities (where there is political appetite for UK modern partnerships in areas such as women’s economic empowerment or utilising UK expertise in countering domestic violence) as well as risks (e.g. closing civic space and areas of rollback for women’s and LGBT+ rights, which require very different, highly discrete approaches). It will also enable posts to complement their growth and climate portfolios, using the programme to provide technical assistance, research and insights to ensure these portfolios deliver “inclusion” outcomes and socially just transitions. Where posts require support to deliver discrete workstreams countering rollback, the project design will be informed by FCDO’s central analysis on countries most at risk of negative impacts from anticipated anti-abortion politics and policies under new US Administration. For example, Nepal has been identified as at greatest risk in the region (receiving large amounts of USAID and in the frame for intensified rollback on its abortion laws and women’s rights).
4. The programme will take a “twin track” approach to gender with (i) targeted interventions, (ii) mainstreaming throughout. GESI analysis will be built into political economy analysis, key qualitative and quantitative targets will be captured in results frameworks and theories of change, and through SDA involvement – partners will be required to meet FCDO minimum standards. Such an approach builds on recent recommendations from the IP Portfolio Board to “grow our GESI pipeline” after a 2024 Portfolio Review exposed gaps in our approach.
5. Partnership principles: This programme will not provide direct financial support to governments in the region. The Partnership Principles will guide our engagement. We will escalate risks to ministers if any government’s policies substantially hamper or restrict the UK’s ability to deliver assistance.
  [note] The Partnership Principles commit a partner government to (i) reducing poverty and achieving the MDGs; (ii) respecting human rights and other international obligations; (iii) strengthening financial management and accountability and reducing the risk of funds being misused through weak administration or corruption; and (iv) a commitment to strengthening domestic accountability.
6. Safeguarding: In line with FCDO’s safeguarding policy we will actively seek to prevent sexual exploitation and abuse and sexual harassment from occurring; respond sensitively but robustly when harm or allegations of harm occur; and learn from every case. Any partner selected for funding will be subject to due diligence, including a robust assessment of safeguarding measures, and regular reminders of FCDO expectations. Regular monitoring, through third-party, field visits and/or ongoing partner engagement will ensure active risk management. First tier partners will be reminded of their responsibility to ensure appropriate safeguarding standards have been cascaded down the delivery chain and to provide evidence that standards have been shared and all partners are clear about those expectations. We will consult the Senior Social Development Adviser to review any high-risk areas (potential work with human rights defenders and civil society in restrictive contexts) and provide regular updates to the Programme Steering Committee (PSC).
7. Risk: IPRD has a comprehensive risk management system and risk register in place. Activities will be tested and adapted over time, ensuring they are kept within IPRD’s risk appetite. Further details on risk management are provided in the Management Case.
8. Conflict Sensitivity: Proposed projects will be required to demonstrate that conflict sensitivity has been properly considered and a full assessment conducted where necessary. Armed conflict is relatively limited in the region, with the exception of Myanmar. However, insurgencies are present such as in southern Thailand, West Papua, and certain areas in the southern Philippines. Extensive research has demonstrated that a decline in democracy, violent crackdowns, and repression increase the likelihood of conflict outbreak. These conflict risks are increasingly present in the region. Additionally, weak states hinder governments' abilities to effectively respond to crises. The programme aims to address these challenges and enhance HMG's understanding of conflict sensitivity in a region characterised more by deep geopolitical tensions and latent conflict, rather than escalated violent conflict.
9. Equalities Impact: The programme will consider the impact of programming on groups with the nine protected characteristics (sex, age, disability status, sexual orientation, race, religion or belief, pregnancy/maternity, marriage and civil partnership, and gender reassignment) on project-by-project basis. The programme will ensure that it fully complies with the duty to protect them. The programme will seek areas of opportunity for inclusion and advancement of groups with protected characteristics, notably on issues of gender, LGBT+, religious minorities and indigenous people.
10. Human Rights: This programme will have a positive impact on human rights. The programme aims to address democratic backsliding and authoritarian tendencies in the region, including supporting projects that aim to uphold human rights. As we did in 2024, the programme will continue supporting projects that catalyse criminal justice reform in the region, including one that seeks to abolish the death penalty in Malaysia, developing guidelines for the use of body cameras in the Royal Thai Police, both of which contribute to advancing and promoting human rights.  The need for an OSJA will be judged on a project-by-project basis and will be completed where necessary.
11. Climate and Environment: We judge that this programme is Paris Aligned. There are no environmental risks associated with this programme and it is not climate sensitive. The programme will not undertake shadow carbon pricing as part of its appraisal and will not invest in fossil fuels or go against country Nationally Determined Contributions. While the programme seeks to better mitigate the security risks of climate change, it has no direct environmental risks or benefits. We do not anticipate any of this programme being eligible to be marked as ICF. We do expect the programme to be making important contributions to understanding governance dimension of climate and support actors engaging with countering negative climate and environment impacts. We do however aim to explore opportunities to work (together with other programmes) on governance approaches linked to climate adaptation priorities.
12. Cyber: This programme may rely on and engage with digital technology where appropriate but will do so cautiously. Digital technology is often fundamental to authoritarian forms of data collection and social control. Any project proposals involving cyber will be required to show that selected implementing partners have sufficient technical expertise to avoid these risks and will specifically focus on protecting individual liberties and civic freedoms in the digital arena wherever possible. Where necessary, the programme will also ensure that staff and implementers receive the necessary cyber training, to ensure that we do not inadvertently put staff working on these interventions at risk from hostile actors. We will also seek to exchange lessons learned and discuss best practice on these issues with the ISF Cyber Programme in Indo-Pacific.

# Appraisal Case

1. The approved Concept Note sets out the need to maintain UK’s support for governance and security in the Indo-Pacific and test approaches to inform a multi-year governance programme, to be managed by the Indo-Pacific Regional Department, with a working title of the Indo-Pacific Regional Governance Programme (IPRGP). During this short term ‘delivery and design’ phase it will be important to balance consolidation and innovation. The programme will absorb several security, justice and democratic governance projects currently funded by the Integrated Security Fund (ISF), which would otherwise end in March 2025. Projects will be selected to provide the greatest impact and political access and influence. The programme will also have scope to be agile and responsive to seed the design for the envisaged long-term programme. The programme will support the FS’s objective of a Free and Open Indo-Pacific and the democratic resilience objective of the Indo-Pacific Delivery Plan.
2. This appraisal case has two parts: the first assess the scope and design (implementation) options and the second set out the considerations for delivery. Given the nature of the programme as a ‘delivery and design’ approach, final decisions on the prioritisation of components and the delivery will be subject to budgets and the decision-making process, as set out in the Management Case. This appraisal case sets out to establish the considerations that will guide these decisions.
3. The ‘do nothing’ option is ruled out given the Ministerial priority to maintain the core components of the ISF portfolio under the FCDO baseline, a decision which underpins the approval of the Concept Note. This option would entail closing all programmes from April 2025, and along with this all programme-funded staff positions that have been instrumental in driving forward the programme objectives. Closure in this way would harm progress towards UK objectives in the region, damage diplomatic relations and UK reputation, leave us with substantially reduced development capabilities and put us in a worse position upon which to build the multi-year regional governance programme. We have explored options to pick up funding through other funding sources (centrally managed programme or bilateral budget) and found these are insufficient to provide the regionally focused support and funding in place under the ISF. Therefore, the Minister for the Indo-Pacific and the directors for SEAPD and IIOD have decided that we need to maintain prioritised activities from the ISF.
Component One: Maintenance of a ‘core portfolio’ of programmes from the ISF (up to £7 million)
1. This component will enable the continuation of high priority projects to ensure a responsible exit or transition, where aligned with longer-term IPRGP objectives. An initial list of ‘core programmes’ has been identified for support under the IPRGP (see Annex 1). This list will be subject to final approval by the Programme Steering Committee (see Management Case) to identify programmes that: a) are high performing and/or in need of consolidation to achieve potential impact; b) provide access and influence/carry reputational risks from early closure; c) offer lessons of learning relevant to future IP governance strategy; d) provide good evidence of value for money; e) provide evidence that no other sources of funding can support projects; and f) satisfy procurement regulations, and secure FCDO Procurement Steering Board approval, where maintaining projects involves the extension of contracts. This initial process of selection has resulted in a list of proposed priority projects in Sri Lanka, Myanmar, Philippines, ASEAN countries and the Maldives. Final selection of these projects will be made by the Programme Steering Committee, as set out in the Management Case.
2. The priority portfolios under consideration for extension under this programme include:
- Security and justice reform in the Maldives
- Democratic governance, institutions and civil society in Sri Lanka
- Support to the Bangsamoro Autonomous Region in Muslim Mindanao (BARMM) governance in support of the peace process in the Philippines
- Justice and Rule of Law in South-East Asia (Thailand/ASEAN)
- Support to women’s political empowerment and human rights in Myanmar
1. Extending existing programming, based on the criteria set out above, ensures that these programmes are effective, provide value for money and are viable (with existing delivery partners), assuming we are able to ensure an early decision. The value for money case for these programmes is documented in the annual reviews carried out under ISF (see Annex 1). Furthermore, we will be seeking to strengthen the delivery model through a reduced number of programme-funded staff and a number of project agreements under a single business case, which will further enhance the value for money case.
2. The selection of the core portfolio will be subject to analysis that will form the basis for funding decisions by the Programme Steering Committee. The remaining options set out below respond to the objective of enabling a transition to a long-term regional governance approach and will be subject to budget availability.
3. There is a need to ensure appropriate support to core and new activities under this programme. In consideration of the options, a core programme team model has been proposed, covering seven locally based staff that will be required to ensure partner and policy engagement necessary to deliver the core portfolio.
4. Expected outcomes and result from the core portfolio are included in Annex 1.
Component Two: Flexible Fund (up to £6.7 million)
1. This component will enable the design and implementation of new governance projects in the Indo-Pacific and support the transition to a longer-term governance programme. This will enable testing of the decision-making structure of the Programme Steering Committee and the Theory of Change and strategic objectives that will be the basis of the longer-term regional governance programme. The development of this Theory of Change will be undertaken following the commencement of the programme to enable engagement across the network under the umbrella of the Programme Steering Committee. Clear strategic focus will be important, given the wide range of demands and scope of governance programming in the Indo-Pacific and will ensure a focus on impact and influence. It is expected that new programming would include regional or multi-country activities and potential partnerships with regional networks and organisations.
2. Inclusion of a flexible fund in the IP Governance Programme will be important, both in terms of responding to emerging needs and opportunities (remaining agile and adaptive) as well as testing the decision-making process and strategy that guides this. We will be able to ‘live test’ the additionality of regionally managed funding, alongside central and bilateral programming, and design and test regional or multi-country approaches. We would expect new programming to commence three months after the start of the programme, following a period of detailed analysis and consultation across the network. Projects that are initiated under the flexible fund will initially be designed for 12 months, with the potential to extend when the long-term programme is approved. There would be scope to continue ‘core programmes’, if considered appropriate, or to include core countries in the selection. However, priority will be given to expanding the geographic focus to enlarge the cohort of countries included in the regional programme.
  Box 2: The Nigeria Partnership to Engage, Reform and Learn (PERL) was the largest governance programme of its kind (up to £100 million over five years). The Quality Assurance Unit praised the Business Case for combining a clear articulation of its intended objectives with a commitment to adaptive programming. The purpose of the programme was ‘supporting the development of stronger public sector accountability’, and the Business Case set out an approach based on (1) a selective focus on issues with political traction, (2) a clear understanding of the local political economy, (3) a willingness to experiment with a variety of intervention approaches, (4) well developed MEL systems to assess the results, and (5) strong management systems to adapt the programme design according to lessons learned and the changing political context
3. Flexible and adaptive programmes have been demonstrated to be effective, especially when working in complex environments. In these case ‘FCDO-funded programmes increasingly need to be catalytic and innovative, rather than delivering known results at scale’, and it is recommended to build this approach into the programme from the concept and business case stage. Lessons from successful programmes from across the world (Box 2) have shown how the ability to be flexible to respond to opportunities and adapt to changes in the context offer greater impact and value for money.
  [note] FCDO Prof Guide: How to design and manage adaptive programmes
4. As part of the flexible fund, we will consider both country level projects as well as regional partnerships with multi-laterals, NGOs, think tanks or networks. This will enable a testing of new approaches to working in the IP including sub-regional ways of working, for instance in the Mekong or Pacific Region.
5. The design of the flexible fund will be agreed three months following programme inception, along with the theory of change. At the outset it is anticipated that the fund will support the following types of activities and governance sectors.
Menu of funding options and type of support (initial proposed)
Initial Governance Priorities	Types of support
Inclusive political processes (parliament, local governance, policy deliberation) / Civic/Constructive Engagement (Civil society strengthening, policy dialogue, deliberative forums, advocacy) / Policy and institutional strengthening (capacity building, technical advice, mentoring) / Social inclusion and integration / Human rights (protection, monitoring and advocacy) / Media and freedom of expression / Anti-corruption and accountability	Eligible: / Technical assistance and capacity building: Experts and UK partnerships, consultant fees / Grant funding (including fees): civil society organisations (including core funding), NGOs. / Study visits and exchanges / Enabling investments (i.e software or limited hardware) / Ineligible / Payment of government salaries or other core costs / On-budget support / Infrastructure (subject to waiver if tied to programme objectives)

Component Three: Strategy testing and learning (up to £300,000)
1. In seeking to move towards a longer-term regional governance programme, we seek to strengthen our capacity for rigorous context analysis and strategy testing to enhance decision making and learning under the regional programme. The design draws on the successful experience of Nepal, where ‘critical friends’ have enabled rigorous context analysis and testing of assumptions (Box 3).
2. Context analysis will enable clearer policy choices on the allocation of UK investments based on capacity to influence change. Strategy testing will interrogate project assumptions and their contributions towards ‘significant changes’. Learning will ensure that lessons are generated in a way that draws parallels with other contexts in the region. As such, the strategy testing and learning (STL) component aims to add significant value to programme investments and strengthen the programme level theory of change.
  (Box 3) ‘Critical Friends’ – Strategy Testing in Nepal
  The British Embassy Kathmandu established collaboration with SOAS and Yale to help BEK collectively learn about the key ‘big changes’ it is seeking to support in Nepal, including federalism and growth. The team members act as ‘critical friends’, bringing in deeper contextual analysis to understand what is working and why, and to test assumptions across the portfolio.
  The collaboration differs from standard Monitoring, Evaluation and Learning. It works in close partnership with the SRO to draw out a granular understanding of power and incentives to identify feasible, practical changes. The programme has been instrumental in helping the Embassy think through the underlying influence of clientelism and how informal deals drive short-term, extractive behaviour by Nepal's politicians and parties. It has helped the Embassy identify plausible interventions that are more likely to have greater impact.
3. In the first year, under this programme, the STL component will: a) enhance the analysis of the structural constraints to governance in the region to create an analytical approach to the region; and b) test the strategic approach under the core programmes. This component will be aligned with plans to enhance capacity for in-house Monitoring, Evaluation and Learning (MEL) through the Indo-Pacific Regional Development department, which will support monitoring at the project level. We will also explore the scope to draw in resources from the central offer on evidence and learning, including the Centre of Expertise (CoE) on democratic governance.
4. This component will support a small independent team of geographic and governance experts who will act as a ‘critical friends’ for the programmes, able to critically analyse programme design and delivery against a broader understanding of the regional and country level governance dynamics. To enable a quick start up, we will consider the use of CoE-based drawdown, engaging internal Research Analysts and individual consultant contracts, with the options for a competitive call for academic or consultancy partnerships for more sustained support.
5. In additional to testing country level impacts, the STL component enhance regional analysis to inform decision about where resources should be focused with the region. A broad set of criteria will be defined including a) prioritisation of non/low ODA spending countries b) capacity to manage and leverage diplomatic impacts of investments c) UK comparative advantage and partnership with host governments d) potential for high impact of investments. This will likely result in a refocusing of the ‘core portfolio’ or the addition of new countries in coordination with other UK fund and strategies.
Component Four: Programme-funded programme and advisory resource (up to £1 million)
1. This component aims to enhance the ‘technical offer’ from FCDO in the region both to deliver direct technical support to governments and non-governmental partners as well as add value to projects through more intensive stakeholder engagement and value for money. This would follow the PROF guidance on ‘Project Funded Staff and In-House Delivery’ where these are roles that are essential for programme delivery, whose work would (and could) be sourced externally if not delivered in house. Final decision on the deployment of these roles, and the location, would be subject to decision from the Programme Steering Committee, but the initial rationale is set out in Annex 2.
  [note] Updated February 2024
2. These two posts aim to expand the existing regional advisory resource, which is currently limited to one Senior Governance Adviser, to work in partnership with central ‘Centre of Expertise’ advisory resources. This model would be a means to test the models of regional direct delivery as an alternative to contracted project delivery.
3. The core tasks of programme funded (G7) Governance Advisers would be to a) build relationships with key counterparts (government, non-government) to identify opportunities and design interventions b) deliver direct policy advice and technical support to counterparts c) support context analysis and contribution analysis and d) build capacity and coherence between stakeholders, including developing coalitions of interest around programme activities. It is anticipated that programme funded advisers will operate at a sub-regional level this providing dedicated support to two or more countries in the Indo-Pacific and would be subject to the ‘dual key’ agreements set out in the management case to ensure they are embedded in the country level operations while reporting to the regional team.
Implementation scenarios – adaptive delivery model
1. The four project components or options set out below can be deployed in combination and scale in response to budget allocation and based on the decision of the Programme Steering Committee, as set out in the Management Case. For the purpose of this Appraisal Case, these scenarios are set out at three levels.
2. Option One: Core programme only (up to £7m, 12 months) Under this scenario, the focus will be on maintaining the core portfolio that has been proposed (pending final decision), focused on legacy programmes in Sri Lanka, the Maldives, ASEAN countries, the Philippines and Myanmar. This model includes limited programme-funded staffing. The budget would enable a one-year extension and responsible exit from programmes only, responding only to short-term concerns.
3. This option focuses on existing projects and partnerships and therefore is based on a strong evidence base of effectiveness, value for money, feasibility (with existing delivery partners) and partnerships or political engagement. We will aim to enhance the delivery model and coherence of this portfolio under the single regional business case. A programme that is limited to Option One does not, however, meet the objective of evolving the strategic approach and testing approaches to inform a longer-term programme, nor will it allow for responsiveness and agility, including the testing of a strategic management approach.
4. Option Two: Responsive funding only (up to £15 million for 24 months) Under this modality, the core portfolio will be implemented initially, with a new flexible regional funding becoming available to support a new portfolio of programmes. This will enable the testing of a longer-term approach to regional governance programming, through the Programme Steering Committee, to assess new project proposals based on the theory of change, ability to respond to new opportunities and the expansion of the reach of the programme beyond the core legacy ISF footprint in the region.
5. This option will realise the value for money and partnership benefits of Option One as well as developing the portfolio towards a more strategic approach, including the expansion or shift into new countries and testing of new thematic areas. IPRD will act as the fund manager, reliant largely on existing capacity at post for analysis and implementation support beyond core programme management. As such, there is limited scope to test new ways of working and drive value-added analysis, learning and direct technical support. This will partially meet the objectives of the approved Concept Note but is unlikely to signal the shift and direction towards a new way of working for future years. The lack of investment in accompanying strategy testing and learning and direct delivery through an expanded advisory capacity will limit the capacity to test new approaches to delivery and the value addition of strategic input.
6. Option Three: Regional Governance Approach (up to £15 million, up to 24 months) Under this scenario, the programme will support the core programme and enable the transition of legacy ISF programmes and the development of a more coherent governance approach, with associated analytical and technical support. This will be achieved through the combination of all four components set out above. Under this option, IPRD will be capable of both meeting the aims of the approved Concept Note, namely, to maintain priority legacy ISF projects and developing and testing a new approach to inform future regional governance programming in the Indo-Pacific.
7. The combination of funding and ‘valued added’ analysis and technical support will be capable of enhancing impact with the current programme and establishing a new approach that can be extended in future years. This includes the establishment of more ambitious new projects (with the option to expand or adapt for multi-year funding), setting up technical and strategy testing and learning resources in a way that will provide scaled-up testing and lesson learning to inform the future programme. Key to this will be the ability to expand the programme beyond the core focus countries (Sri Lanka, the Maldives, ASEAN, the Philippines and Myanmar) and include a wider set of strategic programmes that will enable cross-IP strategy and learning. Within this option there would be scope to flex the implementation options and scale, depending on resources, and enable the Programme Steering Committee to lead these strategic choices to inform the future programme design.
8. The option will offer enhanced value for money in terms of learning, as well as impact of new components. For instance, the investment in STL and direct delivery (advisory resource) will have an IP-wide impact and ensure that we are able to fully test and learn from these investments, alongside HQ and other regional resources.

Summary appraisal of options against objectives
Objectives	Option 1 / Core programme	Option 2 / Core plus flexible fund	Option 3 / Core and flexible fund supported by STL and advisory resource
Maintaining engagement and sustainable closure of ISF governance portfolio	Strong	Strong	Strong
Develop and test longer term approach to governance in IP	Partial	Partial	Strong
Design and test alternative delivery options (direct and programme)	Not in scope	Partial	Strong
Deepen context analysis to inform strategic choices	Not in scope	Not in scope	Strong
	£7 million 12 months	£15 million 24 months	£15 million 24 months

Given the potential to meet the full objectives of the approved Business Case – to continue the core programme and test the modality for a future programme – Option 3 is recommended. Within this option there is scope to refine the allocations across the four components, as well as scale up or down depending on budget allocation. These decisions will be guided through the programme governance arrangements set out in the Management Case.
Delivery Options
1. The key delivery appraisal options for this programme relate the selection and management of the project delivery. While there is scope to consider various modalities (namely in-house management, contracted or grant managed, or multi-lateral management) the agreement set out in the approved concept note determines that the core programme will be managed through ‘in-house’ or FCDO managed portfolio of projects. The option to move towards alternative modalities under the flexible fund can be considered, along with a blending of contracted/multi-lateral management and in-house management.
2. The key consideration for this approach are:
  1. Value for money of contracting or partnership-based management (vs. in-house)
  2. Alignment between delivery modality and broader UK/FCDO objectives of supporting diplomatic and development partnerships
  3. Availability of existence of appropriate programmes or partnership in the region (or sub-region) that fit with the objectives of the programme.
3. As an adaptive programme with an emphasis on testing and learning from the approach to inform future programming, the strategy at the business case stage is to defer the decision on the allocation of the flexible fund to the internal programme processes (Programme Steering Committee) following the initial phase of analysis and strategy development. This key decision point is reflected in the management case, with assurance that proposals and options will be tested based on value for money, risk and impact criteria.
#### Theory of Change

1. Achieving the UK objective of promoting economic growth, combatting climate change and enhancing security in the Indo-Pacific will require a new approach to programming and partnerships. Much as we know that how states are governed is critical to these objectives, we need to take a realist approach while pursing progressive ends. This means moving beyond shared values and focusing on shared interests through principled engagement. As a pilot for this new approach, we will be testing a model based around: a) promoting rights and the rules-based international system; b) supporting enabling political processes to manage contestation and ensure responsiveness; and c) partnering on the adaptation of politics and governance to new challenges such as climate change, disinformation, polarisation and kleptocracy. The aim of this new framing is to ensure a more open dialogue on governance challenges, and building partnerships, with a wider range of regime types (beyond likeminded states).
2. The Indo-Pacific Regional Governance Programme will support strategic investments across a range of IP countries that align with the broad framework of engagement – with a strong focus on contextual analysis and learning to ensure that investments yield broader impact and insights beyond specific projects. By enhancing coherence and contextual analysis, we will aim to better understand the core constraints (and hence significant changes), as well as the opportunities, and focus on embedding change processes that leverage country level commitments (and therefore funding) and alignment with other partners (donors, NGOs) to ensure the sustained impact of investments on long-term change.

Initial Theory of Change

1. With this approach in mind, a robust Theory of Change will be critical – as will be the need to iterate and develop this programme theory, based on experience and learning. With the core portfolio of legacy ISF programmes, it will be possible to ‘hit the ground running’ in terms of implementation, and the focus will be on embedded STL processes that enable a robust strategic approach to be anchored in the Programme Steering Committee to guide investment decisions beyond the core portfolio. This will require a constant assessment of the scope of the programme, given the potentially wide set of focus areas and sectors, that will be assessed alongside the evolving shape of the broader regional and central programmes to ensure that the IPRGP maintains a clear focus and additionality. The ToC will also be developed in close alignment with broader central and regional strategies and the design of new funds and will therefore only be possible to finalise after the commencement of the programme.
2. The initial Theory of Change is articulated as follows: Building on a core set of strategic projects (legacy ISF) and adding flexible funding for new programming and additional analytical and advisory resources (inputs) the IPRGP will be able to test options across the three domains of engagement, namely enabling progressive politics, adapting to new challenges and/while defending right and rule of law (approach) with the overall result of building coalitions of support for open and inclusive governance, enhancing the understanding of challenge and opportunities and fostering ‘problem solving partnerships’ that advance UK diplomatic engagement (outcomes) in support of the objective of supporting a more open and inclusive Indo-Pacific (impact).
3. The assumptions underpinning the theory of change include:
  1. There is consent from the governments of the countries in which the programme operates;
  2. Implementing partners are able to retain sufficient capacity to deliver the programme;
  3. The FCDO is able to retain sufficient capacities to manage the programme from the UK and relevant posts; and
  4. Improved capacities in government institutions and civil society organisations for accountability improves accountability.
The detailed theory of change will be developed following business case approval – and will be assessed be the Programme Steering Group, to be reviewed at least every six months.
## Evidence
1. This programme builds upon a strong evidence base for existing activities, as set out the summary annual review findings set out in Annex 1. There is a broader set of evidence on the contribution of ‘good governance’ practices in relation to stability and long-term growth, and an emerging research agenda in the relationship to climate change. Through the STL component we will be looking to build this evidence base, as well as critically examining programme management and direct delivery from value for money and impact perspectives.
2. The effectiveness of governance interventions is hard to assess in isolation from the specific political context in which they are implemented. The review of ‘governance best buys’ conducted in 2019 lists a range of ‘demand’ and ‘supply side’ interventions that are evidence as being cost effective and impactful. The key finding is that ‘working politically’ or designing intervention in a way that reflect the political economy is a ‘mega buy’. A range of interventions currently lack sufficient evidence across context – but this does not preclude high potential in specific context. The key implication remains that what matter more than the type of intervention than the way in which these interventions are designed and implemented.
  Governance Best Buys (2019):
  selected areas of intervention relevant to IPRGP

  Mega Buy:	Thinking and Working Politically
  Great Buys:	Increasing women’s participation in the election cycle
  Voter education and information dissemination
  Election Monitoring
  Conducting audits linked to social accountability
  High potential:	Participatory Budgeting
  Improved targeting of welfare (social protection)
  Mixed evidence: Decentralisation
  Right to information
  Political parties and parliament

3. Building on this insight, there is growing evidence of the importance of adopting adaptive approaches to governance programming that enable programmes to be managed in ways that respond to learning from implementation of ‘iterations’ or testing strategies and learning through the programme in order to better understand and tackle the root causes of ‘problems’. Alternative approaches focus on specific issues that have traction in a specific context and employ various methods (technical advice, building coalitions, political engagement) to tackle the governance challenges that underpin poor outcomes. These approaches share the fundamental insight that strategic and well-designed interventions can make a positive contribution to change when they are able to nudge domestic politics in positive directions through contributions to change, rather than specific measurable attribution. These examples also demonstrate the important of applying qualitative and context driven ‘strategy testing’ approaches to track results and inform learning.
  [note] PDIA Toolkit – Building State Capability
  [note] Traction_-_Malawi_2_-_for_website_uMViiC8.pdf
  [note] How Change Happens - The Commons
  [note] The-Strategy-Testing-Workbook-Politically-Smart-Adaptive-Programming-in-Complex-Environments-1.pdf
4. The IPRGP aims to seed a range of strategic interventions that both improve governance and support diplomatic and broader UK objectives. The identification of these intended outcomes will be developed further through the Theory of Change, but is likely to include the following type of outcomes that themselves will shape the selection of activities, the performance of which will be captured through the STL component:

Progressive Governance
  1. Shifting political and social norms in favour of more open, rule-based and democratic forms of government.
  2. Contributing to significant positive changes in the constraints to open and effective governance and peaceful resolution of political contests.
Strategic engagement
  1. Contributing to the UK’s objectives in the IP, namely enabling growth, response to climate change and improved stability and security.
  2. Enabling political access and influence through ‘modern partnerships’ that support the UK’s development and diplomatic objectives in the region.
Understanding of context
  1. Demonstrating lessons that are applicable across countries in the region and therefore locally led leadership towards progressive governance.
  2. Deepening the understanding of the drivers, incentives and norm that shape political governance processes in the region, and hence opportunities and challenges.
2. Indicative outputs expected through the ‘core’ programme are set out in Annex 1.

# Commercial Case
1. The approval of the Concept Note was premised on the importance of extending successful ISF programming as we bring these onto the FCDO baseline, to be managed by IPRD. This will include a range of contracts and Memoranda of Understanding (MOUs). As such, prior approval needs to be in place, based on approval of this Business Case, to extend contracts where procurement regulations can be satisfied, based on the recommendation of the Programme Steering Committee and approval by Procurement Steering Board.
2. Should the additional resources for flexible funds and STL component be approved, we will apply standard FCDO procurement procedures for contracts, accountable grants and MOUs. For projects under the local DPO threshold, we will use competitive tenders or, in the case of accountable grants, calls for proposals. Contracts over this value will be tendered through existing small lot framework agreements, either the ISF or GDD Frameworks, depending on the requirements of each contract, and intelligence gained from market engagement. For the STL component we have the option to use the GEMFA framework’s <£600k Lots, if required. Contracts for all projects will include clauses to mitigate the risk of incumbent advantage (real or perceived) for future successor contracts.

Box 4: Implementation and commercial plan
Set up phase / March 2025	Year One April 2025-March 2026	Year Two April 2026-March 2027
Core programme agreements set up for continuity from April 2025
Programme staffing agreed and in place

Core programme commitments
Theory of Change and Context Analysis
New programming window
(rolling proposal considered by PSC)
First Phase Programme funded Advisers
STL support contracted (tbc)
July 25
Sept 25

Key Review Point
Key Decision Point

Implementation of the components and hence commercial strategy will be staggered, as set out in Box 4.
Phase one: March – June 2025: Given the pressure to maintain key ISF programmes, there will be an initial start-up phase, following Business Case approval, to ensure continuity from April 2025. Core programme team roles have been extended (see Management Case), given the need to maintain the core front line staff, as agreed by the IIOD Director. Final selection and approval of continuation programmes will be conducted by March 2025 and approved by the PSC to ensure that agreements can be signed in advance of April 2025. All priority programmes are under MoU or grants, which can be extended, and there is only one contract that would need to be confirmed for continuation (Tetratech Security and Justice Programme in Maldives). It is expected that the core programme will run through into year two of the programmes to enable closure activities, where appropriate.

Proposed extensions of formal agreements (to be confirmed)
Country	Project	Potential Partners and modalities
Sri Lanka	Defence of Civic Space / Land Conflict and Resolution / Parliamentary Support	UNOPS / MoU, UNDP / MoU, WFD / Grant Agreement
Philippines	Democratic Stability in Bangsamoro / Women Participation and Leadership / Bangsamoro Intergovernmental Relationships Body	WFD/Grant Agreement, The Asia Foundation/Grant Agreement, UNDP/MoU, UNDP/MoU
Myanmar	Human Rights Accountability / Women Peace and Security Combatting threats to UK and its interests	Grants and MoU
South-East Asia	Custodial Reform in Thailand / Justice Sector Reform in Malaysia	Partnerships with other government departments (Home Office, Ministry of Justice, Prison Services) / NGO Grants
Maldives	Security and Justice	TetraTech (Contract)

Phase two: Following the establishment of the ‘core programme’ the focus will shift to development of the revised Theory of Change that will inform the roll out of the new programming window from July 2025, though funding will be on a rolling basis. This will form a ‘key decision point’ for the programme, where the strategy for new funding will be reviews and agreed, including assessment of delivery options, through the PSC. The PSC will also approve the plan to mobilise programme-funded technical positions will commence with the aim of deployment from September 2025. Similarly, the design of the SLT component will be agreed by July 2025, with scope to procure services following approval. A second ‘key review point’ is anticipated at the end of the first year of ‘core programme’ where the future phases of the programme will be proposed for agreement.
## Targets, results and reporting
1. Given the nature of the IPRGP as a transition from the ISF legacy to a newly designed regional approach, the results framework will evolve throughout the course of the programme – with a view to bringing a close alignment between programmatic and project result monitoring. Projects under the core phase will draw upon existing result frameworks that will be adapted and agreed for the new phase – with programme level results oriented toward capturing the progress in term of project progress. As part of the Theory of Change process, the IPRGP results approach will be developed with the aim of capturing progress towards programme goals that draw from the project level as well as the value-added inputs in terms of analysis and direct delivery (linked to diplomatic engagement and UK priorities).
2. Partnerships between IPRD and posts will be based on a dual key approach (see Management Case) to ensure that projects supported under the IPRGP are reflected in country strategies and reporting, as well as the regional programme structure. This includes defining the accountability for results reporting.
3. The initial IPRGP results framework will reflect the three areas of impact set out in the Appraisal Case, namely: a) contribution to significant changes in progressive governance capacity; b) enhanced strategic engagement and partnerships; and c) deeper understanding of the context that informs approach. Indicative results set out in Box 5.
Box 5: Indicative IPRGP results framework

Change area	Interim Objectives	Example indicators
Progressive Governance	Shifting political and social norms in favour of more open, rule based and democratic forms of government	# actor/organisation engaged in UK supported coalitions supporting democracy/rights / Evidence of changed positions of key counterparts based on policy announcement/speeches etc
	Contributing to significant positive changes in the constraints to open and effective governance and peaceful resolution of political contests.	# UK supported engagement around ‘progressive governance reforms established / Improvement in political dialogue and participation as result of UK support / Increased awareness and constructive debate on governance constraints
Strategic engagement	Contributing to the UK objectives in the IP, namely enabling growth, response to climate change and improved stability and security	At least 50% of IPRGP support linked to unlocking core UK priorities (growth, climate, security) / IPRGP makes significant contribution to UK/host dialogues on governance contributes to mutual interests.
	Enabling political access and influence through ‘modern partnerships’ that support UK development and diplomatic objectives in the region	Increase engagement with key stakeholders as a result of IPRGP supported activities / # issues/countries where partnerships have improved with IPRGP support
Understanding of context	Demonstrating lessons that are applicable across countries in the region and therefore locally led leadership towards progressive governance.	At least 60% of IPRGP programmes activity present lessons applicable across two or more IP countries / Number of IP actors activity supporting progressive governance objectives as result of IPRGP support.
	Deepening the understanding of the drivers, incentives and cognitions that shape political governance processes in the region, and hence opportunities and challenges.	Analysis of country and regional trends informs greater strategic prioritisation in the IP / Development of active ‘problem solving coalitions of IP actors around core challenges and opportunities.

Value for Money
1. The IPRGP will seek to operate at a high level of ambition, with emphasis on learning, ‘freedom to fail’, but also utilise programme resources to catalyse high level impacts with strategic use of resources. As set out in the Appraisal Case, the addition of technical resources (direct delivery), investments in strategy testing and learning, and the pivot towards more coherent programming with a regional perspective will be the key drivers of this higher ambition. The VFM case will be developed as part of the ToC and design process and will include a detailed VFM strategy, encompassing economy and efficiency across the intended outcomes areas i.e. contribution to improved governance, analysis to shape policy choices and enhanced strategic engagement.
2. Key aspects of the VFM case will include:
Economy: To procure the partnerships, we will either run tenders including for grants (explored further in the Commercial Case) and in the case of MoU we will apply a review of comparator rates (cost drivers). In either case, we will assess bids based on their costs, including how streamlined their proposed management team is, administrative charges for travel, overheads and training. We will also assess how suppliers would manage economy throughout the programme, such as their procurement strategies for inputs.
Efficiency: Efficiency for IPRGP means having a strong, streamlined management team, having the processes and capacity to manage a diverse portfolio of work, being able to pivot, scale and close work quickly and economically, ensure that delivery partners efficiently convert inputs into outputs, and using the STL function to guide investments. Suppliers’ bids will be assessed for all these areas.

Equity: Given the level of inequality across the region, ensuring the programme (particularly civic engagement) reaches marginalised groups will be key to its success. We will expect partners to consider options to reach more remote locations, encourage and facilitate the participation of women and people with disabilities and measure success based on inclusivity. Likewise, we will expect partners working with the centre of government to use evidence and data to drive inclusive policies.

Effectiveness: The critical for effectiveness will be defined in the IPRGP outcomes, initially intended to include governance impacts, learning and engagement. Strategy testing will emphasis scalability and sustainability (leveraging government and other domestic funds) to ensure that FCDO’s funding therefore has the potential to have much larger impacts than the proposed investments. We will also be actively testing comparative impacts of approaches, including partnerships versus direct delivery.

# Financial Case

1. This Business Case seeks approval to spend up to £15 million during FY25/26 and FY26/27. In the FCDO ODA internal ODA Resource Allocation Round for FY25/26, we are seeking £15m for the Indo-Pacific Regional Department to enable the baselining of mission critical projects currently funded by the ISF and piloting new activities in preparation for the multi-year regional governance programme. The programme is design to be flexible to the final decisions on ODA allocations, including flexibility between components and across financial years.
2. The budget includes programme-funded staff costs involved with the delivery of the programme. In order not to lose CBS staff members from the ISF-funded programmes, who have the requisite clearances, access, training and knowledge, we have made a commitment to renewing their contracts from 1 April 2025. We recruit a UKB G7 Programme Lead (acting as PRO) to be posted in London. This post is designed, in line with PRoF guidance to be focused on direct delivery of the programme, including leading relationship with post and partners and ensuring strategic coherence through projects. The programme design also included scope to deploy two G7 Governance Advisers in the region, subject to the decision of the PSC.
3. A detailed case for in-sourcing is set out in Annex 2 along with an initial value for money justification (not for public disclosure).
4. Decisions over project spending will be made by the Programme Steering Committee, which will comprise representatives from across IIOD, SEAPD and NEACD. this Board will make allocation decisions based on the criteria set out in the Appraisal Case, the advice of the SRO, the relevant Heads of Mission and Development Directors and the advice of the Advisory Team in IPRD.
5. It is expected that the majority of funding allocation for the first-year decisions will be made at the outset of the programme by the Programme Steering Committee, as set out in the Management Case. Depending on the funding allocation for the programme as a whole, there will be unallocated funding that can be allocated during implementation.
6. The development of the Theory of Change and implementation plan will commence following programme inception, which will define the strategy for implementation beyond the core programme. Allocation of funds will be contingent on the overall budget allocation, and therefore financial plans will be adjusted through the programme cycle. The two-year financial plan set out below is based on a proposed multi-year allocation of £7.85million (FY25/26) and 7.15 million (FY 26/27) to enable startup of new activities (including SLT and programme funded advisers) with a view to initiating long term programming allocations from FY27/8.
7. The multi-year breakdown of costs is estimated as follows, to ‘up to’ limits dependent on final allocations and subject to reallocations between components as per direction of the Programme Steering Committee:
	25/26	26/27	Total
Core Programme (projects)	£5 million	£2 million	£7m
Programme Delivery (core project team)	£0.25 million	£0.25 million	£0.5m
Programme Delivery (technical)	£0.2 million	£0.3 million	£0.5m
Strategy Testing and Learning	£0.15 million	£0.15 million	£0.3m
Flexible Fund	£2.2 million	£4.5 million	£6.7m
Total Annual	£7.8million	£7.2million	£15m

Programme administration costs will be monitored and kept within 10% of total programme budget (up to £1.5 million) including administration or overhead costs charged by contracted partners.
# Management Case
1. As an adaptive programme, the IPRGP will ensure a robust mechanism to make strategic and transparent decisions within the programme cycle, through a Programme Steering Committee. The Senior Governance Adviser in the Indo-Pacific Regional Department will be the Senior Responsible Owner (SRO). The IPRGP will establish a Programme Steering Committee that will be chaired by the Head of IPRD and will comprise the Head of Indo-Pacific Strategy Team, Heads of Mission (DD) from all participating countries (initial from the core programme) and will also include at least three representatives from non-core countries in the IP. Participation from other regional programmes (i.e. IP Strategy and Geographic Departments) will be invited to ensure coherence. The PSC will meet at least every three months but also on a needs basis (or with virtual ‘write arounds) and will review/approve all spending decisions and progress reports. The SRO and PRO will form the secretariat to the PSC and minutes will be submitted to the Indo-Pacific Portfolio Board.
2. The role of the Programme Steering Committee will include (and not be limited to):
  1. Approval all project funding decisions, including allocation of resources to technical or programme delivery resources
  2. Review and approval of strategic direction, in line with FCDO priorities, including theory of change and geographic priorities
  3. Allocation of funds between components of the programmes (i.e. core and flexible funds) within overall budget allocation
  4. Review of programme management and performance, including risk registers, communications strategy, value for money and financial forecasting.
3. The SRO will chair a Programme Working Group, which will be open to participation from across IP countries and will serve as the main forum for presenting proposals, sharing lessons and learning, etc. The Working Group will meet at least every three months, in advance of the PSG. This working groups will be aligned with existing regional governance and rights working groups, under the leadership of the regional Champion (currently DHM Thailand). We will also be ensuring close coherence with central governance programmes, including the new civil society funding and the Centres for Expertise.
4. Programmes funded under the IPRGP will coordinate with post on the basis of a ‘dual lock mechanism’ that will ensure strong ownership from post, alignment with country strategies and processes (i.e risk assessments, OSJA and results reporting). This dual key approach will be developed and agreed in the PSC but is likely to include the development of a formal agreement between posts and IPRD setting out jointly agreed expectations of how IPRGP will work in country, including:
- Post involvement in key decisions, reviews etc.
- Resources the Post will make available to support the programme.
- Governance arrangements.
- How delivery partners will be managed.
## Programme Team
The Programme Team will be based on a combination of administrative and programme funded staff in order to bridge the gap between ISF and FCDO baseline programming. The core programme will be delivered by CBS in Jakarta, Colombo, Male and Manila (detail in financial case), who will be programme-funded, according to PRoF rules.
The SRO will be supported by a PRO (G7 Programme funded) and HEO (Admin funded). The programme team will be supported by specialist resources from IPRD, with the following tentative allocations set out in the table below. These allocations will be reviews during the first year of the project as part of the testing and development of the longer-term approach.

Roles	Allocation
SRO: Senior Governance Adviser UKB (IPRD)	40% FTE
PRO: G7 Programme Funded (UKB)	90% FTE
HEO Programme Manager (UKB) admin funded	15% FTE
In-Country Programme Delivery (CBS) / EO * 4 / HEO * 3	90% each
Technical Support Roles (IPRD) / Senior Social Development Adviser / Programme Finance / Communications / Monitoring and Evaluation / Economist/VFM	Each approx. 5% FTE

## Risk
1. The overall programme risk is considered to be major. The risk matrix below shows the most significant risks to the programme identified at this stage. A detailed risk register will be prepared following programme approval.
2. Conflict insensitivity: this programme would avoid removing programming abruptly in fragile environments where ISF work has made the UK an actor, particularly where there are ongoing peace processes (Philippines) or fragile political settlements (Sri Lanka, Maldives).

Description	Risk Category	Gross Risk	Mitigation Strategy	Residual Risk
Inadequate staffing to deliver the programme activities, given our inability to commit to a long-term employment to the current staff members and the need to recruit (internally) a UKB programme coordinator.	Operational	Severe	Commitment to continued employment for CBS before resource allocation round has been completed. Use of DFR for UKB staff within UK along with an agreed to use programme resources to support delivery.	Major
Contextual political risks in policy positions of governments in countries in which the programme working makes delivery more difficult, or impossible.	Political	Major	Use the criteria in the Appraisal Case for project selection. Conduct Political Economy Analysis before commencing project and during implementation. Embed flexible and adaptive principles so it is possible to change or close down projects and activities if not making expected progress.	Moderate
In the absence of any programme after the ISF programmes conclude, the UK would lose much of our positive reputation, access and influence in the governance sector in affected countries.	Reputational	Major	One of the major drivers for this programme is to mitigate the reputational damage to the UK. We will be continuing a reduced level of project activity in partner countries but with the expectation of a longer and larger governance programme to follow.	Moderate
An unforeseen negative outcome directly linked to FCDO funded activities occurs and is made public.	Reputational	Major	Conduct Political Economy Analysis before commencing project and during implementation. Embed flexible and adaptive principles so it is possible to change or close down projects and activities if risks of unforeseen negative outcomes is unacceptably high.	Moderate
Funds are not used as intended - Aid Diversion and/or safeguarding risks.	Fiduciary	Major	Use only established partners with current DDAs for core programme. Ensure similar process for new partners and adequate staffing for monitoring from post or regional levels.	Moderate
Risks of lack of continuity or achievement of impact should the progress not be extended towards a longer term approach, resulting in lower value for money	Delivery	Major	Ensure that forward thinking is hardwired into the programme design from the start, ensuring that funded activities are scalable or exitable if needed. Prepare case for extension by mid-term to ensure decisions and preparations can be made in time.	Moderate
Withdrawal of other donor funding in democratic governance space results in critical gaps and reduced partnership and delivery partner options.	Delivery	Major	We are closely tracking the impacts of USAID changes at the political level and delivery level. We will seek to identify areas where IPRGP can respond and work with other partners to explore new delivery options.	Moderate

1. Risks will be continually assessed and measured as part of the regular programme management cycle, and through robust due diligence processes. Partners funded through this programme will be contacted at least quarterly to provide FCDO with updates on key programme risks. Checking on this will also form part of monitoring of the response by post and Advisers.
2. FCDO has zero tolerance to sexual exploitation, abuse and harassment (SEAH). We will only enter into formal agreements with partners with which we have a current Due Diligence Assessment. As the programme will be taking over existing relationships with implementing partners, beneficiaries and other stakeholders, many of the risks associated with a new programme are reduced.
## Monitoring and Evaluation
1. Each project funded through this programme will be subject to monitoring and evaluation by IPRD MEL team and the STL provider(s).
2. Where feasible and appropriate, posts and governance advisers will undertake monitoring/field visits to assess that funds are being used for the intended purposes and assess the impact on affected communities. There will also be close monitoring of lessons learned from other internal and external reviews both in the Indo-Pacific and elsewhere.
3. A detailed logframe will be finalised following programme approval and will be submitted to the PSC for review and approval. All projects (and activities) will be required to develop detailed strategy testing documents that clearly set out the expected results, assumptions and contributions to the programme level result framework. Responsibility for result reporting will be set out as part of the ‘dual lock’ agreement with post, where relevant, with monitoring and reporting plans being assesses for each project/activity.